## Slide 1: Rel-19 SA5 work planning SA5#153, 29 Jan – 2 Feb, 2024
Zou Lan, 3GPP SA5 Chair, HUAWEI
Thomas Tovinger, 3GPP SA5 Vice-Chair, ERICSSON
Anatoly Andrianov, 3GPP SA5 Vice-Chair, NOKIA

## Slide 2: Content
Release 19 timeline– figure with SA5
Relevant of other 3GPP groups WI/SI potentially related to SA5
Expectation of SA5 rapporteur role
SA5 TU planning & statistics

## Slide 3
Release 19 timeline– figure with SA5 (Not yet integrated to SA timeline)
Release 19 timeline
#101
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA including SA5)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop
Management requirements (SA5)
Stage 2 (SA5) Normative supporting SA&RAN
OAM:
Sep 2024: finalize Rel-19 studies which plan to have corresponding normative work in Rel-19
Sep 2025: finalize all Rel-19 work items, majority work items are preferable to be finalized in Jun 2025.
CH:
Dec 2024: finalize Rel-19 studies which plan to have corresponding normative work in Rel-19
Sep 2025: finalize all Rel-19 work items
Group members are welcome to contact SA5 Chair offline for any opinions on the time plan

## Slide 4: Content
Release 19 timeline– figure with SA5
Relevant of other 3GPP groups WI/SI potentially related to SA5
Expectation of SA5 rapporteur role
SA5 TU planning & statistics

## Slide 5
Rel-19 OAM Study / Work Items
 |  | Tdoc | Type | Acronym | UID | Release | Title
Intelligence and Automation | 1 | SP-231780 | SID new | FS_AIML_MGT_Ph2 | 1020007 | Rel-19 | New SID: Study on AI and ML management phase 2
 | 2 | SP-231726 | SID new | FS_eMDAS_Ph3 | 1020019 | Rel-19 | New SID: Study on Management Data Analytics (MDA) – Phase 3
 | 3 | SP-231737 | SID new | FS_IDMS_MN_Ph3 | 1020008 | Rel-19 | New SID: Study on intent driven management services for mobile networks phase 3
 | 4 | SP-231735 | SID new | FS_CCLM | 1020009 | Rel-19 | New SID: Study on Closed Control loop management
 | 5 | SP-231727 | SID new | FS_NDT | 1020018 | Rel-19 | New SID: Study on Management aspect of Network Digital Twin
Management Architecture and Mechanisms | 6 | SP-231781 | SID new | FS_Cloud_OAM | 1020010 | Rel-19 | New SID: Study on cloud aspects of management and orchestration
 | 7 | SP-231736 | SID new | FS_SECM | 1020016 | Rel-19 | New SID: Study on Enablers for Security Monitoring
 | 8 | SP-231725 | SID new | FS_SBMA_Ph3 | 1020011 | Rel-19 | New SID: Study on SBMA enhancement phase 3
 | 9 | SP-231721 | SID new | FS_PlanM | 1020033 | Rel-19 | New SID: Study on Plan management
 | 10 | SP-231746 | WID new | MADCOL_Ph2 | 1020025 | Rel-19 | New WID on Data Management phase 2
 | 11 | SP-231732 | SID new | FS_Data_SREP | 1020012 | Rel-19 | New SID: Study on data management, regarding subscriptions and reporting
 | 12 | SP-231747 | WID new | PM_KPI_5G_Ph4 | 1020026 | Rel-19 | New WID on 5G performance measurements and KPIs phase 4
 | 13 | SP-231745 | WID new | AdNRM_Ph3 | 1020027 | Rel-19 | New WID on 5G Advanced NRM features phase 3
 | 14 | SP-231748 | WID new | TraceQoE_OAM | 1020028 | Rel-19 | New WID on Subscriber and Equipment Trace and QoE collection management
 | 15 | SP-231733 | SID new | FS_ NTN_OAM_Ph2 | 1020013 | Rel-19 | New SID: Study on Management Aspects of NTN Phase 2
 | 16 | SP-231729 | SID new | FS_NR_mobile_IAB_OAM | 1020014 | Rel-19 | New SID: Study on Management of IAB Nodes
 | 17 | SP-231734 | SID new | FS_NR_RedCap_OAM | 1020017 | Rel-19 | New SID: Study on management aspects of RedCap feature
 | 18 | SP-231724 | SID new | FS_NWDAF_OAM_Ph2 | 1020020 | Rel-19 | New SID: Study on Enhancement of Management Aspects related to NWDAF Phase 2
 | 19 | SP-231731 | SID new | FS_NetShare_OAM_Ph3 | 1020015 | Rel-19 | New SID: Study on Management of Network Sharing Phase 3
Support of New Services | 20 | SP-231723 | SID new | FS_Energy_OAM_Ph3 | 1020021 | Rel-19 | New SID: Study on energy efficiency and energy saving aspects of 5G networks and services
 | 21 | SP-231728 | SID new | FS_MExpo | 1020022 | Rel-19 | New SID: Study on Enhanced OAM for management exposure to external consumers
21 OAM topics for Rel-19 sent for SA approval including: 13 OAM prime features and 8 OAM support to network features.
TU will be used for Rel-19 work planning and statistics

## Slide 6: Rel-19 work progress in other SA groups
SA1 (37 topics with 8 topics potentially related to SA5)
960019 | Study on Energy Efficiency as service criteria | FS_EnergyServ | SP-230235 | Xiaonan Shi, CMCC
1000033 | Stage 1 of Energy Efficiency as Service Criteria | EnergyServ | SP-230520 | Xiaonan Shi, CMCC
950008 | Study on AI/ML Model Transfer Phase2 | FS_AIML_MT_Ph2 | SP-220439 | Yang Xu, OPPO
1000030 | AI/ML Model Transfer Phase 2 | AIML_MT_Ph2 | SP-230514 | Yang Xu, OPPO
950004 | Study on Ambient power-enabled Internet of Things | FS_AmbientIoT | SP-220085 | Rapporteur:Xu, weijie, OPPO
1020030 | Stage 1 of Ambient power-enabled Internet of Things | AmbientIoT | SP-231403 | Xu, Weijie, OPPO
960016 | Study on satellite access - Phase 3 | FS_5GSAT_Ph3 | SP-220679 | Rapporteur: Thierry Bérisot, Novamint
1000024 | Stage 1 of Satellite access Phase 3 | 5GSAT_Ph3 | SP-230516 | Rapporteur: Thierry Bérisot, Novamint
950005 | Study on Localized Mobile Metaverse Services | FS_Metaverse | SP-220353 | Guttman, Erik, Samsung
1000028 | Stage 1 of Localized Mobile Metaverse Services | Metaverse | SP-230509 | Guttman, Erik, Samsung
990052 | Supporting UE Mobility for XR Services | XRMobility | SP-230233 | Xiaonan Shi, ChinaMobile
950003 | Study on Integrated Sensing and Communication | FS_Sensing | SP-220717 | Aleksiev, Vasil, Deutsche Telekom
1000026 | Stage 1 of Integrated Sensing and Communication | Sensing | SP-230750 | Aleksiev, Vasil, Deutsche Telekom AG
960017 | Study on (Stage 1 of) UAV Phase 3 | FS_UAV_Ph3 | SP-220954 | Pengtai Qin , China Mobile
1000032 | Stage 1 of Uncrewed Aerial System Phase 3 | UAS_Ph3 | SP-230518 | Pengtai Qin , China Mobile
950006 | Study on Network Sharing Aspects | FS_NetShare | SP-220087 | Wei, Qun, China Unicom
1000029 | Indirect Network Sharing | NetShare | SP-230511 | Wei, Qun, China Unicom
960018 | Study on Upper layer traffic steering, switching and split over dual 3GPP access | FS_DualSteer | SP-220445 | Francesco Pica; Qualcomm
1020031 | Upper layer traffic steering and switching over dual 3GPP access | DualSteer | SP-231412 | Pica Francesco, Qualcomm
1010022 | Edge Computing Considering the Operational Needs of Service Hosting Environment | EdgeOpNeeds | SP-231037 | Yuying Zhang, China Telecom
950007 | Study on FRMCS Phase 5 | FS_FRMCS_Ph5 | SP-220437 | Patrick WIMART, UIC
1000031 | FRMCS Phase 5 | FRMCS_Ph5 | SP-230512 | Nikolopoulou, Vassiliki, UIC
850044 | Study on Supporting of Railway Smart Station Services | FS_RAILSS | SP-190838 | Han, Andrew Min-gyu, Hansung University
960020 | Study on Network of Service Robots with Ambient Intelligence | FS_SOBOT | SP-220447 | LEE, Ki-Dong, LG Electronics
960015 | Study on roaming value added services | FS_RVAS | SP-220442 | Peter Bleckert, Ericsson
990051 | Roaming Value-Added Services | RVAS | SP-230231 | Peter Bleckert, Ericsson
990053 | Study on Interconnect of SNPN | FS_ISN | SP-230236 | Thierry Bérisot, Novamint
990050 | Edge Computing for Industrial Scenarios | EDGINDUS | SP-230229 | Bruno Tossou, Orange
990049 | PS Data Off for IMS Data Channel Service | IMSDCDataOff | SP-230227 | Yue Hu, China Mobile
970044 | Multi-path relay | MultiRelay | SP-220943 | Yuying Zhang, China Telecom
1000025 | UE-to-UE multi-hop relay | UEMHopRelay | SP-230521 | Lipford, Mark, FirstNet Authority,
970043 | Interworking of Non-3GPP Digital Terrestrial Broadcast Networks with 5GS Multicast Broadcast Services | DTT4MBS | SP-220941 | Saha, Anindya, Saankhya Labs
970042 | MPS for Messaging services | MPS4msg | SP-220939 | Singh, Ray, Peraton Labs
970041 | Minimization of Service Interruption During Core Network Failure Phase 2 | MINT_Ph2 | SP-220992 | Yinglin Chen, China Telecom
980108 | Measurement Data Collection | MeasureData | SP-221263 | Yingjun Zhou, ZTE Corporation
1010025 | Local traffic routing for multi-access UE | LTR_MA | SP-231035 | Yinglin Chen, China Telecom
1000027 | Non-Public Network (NPN) security considerations | SecNPN | SP-230523 | Yinglin Chen, China Telecom
Ref: List of Approved Rel-19 topics （https://www.3gpp.org/ftp/Information/WORK_PLAN）
Rapporteurs are requested to identify concrete related aspects in corresponding SA5 topics
Color code: Blue (OAM related)/ Yellow(CH related)/Green( OAM&CH)

## Slide 7: Rel-19 work progress in other SA groups
Ref: List of Approved Rel-19 topics （https://www.3gpp.org/ftp/Information/WORK_PLAN）
SA2 (15 topics with 7 topics potentially related to SA5 OAM and CH, and 4 topics related to CH )
SA3 (14 topics with 1 topics potentially related to SA5 OAM)
1020044 | Study on Security Aspects of 5G Satellite Access Phase 3 | FS_5GSAT_Ph3_SEC | SP-231790 | Zhou Wei
1010010 | 5G Security Assurance Specification (SCAS) for the Unified Data Repository (UDR) | SCAS_5G_UDR | SP-230864 | Andreas, Joerg, BSI Germany
1010011 | 5G Security Assurance Specification (SCAS) for the Short Message Service Function (SMSF) | SCAS_5G_SMSF | SP-231158 | Manjesh K. Hanawal, IIT Bombay
1010012 | Addition of 256-bit security Algorithms | 256_Algo | SP-231159 | Orkopoulos, Stawros
1020036 | Addition of Milenage-256 algorithm | Milenage_256 | SP-231792 | Mireille Pauliac
1020041 | Study on enabling a cryptographic algorithm transition to 256-bits | FS_CAT256 | SP-231788 | Yuto Nakano
1020034 | Study on enablers for Zero Trust Security | FS_eZTS | SP-231784 | Sheeba Backia Mary Baskaran
1020035 | Mission critical security enhancements for release 19 | MCXSec4 | SP-231783 | Woodward, Tim, Motorola Solutions, Inc.
1020038 | Study on the security support for the Next Generation Real Time Communication services phase 2 | FS_NG_RTC_SEC_Ph2 | SP-231785 | Vlasios Tsiatsis
1020039 | Study on security for PLMN hosting a NPN | PLMNNPN_SEC | SP-231786 | Jun Shen
1020040 | Study of ACME for Automated Certificate Management in SBA | FS_ACME_SBA | SP-231787 | Charles Eckel
1020042 | 3GPP profiles for cryptographic algorithms and security protocols | CryptoSP | SP-231793 | Mohsin Khan A
1020043 | Study on mitigations against bidding down attacks | FS_MiBiDA | SP-231789 | Noamen Ben Henda
1020045 | Security for mobility over non-3GPP access to avoid full primary authentication | FS_Non3GPPMob_Sec | SP-231791 | Saurabh Khare, Nokia
Rapporteurs are requested to identify concrete related aspects in corresponding SA5 topics
1010029 | Study on Energy Efficiency and Energy Saving | FS_EnergySys | SP-231391 | Jungshin Park (Samsung)
1020068 | Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) | FS_AIML_CN | SP-231800 | Xiaobo Wu, vivo
1020071 | Study on Architecture support of Ambient power-enabled Internet of Things | FS_AmbientIoT | SP-231803 | Runze Zhou (Huawei)
1010033 | Study on Integration of satellite components in the 5G architecture Phase 3 | FS_5GSAT_Ph3_ARCH | SP-231199 | Jean-Yves Fine (Thales)
1010032 | Study on Extended Reality and Media service (XRM) Phase 2 | FS_XRM_Ph2 | SP-231671 | Primary Rapporteur: Devaki Chandramouli (Nokia)
1020069 | Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM | FS_UAS_Ph3 | SP-231801 | LaeYoung Kim (LG Electronics)
1020070 | Study on Multi-Access (DualSteer and ATSSS_Ph4) | FS_MASSS | SP-231802 | Krisztian Kiss (Apple)
1020004 | Study on Enhancement of support for Edge Computing in 5G Core network - Phase 3 | FS_eEDGE_5GC_Ph3 | SP-231796 | Changhong Shan (Intel)
1020002 | Study on System aspects of 5G NR Femto | FS_5G_Femto | SP-231797 | Malla Reddy Sama (NTT DOCOMO)
1020066 | Study on Proximity-based Services in 5GS Phase 3 | FS_5G_ProSe_Ph3 | SP-231798 | Hugh Shieh (AT&T)
1020067 | Study on Vehicle Mounted Relays Phase 2 | FS_VMR_Ph2 | SP-231799 | Primary Rapporteur: Hong Cheng (Qualcomm)
1020063 | Study on User Identities and Authentication Architecture | FS_UIA_ARC | SP-231804 | Michael Starsinic, Interdigital
1020003 | Study on UPF enhancement for Exposure And SBA Phase 2 | FS_UPEAS_Ph2 | SP-231795 | Zhu Jinguo, ZTE
1010030 | Study on system architecture for next generation real time communication services phase 2 | FS_NG_RTC_Ph2 | SP-231196 | Yi Jiang (China Mobile)
1010031 | Study on MPS for IMS Messaging and SMS services | FS_MPS4msg | SP-231197 | Robert Streijl (Peraton Labs)
Color code: Blue (OAM related)/ Yellow(CH related)/Green( OAM&CH)

## Slide 8: Rel-19 work progress in other SA groups
SA4 (1 topic)
SA6 (16 topics with 9 topics potentially related to SA5 OAM)
1010005 | Study on application layer support for AI/ML services | FS_AIMLAPP | SP-231182 | Pateromichelakis, Emmanouil (Manos)
1020053 | Study on application enablement for Satellite access enabled 5G Services | FS_5GSAT_Ph3_App | SP-231738 | Basavaraj (Basu) Pattan, Samsung
1020052 | Study on application enablement for Localized Mobile Metaverse Services | FS_Metaverse_App | SP-231806 | Shah, Sapan, Samsung
1020051 | Study on Application enabler for XR Services | FS_XRApp | SP-2315739 | Zheng, Shaowen, CMCC
1020054 | Study on Sensing application enabler for vertical applications | FS_SensingAPP | SP-231579 | Yanmei Yang, Huawei
1010008 | Application Architecture for UAS applications Phase 3 | UASAPP_Ph3 | SP-230991 | Monrad, Atle, InterDigital
1000034 | Study on Service aspects for supporting the eMMTel service | FS_eMMTelAPP | SP-230779 | Liu, Yue, China Mobile
1000035 | Study on enhanced application layer support for location services | FS_eLSAPP | SP-230778 | Liping Wu, CATT
1000036 | Sharing of administrative configuration between interconnected MC service systems | MCShAC | SP-230692 | andreas.flander@bdbos.bund.de
1000037 | 5GMSG Service phase 3 | 5GMARCH_Ph3 | SP-230781 | Liu, Yue, China Mobile,
1000038 | Railways specific Enhancements to Mission Critical Services | enh4FRMCS | SP-230780 | Oettl, Martin, Nokia,
1000039 | Enhanced Mission Critical Architecture | enhMC | SP-230988 | Negalaguli, Harish, Motorola Solutions,
1010006 | SEAL DD (Data Delivery) Phase 2 | SEALDD_Ph2 | SP-230989 | Cuili Ge, Huawei
1010007 | Architecture for enabling Edge Applications Phase 3 | EDGEAPP_Ph3 | SP-231160 | Hyesung Kim, Samsung
1010009 | Guidelines for CAPIF Usage | CAPIF_EXT | SP-231161 | Junpei Uoshima, NTT DOCOMO
1020062 | Study on CAPIF Phase 3 | FS_CAPIF_Ph3 | SP-231741 | Preciado Rojas, Diego, Nokia
980008 | Study on Diverse audio Capturing system for End-user Devices | FS_DaCED | SP-221330 | Wang Bin, Xiaomi
Rapporteurs are requested to identify concrete related aspects in corresponding SA5 topics
Ref: List of Approved Rel-19 topics （https://www.3gpp.org/ftp/Information/WORK_PLAN）
Color code: Blue (OAM related)/ Yellow(CH related)/Green( OAM&CH)

## Slide 9: Rel-19 work progress in RAN1/2/3 groups
1021095 | Core part: Enhancements of Network energy savings for NR | Netw_Energy_NR_enh-Core | RP-234065 | Ericsson
1021094 | Core part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) | NR_LPWUS-Core | RP-234056 | vivo
1021093 | Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface | NR_AIML_air-Core | RP-234039 | Qualcomm
1020085 | Study on solutions for Ambient IoT (Internet of Things) in NR | FS_Ambient_IoT_solutions | RP-234058 | CMCC
1020086 | Study on channel modelling for Integrated Sensing And Communication (ISAC) for NR | FS_Sensing_NR | RP-234069 | Xiaomi
1020081 | Study on channel modelling enhancements for 7-24GHz for NR | FS_NR_7_24GHz_CHmod | RP-234018 | Intel
1020089 | NR MIMO Phase 5 | NR_MIMO_Ph5 | RP-234007 | Samsung
1021089 | Core part: NR MIMO Phase 5 | NR_MIMO_Ph5-Core | RP-234007 | Samsung
1020090 | Evolution of NR duplex operation: Sub-band full duplex (SBFD) | NR_duplex_evo | RP-234035 | Huawei
1021090 | Core part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) | NR_duplex_evo-Core | RP-234035 | Huawei
RAN1 (8 topics with 1 topic potentially related to SA5 OAM)
1020084 | Study on Artificial Intelligence (AI)/Machine Learning (ML) for mobility in NR | FS_NR_AIML_Mob | RP-234055 | Oppo
1021097 | Core part: Non-Terrestrial Networks (NTN) for NR Phase 3 | NR_NTN_Ph3-Core | RP-234078 | Thales
1021096 | Core part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 | IoT_NTN_Ph3-Core | RP-234077 | Mediatek
1021098 | Core part: XR (eXtended Reality) for NR Phase 3 | NR_XR_Ph3-Core | RP-234080 | Nokia
1020091 | NR mobility enhancements Phase 4 | NR_Mob_Ph4 | RP-234036 | Apple
1021091 | Core part: NR mobility enhancements Phase 4 | NR_Mob_Ph4-Core | RP-234036 | Apple
1020083 | Study on enhancements for Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN | FS_NR_AIML_NGRAN_enh | RP-234054 | ZTE
1020082 | Study on additional topological enhancements for NR | FS_NR_WAB_5GFemto | RP-234041 | NTT DOCOMO
1020092 | Data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) Phase 4 | NR_ENDC_SON_MDT_Ph4 | RP-234038 | China Unicom
1021092 | Core part: Data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) Phase 4 | NR_ENDC_SON_MDT_Ph4-Core | RP-234038 | China Unicom
RAN2 (5 topics with 1 topic potentially related to SA5 OAM)
RAN3 (3 topics with 2 topic potentially related to SA5 OAM)
Rapporteurs are requested to identify concrete related aspects in corresponding SA5 topics
Ref: List of Approved Rel-19 topics （https://www.3gpp.org/ftp/Information/WORK_PLAN）
Color code: Blue (OAM related)/ Yellow(CH related)/Green( OAM&CH)

## Slide 10: Content
Release 19 timeline– figure with SA5
Relevant of other 3GPP groups WI/SI potentially related to SA5
Expectation of SA5 rapporteur role
SA5 TU planning & statistics

## Slide 11: Expectation of SA5 rapporteur role
Expectation of SA5 rapporteur role:
  Actively contribute and facilitate the progress of the WI/SI, coordinate the discussion within SA5 and with external groups if necessary
  Prepare tdoc sequence list and tdoc grouping suggestion before the meeting
  Provide inputs to Rel-19 TU planning/TU consumption for each meeting.
  Provide timely progress report in NWM before closing plenary with clear highlights for external readers with references to the WID/SID objectives.
  Implement any necessary draftCR/draft TR/draft TS and facilitate the email approval of draftCR/draft TR/draft TS
  Moderate the breakout sessions/offline calls and provide summary report
  Refer to TR 21.900 clause 6.3.2 for Role of the work item rapporteur and 4.1.2 Role of the specification rapporteur
  Be familiar with 3GPP drafting rules as specified in TR 21.801.
If you agree with the expectation above, please provide the nomination (one company one reply email please):
  Please consider the guidance (bullet 2/3/4/5) provided in Rel-19 Rapporteurship document SP-230746 from SA.
  Indicate if the nomination is for the role of Primary Rapporteur.
  Indicate if the nomination is for the role of Secondary Rapporteur.
  The work responsibility of Primary/Secondary Rapporteurs shall be clearly described if there are proposals for co-rapporteurs.

## Slide 12
Reference: SP-230746

## Slide 13: Reference From TR 21.900
4.1.2 Role of the specification rapporteur
The role of the rapporteur is to:
- Serve as Editor (following the guidance of the WG) until the specification is placed under change control.
- Deliver a clean specification to the MCC for editorial clean-up before submission for TSG approval to come under change control.
and, in co-operation with MCC, to:
- Review all CRs to the specification prior to agreement in the Working Group. This includes identifying and resolving clashes.
- Oversee the technical quality of the specification.
- Explain the specification to any other group (WG, TSG, inside or outside 3GPP), where appropriate.
- Serve as focal point for technical questions.
6.3.2 Role of the work item rapporteur
Every Work Item shall have a rapporteur. The rapporteur should be selected from regular attendees of the primary responsible Group and shall be selected from supporting companies. The role of the rapporteur is to:
- Monitor the progress of the work in all WGs for the WI.
- Report to the responsible WG and produce a report to the WG plenary on progress.
- Provide feedback to allow the work plan to be updated.
- Keep the WI sheet up-to-date.
- Identify the completion of the WI.
NOTE: Updates of WI sheets require approval by the responsible WG/TSG.

## Slide 14: Content
Release 19 timeline– figure with SA5
Relevant of other 3GPP groups WI/SI potentially related to SA5
Expectation of SA5 rapporteur role
SA5 TU planning & statistics

## Slide 15: SA5 TU planning & statistics
OAM uses TU to facilitate the Rel-19 discussion.
Opinions are welcome as inputs for evaluation of using TU for CH in SA5#153

## Slide 16: SA5 calendar with OAM TU (one track)
Time | Monday | Tuesday | Wednesday | Thursday | Friday (Closing plenary)
Q0 (If needed) |  | Breakout (opt.) | Breakout (opt.) | Breakout (opt.) | Closing plenary Start at 8:30am (may change depends on the host restriction)
Q1 (9:00 - 10:30) | Plenary Session#1 (1TU) [Single Stream] | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
10:30 - 11:00 | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break | Morning Coffee Break
Q2 (11:00 - 12:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
12:30 - 14:00 | Lunch | Lunch | Lunch | Lunch | Lunch
Q3 (14:00 - 15:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Closing plenary
15:30 - 16:00 | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break | Afternoon Coffee Break
Q4 (16:00 - 17:30) | Stream#1 (1TU) | Stream#1 (1TU) | Stream#1 (1TU) | Revision session | Closing plenary
17:30 - 17:40 | Break | Break | Break | Break | Break
Q5 (17:40 – 19:10) | Stream#1 (1TU) | Stream#1 (0.5 TU) Stop around 18:45 Social evening | Stream#1 (1TU) | Revision session | 
Assumption: Every day = 5 sessions (TUs), total TU in 1 ordinary meeting = 18.5 TUs

## Slide 17: TU Budget for SA5 OAM
Assumptions for SA5 OAM :
  6 ordinary meeting per year.
  Rel-19 spans 21 months for SA5 (with early start of studies) = 10 meetings
  1 Session = 1.5 hour time window
  Max 5 sessions per meeting day
  1 Stream = 1 TU (Time Unit)
  1 TU is time (i.e., 1.5 hours) spent to discuss/handle technical contributions.
  Revisions/Drafting/offline conference call are not counted for the TU estimates.
  OAM revision sessions normally planned to be in Thursday Q4 and Q5 (initial assump.)
  1 parallel (OAM) stream per session => 18.5 TUs per meeting (incl. 2 TUs as buffer) = 185
  Assume Maintenance + Buffer = 33% as in SA2 => ~ 61 TU
  Resulting total TUs avail. f. SI/WI: 10 meetings x 18.5 sessions = 185 TU minus 61 => 124 TU
  With 20 SI/WI => Average 6 TU per SI/WI (0.6/meeting). Cf. SA2: Average 6.8 TU
  => Recommended MAX no. of SI/WI = 20
  => Proposed max number of TUs allocated to any SI/WI in 1 meeting = same as in SA2 = 2

## Slide 18: SA5 Rel-19 OAM TU planning (Jan.2024~Sep.2025)
 | Maintenance+R18 | R19 | R20 preparation | Buffer (revision session)
Jan.2024~Mar.2024 SA5#153 (1 meeting) (Last meeting for Rel-18) | 1.5 TU (CR)+13 TU (Rel-18)=14.5 TU | 2 TU | NA | 2 TU
Apr. 2024~Dec.2024: SA5#154~#158 (5 meetings) | 2.5 TU*5 meetings = 12.5 TU (CRs) | 14 TU*5 meetings= 70 TU | NA | 2 TU*5=10 TU
Jan.2025~Sep.2025: SA5#159~#162 (4 meetings) | 1.5 TU*4 meetings= 6 TU (CRs) | 13 TU*4 meetings= 52 TU | 2 TU*4 meetings = 8 TU | 2 TU*4=8 TU
Total=185 TU | 33 TU | 124 TU | 8 TU | 20 TU
Assumptions:
Every meeting day = 5 quarters (= 5 TUs)
Total TUs per meeting = 18.5 TUs
  Buffer = 2 TUs
  OAM = 16.5 TUs
    Maintenance CRs + remaining Rel-18 work (TU allocation will decrease over time )
    Rel-20 preparation work (TU allocation will be zero at the beginning and will increase over time )
    All remaining time is available for Rel-19 SIDs / WIDs
Total TUs allocated to Rel-19 SIDs / WIDs = 120 TUs, implying:
  12 TUs allocated to Rel-19 SIDs / WIDs per meeting (= 120 TUs / 10 meetings)
  6 TUs allocated to each Rel-19 SID / WID in average (= 120 TUs / 20 Rel-19 SIDs/WIDs)
  0.6 TU allocated per Rel-19 SID / WID per meeting in average (= 12 TUs / 20 Rel-19 SIDs/WIDs)

## Slide 19: Sample of OAM TU planning and statistics
This is an example to illustrate TU statistics
TU planning: to be proposed by rapporteurs and agreed by the group
TU statistics: to be filled by chair based on the time consumed after each meeting

## Slide 20: Thank you!