3GPP TSG-SA5 Meeting #162	S5-253637

Gothenburg, Sweden, 25 - 29 August 2025

# Source:	China Mobile, Verizon, SK Telecom, CATT, ZTE, Rakuten Mobile, NEC, Orange

# Title:	Suggestions for 6G OAM Study

# Document for:	Discussion/Endorsement

Agenda Item:	5.5

1	Decision/action requested

The group is asked to discuss & endorse the proposals.

2	References

None.

3	Rationale

This paper proposes suggestions for the 6G OAM Study Item.

1. Organization of 6G OAM SID discussion

(1) Timing and Work coordination with SA1 and SA2

Figure 1 Timeline of 6G OAM items in SA5

The 6G study item of SA1 reached 66% in June 2025. It is expected that the TR will be consolidated by the end of 2025 and conclude at the beginning of 2026. For SA2, the 6G Architecture SID was approved in June 2025 and might be finalized no later than March 2027. Therefore, SA5 6G OAM should maintain a 3-month delay with SA2/RAN architecture study from 2025.09 to 2027.06, with full consideration of management support for architecture and new features. The supporting features for SA2 architecture and RAN need to be carefully considered. Several checkpoints with SA2 and RAN2/RAN3 can be set to see whether SA5 6G OAM study satisfies their management requirements, which is suggested to be set for June/September 2026.

(2) There are some considerations on timeline for SA5 6G OAM SID:

- To ensure that 6G OAM Day one features have sufficient discussions on solutions and conclusions, it is necessary to set a finalized time for new use cases and requirements:

- Overview and use cases should be fully discussed before June 2026. New Reqs should be finalized in September 2026. New solutions finalize in March 2027. TR conclude in June 2027.

- Two checkpoints with SA1 and SA2 should be set: one aligned with SA1 for Requirements in December 2025, and the other aligned with SA2 for Architecture in June/September 2026.

- The 6G OAM shall start as a single SID within the unified study framework, the study time windows of the technical directions can allow for variability, with those that have clear solutions allowed to conclude first.

- The single SID can be developed into multiple WIDs based on the OAM study conclusions and the outcomes considered from other WGs (e.g., OAM requirements, foundational architecture and management services, AI topics). It is expected to be completed 80% or checked in December 2026 for WIDs scope discussion.

Proposal 1:

The 6G OAM study should maintain an approximate 3-month offset from SA2 architecture work, enabling SA5 to base potential OAM solutions on stable architectural decisions and avoid unnecessary rework, while considering management support for the agreed architecture and relevant features.

Proposal 2:

The following checkpoints should be used to align the 6G OAM study with other 3GPP groups:

- Alignment with SA1 for Requirements – December 2025.

- Alignment with SA2 for Architecture – June/September 2026.

- Alignment with RAN2/RAN3 for RAN management – June/September 2026.

- Scope discussion for separating WIDs based on the 6G SID study conclusions and requirements from other WGs – December 2026.
Note: The timing of checkpoints may be adjusted according to the 6G work progress.

2. The principles of 6G OAM Design

At the outset of the 6G Operations and Management (OAM) study, it is essential to thoroughly analyze the specific requirements and use cases that 6G aims to address, as well as the new services that OAM will need to provide or support. In order to ensure SA5 maintains its essential role in the 6G management and orchestration, the coordination with other SDOs needs to be considered if needed. This comprehensive analysis is crucial because it allows stakeholders to identify the unique challenges and opportunities that 6G presents compared to previous generations. The 6G OAM Architecture should be discussed from the use case perspective and also from a functional perspective. By systematically evaluating these needs and potential use cases, we can explore solutions by leveraging advanced technologies, ensuring that the OAM framework is robust enough to handle the complexities of 6G. Ultimately, this will facilitate the management and service provisioning of seamless, efficient, and reliable services in an increasingly interconnected world.

Proposal 3:

The 6G OAM study should begin by examining 5G capabilities to identify potential gaps, use cases, and management requirements that 6G is expected to address, guiding the subsequent development of potential solutions and ensuring the OAM framework supports new features and services.

3. The structure of 6G OAM Specification

Based on our experience with 5G OAM specification development, we have observed that the number of 3GPP specifications continues to increase, making it difficult to keep track of the growing list of standard numbers. While there may be various factors for this, it adds unnecessary complexity to the scalability, readability, and usability of the specifications.

Therefore, at the outset of developing the 6G OAM specifications, we propose to endorse an overall principle to create lean and streamlined standards for 6G OAM, reducing the number of specifications while enhancing the usability of core ones.

The experience learned from the 5G SA5 specifications is that the specifications are fragmented, with TS28.533 serving as the fundamental management architecture combined with 40+ concrete specifications. The current issue is that there are too many specifications, and the relationships among them lack a clear view and logic, resulting in low readability. Therefore, we propose developing a few foundational specifications within SA5 for 6G OAM: Use case and Requirements, Management Architecture and Functions, NRM, PM/KPI, etc, following the well-known TS 23.501/23.502 established in the SA2 5G specifications as an example. If there is a need to add some specific functional specifications later, these specific functions should be updated in the Management Architecture and Functions foundational document, clearly outlining their relationships with the management architecture and other functions. Detailed procedures, IOC, data types, etc., can be defined in separate specifications, but they should at least be indexed from the foundational Management Architecture and Functions specification. Similar approach to the requirement specification, a single requirement specification could be maintained, primarily sourced from SA1, SA5 itself, and other SDOs.

Proposal 4:

It is proposed to endorse an overall principle to create lean and streamlined standards for 6G OAM, reducing the number of specifications while enhancing the usability of core specifications.

4	Detailed proposals

(If asking for an endorsement, please provide the clear text to be endorsed.)

Proposal 1:

The 6G OAM study should maintain an approximate 3-month offset from SA2 architecture work, enabling SA5 to base potential OAM solutions on stable architectural decisions and avoid unnecessary rework, while considering management support for the agreed architecture and relevant features.

Proposal 2:

The following checkpoints should be used to align the 6G OAM study with other 3GPP groups:

- Alignment with SA1 for Requirements – December 2025.

- Alignment with SA2 for Architecture – June/September 2026.

- Alignment with RAN2/RAN3 for RAN management – June/September 2026.

- Scope discussion for separating WIDs based on the 6G SID study conclusions and requirements from other WGs – December 2026.
Note: The timing of checkpoints may be adjusted according to the 6G work progress.

Proposal 3:

The 6G OAM study should begin by examining 5G capabilities to identify potential gaps, use cases, and management requirements that 6G is expected to address, guiding the subsequent development of potential solutions and ensuring the OAM framework supports new features and services.

Proposal 4:

It is proposed to endorse an overall principle to create lean and streamlined standards for 6G OAM, reducing the number of specifications while enhancing the usability of core specifications.