## Slide 1: FS_eEDGEAPP - Status and Plan
Basavaraj (Basu) Pattan
eEdgeApp Rapporteur, SAMSUNG
Mar 21st , 2022

## Slide 2: FS_eEDGEAPP Timeline – Status and Plan
Study Item | WI Code | SID Approved | SA6#46-e | Target Completion | Remarks
Study on enhanced Application Architecture for enabling Edge Applications | FS_eEDGEAPP | SA#92 (06/2021) | 55% | SA#96 (06/2022) SA#97 (09/2022) | 4 meetings available until 09/2022 to complete remaining 45% study.
 | Nov 2021 | Feb 2022 | Apr 2022 | May 2022 | Jun 2022 | Aug 2022 | Oct 2022 | Nov 2022 | Jan 2023 | Feb 2023 | 
SID/WID | SA6#46-e TUs | SA6#47-e TUs | SA6#48 TUs | SA6#49 TUs | SA6#49-BIS TUs | SA6#50 TUs | SA6#51 TUs | SA6#52 TUs | SA6#52-BIS TUs | SA6#53 TUs | Total
FS_eEDGEAPP | 4 | 4 | 6 | 6 | 4? | 4? | 5 | 5 | 5 | 5 | 48
Study
Normative

## Slide 3: Work plan eEDGEAPP (SID + WID)-Updated
Meeting | 2021 |  | Proposed work plan for <WID/SID> | Estimated TUs
SA6#46-e | 15 – 23 November 2021 | Online | SID: Key issues + Solutions | 4
 | 2022 |  |  | 
SA6#47-e | 14 – 18 February 2022 | To be converted to e-meeting | SID: Key issues + Solutions | 4
SA6#48 | 04 – 08 April 2022 | North America, Location, TBC | SID: Key issues + Solutions + Evaluations | 6
SA6#49 | 16 – 20 May 2022 | Asia, Location, TBC | SID: Complete Solutions + Evaluations + Conclusion; Send for Information WI approval | 6
SA6#49-BIS | 27 June – 01 July 2022 | [Only, if needed] Location, TBC | SID: Complete Solutions + Overall Evaluations + Conclusion WID: Requirements/Architecture based on concluded solutions | 4
SA6#50 | 22 – 26 August 2022 | Europe, Location, TBC | SID: Complete Solutions + Overall Evaluations + Conclusion; Send for Approval WID: Requirements/Architecture + Procedures based on concluded solutions | 4
SA6#51 | 10 – 14 October 2022 | Asia, Location, TBC | WID: Procedures | 5
SA6#52 | 14 – 18 November 2022 | North America, Location, TBC | WID: Procedures | 5
 | 2023 |  |  | 
SA6#52-BIS | 16 – 20 January 2023 | [Only, if needed] Location, TBC | WID: Procedures | 5
SA6#53 | 27 Feb – 03 Mar 2023 | Europe, Location, TBC | WID: Procedures | 5
Total TUs |  |  |  | 48

## Slide 4: Mapping of solutions to key issues - observations
Current Status of TR:
Total # of Kis agreed: 20
Total # of Solutions agreed: 20
# of KIs not having solutions agreed: 8
Solutions having evaluations: 8
Total # of ENs: 48 (ENs dependent on other groups: 5)
Guidance to make timely progress of TR:
Request timely closure of ENs in the solution before TR approval, to get conclusion on solutions
    Working on ENs directly during normative phase is subject to SA6 group conclusions.
Initiate LS for resolving dependency on other groups
List all open issues and Call for Volunteers (Rapporteur TBD)
Issue Analysis - Easy v/s Tough ones (Rapporteur TBD)
Any other suggestions?
 | KI # 1 | KI # 2 | KI # 3 | KI # 4 | KI # 5 | KI # 6 | KI # 7 | KI # 8 | KI # 9 | KI # 10 | KI # 11 | KI # 12 | KI # 13 | KI # 14 | KI # 15 | KI # 16 | KI # 17 | KI # 18 | KI # 19 | KI # 20
Sol #1 | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Sol #2 |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  | 
Sol #4 |  |  |  |  |  | X |  |  |  | X |  |  |  |  |  |  |  |  |  | 
Sol #5 |  |  |  |  |  | X |  |  |  | X |  |  |  |  |  |  |  |  |  | 
Sol #6 |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Sol #7 |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Sol #8 |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Sol #9 |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  | 
Sol #10 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  | 
Sol #11 |  | X |  |  | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
Sol #12 |  |  | X |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  | 
Sol #13 |  |  |  |  |  | X |  |  |  | X |  |  |  |  |  |  |  |  |  | 
Sol #14 |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  |  |  | 
Sol #15 |  |  |  |  |  |  |  | X |  |  |  |  |  | X |  |  |  |  |  | 
Sol #16 |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  |  |  | 
Sol #17 |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  |  | 
Sol #18 |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X |  |  |  |  | 
Sol #19 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | X | 
Sol #20 | X |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
… |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 

## Slide 5: Summary
Focus more on resolving remaining open issues
Additional 2 meetings for Study does not mean additional TUs
Co-operation required to adhere to work plan guidelines (on Slide#3)
Consider current status and follow guidance (on Slide#4)

## Slide 6: Thank You!