## Slide 1: FS_NSCALE status and plan
Shaowen Zheng
China Mobile

## Slide 2: Overview
 | Apr 2022 | May 2022 | Jun 2022 | Aug 2022 | Oct 2022 | Nov 2022 | Jan 2023 | Feb 2023 | 
SID/WID | SA6#48 TUs | SA6#49 TUs | SA6#49-BIS TUs | SA6#50 TUs | SA6#51 TUs | SA6#52 TUs | SA6#52-BIS TUs | SA6#53 TUs | Remaining TU
FS_NSCALE | 1 | 1.5 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 8.5
SID：only 2 meetings !!
WID: 6meetings
Study Item | WI Code | SID Approved | SA#94-e | SA#95-e | Target Completion | Remarks
Study on Network Slice Capability Exposure for Application Layer Enablement | FS_NSCALE | SA#91 (03/2021) | 55% | 70% | SA#96 (06/2022) | TR for information in SP-220091
WID proposal

## Slide 3
Plan (SID + WID)
Meeting | 2022 | Proposed work plan for <WID/SID> | Estimated TUs
SA6#47-e | 14 – 18 February 2022 | SID: KI+Solutions+ Evaluations | 1
SA6#48 | 04 – 08 April 2022 | SID: KI under discussion+Solutions + Evaluations+ Overall evaluation | 1
SA6#49 | 16 – 20 May 2022 | SID: Solutions + Evaluations + Conclusion + WI approval | 1.5
SA6#49-BIS | 27 June – 01 July 2022 | WID: TS template + Scope + Requirements/Architecture | 1
SA6#50 | 22 – 26 August 2022 | WID: Requirements/Architecture + Procedures | 1
SA6#51 | 10 – 14 October 2022 | WID: Procedures | 1
SA6#52 | 14 – 18 November 2022 | WID: Procedures | 1
 | 2023 |  | 
SA6#52-BIS | 16 – 20 January 2023 | WID: Procedures | 0.5
SA6#53 | 27 Feb – 03 Mar 2023 | WID: Procedures | 0.5

## Slide 4: solutions and KIs
 | Key issue 1 | Key issue 2 | Key issue 3 | Key issue 4 | Key issue 5 | Key issue 6 | Key issue 7 | Key issue 8 | Key issue 9 | Key issue 10 | Key issue 11 | Key issue 12 | Key issue 13 | Key issue 14 | evalustion
Solution 1 |  | X |  |  |  |  |  |  |  |  |  |  |  |  | Y
Solution 2 |  |  |  | X |  |  |  |  |  |  |  |  |  |  | Y
Solution 3 |  |  |  |  |  |  |  | X |  |  |  |  |  |  | N
Solution 4 |  |  |  |  |  | X |  |  |  |  |  |  |  |  | Y
Solution 5 |  |  |  |  |  |  | X |  |  |  |  |  |  |  | Y
Solution 6 |  |  |  |  |  |  |  |  | X |  |  |  |  |  | N
Solution 7 |  |  | X |  |  |  |  |  |  |  |  |  |  |  | N
Solution 8 |  |  | X |  |  |  |  |  |  |  |  |  |  |  | N
Solution 9 |  |  |  |  |  |  |  |  |  | X |  |  |  |  | N
Solution 10 |  |  |  |  |  |  |  |  |  | X |  |  |  |  | N
Solution 11 |  |  |  |  | X |  |  |  |  |  |  |  |  |  | N
… |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 
5 Key Issues without solution
KI 1: Network slice capability management enhancements
KI11: Dynamic slice SLA alignment
KI 12: Network slice capability exposure in the edge data network
KI 13: Delivery of the existing Network Slice information to the trusted third-party
KI 14: Network Slice creation to the third-party and UE
Call for valuteers to contribute corresponding solutions at SA6#48-e.
7 solutions without evaluation
Ongoing Topics:
deployment;
Architecture update

## Slide 5: Unsolved open issues about API
Key issue 2: Application layer exposed network slice lifecycle management
  Whether and how additional service APIs are required to be supported for application layer enablement of network slice lifecycle management?
Key issue 4: Network slice fault management capability
  - Whether and how additional APIs dedicated to network slice fault management capability are required?
  - How to define the APIs to expose the fault report to verticals client/server
Key issue 5: Communication service management exposure
  - What kinds of service APIs are required to be supported for application layer exposure of communication services life cycle management?
  - What kinds of additional service APIs are required to be supported for application layer exposure of communication services SLA assurance?
Key issue 6: Application layer QoS verification capability enablement
  - What kinds of additional service APIs are required to be supported for application layer enablement of QoS verification?
  - What kinds of additional service APIs are required to obtain the real vertical QoS to support the QoS verification?
Key issue 7: Network slice related performance and analytics exposure
  - Whether and how additional service APIs are required to be supported at SEAL for the network slice measurements and analytics exposure?
1. Updating the solutions to add some description or definition about the API;
2. Postponing the API definition to normative work phase, and maybe we could add an NOTE in the conclusion to capture this.

## Slide 6: Summary
Call for volunteers to propose solutions at SA6#48-e.
It is suggested to define the specific API during the normative work phase