## Slide 1: SA6#51-e Work Plan Review
Alan Soloway (Qualcomm)
SA6 Chair

## Slide 2: Overview: Ongoing Studies
Study Item | WI Code | SID Approved | SA#97-e | SA6#51-e | Target Completion | Remarks
Study on sharing of administrative configuration between interconnected MC service systems | FS_MCShAC | SA#94 (12/2021) | 25% | % | SA#99 (03/2023) | 
Study on Mission Critical Ad hoc Group Communications Support for Mission Critical Services | FS_MCAHGC | SA#94 (12/2021) | 90% | 95% | SA#97 (09/2022) | 
Study on Network Slice Capability Exposure for Application Layer Enablement | FS_NSCALE | SA#91 (03/2021) | 95% | 95% | SA#96 (06/2022) | 
Study on application enablement aspects for subscriber-aware NB API access | FS_SNAAPP | SA#92 (06/2021) | 90% | 90% | SA#96 (06/2022) | 

## Slide 3: Overview: Ongoing Studies
Study Item | WI Code | SID Approved | SA#97-e | SA6#51-e | Target Completion | Remarks
Study on Application Capability Exposure for IoT Platforms | FS_ACE_IOT | SA#92 (06/2021) | 75% | 85% | SA#97 (09/2022) | 
Study on 5G-enabled fused location service capability exposure | FS_5GFLS | SA#92 (06/2021) | 75% | 90% | SA#97 (09/2022) | 
Study on enhanced Application Architecture for enabling Edge Applications | FS_eEDGEAPP | SA#92 (06/2021) | 90% | 95% | SA#96 (06/2022) | 
Study on enhanced architecture for UAS Applications | FS_eUASAPP | SA#93 (09/2021) | 80% | ??% | SA#97 (09/2022) | 

## Slide 4: Overview: Ongoing Studies
Study Item | WI Code | SID Approved | SA#97-e | SA6#51-e | Target Completion | Remarks
Study on SEAL data delivery enabler for vertical applications | FS_SEALDD | SA#93 (09/2021) | 85% | 95% | SA#97 (09/2022) | 
Study on enhancements to application layer support for V2X services; Phase 2 | FS_eV2XAPP2 | SA#93 (09/2021) | 85% | 90% | SA#97 (09/2022) | 
Study on Application Data Analytics Enablement Service | FS_ADAES | SA#94 (12/2021) | 95% | 100% | SA#97 (09/2022) | 
Study on Application layer support for Personal IoT and Residential Networks | FS_PINAPP | SA#94 (12/2021) | 60% | 75% | SA#97 (09/2022) | 

## Slide 5: Overview: Rel-18 Work-Items
Study Item | WI Code | WID Approved | SA#97-e | SA6#51-e | Target Completion | Remarks
Mission Critical Services over 5MBS | MCOver5MBS | SA#93 (09/2021) | 98% | % | SA#95 (03/2022) | 
Mission Critical Services over 5GProSe | MCOver5GProSe | SA#94 (12/2021) | 100% | % | SA#99 (03/2023) | 
Gateway UE function for Mission Critical Communication | MCGWUE | SA#93 (09/2021) | 100% | % | SA#96 (06/2022) | 
Enhanced Mission Critical Push-to-talk architecture phase 4 | enh4MCPTT | SA#94 (12/2021) | 55% | 60% | SA#99 (03/2023) | 
Interconnection and Migration Aspects for Railways | IRail | SA#95 (03/2022) | 60% | 70% | SA#98 (12/2022) | 
Application layer support for Factories of the Future (FF) | FFAPP | SA#93 (09/2021) | 55% | 60% | SA#98 (12/2022) | 

## Slide 6: Overview: Rel-18 Work-Items
Study Item | WI Code | WID Approved | SA#97-e | SA6#51-e | Target Completion | Remarks
Enhanced Service Enabler Architecture Layer for Verticals Phase 2 | eSEAL2 | SA#94 (12/2021) | 35% | 45% | SA#98 (12/2022) | 
New WID on support of the MSGin5G Service phase 2 | 5GMARCH_Ph2 | SA#95 (03/2022) | 55% | % | SA#99 (03/2023) | 
Application enablement aspects for subscriber-aware northbound API access | SNAAPP | SA#96 (06/2022) | 0% | % | SA#99 (03/2023) | 
Network Slice Capability Exposure for Application Layer Enablement | NSCALE | SA#96 (06/2022) | 10% | 10/15% | SA#99 (03/2023) | 
Application Architecture for enabling Edge Applications Phase 2 | EDGEAPP_Ph2 | SA#97 (09/2022) | 5 | 15% | SA#99 (03/2023) | 

## Slide 7: Overview: Rel-18 Work-Items
Study Item | WI Code | WID Approved | SA#97-e | SA6#51-e | Target Completion | Remarks
Edge Application Standards in 3GPP and alignment with External Organizations | EDGEAPP_EXT | SA#96 (06/2022) | 5% | 5% | SA#100 (06/2023) | 
Architecture for UAS Applications, Phase 2 | UASAPP_Ph2 | SA#97 (09/2022) | NA | 25% | SA#99 (03/2023) | 
SEAL data delivery enabler for vertical applications | SEALDD | SA#97 (09/2022) | NA | 30% | SA#99 (03/2023) | 
Application layer support for V2X services; Phase 3 | V2XAPP_Ph3? | SA#97 (09/2022) | NA | 10% | SA#99 (03/2023) | 
Application Data Analytics Enablement Service | ADAES | SA#97 (09/2022) | NA | 10% | SA#99 (03/2023) | 

## Slide 8: Conference calls and other items
Pre-SA6#51-e conference calls (Dates are TBD) – 1.5 hours in duration
  MCAHGC, MCPTT, MCShAC, IRail, EDGEAPP, ACE-IoT, PINAPP, NSCALE, SNAAPP, 5GFLS, 5GMARCH, FFAPP, UASAPP, V2XAPP, ADAES, SEAL/SEALDD
  Working Methods – 1 meeting
Rapporteurs to make the draft TRs/TSs available within one week
All pre-agreed/approved revisions MUST be in the inbox folder
SA6#52 Meeting Procedures – Requested a conference call to review these with all SA WG participants

## Slide 9: Thank You!