## Slide 1: Planning of 5GA-features in SA6 for Release 20
Atle Monrad (InterDigital)
SA6 Chair
3GPP TSG-SA WG6 Meeting #69
Wuhan, P. R. China, 13th – 17th October 2025

## Slide 2: Overview of 5GA-features in SA6
Guidelines for 3GPP Application Enablement usage | AppEnable_EXT | SP-250883 | David Artuñedo, Telefónica
Stage 2 for Enhanced Mission Critical Services Architecture Phase 2 | enhMC_Ph2-MC | SP-250391 | Harish Negalaguli, Motorola Solutions
Stage 2 for FRMCS Phase 6 | FRMCS_Ph6-MC | SP-250390 | Martin Oettl, Nokia
Study on application enablement for satellite access enabled 5G services Phase 4 | FS_5GSAT_Ph4_APP | SP-250874 | Zhou Zhe, China Telecom
Study on Stage 2 for AI/ML service Phase 2 | FS_AIML_App_Ph2 | SP-250384 | Emmanouil (Manos) Pateromichelakis, Lenovo
Study on application enablement for Ambient IoT services Phase 2 | FS_AmbientIoT_Ph2_APP | SP-250870 | Liping Wu, CATT
Study on Application user consent | FS_APCOT | SP-250872 | Cristina Badulescu, Ericsson
Study of CAPIF Phase 4 | FS_CAPIF_Ph4 | SP-251043 | Sapan Shah, Nokia
Study on Application Enablement to support Energy Saving Phase 2 | FS_EnergySys_Ph2_APP | SP-250871 | Jing Yue, Ericsson
Study on Discreet listening and monitoring of mission critical services, Phase 2 | FS_MCDISC_Ph2 | SP-250379 | Kees Verweij, Netherlands Police
Study on Logging and recording of mission critical services, Phase 2 | FS_MCLOG_Ph2 | SP-250581 | Jukka Vialén, Airbus
Study on Stage 2 for MMTel Phase 2 | FS_MMTel_Ph2_APP | SP-250383 | Yue Liu, China Mobile
Study on Service Enabler Architecture Layer (SEAL) Phase 4 Service Enabler Architecture Layer (SEAL) Phase 4 | FS_SEAL_Ph4 SEAL_Ph4-APP | SP-250374 SP-251215 | Yanmei Yang, Huawei
Study on SEAL data delivery Phase 3 | FS_SEALDD_Ph3 | SP-251217 | Cuili Ge, Huawei
Study on use of Sensing results for Vertical Applications | FS_Sensing_APP | SP-251044 | Liu, Yue, China Mobile
Study on Application enabler for XR Services Phase 3 | FS_XRM_Ph3_APP | SP-251042 | Tangqing Liu, China Mobile
Stage 2 for mobile metaverse services Phase 2 | Metaverse_Ph2-APP | SP-250392 | Arunprasath (Arun) Ramamoorthy, Samsung
Stage 2 for Mission Critical Services for UE-to-UE and UE-to-Network over multi-hop relay | MultiHop-MC | SP-250389 | Mark Lipford, FirstNet Authority

## Slide 3: XR_Ph3_APP Work Plan
Shaowen Zheng, China Mobile (Rapporteur)

## Slide 4: Milestone proposals for FS_XR_Ph3_APP
Milestone proposals for SID |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71
Key issue | New key issues Update key issues END of key issues | Update key issues |  | 
Solution | New solutions Update solutions Solutions evaluations | New solutions Update solutions Solutions evaluations END of new solutions | Update solutions Solutions evaluations | 
Interim conclusion |  | Agree interim conclusions | Finalize interim conclusions | 
Conclusion |  |  | Finalize conclusions | 
NOTE 1: The TR for the SID is planned to send SA plenary for information at Sep SA#109.
NOTE 2: The TR for the SID is planned to send SA plenary for approval at Dec SA#110.

## Slide 5: Potential coordination for FS_XR_Ph3_APP
Work on the following aspects need to be coordinated:
None

## Slide 6: XR_Ph3_APP
Planning of 5GA feature XR_Ph3_APP, study and normative work – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (# of TUs) | Oct #69 (# of TUs) | Nov #70 (# of TUs) | Feb #71 (# of TUs) | Apr #72 (# of TUs) | May #73 (# of TUs) | Aug #74 (# of TUs)
Plenary | Sept #109 |  | Dec #110 | March #111 Study deadline |  | June #112 Stage 2 80% | Sept #113 Stage 2 100%
Focus area | KI’s, Solutions, Update solutions, | Solutions, Update solutions, Interim conclusions Start of WI | Update solutions, conclusions SI Completed | Start of normative | Normative | Normative WI Completed | Maintenance
TUs consumed (until SA6#67): 6TUs
NOTE: The normative WID is not yet approved and the progress of the normative phase is just an estimate.

## Slide 7: SEALDD_Ph3 Work Plan
Cuili Ge, Huawei (Rapporteur)

## Slide 8: Milestone proposals for FS_SEALDD_Ph3
Milestone proposals for SID |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71
Key issue | New key issues Update key issues | Update key issues END of key issues |  | 
Solution | New solutions Update solutions Solutions evaluations | New solutions Update solutions Solutions evaluations | Update solutions Solutions evaluations END of new solutions | 
Interim conclusion |  | Agree interim conclusions | Finalize interim conclusions | 
Conclusion |  |  | Finalize conclusions | 
NOTE 1: The TR for the SID is planned to send SA plenary for information at Sep SA#109.
NOTE 2: The TR for the SID is planned to send SA plenary for approval at Dec SA#110.

## Slide 9: Potential coordination for FS_SEALDD_Ph3
Work on the following aspects need to be coordinated:
None

## Slide 10: SEALDD_Ph3
Planning of 5GA feature FS_SEALDD_Ph3, study and normative work – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (# of TUs) | Oct #69 (# of TUs) | Nov #70 (# of TUs) | Feb #71 (# of TUs) | Apr #72 (# of TUs) | May #73 (# of TUs) | Aug #74 (# of TUs)
Plenary | Sept #109 |  | Dec #110 | March #111 Study deadline |  | June #112 Stage 2 80% | Sept #113 Stage 2 100%
Focus area | KI’s, Solutions, Update solutions, | Solutions, Update solutions, Interim conclusions | Update solutions, conclusions SI Completed WID proposal | Start of normative | Normative | Normative WI Completed | Maintenance
TUs consumed (until SA6#67): 6TUs
NOTE: The normative WID is not yet approved and the progress of the normative phase is just an estimate.

## Slide 11: AΙML_App_Ph2 Work Plan
Manos Pateromichelakis, Lenovo (Rapporteur)

## Slide 12: Milestone proposals for FS_AIML_App_Ph2
Milestone proposals for SID |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71
Key issue | KI updates END of new/updated key issues |  |  | 
Solution | New solutions Solution updates Architecture enh. | Solution updates Architecture enh./ Business/Deployment models END of new solutions | Necessary updates Finalize architecture enhancements | 
Interim conclusion |  | Solution evaluation Interim conclusions | Solution evaluation Finalize interim conclusions | 
Conclusion |  |  | Finalize conclusions | 
NOTE 1: The TR for the SID is planned to send SA plenary for information at Aug #68 (if 65% is reached).
NOTE 2: The TR for the SID is planned to send SA plenary for approval at Nov#70.

## Slide 13: Potential coordination for FS_AIML_App_Ph2
Work on the following aspects need to be coordinated:
None

## Slide 14: AIML_App_Ph2
Planning of 5GA feature AIML_App_Ph2, study and normative work – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (1.5 of TUs) | Oct #69 (1.5 of TUs) | Nov #70 (1 of TUs) | Feb #71 (1.5 of TUs) | Apr #72 (1.5 of TUs) | May #73 (1.5 of TUs) | Aug #74 (0.5 of TUs)
Plenary | Sept #109 |  | Dec #110 Study deadline | March #111 |  | June #112 Stage 2 80% | Sept #113 Stage 2 100%
Focus area | Updated KIs, New/updated Solutions Arch enh | Solutions Update solutions, Solution evaluation ,Interim conclusions | Necessary updates, Conclusions, SI Completed WID proposal | Start of normative | Normative | Normative WI Completed | Maintenance
NOTE: The normative WID is not yet approved and the progress of the normative phase is just an estimate.
TUs consumed (until SA6#74): 9 TUs

## Slide 15: Metaverse_Ph2-APP Work Plan
Arun Ramamoorthy, Samsung (Rapporteur)

## Slide 16: Milestone proposals for Metaverse_Ph2-APP
Milestone proposals for Metaverse_Ph2-APP |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71
Progress | Normative 1.Spatial anchor grouping 2.Spatial Map enhancements 3.DA management 4.Spatial Map object tracking | Normative 1.Complete the pending procedures 2.Correction related CRs 3.Resolution of pending Editor Notes | Normative 1.Pending procedures if any 2.Correction related CRs WID completion | 

## Slide 17: Potential coordination for Metaverse_Ph2-APP
Work on the following aspects need to be coordinated: NONE

## Slide 18: Metaverse_Ph2-APP
Planning of 5GA feature Metaverse_Ph2-APP normative work – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (1 TU) | Oct #69 (1 TU) | Nov #70 (1 TU) | Feb #71 (# of TUs) | Apr #72 (# of TUs) | May #73 (# of TUs) | Aug #74 (# of TUs)
Plenary | Sept #109 |  | Dec #110 | March #111 Study deadline |  | June #112 Stage 2 80% | Sept #113 Stage 2 100%
Focus area | Normative | Normative | Normative WI completed | Maintenance | Maintenance | Maintenance | Maintenance
TUs consumed (until SA6#67): 2 TUs

## Slide 19: AmbientIoT_Ph2_APP Work Plan
Liping Wu, CATT (Rapporteur)

## Slide 20: Milestone proposals for FS_AmbientIoT_Ph2_APP
Milestone proposals for SID |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71
Key issue | TR skeleton New key issues | New key issues Update key issues END of new key issues | Update key issues | 
Solution |  | New solutions | New solutions Update solutions END of new solutions | Update solutions
Interim conclusion |  |  | Solution evaluation Interim conclusions | Solution evaluation Finalize interim conclusions
Conclusion |  |  |  | Finalize conclusions
NOTE 1: The TR for the SID is planned to send SA plenary for information at Nov#70.
NOTE 2: The TR for the SID is planned to send SA plenary for approval at Feb#71.

## Slide 21: Potential coordination for FS_AmbientIoT_Ph2_APP
Work on the following aspects need to be coordinated:
Study how to utilize the exposure from other working group and provide the value-added Ambient IoT device information to the consumer. <SA2>
Study how to monitor the status of the Ambient IoT devices to minimize the service impact. <SA2>

## Slide 22: AmbientIoT_Ph2_APP
Planning of 5GA feature AmbientIoT_Ph2_APP, study and normative work – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (0.5 of TUs) | Oct #69 (1 of TUs) | Nov #70 (1.5 of TUs) | Feb #71 (1 of TUs) | Apr #72 (1 of TUs) | May #73 (1.5 of TUs) | Aug #74 (0.5 of TUs)
Plenary | Sept #109 |  | Dec #110 | March #111 Study deadline |  | June #112 Stage 2 80% | Sept #113 Stage 2 100%
Focus area | KI’s | KI’s, Solutions | Solutions, Update solutions, Solution evaluation ,Interim conclusions Start of WI | Update solutions, Solution evaluation, Conclusions, SI Completed Start of normative | Normative | Normative WI Completed | Maintenance
NOTE: The normative WID is not yet approved and the progress of the normative phase is just an estimate.
TUs consumed (until SA6#74): 7 TUs

## Slide 23: SEAL_Ph4 Work Plan
Yanmei Yang, Huawei (Rapporteur)

## Slide 24: Milestone proposals for FS_SEAL_Ph4
Milestone proposals for FS_SEAL_Ph4 |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71
Progress | END of key issues and new solutions New solution for Gap#7 Solution evaluation Technical solutions #5,#7,#10,#12; Solution evaluation for adoption solutions##5,#6 Start of Overall evaluation on all Gaps Start of TR Conclusions NOTE: WID proposal on Normative (see time plan for WID) | Complete the pending overall evaluation on all gaps Complete the pending TR Conclusions SID completion NOTE: Star of Normative ((see time plan for WID)) |  | 

## Slide 25: Potential coordination for SEAL_Ph4
Work on the following aspects need to be coordinated: NONE

## Slide 26: Milestone proposals for SEAL_Ph4
Planning of 5GA feature SEAL_Ph4 normative work – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (1 TU) | Oct #69 (1 TU) | Nov #70 (2 TU) | Feb #71 (1 TUs) | Apr #72 (1 TUs) | May #73 (# of TUs) | Aug #74 (# of TUs)
Plenary | Sept #109 |  | Dec #110 | March #111 Study deadline |  | June #112 Stage 2 80% | Sept #113 Stage 2 100%
Focus area | SID completion WID proposal | CRs to existing SEAL TSs Skeleton on new External TR | CRs to existing SEAL TSs PCRs on new External TR | CRs to existing SEAL TSs (completion) PCRs on new External TR | Normative completed WI completed | Maintenance | Maintenance

## Slide 27: Study on MultiHop-MC Work Plan
Mark Lipford, FirstNet Authority (Rapporteur)

## Slide 28: Milestone proposals for MultiHop-MC
Milestone proposals for WID |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71
Progress | Discussion and possible resolution on remain open item (quality/reliability/performance of the relay connection info to end user) See TS22.261 clause 6.9.2.2 | Final closure on open issue from #68 | Any needed CRs for final clean-up of feature | Nothing expected WI Completed

## Slide 29: Potential coordination for MultiHop-MC
Work on the following aspects need to be coordinated:
None

## Slide 30: MultiHop-MC
Planning of 5GA feature MultiHop-MC normative work – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (.5 of TUs) | Oct #69 (.5 of TUs) | Nov #70 (.25 of TUs) | Feb #71 (0 of TUs) | Apr #72 (0 of TUs) | May #73 (0 of TUs) | Aug #74 (0# of TUs)
Plenary | Sept #109 |  | Dec #110 | March #111 WID deadline |  | June #112 | Sept #113
Focus area | Discuss open issue | Resolve final open issue | Final clean up and validation of work | Normative WI Completed |  |  | 
TUs consumed (until SA6#67): 1.25 TUs

## Slide 31: 5GSAT_Ph4_App Work Plan
Zhou Zhe, China Telecom (Rapporteur)

## Slide 32: Milestone proposals for FS_5GSAT_Ph4_App
Milestone proposals for SID |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71
Key issue | TR skeleton New key issues | New key issues Update key issues END of new key issues | Update key issues | 
Solution |  | New solutions | New solutions Update solutions END of new solutions | Update solutions
Interim conclusion |  |  | Solution evaluation Interim conclusions | Solution evaluation Finalize interim conclusions
Conclusion |  |  |  | Finalize conclusions
NOTE 1: The TR for the SID is planned to send SA plenary for information at Nov#70.
NOTE 2: The TR for the SID is planned to send SA plenary for approval at Feb#71.

## Slide 33: Potential coordination for FS_5GSAT_Ph4_App
Work on the following aspects need to be coordinated:
Study how to support security aspect while enhancing existing SA6 Application Enablers based on satellite access <SA3>

## Slide 34: 5GSAT_Ph4_App
Planning of 5GA feature 5GSAT_Ph4_App study and normative work – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (0.5 of TUs) | Oct #69 (1 of TUs) | Nov #70 (1.5 of TUs) | Feb #71 (1 of TUs) | Apr #72 (1 of TUs) | May #73 (1.5 of TUs) | Aug #74 (0.5 of TUs)
Plenary | Sept #109 |  | Dec #110 | March #111 Study deadline |  | June #112 Stage 2 80% | Sept #113 Stage 2 100%
Focus area | KI’s | KI’s, Solutions | Solutions, Update solutions, Solution evaluation ,Interim conclusions Start of WI | Update solutions, Solution evaluation, Conclusions, SI Completed Start of normative | Normative | Normative WI Completed | Maintenance
NOTE: The normative WID is not yet approved and the progress of the normative phase is just an estimate.
TUs consumed (until SA6#74): 7 TUs

## Slide 35: FRMCS_Ph6-MC Work Plan
Martin Oettl, Nokia (Rapporteur)

## Slide 36: Milestone proposals for FRMCS_Ph6-MC
Milestone proposals for WID |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71
Progress | Normative Resolve editor’s notes Adhoc group enhancements MC gateway UE Interworking/Interconnection Open issues | Normative Resolve editor’s notes Adhoc group enhancements MC gateway UE Interworking/Interconnection Open issues | Normative Resolve editor’s notes Continue work on remaining objectives Open issues | Normative Resolve editor’s notes Continue work on remaining objectives Open issues

## Slide 37: Potential coordination for FRMCS_Ph6-MC
Work on the following aspects need to be coordinated:
None

## Slide 38: FRMCS_Ph6-MC
Planning of 5GA feature FRMCS_Ph6-MC normative work – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (# of TUs) | Oct #69 (# of TUs) | Nov #70 (# of TUs) | Feb #71 (# of TUs) | Apr #72 (# of TUs) | May #73 (# of TUs) | Aug #74 (# of TUs)
Plenary | Sept #109 |  | Dec #110 | March #111 Stage 2 80% |  | June #112 Stage 2 100% | Sept #113
Focus area | Normative | Normative | Normative | Normative | Normative | Normative WI Completed | Maintenance
TUs consumed (until SA6#67): 2 TUs

## Slide 39: MMTel_Ph2_App Work Plan
Yue Liu, China Mobile (Rapporteur)

## Slide 40: Milestone proposals for FS_MMTel_Ph2_App
Milestone proposals for SID |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71
Key issue | New key issues Update key issues | New key issues Update key issues END of key issues | Update key issues | 
Solution | New solutions Update solutions Solutions evaluations | New solutions Update solutions Solutions evaluations interim conclusions | New solutions Update solutions Solutions evaluations END of new solutions | Update solutions Solutions evaluations
Interim conclusion |  |  | Agree interim conclusions | Finalize interim conclusions
Conclusion |  |  |  | Finalize conclusions
NOTE 1: The TR for the SID is planned to send SA plenary for information at Dec SA#110.
NOTE 2: The TR for the SID is planned to send SA plenary for approval at March#111.

## Slide 41: Potential coordination for FS_MMTel_Ph2_App
Work on the following aspects need to be coordinated:
Whether the external data channel content access requirements (described in incoming LS S6-253007) are needed to be studied is FFS and if needed, coordination with SA2/SA4 is needed

## Slide 42: MMTel_Ph2_App
Planning of 5GA feature MMTel_Ph2_App, study and normative work – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (1 of TU) | Oct #69 (1 of TU) | Nov #70 (1 of TU) | Feb #71 (1 of TU) | Apr #72 (1 of TU) | May #73 (1 of TU) | Aug #74 (1 of TU)
Plenary | Sept #109 |  | Dec #110 | March #111 Study deadline |  | June #112 Stage 2 80% | Sept #113 Stage 2 100%
Focus area | KI’s, Solutions, Update solutions, | KI’s, Solutions, Update solutions, Interim conclusions | solutions, Update solutions, conclusions, Start of WI | conclusions, Start of normative SI Completed | Normative | Normative WI Completed | Maintenance
NOTE: The normative WID is not yet approved and the progress of the normative phase is just an estimate.
TUs consumed (until SA6#74): 7 TUs

## Slide 43: Sensing_App Work Plan
Yue Liu, China Mobile (Rapporteur)

## Slide 44: Milestone proposals for FS_Sensing_App
Milestone proposals for SID |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71
Key issue | TR skeleton New key issues | New key issues Update key issues | Update key issues END of new key issues | 
Solution |  | New solutions | New solutions Update solutions END of new solutions | Update solutions
Interim conclusion |  |  | Solution evaluation Interim conclusions | Solution evaluation Finalize interim conclusions
Conclusion |  |  |  | Finalize conclusions
NOTE 1: The TR for the SID is planned to send SA plenary for information at Dec SA#110.
NOTE 2: The TR for the SID is planned to send SA plenary for approval at March#111.

## Slide 45: Potential coordination for FS_Sensing_App
Work on the following aspects need to be coordinated:
The 3GPP systems aspects need to be coordinated with SA2

## Slide 46: Sensing_App
Planning of 5GA feature Sensing_App, study and normative work – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (1 of TU) | Oct #69 (1 of TU) | Nov #70 (1 of TU) | Feb #71 (1 of TU) | Apr #72 (1 of TU) | May #73 (1 of TU) | Aug #74 (1 of TU)
Plenary | Sept #109 |  | Dec #110 | March #111 Study deadline |  | June #112 Stage 2 80% | Sept #113 Stage 2 100%
Focus area | KI’s | KI’s, Solutions | Solutions, Update solutions, Solution evaluation ,Interim conclusions Start of WI | Update solutions, Solution evaluation, Conclusions, SI Completed Start of normative | Normative | Normative WI Completed | Maintenance
NOTE: The normative WID is not yet approved and the progress of the normative phase is just an estimate.
TUs consumed (until SA6#74): 7 TUs

## Slide 47: CAPIF Phase 4 Work Plan
Niranth Amogh, Nokia (Rapporteur)

## Slide 48: Milestone proposals for FS_CAPIF_Ph4
Milestone proposals for SID |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71
Key issue | TR (23.700-43) skeleton New key issues | New key issues Update key issues END of new key issues | Update key issues | 
Solution | New solutions | New solutions | New solutions Update solutions END of new solutions | Update solutions
Interim conclusion |  |  | Solution evaluation Interim conclusions | Solution evaluation Finalize interim conclusions
Conclusion |  |  |  | Finalize conclusions
TR Progress |  |  | (Expected to complete >70%) To send for information | (Expected to complete >95%) To send for approval

## Slide 49: Potential coordination for FS_CAPIF_Ph4
Work on the following aspects need to be coordinated:
Security consideration for new solutions. <SA3>

## Slide 50: CAPIF_Ph4
Planning of 5GA feature CAPIF_Ph4, study and normative work – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (1 of TUs) | Oct #69 (1 of TUs) | Nov #70 (1 of TUs) | Feb #71 (1 of TUs) | Apr #72 (1 of TUs) | May #73 (1 of TUs) | Aug #74 (0.5 of TUs)
Plenary | Sept #109 |  | Dec #110 | March #111 Study deadline |  | June #112 Stage 2 80% | Sept #113 Stage 2 100%
Focus area | KI’s | KI’s, Solutions | Solutions, Update solutions, Interim conclusions Start of WI | Update solutions, conclusions SI Completed Start of normative | Normative | Normative WI Completed | Maintenance
NOTEs: The WID for normative work is not approved yet. Above is estimate for the normative work.
TUs consumed (until SA6#67): 0 TUs

## Slide 51: EnergySys_Ph2_APP Work Plan
Jing Yue, Ericsson (Rapporteur)

## Slide 52: Milestone proposals for FS_EnergySys_Ph2_APP
Milestone proposals for SID |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71
Key issue | TR skeleton New key issues | New key issues Update key issues END of new key issues | Update key issues | 
Solution |  | New solutions | New solutions Update solutions END of new solutions | Update solutions
Interim conclusion |  |  | Solution evaluation Interim conclusions | Solution evaluation Finalize interim conclusions
Conclusion |  |  |  | Finalize conclusions
NOTE 1: The TR for the SID is planned to send SA plenary for information at Dec SA#110.
NOTE 2: The TR for the SID is planned to send SA plenary for approval at March SA#111.

## Slide 53: Potential coordination for FS_EnergySys_Ph2_APP
Work on the following aspects need to be coordinated:
None

## Slide 54: EnergySys_Ph2_APP
Planning of 5GA feature EnergySys_Ph2_APP, study and normative work – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (1 of TUs) | Oct #69 (1.5 of TUs) | Nov #70 (2 of TUs) | Feb #71 (1.5 of TUs) | Apr #72 (1.5 of TUs) | May #73 (1.5 of TUs) | Aug #74 (1 of TUs)
Plenary | Sept #109 |  | Dec #110 | March #111 Study deadline |  | June #112 Stage 2 80% | Sept #113 Stage 2 100%
Focus area | KI’s | KI’s, Solutions | Solutions, Update solutions, Solution evaluation, Interim conclusions Start of WI | Update solutions, Solution evaluation, Conclusions, SI Completed Start of normative | Normative | Normative WI Completed | Maintenance
NOTE: The normative WID is not yet approved and the progress of the normative phase is just an estimate.
TUs consumed (until SA6#74): 10 TUs

## Slide 55: APCOT Work Plan
Cristina Badulescu, Ericsson (Rapporteur)

## Slide 56: Milestone proposals for FS_APCOT
Milestone proposals for SID |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71
Phase 1 | TR 23.700-42 skeleton New Business relationships Terminology analysis New use cases | New/Update UCs UC analysis END of NEW UCs Business relationships Terminology analysis END of NEW Terminology analysis END of NEW Business relationships | UC analysis Update UCs Update Business relationships Update Terminology analysis End of SI Phase 1 | 
Phase 2: Key issue |  |  | Start of SI Phase 2 New Key issues | New/Update Key issues
Phase 2: Solution |  |  | New solutions | New/Update solutions New Solutions evaluations
Interim conclusion |  |  |  | Interim conclusions (NOTE 1)
Conclusion |  |  |  | 
NOTE 1: The TR for the SID is planned to send SA plenary for information at SA#110 (Dec 2025) with >65% completion rate
NOTE 2: The TR for the SID is planned to send SA plenary for approval at SA#111 (March 2026)

## Slide 57: Potential coordination for FS_APCOT
Work on the following aspects need to be coordinated:
FS_APCOT Study phase 2: system aspects if/as needed <SA2>, security areas <SA3>

## Slide 58: APCOT
Planning of 5GA feature APCOT study and normative work – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (1.5 TU) | Oct #69 (1.5 TU) | Nov #70 (1.5 TU) | Feb #71 (1 TU) | Apr #72 (1 TU) | May #73 (1 TU) | Aug #74 (1 TU)
Plenary | Sept #110 |  | Dec #111 | March #112 Study deadline |  | June #113 Stage 2 80% | Sept #114 Stage 2 100%
Focus area | Business relationships Terminology analysis UCs | New/Update Business relationships Terminology analysis UCs, UC analysis End of new UCs, new business relationships | Update Business relationships Terminology, UCs, UC analysis Start of SI phase 2 New KIs, solutions | New & update of KIs, solutions New evaluations, interim conclusions | New/Update of KIs, solutions, evaluations, conclusions SI Completed Start of Normative | Normative | WI Completed Maintenance
NOTE: The normative WID is not yet approved, so the normative phase is just an initial estimate.
TUs consumed (until SA6#67): 0 TUs

## Slide 59: MCDISC_Ph2 Work Plan
Kees Verweij, Netherlands Police (Rapporteur)

## Slide 60: Milestone proposals for FS_MCDISC_Ph2
Milestone proposals for SID |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71
Key issue | New scenarios New key issues | New key issues Update key issues END of key issues |  | 
Solution |  | New solutions | New solutions Update solutions END of new solutions | Update solutions
Interim conclusion |  |  | Agree interim conclusions | Finalize interim conclusions
Conclusion |  |  |  | Finalize conclusions

## Slide 61: Potential coordination for FS_MCDISC_Ph2
Work on the following aspects need to be coordinated:
Architecture for FS_MCDISC_Ph2 is likely to reuse large parts of the architecture for FS_MCLOG_Ph2.

## Slide 62: MCDISC_Ph2
Planning of 5GA feature MCDISC_Ph2 study – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (# of TUs) | Oct #69 (# of TUs) | Nov #70 (# of TUs) | Feb #71 (# of TUs) | Apr #72 (# of TUs) | May #73 (# of TUs) | Aug #74 (# of TUs)
Plenary | Sept #109 |  | Dec #110 | March #111 Study deadline |  | June #112 Stage 2 80% | Sept #113 Stage 2 100%
Focus area | Scenarios KI’s | KI’s, Solutions | Solutions, Update solutions, Interim conclusions | Update solutions, conclusions SI Completed |  |  | 
TUs consumed (until SA6#67): 0,5 TUs
Normative part is not yet determined

## Slide 63: AppEnable_EXT Work Plan
David Artuñedo, Telefónica (Work item Rapporteur)
Walter Featherstone, Apple (TR 23.947 Rapporteur)

## Slide 64: Milestone proposals for AppEnable_EXT
Milestone proposals for WID |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71
Progress | Informative TR skeleton Scope / Intro | Informative Framework overviews Use cases | Informative Integration architecture Developer guidelines | Informative Wrap-up outstanding aspects, including Security & Privacy considerations Summary WI Completed
NOTEs: N/A

## Slide 65: Potential coordination for AppEnable_EXT
Work on the following aspects need to be coordinated: None

## Slide 66: AppEnable_EXT
Planning of 5GA AppEnable_EXT informative work – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (0.5 TU) | Oct #69 (0.5 TU) | Nov #70 (0.5 TU) | Feb #71 (0.5 TU) | Apr #72 (0 TUs) | May #73 (0 TUs) | Aug #74 (0 TUs)
Plenary | Sept #109 |  | Dec #110 | March #111 Study deadline |  | June #111 Stage 2 80% | Sept #113 Stage 2 100%
Focus area | TR skeleton Start of WI | Framework overviews Use cases | Integration arch Dev guidelines | Wrap-up Summary / outlook WI Completed | Maintenance | Maintenance | Maintenance
NOTEs: N/A
TUs consumed (until SA6#67): 0 TUs

## Slide 67: enhMC_Ph2-MC Work Plan
Harish Negalaguli, Motorola Solutions (Rapporteur)

## Slide 68: Milestone proposals for enhMC_Ph2-MC
Milestone proposals for WID |  |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71 | April #72
Progress | Normative | Normative | Normative | Normative | Normative WI Completed

## Slide 69: Potential coordination for enhMC_Ph2-MC
Work on the following aspects need to be coordinated:
None

## Slide 70
Planning of 5GA feature enhMC_Ph2-MC normative work – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (# of TUs) | Oct #69 (# of TUs) | Nov #70 (# of TUs) | Feb #71 (# of TUs) | Apr #72 (# of TUs) | May #73 (# of TUs) | Aug #74 (# of TUs)
Plenary | Sept #109 |  | Dec #110 | March #111 Stage 2 80% | Stage 2 100% | June #112 | Sept #113
Focus area | Normative | Normative | Normative | Normative | Normative WI Completed |  | 
TUs consumed (until SA6#67): 5 TUs
enhMC_Ph2-MC

## Slide 71: MCLOG_Ph2 Work Plan
Jukka Vialén, Airbus (Rapporteur)

## Slide 72: Milestone proposals for FS_MCLOG_Ph2
Milestone proposals for SID |  |  |  | 
 | Aug #68 | Oct #69 | Nov #70 | Feb #71
Key issue | New scenarios New key issues | New scenarios New key issues Update key issues END of scenarios | New key issues Update key issues END of key issues | 
Solution | New solutions | New solutions Update solutions | New solutions Update solutions | New solutions Update solutions END of new solutions
Interim conclusion |  |  | Agree interim conclusions | Finalize interim conclusions
Conclusion |  |  |  | Finalize conclusions

## Slide 73: Potential coordination for FS_MCLOG_Ph2
Work on the following aspects need to be coordinated:
Security aspects arising from KIs/solutions SA3

## Slide 74: MCLOG_Ph2
Planning of 5GA feature MCLOG_Ph2, study and normative work – proposed baseline
 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
SA6 | Aug #68 (1,5 TUs) | Oct #69 (1,5 TUs) | Nov #70 (1 TU) | Feb #71 (1,5 TUs) | Apr #72 (1,5 TUs) | May #73 (1 TU) | Aug #74 (1 TU)
Plenary | Sept #109 |  | Dec #110 | March #111 Study deadline |  | June #112 Stage 2 80% | Sept #112 Stage 2 100%
Focus area | Scenarios KI’s Solutions | Scenarios, KI’s, Solutions Draft WID | KI’s, Solutions, Update solutions, Interim conclusions SA6: Agree WID SA: Approve WID | Update solutions, conclusions (New Kis only with related solution& solution evaluation) SI 90% -> for approval Start of normative | Normative | Normative 80% | WI Completed
TUs consumed (until SA6#67): 1 TUs
NOTE: The normative WID is not yet approved and the progress of the normative phase is just an estimate.

## Slide 75: Thank You!