## Slide 1: Study on Modernization of Specification Format and Procedures for 6G: Workplan
Matthew Baker, Suresh Chitturi, Yue Song
SI Co-rapporteurs

## Slide 2: Agenda (6GSM-250001)

## Slide 3: Workplan
  #1 Wed 6th Aug
  #2 Wed 3rd Sep
  [TSG#109]
  #3 Thu 9th Oct
  #4 Mon 10th Nov
  [TSG#110] (TR v1.0.0)
  #5 Thu 15th Jan
  #6 Wed 25th Feb
  [TSG#111] (TR v2.0.0)
Objective 1
Objectives 2 & 3
Conclusions /
Recommendations
Background and preparation
In preparation for studies for objectives 2 & 3, delegates may wish to review the GoToWebinar sessions held on 24th/26th March (as advertised on the TSG RAN reflector), whose content is available at: https://www.3gpp.org/ftp/tsg_ran/TSG_RAN/Tool_Automation_6G