## Sheet1
ID | Delegate | Work Item | Class | TDoc | Status | Processed | Proposed Conclusion | Description | Proposed Change | Rapporteur Comments | Section | Implementaion Status (Yes/No)
H904 | Huawei (YinghaoGuo) | POS | 1 |  | PropAgree |  | v061 | SIB23 is missing | Add SIB23 | To be implemented in Rapporteur CR | 5.2.2.1 General UE requirements
G114 | Google (Eric) | POS | 1 | None | PropAgree |  |  | Both the srs-PosRRC-InactiveValidityAreaPreConfigList and srs-PosRRC-InactiveValidityAreaNonPreConfig successPSCell-Config are setuprelease type and may includes with release value. | Change the procedure text according to guidline in 6.3.0: 1> if field-rX is set to "setup": 2> do something; 1> else (field-rX is set to "release"): 2> release field-rX (if appropriate). | To be implemented in Rapporteur CR | 5.3.3.4 Reception of the RRCSetup by the UE
G115 | Google (Eric) | POS | 0 | None | PropAgree |  |  | the bullet “2> else if srs-PosRRC-InactiveValidityAreaPreConfigList is set to release:” should change to next line. | Change the bullet “2> else if srs-PosRRC-InactiveValidityAreaPreConfigList is set to release:“ to next line. [Comments]: | To be implemented in Rapporteur CR | 5.3.8.3 Reception of the RRCRelease by the UE
H905 | Huawei (YinghaoGuo) | POS | 1 | R2-2402468 | ToDo |  | v061 | The corresponding SRS linkage configuration for CA positioning should also be released. | when SRS is released, the correespoding SRS linkage configuation for CA positioning should also be released. | This can be discussed. We noted also Rel-17 CR for release of TEG reporting. As such when SRS is released, all the assocoaition would anyway be released by UE. We can disucss if explicit release clause is needed or not. | 5.3.12 UE actions upon PUCCH/SRS release request
G116 | Google (Eric) | POS | 1 | None | PropAgree |  |  | Same as G114 | Change the procedure text according to guidline in 6.3.0: 1> if field-rX is set to "setup": 2> do something; 1> else (field-rX is set to "release"): 2> release field-rX (if appropriate). |  | 5.3.13.2 Initiation
H906 | Huawei (YinghaoGuo) | POS | 1 | R2-2402468 | ToDo |  | v061 | For this case, the trigger is not from the RRC layer, So the AC should not be determined in the RRC layer. | AC shouled be determined in the upper layer rather thant he RRC layer for activation request. | The clause does not say that it is triggered by RRC layer. It only says if triggered but who triggers is not stated. we can discuss this in coming meeting. Anyhow AC is needed for this case too. | 5.3.13.2 Initiation
G117 | Google (Eric) | POS | 1 | None | PropAgree |  |  | Same as G114 | Change the procedure text according to guidline in 6.3.0: 1> if field-rX is set to "setup": 2> do something; 1> else (field-rX is set to "release"): 2> release field-rX (if appropriate). | To be implemented in Rapporteur CR | 5.3.13.4 Reception of the RRCResume by the UE
H907 | Huawei (YinghaoGuo) | POS | 1 |  | PropAgree |  | v061 | The field name needs to be updated It should be srs-PosRRC-InactiveValidityAreaNonPreConfig | udpate the name of the field to the correct one. | To be implemented in Rapporteur CR | 5.3.13.6 Cell re-selection or cell selection or L2 U2N relay (re)selection while T390, T319 or T302 is running or SDT procedure is ongoing (UE in RRC_INACTIVE) or SRS transmission in RRC_INACTIVE is configured
H908 | Huawei (YinghaoGuo) | POS | 1 |  | PropAgree |  | v061 | Should be srs-PosRRC-InactiveValidityAreaPreConfig | update the name of the field to the correct one. | To be implemented in Rapporteur CR | 5.3.13.6 Cell re-selection or cell selection or L2 U2N relay (re)selection while T390, T319 or T302 is running or SDT procedure is ongoing (UE in RRC_INACTIVE) or SRS transmission in RRC_INACTIVE is configured
S208 | Samsung (Taeseop) | POS | 1 | R2-24xxxxx | PropAgree |  | v023 | The UE should apply the SRS pre-configuration after receiving RRCRelease message. | According to the following agreement, the UE should apply the SRS pre-configuration after receiving RRCRelease message. The corresponding part should be moved to 5.3.8.3 (Reception of the RRCRelease by the UE). TP will be provided by our contribution at this meeting. *Agreement in RAN2#125: For preconfigured SRS, when the UE moves to a new validity area, it does not continue transmitting SRS until it has gone through RRCResumeRequest/RRCRelease procedure. No additional acknowledgement message is needed for the activation request, i.e., the UE can apply the preconfiguration after it receives the RRCRelease. | That is right. As per the agreement, it should be only after RRCRelease. To be implemented in Rapporteur CR | 5.3.13.6 Cell re-selection or cell selection or L2 U2N relay (re)selection while T390, T319 or T302 is running or SDT procedure is ongoing (UE in RRC_INACTIVE) or SRS transmission in RRC_INACTIVE is configured
H909 | Huawei (YinghaoGuo) | POS | 1 |  | PropAgree |  | v061 | Should be Positioning SRS transmission | Should be Positioning SRS transmission | Right. Pls also note that S208 proposes to move it to RRCRelease. So, this change would be then reflected in RRCRelease. To be implemented in Rapporteur CR. | 5.3.13.6 Cell re-selection or cell selection or L2 U2N relay (re)selection while T390, T319 or T302 is running or SDT procedure is ongoing (UE in RRC_INACTIVE) or SRS transmission in RRC_INACTIVE is configured
H910 | Huawei (YinghaoGuo) | POS | 1 |  | PropAgree |  | v061 | Perform SL-PRS reception/measurement | Perform SL-PRS reception/measurement | Already implemented in running CR | 5.8.3.2 Initiation
H911 | Huawei (YinghaoGuo) | POS | 1 |  | PartlyAgree |  | v061 | Should be both SIB12 and SIB23?? | Should be both SIB12 and SIB23?? | It can be and/or; since it can also work with SIB23 with dedicated resource pool or can work with shared reposurce pool SIB12. We can check this further next week. | 5.8.18.2 NR sidelink positioning measurement
O800 | <OPPO (Yang Liu)> | POS | 1 | None | PropDisagree |  |  | Have we made agreement that sl-RxPool and/or sl-PRS-RxPool should be only included in handover message but not other RRC dedicated message? | delete ‘with reconfigurationWithSync (i.e. handover)’ | This is same as legacy SL communication. We have said we will reuse legacy SL framework where applicable. | 5.8.18.2 NR sidelink positioning measurement
E138 | Ericsson (Ritesh Shreevastav) | POS | 1 | R2-24xxxxx | ToDoOld |  |  | This statement is explaining the field behaviour of GNSS-ID. In fact the field setting of GNSS-ID should be fixed not that of SBAS-ID. | Update GNSS-ID field description to reflect corresponding settings of SBAS field value. | Lenovo (Hyung-Nam): Disagree. There is no technical issue with the current description. Furthermore, it’s a legacy issue. The concerned statement was introduced in R16. Rapporteur: Agree that this should be corrected from Rel-16 or at least the correction should be discussed for technical merit | – DedicatedSIBRequest
S210 | Samsung (Taeseop) | POS | 1 | R2-24xxxxx | PropAgree |  | v023 | Need to support up to 32 combination of aggregated positioning SRS resource sets. | According to the LS from RAN1 (R1-2401708), RRC ASN.1 should be updated to support up to 32 combinations of aggregated positioning SRS resource sets. TP will be provided by our contribution at this meeting. | in the CR R2-2401632 taht we submitted, the maxNrOfLinkedSRS-PosResourceSet-r18 INTEGER ::= 32 -- Maximum number of linked SRSPosResourceSets that can be aggregated across CCs. However, it appears during CR implementation, this was missed. It can be updated in rapporteur CR | – RRCReconfiguration
H913 | Huawei (YinghaoGuo) | POS | 1 |  | PropDisagree |  | v061 | on the field srs-PosHyperSFN-Index, Previous RAN1 agreeement was that the hyper SFN either with odd or even needs to be carried in the RRC message?? | Previous RAN1 agreeement was that the hyper SFN either with odd or even needs to be carried in the RRC message?? | Yes, we had added here previously but then companies commented that no need to duplicate it. Add it only for SRS-PosResource since it is used to transmit SRS with periodicty longer than 1-HSFN | – RRCRelease
H912 | Huawei (YinghaoGuo) | POS | 1 |  | PropAgree |  | v061 | there is no validity area configuration in SRS-posRRC_INACTIVE_v1800. Validity area cannot be configured for the case when SRS with validty area is not preconfigured. | Add validity area configuration to SRS-PosRRC-inactive-v1800 | To be implemented in Rapporteur CR | – RRCRelease
H924 | Huawei (YinghaoGuo) | POS | 1 | R2-2402468 | ToDo |  | v092 | there is no need to configure TA configuratio for each validity area. A single TA configuration would be fine | Move the TA configuration to SRS-posRRC-INACTIVE-v1800 | We can discuss this | – RRCRelease
I110 | Intel (Sudeep) | POS | 2 | None | PropAgree |  | V71 | As the IE SRS-PosRRC-InactiveValidityAreaConfig-r18 is an element of a non-toAddMod list, there is no delta configuration for the list elements. The list entries are always fully replaced when signalled the next time. Hence using setupRelease for these fields is not recommended. | Replace setupRelease for this and next two fields and use Need R. | Lenovo (Hyung-Nam): Agree, see also B011. Rapporteur: This is already implemented | – RRCRelease
X041 | Xiaomi (Xiaowei) | POS | 1 |  | ToDo |  |  | Similar to UAI based SL-PRS resource configuration, the bandwidth should also be indicated | To include bandwidth IE in the SL-PRS-QoS-Info-r18 | This can be discussed | – SidelinkUEInformationNR
I166 | Yi Guo (Intel) | POS | 1 | R2-2402417 | PropAgree |  |  | Based on SLPP specification, server provides DelayBudget and priority to Tx UE. Therefore the RRC layer of Tx UE obtains these two parameters from upper layers. | update the field description of sl-PRS-DelayBudget as “Indicates the SL-PRS delay budget provided by upper layers (see TS 38.355 [77).”. | To be implemented in Rapporteur CR | – SidelinkUEInformationNR
I167 | Yi Guo (Intel) | POS | 1 | R2-2402417 | PropAgree |  |  | Based on SLPP specification, server provides DelayBudget and priority to Tx UE. Therefore the RRC layer of Tx UE obtains these two parameters from upper layers. | update the field description of sl-PRS-Priority as “Indicates the priority of SL-PRS provided by upper layers (see TS 38.355 [77).”. | To be implemented in Rapporteur CR | – SidelinkUEInformationNR
H914 | Huawei (YinghaoGuo) | POS | 1 | R2-2402468 | ToDo |  | v061 | Priority and delay budget do not need to be carried in the UAI anymore. The UE can sned this information to the network by the SUI message. | as above | We can discuss this | – UEAssistanceInformation
I168 | Yi Guo (Intel) | POS | 1 | R2-2402417 | PropAgree |  |  | Based on SLPP specification, server provides DelayBudget, priority and Bandwidth to Tx UE. Therefore the RRC layer of Tx UE obtains these two parameters from upper layers | Remove the EN “Editor's Note: sl-PRS-Priority and sl-PRS-DelayBudgetis FFS.” | To be implemented in Rapporteur CR | – UEAssistanceInformation
I171 | Yi Guo (Intel) | POS | 1 | R2-2402417 | PropAgree |  |  | Based on SLPP specification, server provides DelayBudget, priority and Bandwidth to Tx UE. Therefore the RRC layer of Tx UE obtains these two parameters from upper layers. | update the field description of sl-PRS-BW as “sl-PRS-Bandwidth Indicates the desired bandwidth of the requested SL-PRS resources provided by upper layers (see TS 38.355 [77) in the unit of MHz. ”. | To be implemented in Rapporteur CR | – UEAssistanceInformation
I169 | Yi Guo (Intel) | POS | 1 | R2-2402417 | PropAgree |  |  | Based on SLPP specification, server provides DelayBudget, priority and Bandwidth to Tx UE. Therefore the RRC layer of Tx UE obtains these two parameters from upper layers. | update the field description of sl-PRS-DelayBudget as “Indicates the SL-PRS delay budget provided by upper layers (see TS 38.355 [77).”. | To be implemented in Rapporteur CR | – UEAssistanceInformation
I170 | Yi Guo (Intel) | POS | 1 | R2-2402417 | PropAgree |  |  | Based on SLPP specification, server provides DelayBudget, priority and Bandwidth to Tx UE. Therefore the RRC layer of Tx UE obtains these two parameters from upper layers. | update the field description of sl-PRS-Priority as “Indicates the priority of SL-PRS provided by upper layers (see TS 38.355 [77).”. | To be implemented in Rapporteur CR | – UEAssistanceInformation
O320 | OPPO (Qianxi Lu) | MULTI, Pos, UAV, SL | 1 | R2-xxxxxx | PropDisagree |  | Q2-v003 | It is not clear whether the SL-Pos can be co-configured with A2X and SL-U or not, we will raise a DP to discuss this issue. | R2 discuss this issue to decide whether the co-configuration of SL Pos and A2X and SL-U are allowed. | SL-U is not support with SL-Positioning. It is outside of WID (Rel-18 scope) | – SIB23
O310 | OPPO (Qianxi Lu) | Pos, SL, SLrelay, MULTI | 2 | R2-24xxxx | PropAgree |  | v95 | Previously, R2 did not include two SIBs with the same IE definition, now here we have SIB12 and SIB23 here. It is not clear whether the two SIBs 1) aim at different IEs, or 2) there might be overlapping IEs in-between. And in case of 1) good to separate the IEs out using a different structure, and in case of 2), whether the two SIBs tend to give different/same values for the overlapping IEs. If different values, what is the reason, and if same values, what is the benefit to do duplicate configuration? (the overhead issue is obvious by seeing B012 request to do segmentaion operation like SIB12). | We will bring a paper for R2 to further discuss the motivation to have a separate SIB via same IE. | Already implemented in running CR | – SIB23
H915 | Huawei (YinghaoGuo) | POS | 1 |  | PropAgree |  | v061 | Should be SI message rather than SIB mesage | as above | To be implemented in Rapporteur CR | – SIB23
H916 | Huawei (YinghaoGuo) | POS | 2 | R2-2402468 | PropAgree |  | v061 | Can include this in the non-critical extension of periodic and semi-persisitent | move this under the field periodic-r16 and semi-persisitent? | it is not as such essential but can be considered | – SRS-Config
H917 | Huawei (YinghaoGuo) | POS | 1 |  | PropAgree |  | v061 | The field should be used for whether the SRS is transmitted in the even or odd hyper frame | change the field description accoridngly | I agree some ploishing is needed. The field description as per RAN1 parameter list:Indicates hyper SFN information in which the positioning SRS is transmitted for the periodicity value of 20480ms. • The value range is {0, 1} to indicate even or odd hyper SFN. • The parameter is absent when the periodicity of positioning SRS is less than or equal to 10240ms. | – SRS-Config
H110 | Huawei (Rama Kumar) | POS | 1 | None | PartlyAgree |  |  | Update the field decription to reflect the RAN1-116 conclusion “The network may configure positioning SRS outside the active UL BWP with Tx hopping configured with the number of hops equal to 1.” | Provides the SRS Configuration to be used for frequency hopping. The network may configure positioning SRS outside the active UL BWP with Tx hopping configured with the number of hops equal to 1. | In such case, we should update the ASN.1 from 1 to 6 rather than updating the field description. In the next change, we will udoate the value range from INTEGER (2..6) to INTEGER (1..6) | – SRS-PosTx-Hopping
H918 | Huawei (YinghaoGuo) | POS | 1 |  | PropDisagree |  | v061 | Can give a reference to the MAC spec | as above | It should be RAN1 spec reference that shoudl be added andhas been done in latest CR submitted to this meeting | – SRS-PosTx-Hopping
H919 | Huawei (YinghaoGuo) | POS | 1 | R2-2402468 | PropAgree |  | v061 | Just need to use the Serving cell index to link to the cell configuration for RRC_CONNECCTED, same as ul-bwp-ID For RRC_INACTIVE, the field is needed | as above | Yes, it looks bit clean rather thean having condition | – SRS-PosResourceSetLinkedForAggBW
O318 | OPPO (Qianxi Lu) | MULTI, SL, Pos | 2 | None | PropAgree |  | Q2-v003 | sl-TriggerConditionRequest has already been included in SL-InterUE-CoordinationConfig, seems no need to re-introduce the parameter | remove this r18 field which is duplicated with legacy field. | Yes, we can remove this as legacy field description has been updated to include both data and SL-PRS | – SL-ResourcePool
H922 | Huawei (YinghaoGuo) | POS | 1 |  | PropDisagree |  | v061 | it might be OK just to extend the legacy type PosSIB-ReqInfo-r16 into an IE and reuse it here | change per above | Lenovo (Hyung-Nam): Disagree. Using legacy type PosSIB-ReqInfo-r16 creates signaling overhead since posSibType-r16 IE contains values which have been added after the extension marker. Rapporteur: Agree with Lenovo | – RemoteUEInformationSidelink
O311 | OPPO (Qianxi Lu) | Pos, SL, SLrelay, MULTI | 2 | R2-24xxxx | PropAgree |  | v95 | Previously, R2 did not include two SIBs /Preconfigurations with the same IE definition, now here we have SIB12 and SIB23 here, and SL-PreconfigurationNR and SL-PosPreconfigurationNR . It is not clear whether the two SIBs/Preconfigurations 1) aim at different IEs, or 2) there might be overlapping IEs in-between. And in case of 1) good to separate the IEs out using a different structure, and in case of 2), whether the two SIBs tend to give different/same values for the overlapping IEs. If different values, what is the reason, and if same values, what is the benefit to do duplicate configuration? (the overhead issue is obvious by seeing B012 request to do segmentaion operation like SIB12). | We will bring a paper for R2 to further discuss the motivation to have a separate Preconfiguration although the included IE is the same | This is resolved in last meeting | – SL-PreconfigurationNR
H921 | Huawei (YinghaoGuo) | POS | 1 |  | PropAgree |  | v061 | Should clarify that it is for the configuration of SL-PRS dedicated resource pool | as above | To be implemented in Rapporteur CR | – SL-PreconfigurationNR
S209 | Samsung (Taeseop) | POS | 1 | R2-24xxxxx | PropDisagree |  | v023 | Need of including SRS pre-configuration (i.e., srs-PosRRC-InactiveValidityAreaPreConfigList-r18) in HandoverPreparationInformation message. | With the current specification, the SRS pre-configuration (i.e., srs-PosRRC-InactiveValidityAreaPreConfigList-r18) is not included in HandoverPreparationInformation message, which can make the R18 SRS pre-configuration feature not workable. Specifically, when the UE reselects a new cell and sends RRC Resume message with the new resume cause for activation of pre-configured SRS, the new serving cell should be aware of whether the UE has any valid SRS pre-configuration in the cell. Otherwise, the gNB may not understand the intention correctly and initiate the procedure for new SRS configuration instead of activation, which makes R18 SRS pre-configuration feature useless. This is because the same resume cause (srs-PosConfigOrActivationReq) is defined to be used for the two different purpose (i.e., request for activation of pre-configured SRS or request for new SRS configuration). To resolve the issue above, the SRS pre-configuration (i.e., srs-PosRRC-InactiveValidityAreaPreConfigList-r18) should be included in AS-Config in HandoverPreparationInformation message as like sdt-Config-r17. TP will be provided by our contribution at this meeting. | This appears more an ehancement than the correction. It may also have RAN3 impact. It should be discussed seperately and not as RIL. | – HandoverPreparationInformation
B021 | Lenovo (Hyung-Nam) | PosRemoteUE | 2 | None | PropAgree |  | v067 | In posSibType-r18 IE the value “posSibType2-17a” is missing. Furthermore, 9 spare values can be added before the extension marker. | Add the missing value “posSibType2-17a” and 9 spare values in posSibType-r18 IE. | To be implemented in Remote UE Rapporteur CR