## Combined_Tables
RIL Id | WI | Class | Title | Tdoc | Delegate | Misc | File version | Status | Rapportaur comments
V220 | IoTTDD | 1 | Refine the sentence for the postponement of SI transmission |  | vivo (Stephen) |  | v004 | PropAgree | This was discussed during the last review, and the understanding was that “one repetition” means the first transmission. But since there is still concern, it is OK to revise based on this proposal with a little update: For IoT NTN TDD mode, either the first SI message transmission or the one or more repetitions of SI message transmission, that falling on the non-D subframes are postponed to the next valid D subframe within the SI-Window.
X501 | IoTTDD | 2 | radioFrameOffset | R2-xxxxxxx | Xiaomi (Xiaolong Li) |  | V002 | ToDo | I have some sympathy with this proposal. But since the agreement from last meeting was specific about indicating this in SIB33. If we change it, we need further discussion. So I suggest Xiaomi to bring a contritbuion on this issue to the next meeting.
V221 | IoTTDD | 1 | Change Need code of radioFrameOffset-r19 |  | vivo (Stephen) |  | v004 | PropAgree | Agree.
Z051 | IoTTDD | 2 | Change the value of radioFrameOffset-r19 |  | ZTE (Zhihong) |  | v005 | PropAgree | Agree. No need of contribution unless there is a different view. Qualcomm: We suggest to change it to “ToDo”. It should be possible to signale only positive offset of same SFN0 of serving and SFN0 of the target. Rapporteur’s comment: To qualcommon: it doesn’t really matter right? Both ways work. Suggest to focus on more important issues.
Z052 | IoTTDD | 1 | Update the field description of radioFrameOffset-r19 |  | ZTE (Zhihong) |  | v005 | PropAgree | Agree. No need of contribution unless there is a different view. Qualcomm: Additionally we should clarify it is “in number of radio frames”, it is not subframe. Perhaps naming can also be reconsidered to avoid confusion with existing si-RadioFrameOffset. Rapporteur’s comment: OK with QC’s suggestion.
Z053 | IoTTDD | 1 | Update the field description of downlinkBitmapNonAnchor in CarrierConfigDedicated-NB |  | ZTE (Zhihong) |  | v005 | PropAgree | Agree.
Z054 | IoTTDD | 1 | Update the field description of downlinkBitmapNonAnchor in DL-CarrierConfigCommon-NB |  | ZTE (Zhihong) |  | v005 | PropAgree | Agree. But the wording will be updated to follow legacy: For IoT NTN TDD mode, if this field is signalled, this field is set to useNoBitmap-r16 is used.
N021 | IoTTDD |  | Update the field description for npdcch-StartSF-xx |  | Nokia (Ping Yuan) |  | V008 | PropAgree | Agree. Will update all related places. Qualcomm: I guess intention is value 4 is possible for normal mode but it should never be configured for TDD mode. Perhaps we need to be more clear, instead of saying interpreted, should use better wording like it corresponds to “4*11.25” subframes. Suggest to change, value v1dot5 corresponds to 1.5, value v2 corresponds to 2, value v4 corresponds to 4 and so on. For IoT NTN TDD mode, value v4 corresponds to 4*11.2” and value v8 corresponds to 8*11.25. Rapporteur’s comment: OK with QC’s suggestion.
N022 | IoTTDD |  | Update the field description for npusch-TxDuration to reflect RAN1 agreement |  | Nokia (Ping Yuan) |  | V008 | ProReject | Based on the lasest RAN4 LS to RAN1 in R4-2512550, RAN1 may need to re-discuss whether to support segmented precompensation in IoT NTN TDD. So we don’t need to make a change now in RAN2. Besides it may be enough if RAN1 has captured the agreement in RAN1 spec since we refer to RAN1 spec already. Qualcomm: Suggest to change to “ToDo”. It is perhaps better to clarify this filed is not applicable in IoT NTN TDD mode as UE restarts every 8ms. Rapporteur’s comment: Let’s wait for RAN1 conclusion for now.