## Slide 1: SA WG3 Status report for FS_Ranging_SL_Sec
Wei Lu
Xiaomi

## Slide 2
August meeting:
  Agreed on a new key issue for Protection of Direct Communication
October meeting:
  Added/updated key issues, based on the progress after SA2’s August meeting
  Started to add solutions for key issues
November meeting:
  Updated KI#2 and KI#4 to be aligned with SA2 conclusion
  Updated existing solutions (sol#1, sol#2) and added new solutions for KI#1 & KI#4
January meeting:
  Added new key issue (KI#5)
  Updated existing solutions and added new solutions
February meeting:
  Updated solutions and added new solutions
  Added conclusions for KI#2 and KI#3
  WID approved
April meeting:
  Continued the update of solutions and added new solutions
  Updated and added conclusions
  Started normative work
May meeting:
  Completed all conclusions (except KI#5) and finalized the study
  Continued with the normative work
August meeting:
  Finalize the normative work
Overall plan
FS_Ranging_SL_Sec Status
Notes: Key issues added during June and August meetings should be concluded in November.
(e.g. Resolve the ENs in the agreed key issues)

## Slide 3
General
  TR 33.893 v1.0.0 contains 5 key issues, 29 solutions and conclusions on 4 key issues.
Dependencies:
  Dependencies on SA2 and RAN2 have been recorded in the conclusions
FS_Ranging_SL_Sec status after SA3#111
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960036 | Study on Security Aspects of Ranging Based Services and Sidelink Positioning | FS_Ranging_SL_Sec | Rel-18 | S3 | Q2-2023 | 70% | 100% | TR 33.893

## Slide 4
Key Issues | Solutions | Conclusions
Privacy protection for Ranging/SL Positioning services | 11 solutions | Done
Authorization for Ranging/Sidelink Positioning Service | 8 solutions | Done
Protection of discovery procedure | 4 solutions | Done
Protection of direct communication | 5 solutions | Done
Protection of groupcast/broadcast | 10 solutions | To be made during normative work
TR 33.893 Summary
FS_Ranging_SL_Sec Status

## Slide 5: FS_Ranging_SL_SEC status after SA3#111
  SA2/RAN impacts and dependencies:
  Dependencies on SA2 TS final status
  RAN2 progress on SLPP broadcast/groupcast
Contentious Issue:
  KI #2: Whether the authorization is based on the existing UE LCS privacy profile in UDM or whether it is new data or profile is to be decided in normative work, and needs to be coordinated with SA2.
  KI #3: Whether the DCR message of V2X capable UEs needs to be protected is to be determined during normative work based on the DCR information defined by SA2 and RAN2.
  KI #5: Conclusions are to be made during normative work based on the progress in RAN2.
Overall Plan:
  See slide #2
Risks:
  None