## Slide 1
SA WG3 Status report for FS_eNA_SEC_Ph3
Chang Liu
China Mobile

## Slide 2
The TR has 6 key issues ,21 solutions and 6 conclusions.
November meeting:
  Solution completion(including evaluation and solving ENs)
  Add 5 solutions.
January meeting
  Last meeting to add solutions to the existing key issues.
  Add conclusions
February meeting(SA3 #110):
  Add conclusions and solution completion
  Send TR for information
  WID proposal
April meeting(SA3 #110adhoc-e):
  Complete conclusions and solution evaluation
  start normative work
May meeting:(SA3 #111)
  Send TR for approval
  Normative work
August meeting(SA3 #112)
  Finalize normative work
  Clean up for TR
Overall plan
FS_eNA_SEC_PH3 Status

## Slide 3: FS_eNA_SEC_Ph3 status after SA3#111
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
950021 | Study on security aspects of enablers for Network Automation for 5G - phase 3 | FS_eNA_SEC_Ph3 | Rel-18 | S3 | June-2023 | 80% | 95% | Conclusions update
General
  TR 33.738 v0.6.0 contains 6 key issues ,21 solutions and 6 conclusions.
Dependencies:
  None
Contentious Issue:
  None
Focus for the Next Meeting :
  Clean up