## Slide 1: SA WG3 Status report for CryptoSP
Mohsin Khan
Ericsson

## Slide 2
TUs planned
WT1: 1 TU (0.25 TU in each meeting cycle)
WT2 and WT3: 1 TU (0.25 TU in each meeting cycle)
Total TU estimates: 2 TU (4 meeting cycles)
In SA3#115 meeting
  Collect the proposed changes in Draft CRs
In SA3#115Adhoc-e meeting
  Collect the proposed changes in Draft CRs
In SA3#116 meeting
  Collect the proposed changes in Draft CRs
In SA3#117 meeting
  Convert the draft CRs into regular CRs and endorse the regular CRs
In SA3#118 meeting
  Discuss changes (only for the changes that remove algorithms and protocols) that are already endorsed but may have serious impact if implemented and update endorsed CRs only if necessary.
In SA3#119 meeting
  Agree the Endorsed CRs
Overall plan
CryptoSP overall plan

## Slide 3
General
    What happened at SA3#116:
      Seems changes for the IKEv2 profile are now stable
      TLS profile is updated with the use of RFC 9325, 9112, 9113
      Introduction of HMAC-SHA2-256-128 as a negotiation candidate for integrity protection between UE and P-CSCF
    Focus for the Next Meeting :
      Finalizing all the changes related to TLS profile.
      Deprecating the broken use of aes-gcm and aes-gmac in TS 33.203
      Converting the draft CRs into regular CRs and endorse the regular CRs
Dependencies:
  None
Contentious Issue:
  None
Risks:
  None identified
CryptoSP status after SA3#116
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1020042 | 3GPP profiles for cryptographic algorithms and security protocols | CryptoSP | Rel-19 | S3 | Dec 2024 | 20% | 50% | Draft CR S3-242664 Draft CR S3-242665 Draft CR S3-241770 Draft CR S3-242531

## Slide 4
Pending issues
  Finalizing changes in the TLS profile
  Deprecating borken use of aes-gcm and aes-gmac
Dependencies:
  Work based on other WGs study outcomes
TUs consumed
  SA3#115: 0.5
  SA3#115Adhoc-e: 0.5
  SA3#116: 0.5
TUs remaining
  SA3#117 – 0.5
  SA3#118 – 0.5 (will most probably not be needed)
  SA3#119 – 0.5
Plan for completion
  Work item will complete in SA3#119
  The work item is taking 0.5 TU longer than initially planned. The reason is that in SA3#115, a DP was endorsed in which it was agreed that the draft CRs will be converted into regular CRs and be endorsed in SA3#117, left for discussion for one meeting cycle, i.e., SA3#118, and be finally agreed in SA3#119
CryptoSP pending work and plan for completion