## Slide 1: SA WG3 Status report for FS_Ranging_SL_Sec
Wei Lu
Xiaomi

## Slide 2
August meeting:
  Agreed on a new key issue for Protection of Direct Communication
  Start to add solutions for key issues (but blocked due to dependency on SA2 conclusion)
October meeting:
  Last meeting to add/update key issues, based on the progress after SA2’s August meeting
  Start to add solutions for key issues
November meeting:
  Add solutions for key issues and update existing solutions as needed
  Start to add solution evaluations
  WID proposal for discussion
January/February meeting:
  Last meeting to add new solutions and update existing solutions as needed
  Add solution evaluations
  Add conclusions for key issues
  Agree on WID
April meeting:
  Start normative work
May meeting:
  Finalize normative work
Overall plan
FS_Ranging_SL_Sec Status
Notes: Key issues added during June and August meetings should be concluded in November.
(e.g. Resolve the ENs in the agreed key issues)

## Slide 3
Key Issues | Solutions | Solution status
Privacy protection for Ranging/SL Positioning services | None | 
Authorization for Ranging/Sidelink Positioning Service | None | 
Protection of discovery procedure | None | 
Protection of direct communication | None | 
TR 33.893 Summary
FS_Ranging_SL_Sec Status
SA3#108
Aug 22-26, 2022
Four Key Issues
No solution
SA3#108 Adhoc-e Oct 10-14, 2022
Deadline to introduce new Key Issues
New solutions
SA3#109
Nov 14-18, 2022
Solution evaluations
WID approval
SA3#107 Adhoc-3 Jun27-July1st 2022
Three Key Issues

## Slide 4
General
  TR 33.893 v0.2.0 contains the scope and four key issues
Dependencies:
  SA2 work after Aug. (#152e): TR 23.700-86 v0.4.0, completion rate 70%
  Next SA2 meeting Oct. (#153e): Start Evaluation & Conclusions
  Target date of SA2 work: Jan, 2023
FS_Ranging_SL_Sec status after SA3#108e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960036 | Study on Security Aspects of Ranging Based Services and Sidelink Positioning | FS_Ranging_SL_Sec | Rel-18 | S3 | Mar-2023 | 10% | 20% | TR 33.893

## Slide 5: FS_Ranging_SL_SEC status after SA3#108e
  SA2/RAN impacts and dependencies:
  None for RAN
  Dependencies on SA2 progress for SA3 solution development
Contentious Issue:
  Whether SA3 has to wait for SA2 conclusion before proposing solutions ?
Focus for the Next Meeting (Oct.):
  Add further key issues based on the latest status of SA2 work
  Add solutions for the agreed key issues (SA2 conclusion not available by Oct. meeting)
Overall Plan:
  See slide #2
Risks:
  SA3 timeline delay due to SA2 work delay on Ranging
    no time slot for Ranging study in SA2 Nov. meeting
    SA2 work to be concluded in SA2 Jan. meeting