## Slide 1: SA WG3 Status report for FS_USIA
Andreas Kunz
Lenovo

## Slide 2
October meeting:
  Last meeting to add new key issues
  Add solutions and solution evaluations
  Add attack model and actor description
November meeting:
  Last meeting to add new solutions
  Solution evaluations
  Conclusions. Key issues added during June and August meetings should be concluded in November.
  Agree on WID with first set of objectives
  Send TR 33.892 for information
January/February meeting:
  Start normative work.
  Conclusions for key issues added in October.
  Last meeting for extending WID objectives
  Send TR 33.892 for approval
April meeting:
  Normative work
May meeting:
  Finalize normative work
Overall plan
FS_USIA Status

## Slide 3
Key Issues | Solutions | Solution status
Determination of application identification | Provide additional authentication information to enhance URSP policy enforcement. | Evaluation TBD
Determination of application identification | Solution on enhancing the URSP rule with certificate fingerprint | Evaluation TBD
TR 33.892 Summary
FS_USIA Status
SA3#107 Adhoc-3 Jun27-July1st 2022
Key Issues
SA3#108
Aug 22-26, 2022
Key Issues and Solution proposals
SA3#108 Adhoc-e Oct 10-14, 2022
Deadline to introduce new Key Issues
SA3#109
Nov 14-18, 2022
Conclusions

## Slide 4
General
  TR 33.892 v0.1.0 contains one key issue (Determination of application identification)
  Scope and two new solutions were agreed
Dependencies:
  None
FS_USIA status after SA3#107Adhoc-e
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
960035 | Study on URSP rules to securely identify applications | FS_USIA | Rel-18 | S3 | Mar-2023 | 10% | 30% | TR 33.892

## Slide 5: FS_USIA status after SA3#107Adhoc-e
Contentious Issue:
  Attack model and actors as well as KI#1 requirement were not agreed at SA3#107adhoc-e
Focus for the Next Meeting (August):
  Agree on attack model and actors
  Add potential security requirement to KI#1.
  Add further key issues based on SID objective
  Add further solutions for key issue on determination of application identification
Overall Plan:
  See dedicated slide
Risks:
  Tight schedule if not scheduled on the agenda in upcoming meetings