## Slide 1: SA WG3 Status report for ‘FS_CAPIF_Ph4_SEC’
Weiyin Zhang (Chinatelecom)

## Slide 2
TUs planned
In SA3#124 meeting:
  Progressed aspects: Scope, architecture and 4 key issues
In SA3#125 meeting:
  Progressed aspects: Solutions to KI#1,2,3
In SA3#126 meeting:
  Progressed aspects: Solutions update, evaluation, KI#4 update
In SA3#127 (upcoming) meeting:
  Focus to achieve: Solution evaluation and conclusion, Initiate WID
  In SA3#128 meeting:
  Send TR for Info/Approval
Overall plan
‘FS_CAPIF_Ph4_SEC’ overall plan
Work Task ID | TU Estimate (Study) | TU Estimate (Normative) | RAN/SA2 Dependency (Yes/No/Maybe) | Inter Work Tasks Dependency
 | 2 | 1 |  | 

## Slide 3
General
  TR 33.700-23 v0.3.0 contains the following aspects:
    High-level architectures;
    4 Kye issues;
    11 Solutions;
    1 conclusion
Dependencies:
  None
Contentious Issues:
  None.
Risks:
  None
‘‘FS_CAPIF_Ph4_SEC‘‘ status after SA3#126
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1090023 | Study on Security aspects of CAPIF Phase 4 | ‘FS_CAPIF_Ph4_SEC’ | Rel-20 | S3 | Dec-2026 | 50% | 70% | TR 33.700-23

## Slide 4
TUs consumed
  SA3#124 - 0.5 TU
  SA3#125 – 0.5 TU
  SA3#126 – 0.5 TU
TUs remaining
  Study: 0.5 TU
  Normative: 1 TU
TUs to be requested for the upcoming meeting
  0.25 TUs
Plan for completion
  Planned to close the study by SA3#128
‘‘FS_CAPIF_Ph4_SEC‘‘ status after SA3#126