## Slide 1: SA WG3 Status report for ‘FS_PLMNNPN_Ph2’
Jun Shen (China Telecom)
Yuze Liu (ZTE)

## Slide 2
TUs planned
In SA3#124 meeting:
  2 KIs and evaluation for SBA interface protection agreed
In SA3#125 meeting:
  Was not included in agenda as offline discussion was needed
In SA3#126 meeting:
  Solution and conclusion for KI#2 agreed
In SA3#127 (upcoming) meeting:
  Request to be part of the agenda
  Open for solution and conclusion for KI#1
Overall plan
‘FS_PLMNNPN_Ph2’ overall plan
Work Task ID | TU Estimate (Study) | TU Estimate (Normative) | RAN/SA2 Dependency (Yes/No/Maybe) | Inter Work Tasks Dependency
WT1&2 | 2 | 1 | No | NA

## Slide 3
General
  TR 33.758 v0.2.0 currently includes 2 KIs, 1 solution, 1 conclusion, and evaluation for SBA interface protection of the study.
Dependencies:
  None
Contentious Issues:
  None.
Risks:
  None
‘‘FS_PLMNNPN_Ph2‘‘ status after SA3#126
UID | Name | Acronym | Rel | WG | Target | Old % | New % | Change or comment
1090017 | Study on security for PLMN hosting a NPN phase 2 | ‘FS_PLMNNPN_Ph2’ | Rel-20 | S3 | Jun-2026 | 35% | 75% | -

## Slide 4
Pending issues
  Solutions and conclusion to KI#1
Dependencies:
  None
TUs consumed
  SA3#124 - 0.5 TU
  SA3#125 - None
  SA3#126 - 0.5 TU
TUs remaining
  2 TUs
TUs to be requested for the upcoming meeting
  0.5 TUs
Plan for completion
  Planned to close the study by SA3#127/SA3#128
‘‘FS_PLMNNPN_Ph2‘‘ pending work and plan for completion