## Slide 1
Peilin Liu, ZTE
SA WG3 Status report for
FS_NR_Femto_SEC_Ph2

## Slide 2: 5G-A/6G SID: FS_NR_Femto_SEC_Ph2
Progress since SA3#125
  TR 33.746 v0.4.0 contains 5 key issues and 10 solutions.
  Clause 7: 4 key issues were concluded.
  WID proposal was approved in SA3#126.
Impacts and dependencies on other WGs
  None
Outstanding issues
  None
Contentious issues
  None
Next steps (plan for next meeting)
  Evaluation updates.
  Finalizing conclusions.
UID | Name | Acronym | Target for approval | Old % | WID | New % | Change or comment
1090030 | New SID on Security Aspect for NR Femto Phase 2 | FS_NR_Femto_SEC_Ph2 | May 2026 | 40% | SP-251249 | 60% | +20%

## Slide 3
TU planned
TUs consumed : 1.25 TUs (till date)
TUs remaining :
  Study: 0.75 TUs
  Normative: 1 TUs
TUs to be requested for the upcoming meeting : 0.5 TUs
Plan for completion
  Planned to close the study by SA3#128
Work Task ID | TU Estimate (Study) | TU Estimate (Normative) | RAN/SA2 Dependency (Yes/No/Maybe) | Inter Work Tasks Dependency
WT1 | 1 | 0.5 | No | No
WT2 | 1 | 0.5 | No | No
5G-A/6G SID: FS_NR_Femto_SEC_Ph2

## Slide 4
Highlights (if any)
  ……..
5G-A/6G SID: FS_NR_Femto_SEC_Ph2

## Slide 5: Thank You !