{"text_format":"1","workbook":"xlsx","n_sheets":1,"sheets":["Work_plan_3gpp_250306"],"not_rendered":{"charts":0,"images":0,"macros":1,"external_links":0,"defined_names":1,"comments":0,"pivot_tables":0},"unopened":[],"bounds":{"document_bytes":16777216,"sheet_cells":100000,"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0,"cell_chars":16384,"cell_head_chars":4096},"cells_cut":0,"cells_raw":0,"read":"whole","date_system":"1900"}

{"sheet":"Work_plan_3gpp_250306","index":0,"n_rows":9269,"n_cols":22,"rows_kept":4500,"cut":true,"hidden":false,"merged":[],"bounds":{"rows_first":2000,"rows_last":500,"rows_between":2000,"halvings":0}}
["ID","Unique_ID","Name","Acronym","OutlineLevel","Release","ResourceNames","Start","Finish","%Complete","Hyperlink","Status Report","WI rapporteur name","WI rapporteur e-mail","Notes","Impacted TSs and TRs","TSG approved","PCG approved","TSG stopped","PCG stopped","Created","last modif"]
[1,0,"Work Plan 3GPP version July 18th 2025",null,1,"Rel-20",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2015-01-15","2015-03-05"]
[2,0,"Post TSG#108 version",null,1,"Rel-20",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2018-03-15","NA"]
[3,0,"Next main milestones: Rel-19 St.3: Sept.25",null,1,"Rel-20",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2015-08-12","NA"]
[4,0,null,null,1,"Rel-20",null,"2019-03-07","2019-03-07",0,null,null,null,null,null,null,null,null,null,null,"2017-03-03","NA"]
[5,0,"--- RELEASE 20 ---","-",1,"Rel-20",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[6,0,"Rel-20 6G Studies","-",1,"Rel-20",null,"Tue 02/04/24","Thu 11/06/26",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[7,1050110,"Study on 6G Use Cases and Service Requirements ","FS_6G_REQ",1,"Rel-20","S1","Wed 04/09/24","Tue 03/03/26",0.66,"SP-241391",null,"Xiaonan Shi, China Mobile","shixiaonan@chinamobile.com","6/3/25: 0%->25; 5/6/25: 25%->66",null,105,53,null,null,"Wed 04/09/24","Thu 05/06/25"]
[8,1080057,"Study on Architecture for 6G System ","FS_6G_ARC",1,"Rel-20","S2","Thu 05/06/25","Sat 06/06/26",0,"SP-250806",null,"Malla Reddy Sama, NTT DOCOMO","sama@docomolab-euro.com",null,null,108,55,null,null,"Thu 05/06/25","NA"]
[9,1060079,"Study on 6G Scenarios and Requirements ","FS_6G_RAN_Scen_Req",1,"Rel-20","RP","Sun 08/12/24","Fri 05/06/26",0.1,"RP-251395","RP-251396","CMCC ",null,"6/3/25: FCD:01/03/2026->05/06/2026; Compl:0%->5%; Stat Rep: ->RP-250266; ; 26/3/25: 38.914 added;; 3/4/25: WID:RP-243327->RP-250810; 6/6/25: Compl:5%->10%; Stat Rep: RP-250266->RP-251396; List of Impacted TS & TR updated; ; 18/7/25: WID:RP-250810->RP-2513","38,914",106,54,null,null,"Fri 24/01/25","Fri 18/07/25"]
[10,1080064,"Study on Modernization of Specification Format and Procedures for 6G ","FS_6GSpecs",1,"Rel-20","SP","Fri 27/06/25","Tue 03/03/26",0,"SP-250802",null,"Baker, Matthew, Nokia ","matthew.baker@nokia.com ",null,null,108,55,null,null,"Fri 27/06/25","NA"]
[11,1080072,"Study on 6G Radio ","FS_6G_Radio",1,"Rel-20","R1","Fri 06/06/25","Wed 03/03/27",0,"RP-251881",null,"NTT DOCOMO ",null,"TR 38.9xx (RAN; work done in WGs!), TR 38.8xx (RAN1), TR 38.8xx (RAN2), TR 38.8xx (RAN3), TR 38.8xx (RAN4) ; note: SID shows June 27 as target which would be REL-21 so corrected to March 27 ",null,108,55,null,null,"Fri 18/07/25","NA"]
[12,0,"Rel-20 Satellite, Non-Terrestrial Networks (NTN)","-",1,"Rel-20",null,"Thu 07/03/19","Wed 09/06/21",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[13,1080054,"Satellite access - Phase 4","5GSAT_Ph4",1,"Rel-20",null,"Tue 02/04/24","Fri 06/06/25",1,null,null,null,null,null,null,108,55,null,null,"Thu 05/06/25","NA"]
[14,1030042,"   Study on satellite access - Phase 4 ","FS_5GSAT_Ph4",2,"Rel-20","S1","Tue 02/04/24","Thu 12/12/24",1,"SP-241824",null,"Thierry Bérisot, Novamint ","tberisot@novamint.com ","13/6/24: 0%->30; 4/9/24: 30%->60; 8/1/25: WID:SP-240495->SP-241824; 6/3/25: 60%->85; 5/6/25: 85%->100",22.887,103,52,null,null,"Wed 13/03/24","Thu 05/06/25"]
[15,1060071,"   Stage 1 for Satellite access - Phase 4","5GSAT_Ph4-REQ",2,"Rel-20","S1","Thu 05/12/24","Fri 06/06/25",1,"SP-250386",null,"Thierry Bérisot, Novamint, ","tberisot@novamint.com ","; 6/3/25: 0%->60; 26/3/25: WID:SP-241822->SP-250386; 26/3/25: FCD:03/02/2025->/25; 5/6/25: 60%->100",22.260999999999999,106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[16,1070011,"Study on Integration of satellite components in the 5G architecture Phase 4 ","FS_5GSAT_Ph4_ARC",1,"Rel-20","S2","Wed 26/03/25","Fri 12/12/25",0,"SP-250787",null,"Hucheng Wang (CATT) ","wanghucheng@catt.cn ","27/6/25: WID:SP-250400->SP-250787",null,107,54,null,null,"Wed 05/03/25","Fri 27/06/25"]
[17,1050105,"Indirect Network Sharing on Satellite Access Network ","INS_SAT",1,"Rel-20","S1","Wed 04/09/24","Mon 09/09/24",1,"SP-241393",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,22.260999999999999,105,53,null,null,"Wed 04/09/24","NA"]
[18,1060072,"MPS support in 3GPP system with satellite ","MPS_Sat",1,"Rel-20","S1","Thu 05/12/24","Thu 12/12/24",1,"SP-241823",null,"Singh, Ray, Peraton Labs, ","rsingh@peratonlabs.com ","; 5/12/24: 0%->100",22.152999999999999,106,54,null,null,"Thu 05/12/24","Thu 05/12/24"]
[19,1080027,"Study on application enablement for satellite access enabled 5G services Phase 4","FS_5GSAT_Ph4_APP",1,"Rel-20","S6","Thu 05/06/25","Tue 03/03/26",0,"SP-250874",null,"Zhou Zhe, China Telecom, ","zhouz11@chinatelecom.cn ","18/7/25: 23.700-02 added;","23.700-02",108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[20,1080071,"Study on GNSS resilient NR-NTN operation ","FS_NR_NTN_GNSS_resilient",1,"Rel-20","R1","Fri 06/06/25","Sat 06/06/26",0,"RP-251863",null,"Thales ",null,"compare REL-16 SI FS_NR_NTN_solutions, REL-17 WI NR_NTN_solutions, REL-18 WI NR_NTN_enh, REL-19 WI NR_NTN_Ph3 ",null,108,55,null,null,"Fri 18/07/25","NA"]
[21,1070055,"Study on Ultra Low Bitrate Speech Codec ","FS_ULBC",1,"Rel-20","S4","Wed 26/03/25","Sat 06/06/26",0.1,"SP-250635",null,"Xu Jiayi, China Mobile ","xujiayi@chinamobile.com ","3/4/25: 26.940 added;; 5/6/25: 0%->10; 27/6/25: WID:SP-250378->SP-250635",26.94,107,54,null,null,"Wed 05/03/25","Fri 27/06/25"]
[22,1080091,"E-UTRA TN (Terrestrial Network) to NR NTN handover enhancements ","LTE_TN_NR_NTN_HO",1,"Rel-20",null,"Fri 06/06/25","Thu 09/09/27",0,"RP-251878",null,"CATT ",null,"to support RRC connected mode mobility; compare: REL-19 WI LTE_TN_NR_NTN_mob-Core which introduced idle mode mobility ",null,108,55,null,null,"Fri 18/07/25","NA"]
[23,1081091,"   Core part: E-UTRA TN to NR NTN handover enhancements ","LTE_TN_NR_NTN_HO-Core",2,"Rel-20","R2","Fri 06/06/25","Wed 03/03/27",0,"RP-251878",null,"CATT ",null,"to support RRC connected mode mobility; compare: REL-19 WI LTE_TN_NR_NTN_mob-Core which introduced idle mode mobility ",null,108,55,null,null,"Fri 18/07/25","NA"]
[24,1082091,"   Perf. Part: E-UTRA TN to NR NTN handover enhancements ","LTE_TN_NR_NTN_HO-Perf",2,"Rel-20","R4","Fri 06/06/25","Thu 09/09/27",0,"RP-251878",null,"CATT ",null,null,null,108,55,null,null,"Fri 18/07/25","NA"]
[25,1080090,"NTN for IoT Phase 4 ","IoT_NTN_Ph4",1,"Rel-20",null,"Thu 07/03/19","Wed 09/06/21",0,"RP-251867",null,"vivo ",null,"no Perf. part; compare: REL-19 WI IoT_NTN_Ph3, REL-18 WI IoT_NTN_enh, REL-17 WI LTE_NBIOT_eMTC_NTN; enhancement of NB-IoT-NTN to support IMS voice call over GSO ",null,108,55,null,null,"Fri 18/07/25","NA"]
[26,1081090,"   Core part: NTN for IoT Phase 4 ","IoT_NTN_Ph4-Core",2,"Rel-20","R2","Thu 07/03/19","Wed 09/06/21",0,"RP-251867",null,"vivo ",null,"no Perf. part; compare: REL-19 WI IoT_NTN_Ph3, REL-18 WI IoT_NTN_enh, REL-17 WI LTE_NBIOT_eMTC_NTN; enhancement of NB-IoT-NTN to support IMS voice call over GSO ",null,108,55,null,null,"Fri 18/07/25","NA"]
[27,0,"Rel-20 Internet of Things (IoT), Ambient power-enabled IoT (AmbientIoT), RedCap, MTC","-",1,"Rel-20",null,"Sun 05/05/24","Wed 12/12/25",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[28,1080061,"MPS Enhancements for IoT ","MPS_IOT-ARC",1,"Rel-20","S2","Fri 27/06/25","Fri 12/12/25",0,"SP-250842",null,"Hala Mowafy, (Peraton Labs) ","hala.mowafy@peratonlabs.com ",null,"23.401; 23.682 ",108,55,null,null,"Thu 05/06/25","NA"]
[29,1080063,"Study on Architecture support of AmbientIoT - Phase 2 ","FS_AmbientIoT_Ph2_ARC",1,"Rel-20","S2","Thu 05/06/25","Tue 03/03/26",0,"SP-250834",null,"Runze ZHOU, huawei ","zhourunze@huawei.com ",null,null,108,55,null,null,"Thu 05/06/25","NA"]
[30,1080023,"Study on application enablement for Ambient IoT services Phase 2","FS_AmbientIoT_Ph2_APP",1,"Rel-20","S6","Thu 05/06/25","Tue 03/03/26",0,"SP-250870",null,"Liping Wu, CATT ","wuliping@cictmobile.com ","18/7/25: 23.700-26 added;","23.700-26",108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[31,1080073,"Study on enhancements for solutions for Ambient IoT in NR outdoor for active devices ","FS_Ambient_IoT_Outdoor_Active",1,"Rel-20","R1","Thu 07/03/19","Wed 09/06/21",0,"RP-251884",null,"LG Electronics ",null,"affecting TR 38.769 of REL-19 SI FS_Ambient_IoT_solutions ",null,108,55,null,null,"Fri 18/07/25","NA"]
[32,1080086,"Solutions for Ambient IoT in NR Phase 2 ","Ambient_IoT_Solutions_Ph2",1,"Rel-20",null,"Fri 06/06/25","Thu 09/09/27",0,"RP-251885",null,"Huawei ",null,"compare REL-19 WI Ambient_IoT_Solutions; note: There is a parallel REL-20 SI FS_Ambient_IoT_Outdoor_Active (no overlap allowed); SI TR 38.769 must be removed from this WID ",null,108,55,null,null,"Fri 18/07/25","NA"]
[33,1081086,"   Core part: Solutions for Ambient IoT in NR Phase 2 ","Ambient_IoT_Solutions_Ph2-Core",2,"Rel-20","R1","Fri 06/06/25","Wed 03/03/27",0,"RP-251885",null,"Huawei ",null,"compare REL-19 WI Ambient_IoT_Solutions; note: There is a parallel REL-20 SI FS_Ambient_IoT_Outdoor_Active (no overlap allowed); SI TR 38.769 must be removed from this WID ",null,108,55,null,null,"Fri 18/07/25","NA"]
[34,1082086,"   Perf. Part: Solutions for Ambient IoT in NR Phase 2 ","Ambient_IoT_Solutions_Ph2-Perf",2,"Rel-20","R4","Fri 06/06/25","Thu 09/09/27",0,"RP-251885",null,"Huawei ",null,null,null,108,55,null,null,"Fri 18/07/25","NA"]
[35,0,"See also \"NTN for IoT Phase 4\" (UID 1080090)",null,1,"Rel-20",null,"Thu 07/03/19","Thu 07/03/19",0,null,null,null,null,null,null,null,null,null,null,"Fri 18/07/25","NA"]
[36,0,"Rel-20 AIML (Artificial Intelligence/Machine Learning)","-",1,"Rel-20",null,"Tue 02/04/24","Thu 11/06/26",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[37,1070013,"Study on Core Network Enhanced Support for AIML Phase 2 ","FS_AIML_CN_Ph2",1,"Rel-20","S2","Wed 26/03/25","Fri 12/12/25",0,"SP-250810",null,"Xiaobo Wu, vivo ","xiaobo.wu@vivo.com ","27/6/25: WID:SP-250413->SP-250810",null,107,54,null,null,"Wed 05/03/25","Fri 27/06/25"]
[38,1080074,"Study on AIML for NG-RAN Phase 3 ","FS_NR_AIML_NGRAN_Ph3",1,"Rel-20","R3","Fri 06/06/25","Tue 03/03/26",0,"RP-251868",null,"ZTE ",null,"compare REL-17 SI FS_NR_ENDC_data_collect and REL-19 SI FS_NR_AIML_NGRAN_enh; TR 38.7XX ",null,108,55,null,null,"Fri 18/07/25","NA"]
[39,1070029,"Study on Stage 2 for AI/ML service Phase 2 ","FS_AIML_App_Ph2",1,"Rel-20","S6","Wed 26/03/25","Fri 12/12/25",0.4,"SP-250384",null,"Pateromichelakis, Emmanouil (Manos), Lenovo ","epateromiche@lenovo.com ","3/4/25: 23.700-83 added;; 6/6/25: 0%->40","23.700-83",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[40,1080012,"Study on AIML management phase 3 ","FS_AIML_MGT_Ph3",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250867",null,"Hassan Al-Kanani (NEC), ","Hassan.Alkanani@EMEA.NEC.COM ","18/7/25: 28.882 added;",28.882000000000001,108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[41,1080049,"Media aspects for AI/ML in IMS services ","AIML_IMS-MED",1,"Rel-20","S4","Wed 06/07/22","Sun 12/03/23",0,"SP-250878",null,"Yip, Eric, Samsung Electronics Co., Ltd, ","eric dot yip AT samsung dot com ",null,"26.114; 26.264 ",108,55,null,null,"Thu 05/06/25","NA"]
[42,1080085,"AIML for NR air interface Phase 2 ","NR_AIML_air_Ph2",1,"Rel-20",null,"Fri 06/06/25","Thu 09/09/27",0,"RP-251870",null,"Qualcomm ",null,"follow-up WI of REL-19 SI FS_NR_AIML_air_Ph2; compare REL-19 WI NR_AIML_air ",null,108,55,null,null,"Fri 18/07/25","NA"]
[43,1081085,"   Core part: AIML or NR air interface Phase 2 ","NR_AIML_air_Ph2-Core",2,"Rel-20","R1","Fri 06/06/25","Wed 03/03/27",0,"RP-251870",null,"Qualcomm ",null,"follow-up WI of REL-19 SI FS_NR_AIML_air_Ph2; compare REL-19 WI NR_AIML_air ",null,108,55,null,null,"Fri 18/07/25","NA"]
[44,1082085,"   Perf. Part: AIML for NR air interface Phase 2 ","NR_AIML_air_Ph2-Perf",2,"Rel-20","R4","Fri 06/06/25","Thu 09/09/27",0,"RP-251870",null,"Qualcomm ",null,null,null,108,55,null,null,"Fri 18/07/25","NA"]
[45,1080087,"AIML for mobility in NR ","NR_AIML_Mob",1,"Rel-20",null,"Fri 06/06/25","Sun 06/06/27",0,"RP-251864",null,"OPPO ",null,"follow-up WI of REL-19 SI FS_NR_AIML_Mob ",null,108,55,null,null,"Fri 18/07/25","NA"]
[46,1081087,"   Core part: AIML for mobility in NR ","NR_AIML_Mob-Core",2,"Rel-20","R2","Fri 06/06/25","Wed 03/03/27",0,"RP-251864",null,"OPPO ",null,"follow-up WI of REL-19 SI FS_NR_AIML_Mob ",null,108,55,null,null,"Fri 18/07/25","NA"]
[47,1082087,"   Perf. Part: AIML for mobility in NR ","NR_AIML_Mob-Perf",2,"Rel-20","R4","Fri 06/06/25","Sun 06/06/27",0,"RP-251864",null,"OPPO ",null,null,null,108,55,null,null,"Fri 18/07/25","NA"]
[48,0,"Rel-20 Energy Efficiency, Energy Saving","-",1,"Rel-20",null,"Sun 05/05/24","Wed 12/12/25",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[49,1080053,"Energy Efficiency as Service Criteria Phase 2 ",null,1,"Rel-20",null,"Tue 02/04/24","Fri 06/06/25",1,null,null,null,null,null,null,108,55,null,null,"Thu 05/06/25","NA"]
[50,1030044,"   Study on Energy Efficiency as Service Criteria Phase 2 ","FS_EnergyServ_Ph2",2,"Rel-20","S1","Tue 02/04/24","Mon 03/03/25",1,"SP-240494",null,"Laurent-WalterGoix, Nokia ","laurent-walter.goix@NOKIA.COM ","13/6/24: 0%->25; 4/9/24: 25%->55; 6/3/25: 55%->100",22.882999999999999,103,52,null,null,"Wed 13/03/24","Thu 06/03/25"]
[51,1070051,"   Stage 1 for Energy Efficiency as Service Criteria Phase 2 ","EnergyServ_Ph2-REQ",2,"Rel-20","S1","Thu 06/03/25","Fri 06/06/25",1,"SP-250385",null,"Laurent-Walter Goix, Nokia ","laurent-walter.goix@nokia.com ","; 26/3/25: WID:SP-250271->SP-250385",22.260999999999999,107,54,null,null,"Wed 05/03/25","Wed 26/03/25"]
[52,1070058,"Study on Energy Efficiency and Energy Saving Phase2","FS_EnergySys_Ph2",1,"Rel-20","S2","Wed 26/03/25","Fri 12/12/25",0,"SP-250791",null,"Konstantinos Samdanis (Lenovo)","ksamdanis@lenovo.com","27/6/25: WID:SP-250417->SP-250791",null,107,54,null,null,"Wed 26/03/25","Fri 27/06/25"]
[53,1080024,"Study on Application Enablement to support Energy Saving Phase 2","FS_EnergySys_Ph2_APP",1,"Rel-20","S6","Thu 05/06/25","Tue 03/03/26",0,"SP-250871",null,"Yue, Jing, Ericsson ","jing.yue@ericsson.com ","18/7/25: 23.700-44 added;","23.700-44",108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[54,1080005,"Study on energy efficiency and energy saving aspects of 5G Advanced ","FS_Energy_Ph4_OAM",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250860",null,"Srilakshmi S (Nokia), ","srilakshmi.s@nokia.com ","18/7/25: 28.885 added;",28.885000000000002,108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[55,1080050,"Study on Media energy consumption exposure and evaluation framework Phase 2 ","FS_Energy_Ph2_MED",1,"Rel-20","S4","Thu 05/06/25","Tue 03/03/26",0,"SP-250636",null,"Julien Lemotheux, Orange ","<julien.lemotheux@orange.com> ",null,26.942,108,55,null,null,"Thu 05/06/25","NA"]
[56,0,"Rel-20 Radio-centric: NR-only, not band-related","-",1,"Rel-20",null,"Thu 07/03/19","Wed 09/06/21",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[57,1080092,"Data Collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR Phase 5 ","NR_SON_MDT_Ph5",1,"Rel-20",null,"Fri 06/06/25","Wed 03/03/27",0,"RP-251869",null,"China Unicom ",null,"no Perf. part; compare: REL-19 WI NR_ENDC_SON_MDT_Ph4, REL-18 WI NR_ENDC_SON_MDT_enh2, REL-17 WI NR_ENDC_SON_MDT_enh, REL-16 WI NR_SON_MDT ",null,108,55,null,null,"Fri 18/07/25","NA"]
[58,1081092,"   Core part: Data collection for SON/MDT in NR Phase 5 ","NR_SON_MDT_Ph5-Core",2,"Rel-20","R3","Fri 06/06/25","Wed 03/03/27",0,"RP-251869",null,"China Unicom ",null,"no Perf. part; compare: REL-19 WI NR_ENDC_SON_MDT_Ph4, REL-18 WI NR_ENDC_SON_MDT_enh2, REL-17 WI NR_ENDC_SON_MDT_enh, REL-16 WI NR_SON_MDT ",null,108,55,null,null,"Fri 18/07/25","NA"]
[59,1080088,"NR mobility enhancements Phase 5 ","NR_Mob_Ph5",1,"Rel-20","R2","Fri 06/06/25","Sun 06/06/27",0,"RP-251865",null,"Apple ",null,"compare: REL-16 WI NR_Mob_enh, REL-18 WI NR_Mob_enh2, REL-19 WI NR_Mob_Ph4 ",null,108,55,null,null,"Fri 18/07/25","NA"]
[60,1081088,"   Core part: NR mobility enhancements Phase 5 ","NR_Mob_Ph5-Core",2,"Rel-20","R2","Fri 06/06/25","Wed 03/03/27",0,"RP-251865",null,"Apple ",null,"compare: REL-16 WI NR_Mob_enh, REL-18 WI NR_Mob_enh2, REL-19 WI NR_Mob_Ph4 ",null,108,55,null,null,"Fri 18/07/25","NA"]
[61,1082088,"   Perf. part: NR mobility enhancements Phase 5 ","NR_Mob_Ph5-Perf",2,"Rel-20","R4","Fri 06/06/25","Sun 06/06/27",0,"RP-251865",null,"Apple ",null,null,null,108,55,null,null,"Fri 18/07/25","NA"]
[62,1080083,"NR MIMO Phase 6 ","NR_MIMO_Ph6",1,"Rel-20",null,"Fri 06/06/25","Thu 09/09/27",0,"RP-251856",null,"MediaTek ",null,"compare REL-19 WI NR_MIMO_Ph5, REL-18 WIs NR_MIMO_evo_DL_UL, NR_MIMO_OTA_enh, REL-17 WIs NR_feMIMO, NR_MIMO_OTA, REL-16 WI NR_eMIMO ",null,108,55,null,null,"Fri 18/07/25","NA"]
[63,1081083,"   Core part: NR MIMO Phase 6 ","NR_MIMO_Ph6-Core",2,"Rel-20","R1","Fri 06/06/25","Wed 03/03/27",0,"RP-251856",null,"MediaTek ",null,"compare REL-19 WI NR_MIMO_Ph5, REL-18 WIs NR_MIMO_evo_DL_UL, NR_MIMO_OTA_enh, REL-17 WIs NR_feMIMO, NR_MIMO_OTA, REL-16 WI NR_eMIMO ",null,108,55,null,null,"Fri 18/07/25","NA"]
[64,1082083,"   Perf. part: NR MIMO Phase 6 ","NR_MIMO_Ph6-Perf",2,"Rel-20","R4","Fri 06/06/25","Thu 09/09/27",0,"RP-251856",null,"MediaTek ",null,null,null,108,55,null,null,"Fri 18/07/25","NA"]
[65,1080084,"NR coverage enhancements Phase 3 ","NR_cov_Ph3",1,"Rel-20",null,"Fri 06/06/25","Wed 03/03/27",0,"RP-251862",null,"China Telecom ",null,"compare REL-18 WI NR_cov_enh2, REL-17 WI NR_cov_enh ",null,108,55,null,null,"Fri 18/07/25","NA"]
[66,1081084,"   Core part: NR coverage enhancements Phase 3 ","NR_cov_Ph3-Core",2,"Rel-20","R1","Fri 06/06/25","Sat 12/12/26",0,"RP-251862",null,"China Telecom ",null,"compare REL-18 WI NR_cov_enh2, REL-17 WI NR_cov_enh ",null,108,55,null,null,"Fri 18/07/25","NA"]
[67,1082084,"   Perf. part: Coverage enhancements for NR Phase 3 ","NR_cov_Ph3-Perf",2,"Rel-20","R4","Fri 06/06/25","Wed 03/03/27",0,"RP-251862",null,"China Telecom ",null,null,null,108,55,null,null,"Fri 18/07/25","NA"]
[68,0,"Rel-20 Radio-centric: NR-only, band-related","-",1,"Rel-20",null,"Thu 07/03/19","Sat 15/05/21",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[69,1080093,"Introduction of NR TDD 4.9GHz band for US operation ","NR_TDD_band_4900MHz_US",1,"Rel-20","R4","Fri 06/06/25","Sat 06/06/26",0,"RP-251887",null,"Fujitsu ",null,"4940-4990 MHz NR TDD band for public safety in US, REL-independent from REL-15; Core part target colliding with REL-19 ASN.1 freeze ",null,108,55,null,null,"Fri 18/07/25","NA"]
[70,1081093,"   Core part: Introduction of NR TDD 4.9GHz band for US operation ","NR_TDD_band_4900MHz_US-Core",2,"Rel-20","R4","Fri 06/06/25","Fri 12/12/25",0,"RP-251887",null,"Fujitsu ",null,"4940-4990 MHz NR TDD band for public safety in US, REL-independent from REL-15; Core part target colliding with REL-19 ASN.1 freeze ",null,108,55,null,null,"Fri 18/07/25","NA"]
[71,1082093,"   Perf. part: Introduction of NR TDD 4.9GHz band for US operation ","NR_TDD_band_4900MHz_US-Perf",2,"Rel-20","R4","Fri 06/06/25","Sat 06/06/26",0,"RP-251887",null,"Fujitsu ",null,null,null,108,55,null,null,"Fri 18/07/25","NA"]
[72,0,"Rel-20 Other topics","-",1,"Rel-20",null,"Tue 02/04/24","Thu 11/06/26",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[73,1080052,"Indirect Network Sharing Phase 2 ","NetShare_Ph2",1,"Rel-20",null,"Thu 08/02/24","Wed 09/09/26",0.32,"SP-241147",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,22.260999999999999,105,53,null,null,"Wed 04/09/24","NA"]
[74,1050106,"   Stage 1 for Indirect Network Sharing Phase 2 ","NetShare_Ph2-REQ",2,"Rel-20","S1","Thu 08/02/24","Mon 09/09/24",1,"SP-241147",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,null,105,53,null,null,"Thu 05/06/25","NA"]
[75,1080059,"   Stage 2 for Indirect Network Sharing Phase2 ","NetShare_Ph2-ARC",2,"Rel-20","S2","Thu 05/06/25","Wed 09/09/26",0,"SP-250838",null,"Tianqi Xing, China Unicom ","xingtq@chinaunicom.cn ",null,"23.501; 23.502; 23.503 ",108,55,null,null,"Thu 05/06/25","NA"]
[76,1080055,"FRMCS Phase 6 ","FRMCS_Ph6",1,"Rel-20",null,"Wed 13/03/24","Sat 06/06/26",0.48,null,null,null,null,null,null,108,55,null,null,"Thu 05/06/25","NA"]
[77,1030043,"   Study on FRMCS Phase 6 ","FS_FRMCS_Ph6",2,"Rel-20","S1","Wed 13/03/24","Mon 03/03/25",1,"SP-241392",null,"Nikolopoulou, Vassiliki, UIC, ","nikolopoulou@uic.org ","; 13/6/24: 0%->20; 4/9/24: 20%->40; 26/9/24: WID:SP-240199->SP-241392; 26/9/24: FCD:09/09/2024->/25; 6/3/25: 40%->100",22.989000000000001,103,52,null,null,"Wed 13/03/24","Thu 06/03/25"]
[78,1070054,"   Stage 1 for FRMCS Phase 6 ","FRMCS_Ph6-REQ",2,"Rel-20","S1","Thu 06/03/25","Tue 09/09/25",0.1,"SP-250277",null,"Nikolopoulou, Vassiliki, UIC ","nikolopoulou@uic.org ","; 6/6/25: 0%->10; 6/6/25: FCD:Fri 06/06/->/25","22.280; 22.179; 22.281 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[79,1070031,"   Stage 2 for FRMCS Phase 6 ","FRMCS_Ph6-MC",2,"Rel-20","S6","Wed 26/03/25","Sat 06/06/26",0.35,"SP-250390",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","; 6/6/25: 0%->35","23.280; 23.281; 23.282; 23.379; 23.283; 23.289 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[80,1080056,"Short Message Service to Emergency Response Centre","SMS2EC",1,"Rel-20",null,"Sun 02/02/25","Fri 12/12/25",0.14000000000000001,null,null,null,null,null,null,108,55,null,null,"Thu 05/06/25","NA"]
[81,1070052,"   Stage 1 of SMS to Emergency Centre","SMS2EC-REQ",2,"Rel-20","S1","Sun 02/02/25","Mon 03/03/25",1,"SP-250387",null,"Francesco Pica, Qualcomm ","fpica@qti.qualcomm.com ",null,22.201000000000001,107,54,null,null,"Wed 05/03/25","NA"]
[82,1080062,"   Study on Short Message Service to Emergency Response Centre ","FS_SMS2EC_ARC",2,"Rel-20","S2","Thu 05/06/25","Fri 12/12/25",0,"SP-250837",null,"Krisztian Kiss, Apple ","krisztian@apple.com ",null,null,108,55,null,null,"Thu 05/06/25","NA"]
[83,1070025,"Study on Logging and recording of mission critical services, Phase 2 ","FS_MCLOG_Ph2",1,"Rel-20","S6","Wed 26/03/25","Tue 03/03/26",0.1,"SP-250581",null,"Vialen, Jukka, Airbus ","jukka.vialen@airbus.com ","3/4/25: 23.700-39 added;; 6/6/25: 0%->10; 27/6/25: WID:SP-250380->SP-250581","23.700-39",107,54,null,null,"Wed 05/03/25","Fri 27/06/25"]
[84,1070024,"Study on Discreet listening and monitoring of mission critical services, Phase 2 ","FS_MCDISC_Ph2",1,"Rel-20","S6","Wed 26/03/25","Tue 03/03/26",0.1,"SP-250379",null,"Vialen, Jukka, Airbus ","jukka.vialen@airbus.com ","3/4/25: 23.700-37 added;; 6/6/25: 0%->10","23.700-37",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[85,1080044,"Mission critical security for Rel-20 ","MCX20-SEC",1,"Rel-20","S3","Thu 07/03/19","Tue 01/12/20",0,"SP-250653",null,"Woodward, Tim, Motorola Solutions, Inc., ","tim.woodward@motorolasolutions.com ",null,33.18,108,55,null,null,"Thu 05/06/25","NA"]
[86,1060070,"Vehicle-Mounted Relays Phase3 ","VMR_Ph3",1,"Rel-20","S1","Thu 05/12/24","Thu 12/12/24",1,"SP-241821",null,"Qing Wan, CATT, ","wanqing1@cictmobile.com ","; 5/12/24: 0%->100",22.260999999999999,106,54,null,null,"Thu 05/12/24","Thu 05/12/24"]
[87,1050107,"Resident Phase 2 ","Resident_Ph2",1,"Rel-20","S1","Wed 04/09/24","Mon 09/09/24",1,"SP-241149",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,22.260999999999999,105,53,null,null,"Wed 04/09/24","NA"]
[88,1080058,"5G ProSe Phase 4 ","ProSe_Ph4-ARC",1,"Rel-20","S2","Thu 05/06/25","Wed 09/09/26",0,"SP-250839",null,"Toumi, Nassima, KPN N.V. ","nassima (dot) toumi (dot) tno (dot) nl ",null,23.303999999999998,108,55,null,null,"Thu 05/06/25","NA"]
[89,1080045,"Study on Transitioning to Post Quantum Cryptography in 3GPP ","FS_CryptoPQC",1,"Rel-20","S3","Thu 05/06/25","Sat 06/06/26",0,"SP-250858",null,"Primary: Zander, Huawei ","lei.zhongding@huawei.com ",null,null,108,55,null,null,"Thu 05/06/25","NA"]
[90,1080047,"CPAS specific requirement ","CPAS-REQ",1,"Rel-20","S1","Thu 05/06/25","Fri 06/06/25",1,"SP-250627",null,"Pengtai Qin ","qinpengtai@chinamobile.com ","; 5/6/25: 0%->100",23.303999999999998,108,55,null,null,"Thu 05/06/25","Thu 05/06/25"]
[91,1080042,"Security Assurance Specification for 5G-Advanced ","SCAS_5GA",1,"Rel-20","S3","Thu 05/06/25","Wed 09/09/26",0,"SP-250877",null,"Wurong (raina), Huawei ","raina.wu@huawei.com ",null,null,108,55,null,null,"Thu 05/06/25","NA"]
[92,1080041,"Security related Events Handling ","SECHAND",1,"Rel-20","S3","Thu 05/06/25","Fri 12/12/25",0,"SP-250876",null,"Susana Sabater, Vodafone ","susana.sabater@vodafone.com ","18/7/25: 33.502 added;",33.502000000000002,108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[93,1080029,"Guidelines for 3GPP Application Enablement usage ","AppEnable_EXT",1,"Rel-20","S6","Thu 05/06/25","Tue 03/03/26",0,"SP-250883",null,"David Artuñedo, Telefónica ","david.artunedoguillen@telefonica.com ",null,null,108,55,null,null,"Thu 05/06/25","NA"]
[94,1080026,"Study of CAPIF Phase 4 ","FS_CAPIF_Ph4",1,"Rel-20","S6","Thu 05/06/25","Tue 03/03/26",0,"SP-250873",null,"Niranth Amogh, Nokia, ","niranth.amogh@nokia.com ","18/7/25: 23.700-43 added;","23.700-43",108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[95,1080025,"Study on Application user consent ","FS_APCOT",1,"Rel-20","S6","Thu 05/06/25","Tue 03/03/26",0,"SP-250872",null,"Cristina Badulescu ","cristina.badulescu@ericsson.com ","18/7/25: 23.700-42 added;","23.700-42",108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[96,1080060,"Study on system architecture for Phae 3 of NG RTC","FS_NG_RTC_Ph3_ARC",1,"Rel-20","S2","Thu 05/06/25","Tue 03/03/26",0,"SP-250855",null,"Christopher Joul, T-Mobile USA, ","chris.joul@t-mobile.com ",null,null,108,55,null,null,"Thu 05/06/25","NA"]
[97,1050034,"Study on Service Enabler Architecture Layer (SEAL) Phase 4","FS_SEAL_Ph4",1,"Rel-20","S6","Wed 04/09/24","Fri 12/12/25",0.75,"SP-250374",null,"Yang, Yanmei, Huawei Technologies Co.,Ltd. ","yangyanmei@huawei.com","5/12/24: 0%->20; 6/3/25: 20%->40. Moved from Rel-19; 26/3/25: WID:SP-241375->SP-250374; 26/3/25: FCD:12/12/2024->12/25; 6/6/25: 40%->75",null,105,53,null,null,"Wed 04/09/24","Fri 06/06/25"]
[98,1070053,"Stage 1 for Ambient listening enhancements including pause and resume in MCS ","ALPR-REQ",1,"Rel-20","S1","Tue 11/02/25","Mon 03/03/25",1,"SP-250275",null,"S. (Ram) Ramanan ","Sivasubramaniam.ramanan@homeoffice.gov.uk ","; 26/3/25: 0%->100","22.179; 22.280 ",107,54,null,null,"Wed 05/03/25","Wed 26/03/25"]
[99,1070026,"Study on Application enabler for XR Services Phase 3 ","FS_XRM_Ph3_APP",1,"Rel-20","S6","Wed 26/03/25","Fri 12/12/25",0.35,"SP-250381",null,"Zheng, Shaowen, China Mobile ","zhengshaowen@chinamobile.com ","3/4/25: 23.700-51 added;; 6/6/25: 0%->35","23.700-51",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[100,1070027,"Study on SEAL data delivery Phase 3 ","FS_SEALDD_Ph3",1,"Rel-20","S6","Wed 26/03/25","Fri 12/12/25",0.3,"SP-250382",null,"Ge, Cuili, Huawei ","gecuili@huawei.com ","3/4/25: 23.700-52 added;; 6/6/25: 0%->30","23.700-52",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[101,1070028,"Study on Stage 2 for MMTel Phase 2 ","FS_MMTel_Ph2_APP",1,"Rel-20","S6","Wed 26/03/25","Tue 03/03/26",0.3,"SP-250383",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","3/4/25: 23.700-57 added;; 6/6/25: 0%->30","23.700-57",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[102,1070030,"Stage 2 for Mission Critical Services for UE-to-UE and UE-to-Network over multi-hop relay ","MultiHop-MC",1,"Rel-20","S6","Wed 26/03/25","Tue 03/03/26",0,"SP-250389",null,"Lipford, Mark, FirstNet Authority ","mark.lipford@firstnet.gov ","; 6/6/25: 0%->75",23.289000000000001,107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[103,1070032,"Stage 2 for Enhanced Mission Critical Services Architecture Phase 2 ","enhMC_Ph2-MC",1,"Rel-20","S6","Wed 26/03/25","Sat 06/06/26",0.15,"SP-250391",null,"Negalaguli, Harish, Motorola Solutions ","harish.negalaguli@motorolasolutions.com ","; 6/6/25: 0%->15","23.280; 23.379; 23.281; 23.282; 23.283; 23.289 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[104,1050108,"Combined QoS configuration and monitoring ","CombQoS",1,"Rel-20","S1","Wed 04/09/24","Mon 09/09/24",1,"SP-241150",null,"Yansheng Liu, ZTE ","liu.yansheng@zte.com.cn ",null,22.260999999999999,105,53,null,null,"Wed 04/09/24","NA"]
[105,1050109,"Legacy Residential Gateway Supporting 5G LAN-type Service ","LegacyRG_5GLAN",1,"Rel-20","S1","Wed 04/09/24","Mon 09/09/24",1,"SP-241151",null,"Yuying Zhang, China Telecom ","zhangyy45@chinatelecom.cn ",null,22.260999999999999,105,53,null,null,"Wed 04/09/24","NA"]
[106,1050111,"Exposure for Virtual Network information and capability ","VNExposure",1,"Rel-20","S1","Wed 04/09/24","Mon 09/09/24",1,"SP-241153",null,"Pengtai Qin, China Mobile ","qinpengtai@chinamobile.com ",null,22.260999999999999,105,53,null,null,"Wed 04/09/24","NA"]
[107,0,"Rel-20 Extended reality, Metaverse","-",1,"Rel-20",null,"Tue 02/04/24","Thu 11/06/26",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[108,1070033,"Stage 2 for mobile metaverse services Phase 2 ","Metaverse_Ph2-APP",1,"Rel-20","S6","Wed 26/03/25","Fri 12/12/25",0.45,"SP-250392",null,"Ramamoorthy, Arunprasath (Arun), Samsung, ","arun.prasath@samsung.com ","; 6/6/25: 0%->45","23.437; 23.438 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[109,1080089,"XR (eXtended Reality) for NR Phase 4 ","NR_XR_Ph",1,"Rel-20","R2","Fri 06/06/25","Wed 03/03/27",0,"RP-251866",null,"Meta ",null,"no Perf. part; no affected RAN2 spec??? ",null,108,55,null,null,"Fri 18/07/25","NA"]
[110,1081089,"   Core part: XR (eXtended Reality) for NR Phase 4 ","NR_XR_Ph4-Core",2,"Rel-20","R2","Fri 06/06/25","Wed 03/03/27",0,"RP-251866",null,"Meta ",null,"no Perf. part; no affected RAN2 spec??? ",null,108,55,null,null,"Fri 18/07/25","NA"]
[111,0,"Rel-20 Integrated Sensing and Communication (Sensing, ISAC)","-",1,"Rel-20",null,"Tue 02/04/24","Thu 11/06/26",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[112,1070012,"Study on Stage 2 for Integrated Sensing and Communication ","FS_Sensing_ARC",1,"Rel-20","S2","Wed 26/03/25","Fri 12/12/25",0,"SP-250809",null,"Jianning LIU, Xiaomi ","liujianning@xiaomi.com ","; 27/6/25: WID:SP-250401->SP-250809",null,107,54,null,null,"Wed 05/03/25","Fri 27/06/25"]
[113,1080028,"Study on use of Sensing results for Vertical Applications","FS_Sensing_APP",1,"Rel-20","S6","Thu 05/06/25","Tue 03/03/26",0,"SP-250875",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","18/7/25: 23.700-15 added;","23.700-15",108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[114,1080070,"Study on Integrated Sensing And Communication (ISAC) for NR ","FS_Sensing_NR_bis",1,"Rel-20","R1","Fri 06/06/25","Sat 06/06/26",0,"RP-251861",null,"Xiaomi ",null,"compare REL-19 RAN1 SI FS_Sensing_NR and REL-20 SA2 SI FS_Sensing_ARC; 38.xxx ? ",null,108,55,null,null,"Fri 18/07/25","NA"]
[115,0,"Rel-20 Miscellaneous OAM&Charging","-",1,"Rel-20",null,"Tue 02/04/24","Thu 11/06/26",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[116,1080006,"Study on intent driven management services for mobile network phase 4 ","FS_IDMS_MN_Ph4",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250861",null,"Ruiyue Xu (Huawei), ","xuruiyue@huawei.com ","18/7/25: 28.881 added;",28.881,108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[117,1080007,"Study on Management Data Analytics (MDA) phase 4 ","FS_eMDAS_Ph4",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250862",null,"Brendan T Hassett (Huawei), ","brendan.t.hassett@huawei.com ","18/7/25: 28.886 added;",28.885999999999999,108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[118,1080008,"Study on Service Based Management Architecture enhancement phase 4 ","FS_SBMA_Ph4",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250863",null,"Kai Zhang (Huawei), ","kai.zhangkai@huawei.com ","18/7/25: 28.884 added;",28.884,108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[119,1080009,"Study on Enhanced exposure of management services ","FS_EnExpo",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250864",null,"Winnie Nakimuli (Nokia) ","winnie.nakimuli@nokia.com ","18/7/25: 28.888 added;",28.888000000000002,108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[120,1080010,"Study for Data management phase 3 ","FS_MADCOL_Ph3",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250865",null,"Sreekumar PK (Nokia), ","sreekumar.pk@nokia.com ","18/7/25: 28.887 added;",28.887,108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[121,1080011,"Study on management aspects of Network Digital Twins phase 2 ","FS_NDT_Ph2",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250866",null,"Xian Zhao (Huawei), ","zhaoxian7@huawei.com ","18/7/25: 28.883 added;",28.882999999999999,108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[122,1080013,"Study on Closed Control Loop Management phase 2 ","FS_CCLM_Ph2",1,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250868",null,"Deepanshu Gautam (Samsung), ","deepanshu.g@samsung.com ","18/7/25: 28.889 added;",28.888999999999999,108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[123,1080015,"5G performance measurements/KPIs and Trace/MDT/QoE ","PM_KPI_Trace_MDT_QoE-OAM",1,"Rel-20","S5","Thu 05/06/25","Wed 09/09/26",0,"SP-250879",null,"XiuMin Chen (China Telecom), ","chenxiumin@chinatelecom.cn ",null,"28.552; 28.554; 28.532; 28.558; 32.404; 32.421; 32.422; 32.423; 28.404; 28.405; 28.406; 28.622; 28.623; 28.541 ",108,55,null,null,"Thu 05/06/25","NA"]
[124,1080017,"Management Aspects related to NWDAF phase 3 ","NWDAF_Ph3-OAM",1,"Rel-20","S5","Thu 05/06/25","Sat 06/06/26",0,"SP-250881",null,"Song Zhao (China Telecom), ","zhaosong1@chinatelecom.cn ",null,"28.541; 28.552; 28.554 ",108,55,null,null,"Thu 05/06/25","NA"]
[125,1080018,"5G Advanced NRM features phase 4 ","AdNRM_Ph4-OAM",1,"Rel-20","S5","Thu 05/06/25","Sat 12/12/26",0,"SP-250882",null,"Sean Sun (Nokia) ","sean.sun@nokia-sbell.com ",null,"28.540; 28.541; 28.622; 28.623; 32.160 ",108,55,null,null,"Thu 05/06/25","NA"]
[126,1089999,"(Small) Technical Enhancements and Improvements for Rel-20","TEI20",1,"Rel-20",null,"Thu 05/06/25","Sat 12/12/26",0,null,null,null,null,null,null,92,47,null,null,"Mon 15/06/15","Mon 15/06/15"]
[127,1040011,"Lawful Interception Rel-20 ","LI20",1,"Rel-20","S3LI","Thu 06/03/25","Wed 03/03/27",0,"SP-250447",null,"Koen Jaspers, PIDS, ","k.b.jaspers@minjenv.nl ","; 26/3/25: WID:SP-241012->SP-250388; 27/6/25: WID:SP-250388->SP-250447","33.107; 33.108; 33.126; 33.127; 33.128; 33.928 ; 33.129",104,53,null,null,"Wed 12/06/24","Fri 27/06/25"]
[128,0,"--- RELEASE 19 ---","-",1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[129,0,"Rel-19 Energy Efficiency, Energy Saving","-",1,"Rel-19",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[130,1020060,"Energy Efficiency as Service Criteria ","EnergyServ",1,"Rel-19",null,"Thu 02/06/22","Tue 09/09/25",0.88,"SP-230520",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 6/9/23: 0%->75; 8/12/23: 75%->100",22.260999999999999,100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[131,960019,"   Study on Energy Efficiency as service criteria ","FS_EnergyServ",2,"Rel-19","S1","Thu 02/06/22","Sat 09/09/23",1,"SP-230235",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","13/7/22: 22.882 added;; 9/9/22: 0%->10; 10/12/22: FCD:10/03/2023->06/23; 10/12/22: 10%->40; 16/3/23: WID:SP-220446->SP-230235; 17/3/23: 40%->70; 8/6/23: 70%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->95; 8/12/23: 95%->100",22.882000000000001,96,49,null,null,"Thu 02/06/22","Fri 08/12/23"]
[132,1000033,"   Stage 1 of Energy Efficiency as Service Criteria ","EnergyServ",2,"Rel-19","S1","Thu 08/06/23","Tue 12/12/23",1,"SP-230520",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 6/9/23: 0%->75; 8/12/23: 75%->100",22.260999999999999,100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[133,1040018,"   Charging Aspects for Energy Efficiency of Network Slice","EnergySys_CH",2,"Rel-19","S5","Wed 12/06/24","Fri 06/06/25",1,"SP-250124",null,"YiMeng, DENG, Huawei, ","dengyimeng@huawei.com ","; 4/9/24: 0%->45; 6/3/25: 45%->100; 26/3/25: WID:SP-241003->SP-250124; 26/3/25: FCD:12/12/2024->6/6/25. Name changed from \"Charging Aspects for Energy Efficiency of 5G\"","32.240; 28.201; 28.202; 32.291; 32.298 ",104,53,null,null,"Wed 12/06/24","Wed 26/03/25"]
[134,1010029,"   Study on Energy Efficiency and Energy Saving","FS_EnergySys",2,"Rel-19","S2","Sat 09/09/23","Thu 06/06/24",1,"SP-231391",null,"Jungshin Park (Samsung)","shin02.park@samsung.com","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-66 added;; 8/12/23: 0%->15; 4/1/24: 28.880 added;; 14/3/24: 15%->55; 13/6/24: 55%->100; 4/9/24: 99%->100","SP-231192; 23.700-66; 28.880",101,51,null,null,"Wed 20/09/23","Wed 04/09/24"]
[135,1050112,"   Energy Efficiency and Energy Saving ","EnergySys",2,"Rel-19","S2","Wed 04/09/24","Thu 12/12/24",1,"SP-250069",null,"Primary Rapporteur: Jungshin Park (Samsung) ","shin02.park@samsung.com ","; 5/12/24: 0%->70; 6/3/25: 70%->100; 26/3/25: WID:SP-241388->SP-250069","23.501; 23.502; 23.503 ",105,53,null,null,"Wed 04/09/24","Wed 26/03/25"]
[136,1070002,"   CT aspects of energy efficiency and energy saving","EnergySys",2,"Rel-19","C3","Mon 03/03/25","Tue 09/09/25",0.52,"CP-250247",null,"Suh, Kyungjoo(Grace), Samsung","joo.suh@samsung.com",null,"29.508,29.513,29.522,29.122,29.519,29.510,29.503,29.504,29.518",105,53,null,null,"Wed 04/09/24","Thu 05/12/24"]
[137,1070034,"      CT3 aspects of energy efficiency and energy saving","EnergySys",3,"Rel-19","C3","Mon 03/03/25","Tue 09/09/25",0.75,"CP-250247",null,"Suh, Kyungjoo(Grace), Samsung","joo.suh@samsung.com",null,"29.508,29.513,29.522,29.122,29.519,29.510,29.503,29.504,29.518",105,53,null,null,"Wed 04/09/24","Thu 05/12/24"]
[138,1070035,"      CT4 aspects of energy efficiency and energy saving","EnergySys",3,"Rel-19","C4","Mon 03/03/25","Tue 09/09/25",0.75,"CP-250247",null,"Suh, Kyungjoo(Grace), Samsung","joo.suh@samsung.com",null,"29.508,29.513,29.522,29.122,29.519,29.510,29.503,29.504,29.518",105,53,null,null,"Wed 04/09/24","Thu 05/12/24"]
[139,1020021,"   Study on energy efficiency and energy saving aspects of 5G networks and services ","FS_Energy_OAM_Ph3",2,"Rel-19","S5","Fri 08/12/23","Thu 12/12/24",1,"SP-241568",null,"Jean-Michel Cornily (Huawei)","jean.michel.cornily@huawei.com","4/1/24: 28.866 added;; 14/3/24: 0%->10; 13/6/24: 10%->25; 4/9/24: 25%->60; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 60%->100; 8/1/25: WID:SP-231723->SP-241568",28.866,102,52,null,null,"Thu 07/12/23","Wed 08/01/25"]
[140,1030038,"   Study on security aspects of energy saving in 5G ","FS_Energy_Sec",2,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240512",null,"Bo Bjerrum ","bo.bjerrum@nokia.com ","3/4/24: 33.766 added;; 13/6/24: 0%->30; 5/9/24: 30%->70; 5/12/24: 70%->90; 6/3/25: 90%->100; 5/6/25: 100%->100",33.765999999999998,103,52,null,null,"Thu 14/03/24","Thu 05/06/25"]
[141,1060007,"   Energy efficiency and energy saving aspects of 5G networks and services ","Energy_OAM_Ph3",2,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.7,"SP-241940",null,"Jean-Michel Cornily (Huawei)","jean.michel.cornily@huawei.com ","; 6/3/25: 0%->20; 6/6/25: 20%->70","28.310; 28.622; 28.623; 28.541; 28.554; 28.104 ",106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[142,1020095,"Enhancements of Network energy savings for NR ","Netw_Energy_NR_enh",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.52,"RP-251678",null,"Ericsson ",null,"2/4/24: WID:RP-234065->RP-240170; 23/7/24: WID:RP-240170->RP-241650; 26/9/24: WID:RP-241650->RP-242354; 3/4/25: WID:RP-242354->RP-250343; 18/7/25: WID:RP-250343->RP-251678",null,102,52,null,null,"Tue 02/01/24","Fri 18/07/25"]
[143,1021095,"   Core part: Enhancements of Network energy savings for NR ","Netw_Energy_NR_enh-Core",2,"Rel-19","R1","Wed 13/12/23","Tue 09/09/25",0.9,"RP-251678","RP-251677","Ajit Nimbalker, Ericsson","Ajit.Nimbalker@ericsson.com","14/3/24: Compl:0%->5%; Stat Rep: ->RP-240169; Rapporteur: Ericsson->Ajit Nimbalker, Ericsson; Rap eMail: ->Ajit.Nimbalker@ericsson.com; ; 13/6/24: Compl:5%->25%; Stat Rep: RP-240169->RP-241182; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:25%->35%; Stat Re",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[144,1022095,"   Perf. part: Enhancements of Network energy savings for NR ","Netw_Energy_NR_enh-Perf",2,"Rel-19","R4","Sun 18/08/24","Tue 03/03/26",0.1,"RP-251678","RP-251677","Ajit Nimbalker, Ericsson","Ajit.Nimbalker@ericsson.com","14/3/24: Stat Rep: ->RP-240169; Rapporteur: Ericsson->Ajit Nimbalker, Ericsson; Rap eMail: ->Ajit.Nimbalker@ericsson.com; ; 13/6/24: Stat Rep: RP-240169->RP-241182; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241182->RP-241866; ; 6/12/24: FCD:03/03",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[145,1030004,"Study on Media enerGy consumption exposuRE and EvaluatioN framework ","FS_MediaEnergyGREEN",1,"Rel-19","S4","Tue 02/04/24","Mon 03/03/25",1,"SP-240481",null,"Julien Lemotheux, Orange, ","julien.lemotheux@orange.com ","14/5/24: 26.942 added;; 13/6/24: 0%->15; 4/9/24: 15%->30; 5/12/24: 30%->60; 6/3/25: 60%->100",26.942,103,52,null,null,"Wed 13/03/24","Thu 06/03/25"]
[146,1020094,"Low-power wake-up signal and receiver for NR (LP-WUS/WUR) ","NR_LPWUS",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.5,"RP-251200",null,"vivo ",null,"2/4/24: WID:RP-234056->RP-240801; 26/9/24: WID:RP-240801->RP-241824; 26/9/24: 38.774 added;; 18/7/25: WID:RP-241824->RP-251200",38.774000000000001,102,52,null,null,"Tue 02/01/24","Fri 18/07/25"]
[147,1021094,"   Core part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) ","NR_LPWUS-Core",2,"Rel-19","R1","Wed 13/12/23","Tue 09/09/25",0.9,"RP-251200","RP-251199","Xueming Pan, vivo","panxueming@vivo.com","14/3/24: Compl:0%->8%; Stat Rep: ->RP-240134; Rapporteur: vivo->Xueming Pan, vivo; Rap eMail: ->panxueming@vivo.com; ; 13/6/24: Compl:8%->20%; Stat Rep: RP-240134->RP-241039; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:20%->30%; Stat Rep: RP-241039->RP-24",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[148,1022094,"   Perf. part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) ","NR_LPWUS-Perf",2,"Rel-19","R4","Sun 18/08/24","Tue 03/03/26",0.05,"RP-251200","RP-251199","Xueming Pan, vivo","panxueming@vivo.com","14/3/24: Stat Rep: ->RP-240134; Rapporteur: vivo->Xueming Pan, vivo; Rap eMail: ->panxueming@vivo.com; ; 13/6/24: Stat Rep: RP-240134->RP-241039; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241039->RP-241822; ; 6/12/24: FCD:03/03/2025->03/03/2026; ",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[149,0,"Rel-19 Artificial Intelligence (AI)/Machine Learning (ML)","-",1,"Rel-19",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[150,1060078,"Study on Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface Phase 2 ","FS_NR_AIML_air_Ph2",1,"Rel-19","R1","Mon 14/10/24","Tue 09/09/25",0.9,"RP-250308","RP-251184","Qualcomm ",null,"6/3/25: FCD:07/09/2025->09/09/2025; Compl:0%->50%; Stat Rep: ->RP-250307; ; 3/4/25: WID:RP-243245->RP-250308; 6/6/25: Compl:50%->90%; Stat Rep: RP-250307->RP-251184; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[151,1040084,"Study on 3GPP AI/ML Consistency Alignment","FS_AIML_CAL",1,"Rel-19","SP","Sun 06/10/24","Fri 12/12/25",0,"SP-250745",null,"Johannes Achter, Magenta",null,"26/9/24: WID:SP-240970->SP-241368; 27/6/25: WID:SP-241368->SP-250745; 27/6/25: FCD:Fri 06/06/->12/25",null,104,53,null,null,"Thu 20/06/24","Fri 27/06/25"]
[152,950008,"Study on AI/ML Model Transfer Phase2 ","FS_AIML_MT_Ph2",1,"Rel-19","S1","Thu 10/03/22","Sat 09/09/23",1,"SP-220439",null,"Yang Xu, OPPO ","xuyang@oppo.com ","5/4/22: 22.875 added;; 4/6/22: 0%->15; 21/6/22: WID:SP-220083->SP-220439. FS_AIML_Ph2->FS_AIML_MT_Ph2; 13/7/22: 22.876 added;; 10/12/22: 15%->50; 10/12/22: FCD:12/12/2022->06/23; 17/3/23: 50%->75; 8/6/23: 75%->95; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 95","22.875; 22.876",95,48,null,null,"Thu 10/03/22","Wed 06/09/23"]
[153,950011,"Study on Artificial Intelligence (AI) and Machine Learning (ML) for Media ","FS_AI4Media",1,"Rel-19","S4","Sat 12/03/22","Fri 06/06/25",1,"SP-220328",null,"Eric Yip, Samsung ","eric.yip@samsung.com ","5/4/22: 26.927 added;; 4/6/22: 0%->10; 12/9/22: 10%->15; 12/9/22: FCD:12/03/2022->12/23; 11/12/22: 15%->20; 17/3/23: 20%->25; 8/6/23: 25%->35; 8/6/23: FCD:12/12/2023->/24; 7/9/23: 35%->40; 21/9/23: 26.847 added;; 8/12/23: 40%->50; 14/3/24: 50%->60; 14/...","26.927; 26.847",95,48,null,null,"Thu 10/03/22","Thu 05/06/25"]
[154,1000030,"AI/ML Model Transfer Phase 2 ","AIML_MT_Ph2",1,"Rel-19","S1","Thu 08/06/23","Tue 12/12/23",1,"SP-230514",null,"Yang Xu, OPPO ","xuyang<at>oppo.com ","; 6/9/23: 0%->80; 8/12/23: 80%->100",22.260999999999999,100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[155,1050047,"Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","AIML_CN",1,"Rel-19",null,"Wed 12/06/24","Tue 09/09/25",0.64,"SP-240991",null,"Xiaobo Wu, vivo ","(xiaobo.wu@vivo.com) ",null,"23.288; 23.501; 23.502; 23.503; 23.273 ",105,53,null,null,"Wed 12/06/24","NA"]
[156,1040033,"   Stage 2 of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","AIML_CN",2,"Rel-19","S2","Wed 12/06/24","Thu 17/10/24",0.99,"SP-240991",null,"Xiaobo Wu, vivo ","(xiaobo.wu@vivo.com) ","; 4/9/24: 0%->15; 5/12/24: 15%->85; 6/3/25: 85%->98; 5/6/25: 98%->99","23.288; 23.501; 23.502; 23.503; 23.273 ",104,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[157,1050014,"   CT aspects of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","AIML_CN",2,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.48,"CP-251283",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com",null,"29.508,29.513,29.520,29.522,29.552,29.574,29.575,29.576,29.591,24.080,29.503,29.510,29.518,29.572",105,53,null,"x","Wed 12/06/24","NA"]
[158,1050048,"      CT3 aspects of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","AIML_CN",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.7,"CP-251283",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com",null,null,105,53,null,"x","Wed 12/06/24","NA"]
[159,1050049,"      CT4 aspects of Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","AIML_CN",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.7,"CP-251283",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com","; 26/3/25: 29.570 added;",29.57,105,53,null,"x","Wed 12/06/24","Wed 26/03/25"]
[160,1060059,"   Security aspects of Core Network Enhanced Support for AIML ","AIML_CN_SEC",2,"Rel-19","S3","Thu 05/12/24","Fri 06/06/25",1,"SP-241957",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","; 6/3/25: 0%->80; 5/6/25: 80%->100",33.500999999999998,106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[161,1050044,"Application enablement for AI/ML services ","AIML_App",1,"Rel-19",null,"Tue 16/07/24","Tue 09/09/25",0.49,"SP-241008",null,"Pateromichelakis, Emmanouil (Manos), ","epateromiche@lenovo.com ",null,"23.436; 23.434; 23.558 ",105,53,null,null,"Wed 12/06/24","NA"]
[162,1040075,"   Stage 2 of Application enablement for AI/ML services ","AIML_App",2,"Rel-19","S6","Tue 16/07/24","Thu 12/12/24",1,"SP-241008",null,"Pateromichelakis, Emmanouil (Manos), ","epateromiche@lenovo.com ","; 4/9/24: 0%->40; 26/9/24: 23.482 added;; 5/12/24: 40%->100","23.436; 23.434; 23.558 ; 23.482",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[163,1050024,"   CT aspects of Application enablement for AI/ML services ","AIML_App",2,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.42,"CP-243310",null,"Atarius, Roozbeh (Lenovo)","ratarius@motorola.com",null,"24.559, 29.549, 29.558, 24.559, 29.549, 29.558",105,53,null,null,"Wed 12/06/24","NA"]
[164,1050045,"      CT1 aspects of Application enablement for AI/ML services ","AIML_App",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.6,"CP-243310",null,"Atarius, Roozbeh (Lenovo)","ratarius@motorola.com","; 26/9/24: 24.560 added;",null,105,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[165,1050046,"      CT3 aspects of Application enablement for AI/ML services ","AIML_App",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.6,"CP-243310",null,"Atarius, Roozbeh (Lenovo)","ratarius@motorola.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[166,1060011,"AI/ML Management Phase 2 ","AIML_MGT_Ph2",1,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.52,"SP-241944",null,"Hassan Al-Kanani (NEC)","Hassan.Alkanani@EMEA.NEC.COM","; 6/3/25: 0%->15; 6/6/25: 15%->52","28.105; 28.552; 28.554; 28.541 ",106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[167,1020068,"Study on Core Network Enhanced Support for Artificial Intelligence (AI)/Machine Learning (ML) ","FS_AIML_CN",1,"Rel-19","S2","Thu 04/01/24","Thu 06/06/24",1,"SP-241936",null,"Xiaobo Wu, vivo ","xiaobo.wu@vivo.com) ","14/3/24: 0%->25; 13/6/24: 25%->100; 26/9/24: WID:SP-231800->SP-241383; 8/1/25: WID:SP-241383->SP-241936; 6/3/25: 100%->100",null,102,52,null,null,"Wed 03/01/24","Thu 06/03/25"]
[168,1030035,"Study on security aspects of Core Network Enhanced Support for AIML ","FS_AIML_CN_SEC",1,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240509",null,"Chang Liu, ","liuchangyjy@chinamobile.com ","3/4/24: 33.784 added;; 13/6/24: 0%->35; 5/9/24: 35%->60; 5/12/24: 60%->100; 6/3/25: 100%->100; 5/6/25: 100%->100",33.783999999999999,103,52,null,null,"Thu 14/03/24","Thu 05/06/25"]
[169,1020007,"Study on AI/ML management - phase 2 ","FS_AIML_MGT_Ph2",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-241567",null,"Yizhi Yao (Intel) ","yizhi.yao@intel.com ","13/6/24: 0%->19; 16/7/24: WID:SP-231780->SP-240965; 4/9/24: 19%->55; 4/9/24: FCD:09/09/2024->12/24; 26/9/24: 28.858 added;; 5/12/24: 55%->100; 8/1/25: WID:SP-240965->SP-241567; 6/6/25: 100%->100",28.858000000000001,102,52,null,null,"Thu 07/12/23","Fri 06/06/25"]
[170,1010005,"Study on application layer support for AI/ML services ","FS_AIMLAPP",1,"Rel-19","S6","Thu 07/09/23","Mon 09/09/24",1,"SP-231182",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","8/12/23: 0%->35; 4/1/24: 23.700-82 added;; 14/3/24: 35%->55; 13/6/24: 55%->95; 4/9/24: 95%->100","23.700-82",101,51,null,null,"Thu 07/09/23","Wed 04/09/24"]
[171,1020083,"Study on enhancements for Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN ","FS_NR_AIML_NGRAN_enh",1,"Rel-19","R3","Wed 13/12/23","Mon 09/09/24",1,"RP-240323","RP-241791","ZTE ",null,"14/3/24: FCD:06/06/2024->/24; 2/4/24: WID:RP-234054->RP-240323; 3/4/24: 38.743 added;; 13/6/24: Compl:0%->80%; Stat Rep: ->RP-241097; ; 4/9/24: FCD:09/09/2024->24/09/2024; Compl:80%->100%; Stat Rep: RP-241097->RP-241791; ",38.743000000000002,102,52,null,null,"Tue 02/01/24","Wed 04/09/24"]
[172,1020084,"Study on Artificial Intelligence (AI)/Machine Learning (ML) for mobility in NR ","FS_NR_AIML_Mob",1,"Rel-19","R2","Thu 07/03/19","Tue 09/09/25",0.9,"RP-242393","RP-250970","Zhongda Du, OPPO","duzhongda@oppo.com","14/3/24: FCD:28/05/2021->12/12/2024; Stat Rep: ->RP-240083; Rapporteur: Oppo->Zhongda Du, OPPO; Rap eMail: ->duzhongda@oppo.com; ; 2/4/24: WID:RP-234055->RP-240082; 3/4/24: 38.744 added;; 4/9/24: FCD:12/12/2024->25/09/2024; Compl:0%->38%; Stat Rep: RP-...","38,744",102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[173,1020093,"Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface ","NR_AIML_air",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.5,"RP-243244",null,"Qualcomm ",null,"2/4/24: WID:RP-234039->RP-240774; 26/9/24: WID:RP-240774->RP-242399; 24/1/25: WID:RP-242399->RP-243244",null,102,52,null,null,"Tue 02/01/24","Fri 24/01/25"]
[174,1021093,"   Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface ","NR_AIML_air-Core",2,"Rel-19","R1","Wed 13/12/23","Tue 09/09/25",0.85,"RP-250792","RP-251185","Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson","juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsson.com","14/3/24: Compl:0%->5%; Stat Rep: ->RP-240499; Rapporteur: Qualcomm->Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson; Rap eMail: ->juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsso...",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[175,1022093,"   Perf. part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface ","NR_AIML_air-Perf",2,"Rel-19","R4","Sun 18/08/24","Tue 03/03/26",0.1,"RP-250792","RP-251185","Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson","juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsson.com","14/3/24: Stat Rep: ->RP-240499; Rapporteur: Qualcomm->Juan Montojo (RAN1); Xiaofeng Liu (RAN4); Marco Belleschi (RAN2/RAN3), Qualcomm; CAICT; Ericsson; Rap eMail: ->juanm@qti.qualcomm.com; liuxiaofeng1@caict.ac.cn; marco.belleschi@ericsson.com; ; 13/6/...",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[176,1050124,"Enhancements for Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN ","NR_AIML_NGRAN_enh",1,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.8,"RP-251245",null,"ZTE ",null,"3/4/25: WID:RP-242385->RP-250326; 18/7/25: WID:RP-250326->RP-251245",null,105,53,null,null,"Thu 26/09/24","Fri 18/07/25"]
[177,1051124,"   Core part: Enhancements for Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN ","NR_AIML_NGRAN_enh-Core",2,"Rel-19","R3","Mon 09/09/24","Tue 09/09/25",0.8,"RP-251245","RP-251246","ZTE ",null,"6/12/24: Compl:0%->30%; Stat Rep: ->RP-242503; ; 6/3/25: FCD:20/05/2025->09/09/2025; Compl:30%->50%; Stat Rep: RP-242503->RP-250327; ; 6/6/25: Compl:50%->80%; Stat Rep: RP-250327->RP-251246; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[178,0,"Rel-19 Ambient power-enabled Internet of Things ","-",1,"Rel-19",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[179,1020055,"Ambient power-enabled Internet of Things ","AmbientIoT",1,"Rel-19",null,"Thu 10/03/22","Tue 09/09/25",0.95,"SP-231403",null,"Xu, Weijie, OPPO ","xuweijie@oppo.com ","; 8/12/23: 0%->95",22.260999999999999,102,52,null,null,"Thu 07/12/23","Fri 08/12/23"]
[180,950004,"   Study on Ambient power-enabled Internet of Things ","FS_AmbientIoT",2,"Rel-19","S1","Thu 10/03/22","Tue 12/12/23",1,"SP-220085",null,"Rapporteur:Xu, weijie, OPPO ","xuweijie@oppo.com ","5/4/22: 22.840 added;; 4/6/22: 0%->25; 9/9/22: 25%->50; 10/12/22: 50%->65; 17/3/23: 65%->80; 17/3/23: FCD:12/12/2022->/23; 8/6/23: 80%->90; 8/6/23: FCD:03/03/2023->12/20; 6/9/23: 90%->95; 8/12/23: 95%->100",22.84,95,48,null,null,"Thu 10/03/22","Fri 08/12/23"]
[181,1020071,"   Study on Architecture support of Ambient power-enabled Internet of Things ","FS_AmbientIoT",2,"Rel-19","S2","Thu 04/01/24","Thu 12/12/24",1,"SP-240969",null,"Runze Zhou (Huawei) ","zhourunze@huawei.com ","14/3/24: 0%->25; 13/6/24: 25%->65; 16/7/24: WID:SP-231803->SP-240969; 4/9/24: 65%->80; 5/12/24: 80%->90; 6/3/25: 90%->100",null,102,52,null,null,"Wed 03/01/24","Thu 06/03/25"]
[182,1020030,"   Stage 1 of Ambient power-enabled Internet of Things ","AmbientIoT",2,"Rel-19","S1","Thu 07/12/23","Tue 12/12/23",1,"SP-231403",null,"Xu, Weijie, OPPO ","xuweijie@oppo.com ","; 8/12/23: 0%->95; 6/3/25: 95%->100",22.260999999999999,102,52,null,null,"Thu 07/12/23","Thu 06/03/25"]
[183,1070010,"   Architecture support of Ambient power-enabled Internet of Things ","AmbientIoT-ARC",2,"Rel-19","S2","Wed 26/03/25","Fri 06/06/25",0.9,"SP-250377",null,"Runze Zhou (Huawei) ","zhourunze@huawei.com ","; 5/6/25: 0%->90","23.501; 23.502 ",107,54,null,null,"Wed 05/03/25","Thu 05/06/25"]
[184,1080021,"   CT aspects of Ambient power-enabled Internet of Things","AmbientIoT-CT",2,"Rel-19","C1","Fri 06/06/25","Tue 09/09/25",0.84,"CP-251281",null,"Wass, Mikael, Huawei","mikael.wass@huawei.com","; 18/7/25: 24.369 added;","24.007, 29.522, 23.003, 29.518, 29.504, 29.505, 29.510, 29.571; 24.369",107,54,null,"x","Wed 05/03/25","Fri 18/07/25"]
[185,1080030,"      CT1 aspects of Ambient power-enabled Internet of Things","AmbientIoT-CT",3,"Rel-19","C1","Fri 06/06/25","Tue 09/09/25",0.3,"CP-251281",null,"Wass, Mikael, Huawei","mikael.wass@huawei.com",null,"29.522, 23.003, 29.518, 29.504, 29.505, 29.510, 29.571",107,54,null,"x","Wed 05/03/25","NA"]
[186,1080031,"      CT3 aspects of Ambient power-enabled Internet of Things","AmbientIoT-CT",3,"Rel-19","C3","Fri 06/06/25","Tue 09/09/25",0.7,"CP-251281",null,"Wass, Mikael, Huawei","mikael.wass@huawei.com",null,"29.522, 23.003, 29.518, 29.504, 29.505, 29.510, 29.571",107,54,null,"x","Wed 05/03/25","NA"]
[187,1080032,"      CT4 aspects of Ambient power-enabled Internet of Things","AmbientIoT-CT",3,"Rel-19","C4","Fri 06/06/25","Tue 09/09/25",0.6,"CP-251281",null,"Wass, Mikael, Huawei","mikael.wass@huawei.com","; 18/7/25: 29.506, 29.369added;","29.522, 23.003, 29.518, 29.504, 29.505, 29.510, 29.571; 29.506; 29.369",107,54,null,"x","Wed 05/03/25","Fri 18/07/25"]
[188,1020085,"Study on solutions for Ambient IoT (Internet of Things) in NR ","FS_Ambient_IoT_solutions",1,"Rel-19","R1","Wed 13/12/23","Thu 12/12/24",1,"RP-240826","RP-242965","Xiaodong Shen, CMCC","shenxiaodong@chinamobile.com","14/3/24: Compl:0%->8%; Stat Rep: ->RP-240155; Rapporteur: CMCC->Xiaodong Shen, CMCC; Rap eMail: ->shenxiaodong@chinamobile.com; ; 2/4/24: WID:RP-234058->RP-240826; 3/4/24: 38.769 added;; 13/6/24: Compl:8%->40%; Stat Rep: RP-240155->RP-241206; ; 4/9/24: FC",38.768999999999998,102,52,null,null,"Tue 02/01/24","Fri 24/01/25"]
[189,1030031,"Study on Security Aspect of Ambient IoT Services in 5G ","FS_Ambient_IoT_Sec",1,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",0.9,"SP-240506",null,"Marcus Wong, ","marcus.wong@oppo.com ","3/4/24: 33.713 added;; 13/6/24: 0%->30; 5/9/24: 30%->35; 5/12/24: 35%->55; 6/3/25: 55%->75; 6/3/25: FCD:12/12/2024->/25; 5/6/25: 75%->90",33.713000000000001,103,52,null,null,"Thu 14/03/24","Thu 05/06/25"]
[190,1070018,"Charging for Ambient power-enabled Internet of Things ","AmbientIoT-CH",1,"Rel-19","S5","Wed 26/03/25","Tue 09/09/25",1,"SP-250369",null,"YiMeng, DENG, Huawei ","dengyimeng@huawei.com ","; 6/6/25: 0%->100","32.240; 32.254; 32.291; 32.298 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[191,1070022,"Security Aspects of Ambient IoT Services in 5G ","AmbientIoT-SEC",1,"Rel-19","S3","Wed 26/03/25","Tue 09/09/25",0.45,"SP-250359",null,"Marcus Wong ","marcus.wong@oppo.co ","3/4/25: 33.369 added;; 5/6/25: 0%->45",33.369,107,54,null,null,"Wed 26/03/25","Thu 05/06/25"]
[192,1060084,"Solutions for Ambient IoT (Internet of Things) in NR ","Ambient_IoT_Solutions",1,"Rel-19",null,"Sun 19/05/24","Mon 02/03/26",0.36,"RP-250796",null,"CMCC ",null,"26/3/25: 38.391 added;; 26/3/25: 38.191 added;; 26/3/25: 38.194 added;; 26/3/25: 38.195 added;; 3/4/25: WID:RP-243326->RP-250796","38.391; 38.191; 38.194; 38.195",106,54,null,null,"Fri 24/01/25","Thu 03/04/25"]
[193,1061084,"   Core part: Solutions for Ambient IoT (Internet of Things) in NR ","Ambient_IoT_Solutions-Core",2,"Rel-19","R1","Mon 14/10/24","Tue 09/09/25",0.84,"RP-240796","RP-251399","CMCC ",null,"6/3/25: FCD:07/09/2025->09/09/2025; Compl:0%->27%; Stat Rep: ->RP-250267; ; 6/6/25: Compl:27%->84%; WID: RP-250796->RP-240796; Stat Rep: RP-250267->RP-251399; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[194,1062084,"   Perf. part: Solutions for Ambient IoT (Internet of Things) in NR ","Ambient_IoT_Solutions-Perf",2,"Rel-19","R4","Sun 08/12/24","Tue 03/03/26",0,"RP-240796","RP-251399","CMCC ",null,"6/3/25: FCD:01/03/2026->03/03/2026; Stat Rep: ->RP-250267; ; 6/6/25: WID: RP-250796->RP-240796; Stat Rep: RP-250267->RP-251399; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[195,0,"See also IoT_NTN_Ph3 under Satellite/NTN ","-",1,"Rel-19",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[196,0,"Rel-19 Internet of Things, RedCap, MTC","-",1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[197,1040133,"NR power class 2 RedCap (Reduced Capability) UE in FR1 ","NR_PC2_RedCap_UE",1,"Rel-19",null,"Thu 06/06/24","Fri 06/06/25",0.4,"RP-243267",null,"China Telecom ",null,"26/9/24: WID:RP-241665->RP-241997; 24/1/25: WID:RP-241997->RP-243267",null,104,53,null,null,"Tue 23/07/24","Fri 24/01/25"]
[198,1041133,"   Core part: NR power class 2 RedCap (Reduced Capability) UE in FR1 ","NR_PC2_RedCap_UE-Core",2,"Rel-19","R4","Thu 06/06/24","Fri 06/06/25",1,"RP-243267","RP-251452","China Telecom ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->20%; Stat Rep: ->RP-241998; ; 6/12/24: Compl:20%->50%; Stat Rep: RP-241998->RP-242859; ; 6/3/25: FCD:14/02/2025->06/06/2025; Compl:50%->70%; Stat Rep: RP-242859->RP-250372; ; 6/6/25: Compl:70%->100%; Stat Rep",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[199,1080078,"   UE Conformance - NR power class 2 RedCap (Reduced Capability) UE in FR1 ","NR_PC2_RedCap_UE-UEConTest",2,"Rel-19","R5","Fri 06/06/25","Sat 12/12/26",0,"RP-251456",null,"China Telecom ",null,"tested: REL-19 WI NR_PC2_RedCap_UE-Core ",null,108,55,null,null,"Fri 18/07/25","NA"]
[200,1050123,"Introduction of IoT-NTN TDD mode ","IoT_NTN_TDD",1,"Rel-19",null,"Mon 09/09/24","Tue 03/03/26",0.38,"RP-243293",null,"Iridium ",null,"24/1/25: WID:RP-242415->RP-243293",null,105,53,null,null,"Thu 26/09/24","Fri 24/01/25"]
[201,1051123,"   Core part: Introduction of IoT-NTN TDD mode ","IoT_NTN_TDD-Core",2,"Rel-19","R1","Mon 09/09/24","Tue 09/09/25",0.76,"RP-243293","RP-251175","Iridium ",null,"6/12/24: Compl:0%->20%; Stat Rep: ->RP-242652; ; 6/3/25: FCD:20/05/2025->09/09/2025; Compl:20%->30%; Stat Rep: RP-242652->RP-250045; ; 6/6/25: Compl:30%->76%; Stat Rep: RP-250045->RP-251175; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[202,1052123,"   Perf. part: Introduction of IoT-NTN TDD mode ","IoT_NTN_TDD-Perf",2,"Rel-19","R4","Sun 23/02/25","Tue 03/03/26",0,"RP-243293","RP-251175","Iridium ",null,"6/12/24: Stat Rep: ->RP-242652; ; 6/3/25: Stat Rep: RP-242652->RP-250045; ; 6/6/25: Stat Rep: RP-250045->RP-251175; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[203,1060008,"Management Aspects of RedCap features ","NR_RedCap_OAM",1,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.9,"SP-241941",null,"Zhen Xing (China Unicom)","xingz12@chinaunicom.cn ","; 6/3/25: 0%->50; 6/6/25: 50%->90","28.540; 28.541; 28.552; 28.554 ",106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[204,0,"Rel-19 Satellite (5GSAT), NTN","-",1,"Rel-19",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[205,1020058,"Satellite access Phase 3 ","5GSAT_Ph3",1,"Rel-19",null,"Thu 02/06/22","Tue 09/09/25",0.72,"SP-230516",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","; 6/9/23: 0%->95; 8/12/23: 95%->100",22.260999999999999,100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[206,960016,"   Study on satellite access - Phase 3 ","FS_5GSAT_Ph3",2,"Rel-19","S1","Thu 02/06/22","Sat 09/09/23",1,"SP-220679",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","17/8/22: WID:SP-220443->SP-220679; 9/9/22: 0%->35; 10/12/22: 35%->55; 10/12/22: FCD:10/03/2023->06/23; 17/3/23: 55%->80; 8/6/23: 80%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->100",null,96,49,null,null,"Thu 02/06/22","Wed 06/09/23"]
[207,1000024,"   Stage 1 of Satellite access Phase 3 ","5GSAT_Ph3",2,"Rel-19","S1","Thu 08/06/23","Tue 12/12/23",1,"SP-230516",null,"Rapporteur: Thierry Bérisot, Novamint ","tberisot@novamint.com ","; 6/9/23: 0%->95; 8/12/23: 95%->100",22.260999999999999,100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[208,1010033,"   Study on Integration of satellite components in the 5G architecture Phase 3","FS_5GSAT_Ph3_ARCH",2,"Rel-19","S2","Wed 20/09/23","Thu 06/06/24",1,"SP-231199",null,"Jean-Yves Fine (Thales) ","jean-yves.fine@thalesgroup.com ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-29 added;; 8/12/23: 0%->15; 4/1/24: 28.874 added;; 14/3/24: 15%->55; 13/6/24: 55%->100; 4/9/24: 99%->100","23.700-29; 28.874",101,51,null,null,"Wed 20/09/23","Wed 04/09/24"]
[209,1020053,"   Study on application enablement for Satellite access enabled 5G Services ","FS_5GSAT_Ph3_App",2,"Rel-19","S6","Wed 03/01/24","Mon 09/09/24",1,"SP-240296",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","8/12/23: 0%->5; 14/3/24: 0%->25; 2/4/24: WID:SP-231738->SP-240296; 3/4/24: 23.700-01 added;; 13/6/24: 25%->60; 4/9/24: 60%->100","23.700-01",102,52,null,null,"Thu 07/12/23","Wed 04/09/24"]
[210,1040027,"   Integration of satellite components in the 5G architecture Phase 3","5GSAT_Ph3-ARC",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-241386",null,"Hucheng Wang (CATT) ","wanghucheng@catt.cn","4/9/24: 0%->15; 26/9/24: WID:SP-240986->SP-241386; 5/12/24: 15%->65; 6/3/25: 65%->100; 5/6/25: 100%->100","23.501; 23.502; 23.503; 23.682; 23.228; 23.401 ",104,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[211,1040077,"   Application enablement for satellite access Phase 3 ","5GSAT_Ph3_App",2,"Rel-19","S6","Tue 16/07/24","Mon 28/10/24",1,"SP-241690",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","; 4/9/24: 0%->5; 5/12/24: 5%->75; 8/1/25: WID:SP-241010->SP-241690; 6/3/25: 75%->100","23.558; 23.434; 23.289 ",104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[212,1060023,"   CT aspects for application enablement for satellite access Phase 3","5GSAT_Ph3_App",2,"Rel-19","C3","Mon 02/12/24","Tue 09/09/25",0.36,"CP-243071",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com","; 4/9/24: 0%->5",null,104,53,null,null,"Wed 12/06/24","Wed 04/09/24"]
[213,1060032,"      CT1 aspects for application enablement for satellite access Phase 3","5GSAT_Ph3_App",3,"Rel-19","C1","Mon 02/12/24","Tue 09/09/25",0.3,"CP-243071",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com","; 4/9/24: 0%->5",null,104,53,null,null,"Wed 12/06/24","Wed 04/09/24"]
[214,1060033,"      CT3 aspects for application enablement for satellite access Phase 3","5GSAT_Ph3_App",3,"Rel-19","C3","Mon 02/12/24","Tue 09/09/25",0.75,"CP-243071",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com","; 4/9/24: 0%->5",null,104,53,null,null,"Wed 12/06/24","Wed 04/09/24"]
[215,1050019,"   CT aspects of integration of satellite components in the 5G architecture Phase 3","5GSAT_Ph3_ARCH",2,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.63,"CP-250134",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com","24.301,23.040,27.007,24.229,29.122,29.214,29.508,29.512,29.513,29.514,29.272,29.128,29.336,29.502,29.571,29.230",null,105,53,null,null,"Wed 12/06/24","NA"]
[216,1050041,"      CT1 aspects of integration of satellite components in the 5G architecture Phase 3","5GSAT_Ph3_ARCH",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.9,"CP-250134",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[217,1050042,"      CT3 aspects of integration of satellite components in the 5G architecture Phase 3","5GSAT_Ph3_ARCH",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.95,"CP-250134",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[218,1050043,"      CT4 aspects of integration of satellite components in the 5G architecture Phase 3","5GSAT_Ph3_ARCH",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.9,"CP-250134",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[219,1060016,"Management Aspects of NTN Phase 2 ","NTN_OAM_Ph2",1,"Rel-19","S5","Thu 30/01/25","Fri 06/06/25",1,"SP-250514",null,"MingRui Sun (China Unicom)","sunmr19@chinaunicom.cn","; 6/3/25: 0%->25; 6/6/25: 25%->100; 27/6/25: WID:SP-241949->SP-250514","28.541; 28.552; 28.554; 28.658; 28.540; 28.530 ; TS 28.657;TS 28.659;TS 28.707;TS 28.708;TS 28.709",106,54,null,null,"Thu 05/12/24","Fri 27/06/25"]
[220,1020044,"Study on Security Aspects of 5G Satellite Access Phase 3 ","FS_5GSAT_Ph3_SEC",1,"Rel-19","S3","Thu 04/01/24","Thu 12/12/24",1,"SP-240232",null,"Zhou Wei ","zhouwei@catt.cn ","No end date in initial WID SP-231317; 4/1/24: 33.700-29 added;; 14/3/24: 0%->10; 2/4/24: WID:SP-231790->SP-240232; 13/6/24: 10%->65; 5/9/24: 65%->75; 5/12/24: 75%->85; 6/3/25: 85%->100; 5/6/25: 100%->100","33.700-29",102,52,null,null,"Thu 07/12/23","Thu 05/06/25"]
[221,1060065,"Security Aspects of 5G Satellite Access Phase 3 ","5GSAT_Ph3_SEC",1,"Rel-19","S3","Thu 05/12/24","Fri 06/06/25",1,"SP-241780",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 6/3/25: 0%->35; 5/6/25: 35%->100",33.401000000000003,106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[222,1040014,"Study on charging aspects of satellite access Phase 3 ","FS_5GSAT_Ph3_CH",1,"Rel-19","S5","Wed 12/06/24","Wed 11/12/24",1,"SP-240980",null,"Yingying Liu, CATT, ","liuyingying@cictmobile.com ","13/6/24: 0%->10; 4/9/24: 10%->40; 26/9/24: 28.846 added;; 5/12/24: 40%->75; 5/12/24: FCD:12/12/2024->/25; 6/3/25: 75%->100",28.846,104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[223,1070014,"Charging aspects of satellite access Phase 3 ","5GSAT_Ph3-CH",1,"Rel-19","S5","Wed 26/03/25","Fri 06/06/25",0.9,"SP-250365",null,"Yingying Liu, CATT ","liuyingying@cictmobile.com ","; 6/6/25: 0%->90","32.240; 32.251; 32.255; 32.257; 32.260; 32.291; 32.298 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[224,1020097,"Non-Terrestrial Networks (NTN) for NR Phase 3 ","NR_NTN_Ph3",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.48,"RP-243300",null,"Thales ",null,"2/4/24: WID:RP-234078->RP-240775; 23/7/24: WID:RP-240775->RP-241667; 26/9/24: WID:RP-241667->RP-241789; 24/1/25: WID:RP-241789->RP-243300",null,102,52,null,null,"Tue 02/01/24","Fri 24/01/25"]
[225,1021097,"   Core part: Non-Terrestrial Networks (NTN) for NR Phase 3 ","NR_NTN_Ph3-Core",2,"Rel-19","R2","Wed 13/12/23","Tue 09/09/25",0.9,"RP-243300","RP-251003","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","14/3/24: Compl:0%->5%; Stat Rep: ->RP-240091; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com; ; 13/6/24: Compl:5%->25%; Stat Rep: RP-240091->RP-240923; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:25%->45%",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[226,1022097,"   Perf. part: Non-Terrestrial Networks (NTN) for NR Phase 3 ","NR_NTN_Ph3-Perf",2,"Rel-19","R4","Sun 18/08/24","Tue 03/03/26",0,"RP-243300","RP-251003","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","14/3/24: Stat Rep: ->RP-240091; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com; ; 13/6/24: Stat Rep: RP-240091->RP-240923; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-240923->RP-241742; ; 6/12/24: ",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[227,1020096,"Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 (for LTE)","IoT_NTN_Ph3",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.63,"RP-250472",null,"Mediatek ",null,"2/4/24: WID:RP-234077->RP-240776; 23/7/24: WID:RP-240776->RP-241624; 26/9/24: WID:RP-241624->RP-242397; 24/1/25: WID:RP-242397->RP-243278; 3/4/25: WID:RP-243278->RP-250472",null,102,52,null,null,"Tue 02/01/24","Thu 03/04/25"]
[228,1021096,"   Core part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 ","IoT_NTN_Ph3-Core",2,"Rel-19","R2","Wed 13/12/23","Tue 09/09/25",0.9,"RP-250472","RP-251289","Mediatek ",null,"13/6/24: Compl:0%->15%; Stat Rep: ->RP-241356; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:15%->30%; Stat Rep: RP-241356->RP-242050; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:30%->50%; Stat Rep: RP-242050->RP-242996; ; 6/3/25: FCD:26/02/2025->09/09/202",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[229,1032087,"   Perf. part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 ","IoT_NTN_Ph3-Perf",2,"Rel-19","R4","Sun 13/10/24","Tue 03/03/26",0.3,"RP-250472","RP-251289","Mediatek ",null,"13/6/24: FCD:03/03/2026->12/12/2025; Stat Rep: ->RP-241356; ; 4/9/24: FCD:12/12/2025->26/03/2025; Stat Rep: RP-241356->RP-242050; ; 6/12/24: Stat Rep: RP-242050->RP-242996; ; 6/3/25: WID: RP-243278->RP-242397; Stat Rep: RP-242996->RP-250470; ; 6/6/25: Com",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[230,1030076,"Inter-RAT mode mobility support from E-UTRAN TN to NR NTN ","LTE_TN_NR_NTN_mob",1,"Rel-19",null,"Sun 03/03/24","Mon 09/09/24",0.99,"RP-240924",null,"Thales ",null,"23/7/24: WID:RP-240846->RP-240924",null,103,52,null,null,"Tue 02/04/24","Tue 23/07/24"]
[231,1031076,"   Core part: Inter-RAT mode mobility support from E-UTRAN TN to NR NTN ","LTE_TN_NR_NTN_mob-Core",2,"Rel-19","R2","Sun 03/03/24","Tue 09/09/25",0.99,"RP-240846","RP-251004","Thales ",null,"13/6/24: Compl:0%->70%; Stat Rep: ->RP-240925; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:70%->95%; WID: RP-240924->RP-240846; Stat Rep: RP-240925->RP-241741; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:95%->96%; Stat Rep: RP-241741->RP-242463; ; 6/3/25",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[232,1030086,"Enhanced requirements and test methodology for NR NTN and IoT NTN ","NR_IoT_NTN_req_test_enh",1,"Rel-19",null,"Sun 03/03/24","Mon 03/03/25",0.61,"RP-242901",null,"Samsung ",null,"23/7/24: WID:RP-240857->RP-241281; 26/9/24: WID:RP-241281->RP-241985; 24/1/25: WID:RP-241985->RP-242901",null,103,52,null,null,"Tue 02/04/24","Fri 24/01/25"]
[233,1031086,"   Core part: Enhanced requirements and conductive test methodology for NR NTN and IoT NTN ","NR_IoT_NTN_req_test_enh-Core",2,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.88,"RP-242901","RP-251015","Samsung ",null,"13/6/24: Stat Rep: ->RP-241280; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->16%; Stat Rep: RP-241280->RP-241984; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:16%->50%; Stat Rep: RP-241984->RP-242592; ; 6/3/25: FCD:23/03/2025->09/09/2025; Compl:50%->65",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[234,1032086,"   Perf. Part: Enhanced requirements and conductive test methodology for NR NTN and IoT NTN ","NR_IoT_NTN_req_test_enh-Perf",2,"Rel-19","R4","Sun 03/03/24","Tue 03/03/26",0.4,"RP-242901","RP-251015","Samsung ",null,"13/6/24: Stat Rep: ->RP-241280; ; 4/9/24: FCD:03/03/2026->26/03/2025; Compl:0%->10%; Stat Rep: RP-241280->RP-241984; ; 6/12/24: FCD:03/03/2025->03/03/2026; Compl:10%->30%; Stat Rep: RP-241984->RP-242592; ; 6/3/25: FCD:22/07/2025->03/03/2026; Compl:30%->35",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[235,1040129,"Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","NR_NTN_Sband",1,"Rel-19",null,"Thu 06/06/24","Fri 06/06/25",1,"RP-250488",null,"Qualcomm ",null,"26/9/24: WID:RP-241661->RP-241885; 3/4/25: WID:RP-241885->RP-250488",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[236,1041129,"   Core part: Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","NR_NTN_Sband-Core",2,"Rel-19","R4","Thu 06/06/24","Fri 06/06/25",1,"RP-250488","RP-251476","Qualcomm ",null,"4/9/24: FCD:03/03/2025->25/06/2025; Compl:0%->20%; Stat Rep: ->RP-241884; ; 6/12/24: FCD:06/06/2025->03/03/2025; Compl:20%->50%; Stat Rep: RP-241884->RP-242615; ; 6/3/25: FCD:09/12/2024->06/06/2025; Compl:50%->70%; Stat Rep: RP-242615->RP-250487; ; 6/6/2",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[237,1042129,"   Perf. part: Introduction of another NR NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","NR_NTN_Sband-Perf",2,"Rel-19","R4","Thu 26/09/24","Fri 06/06/25",1,"RP-250488","RP-251476","Qualcomm ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Stat Rep: ->RP-241884; ; 6/12/24: Stat Rep: RP-241884->RP-242615; ; 6/3/25: Stat Rep: RP-242615->RP-250487; ; 6/6/25: Compl:0%->100%; Stat Rep: RP-250487->RP-251476; ",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[238,1040130,"Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","IoT_NTN_FDD_S_band",1,"Rel-19",null,"Thu 06/06/24","Fri 06/06/25",1,"RP-251820",null,"Mediatek ",null,"26/9/24: WID:RP-241662->RP-242062; 3/4/25: WID:RP-242062->RP-250474; 18/7/25: WID:RP-250474->RP-251820",null,104,53,null,null,"Tue 23/07/24","Fri 18/07/25"]
[239,1041130,"   Core part: Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","IoT_NTN_FDD_S_band-Core",2,"Rel-19","R4","Thu 06/06/24","Fri 06/06/25",1,"RP-251820","RP-251290","Mediatek ",null,"4/9/24: FCD:03/03/2025->25/06/2025; Compl:0%->20%; Stat Rep: ->RP-242061; ; 6/12/24: FCD:06/06/2025->03/03/2025; Compl:20%->50%; WID: RP-241662->RP-242062; Stat Rep: RP-242061->RP-242999; ; 6/3/25: FCD:09/12/2024->06/06/2025; Compl:50%->70%; Stat Rep: RP",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[240,1042130,"   Perf. part: Introduction of another IoT-NTN S-band (MSS band 2000-2020 MHz UL and 2180-2200 MHz DL) ","IoT_NTN_FDD_S_band-Perf",2,"Rel-19","R4","Thu 26/09/24","Fri 06/06/25",1,"RP-251820","RP-251290","Mediatek ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Stat Rep: ->RP-242061; ; 6/12/24: WID: RP-241662->RP-242062; Stat Rep: RP-242061->RP-242999; ; 6/3/25: Stat Rep: RP-242999->RP-250473; ; 6/6/25: Compl:0%->100%; Stat Rep: RP-250473->RP-251290; ",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[241,1040135,"Introduction of Ku bands for NR NTN ","NR_NTN_Ku_bands",1,"Rel-19",null,"Thu 06/06/24","Mon 03/03/25",0.33,"RP-250799",null,"Intelsat ",null,"24/1/25: WID:RP-241690->RP-243314; 3/4/25: WID:RP-243314->RP-250799",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[242,1041135,"   Core part: Introduction of Ku bands for NR NTN ","NR_NTN_Ku_bands-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.65,"RP-250799","RP-251271","Intelsat ",null,"4/9/24: FCD:09/09/2025->24/09/2024; Compl:0%->15%; Stat Rep: ->RP-241788; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->30%; Stat Rep: RP-241788->RP-242946; ; 6/3/25: FCD:19/04/2025->09/09/2025; Compl:30%->50%; Stat Rep: RP-242946->RP-250466; ; 6/6/2",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[243,1042135,"   Perf. part: Introduction of Ku bands for NR NTN ","NR_NTN_Ku_bands-Perf",2,"Rel-19","R4","Fri 20/12/24","Tue 03/03/26",0,"RP-250799","RP-251271","Intelsat ",null,"4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: ->RP-241788; ; 6/12/24: FCD:03/03/2025->03/03/2026; Stat Rep: RP-241788->RP-242946; ; 6/3/25: Stat Rep: RP-242946->RP-250466; ; 6/6/25: Compl:0%->50%; WID: RP-250799->RP-243314; Stat Rep: RP-250466->RP-251271",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[244,1040134,"New NR NTN bands to support Extended L-band and combined MSS L-band and Extended L-band ranges ","NR_NTN_combinedLband",1,"Rel-19",null,"Thu 06/06/24","Fri 06/06/25",0.9,"RP-250983",null,"Aalyria",null,"26/9/24: WID:RP-241689->RP-241856; 3/4/25: WID:RP-241856->RP-250752; rapporteur: Inmarsat=> Aalyria; 18/7/25: WID:RP-250752->RP-250983",null,104,53,null,null,"Tue 23/07/24","Fri 18/07/25"]
[245,1041134,"   Core part: Introduction of new NR NTN bands to support the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) and the combined MSS L-band and Extended L-band ranges (UL 1626.5-1660.5 MHz and 1668-1675 MHz, DL 1518-1559 MHz) ","NR_NTN_combinedLband-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.9,"RP-250983","RP-250982","Aalyria",null,"4/9/24: FCD:03/03/2025->25/03/2025; Compl:0%->15%; Stat Rep: ->RP-241782; ; 6/12/24: Compl:15%->35%; Stat Rep: RP-241782->RP-242601; ; 6/3/25: FCD:09/12/2024->06/06/2025; Compl:35%->70%; Stat Rep: RP-242601->RP-250751; ; 6/6/25: FCD:Fri 06/06/25->Tue 09/",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[246,1042134,"   Perf. part: Introduction of new NR NTN bands to support the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) and the combined MSS L-band and Extended L-band ranges (UL 1626.5-1660.5 MHz and 1668-1675 MHz, DL 1518-1559 MHz) ","NR_NTN_combinedLband-Perf",2,"Rel-19","R4","Thu 26/09/24","Tue 09/09/25",0.9,"RP-250983","RP-250982","Aalyria",null,"4/9/24: FCD:06/06/2025->25/06/2025; Stat Rep: ->RP-241782; ; 6/12/24: Stat Rep: RP-241782->RP-242601; ; 6/3/25: Stat Rep: RP-242601->RP-250751; ; 6/6/25: FCD:Fri 06/06/25->Tue 09/09/25; Compl:0%->90%; Stat Rep: RP-250751->RP-250982; ",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[247,1050127,"Introduction of additional operating NR bands for HAPS (High Altitude Platform Station) ","NR_HAPS_bands",1,"Rel-19",null,"Mon 09/09/24","Mon 03/03/25",1,"RP-242891",null,"SoftBank ",null,"24/1/25: WID:RP-242373->RP-242891",null,105,53,null,null,"Thu 26/09/24","Fri 24/01/25"]
[248,1051127,"   Core part: Introduction of additional operating NR bands for HAPS (High Altitude Platform Station) ","NR_HAPS_bands-Core",2,"Rel-19","R4","Mon 09/09/24","Mon 03/03/25",1,"RP-242891","RP-250407","SoftBank ",null,"6/12/24: FCD:12/12/2024->03/03/2025; Compl:0%->99%; Stat Rep: ->RP-242890; ; 6/3/25: FCD:08/01/2025->03/03/2025; Compl:99%->100%; Stat Rep: RP-242890->RP-250407; ",null,105,53,null,null,"Thu 26/09/24","Thu 06/03/25"]
[249,1052127,"   Stopped - Perf. part: Introduction of additional operating NR bands for HAPS (High Altitude Platform Station) ","NR_HAPS_bands-Perf",2,"Rel-19","R4","Mon 09/09/24","Thu 12/12/24",1,"RP-242891",null,"SoftBank ",null,"24/1/25: Stopped at 0%",null,105,53,null,null,"Thu 26/09/24","Fri 24/01/25"]
[250,0,"Rel-19 XR (eXtended Reality), Metaverse","-",1,"Rel-19",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[251,1020056,"Localized Mobile Metaverse Services ","Metaverse",1,"Rel-19",null,"Thu 10/03/22","Tue 09/09/25",0.76,"SP-230509",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","; 6/9/23: 0%->80; 21/9/23: 22.156 added;; 8/12/23: 80%->100","new 22.156, 22.261 ; 22.156",100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[252,950005,"   Study on Localized Mobile Metaverse Services ","FS_Metaverse",2,"Rel-19","S1","Thu 10/03/22","Sat 09/09/23",1,"SP-220353",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","5/4/22: 22.856 added;; 4/6/22: 0%->15; 9/9/22: 15%->40; 10/12/22: 40%->55; 17/3/23: 55%->75; 8/6/23: 75%->90; 8/6/23: FCD:03/03/2023->09/20; 8/12/23: 90%->100",22.856000000000002,95,48,null,null,"Thu 10/03/22","Fri 08/12/23"]
[253,1000028,"   Stage 1 of Localized Mobile Metaverse Services ","Metaverse",2,"Rel-19","S1","Thu 08/06/23","Tue 12/12/23",1,"SP-230509",null,"Guttman, Erik, Samsung ","erik.guttman@samsung.com ","; 6/9/23: 0%->80; 21/9/23: 22.156 added;; 8/12/23: 80%->100","new 22.156, 22.261 ; 22.156",100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[254,1040076,"   Application enablement for mobile metaverse services ","Metaverse_App",2,"Rel-19","S6","Tue 16/07/24","Mon 28/10/24",1,"SP-241390",null,"Shah, Sapan, Samsung ","<sapan.shah@samsung.com> ","; 4/9/24: 0%->25; 26/9/24: WID:SP-241009->SP-241390; 26/9/24: 23.437 added;; 5/12/24: 25%->80; 6/3/25: 80%->100; 26/3/25: 23.438 added;","23.434; 23.542; 23.558; 23.436 ; 23.437; 23.438",104,53,null,null,"Wed 12/06/24","Wed 26/03/25"]
[255,1020052,"   Study on application enablement for Localized Mobile Metaverse Services ","FS_Metaverse_App",2,"Rel-19","S6","Wed 03/01/24","Mon 09/09/24",1,"SP-231806",null,"Shah, Sapan, Samsung ","sapan.shah@samsung.com ","8/12/23: 0%->10; 14/3/24: 0%->30; 3/4/24: 23.700-21 added;; 13/6/24: 30%->70; 4/9/24: 70%->100","23.700-21",102,52,null,null,"Thu 07/12/23","Wed 04/09/24"]
[256,1030039,"   Study on security aspects of 5G Mobile Metaverse services ","FS_Metaverse_Sec",2,"Rel-19","S3","Tue 02/04/24","Fri 06/06/25",1,"SP-240508",null,"Rohini Rajendran, ","r.rohini@samsung.com ","3/4/24: 33.721 added;; 13/6/24: 0%->20; 5/9/24: 20%->50; 5/12/24: 50%->70; 6/3/25: 70%->79; 6/3/25: FCD:12/12/2024->/25; 5/6/25: 79%->100; 5/6/25: FCD:Sat 25/01/->/25",33.720999999999997,103,52,null,null,"Thu 14/03/24","Thu 05/06/25"]
[257,1050025,"   CT aspects of Application enablement for mobile metaverse services ","Metaverse_App",2,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.43,"CP-251132",null,"Vijay Sangameshwara, Samsung","s.vijay@samsung.com",null,"24.583, 24.545, 29.549",105,53,null,"x","Wed 12/06/24","NA"]
[258,1050060,"      CT1 aspects of Application enablement for mobile metaverse services ","Metaverse_App",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.7,"CP-251132",null,"Vijay Sangameshwara, Samsung","s.vijay@samsung.com","; 26/9/24: 24.437 added;",null,105,53,null,"x","Wed 12/06/24","Thu 26/09/24"]
[259,1050061,"      CT3 aspects of Application enablement for mobile metaverse services ","Metaverse_App",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.55000000000000004,"CP-251132",null,"Vijay Sangameshwara, Samsung","s.vijay@samsung.com",null,null,105,53,null,"x","Wed 12/06/24","NA"]
[260,1060060,"   Security aspects of 5G Mobile Metaverse services ","Metaverse_Sec",2,"Rel-19","S3","Thu 02/01/25","Mon 03/03/25",0,"SP-250075",null,"Rohini Rajendran, r.rohini@samsung.com ","Lihui Xiong, xionglihui@oppo.com ","; 26/3/25: WID:SP-241775->SP-250075",33.433999999999997,106,54,null,null,"Thu 05/12/24","Wed 26/03/25"]
[261,1060034,"Extended Reality and Media",null,1,"Rel-19",null,"Thu 16/03/23","Sat 06/06/26",0.75,null,null,null,null,null,null,104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[262,990052,"   Supporting UE Mobility for XR Services ","XRMobility",2,"Rel-19","S1","Thu 16/03/23","Tue 06/06/23",1,"SP-230233",null,"Xiaonan Shi, ChinaMobile ","shixiaonan@chinamobile.com ","; 17/3/23: 0%->50; 6/9/23: 50%->100",22.260999999999999,99,50,null,null,"Thu 16/03/23","Wed 06/09/23"]
[263,1010032,"   Study on Extended Reality and Media service (XRM) Phase 2 ","FS_XRM_Ph2",2,"Rel-19","S2","Wed 03/01/24","Mon 09/09/24",1,"SP-231671",null,"Primary Rapporteur: Devaki Chandramouli (Nokia) ","devaki.chandramouli@nokia.com. ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-70 added;; 8/12/23: 0%->13; 14/3/24: 0%->45; 13/6/24: FCD:05/06/2024->/24; 13/6/24: 45%->90; 4/9/24: 90%->100","23.700-70",101,51,null,null,"Wed 20/09/23","Wed 04/09/24"]
[264,1040032,"   Extended Reality and Media service (XRM) Phase 2 ","XRM_Ph2",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-241385",null,"Georgios Gkellas (Nokia), ","Georgios.Gkellas@nokia.com. ","; 4/9/24: 0%->5; 26/9/24: WID:SP-240990->SP-241322; 26/9/24: WID:SP-241322->SP-241385; 5/12/24: 5%->65; 6/3/25: 65%->100","23.501; 23.502; 23.503; 23.316 ",104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[265,1060027,"   CT aspects of Extended Reality and Media service (XRM) Phase 2 ","XRM_Ph2",2,"Rel-19",null,"Mon 02/12/24","Tue 09/09/25",0.91,"CP-251135",null,"Ravindran, Parthasarathi, Nokia","parthasarathi.ravindran@nokia.com",null,"24.501, 29.122, 29.508, 29.512, 29.514, 29.522, 29.513, 29.561, 29.281, 29.244, 29.502, 29.564, 29.571",104,53,null,"x","Wed 12/06/24","Thu 26/09/24"]
[266,1060035,"      CT1 aspects of Extended Reality and Media service (XRM) Phase 2 ","XRM_Ph2",3,"Rel-19","C1","Mon 02/12/24","Tue 09/09/25",0.98,"CP-251135",null,"Ravindran, Parthasarathi, Nokia","parthasarathi.ravindran@nokia.com",null,null,104,53,null,"x","Wed 12/06/24","Thu 26/09/24"]
[267,1060036,"      CT3 aspects of Extended Reality and Media service (XRM) Phase 2 ","XRM_Ph2",3,"Rel-19","C3","Mon 02/12/24","Tue 09/09/25",0.85,"CP-251135",null,"Ravindran, Parthasarathi, Nokia","parthasarathi.ravindran@nokia.com",null,null,104,53,null,"x","Wed 12/06/24","Thu 26/09/24"]
[268,1060037,"      CT4 aspects of Extended Reality and Media service (XRM) Phase 2 ","XRM_Ph2",3,"Rel-19","C4","Mon 02/12/24","Tue 09/09/25",0.9,"CP-251135",null,"Ravindran, Parthasarathi, Nokia","parthasarathi.ravindran@nokia.com",null,null,104,53,null,"x","Wed 12/06/24","Thu 26/09/24"]
[269,1020051,"   Study on Application enabler for XR Services ","FS_XRApp",2,"Rel-19","S6","Wed 03/01/24","Thu 12/12/24",1,"SP-2315739",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","8/12/23: 0%->10; 14/3/24: 0%->20; 3/4/24: 23.700-23 added;; 13/6/24: 20%->65; 4/9/24: 65%->90; 5/12/24: 90%->100; 5/12/24: FCD:09/09/2024->12/24","23.700-23",102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[270,1040074,"   Application enablement for XRM Services Phase 2 ","XRM_Ph2_App",2,"Rel-19","S6","Tue 16/07/24","Mon 28/10/24",1,"SP-241207",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","; 4/9/24: 0%->15; 26/9/24: WID:SP-241007->SP-241207; 5/12/24: 15%->90; 6/3/25: 90%->100","23.433; 23.558 ",104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[271,1060024,"   CT aspects of Application enablement for XRM Services Phase 2 ","XRM_Ph2_App",2,"Rel-19",null,"Mon 02/12/24","Tue 09/09/25",0.69,"CP-243072",null,"Zhenning, Huang, China Mobile","huangzhenning@chinamobile.com",null,"24.543, 24.548, 29.548, 29.549, 29.558",104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[272,1060038,"      CT1 aspects of Application enablement for XRM Services Phase 2 ","XRM_Ph2_App",3,"Rel-19","C1","Thu 27/02/25","Tue 09/09/25",0.4,"CP-243072",null,"Zhenning, Huang, China Mobile","huangzhenning@chinamobile.com",null,null,104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[273,1060039,"      CT3 aspects of Application enablement for XRM Services Phase 2 ","XRM_Ph2_App",3,"Rel-19","C3","Mon 02/12/24","Tue 09/09/25",0.9,"CP-243072",null,"Zhenning, Huang, China Mobile","huangzhenning@chinamobile.com",null,null,104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[274,1070021,"   Protection of XRM Media related information ","XRM_Ph2-SEC",2,"Rel-19","S3","Tue 11/02/25","Mon 03/03/25",0,"SP-250361",null,"Daniel Cho ","daniel.cho@ericsson.com ",null,33.500999999999998,107,54,null,null,"Wed 05/03/25","NA"]
[275,1080016,"   OAM support for Extended Reality and Media service (XRM) phase 2 ","XRM_Ph2-OAM",2,"Rel-20","S5","Thu 05/06/25","Sat 06/06/26",0,"SP-250880",null,"Xie Pengxiang (ZTE), ","xie.pengxiang@zte.com.cn ",null,"28.540; 28.541; 28.552; 28.554 ",108,55,null,null,"Thu 05/06/25","NA"]
[276,1020098,"XR (eXtended Reality) for NR Phase 3 ","NR_XR_Ph3",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.48,"RP-250107",null,"Nokia ",null,"2/4/24: WID:RP-234080->RP-240791; 26/9/24: WID:RP-240791->RP-241771; 24/1/25: WID:RP-241771->RP-243318; 3/4/25: WID:RP-243318->RP-250107",null,102,52,null,null,"Tue 02/01/24","Thu 03/04/25"]
[277,1021098,"   Core part: XR (eXtended Reality) for NR Phase 3 ","NR_XR_Ph3-Core",2,"Rel-19","R2","Wed 13/12/23","Tue 09/09/25",0.9,"RP-250107","RP-251002","Benoist Sebire, Nokia","benoist.sebire@nokia.com","14/3/24: Compl:0%->2%; Stat Rep: ->RP-240081; Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com; ; 13/6/24: Compl:2%->18%; Stat Rep: RP-240081->RP-240927; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:18%->30%; Stat Rep: RP-240",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[278,1022098,"   Perf. part: XR (eXtended Reality) for NR Phase 3 ","NR_XR_Ph3-Perf",2,"Rel-19","R4","Sun 18/08/24","Tue 03/03/26",0,"RP-250107","RP-251002","Benoist Sebire, Nokia","benoist.sebire@nokia.com","14/3/24: Stat Rep: ->RP-240081; Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com; ; 13/6/24: Stat Rep: RP-240081->RP-240927; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-240927->RP-241770; ; 6/12/24: FCD:03/03/2025->03",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[279,1030045,"Indirect Network Sharing ","TEI19_NetShare",1,"Rel-19",null,"Thu 10/03/22","Tue 09/09/25",1,null,null,null,null,null,null,103,52,null,null,"Wed 13/03/24","NA"]
[280,950006,"   Study on Network Sharing Aspects ","FS_NetShare",2,"Rel-19","S1","Thu 10/03/22","Sat 09/09/23",1,"SP-220087",null,"Wei, Qun, China Unicom ","Weiqun5 <at> chinaunicom.cn ","5/4/22: 22.851 added;; 4/6/22: 0%->10; 9/9/22: 10%->20; 10/12/22: 20%->75; 17/3/23: 75%->80; 17/3/23: FCD:12/12/2022->/23; 8/6/23: 80%->95; 8/6/23: FCD:03/03/2023->09/20; 6/9/23: 95%->100",22.850999999999999,95,48,null,null,"Thu 10/03/22","Wed 06/09/23"]
[281,1000029,"   (Stage 1 of) Indirect Network Sharing ","NetShare",2,"Rel-19","S1","Thu 08/06/23","Tue 12/12/23",1,"SP-230511",null,"Wei, Qun, China Unicom ","Weiqun5 <at> chinaunicom.cn ","; 6/9/23: 0%->100",22.260999999999999,100,51,null,null,"Thu 08/06/23","Wed 06/09/23"]
[282,1030011,"   (Stage 2 of) Indirect Network Sharing ","TEI19_NetShare",2,"Rel-19","S2","Tue 02/04/24","Thu 06/06/24",1,"SP-240488",null,"Xing, Tianqi, China Unicom, ","xingtq@chinaunicom.cn ","; 13/6/24: FCD:12/12/2024->06/24; 13/6/24: 0%->100","23.501; 23.502 ",103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[283,1040019,"   Charging enhancement for indirect network sharing ","NetShare_CH",2,"Rel-19","S5","Wed 12/06/24","Thu 12/12/24",1,"SP-241004",null,"Robert Törnkvist, Ericsson, ","robert.tornkvist@ericsson.com ","; 5/12/24: 0%->100","32.240; 32.255; 32.256 ",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[284,1050004,"   CT aspects of indirect network sharing ","TEI19_NetShare",2,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",1,"CP-250019",null,"Xing Tianqi, China Unicom","xingtq@chinaunicom.cn",null,"24.501,29.507,29.525,29.531,29.510,29.502,29.509,29.503,29.536",105,53,null,null,"Wed 12/06/24","NA"]
[285,1050074,"      CT1 aspects of indirect network sharing ","TEI19_NetShare",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",1,"CP-250019",null,"Xing Tianqi, China Unicom","xingtq@chinaunicom.cn",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[286,1070048,"      CT3 aspects of indirect network sharing ","TEI19_NetShare",3,"Rel-19","C3","Mon 03/03/25","Tue 09/09/25",1,"CP-250019",null,"Xing Tianqi, China Unicom","xingtq@chinaunicom.cn",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[287,1050075,"      CT4 aspects of indirect network sharing ","TEI19_NetShare",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",1,"CP-250019",null,"Xing Tianqi, China Unicom","xingtq@chinaunicom.cn",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[288,1060017,"Management of Network Sharing Phase 3","NetShare_OAM_Ph3",1,"Rel-19","S5","Thu 30/01/25","Fri 06/06/25",0.95,"SP-241950",null,"ZhaoNing Wang (China Unicom)","wangzn18@chinaunicom.cn","; 6/3/25: 0%->50; 6/6/25: 50%->95","28.552; 32.130; 28.541 ",106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[289,1030046,"Roaming Value-Added Services ","TEI19_RVAS",1,"Rel-19",null,"Thu 02/06/22","Fri 06/06/25",0.87,null,null,null,null,null,null,103,52,null,null,"Wed 13/03/24","NA"]
[290,960015,"   Study on roaming value added services ","FS_RVAS",2,"Rel-19","S1","Thu 02/06/22","Mon 12/12/22",1,"SP-220442",null,"Peter Bleckert, Ericsson ",null,"13/7/22: 22.877 added;; 9/9/22: 0%->60; 10/12/22: FCD:10/03/2023->12/22; 10/12/22: 60%->100",22.876999999999999,96,49,null,null,"Thu 02/06/22","Sat 10/12/22"]
[291,990051,"   Roaming Value-Added Services ","RVAS",2,"Rel-19","S1","Thu 02/02/23","Fri 03/03/23",1,"SP-230231",null,"Peter Bleckert, Ericsson ",null,"; 17/3/23: 0%->100",22.260999999999999,99,50,null,null,"Thu 16/03/23","Fri 17/03/23"]
[292,1030013,"   Architecture support of roaming value-added services ","TEI19_RVAS",2,"Rel-19","S2","Wed 13/03/24","Thu 06/06/24",1,"SP-240119",null,"Qian Chen, Ericsson, ","qian.xb.chen@ericsson.com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.501; 23.502 ",103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[293,1050002,"   CT aspects of Architecture support of roaming value-added services ","TEI19_RVAS",2,"Rel-19",null,"Mon 09/09/24","Fri 06/06/25",0.81,"CP-242022",null,"Frank Yong, Yang, Ericsson","frank.yong.yang@ericsson.com",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[294,1050087,"      CT3 aspects of Architecture support of roaming value-added services ","TEI19_RVAS",3,"Rel-19","C3","Mon 09/09/24","Fri 06/06/25",0.9,"CP-242022",null,"Frank Yong, Yang, Ericsson","frank.yong.yang@ericsson.com",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[295,1050088,"      CT4 aspects of Architecture support of roaming value-added services ","TEI19_RVAS",3,"Rel-19","C4","Mon 09/09/24","Fri 06/06/25",1,"CP-242022",null,"Frank Yong, Yang, Ericsson","frank.yong.yang@ericsson.com",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[296,0,"Rel-19 user plane","-",1,"Rel-19",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[297,1080048,"Media Messaging Enhancements ","MeME-MED",1,"Rel-19","S4","Thu 05/06/25","Tue 09/09/25",0,"SP-250632",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ",null,26.143000000000001,108,55,null,null,"Thu 05/06/25","NA"]
[298,1070056,"Avatar Communications in AR Calls ","AvCall-MED",1,"Rel-19","S4","Thu 06/03/25","Tue 09/09/25",0.15,"SP-250264",null,"Bouazizi, Imed, Qualcomm, ","bouazizi AT qti dot qualcomm dot com ","; 5/6/25: 0%->15",26.263999999999999,107,54,null,null,"Wed 05/03/25","Thu 05/06/25"]
[299,1050037,"Study on immersive Real-Time Communication for WebRTC, Phase 2 ","FS_iRTCW_Ph2",1,"Rel-19","S4","Mon 09/09/24","Fri 06/06/25",1,"SP-241374",null,"Hakju Ryan Lee, Samsung Electronics, CO., LTD, ","hakju00.lee@samsung.com ","5/12/24: 0%->15; 6/3/25: 15%->35; 26/3/25: 26.830 added;; 5/6/25: 35%->100; 5/6/25: FCD:Mon 03/03/->/25",26.83,105,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[300,1050113,"Terminal Audio quality performance and Test methods for Immersive Audio Services, Phase 2 ","ATIAS_Ph2",1,"Rel-19","S4","Mon 09/09/24","Tue 09/09/25",0.65,"SP-241314",null,"Jan Reimes, HEAD acoustics GmbH, ","jan.reimes@head-acoustics.com ","; 6/3/25: 0%->25; 5/6/25: 25%->65; 5/6/25: FCD:Fri 06/06/->/25","26.259; 26.260; 26.261 ",105,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[301,1060022,"Diverse audio Capturing System for UEs ","DaCAS",1,"Rel-19","S4","Thu 05/12/24","Tue 09/09/25",0.5,"SP-241962",null,"Wang Bin, Xiaomi Technology ","wangbin23@xiaomi.com ","6/3/25: 0%->5; 5/6/25: 5%->50; 5/6/25: FCD:Fri 06/06/->/25",26.533000000000001,106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[302,1040022,"Study on Spatial Computing for AR Services ","FS_ARSpatial",1,"Rel-19","S4","Thu 06/06/24","Tue 09/09/25",0.45,"SP-240927",null,"Hamza, Ahmed, InterDigital Canada ","<Ahmed.Hamza@InterDigital.com> ","4/9/24: 0%->10; 26/9/24: 26.819 added;; 5/12/24: 10%->25; 6/3/25: 25%->45; 5/6/25: 45%->45; 5/6/25: FCD:Fri 14/02/->/25",26.818999999999999,104,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[303,1040021,"EVS Codec Extension for Immersive Voice and Audio Services, Phase 2 ","IVAS_Codec_Ph2",1,"Rel-19","S4","Thu 06/06/24","Tue 09/09/25",0.65,"SP-250262",null,"Su, Huan-yu, Huawei Technologies Co Ltd., ","su.huanyu@huawei.com ","; 4/9/24: 0%->5; 5/12/24: 5%->20; 5/12/24: FCD:06/06/2025->/25; 6/3/25: 20%->35; 26/3/25: WID:SP-241000->SP-250262; 26/3/25: FCD:19/04/2025->12/25; 5/6/25: 35%->65; 5/6/25: FCD:Fri 12/12/->/25","26.114; 26.117; 26.119; 26.249; 26.250; 26.252; 26.253; 26.258; 26.997 ",104,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[304,1040020,"Study on Haptics in 5G Media Services ","FS_HapticsMedia",1,"Rel-19","S4","Wed 12/06/24","Mon 03/03/25",1,"SP-241121",null,"Gaëlle Martin-Cocher, InterDigital ","(Gaelle.Martin-Cocher@InterDigital.com) ","4/9/24: WID:SP-240979->SP-241121; acron.: FS_HapticsMed-> FS_HapticsMedia; 4/9/24: 0%->15; 26/9/24: 26.854 added;; 5/12/24: 15%->60; 6/3/25: 60%->100",26.853999999999999,104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[305,1050097,"UPF enhancement for Exposure And SBA Phase 2 ","UPEAS_Ph2",1,"Rel-19","S2","Thu 04/01/24","Tue 09/09/25",1,"SP-240995",null,"Zhu Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,"23.501; 23.502; 23.503 ",105,53,null,null,"Wed 12/06/24","NA"]
[306,1020003,"   Study on UPF enhancement for Exposure And SBA Phase 2 ","FS_UPEAS_Ph2",2,"Rel-19","S2","Thu 04/01/24","Thu 06/06/24",1,"SP-231795",null,"Zhu Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","14/3/24: 0%->45; 13/6/24: 45%->100",null,102,52,null,null,"Wed 03/01/24","Thu 13/06/24"]
[307,1040035,"   Stage 2 of UPF enhancement for Exposure And SBA Phase 2 ","UPEAS_Ph2",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-240995",null,"Zhu Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","; 4/9/24: 0%->65; 5/12/24: 65%->100","23.501; 23.502; 23.503 ",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[308,1050001,"   CT aspects of UPF enhancement for Exposure And SBA Phase 2 ","UPEAS_Ph2",2,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",1,"CP-250018",null,"Shuang Liang, ZTE","liang.shuang3@zte.com.cn",null,"29.244,29.503,29.504,29.510,29.564,29.571,29.508,29.512,29.513,29.514,29.519,29.522",105,53,null,null,"Wed 12/06/24","NA"]
[309,1050098,"      CT3 aspects of UPF enhancement for Exposure And SBA Phase 2 ","UPEAS_Ph2",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",1,"CP-250018",null,"Shuang Liang, ZTE","liang.shuang3@zte.com.cn",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[310,1050099,"      CT4 aspects of UPF enhancement for Exposure And SBA Phase 2 ","UPEAS_Ph2",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",1,"CP-250018",null,"Shuang Liang, ZTE","liang.shuang3@zte.com.cn",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[311,1030002,"Video Operating Points - Harmonization and Stereo MV-HEVC ","VOPS",1,"Rel-19","S4","Wed 13/03/24","Fri 12/12/25",0.7,"SP-250818",null,"Waqar Zia ","waqar_zia (at) apple.com ","14/5/24: 26.265 added;; 13/6/24: 0%->15; 4/9/24: 15%->20; 4/9/24: 20%->; 5/12/24: 20%->45; 5/12/24: FCD:03/03/2025->/25; 6/3/25: 45%->70; 5/6/25: 70%->70; 5/6/25: FCD:Sat 18/01/->12/20; 5/6/25: WID:SP-240060->SP-250633; 27/6/25: WID:SP-250633->SP-250818","26.265; 26.116; 26.118; 26.119; 26.143; 26.511",103,52,null,null,"Wed 13/03/24","Fri 27/06/25"]
[312,1030003,"Split rendering over IMS ","SR_IMS",1,"Rel-19","S4","Tue 02/04/24","Tue 09/09/25",0.95,"SP-240492",null,"He, Shane, Nokia Corporation ","shane.he@nokia.com ","; 14/5/24: 26.567 added;; 13/6/24: 0%->10; 4/9/24: 10%->25; 5/12/24: 25%->45; 5/12/24: FCD:03/03/2025->/25; 6/3/25: 45%->65; 5/6/25: 65%->95; 5/6/25: FCD:Sat 25/01/->/2025","26.264 ; 26.567",103,52,null,null,"Wed 13/03/24","Thu 05/06/25"]
[313,1030005,"Study on Media Messaging ","FS_MeMe",1,"Rel-19","S4","Tue 02/04/24","Fri 06/06/25",1,"SP-240477",null,"Thomas Stockhammer, Qualcomm Incorporated, ","tsto@qti.qualcomm.com ","13/6/24: 0%->10; 13/6/24: FCD:12/12/2024->/25; 4/9/24: 10%->30; 5/12/24: 30%->60; 6/3/25: 60%->65; 6/3/25: FCD:03/03/2025->/25; 5/6/25: 65%->100; 5/6/25: FCD:Sat 25/01/->/25",null,103,52,null,null,"Wed 13/03/24","Thu 05/06/25"]
[314,1030006,"Study on Advanced Media Delivery ","FS_AMD",1,"Rel-19","S4","Tue 02/04/24","Thu 12/12/24",1,"SP-241011",null,"Thomas Stockhammer, Qualcomm Incorporated, ","tsto@qti.qualcomm.com ","; 13/6/24: 0%->15; 16/7/24: WID:SP-240478->SP-241011; 4/9/24: 15%->30; 5/12/24: 30%->75; 6/3/25: 75%->100","26.802; 26.804 ",103,52,null,null,"Wed 13/03/24","Thu 06/03/25"]
[315,1060069,"Stage 2 for Advanced Media Delivery ","AMD-ARCH-MED",1,"Rel-19","S4","Thu 05/12/24","Mon 03/03/25",1,"SP-241963",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ","; 6/3/25: 0%->100","26.501; 26.502 ",106,54,null,null,"Thu 05/12/24","Thu 06/03/25"]
[316,1070057,"Stage 3 for Advanced Media Delivery ","AMD_PRO-MED",1,"Rel-19","S4","Wed 05/03/25","Tue 09/09/25",0.4,"SP-250265",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com, for all topics except OpenAPI ","; 5/6/25: 0%->40","26.510; 26.511; 26.512; 26.517; 26.532; 26.247; 26.510; 26.512; 26.517; 26.532 ",107,54,null,null,"Wed 05/03/25","Thu 05/06/25"]
[317,1080004,"CT aspects of Advanced Media Delivery ","AMD_PRO-MED-CT",1,"Rel-19","C4","Fri 06/06/25","Tue 09/09/25",0.25,"CP-251037",null,"Hanna Lim, Qualcomm Incorporated ","hannalim@qti.qualcomm.com",null,"29.522, 29.580, 29.581",107,54,null,"x","Wed 05/03/25","NA"]
[318,1080033,"   CT3 aspects of Advanced Media Delivery ","AMD_PRO-MED-CT",2,"Rel-19","C3","Fri 06/06/25","Tue 09/09/25",0,"CP-251037",null,"Hanna Lim, Qualcomm Incorporated ","hannalim@qti.qualcomm.com",null,"29.522, 29.580, 29.581",107,54,null,"x","Wed 05/03/25","NA"]
[319,1080034,"   CT4 aspects of Advanced Media Delivery ","AMD_PRO-MED-CT",2,"Rel-19","C4","Fri 06/06/25","Tue 09/09/25",0.5,"CP-251037",null,"Hanna Lim, Qualcomm Incorporated ","hannalim@qti.qualcomm.com",null,"29.522, 29.580, 29.581",107,54,null,"x","Wed 05/03/25","NA"]
[320,1030007,"Study of 5G Real-time Transport Protocol Configurations, Phase 2 ","FS_5G_RTP_Ph2",1,"Rel-19","S4","Tue 02/04/24","Thu 12/12/24",1,"SP-240482",null,"Igor Curcio, Nokia Corporation ","igor.curcio@nokia.com ","14/5/24: 26.822 added;; 13/6/24: 0%->40; 4/9/24: 40%->65; 5/12/24: 65%->100",26.821999999999999,103,52,null,null,"Wed 13/03/24","Thu 05/12/24"]
[321,1060021,"5G Real-time Transport Protocol Configurations, Phase 2 ","5G_RTP_Ph2",1,"Rel-19","S4","Thu 05/12/24","Tue 09/09/25",0.75,"SP-241961",null,"Igor Curcio, Nokia Corporation ","igor.curcio@nokia.com ","; 6/3/25: 0%->35; 5/6/25: 35%->75; 5/6/25: FCD:Sun 15/06/->/25","26.522; 26.510; 26.113 ",106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[322,1030008,"Study on Beyond 2D Video ","FS_Beyond2D",1,"Rel-19","S4","Tue 02/04/24","Tue 09/09/25",0.7,"SP-240479",null,"Jiayi Xu, ","xujiayi@chinamobile.com ","14/5/24: 26.956 added;; 13/6/24: 0%->10; 4/9/24: 10%->17; 5/12/24: 17%->28; 6/3/25: 28%->50; 6/3/25: FCD:06/06/2025->/25; 5/6/25: 50%->70; 5/6/25: FCD:Fri 06/06/->/25",26.956,103,52,null,null,"Wed 13/03/24","Thu 05/06/25"]
[323,1030009,"Study on Audio Codec APIs ","FS_ACAPI",1,"Rel-19","S4","Tue 02/04/24","Fri 12/12/25",0.47,null,null,"Stefan Döhla ","(stefan DOT doehla AT iis DOT fraunhofer DOT de) ","14/5/24: 26.858 added;; 13/6/24: 0%->10; 5/12/24: 10%->20; 5/12/24: FCD:03/03/2025->/25; 6/3/25: 20%->40; 5/6/25: 40%->47; 5/6/25: FCD:Sat 25/01/->12/25",26.858000000000001,103,52,null,null,"Wed 13/03/24","Thu 05/06/25"]
[324,0,"Rel-19 Verticals and Non Public Network","-",1,"Rel-19",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[325,1060040,"Common API Framework (CAPIF) Phase 3 ","CAPIF_Ph3",1,"Rel-19",null,"Thu 04/01/24","Tue 03/03/26",0.66,"SP-241381",null,"Niranth Amogh, Nokia ","niranth.amogh@nokia.com ",null,23.222000000000001,105,53,null,null,"Wed 04/09/24","NA"]
[326,1020062,"   Study on CAPIF Phase 3 ","FS_CAPIF_Ph3",2,"Rel-19","S6","Thu 04/01/24","Thu 12/12/24",1,"SP-231741",null,"Preciado Rojas, Diego, Nokia ","diego.preciado_rojas@nokia.com ","14/3/24: 0%->20; 3/4/24: 23.700-22 added;; 13/6/24: 20%->55; 4/9/24: 55%->90; 5/12/24: 90%->100; 5/12/24: FCD:09/09/2024->12/24","23.700-22",102,52,null,null,"Wed 03/01/24","Thu 05/12/24"]
[327,1050035,"   Stage 2 of Common API Framework (CAPIF) Phase 3 ","CAPIF_Ph3",2,"Rel-19","S6","Fri 04/10/24","Thu 12/12/24",1,"SP-241694",null,"Niranth Amogh, Nokia ","niranth.amogh@nokia.com ","; 8/1/25: WID:SP-241381->SP-241694; 9/6/25: 0%->100",23.222000000000001,105,53,null,null,"Wed 04/09/24","Mon 09/06/25"]
[328,1060026,"   CT aspects of Common API Framework (CAPIF) Phase 3","CAPIF_Ph3",2,"Rel-19","C3","Mon 02/12/24","Tue 09/09/25",0.42,"CP-243074",null,"Paul, Bhaskar, Nokia","bhaskar.paul@nokia.com",null,29.222000000000001,105,53,null,null,"Wed 04/09/24","NA"]
[329,1060041,"      CT3 aspects of Common API Framework (CAPIF) Phase 3","CAPIF_Ph3",3,"Rel-19","C3","Mon 02/12/24","Tue 09/09/25",0.6,"CP-243074",null,"Paul, Bhaskar, Nokia","bhaskar.paul@nokia.com",null,29.222000000000001,105,53,null,null,"Wed 04/09/24","NA"]
[330,1040025,"   Study on security aspects of CAPIF Phase 3 ","FS_CAPIF_Ph3-sec",2,"Rel-19","S3","Wed 12/06/24","Fri 06/06/25",1,"SP-240654",null,"Henry Leung ( Xiaomi) ","lianghaoran@xiaomi.com ","5/9/24: 0%->20; 26/9/24: 33.700-22 added;; 5/12/24: 20%->60; 6/3/25: 60%->60; 5/6/25: 60%->100; 5/6/25: FCD:Thu 17/10/->/25","33.700-22",104,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[331,1060061,"   Security aspects of CAPIF Phase3 ","CAPIF_Ph3_sec",2,"Rel-19","S3","Thu 30/01/25","Fri 06/06/25",1,"SP-250076",null,"1st rapporteur: Henry Leung (Xiaomi), ","lianghaoran@xiaomi.com ","; 26/3/25: WID:SP-241776->SP-250076; 5/6/25: 0%->100",33.122,106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[332,1040015,"   Study on Charging Aspects of CAPIF ","FS_CAPIF_Ph2_CH",2,"Rel-19","S5","Wed 12/06/24","Thu 17/10/24",1,"SP-240981",null,"João Rodrigues, Nokia, ","joao.a.rodrigues@nokia.com ","13/6/24: 0%->15; 4/9/24: 15%->35; 26/9/24: 28.849 added;; 5/12/24: 35%->75; 6/3/25: 75%->100",28.849,104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[333,1070015,"   Charging aspects of CAPIF ","CH_CAPIF_EXT",2,"Rel-19","S5","Wed 26/03/25","Tue 09/09/25",0.7,"SP-250820",null,"João Rodrigues, Nokia ","joao.a.rodrigues@nokia.com ","; 6/6/25: 0%->70; 27/6/25: WID:SP-250366->SP-250820","32.240; 32.254; 32.291; 32.298 ",107,54,null,null,"Wed 05/03/25","Fri 27/06/25"]
[334,1080014,"   Study on Charging Aspects of CAPIF phase 3 ","FS_CAPIF_Ph3_CH",2,"Rel-20","S5","Thu 05/06/25","Tue 03/03/26",0,"SP-250869",null,"ur: João Rodrigues (Nokia), ","joao.a.rodrigues@nokia.com ","18/7/25: 28.891 added;",28.890999999999998,108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[335,1080019,"   Converged Charging aspects of CAPIF Phase 3 ","CAPIF_Ph3_con-CH",2,"Rel-19","S5","Thu 05/06/25","Tue 09/09/25",0,"SP-250509",null,null,null,null,"32.254; 32.291; 32.298 ",108,55,null,null,"Thu 05/06/25","NA"]
[336,1060009,"Enhanced OAM for management service exposure to external consumers through CAPIF ","MExpo",1,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.8,"SP-241942",null,"Winnie Nakimuli (Nokia) ","winnie.nakimuli@nokia.com","6/3/25: 0%->15; 6/6/25: 15%->80",null,106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[337,1000027,"Non-Public Network (NPN) security considerations ","SecNPN",1,"Rel-19","S1","Mon 22/05/23","Tue 06/06/23",1,"SP-230523",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ",null,22.260999999999999,100,51,null,null,"Thu 08/06/23","NA"]
[338,1020039,"Study on security for PLMN hosting a NPN ","PLMNNPN_SEC",1,"Rel-19","S3","Wed 03/01/24","Mon 09/09/24",1,"SP-231786",null,"Jun Shen","shenjun6@chinatelecom.cn","4/1/24: 33.757 added;; 14/3/24: 0%->25; 13/6/24: 25%->70; 5/9/24: 70%->75; 5/12/24: 75%->95; 6/3/25: 95%->100; 5/6/25: 100%->100",33.756999999999998,102,52,null,null,"Thu 07/12/23","Thu 05/06/25"]
[339,1060067,"Security for PLMN hosting a NPN ","PLMNNPN",1,"Rel-19","S3","Thu 05/12/24","Fri 06/06/25",1,"SP-241782",null,"Jun Shen ","shenjun6@chinatelecom.cn ","; 6/3/25: 0%->90; 5/6/25: 90%->100",33.500999999999998,106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[340,1050080,"ProSe support in NPN ","TEI19_ProSe_NPN",1,"Rel-19",null,"Wed 13/03/24","Tue 09/09/25",0.9,"SP-240122",null,"Walter Dees, Philips International B.V., ","walter.dees@philips.com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.304; 23.501 ",103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[341,1030016,"   Stage 2 of ProSe support in NPN ","TEI19_ProSe_NPN",2,"Rel-19","S2","Wed 13/03/24","Thu 06/06/24",1,"SP-240122",null,"Walter Dees, Philips International B.V., ","walter.dees@philips.com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.304; 23.501 ",103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[342,1050021,"   CT aspects of ProSe support in NPN ","TEI19_ProSe_NPN",2,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.9,"CP-251224",null,"Li, Mingxue, China Telecom","limx36@chinatelecom.cn",null,"23.122, 24.501, 24.554, 24.555, 29.525, 23.003",103,52,null,"x","Wed 13/03/24","Thu 13/06/24"]
[343,1050081,"      CT1 aspects of ProSe support in NPN ","TEI19_ProSe_NPN",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",1,"CP-251224",null,"Li, Mingxue, China Telecom","limx36@chinatelecom.cn",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[344,1060042,"      CT3 aspects of ProSe support in NPN ","TEI19_ProSe_NPN",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",1,"CP-251224",null,"Li, Mingxue, China Telecom","limx36@chinatelecom.cn",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[345,1050082,"      CT4 aspects of ProSe support in NPN ","TEI19_ProSe_NPN",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.95,"CP-251224",null,"Li, Mingxue, China Telecom","limx36@chinatelecom.cn",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[346,1050083,"      DELETED - CT6 aspects of ProSe support in NPN ","TEI19_ProSe_NPN",3,"Rel-19","C6","Mon 30/12/24","Tue 09/09/25",1,"CP-251224",null,"Li, Mingxue, China Telecom","limx36@chinatelecom.cn",null,null,103,52,108,null,"Wed 13/03/24","Thu 13/06/24"]
[347,1040009,"Rel-19 Enhancements of 3GPP Northbound and Application Layer Interfaces and APIs","NBI19",1,"Rel-19",null,"Mon 17/06/24","Tue 09/09/25",0.62,"CP-243079",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com",null,"24.558, 24.559, 24.549, 29.116, 29.122, 29.222, 29.255, 29.257, 29.343, 29.435, 29.486, 29.522, 29.538, 29.548, 29.549, 29.558, 29.583",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[348,1040060,"   CT1 aspects of Rel-19 Enhancements of 3GPP Northbound and Application Layer Interfaces and APIs","NBI19",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.4,"CP-243079",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[349,1040061,"   CT3 aspects of Rel-19 Enhancements of 3GPP Northbound and Application Layer Interfaces and APIs","NBI19",2,"Rel-19","C3","Mon 17/06/24","Tue 09/09/25",0.85,"CP-243079",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[350,0,"Rel-19 Radio: NR-only, band-related",null,1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,null,null,null,null,null,null,null,null,null,null,"Thu 07/12/23","NA"]
[351,1060083,"7MHz Channel Bandwidth for n26 and n5 ","NR_FR1_7MHz_BW",1,"Rel-19","R4","Sun 19/05/24","Mon 08/09/25",0.34,"RP-251453",null,"China Telecom",null,"3/4/25: WID:RP-243323->RP-250373; rapporteur: T-Mobile => China Telecom; 18/7/25: WID:RP-250373->RP-251453",null,106,54,null,null,"Fri 24/01/25","Fri 18/07/25"]
[352,1061083,"   Core part: 7MHz Channel Bandwidth for n26 and n5 ","NR_FR1_7MHz_BW-Core",2,"Rel-19","R4","Mon 14/10/24","Tue 09/09/25",0.55000000000000004,"RP-251453","RP-251454","China Telecom",null,"6/3/25: FCD:07/09/2025->09/09/2025; Compl:0%->10%; Stat Rep: ->RP-250374; ; 6/6/25: Compl:10%->55%; Stat Rep: RP-250374->RP-251454; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[353,1062083,"   Perf. Part: 7MHz Channel Bandwidth for n26 and n5 ","NR_FR1_7MHz_BW-Perf",2,"Rel-19","R4","Mon 14/10/24","Tue 03/03/26",0.2,"RP-251453","RP-251454","China Telecom",null,"6/3/25: FCD:07/09/2025->03/03/2026; Stat Rep: ->RP-250374; ; 6/6/25: Compl:0%->20%; Stat Rep: RP-250374->RP-251454; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[354,1040127,"Introduction of the NR FDD 1.4 GHz band ","NR_FDD_1400MHz",1,"Rel-19","R4","Thu 06/06/24","Thu 12/12/24",1,"RP-250760",null,"MidWave Wireless ",null,"26/9/24: WID:RP-241648->RP-242120; 3/4/25: WID:RP-242120->RP-250760",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[355,1041127,"   Core part: Introduction of the NR FDD 1.4 GHz band ","NR_FDD_1400MHz-Core",2,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-250760","RP-250403","MidWave Wireless ",null,"4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->40%; Stat Rep: ->RP-242117; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:40%->99%; WID: RP-242120->RP-241648; Stat Rep: RP-242117->RP-242494; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:99%->100%; Stat Rep: R",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[356,1042127,"   Perf. part: Introduction of the NR FDD 1.4 GHz band ","NR_FDD_1400MHz-Perf",2,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-250760","RP-250403","MidWave Wireless ",null,"4/9/24: FCD:03/03/2025->24/12/2024; Compl:0%->40%; Stat Rep: ->RP-242117; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:40%->99%; WID: RP-242120->RP-241648; Stat Rep: RP-242117->RP-242494; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:99%->100%; Stat Rep: R",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[357,1040131,"Introduction of NR bands n87 and n88 ","NR_bands_n87_n88",1,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-242501",null,"Nokia ",null,"26/9/24: WID:RP-241663->RP-242338; 24/1/25: WID:RP-242338->RP-242501",null,104,53,null,null,"Tue 23/07/24","Fri 24/01/25"]
[358,1041131,"   Core part: Introduction of NR bands n87 and n88 ","NR_bands_n87_n88-Core",2,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-242501","RP-250149","Nokia ",null,"4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->33%; Stat Rep: ->RP-241816; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:33%->66%; Stat Rep: RP-241816->RP-242500; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:66%->100%; Stat Rep: RP-242500->RP-250149; ",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[359,1042131,"   Perf. part: Introduction of NR bands n87 and n88 ","NR_bands_n87_n88-Perf",2,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-242501","RP-250149","Nokia ",null,"4/9/24: FCD:03/03/2025->25/03/2025; Compl:0%->33%; Stat Rep: ->RP-241816; ; 6/12/24: Compl:33%->66%; Stat Rep: RP-241816->RP-242500; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:66%->100%; Stat Rep: RP-242500->RP-250149; ",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[360,1040132,"Introduction of NR band n68 ","NR_band_n68",1,"Rel-19","R4","Thu 06/06/24","Thu 12/12/24",1,"RP-250763",null,"Ericsson ",null,"24/1/25: WID:RP-241664->RP-242606; 3/4/25: WID:RP-242606->RP-250763",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[361,1041132,"   Core part: Introduction of NR band n68 ","NR_band_n68-Core",2,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-250763","RP-250525","Ericsson ",null,"4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->25%; WID: RP-241664->RP-231664; Stat Rep: ->RP-241861; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:25%->60%; WID: RP-231664->RP-241664; Stat Rep: RP-241861->RP-242605; ; 6/3/25: FCD:09/12/2024->03/03/2025; C",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[362,1042132,"   Perf. part: Introduction of NR band n68 ","NR_band_n68-Perf",2,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-250763","RP-250525","Ericsson ",null,"4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->25%; WID: RP-241664->RP-231664; Stat Rep: ->RP-241861; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:25%->60%; WID: RP-231664->RP-241664; Stat Rep: RP-241861->RP-242605; ; 6/3/25: FCD:09/12/2024->03/03/2025; C",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[363,1040121,"Additional NR bands for NR features in Rel-19 ","NR_bands_xFeature_R19",1,"Rel-19","R4","Thu 06/06/24","Mon 09/09/24",0.75,"RP-251250",null,"ZTE ",null,"26/9/24: WID:RP-241677->RP-241922; 24/1/25: WID:RP-241922->RP-242572; 3/4/25: WID:RP-242572->RP-250211; 18/7/25: WID:RP-250211->RP-251250",null,104,53,null,null,"Tue 23/07/24","Fri 18/07/25"]
[364,1041121,"   Core part: Additional NR bands for NR features in Rel-19 ","NR_bands_xFeature_R19-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.75,"RP-251250","RP-251251","ZTE ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->15%; Stat Rep: ->RP-241923; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->35%; Stat Rep: RP-241923->RP-242573; ; 6/3/25: FCD:19/04/2025->09/09/2025; Compl:35%->50%; Stat Rep: RP-242573->RP-250212; ; 6/6/2",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[365,1040120,"Rel-19 NR CA/DC for x bands DL with y bands UL (x<7, y<3) and SUL/CA band combinations with a single SUL or two SUL cells ","NR_CADC_SUL_R19",1,"Rel-19","R4","Thu 06/06/24","Mon 09/09/24",0.44,"RP-251806",null,"Ericsson ",null,"26/9/24: WID:RP-241674->RP-241833; 3/4/25: WID:RP-241833->RP-250214; 18/7/25: WID:RP-250214->RP-251806",null,104,53,null,null,"Tue 23/07/24","Fri 18/07/25"]
[366,1041120,"   Core part: Rel-19 NR Carrier Aggregation (CA)/Dual Connectivity (DC) for x bands DL with y bands UL (x<7, y<3) and Supplementary Uplink (SUL) band combinations/CA band combinations with a single SUL or two SUL cells ","NR_CADC_SUL_R19-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.44,"RP-251806","RP-251256","Ericsson ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->20%; Stat Rep: ->RP-241832; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:20%->34%; Stat Rep: RP-241832->RP-242753; ; 6/3/25: FCD:19/04/2025->09/09/2025; Compl:34%->35%; WID: RP-241833->RP-242754; Stat Rep: RP",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[367,1050120,"Multi-carrier enhancements for NR Phase 2 ","NR_MC_enh2",1,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.9,"RP-242904",null,"Lenovo ",null,"24/1/25: WID:RP-242408->RP-242904",null,105,53,null,null,"Thu 26/09/24","Fri 24/01/25"]
[368,1051120,"   Core part: Multi-carrier enhancements for NR Phase 2 ","NR_MC_enh2-Core",2,"Rel-19","R1","Mon 09/09/24","Tue 09/09/25",0.9,"RP-242904","RP-251421","Lenovo ",null,"6/12/24: FCD:09/09/2025->06/06/2025; Compl:0%->40%; Stat Rep: ->RP-242903; ; 6/3/25: FCD:16/03/2025->09/09/2025; Compl:40%->80%; Stat Rep: RP-242903->RP-250413; ; 6/6/25: Compl:80%->90%; Stat Rep: RP-250413->RP-251421; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[369,0,"Rel-19 Radio: NR-only, topics other than band",null,1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,null,null,null,null,null,null,null,null,null,null,"Thu 07/12/23","NA"]
[370,1080080,"UE Conformance - New Rel-19 NR licensed bands and extension of existing NR bands ","NR_lic_bands_BW_R19-UEConTest",1,"Rel-19","R5","Fri 06/06/25","Sun 06/06/27",0,"RP-251493",null,"Huawei ",null,"tested: REL-19 WIs NR_FDD_1400MHz, NR_bands_n87_n88, NR_band_n68, NR_NTN_Sband, NR_NTN_combinedLband, NR_NTN_Ku_bands, NR_bands_CA_ENDC_R19_BWs, NR_FR1_7MHz_BW; compare NR_lic_bands_BW_R18-UEConTest; ",null,108,55,null,null,"Fri 18/07/25","NA"]
[371,1060082,"Low band carrier aggregation via switching ","NR_LBCA_Sw",1,"Rel-19",null,"Thu 06/03/25","Tue 03/03/26",0.2,"RP-251315",null,"Telus",null,"3/4/25: WID:RP-243317->RP-250247; 18/7/25: WID:RP-250247->RP-251315; AT&T => Telus",null,106,54,null,null,"Fri 24/01/25","Fri 18/07/25"]
[372,1061082,"   Core part: Low band carrier aggregation via switching ","NR_LBCA_Sw-Core",2,"Rel-19","R4","Thu 06/03/25","Tue 09/09/25",0.6,"RP-251315","RP-251316","Telus",null,"6/3/25: Compl:0%->10%; Stat Rep: ->RP-250246; ; 26/3/25: 38.768 added;; 6/6/25: Compl:10%->60%; Stat Rep: RP-250246->RP-251316; List of Impacted TS & TR updated; ","38,768",106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[373,1062082,"   Perf. part: Low band carrier aggregation via switching ","NR_LBCA_Sw-Perf",2,"Rel-19","R4","Thu 06/03/25","Tue 03/03/26",0,"RP-251315","RP-251316","Telus",null,"6/3/25: Stat Rep: ->RP-250246; ; 6/6/25: Stat Rep: RP-250246->RP-251316; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[374,1050126,"mmWave in NR: UE spurious emissions and EESS (Earth Exploration Satellite Service) protection ","NR_mmWave_protect",1,"Rel-19",null,"Mon 09/09/24","Sat 06/06/26",0.6,"RP-251811",null,"China Unicom ",null,"24/1/25: WID:RP-242371->RP-242611; 3/4/25: WID:RP-242611->RP-250818; 18/7/25: WID:RP-250818->RP-251811",null,105,53,null,null,"Thu 26/09/24","Fri 18/07/25"]
[375,1051126,"   Core part: mmWave in NR: UE spurious emissions and EESS (Earth Exploration Satellite Service) protection ","NR_mmWave_protect-Core",2,"Rel-19","R4","Mon 09/09/24","Fri 06/06/25",1,"RP-251811","RP-251593","China Unicom ",null,"6/12/24: Compl:0%->40%; Stat Rep: ->RP-242612; ; 6/3/25: FCD:16/03/2025->06/06/2025; Compl:40%->80%; Stat Rep: RP-242612->RP-250429; ; 6/6/25: Compl:80%->100%; Stat Rep: RP-250429->RP-251593; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[376,1052126,"   Perf. part: mmWave in NR: UE spurious emissions and EESS (Earth Exploration Satellite Service) protection ","NR_mmWave_protect-Perf",2,"Rel-19","R4","Mon 09/09/24","Fri 06/06/25",1,"RP-251811","RP-251593","China Unicom ",null,"6/12/24: Compl:0%->40%; Stat Rep: ->RP-242612; ; 6/3/25: FCD:16/03/2025->06/06/2025; Compl:40%->80%; Stat Rep: RP-242612->RP-250429; ; 6/6/25: Compl:80%->100%; Stat Rep: RP-250429->RP-251593; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[377,1080082,"   UE Conformance - mmWave in NR UE spurious emissions and EESS (Earth Exploration Satellite Service) protection ","NR_mmWave_protect-UEConTest",2,"Rel-19","R5","Fri 06/06/25","Sat 06/06/26",0,"RP-251514",null,"China Unicom ",null,"tested: REL-19 WI NR_mmWave_protect ",null,108,55,null,null,"Fri 18/07/25","NA"]
[378,1040100,"Study on spatial channel model for demodulation performance requirements for NR ","FS_NR_demod_SCM",1,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.7,"RP-251040","RP-251258","Nokia ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->15%; Stat Rep: ->RP-241844; ; 26/9/24: WID:RP-241610->RP-241848; 26/9/24: 38.753 added;; 6/12/24: Compl:15%->40%; WID: RP-241848->RP-241610; Stat Rep: RP-241844->RP-242465; ; 6/3/25: FCD:14/02/2025->06/06/202","38,753",104,53,null,null,"Tue 23/07/24","Fri 18/07/25"]
[379,1040101,"Study on NR FR1 DL fragmented carriers ","FS_NR_FR1_DL_Frag_Carrier",1,"Rel-19","R4","Thu 06/06/24","Fri 06/06/25",1,"RP-243002","RP-251287","Mediatek ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->5%; Stat Rep: ->RP-242054; ; 26/9/24: WID:RP-241669->RP-242404; 26/9/24: 38.755 added;; 6/12/24: Compl:5%->25%; Stat Rep: RP-242054->RP-243001; ; 24/1/25: WID:RP-242404->RP-243002; 6/3/25: FCD:14/02/2025->06/","38,755",104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[380,1020081,"Study on channel modelling enhancements for 7-24GHz for NR ","FS_NR_7_24GHz_CHmod",1,"Rel-19","R1","Wed 13/12/23","Fri 06/06/25",1,"RP-234018","RP-251240","LEE Daewon, Intel Corporation","daewon.lee@intel.com","14/3/24: Stat Rep: ->RP-240265; Rapporteur: Intel->LEE Daewon, Intel Corporation; Rap eMail: ->daewon.lee@intel.com; ; 13/6/24: Compl:0%->15%; Stat Rep: RP-240265->RP-241099; ; 4/9/24: FCD:06/06/2025->25/06/2025; Compl:15%->35%; Stat Rep: RP-241099->RP-24",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[381,1050125,"Additional topological enhancements for NR ","NR_WAB_5GFemto",1,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.85,"RP-243009",null,"NTT DOCOMO ",null,"24/1/25: WID:RP-242395->RP-243009",null,105,53,null,null,"Thu 26/09/24","Fri 24/01/25"]
[382,1051125,"   Core part: Additional topological enhancements for NR ","NR_WAB_5GFemto-Core",2,"Rel-19","R3","Mon 09/09/24","Tue 09/09/25",0.85,"RP-243009","RP-251410","NTT DOCOMO ",null,"6/12/24: Compl:0%->30%; Stat Rep: ->RP-243006; ; 6/3/25: FCD:20/05/2025->09/09/2025; Compl:30%->60%; Stat Rep: RP-243006->RP-250357; ; 6/6/25: Compl:60%->85%; Stat Rep: RP-250357->RP-251410; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[383,1020082,"Study on additional topological enhancements for NR ","FS_NR_WAB_5GFemto",1,"Rel-19","R3","Mon 09/09/24","Tue 09/09/25",1,"RP-241264","RP-241963","Min, Tianyang, NTT DOCOMO","tianyang.min.ex@nttdocomo.com","14/3/24: FCD:28/05/2021->09/09/2024; Stat Rep: ->RP-240320; Rapporteur: NTT DOCOMO->Min, Tianyang, NTT DOCOMO; Rap eMail: ->tianyang.min.ex@nttdocomo.com; ; 2/4/24: WID:RP-234041->RP-240319; 3/4/24: 38.799 added;; 13/6/24: Compl:0%->70%; Stat Rep: RP-2...",38.798999999999999,102,52,null,null,"Tue 02/01/24","Thu 26/09/24"]
[384,1030084,"NR Sidelink: Intra-band Carrier Aggregation in ITS band ","NR_SL_intraB_CA_ITS",1,"Rel-19",null,"Sun 03/03/24","Mon 09/09/24",1,"RP-250997",null,"OPPO ",null,"18/7/25: WID:RP-240840->RP-250997",null,103,52,null,null,"Tue 02/04/24","Fri 18/07/25"]
[385,1031084,"   Core part: NR Sidelink: Intra-band Carrier Aggregation in ITS band ","NR_SL_intraB_CA_ITS-Core",2,"Rel-19","R4","Sun 03/03/24","Fri 06/06/25",1,"RP-250997","RP-250996","OPPO ",null,"14/5/24: 38.787 added;; 13/6/24: Compl:0%->15%; Stat Rep: ->RP-241152; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:15%->25%; Stat Rep: RP-241152->RP-241843; ; 6/12/24: FCD:09/09/2024->04/03/2024; Compl:25%->0%; Stat Rep: RP-241843->RP-242789; ; 6/3/25: FC","38,787",103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[386,1040114,"NR sidelink multi-hop relay ","NR_SL_relay_multihop",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.85,"RP-250188",null,"LG Electronics ",null,"26/9/24: WID:RP-241609->RP-242349; 3/4/25: WID:RP-242349->RP-250188",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[387,1041114,"   Core part: NR sidelink multi-hop relay ","NR_SL_relay_multihop-Core",2,"Rel-19","R2","Thu 06/06/24","Tue 09/09/25",0.85,"RP-250188","RP-250969","LG Electronics ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->15%; Stat Rep: ->RP-241750; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->40%; Stat Rep: RP-241750->RP-242529; ; 6/3/25: FCD:19/04/2025->09/09/2025; Compl:40%->60%; Stat Rep: RP-242529->RP-250187; ; 6/6/2",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[388,1020089,"NR MIMO Phase 5 ","NR_MIMO_Ph5",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.55000000000000004,"RP-242394",null,"Samsung ",null,"2/4/24: WID:RP-234007->RP-240087; 26/9/24: WID:RP-240087->RP-242394",null,102,52,null,null,"Tue 02/01/24","Thu 26/09/24"]
[389,1021089,"   Core part: NR MIMO Phase 5 ","NR_MIMO_Ph5-Core",2,"Rel-19","R1","Wed 13/12/23","Tue 09/09/25",0.95,"RP-242394","RP-251014","Eko Onggosanusi, Samsung","eko.o@samsung.com","14/3/24: Compl:0%->15%; Stat Rep: ->RP-240086; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com; ; 13/6/24: Compl:15%->35%; WID: RP-240087->RP-234007; Stat Rep: RP-240086->RP-241051; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[390,1022089,"   Perf. part: NR MIMO Phase 5 ","NR_MIMO_Ph5-Perf",2,"Rel-19","R4","Sun 18/08/24","Tue 03/03/26",0.1,"RP-242394","RP-251014","Eko Onggosanusi, Samsung","eko.o@samsung.com","14/3/24: Stat Rep: ->RP-240086; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com; ; 13/6/24: WID: RP-240087->RP-234007; Stat Rep: RP-240086->RP-241051; ; 4/9/24: FCD:03/03/2026->26/03/2025; WID: RP-234007->RP-240087; Stat Rep:",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[391,1020090,"Evolution of NR duplex operation: Sub-band full duplex (SBFD) ","NR_duplex_evo",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.55000000000000004,"RP-251874",null,"Huawei ",null,"2/4/24: WID:RP-234035->RP-240789; 23/7/24: WID:RP-240789->RP-241614; 18/7/25: WID:RP-241614->RP-251874",null,102,52,null,null,"Tue 02/01/24","Fri 18/07/25"]
[392,1021090,"   Core part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) ","NR_duplex_evo-Core",2,"Rel-19","R1","Wed 13/12/23","Tue 09/09/25",0.93,"RP-251874","RP-251644","Xinghua Song, He (Jackson) Wang, Huawei, Samsung","songxinghua@huawei.com, h0809.wang@samsung.com","14/3/24: Compl:0%->7%; Stat Rep: ->RP-240171; Rapporteur: Huawei->Xinghua Song, He (Jackson) Wang, Huawei, Samsung; Rap eMail: ->songxinghua@huawei.com, h0809.wang@samsung.com; ; 13/6/24: Compl:7%->18%; Stat Rep: RP-240171->RP-241286; ; 4/9/24: FCD:09/09/",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[393,1022090,"   Perf. part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) ","NR_duplex_evo-Perf",2,"Rel-19","R4","Sun 18/08/24","Tue 03/03/26",0.13,"RP-251874","RP-251644","Xinghua Song, He (Jackson) Wang, Huawei, Samsung","songxinghua@huawei.com, h0809.wang@samsung.com","14/3/24: Stat Rep: ->RP-240171; Rapporteur: Huawei->Xinghua Song, He (Jackson) Wang, Huawei, Samsung; Rap eMail: ->songxinghua@huawei.com, h0809.wang@samsung.com; ; 13/6/24: Stat Rep: RP-240171->RP-241286; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: R",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[394,1020091,"NR mobility enhancements Phase 4 ","NR_Mob_Ph4",1,"Rel-19",null,"Wed 13/12/23","Mon 03/03/25",0.59,"RP-250339",null,"Apple ",null,"2/4/24: WID:RP-234036->RP-240299; 23/7/24: WID:RP-240299->RP-241515; 26/9/24: WID:RP-241515->RP-242356; 3/4/25: WID:RP-242356->RP-250339",null,102,52,null,null,"Tue 02/01/24","Thu 03/04/25"]
[395,1021091,"   Core part: NR mobility enhancements Phase 4 ","NR_Mob_Ph4-Core",2,"Rel-19","R2","Wed 13/12/23","Tue 09/09/25",0.91,"RP-250339","RP-251187","Naveen Palle, Apple Inc.","naveen.palle@apple.com","14/3/24: Stat Rep: ->RP-240298; Rapporteur: Apple->Naveen Palle, Apple Inc.; Rap eMail: ->naveen.palle@apple.com; ; 13/6/24: Compl:0%->5%; Stat Rep: RP-240298->RP-241514; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:5%->20%; Stat Rep: RP-241514->RP-241915;",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[396,1022091,"   Perf. part: NR mobility enhancements Phase 4 ","NR_Mob_Ph4-Perf",2,"Rel-19","R4","Sun 18/08/24","Tue 03/03/26",0,"RP-250339","RP-251187","Naveen Palle, Apple Inc.","naveen.palle@apple.com","14/3/24: Stat Rep: ->RP-240298; Rapporteur: Apple->Naveen Palle, Apple Inc.; Rap eMail: ->naveen.palle@apple.com; ; 13/6/24: Stat Rep: RP-240298->RP-241514; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241514->RP-241915; ; 6/12/24: FCD:03/03/2025->0",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[397,1040023,"   Security aspects of NR mobility enhancement Phase 4 ","NR_Mob_Ph4_Sec",2,"Rel-19","S3","Tue 16/07/24","Fri 06/06/25",1,"SP-240652",null,"Rajavelsamy R ","rajvel@samsung.com ","; 6/3/25: 0%->70; 6/3/25: FCD:03/03/2025->/25; 5/6/25: 70%->100; 5/6/25: FCD:Thu 27/02/->/25",33.500999999999998,104,53,null,null,"Tue 16/07/24","Thu 05/06/25"]
[398,1020092,"Data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) Phase 4 ","NR_ENDC_SON_MDT_Ph4",1,"Rel-19",null,"Wed 13/12/23","Mon 09/09/24",0.85,"RP-234038",null,"China Unicom ",null,null,null,102,52,null,null,"Tue 02/01/24","NA"]
[399,1021092,"   Core part: Data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) Phase 4 ","NR_ENDC_SON_MDT_Ph4-Core",2,"Rel-19","R3","Wed 13/12/23","Tue 09/09/25",0.85,"RP-234038","RP-251000","Xufei Dong, China Unicom","dongxf37@chinaunicom.cn","14/3/24: Stat Rep: ->RP-240118; Rapporteur: China Unicom->Xufei Dong, China Unicom; Rap eMail: ->dongxf37@chinaunicom.cn; ; 13/6/24: Compl:0%->15%; Stat Rep: RP-240118->RP-241081; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:15%->30%; Stat Rep: RP-241081->",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[400,780060,"Study on 6 GHz for LTE and NR","FS_6GHz_LTE_NR",1,"Rel-19","RP","Fri 15/12/17","Sun 03/03/24",1,"RP-234033","RP-231702","Dominique Everaere, Ericsson","dominique.everaere@ericsson.com","27/3/18: Compl:0%->25%27/3/18: WID: RP-172804->RP-180168¦27/3/18: 37.890 added;¦27/3/18: 37.107 added;¦27/6/18: Compl:25%->30%¦27/6/18: CD:Fri 15/¦26/3/19: WID:RP-181019->RP-190681; 26/6/19: WID:RP-190681->RP-190957¦01/24: Rel-18->Rel-19; 2/1/24: WID:R...","37.890; 37.107",78,40,null,null,"Mon 08/01/18","Tue 02/04/24"]
[401,1030074,"Study on NR FR2 OTA (Over the Air) testing Phase 3 ","FS_NR_FR2_OTA_Ph3",1,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.98,"RP-242833","RP-251277","Qualcomm ",null,"13/6/24: Compl:0%->30%; Stat Rep: SI ->RP-241157; ; 23/7/24: WID:RP-240856->RP-241158; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:30%->70%; Stat Rep: RP-241157->RP-241845; ; 26/9/24: WID:RP-241158->RP-242400; 26/9/24: 38.771 added;; 6/12/24: FCD:09/09/2024","38,771",103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[402,1030075,"Study on IMT parameters for NR for 4400 to 4800 MHz, 7125 to 8400 MHz and 14800 to 15350 MHz ","FS_NR_IMT_4400_7125_14800MHz",1,"Rel-19","R4","Thu 07/03/19","Mon 03/03/25",1,"RP-242944","RP-250538","Ericsson ",null,"14/5/24: 38.922 added;; 23/7/24: WID:RP-240787->RP-241326; 4/9/24: FCD:09/03/2021->24/12/2024; Compl:0%->50%; Stat Rep: SI ->RP-241840; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:50%->95%; Stat Rep: RP-241840->RP-242943; ; 24/1/25: WID:RP-241326->RP-242",38.921999999999997,103,52,null,null,"Tue 02/04/24","Thu 06/03/25"]
[403,1030078,"NR base station (BS) RF requirement evolution for FR1/FR2 and testing ","NR_BS_RF_req_evo",1,"Rel-19",null,"Sun 03/03/24","Mon 03/03/25",0.53,"RP-243270",null,"ZTE ",null,"23/7/24: WID:RP-240829->RP-241284; 26/9/24: WID:RP-241284->RP-242010; 24/1/25: WID:RP-242010->RP-243270",null,103,52,null,null,"Tue 02/04/24","Fri 24/01/25"]
[404,1031078,"   Core part: NR base station (BS) RF requirement evolution for FR1/FR2 and testing ","NR_BS_RF_req_evo-Core",2,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.7,"RP-243270","RP-251435","ZTE ",null,"13/6/24: Compl:0%->10%; Stat Rep: ->RP-241285; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:10%->20%; Stat Rep: RP-241285->RP-242011; ; 26/9/24: 38.908 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:20%->30%; Stat Rep: RP-242011->RP-242831; ; 6/3/25: F","38,908",103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[405,1032078,"   Perf. part: NR base station (BS) RF requirement evolution for FR1/FR2 and testing ","NR_BS_RF_req_evo-Perf",2,"Rel-19","R4","Sun 03/03/24","Tue 03/03/26",0.4,"RP-243270","RP-251435","ZTE ",null,"13/6/24: Stat Rep: ->RP-241285; ; 4/9/24: FCD:03/03/2026->26/03/2025; Compl:0%->5%; Stat Rep: RP-241285->RP-242011; ; 6/12/24: FCD:03/03/2025->03/03/2026; Compl:5%->10%; Stat Rep: RP-242011->RP-242831; ; 6/3/25: FCD:22/07/2025->03/03/2026; Compl:10%->30%;",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[406,1030079,"NR Radio Resource Management (RRM) Phase 5 ","NR_RRM_Ph5",1,"Rel-19",null,"Sun 03/03/24","Mon 03/03/25",0.56999999999999995,"RP-242380",null,"Apple ",null,"26/9/24: WID:RP-240830->RP-242380",null,103,52,null,null,"Tue 02/04/24","Thu 26/09/24"]
[407,1031079,"   Core part: NR Radio Resource Management (RRM) Phase 5 ","NR_RRM_Ph5-Core",2,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.9,"RP-242380","RP-251343","Apple ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241268; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:5%->25%; Stat Rep: RP-241268->RP-241971; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:25%->60%; Stat Rep: RP-241971->RP-242569; ; 6/3/25: FCD:23/03/2025->09/09/2025;",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[408,1032079,"   Perf. part: NR Radio Resource Management (RRM) Phase 5 ","NR_RRM_Ph5-Perf",2,"Rel-19","R4","Sun 13/10/24","Tue 03/03/26",0.2,"RP-242380","RP-251343","Apple ",null,"13/6/24: Stat Rep: ->RP-241268; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241268->RP-241971; ; 6/12/24: FCD:03/03/2025->03/03/2026; Stat Rep: RP-241971->RP-242569; ; 6/3/25: Stat Rep: RP-242569->RP-250320; ; 6/6/25: Compl:0%->20%; Stat Rep: RP-25",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[409,1030080,"NR demodulation performance Phase 5 ","NR_demod_Ph5",1,"Rel-19",null,"Sun 03/03/24","Mon 09/09/24",0.86,"RP-241297",null,"China Telecom ",null,"23/7/24: WID:RP-240831->RP-241297",null,103,52,null,null,"Tue 02/04/24","Tue 23/07/24"]
[410,1032080,"   Perf. part: NR demodulation performance Phase 5 ","NR_demod_Ph5-Perf",2,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.86,"RP-251448","RP-251447","China Telecom ",null,"13/6/24: FCD:03/03/2026->09/09/2025; Stat Rep: ->RP-241296; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->14%; Stat Rep: RP-241296->RP-241996; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:14%->43%; Stat Rep: RP-241996->RP-242855; ; 6/3/25: FCD:23/03/202",null,103,52,null,null,"Tue 02/04/24","Fri 18/07/25"]
[411,1030081,"NR channel BW less than 5MHz for FR1 Phase 2 ","NR_FR1_lessthan_5MHz_BW_Ph2",1,"Rel-19",null,"Sun 03/03/24","Sat 12/12/26",0.49,"RP-251670",null,"Intel ",null,"23/7/24: WID:RP-240832->RP-241622; 24/1/25: WID:RP-241622->RP-243309; 3/4/25: WID:RP-243309->RP-250781; 18/7/25: WID:RP-250781->RP-251670",null,103,52,null,null,"Tue 02/04/24","Fri 18/07/25"]
[412,1031081,"   Core part: NR channel BW less than 5MHz for FR1 Phase 2 ","NR_FR1_lessthan_5MHz_BW_Ph2-Core",2,"Rel-19","R4","Sun 03/03/24","Mon 03/03/25",1,"RP-251670","RP-250462","Intel ",null,"13/6/24: Compl:0%->25%; Stat Rep: ->RP-241496; ; 4/9/24: FCD:12/12/2024->24/12/2024; Compl:25%->70%; Stat Rep: RP-241496->RP-242031; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:73%->99%; Stat Rep: RP-242031->RP-243146; ; 6/3/25: FCD:12/11/2024->03/03/202",null,103,52,null,null,"Tue 02/04/24","Thu 06/03/25"]
[413,1032081,"   Perf. part: NR channel BW less than 5MHz for FR1 Phase 2 ","NR_FR1_lessthan_5MHz_BW_Ph2-Perf",2,"Rel-19","R4","Sun 21/07/24","Fri 06/06/25",1,"RP-251670","RP-251669","Intel ",null,"13/6/24: Stat Rep: ->RP-241496; ; 6/12/24: Stat Rep: RP-241496->RP-243146; ; 6/3/25: Compl:0%->30%; Stat Rep: RP-243146->RP-250462; ; 6/6/25: Compl:30%->100%; Stat Rep: RP-250462->RP-251669; ",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[414,1080077,"   UE Conformance - NR channel BW less than 5MHz for FR1 Phase 2 ","NR_FR1_lessthan_5MHz_BW_Ph2-UEConTest",2,"Rel-19","R5","Fri 06/06/25","Sat 12/12/26",0,"RP-251455",null,"China Telecom ",null,"tested: REL-19 WI NR_FR1_lessthan_5MHz_BW_Ph2 ",null,108,55,null,null,"Fri 18/07/25","NA"]
[415,1030083,"Enhancements for Air-to-ground network for NR ","NR_ATG_enh",1,"Rel-19",null,"Sun 03/03/24","Mon 03/03/25",0.63,"RP-243285",null,"CMCC ",null,"23/7/24: WID:RP-240839->RP-241213; 26/9/24: WID:RP-241213->RP-242381; 24/1/25: WID:RP-242381->RP-243285",null,103,52,null,null,"Tue 02/04/24","Fri 24/01/25"]
[416,1031083,"   Core part: Enhancements for Air-to-ground network for NR ","NR_ATG_enh-Core",2,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.9,"RP-243285","RP-251400","CMCC ",null,"13/6/24: Compl:0%->10%; Stat Rep: ->RP-241214; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:10%->25%; Stat Rep: RP-241214->RP-241933; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:25%->55%; Stat Rep: RP-241933->RP-242960; ; 6/3/25: FCD:23/03/2025->09/09/202",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[417,1032083,"   Perf. part: Enhancements for Air-to-ground network for NR ","NR_ATG_enh-Perf",2,"Rel-19","R4","Sun 13/10/24","Tue 03/03/26",0.33,"RP-243285","RP-251400","CMCC ",null,"13/6/24: Stat Rep: ->RP-241214; ; 4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: RP-241214->RP-241933; ; 6/12/24: FCD:03/03/2025->03/03/2026; Stat Rep: RP-241933->RP-242960; ; 6/3/25: Stat Rep: RP-242960->RP-250271; ; 6/6/25: Compl:0%->33%; Stat Rep: RP-25",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[418,1040123,"Rel-19 High power UE (power class 1.5 or 2) for NR intra-band Carrier Aggregation (CA) or NR inter-band CA/Dual connectivity (DC) band combinations with/without NR Supplementary Uplink (UL)","HPUE_NR_CADC_SUL_R19",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.65,"RP-251450",null,"China Telecom ",null,"26/9/24: WID:RP-241679->RP-242003; 24/1/25: WID:RP-242003->RP-242754; 24/1/25: WID:RP-242754->RP-242865; 3/4/25: WID:RP-242865->RP-250806; 18/7/25: WID:RP-250806->RP-251450",null,104,53,null,null,"Tue 23/07/24","Fri 18/07/25"]
[419,1041123,"   Core part: Rel-19 High power UE (power class 1.5 or 2) for NR intra-band Carrier Aggregation (CA) or NR inter-band CA/Dual connectivity (DC) band combinations with/without NR Supplementary Uplink (UL)","HPUE_NR_CADC_SUL_R19-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.65,"RP-251450","RP-251451","China Telecom ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-242004; ; 26/9/24: 38.794 added;; 26/9/24: 38.746 added;; 26/9/24: 38.750 added;; 26/9/24: 38.792 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:10%->30%; Stat Rep: RP-242004->RP-24286","38.794; 38.746; 38.750; 38.792",104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[420,1040124,"Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band for handheld/FWA UEs, and high power UE operation (power class 1) for FWVM (fixed-wireless/vehicle-mounted) use cases in a single NR band","HPUE_NR_FR1_bands_R19",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.47,"RP-251402",null,"CMCC ",null,"26/9/24: WID:RP-241680->RP-241932; 18/7/25: WID:RP-241932->RP-251402",null,104,53,null,null,"Tue 23/07/24","Fri 18/07/25"]
[421,1041124,"   Core part: Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band for handheld/FWA Ues, and high power UE operation (power class 2, 1.5 and 1) for FWVM (fixed-wireless/vehicle-mounted) use cases in a single NR band","HPUE_NR_FR1_bands_R19-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.85,"RP-251402","RP-251401","CMCC ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->15%; Stat Rep: ->RP-241931; ; 26/9/24: 38.795 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->30%; Stat Rep: RP-241931->RP-242959; ; 6/3/25: FCD:19/04/2025->09/09/2025; Compl:30%->55%; Stat Rep: RP-24","38,795",104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[422,1080076,"   UE Conformance - Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band for handheld/FWA UEs, and high power UE operation (power class 2, 1.5 and 1) for FWVM (fixed-wireless/vehicle-mounted) use cases in a single NR band ","HPUE_NR_FR1_bands_R19-UEConTest",2,"Rel-19","R5","Fri 06/06/25","Sat 06/06/26",0,"RP-251374",null,"CMCC ",null,"tested: REL-19 WI HPUE_NR_FR1_bands_R19-Core ",null,108,55,null,null,"Fri 18/07/25","NA"]
[423,1040128,"Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28 ","NR_n28_PC2_40MHz_CBW",1,"Rel-19",null,"Thu 06/06/24","Thu 12/12/24",0.77,"RP-243321",null,"CMCC ",null,"26/9/24: WID:RP-241660->RP-241930; 24/1/25: WID:RP-241930->RP-243321",null,104,53,null,null,"Tue 23/07/24","Fri 24/01/25"]
[424,1041128,"   Core part: Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28 ","NR_n28_PC2_40MHz_CBW-Core",2,"Rel-19","R4","Thu 06/06/24","Fri 06/06/25",1,"RP-243321","RP-250273","CMCC ",null,"4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->20%; Stat Rep: ->RP-241929; ; 6/12/24: Compl:20%->99%; Stat Rep: RP-241929->RP-242957; ; 6/3/25: FCD:15/10/2024->06/06/2025; Compl:99%->100%; Stat Rep: RP-242957->RP-250273; ",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[425,1070062,"   UE Conformance - Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28 ","NR_n28_PC2_40MHz_CBW-UEConTest",2,"Rel-19","R5","Mon 03/03/25","Tue 03/03/26",0.54,"RP-250249","RP-251380","CMCC ",null,"6/6/25: Compl:0%->54%; Stat Rep: ->RP-251380; ",null,107,54,null,null,"Wed 26/03/25","Fri 06/06/25"]
[426,0,"Rel-19 Radio: NR and LTE","-",1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[427,1040118,"Rel-19 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R19",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.8,"RP-250369",null,"China Telecom ",null,"basket WI; no Perf. part; compare DL_intrpt_combos_TxSW_R18; TR 37.8xx ; 3/4/25: WID:RP-241672->RP-250369",null,104,53,null,null,"Tue 23/07/24","Thu 03/04/25"]
[428,1041118,"   Core part: Rel-19 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R19-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.8,"RP-250369","RP-251449","China Telecom ",null,"basket WI; no Perf. part; compare DL_intrpt_combos_TxSW_R18; TR 37.8xx ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-241999; ; 26/9/24: 37.887 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:10%->20%; Stat Rep: RP-241999->RP-2428","37,887",104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[429,1040126,"Adding channel bandwidth(s) support to existing NR bands and CA/ENDC combinations in REL-19 ","NR_bands_CA_ENDC_R19_BWs",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.9,"RP-251160",null,"Ericsson ",null,"basket WI; no Perf. part; compare: NR_bands_R18_BWs; TR 37.8xx ; 26/9/24: WID:RP-241684->RP-242402; 24/1/25: WID:RP-242402->RP-242604; 3/4/25: WID:RP-242604->RP-250524; 18/7/25: WID:RP-250524->RP-251160",null,104,53,null,null,"Tue 23/07/24","Fri 18/07/25"]
[430,1041126,"   Core part: Adding channel bandwidth(s) support to existing NR bands and CA/ENDC combinations in REL-19 ","NR_bands_CA_ENDC_R19_BWs-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.9,"RP-251160","RP-251159","Ericsson ",null,"basket WI; no Perf. part; compare: NR_bands_R18_BWs; TR 37.8xx ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->5%; WID: RP-241684->RP-231684; Stat Rep: ->RP-241757; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:5%->15%; Stat Rep: RP-241757->RP-242603; ; 6",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[431,1040122,"Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s) ","HPUE_DC_LTE_NR_R19",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.27,"RP-251595",null,"China Unicom ",null,"basket WI; no Perf. part; compare HPUE_FR1_DC_LTE_NR_R18 and DC_R19_xBLTE_yBNR ; 26/9/24: WID:RP-241678->RP-242341; 24/1/25: WID:RP-242341->RP-242609; 3/4/25: WID:RP-242609->RP-250424; 18/7/25: WID:RP-250424->RP-251595",null,104,53,null,null,"Tue 23/07/24","Fri 18/07/25"]
[432,1041122,"   Core part: Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s) ","HPUE_DC_LTE_NR_R19-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.6,"RP-251595","RP-251594","China Unicom ",null,"basket WI; no Perf. part; compare HPUE_FR1_DC_LTE_NR_R18 and DC_R19_xBLTE_yBNR ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->15%; Stat Rep: ->RP-242019; ; 26/9/24: 37.898 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:15%->30%; Stat Rep: RP-242019-","37,898",104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[433,1080081,"   UE Conformance - Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s) ","HPUE_DC_LTE_NR_R19-UEConTest",2,"Rel-19","R5","Fri 06/06/25","Sat 12/12/26",0,"RP-251512",null,"China Unicom ",null,"tested: REL-19 WI HPUE_DC_LTE_NR_R19-Core ",null,108,55,null,null,"Fri 18/07/25","NA"]
[434,1040125,"Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-19 ","LTE_NR_R19_Simult_RxTx",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.75,"RP-251536",null,"Huawei ",null,"basket WI; no Perf. part; compare REL-18 WI LTE_NR_Simult_RxTx_R18 and REL-17 WI LTE_NR_Simult_RxTx; TR 37.8xx ; 26/9/24: WID:RP-241682->RP-242088; 18/7/25: WID:RP-242088->RP-251536",null,104,53,null,null,"Tue 23/07/24","Fri 18/07/25"]
[435,1041125,"   Core part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-19 ","LTE_NR_R19_Simult_RxTx-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.75,"RP-251536","RP-251535","Huawei ",null,"basket WI; no Perf. part; compare REL-18 WI LTE_NR_Simult_RxTx_R18 and REL-17 WI LTE_NR_Simult_RxTx; TR 37.8xx ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-242087; ; 26/9/24: 38.793 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Comp","38,793",104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[436,1040119,"Rel-19 Dual connectivity (DC) of x LTE band(s), y NR band(s) (1<=x<6, 1<=y<6, x+y<=6) and single or two NR Supplementary Uplink (SUL) bands","DC_R19_xBLTE_yBNR",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.5,"RP-250966",null,"Nokia ",null,"26/9/24: WID:RP-241673->RP-241786; 24/1/25: WID:RP-241786->RP-243257; 3/4/25: WID:RP-243257->RP-250143; 18/7/25: WID:RP-250143->RP-250966",null,104,53,null,null,"Tue 23/07/24","Fri 18/07/25"]
[437,1041119,"   Core part: Rel-19 Dual connectivity (DC) of x LTE band(s), y NR band(s) (1<=x<6, 1<=y<6, x+y<=6) and single or two NR Supplementary Uplink (SUL) bands","DC_R19_xBLTE_yBNR-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.5,"RP-250966","RP-250965","Nokia ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-241785; ; 26/9/24: 37.719-11-11 added;; 26/9/24: 37.719-21-11 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:10%->15%; Stat Rep: RP-241785->RP-242535; ; 6/3/25: FCD:19/04/2025->09/09/2","37.719-11-10; 37.719-11-11; 37.719-21-11",104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[438,1030077,"UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 ","NR_ENDC_RF_Ph4",1,"Rel-19",null,"Sun 03/03/24","Mon 03/03/25",0.69,"RP-251816",null,"Huawei ",null,"23/7/24: WID:RP-240828->RP-241656; 3/4/25: WID:RP-241656->RP-250780; 18/7/25: WID:RP-250780->RP-251816",null,103,52,null,null,"Tue 02/04/24","Fri 18/07/25"]
[439,1031077,"   Core part: UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 ","NR_ENDC_RF_Ph4-Core",2,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.8,"RP-251816","RP-251532","Huawei ",null,"13/6/24: Compl:0%->20%; Stat Rep: ->RP-241236; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:20%->35%; Stat Rep: RP-241236->RP-242084; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:35%->50%; Stat Rep: RP-242084->RP-243011; ; 6/3/25: FCD:23/03/2025->09/09/202",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[440,1032077,"   Perf. part: UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 ","NR_ENDC_RF_Ph4-Perf",2,"Rel-19","R4","Sun 03/03/24","Tue 03/03/26",0.6,"RP-251816","RP-251532","Huawei ",null,"4/9/24: FCD:03/03/2026->26/03/2025; Compl:0%->15%; Stat Rep: ->RP-242084; ; 6/12/24: FCD:03/03/2025->03/03/2026; Compl:15%->20%; Stat Rep: RP-242084->RP-243011; ; 6/3/25: FCD:22/07/2025->03/03/2026; Stat Rep: RP-243011->RP-250280; ; 6/6/25: Compl:20%->60%",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[441,1030082,"Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) ","NonCol_intraB_ENDC_NR_CA_Ph2",1,"Rel-19",null,"Sun 03/03/24","Mon 03/03/25",0.42,"RP-242083",null,"KDDI ",null,"26/9/24: WID:RP-240838->RP-242083",null,103,52,null,null,"Tue 02/04/24","Thu 26/09/24"]
[442,1031082,"   Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) ","NonCol_intraB_ENDC_NR_CA_Ph2-Core",2,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.8,"RP-242083","RP-251278","KDDI ",null,"4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->35%; Stat Rep: ->RP-242079; ; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:35%->45%; Stat Rep: RP-242079->RP-242842; ; 6/3/25: FCD:23/03/2025->09/09/2025; Compl:45%->50%; Stat Rep: RP-242842->RP-250279; ; 6/6/25",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[443,1032082,"   Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) ","NonCol_intraB_ENDC_NR_CA_Ph2-Perf",2,"Rel-19","R4","Sun 13/10/24","Tue 03/03/26",0,"RP-242083","RP-251278","KDDI ",null,"4/9/24: FCD:03/03/2026->26/03/2025; Stat Rep: ->RP-242079; ; 6/12/24: FCD:03/03/2025->03/03/2026; Stat Rep: RP-242079->RP-242842; ; 6/3/25: Stat Rep: RP-242842->RP-250279; ; 6/6/25: Stat Rep: RP-250279->RP-251278; ",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[444,1030085,"FR1 TRP, TRS and MIMO OTA testing enhancement Phase 3 ","TRP_TRS_MIMO_OTA_Ph3",1,"Rel-19",null,"Sun 03/03/24","Mon 03/03/25",0.67,"RP-250197",null,"Vivo ",null,"23/7/24: WID:RP-240841->RP-241623; 24/1/25: WID:RP-241623->RP-243277; 3/4/25: WID:RP-243277->RP-250197",null,103,52,null,null,"Tue 02/04/24","Thu 03/04/25"]
[445,1031085,"   Core part: FR1 TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 ","TRP_TRS_MIMO_OTA_Ph3-Core",2,"Rel-19","R4","Sun 03/03/24","Tue 09/09/25",0.9,"RP‑250197","RP-251201","Vivo ",null,"13/6/24: Compl:0%->10%; Stat Rep: ->RP-241043; ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:10%->20%; Stat Rep: RP-241043->RP-241828; ; 26/9/24: 38.762 added;; 6/12/24: FCD:09/09/2024->09/09/2025; Compl:20%->45%; Stat Rep: RP-241828->RP-242623; ; 6/3/25: F","38,762",103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[446,1032085,"   Perf. Part: FR1 TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 ","TRP_TRS_MIMO_OTA_Ph3-Perf",2,"Rel-19","R4","Sun 03/03/24","Tue 03/03/26",0.5,"RP‑250197","RP-251201","Vivo ",null,"13/6/24: Stat Rep: ->RP-241043; ; 4/9/24: FCD:03/03/2026->26/03/2025; Compl:0%->5%; Stat Rep: RP-241043->RP-241828; ; 6/12/24: FCD:03/03/2025->03/03/2026; Compl:5%->25%; Stat Rep: RP-241828->RP-242623; ; 6/3/25: FCD:22/07/2025->03/03/2026; Compl:25%->35%;",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[447,1070063,"UE Conformance - Rel-19 NR CA and DC; and NR and LTE DC Configurations ","NR_CADC_NR_LTE_DC_R19-UEConTest",1,"Rel-19","R5","Mon 03/03/25","Fri 11/12/26",0.05,"RP-250452","RP-251492","Huawei ",null,"6/6/25: FCD:Sat 12/12/26->Fri 11/12/26; Compl:0%->5%; Stat Rep: ->RP-251492; ",null,107,54,null,null,"Wed 26/03/25","Fri 06/06/25"]
[448,0,"Rel-19 Radio: LTE","-",1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[449,1070064,"New LTE band for 5G broadcast for region 3 utilizing a geosynchronous satellite ","LTE_band_5G_bcast_GSO",1,"Rel-19","R4","Mon 03/03/25","Tue 03/03/26",0.26,"RP-251419",null,"Astrum Mobile ",null,"18/7/25: WID:RP-250788->RP-251419",null,107,54,null,null,"Wed 26/03/25","Fri 18/07/25"]
[450,1071064,"   Core part: New LTE band for 5G broadcast for region 3 utilizing a geosynchronous satellite ","LTE_band_5G_bcast_GSO-Core",2,"Rel-19","R4","Mon 03/03/25","Tue 09/09/25",0.75,"RP-251419","RP-251276","Astrum Mobile ",null,"6/6/25: Compl:0%->75%; WID: RP-250788->RP-251419; Stat Rep: ->RP-251276; ",null,107,54,null,null,"Wed 26/03/25","Fri 06/06/25"]
[451,1072064,"   Perf. part: New LTE band for 5G broadcast for region 3 utilizing a geosynchronous satellite ","LTE_band_5G_bcast_GSO-Perf",2,"Rel-19","R4","Mon 03/03/25","Tue 03/03/26",0,"RP-251419","RP-251276","Astrum Mobile ",null,"6/6/25: WID: RP-250788->RP-251419; Stat Rep: ->RP-251276; ",null,107,54,null,null,"Wed 26/03/25","Fri 06/06/25"]
[452,1060081,"LTE-based 5G Broadcast Phase 2 ","LTE_terr_bcast_Ph2",1,"Rel-19",null,"Sun 19/05/24","Fri 12/12/25",0.43,"RP-250794",null,"EBU ",null,"3/4/25: WID:RP-243290->RP-250794",null,106,54,null,null,"Fri 24/01/25","Thu 03/04/25"]
[453,1061081,"   Core part: LTE-based 5G Broadcast Phase 2 ","LTE_terr_bcast_Ph2-Core",2,"Rel-19","R1","Mon 14/10/24","Tue 09/09/25",0.95,"RP-250794","RP-251143","EBU ",null,"6/3/25: FCD:07/09/2025->09/09/2025; Compl:0%->40%; Stat Rep: ->RP-250238; ; 6/6/25: Compl:40%->95%; Stat Rep: RP-250238->RP-251143; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[454,1062081,"   Perf. part: LTE-based 5G Broadcast Phase 2 ","LTE_terr_bcast_Ph2-Perf",2,"Rel-19","R4","Mon 11/11/24","Fri 12/12/25",0,"RP-250794","RP-251143","EBU ",null,"6/3/25: Stat Rep: ->RP-250238; ; 6/6/25: Stat Rep: RP-250238->RP-251143; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[455,1060080,"New bands for LTE based 5G terrestrial broadcast for early deployments ","LTE_terr_bcast_bands_sub_108",1,"Rel-19",null,"Sun 19/05/24","Fri 06/06/25",1,"RP-250793",null,"EBU ",null,"3/4/25: WID:RP-243268->RP-250793",null,106,54,null,null,"Fri 24/01/25","Thu 03/04/25"]
[456,1061080,"   New bands for LTE based 5G terrestrial broadcast for early deployments ","LTE_terr_bcast_bands_sub_108-Core",2,"Rel-19","R4","Sat 14/09/24","Fri 06/06/25",1,"RP-250793","RP-251141","EBU ",null,"6/3/25: Compl:0%->40%; Stat Rep: ->RP-250235; ; 6/6/25: Compl:40%->100%; Stat Rep: RP-250235->RP-251141; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[457,1040117,"Introduction of LTE FDD band in 1800–1830 MHz for Canada ","LTE_FDD_1800_1830MHz_CAN",1,"Rel-19",null,"Thu 06/06/24","Mon 03/03/25",1,"RP-242461",null,"Novamint ",null,"; 26/9/24: WID:RP-241649->RP-241739; 24/1/25: WID:RP-241739->RP-242461",null,104,53,null,null,"Tue 23/07/24","Fri 24/01/25"]
[458,1041117,"   Core part: Introduction of LTE FDD band in 1800–1830 MHz for Canada ","LTE_FDD_1800_1830MHz_CAN-Core",2,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-242461","RP-250105","Novamint ",null,"; 4/9/24: FCD:12/12/2024->24/12/2024; Compl:0%->25%; Stat Rep: ->RP-241738; ; 6/12/24: FCD:12/12/2024->03/03/2025; Compl:25%->99%; Stat Rep: RP-241738->RP-242460; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:99%->100%; Stat Rep: RP-242460->RP-250105; ",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[459,1042117,"   Perf.part: Introduction of LTE FDD band in 1800–1830 MHz for Canada ","LTE_FDD_1800_1830MHz_CAN-Perf",2,"Rel-19","R4","Thu 06/06/24","Mon 03/03/25",1,"RP-242461","RP-250105","Novamint ",null,"; 4/9/24: FCD:03/03/2025->25/03/2025; Stat Rep: ->RP-241738; ; 6/12/24: Compl:0%->99%; Stat Rep: RP-241738->RP-242460; ; 6/3/25: FCD:09/12/2024->03/03/2025; Compl:99%->100%; Stat Rep: RP-242460->RP-250105; ",null,104,53,null,null,"Tue 23/07/24","Thu 06/03/25"]
[460,1040116,"Rel-19 High power UE (power class 2) and high power operation (power class 1) for fixed-wireless/vehicle-mounted use cases in a single LTE band ","HPUE_LTE_bands_R19",1,"Rel-19",null,"Thu 06/06/24","Mon 09/09/24",0.1,"RP-241681",null,"Nokia ",null,"basket WI; no Perf. part; TR 36.8xx ",null,104,53,null,null,"Tue 23/07/24","NA"]
[461,1041116,"   Core part: Rel-19 High power UE (power class 2) and high power operation (power class 1) for fixed-wireless/vehicle-mounted use cases in a single LTE band ","HPUE_LTE_bands_R19-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.1,"RP-242086","RP-250899","Nokia ",null,"basket WI; no Perf. part; TR 36.8xx ; 4/9/24: FCD:09/09/2025->25/09/2024; Compl:0%->10%; Stat Rep: ->RP-241814; ; 26/9/24: 36.767 added;; 6/12/24: FCD:09/09/2024->09/09/2025; WID: RP-241681->RP-242086; Stat Rep: RP-241814->RP-242499; ; 6/3/25: FCD:19/04/","36,767",104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[462,1040115,"Rel-19 LTE-Advanced Carrier Aggregation for x bands (1<=x<= 6) DL with y bands (y=1, 2) UL","LTE_CA_R19_xBDL_yBUL",1,"Rel-19",null,"Thu 06/06/24","Fri 06/06/25",0.65,"RP-251534",null,"Huawei ",null,"basket WI; no Perf. part; TR 36.8xx; compare REL-18 WI LTE_CA_R18_xBDL_yBUL ; 26/9/24: WID:RP-241676->RP-242086; 24/1/25: WID:RP-242086->RP-243014; 3/4/25: WID:RP-243014->RP-250282; 18/7/25: WID:RP-250282->RP-251534",null,104,53,null,null,"Tue 23/07/24","Fri 18/07/25"]
[463,1041115,"   Core part: Rel-19 LTE-Advanced Carrier Aggregation for x bands (1<=x<= 6) DL with y bands (y=1, 2) UL","LTE_CA_R19_xBDL_yBUL-Core",2,"Rel-19","R4","Thu 06/06/24","Tue 09/09/25",0.65,"RP-251534","RP-251533","Huawei ",null,"basket WI; no Perf. part; TR 36.8xx; compare REL-18 WI LTE_CA_R18_xBDL_yBUL ; 4/9/24: FCD:09/09/2025->24/06/2025; Compl:0%->10%; Stat Rep: ->RP-242085; ; 26/9/24: 36.719-01-01 added;; 6/12/24: FCD:06/06/2025->09/09/2025; Compl:10%->31%; Stat Rep: RP-2420","36.719-01-01",104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[464,0,"Rel-19 other topics","-",1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[465,1070023,"Specification of example algorithm for alternative f5* (f5**) function","Crypto_f5**",1,"Rel-19","S3","Thu 06/03/25","Fri 06/06/25",0,"SP-250360",null,"Ferhat Karakoc ","ferhat.karakoc@ericsson.com ","; 26/3/25: 35.249 added;; 26/3/25: 23.369 added;; 26/3/25: 23.700-14 added;","33.102; 35.205; 35.231 ; 35.249; 23.369; 23.700-14",107,54,null,null,"Wed 05/03/25","Wed 26/03/25"]
[466,1060056,"Study on 3GPP Cryptographic Inventory ","FS_CryptoInv",1,"Rel-19","S3","Thu 05/12/24","Fri 06/06/25",1,"SP-241955",null,"Stawros Orkopoulos","stawros.orkopoulos@nokia.com","6/3/25: 0%->25; 5/6/25: 25%->100",null,106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[467,1040012,"CHF Segmentation ","CHFSeg",1,"Rel-19","S5","Wed 12/06/24","Tue 09/09/25",0.9,"SP-250122",null,"Cetinkaya Egemen Kemal,Verizon ","(egemen.cetinkaya@verizon.com) ","; 4/9/24: 5%->25; 5/12/24: 25%->55; 6/3/25: 55%->60; 26/3/25: WID:SP-241001->SP-250122; 26/3/25: FCD:11/12/2024->/25; 6/6/25: 60%->90","32.290; 32.291 ",104,53,null,null,"Wed 12/06/24","Fri 06/06/25"]
[468,1050121,"Introduction of BDS (BeiDou Navigation Satellite System) B2b Signal in A-GNSS for LTE and NR ","LCS_BDS_B2b_LTE_NR",1,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.99,"RP-250767",null,"CAICT ",null,"24/1/25: WID:RP-242413->RP-242459; 3/4/25: WID:RP-242459->RP-250767",null,105,53,null,null,"Thu 26/09/24","Thu 03/04/25"]
[469,1051121,"   Core part: Introduction of BDS (BeiDou Navigation Satellite System) B2b Signal in A-GNSS for LTE and NR ","LCS_BDS_B2b_LTE_NR-Core",2,"Rel-19","R2","Mon 09/09/24","Tue 09/09/25",0.99,"RP-250767","RP-251012","CAICT ",null,"6/12/24: FCD:06/06/2025->09/09/2025; Compl:0%->70%; Stat Rep: ->RP-242580; ; 6/3/25: FCD:20/05/2025->09/09/2025; Compl:70%->99%; WID: RP-242459->RP-250330; Stat Rep: RP-242580->RP-250329; ; 6/6/25: Stat Rep: RP-250329->RP-251012; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[470,1052121,"   Perf. part: Introduction of BDS (BeiDou Navigation Satellite System) B2b Signal in A-GNSS for LTE and NR ","LCS_BDS_B2b_LTE_NR-Perf",2,"Rel-19","R4","Mon 30/12/24","Tue 09/09/25",0.99,"RP-250767","RP-251012","CAICT ",null,"6/12/24: Stat Rep: ->RP-242580; ; 6/3/25: WID: RP-242459->RP-250330; Stat Rep: RP-242580->RP-250329; ; 6/6/25: Compl:0%->99%; Stat Rep: RP-250329->RP-251012; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[471,1050122,"Introduction of A-GNSS support for NavIC (Navigation with Indian Constellation) L1 SPS (Standard Positioning Service) in NR & LTE ","LCS_NAVIC_L1_SPS_NR_LTE",1,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.99,"RP-251552",null,"Reliance Jio ",null,"24/1/25: WID:RP-242414->RP-243247; 18/7/25: WID:RP-243247->RP-251552",null,105,53,null,null,"Thu 26/09/24","Fri 18/07/25"]
[472,1051122,"   Core part: Introduction of A-GNSS support for NavIC (Navigation with Indian Constellation) L1 SPS (Standard Positioning Service) in NR & LTE ","LCS_NAVIC_L1_SPS_NR_LTE-Core",2,"Rel-19","R2","Mon 09/09/24","Tue 09/09/25",0.99,"RP-251552","RP-251554","Reliance Jio ",null,"6/12/24: Compl:0%->50%; Stat Rep: ->RP-243246; ; 6/3/25: FCD:16/03/2025->06/06/2025; Compl:50%->80%; Stat Rep: RP-243246->RP-250047; ; 6/6/25: FCD:Fri 06/06/25->Tue 09/09/25; Compl:80%->99%; Stat Rep: RP-250047->RP-251554; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[473,1052122,"   Perf. part: Introduction of A-GNSS support for NavIC (Navigation with Indian Constellation) L1 SPS (Standard Positioning Service) in NR & LTE ","LCS_NAVIC_L1_SPS_NR_LTE-Perf",2,"Rel-19","R4","Mon 30/12/24","Fri 06/06/25",1,"RP-251552","RP-251554","Reliance Jio ",null,"6/12/24: Stat Rep: ->RP-243246; ; 6/3/25: Stat Rep: RP-243246->RP-250047; ; 6/6/25: FCD:Tue 09/09/25->Fri 06/06/25; Compl:0%->100%; Stat Rep: RP-250047->RP-251554; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[474,1050033,"Data management regarding subscriptions and reporting ","Data_SREP",1,"Rel-19","S5","Sat 28/12/24","Tue 09/09/25",0.4,"SP-241380",null,"Robert Petersen (Ericsson) ","robert.petersen@ericsson.com ","; 6/6/25: 0%->40","28.537; 28.550; 28.532; 32.421; 32.422; 32.423; 28.404; 28.405; 28.622; 28.623 ",105,53,null,null,"Wed 04/09/24","Fri 06/06/25"]
[475,1040071,"Study on MC services support on IOPS mode of operation for 5G ","FS_Generic_IOPS",1,"Rel-19","S6","Tue 16/07/24","Thu 12/12/24",1,"SP-241017",null,"FirstNet, Mark Lipford ","mark.lipford@firstnet.gov ","4/9/24: 0%->40; 26/9/24: 23.700-09 added;; 5/12/24: 40%->100; 5/12/24: FCD:06/06/2025->12/24; 5/12/24: 40%->100","23.700-09",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[476,1050036,"MC services for generic support on IOPS mode of operation","Generic_IOPS",1,"Rel-19","S6","Wed 04/09/24","Thu 12/12/24",1,"SP-241382",null,"FirstNet, Mark Lipford ","mark.lipford@firstnet.gov ","; 5/12/24: 0%->100; 5/12/24: 100%->65; 6/3/25: 65%->100",23.18,105,53,null,null,"Wed 04/09/24","Thu 06/03/25"]
[477,1050114,"Monitoring of signalling traffic in 5G ","MonSTra",1,"Rel-19","S1","Mon 06/05/24","Thu 12/12/24",0.28999999999999998,"SP-240793",null,"Cristina Romaguera ","cristina.romaguera@vodafone.com ","; 12/6/24: 0%->100",22.260999999999999,105,53,null,null,"Wed 12/06/24","Wed 12/06/24"]
[478,1040082,"   Stage 1 for MonSta","MonSTra",2,"Rel-19","S1","Mon 06/05/24","Thu 06/06/24",1,"SP-240793",null,"Cristina Romaguera ","cristina.romaguera@vodafone.com ","; 12/6/24: 0%->100",22.260999999999999,104,53,null,null,"Wed 12/06/24","Wed 12/06/24"]
[479,1050028,"   Security for MonStra ","MonStra-Sec",2,"Rel-19","S3","Fri 04/10/24","Thu 12/12/24",0,"SP-241376",null,"Vodafone, Susana Sabater","susana.sabatr@vodafone.com",null,33.500999999999998,105,53,null,null,"Wed 04/09/24","NA"]
[480,1060012,"   Management for MonStra ","Monstra-OAM",2,"Rel-19","S5","Thu 05/12/24","Tue 10/12/24",1,"SP-241945",null,"Susana Sabater (Vodafone)","susana.sabater@vodafone.com","5/12/24: 0%->80; 6/6/25: 80%->100",null,106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[481,1040036,"Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","eEDGE_5GC_Ph3",1,"Rel-19",null,"Thu 04/01/24","Tue 09/09/25",0.75,"SP-241284",null,"Changhong Shan (Intel) ","chang.hong.shan@intel.com ","; 26/9/24: WID:SP-240996->SP-241284; 6/3/25: 82%->","23.501; 23.502; 23.548; 23.503 ",104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[482,1020004,"   Study on Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","FS_eEDGE_5GC_Ph3",2,"Rel-19","S2","Thu 04/01/24","Mon 09/09/24",1,"SP-240962",null,"Changhong Shan (Intel) ","chang.hong.shan@intel.com ","14/3/24: 0%->50; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 50%->90; 16/7/24: WID:SP-231796->SP-240962; 4/9/24: 90%->100",null,102,52,null,null,"Wed 03/01/24","Wed 04/09/24"]
[483,1030036,"   Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC phase 3 ","FS_EDGE_Ph3",2,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240510",null,"Ge Yao, ","yaog9@chinaunicom.cn ","3/4/24: 33.749 added;; 13/6/24: 0%->30; 5/9/24: 30%->60; 5/12/24: 60%->95; 6/3/25: 95%->100; 5/6/25: 100%->100",33.749000000000002,103,52,null,null,"Thu 14/03/24","Thu 05/06/25"]
[484,1060064,"   Security Aspects of Enhancement of Support for Edge Computing in 5GC phase 3 ","EDGE_Ph3",2,"Rel-19","S3","Thu 02/01/25","Mon 03/03/25",0,"SP-241959",null,"TBD ",null,null,"33.501; 33.558 ",106,54,null,null,"Thu 05/12/24","NA"]
[485,1050050,"   Stage 2 of Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","eEDGE_5GC_Ph3",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-241505",null,"Meghashree Dattatri Kedalagudde (Intel); ","meghashree.dattatri.kedalagudde@intel.com","; 4/9/24: 0%->30; 5/12/24: 30%->97; 8/1/25: WID:SP-240996->SP-241505 (Rapp change); 6/3/25: 97%->100","23.501; 23.502; 23.548; 23.503 ",105,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[486,1050006,"   CT aspects of Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","eEDGE_5GC_Ph3",2,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.64,"CP-250016",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,"29.244, 29.502, 29.503, 29.504, 29.510, 29.556 , 29.571, 29.512, 29.513, 29.514, 29.519, 29.522, 29.591, 29.244, 29.502, 29.503, 29.504, 29.510, 29.556 , 29.571, 29.512, 29.513, 29.514, 29.519, 29.522, 29.591, 29.518",105,53,null,null,"Wed 12/06/24","NA"]
[487,1050051,"      CT3 aspects of Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","eEDGE_5GC_Ph3",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.96,"CP-250016",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[488,1050052,"      CT4 aspects of Enhancement of support for Edge Computing in 5G Core network - Phase 3 ","eEDGE_5GC_Ph3",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.9,"CP-250016",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[489,1050056,"Multi-Access (ATSSS_Ph4) ","MASSS",1,"Rel-19",null,"Thu 04/01/24","Tue 09/09/25",0.76,"SP-240994",null,"Krisztian Kiss (Apple), ","krisztian@apple.com ",null,"23.501; 23.502; 23.503 ",105,53,null,null,"Wed 12/06/24","NA"]
[490,1020070,"   Study on Multi-Access (DualSteer and ATSSS_Ph4) ","FS_MASSS",2,"Rel-19","S2","Thu 04/01/24","Mon 09/09/24",1,"SP-240467",null,"Krisztian Kiss (Apple) ","krisztian@apple.com ","14/3/24: 0%->30; 2/4/24: WID:SP-231802->SP-240467; 2/4/24: FCD:09/09/2024->/24; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 30%->70; 4/9/24: 70%->100",null,102,52,null,null,"Wed 03/01/24","Wed 04/09/24"]
[491,1030037,"   Study on security aspects for Multi-Access (DualSteer + ATSSS Ph-4) ","FS_MASSS_Sec",2,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240511",null,"Kolekar, Abhijeet (Intel) ","abhijeet.kolekar@intel.com ","3/4/24: 33.754 added;; 13/6/24: 0%->45; 5/9/24: 45%->95; 5/12/24: 95%->100; 6/3/25: 100%->100",33.753999999999998,103,52,null,null,"Thu 14/03/24","Thu 06/03/25"]
[492,1040034,"   Stage 2 of Multi-Access (ATSSS_Ph4) ","MASSS",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-241331",null,"Krisztian Kiss (Apple), ","krisztian@apple.com ","; 4/9/24: 0%->50; 26/9/24: WID:SP-240994->SP-241331; 5/12/24: 50%->100","23.501; 23.502; 23.503 ",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[493,1050020,"   CT aspects of Multi-Access (ATSSS_Ph4) ","MASSS",2,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.66,"CP-251226",null,"Gupta, Vivek, Apple","vivek_g_gupta@apple.com",null,"24.193, 24.501, 24.302, 27.007, 29.512, 29.244, 29.571",105,53,null,"x","Wed 12/06/24","NA"]
[494,1050057,"      CT1 aspects of Multi-Access (ATSSS_Ph4) ","MASSS",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.95,"CP-251226",null,"Gupta, Vivek, Apple","vivek_g_gupta@apple.com",null,null,105,53,null,"x","Wed 12/06/24","NA"]
[495,1050058,"      CT3 aspects of Multi-Access (ATSSS_Ph4) ","MASSS",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.95,"CP-251226",null,"Gupta, Vivek, Apple","vivek_g_gupta@apple.com",null,null,105,53,null,"x","Wed 12/06/24","NA"]
[496,1050059,"      CT4 aspects of Multi-Access (ATSSS_Ph4) ","MASSS",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.95,"CP-251226",null,"Gupta, Vivek, Apple","vivek_g_gupta@apple.com",null,null,105,53,null,"x","Wed 12/06/24","NA"]
[497,1050066,"System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",1,"Rel-19",null,"Wed 20/09/23","Tue 09/09/25",0.63,"SP-240985",null,"Yi Jiang, China Mobile ","jiangyi at chinamobile dot com ","; 16/7/24: WID:SP-240625->SP-240985","23.228; 23.502 ",105,53,null,null,"Wed 12/06/24","Tue 16/07/24"]
[498,1010030,"   Study on system architecture for next generation real time communication services phase 2 ","FS_NG_RTC_Ph2",2,"Rel-19","S2","Wed 20/09/23","Mon 09/09/24",1,"SP-231196",null,"Yi Jiang (China Mobile) ","jiangyi@chinamobile.com ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-77 added;; 8/12/23: 0%->15; 14/3/24: 15%->45; 13/6/24: FCD:05/06/2024->/24; 13/6/24: 45%->95; 5/12/24: 95%->100","23.700-77",101,51,null,null,"Wed 20/09/23","Thu 05/12/24"]
[499,1040016,"   Study on Charging aspects of next generation real time communication services phase 2 ","FS_NG_RTC_Ph2_CH",2,"Rel-19","S5","Wed 12/06/24","Wed 11/12/24",1,"SP-240982",null,"Chen Ai, China Mobile ","chenai@chinamobile.com ","13/6/24: 0%->10; 4/9/24: 10%->45; 26/9/24: 28.851 added;; 5/12/24: 45%->75; 5/12/24: FCD:12/12/2024->/25; 6/3/25: 75%->100",28.850999999999999,104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[500,1040026,"   Stage 2 of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",2,"Rel-19","S2","Wed 12/06/24","Thu 17/10/24",0.99,"SP-241384",null,"Yi Jiang, China Mobile ","jiangyi at chinamobile dot com ","; 16/7/24: WID:SP-240625->SP-240985; 4/9/24: 0%->10; 26/9/24: WID:SP-240985->SP-241384; 5/12/24: 10%->70; 6/3/25: 70%->98; 5/6/25: 98%->99","23.228; 23.502 ",104,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[501,1050022,"   CT aspects of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",2,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.47,"CP-242250",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,null,105,53,null,null,"Wed 12/06/24","Tue 16/07/24"]
[502,1050067,"      CT1 aspects of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.8,"CP-242250",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,null,105,53,null,null,"Wed 12/06/24","Tue 16/07/24"]
[503,1050068,"      CT3 aspects of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.85,"CP-242250",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,null,105,53,null,null,"Wed 12/06/24","Tue 16/07/24"]
[504,1050069,"      CT4 aspects of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.85,"CP-242250",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,null,105,53,null,null,"Wed 12/06/24","Tue 16/07/24"]
[505,1050070,"      CT6 aspects of System architecture for Next Generation Real time Communication services Phase 2 ","NG_RTC_Ph2",3,"Rel-19","C6","Mon 30/12/24","Tue 09/09/25",0,"CP-242250",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,null,105,53,null,null,"Wed 12/06/24","Tue 16/07/24"]
[506,1070016,"   Charging aspects of next generation real time communication services phase 2 ","NG_RTC_Ph2-CH",2,"Rel-19","S5","Wed 26/03/25","Tue 09/09/25",0.7,"SP-250513",null,"Chen Ai, China Mobile ","chenai@chinamobile.com ","; 6/6/25: 0%->70; 27/6/25: WID:SP-250367->SP-250513","32.254; 32.255; 32.260; 32.291; 32.298 ",107,54,null,null,"Wed 05/03/25","Fri 27/06/25"]
[507,1070044,"Rel-19 Application Data Analytics Enablement Service ","TEI19_ADAES",1,"Rel-19",null,"Sat 07/12/24","Tue 09/09/25",0.76,"SP-241695",null,"Yue, Jing, Ericsson ","jing.yue@ericsson.com ",null,23.436,107,54,null,null,"Thu 05/12/24","NA"]
[508,1060068,"   Stage 2 of Rel-19 Application Data Analytics Enablement Service ","TEI19_ADAES",2,"Rel-19","S6","Sat 07/12/24","Thu 12/12/24",1,"SP-241695",null,"Yue, Jing, Ericsson ","jing.yue@ericsson.com ","; 3/4/25: 0%->100",23.436,106,54,null,null,"Thu 05/12/24","Thu 03/04/25"]
[509,1070004,"   CT aspects of Rel-19 Application Data Analytics Enablement Service ","TEI19_ADAES",2,"Rel-19",null,"Thu 06/03/25","Tue 09/09/25",0.75,"CP-250074",null,"Pastushok, Igor, Ericsson","igor.pastushok@ericsson.com",null,29.548999999999999,107,54,null,null,"Thu 05/12/24","NA"]
[510,1070045,"      CT3 aspects of Rel-19 Application Data Analytics Enablement Service ","TEI19_ADAES",3,"Rel-19","C3","Thu 06/03/25","Tue 09/09/25",0.75,"CP-250074",null,"Pastushok, Igor, Ericsson","igor.pastushok@ericsson.com",null,29.548999999999999,107,54,null,null,"Thu 05/12/24","NA"]
[511,1070046,"MSISDN verification operation support to Nnef_UEId Service ","TEI19_MVOSNS",1,"Rel-19",null,"Sat 07/12/24","Fri 06/06/25",1,"SP-241498",null,"Rohit Abhishek (AT&T) ","ra503n@att.com ",null,"23.502; 23.501 ",107,54,null,null,"Thu 05/12/24","NA"]
[512,1060028,"   Stage 2 of MSISDN verification operation support to Nnef_UEId Service ","TEI19_MVOSNS",2,"Rel-19","S2","Sat 07/12/24","Thu 12/12/24",1,"SP-241498",null,"Rohit Abhishek (AT&T) ","ra503n@att.com ","; 26/3/25: 0%->100","23.502; 23.501 ",106,54,null,null,"Thu 05/12/24","Wed 26/03/25"]
[513,1070007,"   CT aspects of MSISDN verification operation support to Nnef_UEId Service ","TEI19_MVOSNS",2,"Rel-19",null,"Mon 03/03/25","Fri 06/06/25",1,"CP-250077",null,"Shahram Mohajeri, AT&T","sm7084@att.com",null,29.521999999999998,107,54,null,null,"Thu 05/12/24","NA"]
[514,1070047,"      CT3 aspects of MSISDN verification operation support to Nnef_UEId Service ","TEI19_MVOSNS",3,"Rel-19","C3","Mon 03/03/25","Fri 06/06/25",1,"CP-250077",null,"Shahram Mohajeri, AT&T","sm7084@att.com",null,29.521999999999998,107,54,null,null,"Thu 05/12/24","NA"]
[515,1070041,"Network Controlled Network Slice Selection ","TEI19_SliceSel",1,"Rel-19",null,"Sat 07/12/24","Tue 09/09/25",0.95,"SP-241502",null,"Saito, Koji, KDDI ","kj-saitou_at_kddi_dot_com ",null,"23.501; 23.502; 23.503 ",107,54,null,null,"Thu 05/12/24","NA"]
[516,1060030,"   Stage 2 of Network Controlled Network Slice Selection ","TEI19_SliceSel",2,"Rel-19","S2","Sat 07/12/24","Thu 12/12/24",1,"SP-241502",null,"Saito, Koji, KDDI ","kj-saitou_at_kddi_dot_com ","; 26/3/25: 0%->100","23.501; 23.502; 23.503 ",106,54,null,null,"Thu 05/12/24","Wed 26/03/25"]
[517,1070003,"   CT aspects of Network Controlled Network Slice Selection ","TEI19_SliceSel",2,"Rel-19",null,"Mon 03/03/25","Tue 09/09/25",0.95,"CP-251133",null,"Xiaojian Yan, ZTE","yan.xiaojian@zte.com.cn",null,"29.522, 29.534, 29.519, 29.507, 29.523, 29.502, 29.504, 29.518",107,54,null,"x","Thu 05/12/24","NA"]
[518,1070042,"      CT3 aspects of Network Controlled Network Slice Selection ","TEI19_SliceSel",3,"Rel-19","C3","Mon 03/03/25","Tue 09/09/25",0.9,"CP-251133",null,"Xiaojian Yan, ZTE","yan.xiaojian@zte.com.cn",null,null,107,54,null,"x","Thu 05/12/24","NA"]
[519,1070043,"      CT4 aspects of Network Controlled Network Slice Selection ","TEI19_SliceSel",3,"Rel-19","C4","Mon 03/03/25","Tue 09/09/25",1,"CP-251133",null,"Xiaojian Yan, ZTE","yan.xiaojian@zte.com.cn",null,null,107,54,null,"x","Thu 05/12/24","NA"]
[520,1070039,"PRU Usage Extension supported by Core Network ","TEI19_PRUE",1,"Rel-19",null,"Sat 07/12/24","Fri 06/06/25",1,"SP-241504",null,"Hou, Yunjing, CATT ","houyunjing@catt.cn ",null,null,107,54,null,null,"Thu 05/12/24","NA"]
[521,1060031,"   Stage 2 of PRU Usage Extension supported by Core Network ","TEI19_PRUE",2,"Rel-19","S2","Sat 07/12/24","Thu 12/12/24",1,"SP-241504",null,"Hou, Yunjing, CATT ","houyunjing@catt.cn ","26/3/25: 0%->100",null,106,54,null,null,"Thu 05/12/24","Wed 26/03/25"]
[522,1070001,"   CT aspects of PRU Usage Extension supported by Core Network ","TEI19_PRUE",2,"Rel-19",null,"Mon 03/03/25","Fri 06/06/25",1,"CP-250017",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com",null,29.571999999999999,107,54,null,null,"Thu 05/12/24","NA"]
[523,1070040,"      CT4 aspects of PRU Usage Extension supported by Core Network ","TEI19_PRUE",3,"Rel-19","C4","Mon 03/03/25","Fri 06/06/25",1,"CP-250017",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com",null,29.571999999999999,107,54,null,null,"Thu 05/12/24","NA"]
[524,1050078,"On-demand broadcast of GNSS assistance data ","TEI19_OBGAD",1,"Rel-19",null,"Tue 02/04/24","Tue 09/09/25",1,"SP-240487",null,"Aihua Li, China Mobile ","<liaihua@chinamobile.com> ",null,"23.502; 23.273 ",103,52,null,null,"Wed 13/03/24","NA"]
[525,1030010,"   Stage 2 of On-demand broadcast of GNSS assistance data ","TEI19_OBGAD",2,"Rel-19","S2","Tue 02/04/24","Thu 12/12/24",1,"SP-240487",null,"Aihua Li, China Mobile ","<liaihua@chinamobile.com> ","; 4/9/24: 0%->100","23.502; 23.273 ",103,52,null,null,"Wed 13/03/24","Wed 04/09/24"]
[526,1050003,"   CT aspects of On-demand broadcast of GNSS assistance data ","TEI19_OBGAD",2,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",1,"CP-242023",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com",null,null,103,52,null,null,"Wed 13/03/24","NA"]
[527,1050079,"      CT4 aspects of On-demand broadcast of GNSS assistance data ","TEI19_OBGAD",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",1,"CP-242023",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com",null,null,103,52,null,null,"Wed 13/03/24","NA"]
[528,1080039,"ATSSS Rule Provisioning via 3GPP access connected to EPC ","TEI19_ARP3E",1,"Rel-19","S2","Sat 07/12/24","Fri 06/06/25",1,"SP-241500",null,"Chunhui Zhu (NEC) ","zhu_chunhui@nec.cn ","; 26/3/25: 0%->100",23.501999999999999,106,54,null,null,"Thu 05/12/24","Wed 26/03/25"]
[529,1060029,"   Stage 2 of ATSSS Rule Provisioning via 3GPP access connected to EPC ","TEI19_ARP3E",2,"Rel-19","S2","Sat 07/12/24","Thu 12/12/24",1,"SP-241500",null,"Chunhui Zhu (NEC) ","zhu_chunhui@nec.cn ","; 26/3/25: 0%->100",23.501999999999999,106,54,null,null,"Thu 05/12/24","Wed 26/03/25"]
[530,1080020,"   CT aspects of ATSSS Rule Provisioning via 3GPP access connected to EPC ","TEI19_ARP3E-CT",2,"Rel-19","C1","Fri 06/06/25","Fri 06/06/25",1,"CP-251217",null,"Chunhui Zhu (NEC) ","zhu_chunhui@nec.cn ","; 26/3/25: 0%->100",24.193000000000001,106,54,null,null,"Thu 05/12/24","Wed 26/03/25"]
[531,1080040,"      CT1 aspects of ATSSS Rule Provisioning via 3GPP access connected to EPC ","TEI19_ARP3E-CT",3,"Rel-19","C1","Fri 06/06/25","Fri 06/06/25",1,"CP-251217",null,"Chunhui Zhu (NEC) ","zhu_chunhui@nec.cn ","; 26/3/25: 0%->100",24.193000000000001,106,54,null,null,"Thu 05/12/24","Wed 26/03/25"]
[532,1030012,"Minimize the Number of Policy Associations ","TEI19_MINPA",1,"Rel-19",null,"Mon 17/06/24","Mon 03/03/25",1,"SP-240118",null,"Ericsson, Belen Pancorbo ","belen . pancorbo {@} ericsson . com) ",null,"23.502; 23.501; 23.503 ",103,52,null,null,"Wed 13/03/24","NA"]
[533,1040078,"   Stage 2 of Minimize the Number of Policy Associations","TEI19_MINPA",2,"Rel-19","S2","Mon 17/06/24","Mon 03/03/25",1,"SP-240118",null,"Ericsson, Belen Pancorbo ","belen . pancorbo {@} ericsson . com) ","13/6/24: 0%->100",null,101,51,null,null,"Wed 06/09/23","Thu 13/06/24"]
[534,1040004,"   CT Aspects on Minimize the Number of Policy Associations","TEI19_MINPA",2,"Rel-19",null,"Mon 17/06/24","Mon 03/03/25",1,"CP-241295",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,"TS 29.503,TS 29.507,TS 29.513,TS 29.518,TS 29.525",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[535,1040052,"      CT3 Aspects on Minimize the Number of Policy Associations","TEI19_MINPA",3,"Rel-19","C3","Mon 17/06/24","Mon 03/03/25",1,"CP-241295",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[536,1040053,"      CT4 Aspects on Minimize the Number of Policy Associations","TEI19_MINPA",3,"Rel-19","C4","Mon 17/06/24","Mon 03/03/25",1,"CP-241295",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[537,1050089,"Spending Limits for UE Policies in Roaming scenario","TEI19_SLUPiR",1,"Rel-19",null,"Wed 13/03/24","Thu 12/12/24",1,"SP-240486",null,"uri baniel, oracle ","uri dot baniel at oracle dot com","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.502; 23.501; 23.503 ",103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[538,1030014,"   Stage 2 of Spending Limits for UE Policies in Roaming scenario","TEI19_SLUPiR",2,"Rel-19","S2","Wed 13/03/24","Thu 06/06/24",1,"SP-240486",null,"uri baniel, oracle ","uri dot baniel at oracle dot com","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.502; 23.501; 23.503 ",103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[539,1050011,"   CT aspects of Spending Limits for UE Policies in Roaming scenario","TEI19_SLUPiR",2,"Rel-19",null,"Mon 09/09/24","Thu 12/12/24",1,"CP-242060",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[540,1050090,"      CT3 aspects of Spending Limits for UE Policies in Roaming scenario","TEI19_SLUPiR",3,"Rel-19","C3","Mon 09/09/24","Thu 12/12/24",1,"CP-242060",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[541,1030015,"Enhancing Parameter Provisioning with static UE IP address and UP security policy ","TEI19_IP_SP_EXP",1,"Rel-19",null,"Tue 26/12/23","Fri 06/06/25",1,"SP-240121",null,"Stefan Rommer, Ericsson ","stefan . rommer @ ericsson . com) ",null,"23.501; 23.502 ",103,52,null,null,"Wed 13/03/24","NA"]
[542,1040079,"   Stage 2 of Enhancing Parameter Provisioning with static UE IP address and UP security policy","TEI19_IP_SP_EXP",2,"Rel-19","S2","Tue 26/12/23","Thu 12/12/24",1,"SP-240121",null,"Stefan Rommer, Ericsson ","stefan . rommer @ ericsson . com) ","19/6/24: FCD:06/06/2025->12/20; 4/9/24: 0%->100",null,101,51,null,null,"Wed 06/09/23","Wed 04/09/24"]
[543,1040007,"   CT aspects of Enhancing Parameter Provisioning with static UE IP address and UP security policy","TEI19_IP_SP_EXP",2,"Rel-19",null,"Mon 17/06/24","Fri 06/06/25",1,"CP-243076",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,"29.503,29.522,29.503,29.522",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[544,1040056,"      CT3 aspects of Enhancing Parameter Provisioning with static UE IP address and UP security policy","TEI19_IP_SP_EXP",3,"Rel-19","C3","Mon 17/06/24","Fri 06/06/25",1,"CP-243076",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[545,1040057,"      CT4 aspects of Enhancing Parameter Provisioning with static UE IP address and UP security policy","TEI19_IP_SP_EXP",3,"Rel-19","C4","Mon 17/06/24","Fri 06/06/25",1,"CP-243076",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[546,1030017,"Multiple Location Procedure for Emergency LCS Routing ","TEI19_MLR4RTR",1,"Rel-19","S2","Wed 13/03/24","Thu 12/12/24",1,"SP-240123",null,"Simon Cai (Nokia Shanghai-Bell)Simon<dot>Ca<at> nokia<dash>sbell<dot>com ","Simon<dot>Ca<at> nokia<dash>sbell<dot>com ","; 5/12/24: 0%->100",23.273,103,52,null,null,"Wed 13/03/24","Thu 05/12/24"]
[547,1030018,"Roaming traffic offloading via session breakout in HPLMN ","TEI19_HSBO",1,"Rel-19","S2","Tue 02/04/24","Thu 12/12/24",1,"SP-240491",null,"Hyesung Kim, Samsung ","hs1207.kim@samsung.com ","; 5/12/24: 0%->100",23.501000000000001,103,52,null,null,"Wed 13/03/24","Thu 05/12/24"]
[548,1060043,"Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports ","TEI19_DLPMR",1,"Rel-19",null,"Wed 13/03/24","Mon 03/03/25",1,"SP-240125",null,"Richard, Batorfi, Ericsson, ","richard.batorfi@ericsson.com ",null,23.273,103,52,null,null,"Wed 13/03/24","NA"]
[549,1030019,"   Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports ","TEI19_DLPMR",2,"Rel-19","S2","Wed 13/03/24","Thu 12/12/24",1,"SP-240125",null,"Richard, Batorfi, Ericsson, ","richard.batorfi@ericsson.com ","; 5/12/24: 0%->100",23.273,103,52,null,null,"Wed 13/03/24","Thu 05/12/24"]
[550,1060004,"   CT aspects of Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports ","TEI19_DLPMR",2,"Rel-19","C4","Mon 02/12/24","Mon 03/02/25",1,"CP-243048",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,"29.515, 29.518, 29.572",103,52,null,null,"Wed 13/03/24","NA"]
[551,1060044,"      CT4 aspects of Deferred 5GC-MT-LR Procedure for Periodic Location Events based NRPPa Periodic Measurement Reports ","TEI19_DLPMR",3,"Rel-19","C4","Mon 02/12/24","Mon 03/03/25",1,"CP-243048",null,"Jones Lu, Ericsson","jones.lu@ericsson.com",null,null,103,52,null,null,"Wed 13/03/24","NA"]
[552,1050084,"QoS monitoring enhancement ","TEI19_QME",1,"Rel-19",null,"Tue 02/04/24","Fri 06/06/25",1,"SP-240961",null,"Aihua Li, China Mobile ","<liaihua@chinamobile.com> ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100; 16/7/24: WID:SP-240489->SP-240961","23.501; 23.502 ",103,52,null,null,"Wed 13/03/24","Tue 16/07/24"]
[553,1030020,"   Stage 2 of QoS monitoring enhancement ","TEI19_QME",2,"Rel-19","S2","Tue 02/04/24","Thu 06/06/24",1,"SP-240961",null,"Aihua Li, China Mobile ","<liaihua@chinamobile.com> ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100; 16/7/24: WID:SP-240489->SP-240961","23.501; 23.502 ",103,52,null,null,"Wed 13/03/24","Tue 16/07/24"]
[554,1050012,"   CT aspects of QoS monitoring enhancement ","TEI19_QME",2,"Rel-19",null,"Mon 09/09/24","Fri 06/06/25",1,"CP-243312",null,"Huang, Zhenning, China Mobile","huangzhenning@chinamobile.com",null,"29.122, 29.502, 29.512, 29.514, 29.522, 29.565",103,52,null,null,"Wed 13/03/24","Tue 16/07/24"]
[555,1050085,"      CT3 aspects of QoS monitoring enhancement ","TEI19_QME",3,"Rel-19","C3","Mon 09/09/24","Fri 06/06/25",1,"CP-243312",null,"Huang, Zhenning, China Mobile","huangzhenning@chinamobile.com",null,null,103,52,null,null,"Wed 13/03/24","Tue 16/07/24"]
[556,1050086,"      CT4 aspects of QoS monitoring enhancement ","TEI19_QME",3,"Rel-19","C4","Mon 09/09/24","Fri 06/06/25",1,"CP-243312",null,"Huang, Zhenning, China Mobile","huangzhenning@chinamobile.com",null,null,103,52,null,null,"Wed 13/03/24","Tue 16/07/24"]
[557,1060045,"Subscription control for reference time distribution in EPS ","TEI19_TIME_SUB_EPS",1,"Rel-19",null,"Wed 13/03/24","Thu 12/12/24",1,"SP-240127",null,"Sebastian Speicher, Qualcomm ","speicher AT qti DOT qualcomm DOT com) ","; 4/9/24: 0%->100",null,103,52,null,null,"Wed 13/03/24","Wed 04/09/24"]
[558,1030021,"   Stage 2 of Subscription control for reference time distribution in EPS ","TEI19_TIME_SUB_EPS",2,"Rel-19","S2","Wed 13/03/24","Thu 12/12/24",1,"SP-240127",null,"Sebastian Speicher, Qualcomm ","speicher AT qti DOT qualcomm DOT com) ","; 4/9/24: 0%->100",23.401,103,52,null,null,"Wed 13/03/24","Wed 04/09/24"]
[559,1060001,"   CT aspects of Subscription control for reference time distribution in EPS ","TEI19_TIME_SUB_EPS",2,"Rel-19",null,"Mon 02/12/24","Thu 12/12/24",1,"CP-243017",null,"Hanna Lim, Qualcomm Incorporated","hannalim@qti.qualcomm.com",null,"29.272, 29.274, 29.230, 23.008 ",103,52,null,null,"Wed 13/03/24","Wed 04/09/24"]
[560,1060046,"      CT4 aspects of Subscription control for reference time distribution in EPS ","TEI19_TIME_SUB_EPS",3,"Rel-19","C4","Mon 02/12/24","Thu 12/12/24",1,"CP-243017",null,"Hanna Lim, Qualcomm Incorporated","hannalim@qti.qualcomm.com",null,null,103,52,null,null,"Wed 13/03/24","Wed 04/09/24"]
[561,1030022,"Providing per-subscriber VLAN instructions from UDM and DN-AAA ","TEI19_VLANSUB",1,"Rel-19",null,"Tue 26/12/23","Fri 06/06/25",1,"SP-240128",null,"Stefan Rommer, Ericsson ","stefan . rommer @ ericsson . com) ",null,"23.501; 23.502 ",103,52,null,null,"Wed 13/03/24","NA"]
[562,1040080,"   Stage 2 of Providing per-subscriber VLAN instructions from UDM and DN-AAA","TEI19_VLANSUB",2,"Rel-19","S2","Tue 26/12/23","Thu 12/12/24",1,"SP-240128",null,"Stefan Rommer, Ericsson ","stefan . rommer @ ericsson . com) ","19/6/24: FCD:06/06/2025->12/20; 5/12/24: 0%->100",null,101,51,null,null,"Wed 06/09/23","Thu 05/12/24"]
[563,1040006,"   CT aspects of Providing per-subscriber VLAN instructions from UDM and DN-AAA","TEI19_VLANSUB",2,"Rel-19",null,"Mon 17/06/24","Fri 06/06/25",1,"CP-250078",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,"29.503,29.561,29.230,29.244",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[564,1040054,"      CT3 aspects of Providing per-subscriber VLAN instructions from UDM and DN-AAA","TEI19_VLANSUB",3,"Rel-19","C3","Mon 17/06/24","Fri 06/06/25",1,"CP-250078",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[565,1040055,"      CT4 aspects of Providing per-subscriber VLAN instructions from UDM and DN-AAA","TEI19_VLANSUB",3,"Rel-19","C4","Mon 17/06/24","Fri 06/06/25",1,"CP-250078",null,"Maria Tianmei, Liang, Ericsson","maria.liang@ericsson.co",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[566,1050076,"NF discovery and selection by target PLMN ","TEI19_NFsel_by_tPLMN",1,"Rel-19",null,"Tue 02/04/24","Tue 09/09/25",1,"SP-240490",null,"Dr. Thomas Belling, Nokia, ","thomas (dot) belling (at) nokia (dot) com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.501; 23.502 ",103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[567,1030023,"   Stage 2 of NF discovery and selection by target PLMN ","TEI19_NFsel_by_tPLMN",2,"Rel-19","S2","Tue 02/04/24","Thu 06/06/24",1,"SP-240490",null,"Dr. Thomas Belling, Nokia, ","thomas (dot) belling (at) nokia (dot) com ","; 13/6/24: FCD:12/12/2024->/24; 13/6/24: 0%->100","23.501; 23.502 ",103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[568,1050005,"   CT aspects of NF discovery and selection by target PLMN ","TEI19_NFsel_by_tPLMN",2,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",1,"CP-242025",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[569,1050077,"      CT4 aspects of NF discovery and selection by target PLMN ","TEI19_NFsel_by_tPLMN",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",1,"CP-242025",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,null,103,52,null,null,"Wed 13/03/24","Thu 13/06/24"]
[570,1020057,"Integrated Sensing and Communication ","Sensing",1,"Rel-19",null,"Thu 10/03/22","Tue 12/12/23",1,"SP-230750",null,"Aleksiev, Vasil, Deutsche Telekom AG ","vasil.aleksiev@magenta.at ","6/9/23: 0%->80; 8/12/23: 80%->100",22.137,100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[571,950003,"   Study on Integrated Sensing and Communication ","FS_Sensing",2,"Rel-19","S1","Thu 10/03/22","Sat 09/09/23",1,"SP-220717",null,"Aleksiev, Vasil, Deutsche Telekom ","Vasil.Aleksiev@magenta.at ","5/4/22: 22.837 added;; 4/6/22: 0%->10; 21/6/22: WID:SP-220084->SP-220717; 9/9/22: 10%->40; 10/12/22: 40%->65; 17/3/23: 65%->80; 8/6/23: 80%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->100",22.837,95,48,null,null,"Thu 10/03/22","Wed 06/09/23"]
[572,1000026,"   Stage 1 of Integrated Sensing and Communication ","Sensing",2,"Rel-19","S1","Thu 08/06/23","Tue 12/12/23",1,"SP-230750",null,"Aleksiev, Vasil, Deutsche Telekom AG ","vasil.aleksiev@magenta.at ","6/9/23: 0%->80; 8/12/23: 80%->100",22.137,100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[573,1020086,"Study on channel modelling for Integrated Sensing And Communication (ISAC) for NR ","FS_Sensing_NR",1,"Rel-19","R1","Wed 13/12/23","Fri 06/06/25",1,"RP-242348","RP-251474","Yingyang Li, Jerome Vogedes, Xiaomi, AT&T","liyingyang@xiaomi.com, jerome.vogedes@att.com","14/3/24: Compl:0%->6%; Stat Rep: ->RP-240114; Rapporteur: Xiaomi->Yingyang Li, Jerome Vogedes, Xiaomi, AT&T; Rap eMail: ->liyingyang@xiaomi.com, jerome.vogedes@att.com; ; 2/4/24: WID:RP-234069->RP-240799; 13/6/24: Compl:6%->22%; Stat Rep: RP-240114->RP...",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[574,1020059,"Uncrewed Aerial System Phase 3 ","UAS_Ph3",1,"Rel-19",null,"Thu 02/06/22","Tue 09/09/25",0.94,"SP-230518",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","6/9/23: 0%->95; 8/12/23: 95%->100",null,100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[575,960017,"   Study on (Stage 1 of) UAV Phase 3 ","FS_UAV_Ph3",2,"Rel-19","S1","Thu 02/06/22","Sat 09/09/23",1,"SP-220954",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","17/8/22: WID:SP-220444->SP-220680; 9/9/22: 0%->20; 23/9/22: WID:SP-220680->SP-220954; 10/12/22: 20%->45; 17/3/23: 45%->65; 8/6/23: 65%->95; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 95%->100",null,96,49,null,null,"Thu 02/06/22","Wed 06/09/23"]
[576,1020069,"   Study on (Stage 2 of) Phase 3 for UAS, UAV and UAM ","FS_UAS_Ph3",2,"Rel-19","S2","Thu 04/01/24","Mon 09/09/24",1,"SP-231801",null,"LaeYoung Kim (LG Electronics) ","laeyoung.kim@lge.com ","14/3/24: 0%->50; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 50%->90; 4/9/24: 90%->100",null,102,52,null,null,"Wed 03/01/24","Wed 04/09/24"]
[577,1000032,"   Stage 1 of Uncrewed Aerial System Phase 3 ","UAS_Ph3",2,"Rel-19","S1","Thu 08/06/23","Tue 12/12/23",1,"SP-230518",null,"Pengtai Qin , China Mobile ","qinpengtai@chinamobile.com ","6/9/23: 0%->95; 8/12/23: 95%->100",null,100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[578,1040037,"   (Stage 2 of) UAS, UAV and UAM Phase 3 ","UAS_Ph3",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-241287",null,"LaeYoung Kim (LG Electronics) ","laeyoung.kim@lge.com ","; 4/9/24: 0%->65; 26/9/24: WID:SP-240997->SP-241287; 5/12/24: 65%->99; 6/3/25: 99%->100; 5/6/25: 100%->100","23.256; 23.288; 23.503; 23.502; 23.401 ",104,53,null,null,"Wed 12/06/24","Thu 05/06/25"]
[579,1050013,"   CT aspects of UAS, UAV and UAM Phase 3 ","UAS_Ph3",2,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.95,"CP-251136",null,"Sunhee Kim, LG Electronics","sunhee.kim@lge.com",null,"24.501, 24.301, 27.007, 29.122, 29.255, 29.256, 29.503, 29.518, 29.520, 29.522",105,53,null,"x","Wed 12/06/24","NA"]
[580,1050091,"      CT1 aspects of UAS, UAV and UAM Phase 3 ","UAS_Ph3",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",1,"CP-251136",null,"Sunhee Kim, LG Electronics","sunhee.kim@lge.com",null,null,105,53,null,"x","Wed 12/06/24","NA"]
[581,1050092,"      CT3 aspects of UAS, UAV and UAM Phase 3 ","UAS_Ph3",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.95,"CP-251136",null,"Sunhee Kim, LG Electronics","sunhee.kim@lge.com",null,null,105,53,null,"x","Wed 12/06/24","NA"]
[582,1060047,"      CT4 aspects of UAS, UAV and UAM Phase 3 ","UAS_Ph3",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.9,"CP-251136",null,"Sunhee Kim, LG Electronics","sunhee.kim@lge.com",null,null,105,53,null,"x","Wed 12/06/24","NA"]
[583,1060058,"   Security of Uncrewed Aerial System Phase 3 ","UAS_Ph3_Sec",2,"Rel-19","S3","Thu 02/01/25","Mon 03/03/25",0,"SP-241773",null,"Markus Hanhisalo, Ericsson ","markus.hanhisalo@ericsson.com ",null,33.256,106,54,null,null,"Thu 05/12/24","NA"]
[584,1070017,"   Charging for Uncrewed Aerial Systems Phase 3 ","UAS_Ph3-CH",2,"Rel-19","S5","Wed 26/03/25","Tue 09/09/25",0.45,"SP-250512",null,"Jia Dong, China Mobile ","dongjia@chinamobile.com ","; 6/6/25: 0%->45; 27/6/25: WID:SP-250396->SP-250512","32.240; 32.255; 32.256; 32.291; 32.298 ",107,54,null,null,"Wed 05/03/25","Fri 27/06/25"]
[585,1010008,"   Application Architecture for UAS applications Phase 3 ","UASAPP_Ph3",2,"Rel-19","S6","Thu 07/09/23","Thu 12/12/24",1,"SP-240741",null,"Roy, Michel, InterDigital ","michel.roy@interdigital.com","; 8/12/23: 0%->20; 14/3/24: 20%->40; 13/6/24: 40%->60; 16/7/24: WID:SP-230991->SP-240741; 4/9/24: 60%->75; 5/12/24: 75%->100","23.255; 23.434 ",101,51,null,null,"Thu 07/09/23","Thu 05/12/24"]
[586,1040043,"   CT Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS), Phase 3","UASAPP_Ph3",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.99,"CP-241281",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[587,1040069,"      CT1 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS), Phase 3","UASAPP_Ph3",3,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.98,"CP-241281",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[588,1040070,"      CT3 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS), Phase 3","UASAPP_Ph3",3,"Rel-19","C3","Mon 17/06/24","Tue 09/09/25",1,"CP-241281",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[589,1030033,"   UAS security enhancements ","FS_UAS_Ph3_Sec",2,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240504",null,"Markus Hanhisalo, ","markus.hanhisalo@ericsson.com ","3/4/24: 33.759 added;; 13/6/24: 0%->50; 5/12/24: 50%->100; 6/3/25: 100%->100",33.759,103,52,null,null,"Thu 14/03/24","Thu 06/03/25"]
[590,960018,"Study on Upper layer traffic steering, switching and split over dual 3GPP access ","FS_DualSteer",1,"Rel-19","S1","Thu 02/06/22","Sat 09/09/23",1,"SP-220445",null,"Francesco Pica; Qualcomm ",null,"13/7/22: 22.841 added;; 9/9/22: 0%->30; 10/12/22: 30%->60; 17/3/23: 60%->75; 8/6/23: 75%->90; 8/6/23: FCD:06/06/2023->09/20; 6/9/23: 90%->95; 8/12/23: 95%->100",22.841000000000001,96,49,null,null,"Thu 02/06/22","Fri 08/12/23"]
[591,1040017,"Study on Charging aspects of Uncrewed Aerial Systems ","FS_UAS_CH",1,"Rel-19","S5","Wed 12/06/24","Wed 11/12/24",1,"SP-240983",null,"Jia Dong, China Mobile, ","dongjia@chinamobile.com ","4/9/24: 0%->40; 26/9/24: 28.853 added;; 5/12/24: 40%->75; 5/12/24: FCD:12/12/2024->/25; 6/3/25: 75%->100",28.853000000000002,104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[592,1020031,"Upper layer traffic steering and switching over dual 3GPP access ","DualSteer",1,"Rel-19","S1","Thu 07/12/23","Sun 10/12/23",0.95,"SP-231412",null,"Pica Francesco, Qualcomm ","fpica<at>qti.qualcomm.com ","; 8/12/23: 0%->95",22.260999999999999,102,52,null,null,"Thu 07/12/23","Fri 08/12/23"]
[593,1010022,"Edge Computing Considering the Operational Needs of Service Hosting Environment ","EdgeOpNeeds",1,"Rel-19","S1","Mon 21/08/23","Sat 09/09/23",1,"SP-231037",null,"Yuying Zhang, China Telecom ","zhangyy45@chinatelecom.cn ","; 6/9/23: 0%->100",22.260999999999999,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[594,1060048,"5G NR Femto","5G_Femto",1,"Rel-19",null,"Thu 04/01/24","Tue 09/09/25",0.89,"SP-241327",null,"Malla Reddy Sama ","sama@docomolab-euro.com ","; 4/9/24: 0%->30; 26/9/24: WID:SP-240629->SP-241327","23.501; 23.502 ",104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[595,1020002,"   Study on System aspects of 5G NR Femto ","FS_5G_Femto",2,"Rel-19","S2","Thu 04/01/24","Mon 09/09/24",1,"SP-231797",null,"Malla Reddy Sama (NTT DOCOMO) ","sama@docomolab-euro.com ","14/3/24: 0%->40; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 40%->90; 4/9/24: 90%->100; 4/9/24: 100%->",null,102,52,null,null,"Wed 03/01/24","Wed 04/09/24"]
[596,1040028,"   System aspects of 5G NR Femto ","5G_Femto",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-241327",null,"Malla Reddy Sama ","sama@docomolab-euro.com ","; 4/9/24: 0%->30; 26/9/24: WID:SP-240629->SP-241327; 5/12/24: 30%->100","23.501; 23.502 ",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[597,1060002,"   CT aspects of 5G NR Femto","5G_Femto",2,"Rel-19","C4","Thu 12/12/24","Tue 09/09/25",1,"CP-250020",null,"Dojiri, Shunsuke, NTT DOCOMO","dojiri@nttdocomo.com",null,"29.503, 29.504, 29.505, 29.522, 29.571",104,53,null,"x","Wed 12/06/24","Thu 26/09/24"]
[598,1060049,"      CT3 aspects of 5G NR Femto","5G_Femto",3,"Rel-19","C3","Thu 12/12/24","Tue 09/09/25",1,"CP-250020",null,"Dojiri, Shunsuke, NTT DOCOMO","dojiri@nttdocomo.com",null,null,104,53,null,"x","Wed 12/06/24","Thu 26/09/24"]
[599,1060050,"      CT4 aspects of 5G NR Femto","5G_Femto",3,"Rel-19","C4","Thu 12/12/24","Tue 09/09/25",1,"CP-250020",null,"Dojiri, Shunsuke, NTT DOCOMO","dojiri@nttdocomo.com",null,null,104,53,null,"x","Wed 12/06/24","Thu 26/09/24"]
[600,1030028,"   Study on security aspects of 5G NR Femto Document for: Approval ","FS_5G_Femto_Sec",2,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240505",null,"Peilin LIU (ZTE) ","liu.peilin@zte.com.cn , ","3/4/24: 33.745 added;; 13/6/24: 0%->30; 5/9/24: 30%->60; 5/12/24: 60%->98; 6/3/25: 98%->100; 5/6/25: 100%->100",33.744999999999997,103,52,null,null,"Thu 14/03/24","Thu 05/06/25"]
[601,1060062,"   Security aspects of 5G NR Femto ","5G_Femto_Sec",2,"Rel-19","S3","Thu 30/01/25","Fri 06/06/25",0,"SP-241958",null,"Liu,Peilin liu.peilin@zte.com.cn ","Song,Hua songhua@chinamobile.com ",null,null,106,54,null,null,"Thu 05/12/24","NA"]
[602,1050115,"Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",1,"Rel-19",null,"Thu 04/01/24","Tue 09/09/25",0.76,"SP-231037",null,"Hugh Shieh (AT&T) ","hs6220@att.com ",null,null,102,52,null,null,"Wed 06/09/23","Wed 06/09/23"]
[603,1020066,"   Study on Proximity-based Services in 5GS Phase 3 ","FS_5G_ProSe_Ph3",2,"Rel-19","S2","Thu 04/01/24","Mon 09/09/24",1,"SP-231798",null,"Hugh Shieh (AT&T) ","hs6220@att.com ","14/3/24: 0%->45; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 45%->90; 4/9/24: 90%->100",null,102,52,null,null,"Wed 03/01/24","Wed 04/09/24"]
[604,1040030,"   Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-240988",null,"Nassima Toumi (KPN N.V.)","nassima.toumi@tno.nl","; 4/9/24: 0%->70; 5/12/24: 70%->100",23.303999999999998,104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[605,1050023,"   CT aspects of Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",2,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.65,"CP-243266",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com","; 26/9/24: WID:CP-242108->SP-241290","24.554, 24.555, 24.501, 24.587, 29.519, 29.522, 29.525, 29.503, 29.504, 29.518, 29.510, 29.555, 29.559, 29.571, 31.102",105,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[606,1050038,"      CT1 aspects of Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.85,"CP-243266",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[607,1050116,"      CT3 aspects of Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.8,"CP-243266",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[608,1050039,"      CT4 aspects of Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.9,"CP-243266",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[609,1050040,"      CT6 aspects of Proximity-based Services in 5GS Phase 3 ","5G_ProSe_Ph3",3,"Rel-19","C6","Mon 30/12/24","Tue 09/09/25",0.9,"CP-243266",null,"Zhao, Xiaoxue (CATT)","zhaoxiaoxue@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[610,1060057,"   Security Aspects of Proximity Based Services in 5GS Phase 3 ","5G_ProSe_Sec_Ph3",2,"Rel-19","S3","Thu 05/12/24","Mon 03/03/25",1,"SP-241956",null,"Primary Rapporteur: Ao Lei (Huawei) ","leiao@huawei.com ","; 6/3/25: 0%->95; 6/3/25: FCD:03/03/2025->/25; 5/6/25: 95%->100",33.503,106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[611,1050030,"   Charging for 5G ProSe Ph3 ","5G_ProSe_Ph3_CH",2,"Rel-19","S5","Sat 28/12/24","Tue 09/09/25",1,"SP-241377",null,"Xiaoqian Jia (China Telecom)","jiaxq1@chinatelecom.cn ","; 6/3/25: 0%->100","32.277; 32.291; 32.298 ",105,53,null,null,"Wed 04/09/24","Thu 06/03/25"]
[612,1030034,"Study on Security Aspects of Enhancement for Proximity Based Services in 5GS Phase 3 ","FS_5G_ProSe_Ph3_SEC",1,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240513",null,"Lei, Ao (Huawei) ","leiao@huawei.com ","3/4/24: 33.743 added;; 13/6/24: 0%->30; 5/9/24: 30%->60; 5/12/24: 60%->100",33.743000000000002,103,52,null,null,"Thu 14/03/24","Thu 05/12/24"]
[613,1050100,"Vehicle Mounted Relays Phase 2 ","VMR_Ph2",1,"Rel-19",null,"Thu 04/01/24","Fri 06/06/25",1,"SP-240989",null,"Hong Cheng (Qualcomm) ","hongc@qti.qualcomm.com ",null,"23.501; 23.502; 23.273 ",105,53,null,null,"Wed 12/06/24","NA"]
[614,1020067,"   Study on Vehicle Mounted Relays Phase 2 ","FS_VMR_Ph2",2,"Rel-19","S2","Thu 04/01/24","Mon 09/09/24",1,"SP-240493",null,"Primary Rapporteur: Hong Cheng (Qualcomm) ","hongc@qti.qualcomm.com ","14/3/24: 0%->40; 2/4/24: WID:SP-231799->SP-240493; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 40%->95; 5/12/24: 95%->100",null,102,52,null,null,"Wed 03/01/24","Thu 05/12/24"]
[615,1040031,"   Stage 2 of Vehicle Mounted Relays Phase 2 ","VMR_Ph2",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-240989",null,"Hong Cheng (Qualcomm) ","hongc@qti.qualcomm.com ","; 4/9/24: 0%->40; 5/12/24: 40%->100","23.501; 23.502; 23.273 ",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[616,1050026,"   CT aspects of Vehicle Mounted Relays Phase 2 ","VMR_Ph2",2,"Rel-19",null,"Mon 09/09/24","Fri 06/06/25",1,"CP-251221",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com ",null,"24.501, 23.041, 29.515",105,53,null,"x","Wed 12/06/24","NA"]
[617,1050101,"      CT1 aspects of Vehicle Mounted Relays Phase 2 ","VMR_Ph2",3,"Rel-19","C1","Mon 09/09/24","Fri 06/06/25",1,"CP-251221",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com ",null,null,105,53,null,"x","Wed 12/06/24","NA"]
[618,1050102,"      CT4 aspects of Vehicle Mounted Relays Phase 2 ","VMR_Ph2",3,"Rel-19","C4","Mon 09/09/24","Fri 06/06/25",1,"CP-251221",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com ",null,null,105,53,null,"x","Wed 12/06/24","NA"]
[619,1050093,"Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",1,"Rel-19",null,"Thu 04/01/24","Tue 09/09/25",0.89,"SP-240971",null,"Michael Starsinic, Interdigital","Michael.Starsinic@Interdigital.com",null,null,105,53,null,null,"Thu 20/06/24","NA"]
[620,1020063,"   Study on User Identities and Authentication Architecture ","FS_UIA_ARC",2,"Rel-19","S2","Thu 04/01/24","Mon 09/09/24",1,"SP-231804",null,"Michael Starsinic, Interdigital ","Michael.Starsinic@Interdigital.com ","14/3/24: 0%->35; 14/3/24: 23.700-32 added;; 13/6/24: FCD:06/06/2024->/24; 13/6/24: 35%->90; 4/9/24: 90%->93; 5/12/24: 93%->100","23.700-32",102,52,null,null,"Wed 03/01/24","Thu 05/12/24"]
[621,1040085,"   Stage 2 of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",2,"Rel-19","S2","Thu 20/06/24","Thu 12/12/24",1,"SP-240971",null,"Michael Starsinic, Interdigital","Michael.Starsinic@Interdigital.com","4/9/24: 0%->15; 5/12/24: 15%->90; 6/3/25: 90%->100; 5/6/25: 100%->100",null,104,53,null,null,"Thu 20/06/24","Thu 05/06/25"]
[622,1050009,"   CT aspects of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",2,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.87,"CP-242029",null,"Sethi, Anuj, InterDigital","anuj.sethi@interdigital.com",null,null,105,53,null,null,"Thu 20/06/24","NA"]
[623,1050094,"      CT1 aspects of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.7,"CP-242029",null,"Sethi, Anuj, InterDigital","anuj.sethi@interdigital.com",null,null,105,53,null,null,"Thu 20/06/24","NA"]
[624,1050095,"      CT3 aspects of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.95,"CP-242029",null,"Sethi, Anuj, InterDigital","anuj.sethi@interdigital.com",null,null,105,53,null,null,"Thu 20/06/24","NA"]
[625,1050096,"      CT4 aspects of Identifying non-3GPP Devices Connecting behind a UE or 5G-RG","UIA_ARC",3,"Rel-19","C4","Mon 09/09/24","Tue 09/09/25",0.95,"CP-242029",null,"Sethi, Anuj, InterDigital","anuj.sethi@interdigital.com",null,null,105,53,null,null,"Thu 20/06/24","NA"]
[626,1030032,"Study on security aspects of User Identities and Authentication ","FS_UIA_Sec",1,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240507",null,"Samir Ferdi, ","Samir.Ferdi@InterDigital.com ","3/4/24: 33.700-32 added;; 13/6/24: 0%->35; 5/9/24: 35%->65; 5/12/24: 65%->100","33.700-32",103,52,null,null,"Thu 14/03/24","Thu 05/12/24"]
[627,950007,"Study on FRMCS Phase 5","FS_FRMCS_Ph5",1,"Rel-19","S1","Thu 10/03/22","Tue 12/12/23",1,"SP-241693",null,"Patrick WIMART, UIC","wimart@uic.org","; 4/6/22: 0%->15; 21/6/22: WID:SP-220088->SP-220437. FS_FRMCS_Ph3->FS_FRMCS_Ph5; 9/9/22: 15%->30; 10/12/22: 30%->50; 8/6/23: 50%->80; 8/6/23: FCD:09/09/2023->12/20; 6/9/23: 80%->90; 8/12/23: 90%->100; 8/1/25: WID:SP-220437->SP-241693",22.989000000000001,95,48,null,null,"Thu 10/03/22","Wed 08/01/25"]
[628,1000031,"FRMCS Phase 5 ","FRMCS_Ph5",1,"Rel-19","S1","Thu 08/06/23","Tue 09/09/25",0.75,"SP-230512",null,"Nikolopoulou, Vassiliki, UIC ","nikolopoulou@uic.org ","; 6/9/23: 0%->50; 8/12/23: 50%->100","22.280; 22.179; 22.289; 22.261 ",100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[629,1000038,"   Stage 2 of Railways specific Enhancements to Mission Critical Services ","FRMCS_Ph5",2,"Rel-19","S6","Thu 08/06/23","Thu 12/12/24",1,"SP-230780",null,"Oettl, Martin, Nokia, ","martin.oettl@nokia.com ","; 7/9/23: 0%->10; 8/12/23: 10%->30; 14/3/24: 30%->40. 14/5/24: acronym: enh4FRMCS ->FRMCS_Ph5 ; 13/6/24: 40%->55; 4/9/24: 55%->70; 5/12/24: 70%->100","23.280; 23.281; 23.282; 23.379; 23.283; 23.289 ",100,51,null,null,"Thu 08/06/23","Thu 05/12/24"]
[630,1050018,"   CT aspects of Railways specific Enhancements to Mission Critical Services ","FRMCS_Ph5",2,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.48,"CP-242102",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,null,100,51,null,null,"Thu 08/06/23","Thu 13/06/24"]
[631,1050103,"      CT1 aspects of Railways specific Enhancements to Mission Critical Services ","FRMCS_Ph5",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.7,"CP-242102",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,null,100,51,null,null,"Thu 08/06/23","Thu 13/06/24"]
[632,850044,"Study on Supporting of Railway Smart Station Services ","FS_RAILSS",1,"Rel-19","S1","Thu 19/09/19","Thu 08/09/22",1,"SP-190838",null,"Han, Andrew Min-gyu, Hansung University ","andyhan(at)hansung(dot)ac(dot)kr ","; 8/10/19: 22.890 added;; 6/12/19: 0%->5; 5/12/20: 5%->15; 19/3/21: FCD:12/06/2020->09/21; 19/3/21: 15%->30; 13/9/21: 30%->35; 10/12/21: 35%->45; 11/03/22: Rel-18->Rel-19; 9/9/22: 45%->100","New ; 22.890",85,43,null,null,"Fri 13/09/19","Fri 09/09/22"]
[633,960020,"Study on Network of Service Robots with Ambient Intelligence ","FS_SOBOT",1,"Rel-19","S1","Thu 02/06/22","Tue 12/12/23",1,"SP-220447",null,"LEE, Ki-Dong, LG Electronics ","kidong.lee@lge.com ","13/7/22: 22.916 added;; 9/9/22: 0%->10; 10/12/22: 10%->40; 17/3/23: FCD:03/03/2023->9/9/23; 17/3/23: 40%->70; 8/6/23: 70%->80; 8/6/23: FCD:09/09/2023->12/20; 6/9/23: 80%->90; 8/12/23: 90%->100",22.916,96,49,null,null,"Thu 02/06/22","Fri 08/12/23"]
[634,990053,"Study on Interconnect of SNPN ","FS_ISN",1,"Rel-19","S1","Thu 08/06/23","Thu 27/06/24",0.4,"SP-230236",null,"Thierry Bérisot, Novamint ","tberisot@novamint.com ","8/6/23: 0%->30; 6/9/23: 30%->60; 8/12/23: FCD:12/12/2023->/2024; 8/12/23: 60%->65",22.847999999999999,99,50,null,null,"Thu 16/03/23","Fri 08/12/23"]
[635,1030041,"Interconnect of SNPN ","ISN",1,"Rel-19","S1","Wed 13/03/24","Fri 29/03/24",1,"SP-240194",null,"Thierry Bérisot, Novamint, ","tberisot@novamint.com ","; 14/3/24: 0%->100",22.260999999999999,103,52,null,null,"Wed 13/03/24","Thu 14/03/24"]
[636,990050,"Edge Computing for Industrial Scenarios ","EDGINDUS",1,"Rel-19","S1","Thu 02/02/23","Fri 03/03/23",1,"SP-230229",null,"Bruno Tossou, Orange ","bruno.tossou@orange.com ","; 17/3/23: 0%->100",22.103999999999999,99,50,null,null,"Thu 16/03/23","Fri 17/03/23"]
[637,990049,"PS Data Off for IMS Data Channel Service ","IMSDCDataOff",1,"Rel-19","S1","Thu 02/02/23","Fri 03/03/23",1,"SP-230227",null,"Yue Hu, China Mobile ","huyueyjy@chinamobile.com ","; 9/8/23: 0%->100",22.010999999999999,99,50,null,null,"Thu 16/03/23","Wed 09/08/23"]
[638,970044,"Multi-path relay ","MultiRelay",1,"Rel-19","S1","Thu 01/09/22","Mon 19/09/22",1,"SP-220943",null,"Yuying Zhang, China Telecom ","zhangyy45@chinatelecom.cn ","; 9/9/22: 0%->100",22.260999999999999,97,49,null,null,"Fri 09/09/22","Fri 09/09/22"]
[639,1000025,"UE-to-UE multi-hop relay ","UEMHopRelay",1,"Rel-19","S1","Mon 22/05/23","Tue 06/06/23",1,"SP-230521",null,"Lipford, Mark, FirstNet Authority, ","mark.lipford@firstnet.gov ","; 8/6/23: 100%->","22.261; 22.280 ",100,51,null,null,"Thu 08/06/23","Thu 08/06/23"]
[640,970043,"Interworking of Non-3GPP Digital Terrestrial Broadcast Networks with 5GS Multicast Broadcast Services ","DTT4MBS",1,"Rel-19","S1","Thu 01/09/22","Mon 19/09/22",1,"SP-220941",null,"Saha, Anindya, Saankhya Labs ","anindya@saankhyalabs.com ","; 9/9/22: 0%->100",22.260999999999999,97,49,null,null,"Fri 09/09/22","Fri 09/09/22"]
[641,1040083,"MPS for Messaging services ","MPS4msg",1,"Rel-19",null,"Thu 01/09/22","Tue 20/05/25",0.94,"SP-220939",null,"Singh, Ray, Peraton Labs ","rsingh@peratonlabs.com ","; 9/9/22: 0%->100",22.152999999999999,97,49,null,null,"Fri 09/09/22","Fri 09/09/22"]
[642,970042,"   (stage 1 of) MPS for Messaging services ","MPS4msg",2,"Rel-19","S1","Thu 01/09/22","Mon 19/09/22",1,"SP-220939",null,"Singh, Ray, Peraton Labs ","rsingh@peratonlabs.com ","; 9/9/22: 0%->100",22.152999999999999,97,49,null,null,"Fri 09/09/22","Fri 09/09/22"]
[643,1040029,"   (stage 2 of) MPS for IMS Messaging and SMS services ","MPS4msg",2,"Rel-19","S2","Wed 12/06/24","Thu 12/12/24",1,"SP-240987",null,"Robert Streijl (Peraton Labs), ","rstreijl@peratonlabs.com ","; 4/9/24: 0%->80; 5/12/24: 80%->100","23.401; 23.203; 23.501; 23.502; 23.503; 23.682; 23.204; 23.272; 23.228 ",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[644,1010031,"   Study on MPS for IMS Messaging and SMS services ","FS_MPS4msg",2,"Rel-19","S2","Wed 03/01/24","Thu 06/06/24",1,"SP-231197",null,"Robert Streijl (Peraton Labs) ","rstreijl@peratonlabs.com ","9/23: company-submitted WID, to be corrected; 6/10/23: 23.700-75 added;; 8/12/23: 0%->20; 14/3/24: 0%->70; 13/6/24: 70%->100; 4/9/24: 99%->100","23.700-75",101,51,null,null,"Wed 20/09/23","Wed 04/09/24"]
[645,1050007,"   CT aspects of MPS for IMS Messaging and SMS services ","MPS4msg",2,"Rel-19","C4","Mon 09/09/24","Tue 20/05/25",0.92,"CP-243047",null,"Monnes, Peter (Peraton Labs)","pmonnes@peratonlabs.com",null,"23.540, 24.229, 24.247, 24.301, 24.341, 29.122, 29.128, 29.213, 29.214, 29.228, 29.272, 29.336, 29.338, 24.501, 29.503, 29.513, 29.514, 29.518, 29.522, 29.562, 29.577, 23.540, 24.229, 24.247, 24.301, 24.341, 29.122, 29.128, 29.213, 29.214, 29.228, 29.272,",105,53,null,null,"Wed 12/06/24","NA"]
[646,1050063,"      CT1 aspects of MPS for IMS Messaging and SMS services ","MPS4msg",3,"Rel-19","C1","Mon 09/09/24","Tue 20/05/25",0.93,"CP-243047",null,"Monnes, Peter (Peraton Labs)","pmonnes@peratonlabs.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[647,1050064,"      CT3 aspects of MPS for IMS Messaging and SMS services ","MPS4msg",3,"Rel-19","C3","Mon 09/09/24","Tue 20/05/25",0.9,"CP-243047",null,"Monnes, Peter (Peraton Labs)","pmonnes@peratonlabs.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[648,1050065,"      CT4 aspects of MPS for IMS Messaging and SMS services ","MPS4msg",3,"Rel-19","C4","Mon 09/09/24","Tue 20/05/25",0.92,"CP-243047",null,"Monnes, Peter (Peraton Labs)","pmonnes@peratonlabs.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[649,1050104,"Minimization of Service Interruption During Core Network Failure Phase 2 ","MINT_Ph2",1,"Rel-19","S1","Thu 01/09/22","Tue 09/09/25",0.5,"SP-220992",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ","; 9/9/22: 0%->100",22.260999999999999,97,49,null,null,"Fri 09/09/22","Fri 09/09/22"]
[650,1050029,"   Study on MINT support in EPS for 5G-only national roaming UE","FS_MINT_Ph2",2,"Rel-19","C1","Mon 09/09/24","Mon 03/03/25",1,"CP-251227",null,"Li Mingxue, China Telecom","limx36@chinatelecom.cn","3/4/25: WID:CP-242249->CP-243260",null,97,49,null,"x","Fri 09/09/22","Thu 03/04/25"]
[651,970041,"   Stage 2 of Minimization of Service Interruption During Core Network Failure Phase 2 ","MINT_Ph2",2,"Rel-19","S1","Thu 01/09/22","Mon 19/09/22",1,"SP-220992",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ","; 9/9/22: 0%->100",22.260999999999999,97,49,null,null,"Fri 09/09/22","Fri 09/09/22"]
[652,1080022,"   CT aspects of Minimization of Service Interruption During Core Network Failure Phase 2 ","MINT_Ph2",2,"Rel-19","C1","Fri 06/06/25","Tue 09/09/25",0,"CP-251282",null,"Li Mingxue, China Telecom","limx36@chinatelecom.cn","; 9/9/22: 0%->100","23.122, 24.301, 31.102",97,49,null,"x","Fri 09/09/22","Fri 09/09/22"]
[653,1080037,"      CT1 aspects of Minimization of Service Interruption During Core Network Failure Phase 2 ","MINT_Ph2",3,"Rel-19","C1","Fri 06/06/25","Tue 09/09/25",0,"CP-251282",null,"Li Mingxue, China Telecom","limx36@chinatelecom.cn","; 9/9/22: 0%->100","23.122, 24.301, 31.102",97,49,null,"x","Fri 09/09/22","Fri 09/09/22"]
[654,1080038,"      CT6 aspects of Minimization of Service Interruption During Core Network Failure Phase 2 ","MINT_Ph2",3,"Rel-19","C6","Fri 06/06/25","Tue 09/09/25",0,"CP-251282",null,"Li Mingxue, China Telecom","limx36@chinatelecom.cn","; 9/9/22: 0%->100","23.122, 24.301, 31.102",97,49,null,"x","Fri 09/09/22","Fri 09/09/22"]
[655,980108,"Measurement Data Collection ","MeasureData",1,"Rel-19","S1","Fri 09/12/22","Tue 20/12/22",1,"SP-221263",null,"Yingjun Zhou, ZTE Corporation ","zhou.yingjun@zte.com.cn ","; 10/12/22: 0%->100",22.260999999999999,98,50,null,null,"Fri 09/12/22","Sat 10/12/22"]
[656,1010025,"Local traffic routing for multi-access UE ","LTR_MA",1,"Rel-19","S1","Mon 21/08/23","Sat 09/09/23",1,"SP-231035",null,"Yinglin Chen, China Telecom ","chenyl37@chinatelecom.cn ","; 6/9/23: 0%->100",22.260999999999999,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[657,980008,"Study on Diverse audio Capturing system for End-user Devices ","FS_DaCED",1,"Rel-19","S4","Tue 13/12/22","Thu 12/12/24",1,"SP-221330",null,"Wang Bin, Xiaomi ","wangbin23@xiaomi.com ","; 17/3/23: 0%->5; 17/3/23: 26.933 added;; 8/6/23: 5%->30; 7/9/23: 30%->35; 8/12/23: 35%->45; 14/3/24: 45%->70; 13/6/24: 70%->85; 4/9/24: 85%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100",26.933,98,50,null,null,"Fri 09/12/22","Thu 05/12/24"]
[658,1000034,"Study on Service aspects for supporting the eMMTel service ","FS_eMMTelAPP",1,"Rel-19","S6","Thu 08/06/23","Thu 12/12/24",1,"SP-230779",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 30/6/23: 23.700-92 added;; 7/9/23: 0%->10; 8/12/23: 10%->20; 14/3/24: 20%->35; 13/6/24: 35%->70; 4/9/24: 70%->80; 5/12/24: 80%->100; 5/12/24: FCD:09/09/2024->12/24","23.222 ; 23.700-92",100,51,null,null,"Thu 08/06/23","Thu 05/12/24"]
[659,1070036,"Application enablement aspects for MMTel ","MMTel_App",1,"Rel-19",null,"Tue 16/07/24","Tue 09/09/25",0.56999999999999995,"SP-241019",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","4/9/24: 0%->10; 26/9/24: 23.792 added;; 5/12/24: 10%->60",23.792000000000002,104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[660,1040073,"   Stage 2 of Application enablement aspects for MMTel ","MMTel_App",2,"Rel-19","S6","Tue 16/07/24","Mon 28/10/24",1,"SP-241019",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","4/9/24: 0%->10; 26/9/24: 23.792 added;; 5/12/24: 10%->60; 6/3/25: 60%->100",23.792000000000002,104,53,null,null,"Wed 12/06/24","Thu 06/03/25"]
[661,1070008,"   CT aspects of Application enablement aspects for MMTel ","MMTel_App",2,"Rel-19","C1","Thu 06/03/25","Tue 09/09/25",0.45,"CP-250249",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ",null,24.542000000000002,104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[662,1070037,"      CT1 aspects of Application enablement aspects for MMTel ","MMTel_App",3,"Rel-19","C1","Thu 06/03/25","Tue 09/09/25",0.6,"CP-250249",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ",null,24.542000000000002,104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[663,1070038,"      CT3 aspects of Application enablement aspects for MMTel ","MMTel_App",3,"Rel-19","C3","Thu 06/03/25","Tue 09/09/25",0.3,"CP-250249",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ",null,24.542000000000002,104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[664,1050053,"Enhanced application layer support for location services ","eLSAPP",1,"Rel-19",null,"Thu 08/06/23","Tue 09/09/25",0.77,"SP-241005",null,"Liping Wu, CATT ","wuliping@cictmobile.com ",null,"23.434; 23.436 ",105,53,null,null,"Wed 12/06/24","NA"]
[665,1000035,"   Study on enhanced application layer support for location services ","FS_eLSAPP",2,"Rel-19","S6","Thu 08/06/23","Mon 09/09/24",1,"SP-230778",null,"Liping Wu, CATT ","wuliping@cictmobile.com ","; 30/6/23: 23.700-72 added;; 7/9/23: 0%->15; 8/12/23: 15%->25; 14/3/24: 25%->40; 2/4/24: WID:SP-230778->SP-240295; 2/4/24: FCD:05/06/2024->/24; 13/6/24: 40%->85; 13/6/24: WID:SP-240295->SP-230778; 4/9/24: 85%->100","23.434 ; 23.700-72",100,51,null,null,"Thu 08/06/23","Wed 04/09/24"]
[666,1040072,"   Stage 2 of Enhanced application layer support for location services ","eLSAPP",2,"Rel-19","S6","Wed 12/06/24","Thu 12/12/24",1,"SP-241005",null,"Liping Wu, CATT ","wuliping@cictmobile.com ","; 4/9/24: 0%->30; 5/12/24: 30%->100","23.434; 23.436 ",104,53,null,null,"Wed 12/06/24","Thu 05/12/24"]
[667,1050015,"   CT aspects of Enhanced application layer support for location services ","eLSAPP",2,"Rel-19",null,"Mon 09/09/24","Tue 09/09/25",0.62,"CP-242064",null,"Wang, Baixiao (CATT)","wangbaixiao@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[668,1050054,"      CT1 aspects of Enhanced application layer support for location services ","eLSAPP",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.85,"CP-242064",null,"Wang, Baixiao (CATT)","wangbaixiao@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[669,1050055,"      CT3 aspects of Enhanced application layer support for location services ","eLSAPP",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",0.95,"CP-242064",null,"Wang, Baixiao (CATT)","wangbaixiao@cictmobile.com",null,null,105,53,null,null,"Wed 12/06/24","NA"]
[670,1000036,"Sharing of administrative configuration between interconnected MC service systems ","MCShAC",1,"Rel-19","S6","Thu 08/06/23","Thu 12/12/24",1,"SP-230692",null,"andreas.flander@bdbos.bund.de ","andreas.flander@bdbos.bund.de ","; 7/9/23: 0%->5; 8/12/23: 5%->40; 14/3/24: 40%->90; 13/6/24: 90%->90; 4/9/24: 90%->100","23.280; 23.379; 23.281; 23.282 ",100,51,null,null,"Thu 08/06/23","Wed 04/09/24"]
[671,1060051,"5GMSG Service phase 3 ","5GMARCH_Ph3",1,"Rel-19",null,"Thu 08/06/23","Tue 09/09/25",0.64,"SP-230781",null,"Liu, Yue, China Mobile, ","liuyueyjy@chinamobile.com ","7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50",null,100,51,null,null,"Thu 08/06/23","Wed 04/09/24"]
[672,1000037,"   Stage 2 of GMSG Service phase 3 ","5GMARCH_Ph3",2,"Rel-19","S6","Thu 08/06/23","Thu 12/12/24",1,"SP-230781",null,"Liu, Yue, China Mobile, ","liuyueyjy@chinamobile.com ","7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50; 5/12/24: 50%->100; 5/12/24: FCD:09/09/2024->12/24",null,100,51,null,null,"Thu 08/06/23","Thu 05/12/24"]
[673,1060019,"   CT aspects for enabling MSGin5G Service phase 3","5GMARCH_Ph3",2,"Rel-19","C1","Mon 02/12/24","Tue 09/09/25",0.28999999999999998,"CP-251225",null,"Liu, Yue, China Mobile","liuyueyjy@chinamobile.com","7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50","24.538, 24.544, 24.546, 29.538",100,51,null,"x","Thu 08/06/23","Wed 04/09/24"]
[674,1060052,"      CT1 aspects for enabling MSGin5G Service phase 3","5GMARCH_Ph3",3,"Rel-19","C1","Mon 02/12/24","Tue 09/09/25",0.75,"CP-251225",null,"Liu, Yue, China Mobile","liuyueyjy@chinamobile.com","7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50","24.538, 24.544, 24.546, 29.538",100,51,null,"x","Thu 08/06/23","Wed 04/09/24"]
[675,1060053,"      CT3 aspects for enabling MSGin5G Service phase 3","5GMARCH_Ph3",3,"Rel-19","C3","Mon 02/12/24","Tue 09/09/25",0.5,"CP-251225",null,"Liu, Yue, China Mobile","liuyueyjy@chinamobile.com","7/9/23: 0%->0; 8/12/23: 0%->20; 14/3/24: 20%->35; 13/6/24: 35%->40; 4/9/24: 40%->50","24.538, 24.544, 24.546, 29.538",100,51,null,"x","Thu 08/06/23","Wed 04/09/24"]
[676,1030030,"   Security aspects for MSGin5G Service Phase 3 ","5GMARCH_SEC_Ph3",2,"Rel-19","S3","Tue 02/04/24","Thu 12/12/24",1,"SP-240516",null,"Xiaoting Huang, ","huangxiaoting@chinamobile.com ","; 13/6/24: 0%->70; 5/9/24: 70%->100",33.500999999999998,103,52,null,null,"Thu 14/03/24","Thu 05/09/24"]
[677,1000039,"Enhanced Mission Critical Architecture","enhMC",1,"Rel-19","S6","Thu 08/06/23","Thu 12/12/24",1,"SP-241691",null,"Negalaguli, Harish, Motorola Solutions, ","harish.negalaguli@motorolasolutions.com ","; 7/9/23: WID:SP-230695->SP-230988; 7/9/23: 0%->5; 8/12/23: 5%->30; 14/3/24: 30%->40; 13/6/24: 40%->60; 4/9/24: 60%->75; 5/12/24: 75%->100; 8/1/25: WID:SP-230988->SP-241691","23.280; 23.379; 23.281; 23.282; 23.283; 23.289 ",100,51,null,null,"Thu 08/06/23","Wed 08/01/25"]
[678,1050071,"SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",1,"Rel-19",null,"Thu 07/09/23","Tue 09/09/25",0.84,"SP-230989",null,"Cuili Ge, Huawei ","gecuili@huawei.com ","8/12/23: 0%->25; 14/3/24: 25%->35; 13/6/24: 35%->70",null,101,51,null,null,"Thu 07/09/23","Thu 13/06/24"]
[679,1010006,"   Stage 2 of SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",2,"Rel-19","S6","Thu 07/09/23","Thu 12/12/24",1,"SP-230989",null,"Cuili Ge, Huawei ","gecuili@huawei.com ","8/12/23: 0%->25; 14/3/24: 25%->35; 13/6/24: 35%->70; 4/9/24: 70%->80; 5/12/24: 80%->100",null,101,51,null,null,"Thu 07/09/23","Thu 05/12/24"]
[680,1050017,"   CT aspects of SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",2,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.78,"CP-243261",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,"24.543, 24.548, 29.548, 29.549",101,51,null,null,"Thu 07/09/23","Thu 13/06/24"]
[681,1050072,"      CT1 aspects of SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",3,"Rel-19","C1","Mon 09/09/24","Tue 09/09/25",0.8,"CP-243261",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,null,101,51,null,null,"Thu 07/09/23","Thu 13/06/24"]
[682,1050073,"      CT3 aspects of SEAL DD (Data Delivery) Phase 2 ","SEALDD_Ph2",3,"Rel-19","C3","Mon 09/09/24","Tue 09/09/25",1,"CP-243261",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,null,101,51,null,null,"Thu 07/09/23","Thu 13/06/24"]
[683,1040081,"Architecture for enabling Edge Applications Phase 3 ","EDGEAPP_Ph3",1,"Rel-19",null,"Thu 07/09/23","Tue 09/09/25",0.87,"SP-231160",null,"Hyesung Kim, Samsung ","hs1207.kim@samsung.com ","; 8/12/23: 0%->15; 14/3/24: 15%->35",23.558,101,51,null,null,"Thu 07/09/23","Thu 14/03/24"]
[684,1010007,"   Stage 2 of enabling Edge Applications Phase 3 ","EDGEAPP_Ph3",2,"Rel-19","S6","Thu 07/09/23","Thu 12/12/24",1,"SP-231160",null,"Hyesung Kim, Samsung ","hs1207.kim@samsung.com ","; 8/12/23: 0%->15; 14/3/24: 15%->35; 13/6/24: 35%->80; 4/9/24: 80%->85; 5/12/24: 85%->100",23.558,101,51,null,null,"Thu 07/09/23","Thu 05/12/24"]
[685,1040008,"   CT aspects for Enabling Edge Applications Phase 3","EDGEAPP_Ph3",2,"Rel-19","C3","Mon 17/06/24","Tue 09/09/25",0.82,"CP-241074",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com",null,"24.558,29.558",101,51,null,"x","Wed 06/09/23","Wed 06/09/23"]
[686,1040058,"      CT1 aspects for Enabling Edge Applications Phase 3","EDGEAPP_Ph3",3,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.7,"CP-241074",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com","16/7/24: FCD:06/06/2025->/25",null,101,51,null,"x","Wed 06/09/23","Tue 16/07/24"]
[687,1040059,"      CT3 aspects for Enabling Edge Applications Phase 3","EDGEAPP_Ph3",3,"Rel-19","C3","Mon 17/06/24","Tue 09/09/25",0.98,"CP-241074",null,"Narendranath Durga Tangudu, Samsung","n.tangudu@samsung.com","16/7/24: 0%->100",null,101,51,null,"x","Wed 06/09/23","Tue 16/07/24"]
[688,0,"Rel-19 miscellaneous Security",null,1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,null,null,null,null,null,null,null,null,null,null,"Thu 07/12/23","NA"]
[689,1030029,"Security Assurance Specification for maintenance of 5G features ","SCAS_5G_Maint",1,"Rel-19","S3","Tue 02/04/24","Mon 03/03/25",1,"SP-240515",null,"Rong Wu (Huawei) ","raina.wu@huawei.com ","5/9/24: 0%->50; 5/12/24: 50%->100",null,103,52,null,null,"Thu 14/03/24","Thu 05/12/24"]
[690,1010010,"5G Security Assurance Specification (SCAS) for the Unified Data Repository (UDR) ","SCAS_5G_UDR",1,"Rel-19","S3","Wed 06/09/23","Tue 21/05/24",0.8,"SP-230864",null,"Andreas, Joerg, BSI Germany ","joerg.andreas@bsi.bund.de ","; 8/12/23: 0%->10; 3/4/24: 33.530 added;; 13/6/24: 10%->50; 5/9/24: 50%->60; 5/12/24: 60%->80","33.926 ; 33.530",101,51,null,null,"Wed 06/09/23","Thu 05/12/24"]
[691,1010011,"5G Security Assurance Specification (SCAS) for the Short Message Service Function (SMSF) ","SCAS_5G_SMSF",1,"Rel-19","S3","Wed 06/09/23","Mon 09/09/24",1,"SP-231158",null,"Manjesh K. Hanawal, IIT Bombay","mhanawal@iitb.ac.in","8/12/23: 0%->10; 4/1/24: 33.529 added;; 14/3/24: 10%->40; 13/6/24: 40%->70; 5/9/24: 70%->40; 5/9/24: 40%->100; 5/12/24: 100%->100",33.529000000000003,101,51,null,null,"Wed 06/09/23","Thu 05/12/24"]
[692,1010012,"Addition of 256-bit security Algorithms ","256_Algo",1,"Rel-19","S3","Wed 06/09/23","Sun 03/03/24",1,"SP-240476",null,"Orkopoulos, Stawros ","stawros.orkopoulos@nokia.com ","8/12/23: 0%->10; 4/1/24: 35.248 added;; 14/3/24: 10%->100; 2/4/24: WID:SP-231159->SP-240476","35.248; 35.247; 35.246; 35.245; 35.244; 35.243; 35.242; 35.241; 35.240",101,51,null,null,"Wed 06/09/23","Tue 02/04/24"]
[693,1020036,"Addition of Milenage-256 algorithm ","Milenage_256",1,"Rel-19","S3","Wed 03/01/24","Thu 12/12/24",1,"SP-241087",null,"Mireille Pauliac ","mireille.pauliac@thalesgroup.com ","4/1/24: 35.237 added;; 4/1/24: 35.236 added;; 4/1/24: 35.235 added;; 4/1/24: 35.234 added;; 14/3/24: 0%->5; 5/9/24: 5%->65; 26/9/24: WID:SP-231792->SP-241087; 5/12/24: 65%->100","35.237; 35.236; 35.235; 35.234",102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[694,1020041,"Study on enabling a cryptographic algorithm transition to 256-bits ","FS_CAT256",1,"Rel-19","S3","Wed 03/01/24","Thu 12/12/24",1,"SP-231788",null,"Yuto Nakano ","yt-nakano@kddi.com ","4/1/24: 33.700-41 added;; 14/3/24: 0%->10; 13/6/24: 10%->90; 5/9/24: 90%->100","33.700-41",102,52,null,null,"Thu 07/12/23","Thu 05/09/24"]
[695,1020034,"Study on enablers for Zero Trust Security ","FS_eZTS",1,"Rel-19","S3","Wed 03/01/24","Thu 12/12/24",1,"SP-231784",null,"Sheeba Backia Mary Baskaran ","smary@lenovo.com ","4/1/24: 33.794 added;; 14/3/24: 0%->20; 13/6/24: 20%->50; 5/9/24: 50%->75; 5/12/24: 75%->95; 6/3/25: 95%->100; 5/6/25: 100%->100",33.793999999999997,102,52,null,null,"Thu 07/12/23","Thu 05/06/25"]
[696,1020035,"Mission critical security enhancements for release 19 ","MCXSec4",1,"Rel-19","S3","Thu 04/01/24","Fri 30/08/24",0.99,"SP-231783",null,"Woodward, Tim, Motorola Solutions, Inc. ","tim.woodward@motorolasolutions.com ","; 14/3/24: 0%->10; 5/9/24: 10%->50; 5/12/24: 50%->90; 6/3/25: 90%->95; 5/6/25: 95%->99",33.18,102,52,null,null,"Thu 07/12/23","Thu 05/06/25"]
[697,1020038,"Study on the security support for the Next Generation Real Time Communication services phase 2 ","FS_NG_RTC_SEC_Ph2",1,"Rel-19","S3","Wed 03/01/24","Mon 30/12/24",1,"SP-240233",null,"Vlasios Tsiatsis ","vlasios.tsiatsis@ericsson.com ","4/1/24: 33.790 added;; 14/3/24: 0%->17; 2/4/24: WID:SP-231785->SP-240233; 13/6/24: 17%->40; 5/9/24: 40%->60; 5/12/24: 60%->80; 6/3/25: 80%->80; 6/3/25: FCD:12/12/2024->/25; 5/6/25: 80%->100",33.79,102,52,null,null,"Thu 07/12/23","Thu 05/06/25"]
[698,1060063,"Security support for the Next Generation Real Time Communication services Phase 2 ","NG_RTC_SEC_Ph2",1,"Rel-19","S3","Thu 02/01/25","Mon 03/03/25",0,"SP-250649",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","; 26/3/25: WID:SP-241778->SP-250078; 27/6/25: WID:SP-250078->SP-250649",33.203000000000003,106,54,null,null,"Thu 05/12/24","Fri 27/06/25"]
[699,1020040,"Study of ACME for Automated Certificate Management in SBA ","FS_ACME_SBA",1,"Rel-19","S3","Wed 03/01/24","Thu 12/12/24",1,"SP-231787",null,"Charles Eckel ","eckelcu(at)cisco.com ","4/1/24: 33.776 added;; 14/3/24: 0%->15; 13/6/24: 15%->45; 13/6/24: FCD:06/06/2024->12/24; 5/9/24: 45%->55; 5/12/24: 55%->100; 6/3/25: 100%->100; 5/6/25: 100%->100",33.776000000000003,102,52,null,null,"Thu 07/12/23","Thu 05/06/25"]
[700,1060066,"Automatic Certificate Management Environment (ACME) for the Service Based Architecture (SBA) ","ACME_SBA",1,"Rel-19","S3","Thu 05/12/24","Fri 06/06/25",1,"SP-241960",null,"Charles Eckel (Cisco)","eckelcu(at)cisco.com","; 6/3/25: 0%->55; 5/6/25: 55%->100",33.31,106,54,null,null,"Thu 05/12/24","Thu 05/06/25"]
[701,1080043,"Roaming and interconnect authorization aspects in indirect communication ","SBA_RoamInt-SEC",1,"Rel-19","S3","Fri 27/06/25","Mon 07/07/25",0,"SP-250815",null,"Anja Jerichow ","anja.jerichow@nokia.com ",null,33.500999999999998,108,55,null,null,"Thu 05/06/25","NA"]
[702,1080046,"Public key distribution and Issuer claim verification of the Access Token ","SBA_KDATV-SEC",1,"Rel-19","S3","Thu 05/06/25","Fri 06/06/25",0,"SP-250816",null,"Mohsin Khan ","mohsin.a.khan@ericsson.com ",null,33.500999999999998,108,55,null,null,"Thu 05/06/25","NA"]
[703,1020042,"3GPP profiles for cryptographic algorithms and security protocols ","CryptoSP",1,"Rel-19","S3","Wed 03/01/24","Thu 12/12/24",1,"SP-231793",null,"Mohsin Khan A ","mohsin.a.khan@ericsson.com ","; 14/3/24: 0%->20; 13/6/24: 20%->50; 5/9/24: 50%->80; 5/12/24: 80%->100; 6/3/25: 100%->100; 5/6/25: 100%->100","33.127; 33.203; 33.210; 33.222; 33.246; 33.259; 33.303; 33.310; 33.401; 33.402; 33.434; 33.501 ",102,52,null,null,"Thu 07/12/23","Thu 05/06/25"]
[704,1020043,"Study on mitigations against bidding down attacks ","FS_MiBiDA",1,"Rel-19","S3","Wed 03/01/24","Thu 12/12/24",1,"SP-231789",null,"Noamen Ben Henda ","noamen.ben.henda@huawei.com ","4/1/24: 33.701 added;; 14/3/24: 0%->20; 13/6/24: 20%->85; 13/6/24: FCD:05/06/2024->12/24; 5/9/24: 85%->100",33.701000000000001,102,52,null,null,"Thu 07/12/23","Thu 05/09/24"]
[705,1060054,"Mobility over non-3GPP access to avoid full primary authentication ","Non3GPPMob_Sec",1,"Rel-19",null,"Wed 03/01/24","Tue 09/09/25",0.53,"SP-241088",null,"Khare, Saurabh ","saurabh.khare@nokia.com ","; 26/9/24: WID:SP-240653->SP-241088",33.500999999999998,104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[706,1020045,"   Study on Security for mobility over non-3GPP access to avoid full primary authentication ","FS_Non3GPPMob_Sec",2,"Rel-19","S3","Wed 03/01/24","Fri 30/08/24",0.25,"SP-231791",null,"Saurabh Khare, Nokia ","Saurabh.Khare@nokia.com ","4/1/24: 33.702 added;; 14/3/24: 0%->25",33.701999999999998,102,52,null,null,"Thu 07/12/23","Thu 14/03/24"]
[707,1040024,"   Security for mobility over non-3GPP access to avoid full primary authentication ","Non3GPPMob_Sec",2,"Rel-19","S3","Wed 07/08/24","Thu 12/12/24",0,"SP-241088",null,"Khare, Saurabh ","saurabh.khare@nokia.com ","; 26/9/24: WID:SP-240653->SP-241088",33.500999999999998,104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[708,1060020,"   CT aspects of security for mobility over non-3GPP access to avoid full primary authentication","Non3GPPMob_Sec",2,"Rel-19","C1","Mon 02/12/24","Tue 09/09/25",1,"CP-250133",null,"Nassar, Mohamed Amin, Nokia","mohamed.a.nassar@nokia.com",null,24.501999999999999,104,53,null,null,"Wed 12/06/24","Thu 26/09/24"]
[709,0,"Rel-19 miscellaneous OAM&charging",null,1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,null,null,null,null,null,null,null,null,null,null,"Thu 07/12/23","NA"]
[710,1070020,"Charging aspects for Multi-Operator Core Network (MOCN) Network Sharing ","CH_MOCN_NetShare",1,"Rel-19","S5","Wed 26/03/25","Tue 09/09/25",0.75,"SP-250819",null,"Robert Törnkvist, Ericsson, ","robert.tornkvist@ericsson.com ","; 6/6/25: 0%->75; 27/6/25: WID:SP-250371->SP-250819","32.130; 32.240; 32.255; 32.291; 32.298 ; 28.201",107,54,null,null,"Wed 05/03/25","Fri 27/06/25"]
[711,1060006,"Service Based Management Architecture enhancement phase 3 ","SBMA_Ph3",1,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.9,"SP-241939",null,"Kai Zhang (Huawei)","kai.zhangkai@huawei.com","; 6/3/25: 0%->40; 6/6/25: 40%->90","32.156; 28.532; 28.533; 28.537; 28.622; 28.623; 28.530; 28.550; 32.421; 32.422; 32.423; 28.404; 28.405; 28.406; 28.552; 28.554; 28.558; 32.130; 28.313; 28.314; 28.623; 28.310; 28.530; 28.531; 28.111; 28.550; 28.621; 28.623; 32.421; 32.422; 28.404; 28.405;",106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[712,1020019,"Study on Management Data Analytics (MDA) Phase 3 ","FS_eMDAS_Ph3",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-241157",null,"Brendan T Hassett (Huawei) ","brendan.t.hassett@huawei.com ","13/6/24: 0%->70; 16/7/24: WID:SP-231726->SP-240968; 4/9/24: 70%->90; 4/9/24: FCD:09/09/2024->12/24; 26/9/24: WID:SP-240968->SP-241157; 5/12/24: 90%->100",null,102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[713,1060014,"Management Data Analytics phase 3 ","eMDAS_Ph3",1,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.85,"SP-241947",null,"Brendan T Hassett (Huawei)","brendan.t.hassett@huawei.com","; 6/3/25: 0%->30; 6/6/25: 30%->85",28.103999999999999,106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[714,1020008,"Study on intent driven management services for mobile network phase 3 ","FS_IDMS_MN_Ph3",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-231737",null,"Ruiyue Xu (Huawei) ","xuruiyue@huawei.com ","14/3/24: 0%->5; 13/6/24: 5%->70; 4/9/24: 70%->95; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 95%->100",null,102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[715,1060013,"Intent driven management services for mobile network phase 3 ","IDMS_MN_Ph3",1,"Rel-19","S5","Thu 30/01/25","Fri 06/06/25",1,"SP-241946",null,"Ruiyue Xu (Huawei)","xuruiyue@huawei.com","; 6/3/25: 0%->65; 6/6/25: 65%->100",28.312000000000001,106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[716,1020009,"Study on closed control loop management ","FS_CCLM",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-231735",null,"Deepanshu Gautam (Samsung) ","deepanshu.g@samsung.com ","14/3/24: 0%->5; 13/6/24: 5%->40; 4/9/24: 40%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100",null,102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[717,1020018,"Study on management aspects of Network Digital Twin ","FS_NDT",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-231727",null,"Yushuang Hu (China Mobile) ","huyushuang@chinamobile.com ","4/1/24: 28.915 added;; 14/3/24: 0%->5; 13/6/24: 5%->65; 13/6/24: WID:SP-231428->SP-231727; 4/9/24: 65%->95; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 95%->100",28.914999999999999,102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[718,1060005,"Management aspects of Network Digital Twins ","NDT",1,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.95,"SP-241938",null,"Yushuang Hu (China Mobile) ","huyushuang@chinamobile.com","6/3/25: 0%->10; 6/6/25: 10%->95",null,106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[719,1020010,"Study on Cloud Aspects of Management and Orchestration ","FS_Cloud_OAM",1,"Rel-19","S5","Wed 03/01/24","Tue 09/09/25",0.9,"SP-241566",null,"Guangjing Cao (CMCC)","caoguangjing@chinamobile.com","14/3/24: 0%->2; 13/6/24: 2%->40; 4/9/24: 40%->80; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 80%->90; 8/1/25: WID:SP-231781->SP-241566 (rapp changed); 6/3/25: 90%->85; 6/3/25: FCD:30/08/2024->/25; 6/6/25: 85%->90",null,102,52,null,null,"Thu 07/12/23","Fri 06/06/25"]
[720,1020016,"Study on Enablers for Security Monitoring ","FS_SECM",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-231736",null,"Clifton Fernandes (Nokia) ","clifton.fernandes@nokia.com ","4/1/24: 28.870 added;; 4/9/24: 0%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100",28.87,102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[721,1020011,"Study on Service Based Management Architecture enhancement phase 3 ","FS_SBMA_Ph3",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-241569",null,"Kai Zhang (Huawei) ","kai.zhangkai@huawei.com ","13/6/24: 0%->45; 4/9/24: 45%->75; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 75%->100; 8/1/25: WID:SP-231725->SP-241569",null,102,52,null,null,"Thu 07/12/23","Wed 08/01/25"]
[722,1020033,"Study on Management of planned configurations ","FS_PlanM",1,"Rel-19","S5","Thu 04/01/24","Mon 09/09/24",1,"SP-231721",null,"Olaf Pollakowski (Nokia) ","olaf.pollakowski@nokia.com ","4/1/24: 28.872 added;; 13/6/24: 0%->60; 4/9/24: 60%->100",28.872,102,52,null,null,"Wed 03/01/24","Wed 04/09/24"]
[723,1050032,"Management of planned configurations ","PlanM",1,"Rel-19","S5","Wed 04/09/24","Tue 09/09/25",0.75,"SP-241379",null,"Olaf Pollakowski (Nokia)","olaf.pollakowski@nokia.com","26/9/24: 28.572 added;; 5/12/24: 0%->60; 6/3/25: 60%->75; 6/6/25: 75%->75; 6/6/25: FCD:Fri 06/06/->/25",28.571999999999999,105,53,null,null,"Wed 04/09/24","Fri 06/06/25"]
[724,1060010,"Closed Control Loop Management ","CCLM",1,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.8,"SP-241943",null,"Deepanshu Gautam (Samsung)","deepanshu.g@samsung.com","; 6/3/25: 0%->10; 6/6/25: 10%->80","28.535; 28.536; 28.622; 32.161 ",106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[725,1020025,"Data management phase 2 ","MADCOL_Ph2",1,"Rel-19","S5","Wed 03/01/24","Tue 09/09/25",0.88,"SP-250116",null,"Sreekumar Pothera Kalloor (Nokia)","sreekumar.pk@nokia.com","; 13/6/24: 0%->50; 16/7/24: WID:SP-231746->SP-240877; 4/9/24: 50%->80; 5/12/24: 80%->88. 03/25: Rapporteur updated from sivaramakrishnan.swaminathan@nokia.com; 26/3/25: WID:SP-240877->SP-250116; 26/3/25: FCD:30/12/2024->/25; 6/6/25: 88%->88; 6/6/25: FCD:","28.622; 28.623 ",102,52,null,null,"Thu 07/12/23","Fri 06/06/25"]
[726,1020012,"Study on data management regarding subscriptions and reporting ","FS_Data_SREP",1,"Rel-19","S5","Wed 03/01/24","Mon 09/09/24",1,"SP-231732",null,"Robert Petersen (Ericsson) ","robert.petersen@ericsson.com ","13/6/24: 0%->60; 4/9/24: 60%->100",null,102,52,null,null,"Thu 07/12/23","Wed 04/09/24"]
[727,1020026,"5G performance measurements and KPIs phase 4 ","PM_KPI_5G_Ph4",1,"Rel-19","S5","Wed 03/01/24","Tue 09/09/25",0.9,"SP-250511",null,"XiuMin Chen (China Telecom)","chenxiumin@chinatelecom.cn","; 13/6/24: 0%->20; 4/9/24: 20%->30; Rapporteur update: Xiebaoguo->Ruan bang qiu (ruan.bangqiu@zte.com.cn); 26/9/24: WID:SP-231747->SP-241155; 5/12/24: 30%->65; 6/3/25: 65%->75; 6/6/25: 75%->90; 6/6/25: FCD:Mon 30/12/->/25; 27/6/25: WID:SP-241155->SP-2505","28.552; 32.425; 28.554; 28.532; 28.550; 28.558; 32.404; 32.401",102,52,null,null,"Thu 07/12/23","Fri 27/06/25"]
[728,1020027,"5G Advanced NRM features phase 3 ","AdNRM_Ph3",1,"Rel-19","S5","Wed 03/01/24","Fri 06/06/25",1,"SP-250123",null,"Sean Sun (Nokia) ","sean.sun@nokia-sbell.com ","; 13/6/24: 0%->15; 16/7/24: WID:SP-231745->SP-240875; 4/9/24: 15%->30; 5/12/24: 30%->60; 8/1/25: WID:SP-240875->SP-241565; 6/3/25: 60%->75; 26/3/25: WID:SP-241565->SP-250123; 26/3/25: FCD:30/12/2024->/25; 6/6/25: 75%->100","28.540; 28.541; 28.622; 28.623 ",102,52,null,null,"Thu 07/12/23","Fri 06/06/25"]
[729,1020028,"Subscriber and Equipment Trace and QoE collection management ","TraceQoE_OAM",1,"Rel-19","S5","Wed 03/01/24","Tue 09/09/25",0.8,"SP-250115",null,"Zu Qiang (Ericsson) ","zu.qiang@ericsson.com ","; 13/6/24: 0%->20; 4/9/24: 20%->40; 5/12/24: 40%->75; 6/3/25: 75%->80; 26/3/25: WID:SP-231748->SP-250115; 6/6/25: FCD:Mon 30/12/->/25","32.421; 32.422; 32.423; 28.404; 28.405; 28.406; 28.622; 28.623 ",102,52,null,null,"Thu 07/12/23","Fri 06/06/25"]
[730,1020013,"Study on Management Aspects of NTN Phase 2 ","FS_NTN_OAM_Ph2",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-231733",null,"MingRui Sun (China Unicom) ","sunmr19@chinaunicom.cn ","13/6/24: 0%->65; 4/9/24: 65%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100",null,102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[731,1020014,"Study on management of IAB nodes ","FS_NR_mobile_IAB_OAM",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-231729",null,"JunFeng Wang (Ericsson) ","junfeng.a.wang@ericsson.com ","13/6/24: 0%->40; 13/6/24: FCD:09/09/2024->12/24; 4/9/24: 40%->90; 5/12/24: 90%->100",null,102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[732,1060015,"Management of IAB nodes ","NR_MOBILE_IAB_OAM",1,"Rel-19","S5","Sat 01/03/25","Tue 09/09/25",0.7,"SP-241948",null,"JunFeng Wang (Ericsson)","junfeng.a.wang@ericsson.com","; 6/6/25: 0%->70","28.541; 28.540; 28.531; 28.314; 28.315 ",106,54,null,null,"Thu 05/12/24","Fri 06/06/25"]
[733,1020017,"Study on management aspects of RedCap feature ","FS_NR_RedCap_OAM",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-231734",null,"Zhen Xing (China Unicom) ","xingz12@chinaunicom.cn ","13/6/24: 0%->50; 4/9/24: 50%->75; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 75%->100",null,102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[734,1020020,"Study on Enhancement of Management Aspects related to NWDAF Phase 2 ","FS_NWDAF_OAM_Ph2",1,"Rel-19","S5","Wed 03/01/24","Mon 09/09/24",1,"SP-231724",null,"Primary Rapporteur: Song Zhao (China Telecom) ","zhaosong1@chinatelecom.cn ","13/6/24: 0%->75; 4/9/24: 75%->100",null,102,52,null,null,"Thu 07/12/23","Wed 04/09/24"]
[735,1050031,"Enhancement of Management Aspects Related of NWDAF Phase 2 ","NWDAF_OAM_Ph2",1,"Rel-19","S5","Wed 04/09/24","Fri 06/06/25",1,"SP-241378",null,"Song Zhao (China Telecom) ","zhaosong1@chinatelecom.cn ","; 5/12/24: 0%->60; 6/3/25: 60%->65; 6/6/25: 65%->100","28.552; 28.541 ",105,53,null,null,"Wed 04/09/24","Fri 06/06/25"]
[736,1020015,"Study on Management of Network Sharing Phase3 ","FS_NetShare_OAM_Ph3",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-240966",null,"ZhaoNing Wang (China Unicom) ","wangzn18@chinaunicom.cn ","13/6/24: 0%->50; 16/7/24: WID:SP-231731->SP-240966; 4/9/24: 50%->90; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 90%->100",null,102,52,null,null,"Thu 07/12/23","Thu 05/12/24"]
[737,1020022,"Study on Enhanced OAM for management exposure to external consumers ","FS_MExpo",1,"Rel-19","S5","Wed 03/01/24","Thu 12/12/24",1,"SP-241570",null,"Srilakshmi Srinivasaraju (Nokia)","srilakshmi.s@nokia.com","14/3/24: 0%->5; 13/6/24: 5%->50; 16/7/24: WID:SP-231728->SP-240967; 4/9/24: 50%->60; 4/9/24: FCD:09/09/2024->12/24; 5/12/24: 60%->100; 8/1/25: WID:SP-240967->SP-241570",null,102,52,null,null,"Thu 07/12/23","Wed 08/01/25"]
[738,0,"Rel-19 other",null,1,"Rel-19",null,"Thu 07/03/19","Thu 07/03/19",0,null,null,null,null,null,null,null,null,null,null,"Thu 07/12/23","NA"]
[739,1060055,"Reducing Information Exposure over SBI ","RedInfExp_SBI",1,"Rel-19",null,"Wed 07/06/23","Tue 09/09/25",1,"CP-243308",null,"Nivedya P S, Samsung","nivedya.ps@samsung.com","30/6/23: 29.857 added;; 3/4/25: WID:CP-243019->CP-243308",null,100,51,null,null,"Wed 07/06/23","Thu 03/04/25"]
[740,1000001,"   Study on Reducing Information Exposure over SBI ","FS_RedInfExp_SBI",2,"Rel-19","C4","Wed 07/06/23","Tue 12/12/23",1,"CP-231350",null,"Varini Gupta, Samsung ","varini.gupta@samsung.com ","30/6/23: 29.857 added;",29.856999999999999,100,51,null,null,"Wed 07/06/23","Fri 30/06/23"]
[741,1060003,"   Reducing Information Exposure over SBI ","RedInfExp_SBI",2,"Rel-19","C4","Mon 02/12/24","Tue 09/09/25",1,"CP-243308",null,"Nivedya P S, Samsung","nivedya.ps@samsung.com","30/6/23: 29.857 added;","29.510, 29.500",100,51,null,null,"Wed 07/06/23","Fri 30/06/23"]
[742,1010003,"Study on IMS Disaster Prevention and Restoration Enhancement","FS_IMS_RES",1,"Rel-19","C4","Thu 25/08/22","Sun 03/03/24",1,"CP-232281",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn","21/9/23: 29.866 added;","29.xxx; 29.866",96,49,null,null,"Fri 03/06/22","Thu 21/09/23"]
[743,1080001,"IMS Disaster Prevention and Restoration Enhancement","IMS_RES-CT",1,"Rel-19","C4","Thu 06/06/24","Tue 09/09/25",0.5,"CP-251016",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn",null,"23.380, 24.229, 23.334, 29.244, 29.500, 29.562, 29.213, 29.513",96,49,null,"x","Fri 03/06/22","Thu 21/09/23"]
[744,1080035,"   CT3 aspects of IMS Disaster Prevention and Restoration Enhancement","IMS_RES-CT",2,"Rel-19","C3","Fri 06/06/25","Tue 09/09/25",0,"CP-251016",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn",null,"23.380, 24.229, 23.334, 29.244, 29.500, 29.562, 29.213, 29.513",96,49,null,"x","Fri 03/06/22","Thu 21/09/23"]
[745,1080036,"   CT4 aspects of IMS Disaster Prevention and Restoration Enhancement","IMS_RES-CT",2,"Rel-19","C4","Fri 06/06/25","Tue 09/09/25",1,"CP-251016",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn",null,"23.380, 24.229, 23.334, 29.244, 29.500, 29.562, 29.213, 29.513",96,49,null,"x","Fri 03/06/22","Thu 21/09/23"]
[746,1000016,"Study on Film Grain Synthesis ","FS_FGS",1,"Rel-19","S4","Thu 08/06/23","Mon 09/09/24",1,"SP-241389",null,"Brian Lee (Dolby Laboratories) ","Brian.Lee@dolby.com ","; 7/9/23: 0%->10; 8/12/23: 10%->20; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 20%->30; 14/3/24: FCD:03/03/2024->3/3/25; Rel-18->Rel-19; 13/6/24: 30%->; 4/9/24: 30%->100; 4/9/24: FCD:03/03/2025->09/24; 4/9/24: WID:SP-230539->SP-241120 ; 26/9/24: WID:SP-...","26.955 ; 26.855",100,51,null,null,"Thu 08/06/23","Thu 26/09/24"]
[747,1000019,"Study of Avatars in Real-Time Communication Services ","FS_AVATAR",1,"Rel-19","S4","Thu 08/06/23","Mon 03/03/25",1,"SP-230544",null,"Bouazizi, Imed, Qualcomm Incorporated ","bouazizi AT qti DOT qualcomm DOT com ","7/9/23: 0%->5; 21/9/23: 26.813 added;; 8/12/23: 5%->20; 14/3/24: 20%->30; 14/3/24: FCD:03/03/2024->12/24; ; Rel-18->Rel-19; 13/6/24: 30%->50; 4/9/24: 50%->55; 5/12/24: 55%->60; 5/12/24: FCD:12/12/2024->/25; 6/3/25: 60%->100",26.812999999999999,100,51,null,null,"Thu 08/06/23","Thu 06/03/25"]
[748,1040001,"Service Based Interface Protocol Improvements Release 19","SBIProtoc19",1,"Rel-19",null,"Mon 17/06/24","Tue 09/09/25",0.5,"CP-241021",null,"Wang Rong, China Mobile","wangrongyjy@chinamobile.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[749,1040050,"   CT3 aspects of Service Based Interface Protocol Improvements Release 19","SBIProtoc19",2,"Rel-19","C3","Mon 17/06/24","Tue 09/09/25",0.85,"CP-241021",null,"Wang Rong, China Mobile","wangrongyjy@chinamobile.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[750,1040051,"   CT4 aspects of Service Based Interface Protocol Improvements Release 19","SBIProtoc19",2,"Rel-19","C4","Mon 17/06/24","Tue 09/09/25",0.6,"CP-241021",null,"Wang Rong, China Mobile","wangrongyjy@chinamobile.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[751,1040003,"Subscriber Data Migration","SUBDMIG",1,"Rel-19","C4","Mon 17/06/24","Tue 09/09/25",0.95,"CP-251038",null,"Jesus de Gregorio, Ericsson","Jesus de Gregorio, jesus.de.gregorio@ericsson.com",null,"23.527,29.503,29.504,29.510,29.571",101,51,null,"x","Wed 06/09/23","Wed 06/09/23"]
[752,1050010,"Rel-19 Enhancements of Network Automation Enablers","eNetAE19",1,"Rel-19","C3","Mon 17/06/24","Tue 09/09/25",0.9,"CP-243078",null,"Xuefei Zhang (Huawei)","summer.xuefei@huawei.com",null,"29.508, 29.517, 29.520, 29.522, 29.552, 29.574, 29.575, 29.576, 29.591",101,51,null,null,"Wed 06/09/23","Thu 26/09/24"]
[753,1040005,"Study on Protocol for AI Data Collection from UPF","FS_PAIDC_UPF",1,"Rel-19","C4","Mon 17/06/24","Tue 09/09/25",0.9,"CP-251039",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,null,101,51,null,"x","Wed 06/09/23","Wed 06/09/23"]
[754,1080002,"Study on IMS resiliency","FS_IMSResil",1,"Rel-19","C4","Fri 06/06/25","Tue 09/09/25",0.1,"CP-251280",null,"Kenichi Yamamoto, KDDI","kc-yamamoto@kddi.com","18/7/25: 29.867 added;",29.867000000000001,101,51,null,"x","Wed 06/09/23","Fri 18/07/25"]
[755,1040039,"IMS Stage-3 IETF Protocol Alignment","IMSProtoc19",1,"Rel-19",null,"Mon 17/06/24","Tue 09/09/25",0.43,"CP-251219",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,"23.218, 24.229, 24.930, 24.186, 29.163, 29.165, 29.292",101,51,null,"x","Wed 06/09/23","Wed 06/09/23"]
[756,1040062,"   CT1 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc19",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.4,"CP-251219",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,null,101,51,null,"x","Wed 06/09/23","Wed 06/09/23"]
[757,1040063,"   CT3 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc19",2,"Rel-19","C3","Mon 17/06/24","Tue 09/09/25",0.85,"CP-251219",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com",null,null,101,51,null,"x","Wed 06/09/23","Wed 06/09/23"]
[758,1040041,"Protocol enhancements for Mission Critical Services","MCProtoc19",1,"Rel-19",null,"Mon 17/06/24","Tue 09/09/25",0.46,"CP-241283",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[759,1040064,"   CT1 aspects of Protocol enhancements for Mission Critical Services","MCProtoc19",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.4,"CP-241283",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[760,1040065,"   CT3 aspects of Protocol enhancements for Mission Critical Services","MCProtoc19",2,"Rel-19","C3","Mon 17/06/24","Tue 09/09/25",0.85,"CP-241283",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[761,1040066,"   CT4 aspects of Protocol enhancements for Mission Critical Services","MCProtoc19",2,"Rel-19","C4","Sun 03/11/24","Tue 09/09/25",0,"CP-241283",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,null,101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[762,1040042,"Enhancement of controlling RAT utilization","ECRATU",1,"Rel-19",null,"Mon 17/06/24","Tue 09/09/25",0.68,"CP-251220",null,"Yang Lu, Vodafone","yang.lu@vodafone.com",null,"24.301, 24.501, 23.122, 29.272, 29.503",101,51,null,"x","Wed 06/09/23","Wed 06/09/23"]
[763,1040067,"   CT1 aspects of Enhancement of controlling RAT utilization","ECRATU",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.99,"CP-251220",null,"Yang Lu, Vodafone","yang.lu@vodafone.com",null,null,101,51,null,"x","Wed 06/09/23","Wed 06/09/23"]
[764,1040068,"   CT4 aspects of Enhancement of controlling RAT utilization","ECRATU",2,"Rel-19","C4","Mon 17/06/24","Tue 09/09/25",0.98,"CP-251220",null,"Yang Lu, Vodafone","yang.lu@vodafone.com",null,null,101,51,null,"x","Wed 06/09/23","Wed 06/09/23"]
[765,1040045,"Enhanced Mission Critical Location Management","enhMCLoc",1,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.8,"CP-241288",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,"24.281,24.282,24.283,24.379,24.481,24.482,24.483,24.484,29.379",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[766,1050027,"Alignment of eCall over IMS with CEN","eCallCEN",1,"Rel-19","C1","Mon 09/09/24","Fri 06/06/25",1,"CP-251223",null,"Osama Lotfallah, Qualcomm Incorporated","osamal@qti.qualcomm.com",null,24.228999999999999,101,51,null,"x","Wed 06/09/23","Wed 06/09/23"]
[767,1060075,"UE Conformance - Alignment of eCall over IMS with CEN ","eCallCEN-UEConTest",1,"Rel-19","R5","Sat 14/09/24","Fri 12/12/25",0.9,"RP-242495","RP-251190","Qualcomm ",null,"6/3/25: Compl:0%->80%; Stat Rep: ->RP-250112; ; 6/6/25: FCD:Fri 06/06/25->Fri 12/12/25; Compl:80%->90%; Stat Rep: RP-250112->RP-251190; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[768,1060025,"Rel-19 Enhancements of UE Policy","UEP19",1,"Rel-19","C3","Mon 02/12/24","Tue 09/09/25",0.9,"CP-243073",null,"Susana Fernández, Ericsson","Susana.fernandez@ericsson.com",null,"29.525, 29.523, 29.519, 29.522, 29.513",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[769,1070005,"Rel-19 Enhancements of SM Policy","SMPC19",1,"Rel-19","C3","Mon 03/03/25","Tue 09/09/25",0.7,"CP-250075",null,"Chi Zhang, Huawei","margo.zhangchi@huawei.com",null,"29.512, 29.513",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[770,1070006,"CT Aspects for IP Domain usage","IPD",1,"Rel-19","C3","Mon 03/03/25","Tue 09/09/25",0.5,"CP-250248",null,"Zhenning Huang, China Mobile","huangzhenning@chinamobile.com",null,"29.213, 29.513",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[771,1060018,"NAS layer overhead reduction for data transfer using CP CIoT","NORDAT_CP",1,"Rel-19","C1","Mon 02/12/24","Tue 09/09/25",0.8,"CP-250251",null,"Amer Catovic","amerc@qti.qualcomm.com",null,"24.301, 24.007",101,51,null,null,"Wed 06/09/23","Wed 06/09/23"]
[772,1070009,"Support for PWS in Satellite E-UTRAN and Satellite NG-RAN","PWS_NTN",1,"Rel-19",null,"Mon 03/03/25","Tue 09/09/25",0.81,"CP-251222",null,"Amer Catovic","amerc@qti.qualcomm.com",null,23.041,101,51,null,"x","Wed 06/09/23","Wed 06/09/23"]
[773,1070049,"   CT1 aspects of Support for PWS in Satellite E-UTRAN and Satellite NG-RAN","PWS_NTN",2,"Rel-19","C1","Mon 03/03/25","Tue 09/09/25",0.9,"CP-251222",null,"Amer Catovic","amerc@qti.qualcomm.com",null,null,101,51,null,"x","Wed 06/09/23","Wed 06/09/23"]
[774,1070050,"   DELETED - CT4 aspects of Support for PWS in Satellite E-UTRAN and Satellite NG-RAN","PWS_NTN",2,"Rel-19","C4","Thu 06/03/25","Tue 09/09/25",1,"CP-251222",null,"Amer Catovic","amerc@qti.qualcomm.com",null,null,101,51,108,"x","Wed 06/09/23","Wed 06/09/23"]
[775,1040044,"Stage-3 5GS NAS protocol development 18 ","5GProtoc19",1,"Rel-19",null,"Mon 17/06/24","Tue 09/09/25",0.28000000000000003,"CP-241280",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,null,96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[776,1040046,"   Stage-3 5GS NAS protocol development 18 general aspects","5GProtoc19",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.4,"CP-241280",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,null,96,49,null,null,"Fri 03/06/22","NA"]
[777,1040047,"   Stage-3 5GS NAS protocol development 18 non 3GPP aspects","5GProtoc19-non3GPP",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.4,"CP-241280",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,null,96,49,null,null,"Fri 03/06/22","NA"]
[778,1040040,"Stage-3 SAE Protocol Development ","SAES19",1,"Rel-19",null,"Mon 17/06/24","Tue 09/09/25",0.28000000000000003,"CP-241284",null,"Sethi, Anuj, InterDigital ",null,null,null,96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[779,1040048,"   Stage-3 SAE Protocol Development general","SAES19",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.4,"CP-241284",null,"Sethi, Anuj, InterDigital ",null,null,null,96,49,null,null,"Fri 03/06/22","NA"]
[780,1040049,"   Stage-3 SAE Protocol Development non 3GPP","SAES19-non3GPP",2,"Rel-19","C1","Mon 17/06/24","Tue 09/09/25",0.4,"CP-241284",null,"Sethi, Anuj, InterDigital ",null,null,null,96,49,null,null,"Fri 03/06/22","NA"]
[781,970002,"Lawful Interception Rel-19 ","LI19",1,"Rel-19","S3LI","Fri 24/03/23","Sat 30/03/24",0.15,"SP-250817",null,"Koen Jaspers, PIDS","kbj@xs4all.nl","; 16/3/23: WID:SP-220752->SP-230242; 16/3/23: FCD:03/03/2024->9/9/2024. Rapporteur changed from Alex Leadbeater; 5/9/24: 0%->10; 5/12/24: 10%->15; 26/3/25: WID:SP-230242->SP-250372; 27/6/25: WID:SP-250372->SP-250817; 18/7/25: 33.129-2 added;; 18/7/25: 33","33.107; 33.108; 33.126; 33.127; 33.128 ; 33.129-2; 33.129-2; 33.129-1",97,49,null,null,"Sun 11/09/22","Fri 18/07/25"]
[782,1040010,"Lawful Interception Guidance Rel-19 ","LI19_Guide",1,"Rel-19","S3LI","Tue 16/07/24","Sun 22/12/24",0.52,"SP-240562",null,"Nag Rao, Nokia, ","nagaraja.rao@nokia.com ","5/12/24: 0%->52",null,104,53,null,null,"Tue 16/07/24","Thu 05/12/24"]
[783,1080003,"Harmonization of test case definitions for cross-RAT usability","TestHarmon_CrossRAT",1,"Rel-19","C6","Fri 06/06/25","Tue 03/03/26",0,"CP-251036",null,"Arne Marquordt, COMPRION GmbH","amarquordt@comprion.com",null,"31.117, 31.121, 31.124, 31.127",106,54,null,null,"Fri 24/01/25","Thu 06/03/25"]
[784,980130,"(Small) Technical Enhancements and Improvements for Rel-19","TEI19",1,"Rel-19",null,"Fri 09/09/22","Sat 12/11/22",0,null,null,null,null,null,null,92,47,null,null,"Mon 15/06/15","Mon 15/06/15"]
[785,1080051,"LI Handling of Protected Services","FS_LIHOPES",1,"Rel-19","S3LI","Thu 05/06/25","Tue 03/03/26",0,"SP-250813",null,"Mats Näslund, NDRE ","mats.naslund@fra.se ","27/6/25: WID:SP-250445->SP-250813; 18/7/25: 33.727 added;",33.726999999999997,108,55,null,null,"Thu 05/06/25","Fri 18/07/25"]
[786,0,"--- RELEASE 18 ---","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[787,0,"Rel-18 Satellite (5GSAT), NTN","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[788,970056,"5G system with satellite backhaul ","5GSATB",1,"Rel-18",null,"Fri 11/06/21","Tue 12/12/23",1,"SP-230111",null,"Xu Hui, CATT ","xuhui@catt.cn ","; 11/6/21: 0%->100;",22.260999999999999,92,47,null,null,"Fri 11/06/21","Fri 10/12/21"]
[789,920035,"   Stage 1 of 5GSATB","5GSATB",2,"Rel-18","S1","Fri 11/06/21","Fri 18/06/21",1,"SP-210528",null,"Xu Hui, CATT ","xuhui@catt.cn ","; 11/6/21: 0%->100;",22.260999999999999,92,47,null,null,"Fri 11/06/21","Fri 10/12/21"]
[790,940060,"   Study on Support of Satellite Backhauling in 5GS ","FS_5GSATB",2,"Rel-18","S2","Mon 20/12/21","Fri 03/03/23",1,"SP-211639",null,"Hucheng Wang, CATT ","wanghucheng@catt.cn ","21/1/22: 23.700-27 added;; 12/3/22: 0%->15; 4/6/22: 15%->60; 12/9/22: 60%->80; 10/12/22: 80%->100","23.700-27",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[791,970018,"   Stage 2 of 5GSATB","5GSATB",2,"Rel-18","S2","Mon 12/09/22","Tue 06/06/23",1,"SP-230111",null,"Hucheng Wang, CATT ","wanghucheng@catt.cn ","; 10/12/22: 0%->30; 15/3/23: FCD:03/03/2023->06/23; 15/3/23: 30%->65; 15/3/23: WID:SP-220808->SP-230111; 8/6/23: 65%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[792,980053,"   CT3 aspects of 5GSATB","5GSATB",2,"Rel-18","C3","Fri 16/12/22","Tue 12/12/23",1,"CP-232131",null,"Hou, Yunjing, CATT","houyunjing@catt.cn","6/6/23: Compl:30%->60%","29.512; 29.514; 29.522; 29.525; 29.513; 29.502; 29.244; 29.564",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[793,980054,"   CT4 aspects of 5GSATB","5GSATB",2,"Rel-18","C4","Fri 16/12/22","Tue 12/12/23",1,"CP-232131",null,"Hou, Yunjing, CATT","houyunjing@catt.cn",null,"29.512; 29.514; 29.522; 29.525; 29.513; 29.502; 29.244; 29.564",97,49,null,null,"Sun 11/09/22","NA"]
[794,1020024,"Charging aspects of Satellite Backhaul in 5GS ","5GSATB_CH",1,"Rel-18","S5","Thu 07/12/23","Sun 03/03/24",1,"SP-240266",null,"Yingying, Liu, CATT ","liuyingying@cictmobile.com ","SP-231707 shows UID 1020023 but this duplicates with SP-231706, so changed here to 1020024.; 15/3/24: 0%->100; 2/4/24: WID:SP-231707->SP-240266","32.240; 32.255; 32.256; 32.254; 32.257; 32.291; 32.298 ",102,52,null,null,"Thu 07/12/23","Tue 02/04/24"]
[795,1020029,"Management aspects of 5G system supporting satellite backhaul ","5GSATB_OAM",1,"Rel-18","S5","Thu 07/12/23","Sun 03/03/24",1,"SP-231708",null,"Wen Qi, China Telecom ","qiw@chinatelecom.cn ","; 14/3/24: 0%->100","28.541; 28.552 ",102,52,null,null,"Wed 03/01/24","Thu 14/03/24"]
[796,920034,"5G system with satellite access to Support Control and/or Video Surveillance ","SCVS",1,"Rel-18","S1","Fri 11/06/21","Wed 08/09/21",1,"SP-210527",null,"Dong Chen, Xiaomi ","chendong7@xiaomi.com ","; 10/12/21: 0%->100",22.260999999999999,92,47,null,null,"Fri 11/06/21","Fri 10/12/21"]
[797,940074,"Study on 5GC enhancement for satellite access Phase 2 ","FS_5GSAT_Ph2",1,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211651",null,"Fine, Jean-Yves, Thales ","jean-yves.fine@thalesgroup.com. ","21/1/22: 23.700-28 added;; 12/3/22: 0%->12; 4/6/22: 12%->50; 12/9/22: 50%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-28",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[798,989998,"Satellite access Phase 2 ","5GSAT_Ph2",1,"Rel-18",null,"Fri 09/12/22","Sun 03/03/24",1,"SP-230109",null,"Rapporteur: Jean-Yves Fine, Thales ","jean-yves.fine@thalesgroup.com ",null,"23.501; 23.502; 23.503; 23.401 ",98,50,null,null,"Fri 09/12/22","NA"]
[799,980014,"   (Stage 2 of 5GSAT_Ph2) 5GC/EPC enhancement for satellite access Phase 2 ","5GSAT_Ph2",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-230109",null,"Rapporteur: Jean-Yves Fine, Thales ","jean-yves.fine@thalesgroup.com ","; 15/3/23: 0%->70; 15/3/23: WID:SP-221344->SP-230109; 8/6/23: 70%->100","23.501; 23.502; 23.503; 23.401 ",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[800,990024,"   CT1 aspects of 5GSAT_Ph2","5GSAT_Ph2",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-240269",null,"Amer Catovic, Qualcomm Incorporated","amerc@qti.qualcomm.com","6/6/23: Compl:0%->10%","24.501.24.301.23.122.27.007.29.122.29.522.31.102",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[801,990056,"   deleted - CT6 aspects of 5GSAT_Ph2","5GSAT_Ph2",2,"Rel-18","C6","Mon 13/03/23","Sun 03/03/24",1,"CP-240269",null,"Amer Catovic, Qualcomm Incorporated","amerc@qti.qualcomm.com","; 15/3/24: 0%->100","24.501.24.301.23.122.27.007.29.122.29.522.31.102",99,50,null,null,"Fri 09/12/22","Fri 15/03/24"]
[802,1010018,"   Charging aspects of 5GSAT","5GSAT_Ph2_CH",2,"Rel-18","S5","Thu 07/09/23","Sun 03/03/24",1,"SP-231152",null,"Yingying, Liu, CATT ","liuyingying@cictmobile.com ","; 8/12/23: 0%->35; 14/3/24: 35%->100","32.255; 32.256; 32.291; 32.298 ",101,51,null,null,"Thu 07/09/23","Thu 14/03/24"]
[803,941006,"NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh",1,"Rel-18",null,"Mon 13/12/21","Fri 12/12/25",0.77,"RP-240779",null,"Thales",null,"compare REL-17 WI NR_NTN_solutions; 5/4/22: WID:RP-213690->RP-220953; 12/7/22: WID:RP-220953->RP-221819; 23/9/22: WID:RP-221819->RP-222654; 9/1/23: WID:RP-222654->RP-223534; 29/3/23: WID:RP-223534->RP-230809; 6/10/23: WID:RP-230809->RP-232669; 2/1/24: ...",null,94,48,null,null,"Thu 06/01/22","Tue 02/04/24"]
[804,941106,"   Core part: NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh-Core",2,"Rel-18","R2","Mon 13/12/21","Thu 06/06/24",1,"RP-232669","RP-240921","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","compare REL-17 WI NR_NTN_solutions; 22/3/22: Stat Rep: ->RP-220383; 20/6/22: FCD:12/12/2023->23/12/2022; Compl:0%->5%; Stat Rep: RP-220383->RP-221170 / 1746; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace....",null,94,48,null,null,"Thu 06/01/22","Thu 13/06/24"]
[805,941206,"   Perf. part: NR NTN (Non-Terrestrial Networks) enhancements","NR_NTN_enh-Perf",2,"Rel-18","R2","Wed 15/12/21","Thu 06/06/24",1,"RP-232669","RP-240921","Nicolas Chuberre, Thales","Nicolas.chuberre@thalesaleniaspace.com","; ; 20/6/22: WG: R4->R2; FCD:12/06/2024->24/06/2022; Stat Rep: RP-220383->RP-221170 / 1746; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->Nicolas.chuberre@thalesaleniaspace.com13/7/22: FCD:24/06/2022->06/20 ...; 9/12/22: FCD:24/06/2023->0...",null,94,48,null,null,"Thu 06/01/22","Thu 13/06/24"]
[806,1050130,"   UE Conformance - NR NTN (non-Terrestrial Networks) enhancements plus CT aspects ","NR_NTN_enh_plus_CT-UEConTest",2,"Rel-18","R5","Mon 09/09/24","Fri 12/12/25",0.15,"RP-251230","RP-251231","Qualcomm ",null,"6/12/24: Compl:0%->6%; Stat Rep: ->RP-242899; ; 6/3/25: FCD:24/07/2025->12/12/2025; Compl:6%->10%; Stat Rep: RP-242899->RP-250397; ; 6/6/25: Compl:10%->15%; Stat Rep: RP-250397->RP-251231; ; 18/7/25: WID:RP-242024->RP-251230",null,105,53,null,null,"Thu 26/09/24","Fri 18/07/25"]
[807,941004,"IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.92,"RP-241351",null,"MediaTek",null,"no Perf. part; 5/4/22: WID:RP-213596->RP-220979; 12/7/22: WID:RP-220979->RP-221806; 9/1/23: WID:RP-221806->RP-223519; 2/1/24: WID:RP-223519->RP-234073; 23/7/24: WID:RP-234073->RP-241351",null,94,48,null,null,"Thu 06/01/22","Tue 23/07/24"]
[808,940104,"   Core part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh-Core",2,"Rel-18","R2","Mon 13/12/21","Tue 12/12/23",1,"RP-241351","RP-233260","Abhishek Roy, MediaTek","abhishek.roy@mediatek.com","no Perf. Part. Slight misalignment in UID numberring scheme (940104 instead of 941104) but it was decided to leave it as such to avoid further potential problems by changing a UID; 20/6/22: FCD:12/12/2023->23/12/2022; Compl:0%->3%; Stat Rep: ->RP-22155...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[809,950284,"   Perf. Part: IoT (Internet of Things) NTN (non-terrestrial network) enhancements","IoT_NTN_enh-Perf",2,"Rel-18","R4","Mon 07/03/22","Thu 06/06/24",1,"RP-241351","RP-241350","Abhishek Roy, MediaTek","abhishek.roy@mediatek.com","20/6/22: WG: R4->R2; FCD:07/06/2024->24/06/2022; Stat Rep: ->RP-221553 / 1759; Rapporteur: MediaTek->Abhishek Roy, MediaTek; Rap eMail: ->abhishek.roy@mediatek.com ...; 17/3/23: FCD:23/12/2022->06/06/2024; Stat Rep: ->RP-230633; Rapporteur: MediaTek...",null,95,48,null,null,"Sat 04/06/22","Thu 13/06/24"]
[810,1030073,"   UE Conformance - IoT (Internet of Things) NTN (non-terrestrial network) enhancements plus CT1 aspects ","IoT_NTN_enh_plus_CT1-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.8,"RP-241949","RP-251376","CMCC ",null,"13/6/24: Compl:0%->16%; WID: RP-240784->RP-240144; Stat Rep: ->RP-241198; ; 23/7/24: WID:RP-240144->RP-241197; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:16%->27%; Stat Rep: RP-241198->RP-241950; ; 26/9/24: WID:RP-241197->RP-241949; 6/12/24: FCD:12/12/2024",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[811,981043,"Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband",1,"Rel-18",null,"Tue 13/12/22","Tue 12/12/23",1,"RP-234043",null,"Apple ",null,"29/3/23: WID:RP-223485->RP-230706; 8/6/23: 38.741 added;; 2/1/24: WID:RP-230706->RP-234043",38.741,98,50,null,null,"Mon 09/01/23","Tue 02/01/24"]
[812,981143,"   Core part: Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband-Core",2,"Rel-18","R4","Tue 13/12/22","Tue 12/12/23",1,"RP-234043","RP-233306","Alexander Sayenko, Apple Inc.","asayenko@apple.com","17/3/23: FCD:12/12/2023->08/09/2023; Compl:0%->10%; Stat Rep: ->RP-230154; Rapporteur: Apple->Alexander Sayenko, Apple Inc.; Rap eMail: ->asayenko@apple.com; 31/3/23: FCD:08/09/2023->12/12/2023; Stat Rep: RP-230154->RP-230707; ...; 6/9/23: Compl:50%->...",null,98,50,null,null,"Mon 09/01/23","Fri 08/12/23"]
[813,981243,"   Perf. part: Introduction of the satellite L-/S-band for NR ","NR_NTN_LSband-Perf",2,"Rel-18","R4","Tue 13/12/22","Tue 12/12/23",1,"RP-234043","RP-233306","Alexander Sayenko, Apple Inc.","asayenko@apple.com","17/3/23: Compl:0%->50%; Stat Rep: ->RP-230154; Rapporteur: Apple->Alexander Sayenko, Apple Inc.; Rap eMail: ->asayenko@apple.com; 31/3/23: Stat Rep: RP-230154->RP-230707; ...; 6/9/23: Compl:90%->95%; WID: RP-230706->RP-231179; Stat Rep: RP-230707->RP-...",null,98,50,null,null,"Mon 09/01/23","Fri 08/12/23"]
[814,970028,"Study on Security Aspects of Satellite Access ","FS_5GSAT_Sec",1,"Rel-18","S3","Mon 12/09/22","Fri 03/03/23",1,"SP-220875",null,"Wei Lu, Xiaomi ","luwei10@xiaomi.com ","23/9/22: 33.700-28 added;; 11/12/22: 0%->15; 17/3/23: 15%->25; 8/6/23: 25%->100; 7/9/23: 100%->","33.700-28",97,49,null,null,"Sun 11/09/22","Thu 07/09/23"]
[815,960026,"Study on Management Aspects of IoT NTN Enhancements ","FS_IoT_NTN",1,"Rel-18","S5","Thu 02/06/22","Tue 06/06/23",1,"SP-220490",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ","12/9/22: 0%->30; 11/12/22: 30%->75; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 75%->95; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100",null,96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[816,960091,"Study on requirements and use cases for network verified UE location for Non-Terrestrial-Networks (NTN) in NR ","FS_NR_NTN_netw_verif_UE_loc",1,"Rel-18","RP","Wed 01/06/22","Wed 15/06/22",1,"RP-221820",null,"Thales ",null,null,null,96,49,null,null,"Tue 12/07/22","NA"]
[817,980028,"Study on charging aspects of Satellite in 5GS ","FS_5GSAT_CH",1,"Rel-18","S5","Wed 01/06/22","Tue 12/12/23",1,"SP-221162",null,"Yingying, Liu, CATT ","liuyingying@cictmobile.com ","17/3/23: 0%->5; 17/3/23: 22.844 added;; 8/6/23: 5%->30; 7/9/23: 0%->80; 8/12/23: 80%->100; 8/12/23: 99%->100",22.844000000000001,98,50,null,null,"Fri 09/12/22","Fri 08/12/23"]
[818,1000060,"30 MHz Channel Bandwidth for NR NTN (non-terrestrial networks) in FR1 (frequency range 1) ","NR_NTN_CBW_30MHz",1,"Rel-18","R4","Wed 07/06/23","Fri 08/09/23",1,"RP-232647",null,"Thales ",null,"6/10/23: WID:RP-231499->RP-232647",null,100,51,null,null,"Thu 29/06/23","Fri 06/10/23"]
[819,1001060,"   Core part: 30 MHz Channel Bandwidth for NR NTN (non-terrestrial networks) in FR1 (frequency range 1) ","NR_NTN_CBW_30MHz-Core",2,"Rel-18","R4","Wed 07/06/23","Fri 08/09/23",1,"RP-232647","RP-232646","Dorin Panaitopol, THALES","dorin.panaitopol@thalesgroup.com","6/9/23: Compl:0%->50%; Stat Rep: ->RP-231568; Rapporteur: Thales->Dorin Panaitopol, THALES; Rap eMail: ->dorin.panaitopol@thalesgroup.com; ; 21/9/23: FCD:12/12/2023->08/09/2023; Compl:50%->100%; Stat Rep: RP-231568->RP-232646; ",null,100,51,null,null,"Thu 29/06/23","Thu 21/09/23"]
[820,991041,"Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband",1,"Rel-18","R4","Fri 03/03/23","Fri 06/06/25",1,"RP-240741",null,"Inmarsat ",null,"7/9/23: WID:RP-230790->RP-231487; 6/10/23: WID:RP-231487->RP-232686; 2/1/24: WID:RP-232686->RP-233856; 2/4/24: WID:RP-233856->RP-240741",null,99,50,null,null,"Wed 29/03/23","Tue 02/04/24"]
[821,991141,"   Core part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband-Core",2,"Rel-18","R4","Fri 03/03/23","Sun 03/03/24",1,"RP-240741","RP-232609","Luca Lodigiani, Inmarsat","Luca.lodigiani@inmarsat.com","; 7/6/23: Compl:0%->11%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:11%->30%; WID: RP-230790->RP-231487; Stat Rep: ->RP-232459; Rapporteur: Inmarsat->Luca Lodigiani, Inmarsat; Rap eMail: ->Luca.lodigiani@inmarsat.com; ; 21/9/23: FCD:22/09/2023->12/12/2...",null,99,50,null,null,"Wed 29/03/23","Tue 02/04/24"]
[822,991241,"   Perf. part: Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband-Perf",2,"Rel-18","R4","Fri 03/03/23","Thu 06/06/24",1,"RP-240741","RP-232609","Luca Lodigiani, Inmarsat","Luca.lodigiani@inmarsat.com","6/9/23: WID: RP-230790->RP-231487; Stat Rep: ->RP-232459; Rapporteur: Inmarsat->Luca Lodigiani, Inmarsat; Rap eMail: ->Luca.lodigiani@inmarsat.com; ; 21/9/23: FCD:12/12/2023->06/06/2024; Stat Rep: RP-232459->RP-232609; ; 8/12/23: FCD:06/06/2024->12/12...",null,99,50,null,null,"Wed 29/03/23","Tue 23/07/24"]
[823,1040110,"   UE Conformance - Introduction of the Extended L-band (UL 1668-1675MHz, DL 1518-1525MHz) for IoT NTN ","IoT_NTN_extLband-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 06/06/25",1,"RP-241355","RP-251292","Mediatek ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->5%; Stat Rep: ->RP-242049; ; 6/12/24: Compl:5%->95%; Stat Rep: RP-242049->RP-242993; ; 6/3/25: FCD:14/02/2025->06/06/2025; Stat Rep: RP-242993->RP-250476; ; 6/6/25: Compl:95%->100%; Stat Rep: RP-250476->RP-25",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[824,991043,"Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band",1,"Rel-18","R4","Fri 03/03/23","Mon 03/03/25",1,"RP-241353",null,"MediaTek ",null,"2/1/24: WID:RP-230792->RP-234060; 2/4/24: WID:RP-234060->RP-240451; 23/7/24: WID:RP-240451->RP-241353",null,99,50,null,null,"Wed 29/03/23","Tue 23/07/24"]
[825,991143,"   Core part: Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band-Core",2,"Rel-18","R4","Fri 03/03/23","Tue 12/12/23",1,"RP-241353","RP-241352","Huanren FU, MediaTek Inc.","huanren.fu@mediatek.com","; 7/6/23: Compl:0%->30%; 6/9/23: Compl:30%->60%; WID: RP-230792->RP-231479; Stat Rep: ->RP-232313; Rapporteur: MediaTek->Aijun CAO, MediaTek Inc.; Rap eMail: ->aijun.cao@mediatek.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-232313->RP-233258; ; 4/1/2...",36.764000000000003,99,50,null,null,"Wed 29/03/23","Thu 13/06/24"]
[826,991243,"   Perf. part: Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band-Perf",2,"Rel-18","R4","Mon 06/03/23","Thu 06/06/24",1,"RP-241353","RP-241352","Huanren FU, MediaTek Inc.","huanren.fu@mediatek.com","; 7/6/23: CD:06/06/2024->06/06/2023; 6/9/23: FCD:06/06/2023->06/06/2024; WID: RP-230792->RP-231479; Stat Rep: ->RP-232313; Rapporteur: MediaTek->Aijun CAO, MediaTek Inc.; Rap eMail: ->aijun.cao@mediatek.com; ; 8/12/23: Stat Rep: RP-232313->RP-233258; ...",null,99,50,null,null,"Wed 29/03/23","Thu 13/06/24"]
[827,1040109,"   UE Conformance - Introduction of FDD LTE band (L+S band) for IoT NTN operation ","IoT_NTN_FDD_LS_band-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Thu 12/12/24",1,"RP-242992","RP-242991","Mediatek ",null,"4/9/24: FCD:03/03/2025->25/03/2025; Compl:0%->95%; Stat Rep: ->RP-242048; ; 6/12/24: FCD:03/03/2025->12/12/2024; Compl:95%->99%; Stat Rep: RP-242048->RP-242991; ; 24/1/25: WID:RP-241354->RP-242992; 24/1/25: 99%->100",null,104,53,null,null,"Tue 23/07/24","Fri 24/01/25"]
[828,950074,"NB-IoT/eMTC Core and Perf requirements for NTN","LTE_NBIOT_eMTC_NTN_req",1,"Rel-18",null,"Tue 15/03/22","Sun 03/03/24",1,"RP-223437",null,"MediaTek ",null,"TS 36.10x, TS 36.10y; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 12/7/22: WID:RP-220938->RP-221556; 9/1/23: WID:RP-221556->RP-223437; 23/7/24: 99%->100",null,95,48,null,null,"Tue 05/04/22","Tue 23/07/24"]
[829,950174,"   Core part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIoT_eMTC_NTN_req-Core",2,"Rel-18","R4","Tue 15/03/22","Thu 01/12/22",1,"RP-221556","RP-223231","Tim Frost, MediaTek Inc.","Tim.frost@mediatek.com","TS 36.10x, TS 36.10y; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 20/6/22: FCD:15/12/2022->22/12/2022; Stat Rep: ->RP-221555; Rapporteur: MediaTek->Tim Frost, MediaTek Inc.; Rap eMail: ->tim dot frost at mediatek dot com13/7/22: 36.1...;...","36.102; 36.105; 36.108",95,48,null,null,"Tue 05/04/22","Mon 09/01/23"]
[830,950274,"   Perf. part: NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIoT_eMTC_NTN_req-Perf",2,"Rel-18","R4","Tue 15/03/22","Tue 06/06/23",1,"RP-223437","RP-230634","Hsuanli Lin, MediaTek Inc.","hsuanli.lin@mediatek.com","TS 36.1XX; RAN4 requirements for REL-17 WI LTE_NBIOT_eMTC_NTN-Core ; 6/6/22: CD:15/06/2023->23/06/2022; 6/6/22: Stat Rep: ->RP-221555; 20/6/22: Rapporteur: MediaTek->Tim Frost, MediaTek Inc.; Rap eMail: ->tim dot frost at mediatek dot com13/7/22: ...;...",36.180999999999997,95,48,null,null,"Tue 05/04/22","Wed 07/06/23"]
[831,981034,"   UE Conformance - NB-IoT (Narrowband IoT)/eMTC (enhanced Machine Type Communication) core & performance requirements for Non-Terrestrial Networks (NTN) ","LTE_NBIOT_eMTC_NTN_req-UEConTest",2,"Rel-18","R5","Tue 13/12/22","Sun 03/03/24",1,"RP-240147","RP-240146","Dan SONG, Danbo Fu (MediaTek), CMCC, MediaTek Inc.","songdan@chinamobile.com, Danbo.Fu@mediatek.com","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230284; Rapporteur: CMCC->Dan SONG, Danbo Fu (MediaTek), CMCC, MediaTek Inc.; Rap eMail: ->songdan@chinamobile.com, Danbo.Fu@mediatek.com; 17/3/23: 36.521-4 added;; 29/3/23: WID:RP-223064->RP-230285; ...; 21/9/23...","36.521-4",98,50,null,null,"Mon 09/01/23","Tue 02/04/24"]
[832,0,"Rel-18 Internet of Things (IoT), MTC, Energy, complexity saving","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[833,930029,"Personal IoT and Residential networks","PIRates",1,"Rel-18",null,"Thu 25/06/20","Sun 03/03/24",1,"SP-211505",null,"Xiaowan Ke, vivo Mobile Communications Ltd","xiaowan.ke@vivo.com ","; 10/12/21: WID:SP-211055->SP-211505 (chg rapporteur)",22.260999999999999,93,47,null,null,"Fri 10/09/21","Fri 10/12/21"]
[834,880041,"   Study on Personal IoT Networks","FS_PIN",2,"Rel-18","S1","Thu 25/06/20","Fri 11/06/21",1,"SP-200592",null,"Adrian Buckley, vivo Mobile Communications ","adrian.buckley@vivo.com","28/7/20: 22.859 added;; 12/9/20: 0%->15; 5/12/20: 15%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->90; 13/9/21: 90%->100",22.859000000000002,88,45,null,null,"Thu 25/06/20","Mon 13/09/21"]
[835,880040,"   Study on Enhancements for Residential 5G","FS_Resident",2,"Rel-18","S1","Thu 25/06/20","Fri 11/06/21",1,"SP-200576",null,"Toon Norp, KPN","toon.norp@tno.nl","28/7/20: 22.858 added;; 12/9/20: 0%->30; 5/12/20: 30%->50; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->85; 13/9/21: 85%->100",22.858000000000001,88,45,null,null,"Thu 25/06/20","Mon 13/09/21"]
[836,930022,"   Stage 1 of PIRates","PIRates",2,"Rel-18","S1","Fri 10/09/21","Fri 10/12/21",1,"SP-211505",null,"Xiaowan Ke, vivo Mobile Communications Ltd","xiaowan.ke@vivo.com ","; 13/9/21: 0%->85; 10/12/21: 85%->100; 10/12/21: WID:SP-211055->SP-211505",22.260999999999999,93,47,null,null,"Fri 10/09/21","Fri 10/12/21"]
[837,940065,"   Study on Personal IoT Networks","FS_PIN",2,"Rel-18","S2","Mon 20/12/21","Fri 03/03/23",1,"SP-230089",null,"Zhenhua Xie, vivo Mobile Communications Ltd ","zhenhua.xie@vivo.com ","21/1/22: 23.700-88 added;; 12/3/22: 0%->20; 4/6/22: 20%->60; 12/9/22: 60%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->95; 15/3/23: FCD:12/12/2022->03/23; 15/3/23: 95%->100; 15/3/23: WID:SP-211643->SP-230089","23.700-88",94,48,null,null,"Sun 19/12/21","Wed 15/03/23"]
[838,980011,"   (Stage 2 of) Personal IoT Networks ","PIN",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-221343",null,"Zhenhua Xie, vivo ","zhenhua.xie@vivo.com ","10/1/23: FCD clarified to be June (and not March) by e-mail; 15/3/23: 0%->60; 8/6/23: 60%->100","23.501; 23.502; 23.503 ",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[839,990018,"   CT1 aspects of PIN","PIN",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-233216",null,"Hui Wang, vivo","wanghui.wh@vivo.com","6/6/23: Compl:0%->50%","24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[840,990058,"   CT3 aspects of PIN","PIN",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-233216",null,"Hui Wang, vivo","wanghui.wh@vivo.com","9/6/23: 0%->20","24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"Fri 09/12/22","Fri 09/06/23"]
[841,990059,"   CT4 aspects of PIN","PIN",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-233216",null,"Hui Wang, vivo","wanghui.wh@vivo.com",null,"24.501.24.526.29.512.29.513.29.519.29.522.29.525.23.008.29.502.29.503.29.504.29.505.29.244",99,50,null,null,"Fri 09/12/22","NA"]
[842,990106,"Application layer support for Personal IoT Network ","PINAPP",1,"Rel-18",null,"Mon 13/12/21","Sun 03/03/24",1,"SP-221236",null,"Huazhang Lv, vivo Mobile Communications Ltd, ","huazhang.lv@vivo.com ",null,null,99,50,null,null,"Fri 09/12/22","NA"]
[843,940021,"   Study on Application layer support for Personal IoT Networks","FS_PINAPP",2,"Rel-18","S6","Mon 13/12/21","Mon 12/12/22",1,"SP-220095",null,"Huazhang Lv, vivo Mobile Communications Ltd ","huazhang.lv@vivo.com ","7/1/22: 23.700-78 added;; 12/3/22: WID:SP-211515->SP-220095; 12/3/22: 0%->15; 4/6/22: 15%->40; 12/9/22: 40%->60; 12/9/22: FCD:12/09/2022->12/20; 11/12/22: 60%->100; 31/3/23: 24.583 added;","23.700-78; 24.583",94,48,null,null,"Mon 13/12/21","Fri 31/03/23"]
[844,980052,"   Stage 2 of PINAPP","PINAPP",2,"Rel-18","S6","Fri 09/12/22","Tue 06/06/23",1,"SP-221236",null,"Huazhang Lv, vivo Mobile Communications Ltd, ","huazhang.lv@vivo.com ","17/3/23: FCD:03/03/2023->/23; 17/3/23: 0%->50; 17/3/23: 23.542 added;; 8/6/23: 50%->100",23.542000000000002,98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[845,990017,"   CT1 aspects of PINAPP","PINAPP",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-233218",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com","6/6/23: Compl:0%->40%",27.007000000000001,99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[846,990061,"   CT3 aspects of PINAPP","PINAPP",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-233218",null,"Yizhong ZHANG, vivo","yizhong.zhang@vivo.com","31/3/23: 29.583 added;; 9/6/23: 5%->10","27.007; 29.583",99,50,null,null,"Fri 09/12/22","Fri 09/06/23"]
[847,960027,"Study on Personal IoT Networks Security Aspects ","FS_PIN_Sec",1,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220525",null,"Zhenhua Xie, vivo Mobile Communications Co. Ltd ","zhuenhua.xie@vivo.com ","13/7/22: 33.882 added;; 12/9/22: 0%->20; 11/12/22: 20%->50; 17/3/23: 50%->60; 8/6/23: 60%->100",33.881999999999998,96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[848,920016,"Study on Application Capability Exposure for IoT Platforms ","FS_ACE_IOT",1,"Rel-18","S6","Fri 11/06/21","Thu 09/06/22",1,"SP-220093",null,"Mladin, Catalina; Convida Wireless ","Mladin.Catalina@convidawireless.com ","2/7/21: 23.700-97 added;; 13/9/21: 0%->15; 13/12/21: 15%->40; 12/3/22: 40%->55; 12/3/22: FCD:11/03/2022->6/22; 12/3/22: WID:SP-210478->SP-220093; 4/6/22: 55%->60; 12/9/22: 60%->75; 11/12/22: 75%->75; 17/3/23: 75%->95; 8/6/23: 95%->100","23.700-97",92,47,null,null,"Fri 11/06/21","Thu 08/06/23"]
[849,0,"See also IoT_NTN_en under Satellite and LPHP under Verticals","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[850,0,"See also \" NB-IoT/eMTC requirements for NTN\" (UID 950074) under Satellite ","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[851,940085,"Study on low-power wake-up signal and receiver for NR","FS_NR_LPWUS",1,"Rel-18","R1","Mon 13/12/21","Tue 12/12/23",1,"RP-232672","RP-233067","Xueming Pan, vivo","panxueming@vivo.com","21/1/22: 38.869 added;; 22/3/22: Stat Rep: ->RP-2205966/6/22: CD:12/12/2023->23/12/20226/6/22: Stat Rep: RP-220596->RP-221270; 20/6/22: Rapporteur: vivo->Xiaodong Shen, vivo Communication Technology; Rap eMail: ->shenxiaodong@vivo.com12/7/22: WID:R...;...",38.869,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[852,970080,"Enhanced support of reduced capability NR devices ","NR_redcap_enh",1,"Rel-18",null,"Sun 12/12/21","Thu 12/12/24",0.88,"RP-233637",null,"Ericsson ",null,"9/1/23: WID:RP-222675->RP-223544; 6/10/23: WID:RP-223544->RP-232671; 2/1/24: WID:RP-232671->RP-233637",null,97,49,null,null,"Fri 23/09/22","Tue 02/01/24"]
[853,970180,"   Core part: Enhanced support of reduced capability NR devices ","NR_redcap_enh-Core",2,"Rel-18","R1","Thu 08/09/22","Tue 12/12/23",1,"RP-233637","RP-233636","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-222827; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-222827->RP-230111; ;.....",null,97,49,null,null,"Fri 23/09/22","Fri 08/12/23"]
[854,970280,"   Perf. part: Enhanced support of reduced capability NR devices ","NR_redcap_enh-Perf",2,"Rel-18","R1","Tue 13/09/22","Thu 06/06/24",1,"RP-233637","RP-241124","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","9/12/22: WG: R4->R1; FCD:10/06/2023->01/06/2024; Stat Rep: ->RP-222827; Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; 17/3/23: Stat Rep: RP-222827->RP-230111; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Stat Rep:...",null,97,49,null,null,"Fri 23/09/22","Tue 23/07/24"]
[855,940086,"   Study on further NR RedCap (reduced capability) UE complexity reduction","FS_NR_redcap_enh",2,"Rel-18","R1","Sun 12/12/21","Fri 09/09/22",1,"RP-221161","RP-221160","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","TR 38.8xx; compare REL-17 SI FS_NR_redcap and REL-17 WI NR_redcap; 21/1/22: 38.865 added;; 22/3/22: Stat Rep: ->RP-220470 ; 6/6 ; 20/6/22: Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com12/7/22: WID:RP-213661-...; 23",38.865000000000002,94,48,null,null,"Thu 06/01/22","Fri 23/09/22"]
[856,1030062,"   UE Conformance - Enhanced support of reduced capability NR devices plus CT1 aspects ","NR_redcap_enh_plus_CT1-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.7,"RP-242487","RP-251504","China Unicom ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-240919; ; 23/7/24: WID:RP-240054->RP-240920; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->28%; Stat Rep: RP-240919->RP-241883; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:28%->53%; Stat Rep: RP-241883->RP-242486; ; ",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[857,940056,"Study on RedCap Phase 2","FS_REDCAP_Ph2",1,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220074",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ","21/01/22: name corrected; 21/1/22: 23.700-68 added;; 12/3/22: 0%->30; 12/3/22: WID:SP-211635->SP-220074; 4/6/22: 30%->70; 12/9/22: 70%->99; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 99%->100","23.700-68",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[858,980113,"NR RedCap UE with long eDRX for RRC_INACTIVE State ","NR_REDCAP_Ph2",1,"Rel-18",null,"Thu 15/12/22","Wed 13/12/23",1,"SP-220803",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ",null,"23.501; 23.502 ",97,49,null,null,"Sun 11/09/22","NA"]
[859,970013,"   (Stage 2 of) NR RedCap UE with long eDRX for RRC_INACTIVE State ","NR_REDCAP_Ph2",2,"Rel-18","S2","Mon 12/09/22","Fri 03/03/23",1,"SP-230171",null,"Qian, Chen, Ericsson ","qian.xb.chen@ericsson.com ","; 10/12/22: 0%->60; 15/3/23: WID:SP-220803->SP-230171; 15/3/23: 60%->95; 8/6/23: 95%->100; 4/1/24: 28.876 added;","23.501; 23.502 ; 28.876",97,49,null,null,"Sat 10/12/22","Thu 04/01/24"]
[860,980068,"   CT4 aspects of NR_REDCAP_Ph2","NR_REDCAP_Ph2",2,"Rel-18","C4","Thu 15/12/22","Tue 12/12/23",1,"CP-223021",null,"Frank Yong Yang, Ericsson","frank.yong.yang@ericsson.com","6/6/23: Compl:60%->90%","24.008; 29.502; 29.518",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[861,980069,"   CT1 aspects of NR_REDCAP_Ph2","NR_REDCAP_Ph2",2,"Rel-18","C1","Fri 16/12/22","Tue 12/12/23",1,"CP-223021",null,"Frank Yong Yang, Ericsson","frank.yong.yang@ericsson.com",null,"24.008; 29.502; 29.518",97,49,null,null,"Sun 11/09/22","NA"]
[862,991039,"Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18","NR_FDD_bands_R18_redcap",1,"Rel-18",null,"Mon 06/03/23","Mon 03/03/25",1,"RP-232894",null,"Ericsson",null,"2/1/24: WID:RP-230743->RP-232894",null,99,50,null,null,"Fri 07/04/23","Tue 02/01/24"]
[863,991139,"   Core part: Adding new NR FDD bands for RedCap (Reduced Capability) in Rel-18","NR_FDD_bands_R18_redcap-Core",2,"Rel-18","R4","Mon 06/03/23","Tue 12/12/23",1,"RP-232894","RP-232xyz","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","; 7/6/23: Compl:0%->40%; 6/9/23: Compl:40%->50%; WID: RP-230743->RP-231049; Stat Rep: ->RP-231881; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 8/12/23: Compl:50%->100%; Stat Rep: RP-231881->RP-232xyz; ",null,99,50,null,null,"Fri 07/04/23","Fri 08/12/23"]
[864,1060076,"   UE Conformance - New NR FDD bands for RedCap (Reduced Capability) in Rel-18 ","NR_FDD_bands_R18_redcap-UEConTest",2,"Rel-18","R5","Wed 28/08/24","Mon 03/03/25",1,"RP-250289","RP-250288","Ericsson ",null,"6/3/25: FCD:09/09/2025->03/03/2025; Compl:0%->100%; Stat Rep: ->RP-250288; ; 3/4/25: WID:RP-242648->RP-250289",null,106,54,null,null,"Fri 24/01/25","Thu 03/04/25"]
[865,981037,"Network energy savings for NR ","Netw_Energy_NR",1,"Rel-18",null,"Mon 13/12/21","Fri 12/12/25",0.96,"RP-234009",null,"Huawei ",null,"2/1/24: WID:RP-223540->RP-234009",null,98,50,null,null,"Mon 09/01/23","Tue 02/01/24"]
[866,981137,"   Core part: Network energy savings for NR ","Netw_Energy_NR-Core",2,"Rel-18","R1","Tue 13/12/22","Tue 12/12/23",1,"RP-234009","RP-233655","Yi Wang, Huawei","wangyi6@huawei.com","17/3/23: FCD:12/12/2023->08/09/2023; Compl:0%->15%; Stat Rep: ->RP-230565; Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com; 31/3/23: FCD:08/09/2023->12/12/2023; Stat Rep: RP-230565->RP-230714; ;...; 6/9/23: Compl:55%->75%; Stat Re...",null,98,50,null,null,"Mon 09/01/23","Fri 08/12/23"]
[867,981237,"   Perf. part: Network energy savings for NR ","Netw_Energy_NR-Perf",2,"Rel-18","R4","Wed 14/12/22","Thu 06/06/24",1,"RP-234009","RP-241239","Yi Wang, Huawei","wangyi6@huawei.com","17/3/23: Stat Rep: ->RP-230565; Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com; 31/3/23: FCD:06/06/2024->06/06/2023; Stat Rep: RP-230565->RP-230714; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Stat Rep: RP-230714->RP-231926; ; 8/12/...",null,98,50,null,null,"Mon 09/01/23","Tue 23/07/24"]
[868,1030067,"   UE Conformance - Network energy savings for NR ","Netw_Energy_NR-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.9,"RP-240291","RP-251490","Huawei ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241378; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->24%; Stat Rep: RP-241378->RP-242075; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:24%->54%; Stat Rep: RP-242075->RP-243092; ; 6/3/25: FCD:28/05/2025->12/12/2025;",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[869,940080,"   Study on network energy savings for NR","FS_Netw_Energy_NR",2,"Rel-18","R1","Mon 13/12/21","Thu 01/12/22",1,"RP-230566","RP-223002","Yi Wang, Huawei","wangyi6@huawei.com","21/1/22: 38.864 added;; 22/3/22: Stat Rep: ->RP-220296; 5/4/22: WID:RP-213554->RP-220297 ; 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: Huawei->Yi Wang, Huawei; Rap eMail: ->wangyi6@huawei.com12/7/22: WID:RP-220297->RP-221443; 9/12/22: FCD:22/12/2022->...",38.863999999999997,94,48,null,null,"Thu 06/01/22","Wed 29/03/23"]
[870,0,"Rel-18 Uncrewed Aerial Vehicles (UAV), UAS, UAM","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[871,990107,"Further Architecture Enhancement for UAV and UAM","UAS_Ph2",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-221323",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","10/1/23: FCD clarified to be June (and not March) by e-mail ",23.256,99,50,null,null,"Fri 09/12/22","NA"]
[872,940051,"   Study on Phase 2 of UAS, UAV and UAM ","FS_UAS_Ph2",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211632",null,"Stefano Faccin ","sfaccin@qti.qualcomm.com ","; 21/1/22: 23.700-58 added;; 12/3/22: 0%->20; 4/6/22: 20%->50; 4/6/22: FCD:10/06/2022->09/22; 12/9/22: 50%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->98; 15/3/23: 98%->100","23.256 ; 23.700-58",94,48,null,null,"Sun 19/12/21","Wed 15/03/23"]
[873,980012,"   (Stage 2 of UAS Ph2) Further Architecture Enhancement for UAV and UAM","UAS_Ph2",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-230091",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","10/1/23: FCD clarified to be June (and not March) by e-mail ; 15/3/23: 0%->85; 15/3/23: WID:SP-221323->SP-230091; 8/6/23: 85%->100",23.256,98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[874,960034,"   Study on Security of Phase 2 for UAS, UAV and UAM ","FS_UAS_Ph2_SEC",2,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220532",null,"Escott, Adrian, Qualcomm Incorporated, ","aescott@qti.qualcomm.com ","13/7/22: 33.891 added;; 11/12/22: 0%->65; 17/3/23: 65%->100",33.890999999999998,96,49,null,null,"Thu 02/06/22","Fri 17/03/23"]
[875,990036,"   Security of UAV and UAM Phase 2 ","UAS_Ph2",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230149",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 8/6/23: 0%->60; 7/9/23: 60%->100",33.256,99,50,null,null,"Thu 16/03/23","Thu 07/09/23"]
[876,990012,"   CT1 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","31/3/23: 24.578 added;; 31/3/23: 24.577 added;6/6/23: Compl:0%->50%","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102; 24.578; 24.577",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[877,990063,"   CT3 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","9/6/23: 0%->30","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"Fri 09/12/22","Fri 09/06/23"]
[878,990064,"   CT4 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","6/6/23: Compl:0%->10%","24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[879,990105,"   CT6 aspects of UAS Ph2","UAS_Ph2",2,"Rel-18","C6","Mon 13/03/23","Sun 03/03/24",1,"CP-230330",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com",null,"24.501.23.122.24.587.27.007.29.255.29.513.29.519.29.522.29.525.29.256.23.008.29.503.29.505.29.510.29.518.29.571.31.102",99,50,null,null,"Fri 09/12/22","NA"]
[880,930012,"Study on enhanced architecture for UAS Applications ","FS_eUASAPP",1,"Rel-18","S6","Mon 13/09/21","Mon 12/12/22",1,"SP-220465",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ","13/12/21: 0%->10; 13/12/21: WID:SP-210954->SP-211511; 13/12/21: FCD:Fri 10/06/->09/22; 12/3/22: 10%->30; 12/3/22: WID:SP-211511->SP-22009; 22/3/22: 23.700-55 added;; 4/6/22: 30%->50; 4/6/22: WID:SP-22009->SP-220465; 12/9/22: 50%->80; 12/9/22: FCD:12/09...","23.700-55",93,47,null,null,"Mon 13/09/21","Sun 11/12/22"]
[881,980126,"Architecture for UAS Applications, Phase 2 ","UASAPP_Ph2",1,"Rel-18",null,"Fri 09/09/22","Tue 12/12/23",1,"SP-220915",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ",null,23.254999999999999,97,49,null,null,"Sun 11/09/22","NA"]
[882,970038,"   Stage 2 of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","S6","Fri 09/09/22","Tue 06/06/23",1,"SP-221228",null,"Monrad, Atle, InterDigital ","atle.monrad@interdigital.com ","; 11/12/22: 0%->25; 9/1/23: WID:SP-220915->SP-221228; 17/3/23: 25%->65; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 65%->100",23.254999999999999,97,49,null,null,"Sun 11/12/22","Thu 08/06/23"]
[883,980055,"   CT1 aspects of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","C1","Fri 16/12/22","Tue 12/12/23",1,"CP-240273",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com ","6/6/23: Compl:5%->60%","27.007; 24.257; 29.257",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[884,980056,"   CT3 aspects of UASAPP_Ph2","UASAPP_Ph2",2,"Rel-18","C3","Fri 16/12/22","Tue 12/12/23",1,"CP-240273",null,"Taimoor Abbas, InterDigital","taimoor.abbas@interdigital.com ","; 9/6/23: 0%->40","27.007; 24.257; 29.257",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[885,941005,"NR support for UAV (Uncrewed Aerial Vehicles)","NR_UAV",1,"Rel-18","R2","Mon 13/12/21","Tue 03/03/26",0.7,"RP-233386",null,"Nokia",null,"no Perf. part; no RAN1 spec affected so far; 9/1/23: WID:RP-213600->RP-223545; 29/3/23: WID:RP-223545->RP-230782; 2/1/24: WID:RP-230782->RP-233386",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[886,941105,"   Core part: NR support for UAV (Uncrewed Aerial Vehicles)","NR_UAV-Core",2,"Rel-18","R2","Mon 13/12/21","Tue 12/12/23",1,"RP-233386","RP-233385","Jedrzej Stanczak, Nokia, Nokia Shanghai Bell","jedrzej.stanczak@nokia.com","no Perf. part; no RAN1 spec affected so far; 20/6/22: FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221498; Rapporteur: Nokia->Jedrzej Stanczak, Nokia, Nokia Shanghai Bell; Rap eMail: ->jedrzej.stanczak@nokia.com13/7/22: FCD:23/12/2022->12/20...; 17/3/23:...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[887,1070060,"   UE Conformance - NR Support for UAV (Uncrewed Aerial Vehicles) plus CT1 aspects ","NR_UAV_plus_CT1-UEConTest",2,"Rel-18","R5","Mon 03/03/25","Tue 03/03/26",0.28000000000000003,"RP-250062","RP-251507","China Unicom ",null,"6/6/25: Compl:0%->28%; Stat Rep: ->RP-251507; ",null,107,54,null,null,"Wed 26/03/25","Fri 06/06/25"]
[888,991035,"Enhanced LTE Support for UAV (Uncrewed Aerial Vehicles) ","LTE_UAV_enh",1,"Rel-18","R2","Fri 03/03/23","Tue 12/12/23",1,"RP-233389",null,"Nokia ",null,"2/1/24: WID:RP-230783->RP-233389",null,99,50,null,null,"Wed 29/03/23","Tue 02/01/24"]
[889,991135,"   Core part: Enhanced LTE Support for UAV (Uncrewed Aerial Vehicles) ","LTE_UAV_enh-Core",2,"Rel-18","R2","Fri 03/03/23","Tue 12/12/23",1,"RP-233389","RP-233388","Jedrzej Stanczak, Nokia, Nokia Shanghai Bell","jedrzej.stanczak@nokia.com","; 7/6/23: Compl:0%->60%; 6/9/23: Compl:60%->80%; Stat Rep: ->RP-231865; Rapporteur: Nokia->Jedrzej Stanczak, Nokia, Nokia Shanghai Bell; Rap eMail: ->jedrzej.stanczak@nokia.com; ; 8/12/23: Compl:80%->100%; Stat Rep: RP-231865->RP-233388; ",null,99,50,null,null,"Wed 29/03/23","Fri 08/12/23"]
[890,0,"Rel-18 Sidelink, Proximity, Location and Positioning","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[891,910040,"Ranging-based Service and sidelink positioning ","Ranging",1,"Rel-18",null,"Thu 25/06/20","Mon 03/03/25",1,"SP-210212",null,"Xiaowei jiang, Xiaomi ","jiangxiaowei@xiaomi.com ",null,22.260999999999999,91,46,null,null,"Thu 18/03/21","NA"]
[892,880039,"   Study on Ranging","FS_Ranging",2,"Rel-18","S1","Thu 25/06/20","Fri 11/06/21",1,"SP-200575",null,"Xiaowei jiang ","jiangxiaowei@xiaomi.com","28/7/20: 22.855 added;; 12/9/20: 0%->40; 5/12/20: 40%->80; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 80%->85; 11/6/21: 85%->100",22.855,88,45,null,null,"Thu 25/06/20","Fri 11/06/21"]
[893,910034,"   Stage 1 for Ranging","Ranging",2,"Rel-18","S1","Thu 18/03/21","Fri 11/06/21",1,"SP-210212",null,"Xiaowei jiang, Xiaomi ","jiangxiaowei@xiaomi.com ","; 11/6/21: 0%->100",22.260999999999999,91,46,null,null,"Thu 18/03/21","Fri 11/06/21"]
[894,940069,"   Study on Ranging based services and sidelink positioning ","FS_Ranging_SL",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211647",null,"Shen, Sherry (Yang), Xiaomi, ","shenyang6@xiaomi.com ","21/1/22: 23.700-86 added;; 12/3/22: 0%->15; 4/6/22: 15%->60; 12/9/22: 60%->70; 10/12/22: 70%->85; 15/3/23: 85%->100","23.700-86",94,48,null,null,"Sun 19/12/21","Wed 15/03/23"]
[895,980015,"   Stage 2 of Ranging_SL","Ranging_SL",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-230106",null,"Shen, Sherry (Yang), Xiaomi ","shenyang6@xiaomi.com ","\"Architecture Enhancement to support Ranging based services and Sidelink Positioning\" ; 15/3/23: 0%->50; 15/3/23: WID:SP-221325->SP-230106; 17/3/23: 23.586 added;; 8/6/23: 50%->100","23.304; 23.287; 23.273; 23.502; 23.503 ; 23.586",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[896,960036,"   Study on Security Aspects of Ranging Based Services and Sidelink Positioning ","FS_Ranging_SL_Sec",2,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220534",null,"Wei Lu, Xiaomi, ","luwei10@xiaomi.com ","13/7/22: 33.893 added;; 12/9/22: 0%->20; 11/12/22: 20%->40; 17/3/23: 40%->70; 8/6/23: 70%->100",33.893000000000001,96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[897,990046,"   Security Aspects of Ranging_SL","Ranging_SL_Sec",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230769",null,"Lu, Wei, Xiaomi ","luwei10@xiaomi.com ","31/3/23: 33.533 added;; 8/6/23: 0%->40; 30/6/23: WID:SP-230159->SP-230769; 7/9/23: 40%->100",33.533000000000001,99,50,null,null,"Thu 16/03/23","Thu 07/09/23"]
[898,990014,"   CT1 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-240298",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com","; 31/3/23: 24.514 added;6/6/23: Compl:0%->15%","24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572; 24.514",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[899,990066,"   CT3 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-240298",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com","; 16/7/24: 99%->100","24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572",99,50,null,null,"Fri 09/12/22","Tue 16/07/24"]
[900,990067,"   CT4 aspects of Ranging_SL","Ranging_SL",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-240298",null,"Tingfang Tang, Xiaomi","tangtingfang@xiaomi.com","6/6/23: Compl:0%->30%; 4/1/24: 29.586 added;","24.501.24.554.24.555.24.571.24.587.24.588.29.122.29.522.29.525.29.519.29.503.29.504.29.505.29.510.29.515.29.571.29.572; 29.586",99,50,null,null,"Fri 09/12/22","Thu 04/01/24"]
[901,1040013,"   Charging Aspects of Ranging and Sidelink Positioning","Ranging_SL_CH",2,"Rel-18","S5","Mon 06/05/24","Mon 03/03/25",1,"SP-241002",null,"Zhiwei Mo, China Telecom, ","mozw@chinatelecom.cn ","; 4/9/24: 20%->50; 5/12/24: 50%->100","32.240; 32.290; 32.271; 32.291; 32.298 ",104,53,null,null,"Thu 13/06/24","Thu 05/12/24"]
[902,1000009,"   Charging Aspects of Ranging and Sidelink Positioning ","FS_Ranging_SL_CH",2,"Rel-18","S5","Thu 08/06/23","Sun 03/03/24",1,"SP-230622",null,"Zhiwei Mo, China Telecom, ","mozw<at>chinatelecom<dot>cn ","30/6/23: 28.845 added;; 7/9/23: 0%->15; 8/12/23: 15%->70; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 70%->100",28.844999999999999,100,51,null,null,"Thu 08/06/23","Thu 14/03/24"]
[903,980111,"5GC LoCation Services - Phase 3 ","5G_eLCS_Ph3",1,"Rel-18",null,"Fri 30/09/22","Sun 03/03/24",1,"SP-220811",null,"Ming Ai, CATT ","aiming@catt.cn ",null,23.273,97,49,null,null,"Sun 11/09/22","NA"]
[904,940058,"   Study on Enhancement to the 5GC LoCation Services-Phase 3 ","FS_eLCS_Ph3",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220069",null,"Ming Ai, CATT ","aiming@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-71 added;; 12/3/22: 0%->15; 12/3/22: WID:SP-211637->SP-220069; 4/6/22: 15%->55; 4/6/22: FCD:12/09/2022->12/22; 12/9/22: 55%->80; 10/12/22: 80%->100","23.700-71",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[905,970021,"   (stage 2 of) 5GC LoCation Services - Phase 3 ","5G_eLCS_Ph3",2,"Rel-18","S2","Fri 30/09/22","Tue 06/06/23",1,"SP-230093",null,"Ming Ai, CATT ","aiming@catt.cn ","; 10/12/22: WID:SP-220811->SP-221123; 10/12/22: 0%->30; 10/12/22: 0%->30; 9/1/23: WID:SP-221123->SP-221338; 15/3/23: 30%->65; 15/3/23: WID:SP-221338->SP-230093; 15/3/23: FCD:03/03/2023->06/20; 8/6/23: 65%->100",23.273,97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[906,980057,"   CT1 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C1","Fri 16/12/22","Sun 03/03/24",1,"CP-240233",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","6/6/23: Compl:5%->15%",23.273,97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[907,980058,"   CT3 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C3","Fri 16/12/22","Sun 03/03/24",1,"CP-240233",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","; 9/6/23: 20%->30",23.273,97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[908,980059,"   CT4 aspects of 5G_eLCS_Ph3","5G_eLCS_Ph3",2,"Rel-18","C4","Fri 16/12/22","Sun 03/03/24",1,"CP-240233",null,"Wang, Baixiao, CATT","wangbaixiao@cictmobile.com","; 9/6/23: 25%->65",23.273,97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[909,1070019,"Charging aspects of 5GC LoCation Services ","CH_5G_eLCS_Ph3",1,"Rel-19","S5","Wed 26/03/25","Tue 09/09/25",1,"SP-250370",null,"Zhiwei Mo, China Telecom ","mozw@chinatelecom.cn ","; 6/6/25: 0%->100","32.271; 32.290; 32.291; 32.298 ",107,54,null,null,"Wed 05/03/25","Fri 06/06/25"]
[910,981038,"Expanded and improved NR positioning ","NR_pos_enh2",1,"Rel-18",null,"Tue 13/12/22","Fri 05/06/26",0.69,"RP-241186",null,"Intel ",null,"29/3/23: WID:RP-223549->RP-230328; 6/10/23: WID:RP-230328->RP-232670; 2/1/24: WID:RP-232670->RP-233382; 2/4/24: WID:RP-233382->RP-240778; 23/7/24: WID:RP-240778->RP-241186",null,98,50,null,null,"Mon 09/01/23","Tue 23/07/24"]
[911,981138,"   Core part: Expanded and improved NR positioning ","NR_pos_enh2-Core",2,"Rel-18","R1","Tue 13/12/22","Mon 03/03/25",1,"RP-241186","RP-241919","Debdeep Chatterjee","debdeep.chatterjee@intel.com","17/3/23: Compl:0%->15%; Stat Rep: ->RP-230327; Rapporteur: Intel->Debdeep Chatterjee, Intel Corporation; Rap eMail: ->debdeep.chatterjee@intel.com; 17/3/23: 38.355 added;; ;...; 6/9/23: Compl:50%->70%; WID: RP-230328->RP-231460; Stat Rep: RP-230327->R...",38.354999999999997,98,50,null,null,"Mon 09/01/23","Wed 04/09/24"]
[912,981238,"   Perf. part: Expanded and improved NR positioning ","NR_pos_enh2-Perf",2,"Rel-18","R4","Thu 15/12/22","Sat 04/05/24",0.99,"RP-241186","RP-242766","Debdeep Chatterjee","debdeep.chatterjee@intel.com","Study in Rel-17 UID820025; 13/12/21: 0%->15; 12/3/22: 15%->30; 22/3/22: 23.545 added;; 4/6/22: 30%->50; 12/9/22: 50%->55; 11/12/22: 55%->65; 11/12/22: FCD:09/12/2022->/23; 9/1/23: WID:SP-210957->SP-221233; 17/3/23: 65%->75; 8/6/23: 75%->100; 30/6/23: ...",null,98,50,null,null,"Mon 09/01/23","Fri 06/12/24"]
[913,1040107,"   UE Conformance - Expanded and improved NR positioning ","NR_pos_enh2-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 05/06/26",0.09,"RP-241342","RP-251627","CATT ",null,"4/9/24: FCD:06/06/2026->26/06/2025; Compl:0%->5%; Stat Rep: ->RP-242124; ; 26/9/24: WID:RP-241342->RP-242125; 6/12/24: FCD:06/06/2025->05/06/2026; Compl:5%->6%; WID: RP-242125->RP-241342; Stat Rep: RP-242124->RP-243121; ; 6/3/25: FCD:23/10/2025->05/06/20",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[914,940081,"   Study on expanded and improved NR positioning","FS_NR_pos_enh2",2,"Rel-18","R1","Tue 13/12/22","Wed 05/06/24",1,"RP-222616","RP-222982","Debdeep Chatterjee, Intel Corporation","debdeep.chatterjee@intel.com","compare REL-17 SI FS_NR_pos; TR 38.8xx; 21/1/22: 38.859 added; ; 6/6/22: Compl:0%->12% 20/6/22: Rapporteur: Intel->Alexey Khoryaev, Intel Corporation; Rap eMail: ->alexey.khoryaev@intel.com12/7/22: WID:RP-213588->RP-221814 ;...; 23/9/22: WID:RP-213588...",38.859000000000002,94,48,null,null,"Thu 06/01/22","Mon 09/01/23"]
[915,940097,"NR sidelink evolution","NR_SL_enh2",1,"Rel-18",null,"Mon 13/12/21","Thu 06/06/24",1,"RP-232789",null,"OPPO",null,"TR 38.8xx; compare REL-17 WI NR_SL_enh; 5/4/22: WID:RP-213678->RP-220300; 12/7/22: WID:RP-220300->RP-221798; 23/9/22: WID:RP-221798->RP-221938; 9/1/23: WID:RP-221938->RP-222806; 29/3/23: WID:RP-222806->RP-230077; 2/1/24: WID:RP-230077->RP-232789",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[916,940197,"   Core part: NR sidelink evolution","NR_SL_enh2-Core",2,"Rel-18","R1","Mon 13/12/21","Tue 12/12/23",1,"RP-232789","RP-232786","Kevin Lin, OPPO","Kevin.Lin@oppo.com","TR 38.8xx; compare REL-17 WI NR_SL_enh; 22/3/22: Stat Rep: ->RP-220320 6/6/22: Compl:0%->7% ; ; 20/6/22: Rapporteur: OPPO->Kevin Lin, OPPO; Rap eMail: ->Kevin.Lin@oppo.com13/7/22: FCD:23/12/2022->12/20 ; ...; 9/12/22: FCD:23/12/2022->01/12/2023; Comp...",38.786000000000001,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[917,940297,"   Perf. part: NR sidelink evolution","NR_SL_enh2-Perf",2,"Rel-18","R1","Wed 15/12/21","Thu 06/06/24",1,"RP-232789","RP-240928","Kevin Lin, OPPO","Kevin.Lin@oppo.com","; 22/3/22: CD:12/09/2023->12/06/2024; 22/3/22: Stat Rep: ->RP-220320 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: ; 20/6/22: WG: R4->R1; Rapporteur: OPPO->Kevin Lin, OPPO; Rap eMail: ->Kevin.Lin@oppo.com13/7/22: FCD:24/06/2022->06/20 ; ...; 9/12/22: FCD...",null,94,48,null,null,"Thu 06/01/22","Tue 23/07/24"]
[918,941002,"NR sidelink relay enhancements","NR_SL_relay_enh",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.95,"RP-232972",null,"LG Electronics",null,"compare REL-17 WI NR_SL_relay; 6/1/22: WID:RP-213585->RP-212819; 5/4/22: WID:RP-212819->RP-221010; 12/7/22: WID:RP-221010->RP-221262; 9/1/23: WID:RP-221262->RP-223501; 2/1/24: WID:RP-223501->RP-232972",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[919,941102,"   Core part: NR sidelink relay enhancements","NR_SL_relay_enh-Core",2,"Rel-18","R2","Mon 13/12/21","Tue 12/12/23",1,"RP-232972","RP-232971","Youngdae LEE, LG Electronics Inc.","youngdae.lee@lge.com","compare REL-17 WI NR_SL_relay; 22/3/22: WID: RP-212819->RP-213585; 22/3/22: Stat Rep: ->RP-220524 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 20/6/22: Rapporteur: LG Electronics->Youngdae LEE, LG Electronics; Rap eMail: ->youngdae.lee@lge.com13/7/22: ...;...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[920,941202,"   Perf. part: NR sidelink relay enhancements","NR_SL_relay_enh-Perf",2,"Rel-18","R2","Wed 15/12/21","Thu 06/06/24",1,"RP-223501","RP-241088","Youngdae LEE, LG Electronics Inc.","youngdae.lee@lge.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: WID: RP-212819->RP-213585; 22/3/22: Stat Rep: ->RP-220524 6/6/22: CD:12/06/2024->24/06/2022 20/6/22: WG: R4->R2; FCD:24/06/2022->22/06/2022; Rapporteur: LG Electronics->Youngdae LEE, LG Electronics;...;...",null,94,48,null,null,"Thu 06/01/22","Thu 13/06/24"]
[921,960083,"   UE Conformance - NR Sidelink Relay ","NR_SL_relay-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Tue 09/09/25",0.9,"RP-221447","RP-251629","Xiaozhong CHEN, CATT","chenxiaozhong@catt.cn","9/9/22: Comp...; 23/9/22: WID:RP-221447->RP-222378; 9/12/22: FCD:23/09/2022->01/09/2023; WID: RP-222378->RP-221447; Stat Rep: ->RP-223141; Rapporteur: CATT->Xiaozhong CHEN, CATT; Rap eMail: ->chenxiaozhong@catt.cn; 17/3/23: FCD:09/09/2023.....",null,96,49,null,null,"Tue 12/07/22","Fri 06/06/25"]
[922,941000,"Mobile Terminated-Small Data Transmission (MT-SDT) for NR","NR_MT_SDT",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.95,"RP-234010",null,"ZTE",null,"no Perf. part; 9/1/23: WID:RP-213583->RP-222993; 2/1/24: WID:RP-222993->RP-234010",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[923,941100,"   Core part: Mobile Terminated-Small Data Transmission (MT-SDT) for NR","NR_MT_SDT-Core",2,"Rel-18","R2","Mon 13/12/21","Tue 12/12/23",1,"RP-234010","RP-232887","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","no Perf. part ; 6/6/22: CD:12/09/2023->23/09/2022 6/6/22: Stat Rep: RP-220215->RP-221310; 20/6/22: Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->eswar.vutukuri@zte.com.cn13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/2022->01...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[924,1040103,"   UE Conformance - Mobile Terminated-Small Data Transmission (MT-SDT) for NR ","NR_MT_SDT-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 12/12/25",0.9,"RP-241127","RP-251189","Qualcomm ",null,"4/9/24: FCD:12/12/2025->25/12/2024; Compl:0%->10%; Stat Rep: ->RP-241914; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:10%->40%; Stat Rep: RP-241914->RP-242496; ; 6/3/25: FCD:24/06/2025->12/12/2025; Compl:40%->65%; Stat Rep: RP-242496->RP-250111; ; 6/6/2",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[925,950048,"Study on Proximity based Services Phase 2 ","FS_5G_ProSe_Ph2",1,"Rel-18","S2","Mon 20/12/21","Fri 10/03/23",1,"SP-211653",null,"Deng, Qiang, CATT ","dengqiang1@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-33 added;; 12/3/22: 0%->20; 14/3/24: 95%->100","23.700-33",95,48,null,null,"Sun 19/12/21","Thu 14/03/24"]
[926,940077,"   Study on Stage 2 for Proximity based Services Phase 2 ","FS_5G_ProSe_Ph2",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211653",null,"Deng, Qiang, CATT ","dengqiang1@catt.cn, Primary Rapporteur. ","21/1/22: 23.700-33 added;; 12/3/22: 0%->20; 4/6/22: 20%->55; 12/9/22: 55%->75; 10/12/22: 75%->100","23.700-33",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[927,950024,"   Study on Security Aspects of Proximity Based Services Phase 2 ","FS_5G_ProSe_Ph2",2,"Rel-18","S3","Thu 10/03/22","Fri 10/03/23",1,"SP-220202",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","4/6/22: 0%->5; 13/7/22: 33.740 added;; 13/7/22: 33.741 added;; 12/9/22: 5%->40; 11/12/22: 40%->75; 17/3/23: 75%->80; 8/6/23: 80%->90","33.740; 33.741",95,48,null,null,"Thu 10/03/22","Thu 08/06/23"]
[928,980112,"Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",1,"Rel-18",null,"Tue 27/09/22","Tue 12/12/23",1,"SP-220806",null,"Deng Qiang, CATT ","dengqiang1@catt.cn ",null,"23.304; 23.501; 23.502; 23.503 ",97,49,null,null,"Wed 19/10/22","NA"]
[929,970016,"   (stage 2 of) Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",2,"Rel-18","S2","Tue 27/09/22","Tue 06/06/23",1,"SP-230097",null,"Deng Qiang, CATT ","dengqiang1@catt.cn ","; 9/1/23: WID:SP-220806->SP-221206; 15/3/23: WID:SP-221206->SP-230097; 15/3/23: 0%->80; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 80%->100","23.304; 23.501; 23.502; 23.503 ",97,49,null,null,"Wed 19/10/22","Thu 08/06/23"]
[930,980060,"   CT1 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C1","Fri 16/12/22","Tue 12/12/23",1,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","; 9/6/23: 15%->70","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"Wed 19/10/22","Fri 09/06/23"]
[931,980061,"   CT3 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C3","Fri 16/12/22","Tue 12/12/23",1,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","; 9/6/23: 0%->20","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"Wed 19/10/22","Fri 09/06/23"]
[932,980062,"   CT4 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C4","Fri 16/12/22","Tue 12/12/23",1,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn","6/6/23: Compl:0%->30%","24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"Wed 19/10/22","Tue 06/06/23"]
[933,980063,"   CT6 aspects of 5G_ProSe_Ph2","5G_ProSe_Ph2",2,"Rel-18","C6","Fri 16/12/22","Tue 12/12/23",1,"CP-233220",null,"Duan, Xiaoyan, CATT","duanxiaoyan@catt.cn",null,"24.554; 24.555; 23.122; 24.501; 24.526; 24.587; 27.007; 29.513; 29.519; 29.522; 29.525; 29.559; 29.553; 23.008; 29.503; 29.505; 29.510; 29.518; 29.571; 29.509; 31.102",97,49,null,null,"Wed 19/10/22","NA"]
[934,990045,"   Security Aspects of Proximity-based Services in 5GS Phase 2 ","5G_ProSe_Ph2",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230158",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 8/6/23: 0%->90; 8/12/23: 90%->95; 15/3/24: 95%->100",33.503,99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[935,990108,"5G-enabled fused location service capability exposure ","5GFLS",1,"Rel-18",null,"Fri 11/06/21","Sun 03/03/24",1,"SP-221234",null,"Liping Wu, CATT ","wuliping@cictmobile.com ",null,23.434000000000001,99,50,null,null,"Fri 09/12/22","NA"]
[936,920015,"   Study on 5G-enabled fused location service capability exposure ","FS_5GFLS",2,"Rel-18","S6","Fri 11/06/21","Mon 12/09/22",1,"SP-220097",null,"Zhang, Ling, CATT ","zhangling@catt.cn ","2/7/21: 23.700-96 added;; 13/9/21: 0%->20; 13/12/21: 20%->40; 13/12/21: WID:SP-210477->SP-211512; 13/12/21: FCD:Fri 11/03/->06/22; 12/3/22: FCD:10/06/2022->9/22; 12/3/22: WID:SP-211512->SP-220097; 4/6/22: 40%->55; 12/9/22: 55%->75; 11/12/22: 75%->100","23.700-96",92,47,null,null,"Fri 11/06/21","Sun 11/12/22"]
[937,980109,"   Stage 2 of 5GFLS","5GFLS",2,"Rel-18","S6","Fri 09/12/22","Tue 06/06/23",1,"SP-221234",null,"Liping Wu, CATT ","wuliping@cictmobile.com ","; 17/3/23: 0%->60; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100",23.434000000000001,98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[938,990016,"   CT1 aspects of 5GFLS","5GFLS",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-230195",null,"Zhao, Xiaoxue, CATT","zhaoxiaoxue@cictmobile.com","6/6/23: Compl:0%->60%","24.545; 29.549",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[939,990069,"   CT3 aspects of 5GFLS","5GFLS",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-230195",null,"Zhao, Xiaoxue, CATT","zhaoxiaoxue@cictmobile.com","; 9/6/23: 0%->70","24.545; 29.549",99,50,null,null,"Fri 09/12/22","Fri 09/06/23"]
[940,0,"See also MCOver5GProSe under Mission Critical and LPHP under Verticals","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[941,0,"Rel-18 Verticals, Industries, Factories, Northbound API","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[942,930023,"Service exposure interfaces for industry ","EXPOSE",1,"Rel-18","S1","Fri 10/09/21","Mon 20/09/21",1,"SP-211056",null,"Joachim W. Walewski ","joachim.walewski@siemens.com ","; 13/12/21: 0%->100",22.260999999999999,93,47,null,null,"Fri 10/09/21","Mon 13/12/21"]
[943,1010009,"Guidelines for CAPIF Usage ","CAPIF_EXT",1,"Rel-18","S6","Thu 07/09/23","Mon 09/09/24",1,"SP-241692",null,"Junpei Uoshima, NTT DOCOMO ","junpei.uoshima.mt@nttdocomo.com ","8/12/23: 0%->20; 4/1/24: 23.946 added;; 14/3/24: 20%->55; 13/6/24: 55%->80; 4/9/24: 80%->90; 5/12/24: 90%->100; 8/1/25: WID:SP-231161->SP-241692 (change Rel-19->Rel-18)",23.946000000000002,101,51,null,null,"Thu 07/09/23","Wed 08/01/25"]
[944,990109,"Generic group management, exposure and communication enhancements ","GMEC",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-221339",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","; 10/12/22: 0%->30; 9/1/23: WID:SP-220989->SP-221339","23.501; 23.502; 23.503 ",97,49,null,null,"Fri 23/09/22","Mon 09/01/23"]
[945,940061,"   Study on generic group management, exposure and communication enhancements ","FS_GMEC",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211603",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","21/1/22: 23.700-74 added;; 12/3/22: 0%->25; 4/6/22: 25%->70; 12/9/22: 70%->90; 10/12/22: 90%->95; 10/12/22: FCD:12/09/2022->12/22; 15/3/23: 95%->100","23.700-74",94,48,null,null,"Sun 19/12/21","Wed 15/03/23"]
[946,970069,"   Stage 2 of GMEC","GMEC",2,"Rel-18","S2","Fri 23/09/22","Fri 03/03/23",1,"SP-230101",null,"Qianghua Zhu, Huawei ","zhuqianghua@huawei.com ","; 10/12/22: 0%->30; 9/1/23: WID:SP-220989->SP-221339; 15/3/23: WID:SP-221339->SP-230101; 15/3/23: 30%->70; 8/6/23: 70%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Fri 23/09/22","Thu 08/06/23"]
[947,990009,"   CT3 aspects of GMEC","GMEC",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-240296",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:15%->40%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,null,"Fri 23/09/22","Tue 06/06/23"]
[948,990071,"   CT4 aspects of GMEC","GMEC",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-240296",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:5%->40%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,null,"Fri 23/09/22","Tue 06/06/23"]
[949,990072,"   CT1 aspects of GMEC","GMEC",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-240296",null,"El Moatamid, Abdessamad, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:0%->75%6/6/23: WID: CP-230118->CP-231194","29.122.29.512.29.513.29.519.29.522.29.525.29.565.29.502.29.503.29.504.29.505.29.571.24.501.24.526",97,49,null,null,"Fri 23/09/22","Tue 06/06/23"]
[950,930015,"Application layer support for Factories of the Future (FF) ","FFAPP",1,"Rel-18","S6","Fri 10/09/21","Fri 03/03/23",1,"SP-230751",null,"Shao Weixiang, ZTE Corporation ","shao.weixiang@zte.com.cn ",null,"23.434 ; 23.545",93,47,null,null,"Fri 10/09/21","Fri 30/06/23"]
[951,980131,"Service Enabler Architecture Layer for Verticals Phase 3","SEAL_Ph3",1,"Rel-18",null,"Fri 10/12/21","Sat 09/09/23",1,"SP-211518",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ",null,23.434000000000001,94,48,null,null,"Fri 10/12/21","Mon 12/09/22"]
[952,940024,"   Stage 2 of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","S6","Sun 12/12/21","Tue 06/06/23",1,"SP-230276",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","; 12/3/22: 0%->5; 4/6/22: 5%->20; 12/9/22: 20%->35; 11/12/22: 35%->60. Acronym: eSEAL_Ph2->SEAL_Ph3; 11/12/22: FCD:12/12/2022->/23; 17/3/23: WID:SP-211518->SP-230276; 17/3/23: FCD:03/03/2023->6/6//23; change rapport (was Basavaraj (Basu) Pattan, Samsu...",23.434000000000001,94,48,null,null,"Sun 11/12/22","Thu 08/06/23"]
[953,980064,"   CT1 aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","C1","Sun 12/12/21","Mon 12/12/22",1,"CP-233219",null,"Vijay Sangameshwara (Samsung Electronics)","s.vijay@samsung.com","6/6/23: Compl:10%->45%","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 29.549",94,48,null,null,"Fri 10/12/21","Tue 06/06/23"]
[954,980065,"   CT3 aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","C3","Fri 10/12/21","Fri 09/12/22",1,"CP-233219",null,"Vijay Sangameshwara (Samsung Electronics)","s.vijay@samsung.com","9/6/23: 15%->45","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 29.549",94,48,null,null,"Fri 10/12/21","Fri 09/06/23"]
[955,990047,"   Security aspects of SEAL_Ph3","SEAL_Ph3",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230365",null,"Rajavelsamy Rajadurai, Samsung ","rajvel@samsung.com ","; 8/6/23: 0%->80; 15/3/24: 80%->100",33.433999999999997,99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[956,980124,"SEAL data delivery enabler for vertical applications ","SEALDD",1,"Rel-18",null,"Mon 13/09/21","Sun 03/03/24",1,"SP-220914",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 23/9/22: 23.433 added;","23.434 ; 23.433",97,49,null,null,"Sun 11/09/22","Fri 23/09/22"]
[957,930013,"   Study on SEAL data delivery enabler for vertical applications ","FS_SEALDD",2,"Rel-18","S6","Mon 13/09/21","Mon 12/09/22",1,"SP-220467",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/12/21: 0%->30; 12/3/22: 30%->45; 22/3/22: 23.700-34 added;; 4/6/22: 45%->60; 4/6/22: FCD:10/06/2022->09/22; 4/6/22: WID:SP-210955->SP-220467; 12/9/22: 60%->85; 11/12/22: 85%->100","23.700-34",93,47,null,null,"Mon 13/09/21","Sun 11/12/22"]
[958,970037,"   (Stage 2 of Seal DD) SEAL data delivery enabler for vertical applications","SEALDD",2,"Rel-18","S6","Fri 09/09/22","Tue 06/06/23",1,"SP-221232",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 23/9/22: 23.433 added;; 11/12/22: 0%->60; 9/1/23: WID:SP-220914->SP-221232; 17/3/23: 60%->85; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 85%->100","23.434 ; 23.433; 23.558",97,49,null,null,"Sun 11/12/22","Thu 08/06/23"]
[959,980066,"   CT1 aspects of SEALDD","SEALDD",2,"Rel-18","C1","Fri 16/12/22","Sun 03/03/24",1,"CP-240272",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","30/6/23: WID:CP-230338->CP-231284","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 24.538; 29.549; 29.538; 29.558",97,49,null,null,"Sun 11/09/22","Fri 30/06/23"]
[960,980067,"   CT3 aspects of SEALDD","SEALDD",2,"Rel-18","C3","Fri 16/12/22","Sun 03/03/24",1,"CP-240272",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","31/3/23: 29.548 added;; 9/6/23: 5%->25","24.544; 24.545; 24.546; 24.547; 24.548; 24.549; 24.538; 29.549; 29.538; 29.558; 29.548",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[961,1000006,"   Security aspects of SEAL Data Delivery enabler ","SEALDD",2,"Rel-18","S3","Thu 08/06/23","Sat 09/09/23",1,"SP-230560",null,"Ao Lei, Huawei, ","leiao@huawei.com ","; 15/3/24: 0%->100",33.433999999999997,100,51,null,null,"Thu 08/06/23","Fri 15/03/24"]
[962,910036,"Low Power High Accuracy Positioning for industrial IoT scenarios ","LPHAP",1,"Rel-18","S1","Thu 18/03/21","Fri 11/06/21",1,"SP-210216",null,"Yuan Wang, Huawei ","wangyuan5@huawei.com ","; 19/3/21: 0%->40; 11/6/21: 40%->100","22.104; 22.261 ",91,46,null,null,"Thu 18/03/21","Fri 11/06/21"]
[963,890024,"Subscriber-aware Northbound API access ","SNA",1,"Rel-18","S1","Tue 01/09/20","Thu 17/09/20",1,"SP-200797",null,"Minokuchi, Atsushi, NTT DOCOMO ","minokuchi at nttdocomo dot com ",null,22.260999999999999,89,45,null,null,"Fri 11/09/20","NA"]
[964,990117,"Application enablement aspects for subscriber-aware northbound API access ","SNAAPP",1,"Rel-18",null,"Thu 02/06/22","Sat 09/09/23",1,"SP-220469",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","; 11/12/22: 0%->55","23.222; 23.434 ",96,49,null,null,"Thu 02/06/22","Sun 11/12/22"]
[965,960012,"   Stage 2 of SNAAPP","SNAAPP",2,"Rel-18","S6","Thu 02/06/22","Fri 03/03/23",1,"SP-220469",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","; 11/12/22: 0%->55; 17/3/23: 15%->90; 8/6/23: 90%->100","23.222; 23.434 ",96,49,null,null,"Thu 16/03/23","Thu 08/06/23"]
[966,960028,"   Study on SNAAPP securitY ","FS_SNAAPPY",2,"Rel-18","S3","Thu 02/06/22","Mon 12/12/22",1,"SP-220526",null,"Zugenmaier, Alf, NTT DOCOMO, ","zugenmai@hm.edu ","13/7/22: 33.884 added;; 12/9/22: 0%->10; 11/12/22: 10%->50; 17/3/23: 50%->60; 8/6/23: 60%->100",33.884,96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[967,990048,"   Security aspects of SNAPP ","SNAAPPY",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230161",null,"Zugenmaier, Alf, NTT DOCOMO ","zugenmai@hm.edu ","; 8/6/23: 0%->50; 8/12/23: 50%->85; 15/3/24: 85%->100",33.122,99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[968,1010002,"   CT3 aspects of SNAAPP","SNAAPP",2,"Rel-18","C3","Thu 16/03/23","Sat 09/09/23",1,"CP-232128",null,"Eitoku, Haruka, NTT","haruka.eitoku@ntt.com",null,29.222000000000001,99,50,null,null,"Thu 16/03/23","Thu 08/06/23"]
[969,920039,"Smart Energy and Infrastructure ","SEI",1,"Rel-18",null,"Thu 25/06/20","Fri 10/12/21",1,"SP-210523",null,"XIA Xu, China Telecom ","xiaxu@chinatelecom.cn ",null,"22.104;22.261 ",92,47,null,null,"Fri 11/06/21","NA"]
[970,880038,"   Study on 5G Smart Energy and Infrastructure","FS_5GSEI",2,"Rel-18","S1","Thu 25/06/20","Fri 11/06/21",1,"SP-200574",null,"XIA Xu, China Telecom","xiaxu@chinatelecom.cn","28/7/20: 22.867 added;; 12/9/20: 0%->20; 5/12/20: 20%->60; 19/3/21: FCD:17/03/2021->06/21; 19/3/21: 60%->75; 11/6/21: 75%->90; 13/9/21: 90%->100",22.867000000000001,88,45,null,null,"Thu 25/06/20","Mon 13/09/21"]
[971,920032,"   Stage 1 of Smart Energy and Infrastructure ","SEI",2,"Rel-18","S1","Fri 11/06/21","Fri 10/12/21",1,"SP-210523",null,"XIA Xu, China Telecom ","xiaxu@chinatelecom.cn ","; 13/9/21: 0%->95; 10/12/21: 95%->100","22.104;22.261 ",92,47,null,null,"Fri 11/06/21","Fri 10/12/21"]
[972,940040,"Study on Network and Service Operations for Energy Utilities ","FS_NSOEU",1,"Rel-18","S5","Mon 13/12/21","Tue 06/06/23",1,"SP-211622",null,"Erik Guttman , Samsung ","erik.guttman@samsung.com ","7/1/22: 28.902 added;; 4/6/22: 0%->25; 12/9/22: 25%->45; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 45%->55; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 55%->79; 8/6/23: 79%->100",28.902000000000001,94,48,null,null,"Mon 13/12/21","Thu 08/06/23"]
[973,920014,"Study on application enablement aspects for subscriber-aware northbound API access ","FS_SNAAPP",1,"Rel-18","S6","Fri 11/06/21","Fri 10/06/22",1,"SP-220094",null,"Suzuki, Yuji, NTT DOCOMO ","yuuji.suzuki.rm@nttdocomo.com ","2/7/21: 23.700-95 added;; 13/9/21: 0%->20; 13/12/21: 20%->65; 12/3/22: 65%->75; 12/3/22: FCD:11/03/2022->6/22; 12/3/22: WID:SP-210476->SP-220094; 4/6/22: 75%->85; 12/9/22: 85%->90; 11/12/22: 90%->100","23.700-95",92,47,null,null,"Fri 11/06/21","Sun 11/12/22"]
[974,960022,"Rel-18 Enhancements of 3GPP Northbound and Application Layer interfaces and APIs","NBI18",1,"Rel-18",null,"Fri 03/06/22","Sun 03/03/24",1,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","30/6/23: WID:CP-221105->CP-231190",null,96,49,null,null,"Fri 03/06/22","Fri 30/06/23"]
[975,960053,"   CT1 aspects of NBI18","NBI18",2,"Rel-18","C1","Mon 06/06/22","Sun 03/03/24",1,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:25%->40%6/6/23: WID: CP-221105->CP-231190; 9/6/23: 40%->45; 9/6/23: 45%->",24.558,96,49,null,null,"Fri 03/06/22","Fri 09/06/23"]
[976,960054,"   CT3 aspects of NBI18","NBI18",2,"Rel-18","C3","Fri 03/06/22","Sun 03/03/24",1,"CP-231190",null,"Abdessamad El Moatamid, Huawei","abdessamad.el.moatamid@huawei.com","6/6/23: Compl:30%->60%6/6/23: WID: CP-221105->CP-231190","29.116; 29.122; 29.222; 29.255; 29.257; 29.343; 29.486; 29.522; 29.538; 29.549; 29.558",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[977,980027,"Study on Structure of Charging for Verticals ","FS_SCV",1,"Rel-18","S5","Fri 09/12/22","Tue 12/12/23",1,"SP-230178",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","16/3/23: WID:SP-221161->SP-230178; 17/3/23: 0%->8; 17/3/23: 28.843 added;; 8/6/23: 8%->80; 8/6/23: FCD:06/06/2023->12/23; 7/9/23: 80%->100",28.843,98,50,null,null,"Fri 09/12/22","Thu 07/09/23"]
[978,1010015,"Charging Aspects of B2B","B2B_CH",1,"Rel-18","S5","Wed 06/09/23","Sun 03/03/24",1,"SP-231155",null,"Deng, Yimeng, Huawei ","dengyimeng at huawei dot com ","; 8/12/23: 0%->80; 14/3/24: 80%->100","32.240; 32.290 ",101,51,null,null,"Wed 06/09/23","Thu 14/03/24"]
[979,0,"Rel-18 Mission Critical and emergencies","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[980,940015,"Mission critical security enhancements phase 3 ","MCXSec3",1,"Rel-18","S3","Fri 10/12/21","Fri 03/03/23",1,"SP-211363",null,"Woodward, Tim, Motorola Solutions, Inc. ","tim.woodward@motorolasolutions.com ","; 4/6/22: 0%->10; 12/9/22: 10%->15; 11/12/22: 15%->35; 17/3/23: 35%->75; 8/6/23: 75%->100",33.18,94,48,null,null,"Fri 10/12/21","Thu 08/06/23"]
[981,1000042,"Enhanced Mission Critical Push-to-talk architecture phase 4 ","enh4MCPTT",1,"Rel-18",null,"Fri 10/12/21","Sun 03/03/24",1,"SP-211519",null,"Harish Negalaguli (Motorola Solutions)","harish.negalaguli@motorolasolutions.com","; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->55; 11/12/22: 55%->65; 17/3/23: 65%->80","23.379; 23.280; 23.281; 23.282; 23.283 ",94,48,null,null,"Fri 10/12/21","Fri 17/03/23"]
[982,940025,"   Stage 2 of enh4MCPTT","enh4MCPTT",2,"Rel-18","S6","Fri 10/12/21","Fri 03/03/23",1,"SP-211519",null,"Harish Negalaguli (Motorola Solutions)","harish.negalaguli@motorolasolutions.com","; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->55; 11/12/22: 55%->65; 17/3/23: 65%->80; 8/6/23: 80%->100","23.379; 23.280; 23.281; 23.282; 23.283 ",94,48,null,null,"Fri 10/12/21","Thu 08/06/23"]
[983,1000020,"   CT aspects of enh4MCPTT","enh4MCPTT",2,"Rel-18","C1","Wed 07/06/23","Sun 03/03/24",1,"CP-240297",null,"Kiran Kapale, Samsung, ","kiran.kapale@samsung.com ","; 30/6/23: 24.283 added;","24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582 ; 24.283",100,51,null,null,"Wed 07/06/23","Fri 30/06/23"]
[984,930043,"Gateway UE function for Mission Critical Communication ","MCGWUE",1,"Rel-18",null,"Thu 25/06/20","Sun 03/03/24",1,"SP-210959",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ",null,"23.280; 23.289; 23.281; 23.282; 23.379 ",93,47,null,null,"Fri 10/09/21","NA"]
[985,880033,"   Study of Gateway UE function for Mission Critical Communication ","FS_MCGWUE",2,"Rel-18","S6","Thu 25/06/20","Mon 20/09/21",1,"SP-200335",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","13/9/20: 0%->10; 25/9/20: 23.700-79 added;; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->60; 13/9/21: 60%->100","23.700-79",88,45,null,null,"Fri 26/06/20","Mon 13/09/21"]
[986,930017,"   (Stage 2 of) Gateway UE function for Mission Critical Communication ","MCGWUE",2,"Rel-18","S6","Fri 10/09/21","Fri 10/06/22",1,"SP-210959",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","; 13/12/21: 0%->50; 12/3/22: 50%->75; 4/6/22: 75%->90; 12/9/22: 90%->100","23.280; 23.289; 23.281; 23.282; 23.379 ",93,47,null,null,"Fri 10/09/21","Mon 12/09/22"]
[987,990011,"   CT1 aspects of MCGWUE","MCGWUE",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-232164",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com",null,"24.281.24.282.24.379.24.380.24.483.24.484.24.581.24.582",93,47,null,null,"Fri 10/09/21","Mon 12/09/22"]
[988,970054,"Mission Critical Services over 5MBS ","MCOver5MBS",1,"Rel-18",null,"Thu 07/03/19","Tue 12/12/23",1,"SP-210958",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","; 13/12/21: 0%->30; 12/3/22: 30%->50; 12/3/22: FCD:11/03/2022->9/22; 4/6/22: 50%->85",23.289000000000001,93,47,null,null,"Fri 10/09/21","Sat 04/06/22"]
[989,930016,"   Stage 2 of Mission Critical Services over 5MBS ","MCOver5MBS",2,"Rel-18","S6","Thu 07/03/19","Fri 11/03/22",1,"SP-210958",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","; 13/12/21: 0%->30; 12/3/22: 30%->50; 12/3/22: FCD:11/03/2022->9/22; 4/6/22: 50%->85; 12/9/22: 0%->98; 12/9/22: FCD:10/06/2020->03/22; 11/12/22: 98%->100",23.289000000000001,93,47,null,null,"Fri 10/09/21","Sun 11/12/22"]
[990,970033,"   CT1 aspects of Mission Critical Services over 5MBS","MCOver5MBS",2,"Rel-18","C1","Tue 13/09/22","Tue 12/12/23",1,"CP-222175",null,"Chen, Ying, TD Tech Ltd.","chenying@td-tech.com","6/6/23: Compl:20%->40%","24.281; 24.282; 24.379; 24.380; 24.481; 24.483; 24.484; 42.581; 24.582",97,49,null,null,"Mon 05/09/22","Tue 06/06/23"]
[991,970055,"Mission Critical Services over 5GProSe ","MCOver5GProSe",1,"Rel-18",null,"Thu 07/03/19","Tue 12/12/23",1,"SP-211517",null,"Yanmei YANG, Huawei ","yangyanmei@huawei.com ","; 12/3/22: 0%->50; 4/6/22: 50%->87",23.289000000000001,94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[992,940023,"   Stage 2 of Mission Critical Services over 5GProSe ","MCOver5GProSe",2,"Rel-18","S6","Thu 07/03/19","Mon 12/09/22",1,"SP-211517",null,"Yanmei YANG, Huawei ","yangyanmei@huawei.com ","; 12/3/22: 0%->50; 4/6/22: 50%->87; 12/9/22: 0%->100; 12/9/22: FCD:10/06/2020->09/22",23.289000000000001,94,48,null,null,"Fri 10/12/21","Mon 12/09/22"]
[993,970034,"   CT1 aspects of Mission Critical Services over 5GProSe","MCOver5GProSe",2,"Rel-18","C1","Tue 13/09/22","Tue 12/12/23",1,"CP-233210",null,"Mengdi Ji, Huawei","jimengdi@huawei.com, ","3/24: rapporteur changed (was weihaitao@huawei.com)","24.281; 24.282; 24.379; 24.380; 24.481; 24.483; 24.484; 24.581; 24.582",97,49,null,null,"Mon 05/09/22","NA"]
[994,970027,"Stopped - ProSe Secondary Authentication ","PROSESA",1,"Rel-18","S3","Mon 12/09/22","Fri 03/03/23",1,"SP-220874",null,"Samir Ferdi , Interdigital ","samir. ferdi @ interdigital . com ","; 17/3/23: 0%->30; 8/6/23: 30%->90. 9/23: stopped at 90%",33.503,97,49,101,null,"Sun 11/09/22","Thu 08/06/23"]
[995,930026,"Sharing administrative configuration between interconnected MCX Service systems ","SACI_MCS",1,"Rel-18","S1","Fri 10/09/21","Fri 10/12/21",1,"SP-211059",null,"Toobe, Jens, BDBOS ","jens.toobe@bdbos.bmi.bund.de ","; 13/9/21: 0%->80; 10/12/21: 80%->100",22.28,93,47,null,null,"Fri 10/09/21","Fri 10/12/21"]
[996,930025,"Ad hoc Group Communication support in Mission Critical Services ","AHGC",1,"Rel-18","S1","Fri 10/09/21","Mon 20/09/21",1,"SP-211058",null,"Erik.Guttman, Samsung ","Erik.Guttman@samsung.com ","; 10/12/21: 0%->100",22.28,93,47,null,null,"Fri 10/09/21","Fri 10/12/21"]
[997,1010020,"Mission Critical ad hoc group Communications ","MC_AHGC",1,"Rel-18","S6","Fri 09/12/22","Sun 03/03/24",1,"SP-221235",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ","; 11/12/22: 0%->35; 17/3/23: FCD:03/03/2023->/23; 17/3/23: 35%->85; 8/6/23: 85%->100","23.280; 23.379; 23.281; 23.282 ",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[998,980051,"   Stage 2 of Mission Critical ad hoc group Communications ","MC_AHGC",2,"Rel-18","S6","Fri 09/12/22","Tue 06/06/23",1,"SP-221235",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ","; 11/12/22: 0%->35; 17/3/23: FCD:03/03/2023->/23; 17/3/23: 35%->85; 8/6/23: 85%->100","23.280; 23.379; 23.281; 23.282 ",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[999,1010004,"   CT1 aspects of Mission Critical ad hoc group Communications ","MC_AHGC",2,"Rel-18","C1","Sat 09/09/23","Sun 03/03/24",1,"CP-232162",null,"Kiran Gurudev Kapale, Samsung ","kiran.kapale@samsung.com ",null,"24.379, 24.380, 24.281, 24.581, 24.282, 24.582, 24.481, 24.483, 24.484",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[1000,850043,"Study on sharing administrative configuration between interconnected MCX Service systems ","FS_SACI_MCS",1,"Rel-18","S1","Thu 19/09/19","Fri 10/12/21",1,"SP-190837",null,"Toobe, Jens, BDBOS","jens.toobe at bdbos.bmi.bund.de","; 8/10/19: 22.881 added;; 6/12/19: 0%->5; 12/9/20: 5%->20; 19/3/21: 20%->55; 19/3/21: FCD:12/06/2020->12/21; 11/6/21: 55%->90; 13/9/21: 90%->100","New ; 22.881",85,43,null,null,"Fri 13/09/19","Mon 13/09/21"]
[1001,940020,"Study on sharing of administrative configuration between interconnected MC service systems ","FS_MCShAC",1,"Rel-18","S6","Mon 13/12/21","Fri 03/03/23",1,"SP-211514",null,"Azem, Dania, BDBOS ","dania.azem@bdbos.bmi.bund.de ","7/1/22: 23.700-38 added;; 12/3/22: 0%->5; 4/6/22: 5%->25; 12/9/22: 25%->25; 11/12/22: 25%->65; 17/3/23: 65%->80; 8/6/23: 80%->100","23.700-38",94,48,null,null,"Mon 13/12/21","Thu 08/06/23"]
[1002,940022,"Study on Mission Critical ad hoc group communications ","FS_MCAHGC",1,"Rel-18","S6","Mon 13/12/21","Mon 12/12/22",1,"SP-211516",null,"Arunprasath Ramamoorthy, Samsung ","arun.prasath@samsung.com ","7/1/22: 23.700-76 added;; 12/3/22: 0%->25; 4/6/22: 25%->75; 12/9/22: 75%->90; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 90%->95; 17/3/23: 95%->100","23.700-76",94,48,null,null,"Mon 13/12/21","Fri 17/03/23"]
[1003,800023,"Study on Mission Critical services support over 5G System","FS_MCOver5GS",1,"Rel-18","S6","Wed 06/06/18","Fri 10/06/22",1,"SP-200837",null,"Verweij, Kees, The Police of the Netherlands","kees.verweij@politie.nl","6/8/18: 23.783 added;¦10/9/18: 0%->5¦7/12/18: 5%->35¦7/12/18: FCD:03/19->09/19¦14/12/18: WID:SP-180383->SP-181136. 03/19: Rel corrected (was shown as Rel-17); 31/5/19: 35%->40; 26/3/20: FCD:12/09/2019->09/20; 26/3/20: 40%->45; Rel-16->17; 03/22:Rel17-> ","New; 23.783",80,41,null,null,"Wed 06/06/18","Sat 04/06/22"]
[1004,0,"Rel-18 Artificial Intelligence (AI)/Machine Learning (ML)","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1005,920037,"AI/ML model transfer in 5GS ","AIML_MT",1,"Rel-18",null,"Fri 06/12/19","Fri 10/12/21",1,"SP-210520",null,"Jia SHEN, OPPO, sj@oppo.com ",null,null,22.260999999999999,92,47,null,null,"Fri 11/06/21","Wed 13/07/22"]
[1006,860009,"   Study on traffic characteristics and performance requirements for AI/ML model transfer in 5GS ","FS_AIML_MT",2,"Rel-18","S1","Fri 06/12/19","Fri 11/06/21",1,"SP-220441",null,"Jia SHEN, Oppo . ","sj@oppo.com ","28/7/20: 33.852 added;; 12/9/20: 0%->40; 5/12/20: 40%->70; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 70%->75; 11/6/21: 75%->95; 13/9/21: 95%->100. 06/22: FS_AMMT->FS_AIML_MT; 21/6/22: WID:SP-191040->SP-220441",22.873999999999999,86,44,null,null,"Fri 06/12/19","Tue 21/06/22"]
[1007,920030,"   Stage 1 of AMMT ","AIML_MT",2,"Rel-18","S1","Fri 11/06/21","Fri 10/12/21",1,"SP-220440",null,"Jia SHEN, OPPO, sj@oppo.com ",null,"; 13/9/21: 0%->80; 11/3/22: 80%->10006/22: AMMT->AIML_MT; 21/6/22: WID:SP-210587->SP-220440",22.260999999999999,92,47,null,null,"Fri 11/06/21","Tue 21/06/22"]
[1008,940084,"Study on Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface","FS_NR_AIML_air",1,"Rel-18","R1","Mon 13/12/21","Tue 12/12/23",1,"RP-251186","RP-233132","Juan Montojo (RAN1); Mattias Frenne (RAN2); Xiaofeng Liu (RAN4), Qualcomm; Ericsson; CAICT","juanm@qti.qualcomm.com; mattias.frenne@ericsson.com; liuxiaofeng1@caict.ac.cn","TR 38.8xx; compare REL-18 WI NR_AIML_NGRAN-Core; 21/1/22: 38.843 added;; 22/3/22: Stat Rep: ->RP-220534 ; 6/6/22: Compl:0%->5% 20/6/22: Acronym:FS_NR_AIML_air->FS_NR_AIML_Air; Rapporteur: Qualcomm->Juan Montojo, Qualcomm; Rap eMail: ->juanm@qti....;...",38.843000000000004,94,48,null,null,"Thu 06/01/22","Fri 18/07/25"]
[1009,989997,"Artificial Intelligence (AI)/Machine Learning (ML) ","AIMLsys",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-231278",null,"Alla Goldner, Oppo","v-alla.goldner@oppo.com","10/12/22: 0%->5; 3/1/24: WID:SP-221329->SP-231278","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"Fri 09/12/22","Wed 03/01/24"]
[1010,960037,"   Study on Security and Privacy of AI/ML-based Services and Applications in 5G ","FS_AIML",2,"Rel-18","S3","Tue 21/06/22","Fri 03/03/23",1,"SP-220687",null,"Marcus Wong, OPPO ","marcus.wong@oppo.com ","13/7/22: 33.898 added;; 12/9/22: 0%->5; 11/12/22: 5%->25; 17/3/23: 25%->35; 7/9/23: 35%->100",33.898000000000003,96,49,null,null,"Tue 21/06/22","Thu 07/09/23"]
[1011,940071,"   Study on 5G System Support for AI/ML-based Services ","FS_AIMLsys",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220071",null,"Alla Goldner, Oppo","v-alla.goldner@oppo.com","21/1/22: 23.700-80 added;; 12/3/22: 0%->10; 12/3/22: WID:SP-211648->SP-220071; 4/6/22: 10%->60; 12/9/22: 60%->70; 10/12/22: 70%->100; 10/12/22: FCD:12/09/2022->12/22","23.700-80",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[1012,980019,"   (Stage 2 for AIML) System Support for AI/ML-based Services","AIMLsys",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-231278",null,"Alla Goldner, Oppo","v-alla.goldner@oppo.com","10/12/22: 0%->5; 15/3/23: WID:SP-221329->SP-230095; 15/3/23: 5%->50; 8/6/23: 50%->100; 3/1/24: WID:SP-230095->SP-231278","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"Fri 09/12/22","Wed 03/01/24"]
[1013,990008,"   CT3 aspects of AIML","AIMLsys",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-230329",null,"Tangudu, Narendranath Durga, Samsung","n.tangudu@samsung.com","31/3/23: 29.543 added;6/6/23: Compl:10%->50%","29.122.29.513.29.514.29.517.29.591.29.519.29.520.29.521.29.522.29.244.29.503.29.504.29.505.29.510; 29.543",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1014,990074,"   CT4 aspects of AIML","AIMLsys",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-230329",null,"Tangudu, Narendranath Durga, Samsung","n.tangudu@samsung.com","6/6/23: Compl:0%->60%","29.122.29.513.29.514.29.517.29.591.29.519.29.520.29.521.29.522.29.244.29.503.29.504.29.505.29.510",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1015,941010,"Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN","NR_AIML_NGRAN",1,"Rel-18",null,"Mon 13/12/21","Mon 01/05/23",0.8,"RP-233441",null,"CMCC",null,"no Perf. part; compare REL-18 SI FS_NR_AIML_air; 5/4/22: WID:RP-213602->RP-220635; 2/1/24: WID:RP-220635->RP-233441",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1016,941110,"   Core part: Artificial Intelligence (AI)/Machine Learning (ML) for NG-RAN","NR_AIML_NGRAN-Core",2,"Rel-18","R3","Mon 13/12/21","Mon 01/05/23",0.8,"RP-233441","RP-232673","Fang Xie, Angelo Centonza, CMCC, Ericsson","xiefang@chinamobile.com, angelo.centonza@ericsson.com","no Perf. part; compare REL-18 SI FS_NR_AIML_air; 20/6/22: FCD:23/06/2023->23/06/2022; WID: RP-220635->RP-213602; Stat Rep: ->RP-221381; Rapporteur: CMCC->Fang Xie, Angelo Centonza, CMCC, Ericsson; Rap eMail: ->xiefang@chinamobile.com, angelo.centonza@e...",null,94,48,null,null,"Thu 06/01/22","Thu 21/09/23"]
[1017,960031,"Study on the security aspects of Artificial Intelligence (AI)/Machine Learning (ML) for the NG-RAN ","FS_NR_AIML_NGRAN_SEC",1,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220529",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","13/7/22: 33.877 added; 17/8/22: WID in SP-220529 marked as withdrawn in SA#96 tdoc list; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70. 030/6/23: \"undeleted\" as per Mirko+Vlasios email; 7/9/23: 70%->100",33.877000000000002,96,49,null,null,"Thu 02/06/22","Thu 07/09/23"]
[1018,940039,"Study on AI/ML management ","FS_AIML_MGMT",1,"Rel-18","S5","Mon 13/12/21","Tue 06/06/23",1,"SP-211443",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","7/1/22: 28.908 added;; 4/6/22: 0%->10; 12/9/22: 10%->55; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 55%->85; 11/12/22: FCD:10/03/2023->/23; 8/6/23: 85%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 85%->100",28.908000000000001,94,48,null,null,"Mon 13/12/21","Thu 08/06/23"]
[1019,990119,"AI/ML management ","AIML_MGT",1,"Rel-18","S5","Fri 17/03/23","Sun 03/03/24",1,"SP-230335",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 8/6/23: 0%->20; 7/9/23: 20%->35; 14/3/24: 35%->100; 14/3/24: FCD:12/12/2023->/24","28.105; 28.552; 32.425; 28.554; 28.541 ",99,50,null,null,"Fri 17/03/23","Thu 14/03/24"]
[1020,1020023,"NEF Charging enhancement to support AI/ML in 5GS ","AIMLsysNEF_CH",1,"Rel-18","S5","Thu 07/12/23","Tue 12/12/23",1,"SP-231706",null,"Alla Goldner, OPPO ","v-alla.goldner@oppo.com ","; 14/3/24: 0%->100; 14/3/24: 100%->100","32.254; 32.291 ",102,52,null,null,"Thu 07/12/23","Thu 14/03/24"]
[1021,0,"Rel-18 Multicast and Broadcast Services (MBS)","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1022,940099,"Enhancements of NR Multicast and Broadcast Services","NR_MBS_enh",1,"Rel-18",null,"Mon 13/12/21","Fri 12/12/25",0.66,"RP-232993",null,"CATT",null,"no Perf. part; compare REL-17 WI NR_MBS-Core; 12/7/22: WID:RP-213568->RP-221458; 6/10/23: WID:RP-221458->RP-231829; 2/1/24: WID:RP-231829->RP-232993",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1023,940199,"   Core part: Enhancements of NR Multicast and Broadcast Services","NR_MBS_enh-Core",2,"Rel-18","R2","Mon 13/12/21","Tue 12/12/23",1,"RP-232993","RP-232992","Rui Zhou, CATT","zhourui@catt.cn","no Perf. part; compare REL-17 WI NR_MBS-Core; 22/3/22: Stat Rep: ->RP-220734 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: Stat Rep: RP-220734->RP-221459; 20/6/22: Rapporteur: CATT->Erlin Zeng, CATT; Rap eMail: ->erlin.zeng@catt.cn13/7/22: FCD:23...;...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1024,1060077,"   UE Conformance - Enhancements of NR Multicast and Broadcast Services including CT aspects ","NR_MBS_enh_5MBS_Ph2-UEConTest",2,"Rel-18","R5","Thu 06/03/25","Fri 12/12/25",0.05,"RP-243116","RP-251630","CATT ",null,"6/3/25: Compl:0%->5%; Stat Rep: ->RP-250503; ; 3/4/25: WID:RP-243116->RP-250504; 6/6/25: FCD:Thu 13/11/25->Fri 12/12/25; WID: RP-250504->RP-243116; Stat Rep: RP-250503->RP-251630; ",null,106,54,null,null,"Fri 24/01/25","Fri 06/06/25"]
[1025,989999,"5G multicast-broadcast services Phase 2","5MBS_Ph2",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-221131",null,"Meng Li, Huawei, Huawei ","raymond.limeng@huawei.com ",null,"23.501; 23.502; 23.247 ",98,50,null,null,"Fri 09/12/22","NA"]
[1026,940067,"   Study on architectural enhancements for 5G multicast-broadcast services Phase 2 ","FS_5MBS_Ph2",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220072",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","21/1/22: 23.700-47 added;; 12/3/22: 0%->15; 12/3/22: WID:SP-211645->SP-220072; 4/6/22: 15%->55; 12/9/22: 55%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-47",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[1027,980013,"   (Stage 2 of 5MBS_Ph2) Architectural enhancements for 5G multicast-broadcast services Phase 2","5MBS_Ph2",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-230099",null,"Meng Li, Huawei, Huawei ","raymond.limeng@huawei.com ","; 15/3/23: WID:SP-221131->SP-230099; 15/3/23: 0%->75; 8/6/23: 75%->100","23.501; 23.502; 23.247 ",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[1028,990001,"   CT1 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-232031",null,"Rezagah, Roya, Huawei","roya.rezagah@huawei.com","6/6/23: Compl:0%->65%; 30/6/23: WID:CP-230023->CP-231024. 03/24: rapporteur changed (was giorgi.gulbani@huawei.com)",null,99,50,null,null,"Fri 09/12/22","Fri 30/06/23"]
[1029,990076,"   CT3 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-232031",null,"Rezagah, Roya, Huawei","roya.rezagah@huawei.com","; 9/6/23: 15%->40",null,99,50,null,null,"Fri 09/12/22","Fri 09/06/23"]
[1030,990077,"   CT4 aspects for 5MBS_Ph2","5MBS_Ph2",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-232031",null,"Rezagah, Roya, Huawei","roya.rezagah@huawei.com","; 17/3/23: 5%->206/6/23: Compl:20%->70%",null,99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1031,1000005,"   Security Enhancements for 5G Multicast-Broadcast Services Phase 2 ","5MBS_Ph2",2,"Rel-18","S3","Thu 08/06/23","Sat 09/09/23",1,"SP-230559",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","; 15/3/24: 0%->100",33.500999999999998,100,51,null,null,"Thu 08/06/23","Fri 15/03/24"]
[1032,960041,"   Study on security enhancements for 5G multicast-broadcast services Phase 2 ","FS_5MBS_SEC_Ph2",2,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220539",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","13/7/22: 33.883 added;; 12/9/22: 0%->12; 11/12/22: 12%->50; 17/3/23: 50%->55; 8/6/23: 55%->100",33.883000000000003,96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[1033,920071,"New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 ","LTE_terr_bcast_bands_part2",1,"Rel-18",null,"Tue 15/06/21","Fri 12/12/25",0.62,"RP-223378",null,"EBU ",null,"RAN4 part for WI LTE_terr_bcast_bands_part1-Core; REL--independent starting from REL-17; no Perf. part ; 5/4/22: WID:RP-211145->RP-220518; 23/9/22: WID:RP-220518->RP-222224; 9/1/23: WID:RP-222224->RP-223378",null,92,47,null,null,"Fri 02/07/21","Mon 09/01/23"]
[1034,920171,"   Core part: New bands and bandwidth allocation for 5G terrestrial broadcast - part 2 ","LTE_terr_bcast_bands_part2-Core",2,"Rel-18","R4","Tue 15/06/21","Fri 08/09/23",1,"RP-232590","RP-235288","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","RAN4 part for WI LTE_terr_bcast_bands_part1-Core; REL--independent starting from REL-17; no Perf. part ; 13/9/21: CD:Wed 15/03/23->Wed 23/03/22 ; 22/3/22: CD:23/03/2022->12/06/2023; 22/3/22: Stat Rep: RP ; 6/6/22: CD:12/06/2023->23/0 ; 20/6/22: Rappor...",36.792000000000002,92,47,null,null,"Fri 02/07/21","Fri 06/10/23"]
[1035,1050131,"   UE Conformance - New bands and bandwidth allocation for LTE based 5G terrestrial broadcast ","LTE_terr_bcast_bands_part2-UEConTest",2,"Rel-18","R5","Mon 09/09/24","Fri 12/12/25",0.15,"RP-242026","RP-251233","Qualcomm ",null,"6/12/24: Compl:0%->5%; Stat Rep: ->RP-242900; ; 6/3/25: FCD:24/07/2025->12/12/2025; Compl:5%->15%; Stat Rep: RP-242900->RP-250398; ; 6/6/25: Stat Rep: RP-250398->RP-251233; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[1036,990078,"UE pre-configuration for 5MBS","UEConfig5MBS",1,"Rel-18",null,"Fri 03/03/23","Sun 03/03/24",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com",null,31.102,92,47,null,null,"Fri 02/07/21","Mon 09/01/23"]
[1037,990022,"   CT1 aspects of UEConfig5MBS","UEConfig5MBS",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com","6/6/23: Compl:85%->95%6/6/23: CD:24/03/2023->03/03/2024",31.102,92,47,null,null,"Fri 02/07/21","Tue 06/06/23"]
[1038,990079,"   CT6 aspects of UEConfig5MBS","UEConfig5MBS",2,"Rel-18","C6","Fri 03/03/23","Fri 03/03/23",1,"CP-230201",null,"Herrero-Veron, Christian(Huawei)","Christian.Herrero@huawei.com",null,31.102,92,47,null,null,"Fri 02/07/21","Mon 09/01/23"]
[1039,0,"See also MCOver5MBS under Mission Critical","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1040,0,"See also TEI18_MBS4V2X under Autonomous Driving","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1041,0,"Rel-18 Slice","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1042,910095,"Study on 5G NR UE full stack testing for Network Slicing ","FS_NR_Slice_Test",1,"Rel-18","R5","Fri 12/03/21","Thu 22/09/22",1,"RP-211976","RP-221363","Dan SONG, Yu SHI, CMCC, CU","songdan@chinamobile.com, shiyu19@chinaunicom.cn","TR 38.9XX; compare RAN2 REL-17 SI FS_NR_slice; related to REL-15 WI 5GS_Ph1 and REL-16 WI eNS) ; 2/7/21: 0%->10; 13/9/21: Compl:10%->28%; ; 29/9/21: WID:RP-210371->RP-211977; 04/22: Rel-17->Rel-18; 20/6/22: FCD:22/03/2022->22/09/2022; Compl:28%->82%; ...",null,91,46,null,null,"Wed 07/04/21","Fri 23/09/22"]
[1043,910026,"Study on network slice management capability exposure ","FS_NSCE",1,"Rel-18","S5","Thu 18/03/21","Tue 06/06/23",1,"SP-220350",null,"Xiaobo Yu, Alibaba Group ","shibo.yxb@alibaba-inc.com ","; 11/6/21: 0%->5; 11/6/21: FCD:Fri 10/12/->12/21; 13/9/21: 5%->25; 13/12/21: 25%->65; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 22/3/22: WID:SP-210131->SP-220350; 4/6/22: 65%->80; 4/6/22: FCD:11/03/2022->03/23; 12/9/22: 80%->83; 12/9/2...","New ",91,46,null,null,"Thu 18/03/21","Thu 08/06/23"]
[1044,910038,"Enhanced Access to and Support of Network Slice ","EASNS",1,"Rel-18",null,"Thu 25/06/20","Sun 03/03/24",1,"SP-210210",null,"Chun, SungDuck, LG Electronics Inc. ","sungduck.chun@lge.com ",null,22.260999999999999,91,46,null,null,"Thu 18/03/21","NA"]
[1045,880035,"   Study on EASNS","FS_EASNS",2,"Rel-18","S1","Thu 25/06/20","Wed 17/03/21",1,"SP-200571",null,"Chun, SungDuck, LG Electronics Inc","sungduck.chun@lge.com ","12/9/20: 0%->20; 25/9/20: 22.835 added;; 5/12/20: 20%->60; 19/3/21: 60%->85; 11/6/21: 85%->100",22.835000000000001,88,45,null,null,"Thu 25/06/20","Fri 11/06/21"]
[1046,910032,"   Stage 1 for EASNS","EASNS",2,"Rel-18","S1","Thu 18/03/21","Fri 10/09/21",1,"SP-210210",null,"Chun, SungDuck, LG Electronics Inc. ","sungduck.chun@lge.com ","; 11/6/21: 0%->100",22.260999999999999,91,46,null,null,"Thu 18/03/21","Fri 11/06/21"]
[1047,1000023,"   Stopped – CT1 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C1","Wed 07/06/23","Sun 03/03/24",1,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ","8/8/23: acronym changed SbPS to PLMNsel_NS","23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,51,"CP-102",null,"Wed 07/06/23","NA"]
[1048,1000044,"   Stopped – CT4 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C4","Wed 07/06/23","Sun 03/03/24",1,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ","stopped","23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,51,"CP-102",null,"Wed 07/06/23","NA"]
[1049,1000045,"   Stopped – CT6 aspects of Slice-based PLMN Selection ","PLMNsel_NS",2,"Rel-18","C6","Wed 07/06/23","Sun 03/03/24",1,"CP-232165",null,"Shuang Liang, ZTE ","liang.shuang3@zte.com.cn ","stopped","23.122; 24.501; 29.503; 29.504; 29.505; 29.509; 29.544; 29.550; 31.102; 31.111 ",100,51,"CP-102",null,"Wed 07/06/23","NA"]
[1050,980127,"Network Slicing Phase 3 ","eNS_Ph3",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-221135",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,"23.501; 23.502; 23.503 ",98,50,null,null,"Fri 09/12/22","NA"]
[1051,940063,"   Study on Enhancement of Network Slicing Phase 3 ","FS_eNS_Ph3",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220073",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","21/1/22: 23.700-41 added;; 21/1/22: 23.700-17 added;; 12/3/22: 0%->5; 12/3/22: WID:SP-211641->SP-220073; 4/6/22: 5%->50; 12/9/22: 50%->70; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 70%->100","23.700-41; 23.700-17",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[1052,960029,"   Study on enhanced security for network slicing Phase 3 ","FS_eNS_Ph3",2,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220527",null,"Zander Lei, Huawei ","lei.zhongding@huawei.com ","13/7/22: 33.886 added;; 11/12/22: 0%->15; 17/3/23: 15%->50; 8/6/23: 50%->90; 15/3/24: 90%->100",33.886000000000003,96,49,null,null,"Thu 02/06/22","Fri 15/03/24"]
[1053,980017,"   Stage 2 of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-230104",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","; 15/3/23: WID:SP-221327->SP-230104; 15/3/23: 0%->50; 8/6/23: 50%->100","23.501; 23.502; 23.503 ",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[1054,990015,"   CT1 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","6/6/23: Compl:0%->40%","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1055,990081,"   CT3 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","; 9/6/23: 0%->30","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"Fri 09/12/22","Fri 09/06/23"]
[1056,990082,"   CT4 aspects of Network Slicing Phase 3 ","eNS_Ph3",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-230194",null,"Hannah Wang, ZTE","wang.menghan@zte.com.cn","6/6/23: Compl:5%->45%","24.501.29.244.29.502.29.503.29.510.29.531.29.536.29.507.29.512.29.513.29.519.29.522",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1057,1030024,"   Network Slice Replacement charging ","eNS_Ph3_CH",2,"Rel-18","S5","Fri 02/02/24","Sun 03/03/24",1,"SP-240475",null,"Maryse Gardella, MATRIXX Software, ","Maryse dot Gardella at Matrixx dot com) ","; 2/4/24: 0%->100","32.255; 32.256; 32.291; 32.298 ",103,52,null,null,"Thu 14/03/24","Tue 02/04/24"]
[1058,991037,"Network Slicing Phase 3: NR aspects ","eNS_Ph3-NR",1,"Rel-18","R3","Fri 03/03/23","Tue 12/12/23",1,"RP-232793",null,"ZTE ",null,"2/1/24: WID:RP-230787->RP-232793",null,99,50,null,null,"Wed 29/03/23","Tue 02/01/24"]
[1059,991137,"   Core part: Network Slicing Phase 3: NR aspects ","eNS_Ph3-NR-Core",2,"Rel-18","R3","Fri 03/03/23","Tue 12/12/23",1,"RP-232793","RP-232866","Dapeng Li, ZTE","Li.dapeng@zte.com.cn","; 7/6/23: Compl:0%->30%; 6/9/23: Compl:30%->70%; WID: RP-230787->RP-231396; Stat Rep: ->RP-231889; Rapporteur: ZTE->Dapeng Li, ZTE; Rap eMail: ->Li.dapeng@zte.com.cn; ; 8/12/23: Compl:70%->100%; Stat Rep: RP-231889->RP-232866; ",null,99,50,null,null,"Wed 29/03/23","Fri 08/12/23"]
[1060,940045,"Network slicing provisioning rules ","NSRULE",1,"Rel-18","S5","Fri 10/12/21","Tue 12/12/23",1,"SP-211449",null,"Robert Petersen, Ericsson ","robert.petersen@ericsson.com ","; 4/6/22: 0%->35; 12/9/22: 35%->45; 12/9/22: FCD:12/09/2022->06/23; 11/12/22: 45%->55; 17/3/23: 55%->60; 8/6/23: 60%->60; 8/6/23: FCD:09/06/2023->12/24; 7/9/23: 60%->70; 7/9/23: FCD:12/12/2024->12/23; 8/12/23: 70%->100","28.531; 28.541 ",94,48,null,null,"Fri 10/12/21","Fri 08/12/23"]
[1061,950039,"Study on intent-driven management for network slicing ","FS_NETSLICE_IDMS",1,"Rel-18","S5","Thu 10/03/22","Tue 12/12/23",1,"SP-220278",null,"Jan Groenendijk , Ericsson ","Jan.Groenendijk@ericsson.com ","5/4/22: 28.836 added;; 11/9/22: FCD:12/09/2022->06/23; 12/9/22: 0%->40; 12/9/22: FCD:12/06/2023->12/22; 11/12/22: 40%->50; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 50%->85; 8/6/23: FCD:06/06/2023->/23; 7/9/23: 85%->85; 7/9/23: FCD:09/09/2023->12/23; 8/12/23",28.835999999999999,95,48,null,null,"Thu 10/03/22","Fri 08/12/23"]
[1062,990030,"Intent driven Management Service for Mobile Network phase 2 ","IDMS_MN_ph2",1,"Rel-18","S5","Thu 16/03/23","Tue 12/12/23",1,"SP-230180",null,"Xu Ruiyue, Huawei ","Xuruiyue@huawei.com ","; 8/6/23: 0%->40; 8/6/23: 40%->; 7/9/23: 40%->75; 8/12/23: 75%->100; 4/1/24: 28.914 added;","28.312 ; 28.914",99,50,null,null,"Thu 16/03/23","Thu 04/01/24"]
[1063,910023,"Study on enhanced security for network slicing Phase 2 ","FS_eNS2_SEC",1,"Rel-18","S3","Thu 18/03/21","Fri 10/12/21",1,"SP-210106",null,"Zander Lei, Huawei ","lei.zhongding@huawei.com ","; 19/3/21: 0%->10; 9/4/21: FCD:11/06/2021->09/21; 11/6/21: 10%->15; 11/6/21: FCD:Wed 08/09/->12/21; 2/7/21: 33.874 added;; 13/9/21: 15%->30; 13/3/22: Rel-17->Rel-18; 4/6/22: 30%->100","New ; 33.874",91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1064,960048,"Study on Media Streaming aspects of Network Slicing Phase 2","FS_MS_NS_Ph2",1,"Rel-18","S4","Wed 15/06/22","Tue 12/12/23",1,"SP-220675",null,"Prakash Kolan, samsung ","p.kolan@samsung.com ","3/8/22: 26.941 added; 17/8/22: FS_eNS_Ph3->FS_MS_NS_Ph2; WID:SP-220615->SP-220675; 12/9/22: 0%->15; 11/12/22: 15%->20; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 20%->25; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 25%->40; 7/9/23: 40%->65; 8/12/23: 65%->100",26.940999999999999,96,49,null,null,"Fri 03/06/22","Fri 08/12/23"]
[1065,940013,"Enhanced security for Phase 2 network slicing ","eNS2_SEC",1,"Rel-18","S3","Fri 10/12/21","Fri 11/03/22",1,"SP-211361",null,"Lei, Zander, Huawei ","lei.zhongding@huawei.com ","12/3/22: 0%->70; 13/3/22: Rel-17->Rel-18; 4/6/22: 70%->100","33.501; ",94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[1066,910022,"Study on Network Slice Capability Exposure for Application Layer Enablement ","FS_NSCALE",1,"Rel-18","S6","Thu 18/03/21","Mon 12/09/22",1,"SP-211509",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","2/7/21: 23.700-99 added;; 13/9/21: 0%->25; 13/12/21: 25%->55; 13/12/21: FCD:Fri 11/03/->06/22; 13/12/21: WID:SP-210177->SP-211509; 12/3/22: 55%->70; 4/6/22: 70%->85; 12/9/22: 85%->95; 12/9/22: FCD:10/06/2022->09/22; 11/12/22: 95%->100","23.700-99",91,46,null,null,"Thu 18/03/21","Sun 11/12/22"]
[1067,1020049,"Network Slice Capability Exposure for Application Layer Enablement ","NSCALE",1,"Rel-18",null,"Thu 02/06/22","Fri 15/03/24",1,"SP-220470",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","; 13/7/22: 23.435 added;; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70; 8/6/23: 70%->100","23.434 ; 23.435",96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[1068,960013,"   (Stage 2 of NSCALE) Network Slice Capability Exposure for Application Layer Enablement","NSCALE",2,"Rel-18","S6","Thu 02/06/22","Fri 03/03/23",1,"SP-220470",null,"Zheng, Shaowen, CMCC ","zhengshaowen@chinamobile.com ","; 13/7/22: 23.435 added;; 12/9/22: 0%->10; 11/12/22: 10%->30; 17/3/23: 30%->70; 8/6/23: 70%->100","23.434 ; 23.435",96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[1069,1020050,"   CT1 aspects of NSCALE","NSCALE",2,"Rel-18","C1","Thu 02/06/22","Sun 03/03/24",1,"CP-233310",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,24.548999999999999,96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[1070,1020006,"   CT3 aspects of NSCALE","NSCALE",2,"Rel-18","C3","Thu 02/06/22","Sun 03/03/24",1,"CP-233310",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,"29.222, 29.520, 29.522, 29.549",96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[1071,1020046,"   CT4 aspects of NSCALE","NSCALE",2,"Rel-18","C4","Thu 02/06/22","Fri 15/03/24",1,"CP-233310",null,"Huang Zhenning, China Mobile","huangzhenning@chinamobile.com",null,29.536000000000001,96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[1072,960005,"Study on new UICC application for network slice-specific authentication and authorization (NSSAA)","FS_NS_Slice-USIM",1,"Rel-18","C6","Fri 03/06/22","Sat 09/09/23",1,"CP-221186",null,"COLLET, Hervé, Thales ","herve.collet@thalesgroup.com ","13/7/22: 31.826 added;",31.826000000000001,96,49,null,null,"Fri 03/06/22","Wed 13/07/22"]
[1073,900023,"Study on Charging Aspects for Network Slicing Phase 2 ","FS_NETSLICE_CH_Ph2",1,"Rel-18","S5","Tue 12/01/21","Fri 03/03/23",1,"SP-201082",null,"Matrixx, Gerald Görmer ","Gerald dot Goermer at Matrixx dot com ","21/3/21: 0%->15; 13/9/21: 15%->50; 13/9/21: FCD:Fri 10/09/->12/21; 12/3/22: 50%->70; 4/6/22: 70%->75; 4/6/22: FCD:10/12/2021->03/23; 21/6/22: 75%->100. 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->85; 11/12/22: 85...",null,90,46,null,null,"Tue 12/01/21","Fri 17/03/23"]
[1074,980025,"Charging Aspects of Network Slicing Phase 2 ","NETSLICE_CH_Ph2",1,"Rel-18","S5","Mon 12/12/22","Sun 03/03/24",1,"SP-231448",null,"Gerald Görmer, MATRIXX Software ","Gerald dot Goermer at Matrixx dot com ","; 16/3/23: FCD:09/09/2023->12/20; 16/3/23: WID:SP-221159->SP-230176; 17/3/23: 0%->5; 17/3/23: 28.203 added;; 8/6/23: 5%->40; 7/9/23: 40%->50; 8/12/23: 50%->75; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-230176->SP-231448; 14/3/24: 75%->100","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.203",98,50,null,null,"Fri 09/12/22","Thu 14/03/24"]
[1075,1000002,"Enhancement of Network Slicing UICC application for network slice-specific authentication and authorization ","eNS_UICC",1,"Rel-18","C6","Fri 30/06/23","Sun 03/03/24",1,"CP-231351",null,"COLLET, Hervé, Thales ","herve.collet@thalesgroup.com ","21/9/23: 31.105 added;",31.105,100,51,null,null,"Fri 30/06/23","Thu 21/09/23"]
[1076,0,"Rel-18 eXtended, Augmented and Virtual Reality (XR, AR, VR), immersive ","-",1,"Rel-18",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1077,981039,"XR (eXtended Reality) enhancements for NR ","NR_XR_enh",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.89,"RP-232778",null,"Nokia ",null,"29/3/23: WID:RP-223502->RP-230786; 2/1/24: WID:RP-230786->RP-232778",null,98,50,null,null,"Mon 09/01/23","Tue 02/01/24"]
[1078,981139,"   Core part: XR (eXtended Reality) enhancements for NR ","NR_XR_enh-Core",2,"Rel-18","R2","Tue 13/12/22","Tue 12/12/23",1,"RP-223502","RP-232779","Benoist S bire, Nokia","benoist.sebire@nokia.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230277; Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com; 31/3/23: WID: RP-230786->RP-223502; Stat Rep: RP-230277->RP-230785; ;...; 6/9/23: Compl:45%->68%; Stat Rep: RP-230785->RP-2...",null,98,50,null,null,"Mon 09/01/23","Fri 08/12/23"]
[1079,940087,"   Study on XR (eXtended Reality) enhancements for NR","FS_NR_XR_enh",2,"Rel-18","R2","Mon 13/12/21","Fri 03/03/23",1,"RP-220285","RP-230276","Benoist S bire, Nokia","benoist.sebire@nokia.com","TR 38.8xx; basic XR functionality introduced in REL-15 WI NR_newRAT; 22/3/22: Stat Rep: ->RP-220511; 5/4/22: WID:RP-213587->RP-220285 6/6 ; 20/6/22: Rapporteur: Nokia->Benoist S bire, Nokia; Rap eMail: ->benoist.sebire@nokia.com13/7/22: 38.835 add...;...",38.835000000000001,94,48,null,null,"Thu 06/01/22","Fri 17/03/23"]
[1080,1030063,"   UE Conformance - XR (eXtended Reality) enhancements for NR plus CT1 aspects ","NR_XR_enh_plus_CT1-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.8,"RP-241588","RP-250986","Nokia ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-240936; ; 23/7/24: WID:RP-240088->RP-241588; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->40%; Stat Rep: RP-240936->RP-241790; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:40%->60%; Stat Rep: RP-241790->RP-242607; ; ",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[1081,990110,"Architecture Enhancements for XR (Extended Reality) and media service","XRM",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-221326",null,"Dan WANG, China Mobile","wangdanyjy@chinamobile.com ",null,"23.501; 23.502; 23.503 ",99,50,null,null,"Fri 09/12/22","NA"]
[1082,940068,"   Study on architecture enhancement for XR and media services ","FS_XRM",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220705",null,"Dan Wang, China Mobile ","wangdanyjy@chinamobile.com ","21/1/22: 23.700-60 added;; 12/3/22: 0%->15; 4/6/22: 15%->40; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211646->SP-220705; 12/9/22: 40%->75; 10/12/22: 75%->100","23.700-60",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[1083,980016,"   (Stage 2 for XRM) Architecture Enhancements for XR (Extended Reality) and media service","XRM",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-230092",null,"Dan WANG, China Mobile","wangdanyjy@chinamobile.com ","15/3/23: WID:SP-221326->SP-230092; 15/3/23: 0%->55; 8/6/23: 55%->98; 7/9/23: 98%->100","23.501; 23.502; 23.503 ",98,50,null,null,"Fri 09/12/22","Thu 07/09/23"]
[1084,1030048,"   CT1 aspects of XRM","XRM",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-240081",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","6/6/23: Compl:20%->65%6/6/23: WID: CP-230115->CP-231196; 2/4/24: 0%->98","29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564",99,50,null,null,"Fri 09/12/22","Tue 02/04/24"]
[1085,990006,"   CT3 aspects of XRM","XRM",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-240081",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","6/6/23: Compl:20%->65%6/6/23: WID: CP-230115->CP-231196","29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1086,990084,"   CT4 aspects of XRM","XRM",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-240081",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","6/6/23: Compl:0%->65%6/6/23: WID: CP-230115->CP-231196","29.122.29.508.29.512.29.514.29.522.29.591.29.281.29.244.29.564",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1087,950012,"Study on immersive Real-time Communication for WebRTC Phase 2","FS_eiRTCW",1,"Rel-18","S4","Thu 10/03/22","Sun 03/03/24",1,"SP-230166",null,"Yoshihiro INOUE, NTT","Yoshihiro.inoue@ntt-at.co.jp","4/6/22: 0%->10; 17/8/22: FS_iRTCW_Ph2->FS_eiRTCW ; 12/9/22: 10%->30; 16/3/23: WID:SP-220239->SP-230166; 16/3/23: FCD:06/06/2023->3/3/24. Rapporteur changed from Naotaka MORITA, NTT .; 17/3/23: 30%->35; 17/3/23: FCD:03/03/2024->/24; 8/6/23: 35%->45; 7/9...",26.93,95,48,null,null,"Thu 10/03/22","Thu 14/03/24"]
[1088,950014,"Immersive Real-time Communication for WebRTC ","iRTCW",1,"Rel-18","S4","Tue 15/03/22","Thu 06/06/24",1,"SP-230977",null,"Kyunghun Jung, Facebook ","kyunghun@fb.com ","5/4/22: 26.113 added;; 4/6/22: 0%->5; 12/9/22: 5%->10; 11/12/22: 10%->20; 11/12/22: WID:SP-220241->SP-221032; 17/3/23: 20%->30; 8/6/23: 30%->55; 7/9/23: WID:SP-221032->SP-230977; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 55%->60; 14/3/24: FCD:03/03/2024->/...",26.113,95,48,null,null,"Thu 10/03/22","Thu 13/06/24"]
[1089,950013,"Study on Smartly Tethering AR Glasses ","FS_SmarTAR",1,"Rel-18","S4","Thu 10/03/22","Tue 06/06/23",1,"SP-220240",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ","; 5/4/22: 26.806 added;; 4/6/22: 0%->30; 12/9/22: 30%->40; 12/9/22: FCD:10/03/2023->03/23; 11/12/22: 40%->60; 17/3/23: 60%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100","26.998 ; 26.806",95,48,null,null,"Thu 10/03/22","Thu 08/06/23"]
[1090,950015,"Media Capabilities for Augmented Reality ","MeCAR",1,"Rel-18","S4","Thu 10/03/22","Sun 03/03/24",1,"SP-220242",null,"Emmanuel Thomas, Xiaomi ","thomase@xiaomi.com ","; 5/4/22: 26.119 added;; 4/6/22: 0%->8; 12/9/22: 8%->15; 11/12/22: 15%->30; 11/12/22: FCD:10/03/2023->12/23; 17/3/23: 30%->40; 8/6/23: 40%->60; 7/9/23: 60%->65; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 65%->80; 8/12/23: FCD:03/03/2024->/2024; 14/3/24: 80%->","26.511; 26.117; 26.925; 26.XXX ; 26.119",95,48,null,null,"Thu 10/03/22","Thu 14/03/24"]
[1091,960042,"IMS-based AR Conversational Services ","IBACS",1,"Rel-18","S4","Fri 03/06/22","Thu 06/06/24",1,"SP-230165",null,"Gunkel, Simon, KPN N.V. ","Simon.Gunkel@tno.nl ","3/8/22: 26.264 added; 17/8/22: IMS4AR->IBACS; 17/8/22: WID:SP-220609->SP-220668; 12/9/22: 0%->5; 11/12/22: 5%->15; 11/12/22: FCD:08/12/2023->12/23; 16/3/23: WID:SP-220668->SP-230165; 17/3/23: 15%->20; 8/6/23: 20%->30; 8/6/23: FCD:12/12/2023->03/20; 8/1...",26.263999999999999,96,49,null,null,"Fri 03/06/22","Thu 13/06/24"]
[1092,960044,"Generic architecture for RT and AR/MR ","GA4RTAR",1,"Rel-18","S4","Fri 03/06/22","Tue 06/06/23",1,"SP-220672",null,"Hakju Ryan Lee, Samsung ","hakju00.lee@samsung.com ","17/8/22: GA4RTARMR-> GA4RTAR; 17/8/22: WID:SP-220611->SP-220672; 12/9/22: 0%->25; 11/12/22: 25%->60; 11/12/22: FCD:08/12/2023->03/23; 17/3/23: 60%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100",null,96,49,null,null,"Fri 03/06/22","Thu 08/06/23"]
[1093,960046,"Real-time Transport Protocol Configurations ","5G_RTP",1,"Rel-18","S4","Fri 03/06/22","Sun 03/03/24",1,"SP-230541",null,"Igor Curcio, Nokia Corporation ","igor.curcio@nokia.com ","3/8/22: 26.522 added; 17/8/22: RTPconfig->5G_RTP; 12/9/22: 0%->3; 11/12/22: 3%->7; 11/12/22: FCD:08/06/2023->/23; 17/3/23: 7%->15; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 15%->35; 8/6/23: FCD:12/12/2023->03/20; 8/6/23: WID:SP-220613->SP-230541; 7/9/23:...",26.521999999999998,96,49,null,null,"Fri 03/06/22","Thu 14/03/24"]
[1094,830005,"Terminal Audio quality performance and Test methods for Immersive Audio Services","ATIAS",1,"Rel-18","S4","Thu 07/03/19","Thu 06/06/24",1,"SP-190040",null,"Stéphane Ragot, Orange","stephane.ragot@orange.com ","31/5/19: 0%->10; 25/3/20: 10%->15; 5/12/20: 15%->20; 5/12/20: FCD:04/12/2020->12/20. 12/21: Rel-17->Rel-18; 4/6/22: 20%->; 11/12/22: 20%->25; 11/12/22: FCD:02/12/2022->12/23; 17/3/23: 25%->30; 8/6/23: 30%->40; 7/9/23: 40%->50; 7/9/23: FCD:12/12/2023->/...","26.260; new",83,42,null,null,"Thu 14/03/19","Thu 13/06/24"]
[1095,1030047,"EVS Codec Extension for Immersive Voice and Audio Services","IVAS_Codec",1,"Rel-18",null,"Fri 08/09/17","Thu 06/06/24",1,"SP-220608",null,"Bin Wang, Huawei Technologies Co Ltd","binbin.wang@huawei.com","15/12/17: 0%->5¦16/3/18: 5%->10¦7/6/18: 10%->15¦10/9/18: 15%->20¦7/3/19: 20%->25; 31/5/19: 25%->30; 13/9/19: FCD:11/12/2020->06/20; 13/9/19: 30%->26; 6/12/19: 26%->27; 5/12…; 12/21: Rel-17->Rel-18; 4/6/22: 30%->35; 12/9/22: 35%->40; 11/12/22: 40%->45; ...","26.114; new; 26.258; 26.256; 26.255; 26.254; 26.253; 26.251; 26.252; 26.250; 26.997",77,39,null,null,"Fri 08/09/17","Fri 08/12/23"]
[1096,770024,"   EVS Codec Extension for Immersive Voice and Audio Services","IVAS_Codec",2,"Rel-18","S4","Fri 08/09/17","Thu 06/06/24",1,"SP-220608",null,"Bin Wang, Huawei Technologies Co Ltd","binbin.wang@huawei.com","15/12/17: 0%->5¦16/3/18: 5%->10¦7/6/18: 10%->15¦10/9/18: 15%->20¦7/3/19: 20%->25; 31/5/19: 25%->30; 13/9/19: FCD:11/12/2020->06/20; 13/9/19: 30%->26; 6/12/19: 26%->27; 5/12…; 12/21: Rel-17->Rel-18; 4/6/22: 30%->35; 12/9/22: 35%->40; 11/12/22: 40%->45; ...","26.114; new; 26.258; 26.256; 26.255; 26.254; 26.253; 26.251; 26.252; 26.250; 26.997",77,39,null,null,"Fri 08/09/17","Thu 13/06/24"]
[1097,1030025,"   CT3 aspects of IVAS_Codec","IVAS_Codec",2,"Rel-18","C3","Sun 03/03/24","Thu 06/06/24",1,"CP-240021",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,"23.333, 29.333, 23.334, 29.334, 29.162, 29.238, 29.163, 29.332, 29.292, 29.232, 24.229",77,39,null,null,"Fri 08/09/17","Fri 08/12/23"]
[1098,1030001,"   CT4 aspects of IVAS_Codec","IVAS_Codec",2,"Rel-18","C4","Sun 03/03/24","Thu 06/06/24",1,"CP-240021",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,"23.333, 29.333, 23.334, 29.334, 29.162, 29.238, 29.163, 29.332, 29.292, 29.232, 24.229",77,39,null,null,"Fri 08/09/17","Fri 08/12/23"]
[1099,990025,"Immersive Audio for Split Rendering Scenarios ","ISAR",1,"Rel-18","S4","Thu 16/03/23","Thu 06/06/24",1,"SP-231291",null,"Stefan Bruhn, Dolby Laboratories Inc ","stefan.bruhn@dolby.com ","; 8/6/23: 0%->10; 8/6/23: 26.566 added;; 8/6/23: 26.866 added;; 8/6/23: 26.865 added;; 7/9/23: 10%->15; 8/12/23: 15%->25; 8/12/23: WID:SP-230167->SP-231291; 14/3/24: 25%->35; 14/3/24: FCD:03/03/2024->/24; 3/4/24: 26.249 added; 26.996 added;; 13/6/24: 35%","26.119 ; 26.566; 26.866; 26.865; 26.249; 26.996",99,50,null,null,"Thu 16/03/23","Thu 13/06/24"]
[1100,960045,"Split Rendering Media Service Enabler ","SR_MSE",1,"Rel-18","S4","Fri 03/06/22","Thu 06/06/24",1,"SP-231291",null,"Bouazizi, Imed, Qualcomm Incorporated ","bouazizi@qti.qualcomm.com ","3/8/22: 26.565 added;; 17/8/22: WID:SP-220612->SP-220685; 12/9/22: 0%->5; 11/12/22: 5%->15; 11/12/22: FCD:08/12/2023->09/23; 17/3/23: 15%->25; 17/3/23: FCD:09/09/2023->12/23; 8/6/23: 25%->40; 8/6/23: FCD:12/12/2023->03/20; 7/9/23: 40%->50; 8/12/23: 50%...",26.565000000000001,96,49,null,null,"Fri 03/06/22","Thu 13/06/24"]
[1101,960049,"Study on AR and MR QoE Metrics ","FS_ARMRQoE",1,"Rel-18","S4","Fri 03/06/22","Sun 03/03/24",1,"SP-220708",null,"Shuai Gao, chinaunicom ","gaos30@chinaunicom.cn ","13/7/22: 26.812 added;; 17/8/22: WID:SP-220616->SP-220708; 12/9/22: 0%->5; 11/12/22: 5%->10; 17/3/23: 10%->15; 8/6/23: 15%->27; 7/9/23: 27%->50; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 50%->65; 14/3/24: 65%->100",26.812000000000001,96,49,null,null,"Fri 03/06/22","Thu 14/03/24"]
[1102,960050,"Study on Audio Aspects for Glasses-type AR/MR Devices ","FS_Audio_5GSTAR",1,"Rel-18","S4","Fri 03/06/22","Thu 08/12/22",1,"SP-220617",null,"Stéphane Ragot, Orange ","stephane.ragot@orange.com ","17/8/22: FS_ARMRglass->FS_Audio_5GSTAR; 12/9/22: 0%->5; 11/12/22: 5%->100","26.998; ",96,49,null,null,"Fri 03/06/22","Sun 11/12/22"]
[1103,0,"Rel-18 Transportations (Railways, V2X)","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1104,880036,"Study on Off-Network for Rail","FS_OffNetRail",1,"Rel-18","S1","Thu 25/06/20","Fri 10/12/21",1,"SP-200572",null,"Guillaume Gach","Ext.gach <at> uic.org ","28/7/20: 22.990 added;; 12/9/20: 0%->10; 5/12/20: 10%->30; 19/3/21: FCD:17/03/2021->12/21; 19/3/21: 30%->50; 13/9/21: 50%->90; 10/12/21: 90%->100",22.99,88,45,null,null,"Thu 25/06/20","Fri 10/12/21"]
[1105,880034,"Study of Interconnection and Migration Aspects for Railways ","FS_IRail",1,"Rel-18","S6","Thu 25/06/20","Thu 16/09/21",1,"SP-200336",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","13/9/20: 0%->10; 25/9/20: 23.700-90 added;; 21/3/21: 10%->15; 11/6/21: 15%->30; 13/9/21: 30%->60; 13/12/21: 60%->85; 12/3/22: 85%->100","23.700-90",88,45,null,null,"Fri 26/06/20","Sat 12/03/22"]
[1106,980122,"Interconnection and Migration Aspects for Railways ","IRail",1,"Rel-18",null,"Thu 03/03/22","Tue 12/12/23",1,"SP-220098",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ",null,"23.280; 23.281; 23.282; 23.379 ",95,48,null,null,"Thu 10/03/22","Mon 12/09/22"]
[1107,950025,"   Stage 2 of Irail","IRail",2,"Rel-18","S6","Thu 03/03/22","Mon 12/12/22",1,"SP-220098",null,"Oettl, Martin, Nokia ","martin.oettl@nokia.com ","; 4/6/22: 0%->40; 12/9/22: 40%->60; 11/12/22: 60%->75; 17/3/23: 75%->85; 8/6/23: 85%->100","23.280; 23.281; 23.282; 23.379 ",95,48,null,null,"Sun 11/12/22","Thu 08/06/23"]
[1108,980070,"   CT1 aspects of eMCSMI_IRail","eMCSMI_IRail",2,"Rel-18","C1","Fri 16/12/22","Tue 12/12/23",1,"CP-240270",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com","6/6/23: Compl:10%->15%","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482; 24.281; 24.581; 24.582; 29.283",95,48,null,null,"Thu 10/03/22","Tue 06/06/23"]
[1109,980071,"   deleted - CT4 aspects of eMCSMI_IRail","eMCSMI_IRail",2,"Rel-18","C4","Fri 16/12/22","Tue 12/12/23",1,"CP-240270",null,"Won, Sung Hwan, Nokia","sung.won@nokia.com","2/4/24: deleted at 100%","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482; 24.281; 24.581; 24.582; 29.283",95,48,null,null,"Thu 10/03/22","Tue 02/04/24"]
[1110,900026,"Study on FRMCS Phase 4","FS_FRMCS_Ph4",1,"Rel-18","S1","Fri 04/12/20","Fri 10/12/21",1,"SP-220436",null,"Guillaume Gach; UIC ","Guillaume Gach; gach <at> uic.org ","22.989 ; 19/3/21: FCD:12/09/2021->12/21; 19/3/21: 0%->20; 13/9/21: 20%->80; 10/12/21: 80%->100; 21/6/22: WID:SP-201038->SP-220436. FS_eFRMCS -> FS_FRMCS_Ph4",null,90,46,null,null,"Fri 04/12/20","Tue 21/06/22"]
[1111,930014,"Study on enhancements to application layer support for V2X services; Phase 2 ","FS_eV2XAPP2",1,"Rel-18","S6","Mon 13/09/21","Mon 12/09/22",1,"SP-220466",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/12/21: 0%->30; 22/3/22: 23.700-64 added;; 4/6/22: 30%->65; 4/6/22: FCD:10/06/2022->09/22; 4/6/22: WID:SP-210956->SP-220466; 12/9/22: 65%->85; 11/12/22: 85%->100","23.700-64",93,47,null,null,"Mon 13/09/21","Sun 11/12/22"]
[1112,980125,"Application layer support for V2X services; Phase 3","V2XAPP_Ph3",1,"Rel-18",null,"Fri 09/09/22","Sun 03/03/24",1,"SP-220916",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ",null,"23.286; 23.434 ",97,49,null,null,"Sun 11/09/22","NA"]
[1113,970039,"   Stage 2 of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","S6","Fri 09/09/22","Tue 06/06/23",1,"SP-221229",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 11/12/22: 0%->45; 9/1/23: WID:SP-220916->SP-221229; 17/3/23: 45%->75; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 75%->100","23.286; 23.434 ",97,49,null,null,"Sun 11/12/22","Thu 08/06/23"]
[1114,980072,"   CT1 aspects of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","C1","Fri 16/12/22","Sun 03/03/24",1,"CP-233214",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","6/6/23: Compl:0%->20%; 30/6/23: WID:CP-223107->CP-231285","24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549; 29.486; 24.549; 29.558",97,49,null,null,"Sun 11/09/22","Fri 30/06/23"]
[1115,980073,"   CT3 aspects of V2XAPP_Ph3","V2XAPP_Ph3",2,"Rel-18","C3","Fri 16/12/22","Sun 03/03/24",1,"CP-233214",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,"24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549; 29.486; 24.549; 29.558",97,49,null,null,"Sun 11/09/22","NA"]
[1116,1000043,"MBS support for V2X services ","TEI18_MBS4V2X",1,"Rel-18",null,"Mon 12/09/22","Sun 03/03/24",1,"SP-220793",null,"LaeYoung Kim (LG Electronics), ","laeyoung.kim@lge.com ","; 22/3/23: 0%->100","23.287; 23.501 ",97,49,null,null,"Sun 11/09/22","Wed 22/03/23"]
[1117,970003,"   (Stage 2 of) MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","S2","Mon 12/09/22","Fri 03/03/23",1,"SP-220793",null,"LaeYoung Kim (LG Electronics), ","laeyoung.kim@lge.com ","; 22/3/23: 0%->100","23.287; 23.501 ",97,49,null,null,"Sun 11/09/22","Wed 22/03/23"]
[1118,1000022,"   CT1 aspects of MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","C1","Wed 07/06/23","Sun 03/03/24",1,"CP-231357",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ",null,"24.587; 24.588; 31.102 ",100,51,null,null,"Wed 07/06/23","NA"]
[1119,1010021,"   CT6 aspects of MBS support for V2X services ","TEI18_MBS4V2X",2,"Rel-18","C6","Wed 07/06/23","Sun 03/03/24",1,"CP-231357",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ",null,"24.587; 24.588; 31.102 ",101,51,null,null,"Wed 07/06/23","NA"]
[1120,950079,"Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh",1,"Rel-18",null,"Tue 15/03/22","Thu 12/12/24",0.75,"RP-222272",null,"Samsung ",null,"compare REL-17 WI NR_HST_FR2 ; 23/9/22: WID:RP-220985->RP-222272",null,95,48,null,null,"Tue 05/04/22","Fri 23/09/22"]
[1121,950179,"   Core part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-Core",2,"Rel-18","R4","Tue 15/03/22","Fri 08/09/23",1,"RP-222272","RP- 241272","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","compare REL-17 WI NR_HST_FR2 ; 6/6/22: CD:15/09/2023->23/09/2022 ; 6/6/22: Stat Rep: ->RP-221405; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/202...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1122,950279,"   Perf. part: Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-Perf",2,"Rel-18","R4","Wed 16/03/22","Thu 06/06/24",1,"RP-222272","RP- 241272","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","6/6/22: CD:15/03/2024->24/03/2023 6/6/22: Stat Rep: ->RP-221405; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com13/7/22: FCD:24/03/2023->03/20 ; ...; 9/12/22: FCD:24/03/2023->01/03/2024; Stat Rep: RP-...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1123,1030071,"   UE Conformance - Enhanced NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2_enh-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.38,"RP-240371","RP-251018","Samsung ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241278; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->36%; Stat Rep: RP-241278->RP-241981; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:36%->38%; Stat Rep: RP-241981->RP-242595; ; 6/3/25: FCD:28/05/2025->12/12/2025;",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[1124,0,"Rel-18 User Plane traffic and services","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1125,920036,"Evolution of IMS Multimedia Telephony Service ","eMMTEL",1,"Rel-18",null,"Thu 19/09/19","Fri 12/12/25",0.95,"SP-210519",null,"Hu Yue, China Mobile","huyueyjy@chinamobile.com ",null,"22.261;22.173 ",92,47,null,null,"Fri 11/06/21","NA"]
[1126,850042,"   Study on evolution of IMS multimedia telephony service ","FS_MMTELin5G",2,"Rel-18","S1","Thu 19/09/19","Wed 08/09/21",1,"SP-190836",null,"Yan Di, China Mobile","yandi@chinamobile.com ","; 8/10/19: 22.873 added;; 6/12/19: 0%->10; 12/9/20: 10%->15; 5/12/20: 15%->40; 19/3/21: 40%->75; 19/3/21: FCD:11/12/2020->09/21; 11/6/21: 75%->95; 13/9/21: 95%->100","New ; 22.873",85,43,null,null,"Fri 13/09/19","Mon 13/09/21"]
[1127,920029,"   Stage 1 of Evolution of IMS Multimedia Telephony Service ","eMMTEL",2,"Rel-18","S1","Fri 11/06/21","Fri 10/12/21",1,"SP-210519",null,"Hu Yue, China Mobile","huyueyjy@chinamobile.com","; 13/9/21: 0%->100","22.261;22.173 ",92,47,null,null,"Fri 11/06/21","Mon 13/09/21"]
[1128,940066,"   Study on system architecture for next generation real time communication services ","FS_NG_RTC",2,"Rel-18","S2","Mon 20/12/21","Fri 03/03/23",1,"SP-220288",null,"Yi Jiang ","jiangyi at chinamobile dot com ","21/1/22: 23.700-87 added;; 12/3/22: 0%->20; 5/4/22: WID:SP-211644->SP-220288; 4/6/22: 20%->55; 12/9/22: 55%->79; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 79%->85; 15/3/23: 85%->100; 16/3/23: FCD:12/12/2022->/23","23.700-87",94,48,null,null,"Sun 19/12/21","Thu 16/03/23"]
[1129,970014,"   System architecture for Next Generation Real time Communication services ","NG_RTC",2,"Rel-18","S2","Mon 12/09/22","Tue 06/06/23",1,"SP-230098",null,"Yi Jiang, China Mobile ","jiangyi at chinamobile dot com ","; 15/3/23: WID:SP-220804->SP-230098; 15/3/23: 0%->60; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100","23.228; 23.502 ",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[1130,990023,"   CT1 aspects of NG_RTC","NG_RTC",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-240271",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","; 31/3/23: 24.186 added;6/6/23: Compl:0%->15%","24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 24.186",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1131,990086,"   CT3 aspects of NG_RTC","NG_RTC",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-240271",null,"Chen Xu, China Mobile","chenxu@chinamobile.com",null,"24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333",97,49,null,null,"Sun 11/09/22","NA"]
[1132,990087,"   CT4 aspects of NG_RTC","NG_RTC",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-240271",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","; 31/3/23: 29.176 added;; 31/3/23: 29.175 added;6/6/23: Compl:0%->25%; 4/1/24: 29.330 added;","24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 29.176; 29.175; 29.330",97,49,null,null,"Sun 11/09/22","Thu 04/01/24"]
[1133,1030027,"   CT6 aspects of NG_RTC","NG_RTC",2,"Rel-18","C6","Mon 13/03/23","Sun 03/03/24",1,"CP-240271",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","; 31/3/23: 29.176 added;; 31/3/23: 29.175 added;6/6/23: Compl:0%->25%; 4/1/24: 29.330 added;","24.229.24.275.29.214.29.514.29.165.29.510.29.562.29.228.29.229.29.328.29.329.29.364.29.333.23.333; 29.176; 29.175; 29.330",97,49,null,null,"Sun 11/09/22","Thu 04/01/24"]
[1134,960032,"   Study on security support for Next Generation Real Time Communication services ","FS_NG_RTC_SEC",2,"Rel-18","S3","Thu 02/06/22","Tue 06/06/23",1,"SP-220530",null,"Fei, Li, Huawei ","Austin.lifei@huawei.com ","13/7/22: 33.890 added;; 12/9/22: 0%->40; 11/12/22: 40%->70; 17/3/23: 70%->90; 8/6/23: 90%->100",33.89,96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[1135,990038,"   Security support for Next Generation Real Time Communication services ","NG_RTC_SEC",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230151",null,"Fei, Li, Huawei ","Austin.lifei@huawei.com ","; 15/3/24: 0%->100",33.328000000000003,99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[1136,1050133,"   UE Conformance - IMS Data Channel for NG RTC (Real Time Communication) ","NG_RTC_IMS_dataCH-UEConTest",2,"Rel-18","R5","Mon 09/09/24","Fri 12/12/25",0.71,"RP-242078","RP-251491","Huawei ",null,"6/12/24: Compl:0%->5%; Stat Rep: ->RP-243093; ; 6/3/25: FCD:24/07/2025->12/12/2025; Compl:5%->21%; Stat Rep: RP-243093->RP-250451; ; 6/6/25: Compl:21%->71%; Stat Rep: RP-250451->RP-251491; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[1137,1000008,"Charging Aspects of IMS Data Channel ","IDC_CH",1,"Rel-18","S5","Thu 08/06/23","Sun 03/03/24",1,"SP-230621",null,"Chen, Ai, China Mobile, ","chenai at chinamobile dot com ","; 8/12/23: 0%->40; 14/3/24: 40%->100","32.260; 32.255; 32.291; 32.298 ",100,51,null,null,"Thu 08/06/23","Thu 14/03/24"]
[1138,990111,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 3 ","ATSSS_Ph3",1,"Rel-18",null,"Mon 20/12/21","Tue 03/03/26",0.77,"SP-221334",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","; 9/1/23: WID:SP-220813->SP-221334","23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Mon 09/01/23"]
[1139,940070,"   Study on Access Traffic Steering, Switching and Splitting support in the 5G system architecture; Phase 3 ","FS_ATSSS_Ph3",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211612",null,"Salkintzis, Apostolis, Lenovo, ","y1026c@lenovo.com ","21/1/22: 23.700-53 added;; 12/3/22: 0%->20; 4/6/22: 20%->70; 12/9/22: 70%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-53",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[1140,970023,"   Stage 2 of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","S2","Mon 12/09/22","Tue 06/06/23",1,"SP-221334",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","; 9/1/23: WID:SP-220813->SP-221334; 15/3/23: 0%->85; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 85%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[1141,990021,"   CT1 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","6/6/23: Compl:0%->50%","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1142,990089,"   CT3 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","9/6/23: 0%->60","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1143,990090,"   CT4 aspects of ATSSS_Ph3","ATSSS_Ph3",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-230334",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","6/6/23: Compl:5%->50%","24.193.24.501.24.302.29.512.29.244.29.502.29.518.29.274.29.571.29.510",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1144,1070061,"   UE Conformance - Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 3 ","ATSSS_Ph3-UEConTest",2,"Rel-18","R5","Mon 03/03/25","Tue 03/03/26",0.05,"RP-250067","RP-250896","China Telecom ",null,"6/6/25: Compl:0%->5%; Stat Rep: ->RP-250896; ",null,107,54,null,null,"Wed 26/03/25","Fri 06/06/25"]
[1145,940076,"Study on UPF enhancement for Exposure And SBA ","FS_UPEAS",1,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220417",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","21/1/22: 23.700-62 added;; 12/3/22: 0%->20; 4/6/22: 20%->60; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211652->SP-220417; 12/9/22: 60%->80; 10/12/22: 80%->98; 15/3/23: 98%->100","23.700-62",94,48,null,null,"Sun 19/12/21","Wed 15/03/23"]
[1146,990112,"UPF enhancement for Exposure and SBA ","UPEAS",1,"Rel-18",null,"Mon 12/09/22","Sun 03/03/24",1,"SP-220809",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","; 10/12/22: 0%->20","23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Sat 10/12/22"]
[1147,970019,"   Stage 2 of UPEAS","UPEAS",2,"Rel-18","S2","Mon 12/09/22","Tue 06/06/23",1,"SP-230103",null,"Yan Han, China Mobile ","hanyan@chinamobile.com ","; 10/12/22: 0%->20; 15/3/23: WID:SP-220809->SP-230103; 15/3/23: 20%->75; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 75%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[1148,990002,"   CT4 aspects of UPF enhancement for exposure and SBA","UPEAS",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-240022",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com","17/3/23: 10%->406/6/23: Compl:40%->70%","29.510.29.564.29.244.29.571.29.508.29.522.29.512.29.513.29.514.29.565.29.574.29.575.29.552",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1149,990092,"   CT3 aspects of UPF enhancement for exposure and SBA","UPEAS",2,"Rel-18","C3","Tue 18/04/23","Sun 03/03/24",1,"CP-240022",null,"Rong Wang, China Mobile","wangrongyjy@chinamobile.com","9/6/23: 0%->90","29.510.29.564.29.244.29.571.29.508.29.522.29.512.29.513.29.514.29.565.29.574.29.575.29.552",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1150,930027,"Tactile and multi-modality communication services ","TACMM",1,"Rel-18",null,"Fri 04/12/20","Fri 10/12/21",1,"SP-211053",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ",null,22.260999999999999,93,47,null,null,"Fri 10/09/21","NA"]
[1151,900027,"   Study on TACMM","FS_TACMM",2,"Rel-18","S1","Fri 04/12/20","Fri 11/06/21",1,"SP-210209",null,"Shi, Xiaonan, China Mobile","shixiaonan@chinamobile.com","10/2/21: 22.847 added;; 19/3/21: 0%->30; 11/6/21: 30%->40; 13/9/21: 40%->85; 14/9/21: WID:SP-201039->SP-210209; 10/12/21: 85%->100",22.847000000000001,90,46,null,null,"Fri 04/12/20","Fri 10/12/21"]
[1152,930020,"   Stage 1 of TACMM","TACMM",2,"Rel-18","S1","Fri 10/09/21","Fri 10/12/21",1,"SP-211053",null,"Xiaonan Shi, CMCC ","shixiaonan@chinamobile.com ","; 10/12/21: 0%->100",22.260999999999999,93,47,null,null,"Fri 10/09/21","Fri 10/12/21"]
[1153,0,"Rel-18 Edge computing","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1154,980132,"Architecture for enabling Edge Applications Phase 2 ","EDGEAPP_Ph2",1,"Rel-18",null,"Fri 09/09/22","Tue 12/12/23",1,"SP-221231",null,"Sapan Shah, Samsung ","sapan.shah@samsung.com ",null,null,97,49,null,null,"Sun 11/09/22","Mon 12/09/22"]
[1155,970040,"   (Stage 2 of EDGEAPP_Ph2) Architecture for enabling Edge Applications Phase 2 ","EDGEAPP_Ph2",2,"Rel-18","S6","Fri 09/09/22","Fri 03/03/23",1,"SP-221231",null,"Sapan Shah, Samsung ","sapan.shah@samsung.com ","; 12/9/22: 0%->5; 11/12/22: 0%->30; 9/1/23: WID:SP-220917->SP-221231; 17/3/23: 30%->70; 8/6/23: 70%->100","23.558; 23.958",97,49,null,null,"Sun 11/12/22","Thu 08/06/23"]
[1156,980074,"   CT1 aspects of EDGEAPP_Ph2","EDGEAPP_Ph2",2,"Rel-18","C1","Thu 15/12/22","Tue 12/12/23",1,"CP-233114",null,"Narendranath Durga Tangudu","n.tangudu@samsung.com","; 6/6/23: Compl:5%->40%; 6/6/23: WID: CP-223207->CP-231197","24.558; 29.558; 29.222",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1157,980075,"   CT3 aspects of EDGEAPP_Ph2","EDGEAPP_Ph2",2,"Rel-18","C3","Thu 15/12/22","Tue 12/12/23",1,"CP-233114",null,"Narendranath Durga Tangudu","n.tangudu@samsung.com","; 6/6/23: Compl:10%->40%; 6/6/23: WID: CP-223207->CP-231197","24.558; 29.558; 29.222",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1158,960011,"Edge Application Standards in 3GPP and alignment with External Organizations ","EDGEAPP_EXT",1,"Rel-18","S6","Thu 02/06/22","Tue 12/12/23",1,"SP-220990",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com","13/7/22: 23.958 added;; 12/9/22: 0%->5; 12/9/22: WID:SP-220468->SP-220912; 17/3/23: 5%->10; 8/6/23: 10%->50; 7/9/23: 50%->65; 13/9/23: FCD:06/06/2023->12/20; 13/9/23: WID:SP-220990->SP-231156; 15/3/24: 65%->98; 13/6/24: 98%->100; 13/6/24: WID:SP-231156->S",23.957999999999998,96,49,null,null,"Thu 02/06/22","Thu 13/06/24"]
[1159,920017,"Study on enhanced architecture for enabling Edge Applications ","FS_eEDGEAPP",1,"Rel-18","S6","Fri 11/06/21","Fri 10/06/22",1,"SP-211510",null,"Gupta, Nishant, Samsung ","nishant.gup@samsung.com ","2/7/21: 23.700-98 added;; 13/9/21: 0%->10; 13/12/21: 10%->45; 13/12/21: WID:SP-210479->SP-211510; 13/12/21: FCD:Fri 11/03/->06/22; 12/3/22: 45%->55; 4/6/22: 55%->75; 12/9/22: 75%->90; 11/12/22: 90%->100","23.700-98",92,47,null,null,"Fri 11/06/21","Sun 11/12/22"]
[1160,980123,"Edge Computing Phase 2","FS_EDGE_Ph2",1,"Rel-18",null,"Mon 20/12/21","Thu 06/06/24",1,null,null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070","23.700-48",95,48,null,null,"Sun 11/12/22","NA"]
[1161,950049,"   Study on Edge Computing phase 2","FS_EDGE_Ph2",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220070",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070","23.700-48",95,48,null,null,"Sun 19/12/21","Sat 12/03/22"]
[1162,940059,"   Study on Stage 2 of Edge Computing phase 2","FS_EDGE_Ph2",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220352",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","21/1/22: 23.700-48 added;; 12/3/22: 0%->13; 12/3/22: FCD:12/09/2022->12/22; 12/3/22: WID:SP-211638->SP-220070; 4/6/22: 13%->55; 12/9/22: 55%->83; 10/12/22: 83%->100","23.700-48",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[1163,950023,"   Study on Security of Edge Computing phase 2 ","FS_EDGE_Ph2",2,"Rel-18","S3","Thu 10/03/22","Mon 12/12/22",1,"SP-220201",null,"Bo Zhang, Huawei ","zhangbo6@huawei.com ","4/6/22: 0%->30; 13/7/22: 33.739 added;; 12/9/22: 30%->40; 11/12/22: 40%->70; 17/3/23: 70%->80; 8/6/23: 80%->90; 15/3/24: 90%->100",33.738999999999997,95,48,null,null,"Thu 10/03/22","Fri 15/03/24"]
[1164,970026,"   (stage 2 of) Edge Computing Phase 2 ","EDGE_Ph2",2,"Rel-18","S2","Fri 23/09/22","Tue 06/06/23",1,"SP-230112",null,"Patrice Hédé, Huawei Technologies ","patrice dot hede at huawei dot com ","; 10/12/22: 0%->15; 9/1/23: WID:SP-220987->SP-221337; 15/3/23: WID:SP-221337->SP-230112; 15/3/23: 15%->80; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 80%->100","23.548; 23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[1165,1040038,"   CT1 aspects of EDGE_Ph2","EDGE_Ph2",2,"Rel-18","C1","Fri 16/12/22","Thu 06/06/24",1,"CP-241027",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","9/6/23: 30%->35","29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1166,980076,"   CT3 aspects of EDGE_Ph2","EDGE_Ph2",2,"Rel-18","C3","Fri 16/12/22","Thu 06/06/24",1,"CP-241027",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","9/6/23: 30%->35","29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1167,980077,"   CT4 aspects of EDGE_Ph2","EDGE_Ph2",2,"Rel-18","C4","Fri 16/12/22","Thu 06/06/24",1,"CP-241027",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","; 6/6/23: Compl:20%->45%; 16/7/24: WID:CP-233026->CP-241027","29.510; 29.502; 29.503; 29.504; 29.505; 29.571; 29.556; 29.508; 29.512; 29.514; 29.513; 29.522; 29.519",97,49,null,null,"Sun 11/09/22","Tue 16/07/24"]
[1168,990039,"   Security Aspects of Support for Edge Computing in 5GC phase 2 ","EDGE_Ph2",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230366",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","31/3/23: WID:SP-230152->SP-230366; 7/9/23: 0%->95; 15/3/24: 95%->100","33.558; 33.501 ",99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[1169,0,"Rel-18 Non-Public Networks","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1170,920038,"5G Networks Providing Access to Localized Services ","PALS",1,"Rel-18",null,"Wed 16/09/20","Wed 08/09/21",1,"SP-210522",null,"Lola Awoniyi-Oteri, qualcomm ","oawoniyi@qti.qualcomm.com ",null,22.260999999999999,92,47,null,null,"Fri 11/06/21","NA"]
[1171,890023,"   Study on PALS ","FS_PALS",2,"Rel-18","S1","Wed 16/09/20","Fri 11/06/21",1,"SP-200799",null,"Jack Nasielski ","jackn <at> qti.qualcomm.com ","5/12/20: 0%->35; 19/3/21: 35%->77; 11/6/21: 77%->95; 13/9/21: 95%->100",22.844000000000001,89,45,null,null,"Thu 10/09/20","Mon 13/09/21"]
[1172,920031,"   Stage 1 of PALS ","PALS",2,"Rel-18","S1","Fri 11/06/21","Wed 08/09/21",1,"SP-210588",null,"Lola Awoniyi-Oteri, qualcomm ","oawoniyi@qti.qualcomm.com ","; 10/12/21: 0%->100",22.260999999999999,92,47,null,null,"Fri 11/06/21","Fri 10/12/21"]
[1173,980128,"Non-Public Networks Phase 2 ","eNPN_Ph2",1,"Rel-18",null,"Mon 13/12/21","Fri 12/12/25",0.87,"SP-220805",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","; 10/12/22: 0%->50","23.501; 23.502; 23.402 ",97,49,null,null,"Sun 11/09/22","Sat 10/12/22"]
[1174,940075,"   Study on enhanced support of Non-Public Networks phase 2 ","FS_eNPN_Ph2",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220418",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","21/1/22: 23.700-08 added;; 12/3/22: 0%->10; 4/6/22: 10%->50; 4/6/22: FCD:12/09/2022->12/22; 21/6/22: WID:SP-211656->SP-220418; 12/9/22: 50%->75; 12/9/22: FCD:12/12/2022->12/22; 10/12/22: 75%->98; 15/3/23: 98%->100","23.700-08",94,48,null,null,"Sun 19/12/21","Wed 15/03/23"]
[1175,970015,"   Stage 2 of Non-Public Networks Phase 2 ","eNPN_Ph2",2,"Rel-18","S2","Mon 12/09/22","Tue 06/06/23",1,"SP-230096",null,"Hedman, Peter, Ericsson ","peter . hedman @ ericsson . com ","; 10/12/22: 0%->50; 9/1/23: WID:SP-220805->SP-221340; 15/3/23: 50%->90; 15/3/23: WID:SP-221340->SP-230096; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 90%->100","23.501; 23.502; 23.402 ",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[1176,960033,"   Study on security aspects of enhanced support of Non-Public Networks phase 2 ","FS_eNPN_Ph2_SEC",2,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220531",null,"Jost, Christine, Ericsson, ","(christine.jost@ericsson.com) ","13/7/22: 33.858 added;; 12/9/22: 0%->10; 11/12/22: 10%->60; 17/3/23: 60%->78; 8/6/23: 78%->99; 15/3/24: 99%->100",33.857999999999997,96,49,null,null,"Thu 02/06/22","Fri 15/03/24"]
[1177,990043,"   Security aspects of support of Non-Public Networks phase 2 ","eNPN_Ph2",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230156",null,"Jost, Christine, Ericsson ","christine.jost@ericsson.com ","; 8/6/23: 0%->65; 7/9/23: 65%->90; 14/3/24: 90%->100",33.500999999999998,99,50,null,null,"Thu 16/03/23","Thu 14/03/24"]
[1178,980078,"   CT1 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C1","Fri 16/12/22","Sun 03/03/24",1,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 6/6/23: Compl:33%->60%; 30/6/23: WID:CP-223104->CP-231286","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"Sun 11/09/22","Fri 30/06/23"]
[1179,980079,"   CT3 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C3","Thu 15/12/22","Sun 03/03/24",1,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 9/6/23: 30%->60","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1180,980080,"   CT4 aspects of eNPN_Ph2","eNPN_Ph2",2,"Rel-18","C4","Thu 15/12/22","Sun 03/03/24",1,"CP-231286",null,"Sedlacek, Ivo, Ericsson","ivo <dot> sedlacek <at> ericsson <dot> com","; 6/6/23: Compl:50%->65%","23.122; 24.229; 24.302; 24.501; 24.502; 24.526; 29.507; 29.512; 29.513; 29.525; 23.003; 29.518; 29.503; 29.550",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1181,940043,"   Study on Charging Aspects for Enhanced Support of Non-Public Networks ","FS_eNPN_CH",2,"Rel-18","S5","Mon 13/12/21","Fri 03/03/23",1,"SP-211447",null,"Chen, Ai, China Mobile ","chenai@chinamobile.com ","7/1/22: 28.828 added;; 12/9/22: 0%->60; 11/12/22: 60%->75; 17/3/23: 75%->100",28.827999999999999,94,48,null,null,"Mon 13/12/21","Fri 17/03/23"]
[1182,990028,"   Charging Aspects for Enhanced Support of Non-Public Networks ","eNPN_CH",2,"Rel-18","S5","Thu 16/03/23","Sun 03/03/24",1,"SP-230177",null,"Chen, Ai, China Mobile ","chenai at chinamobile dot com ","; 8/6/23: 0%->10; 7/9/23: 10%->30; 8/12/23: 30%->65; 14/3/24: 65%->100","32.255; 32.256; 28.203; 32.291; 32.298 ",99,50,null,null,"Thu 16/03/23","Thu 14/03/24"]
[1183,991138,"   Core part: Non-Public Networks Phase 2: NG-RAN aspects","eNPN_Ph2-NGRAN-Core",2,"Rel-18","R3","Mon 06/03/23","Tue 12/12/23",1,"RP-233569","RP-233567","Shengnan Liu, China Telecom","liushn@chinatelecom.cn","; 7/6/23: Compl:0%->97%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:97%->100%; WID: RP-230788->RP-231185; Stat Rep: ->RP-232261; Rapporteur: China Telecom->Shengnan Liu, China Telecom; Rap eMail: ->liushn@chinatelecom.cn; ; 21/9/23: FCD:22/09/2023->12/1...",null,99,50,null,null,"Fri 07/04/23","Tue 02/01/24"]
[1184,1040106,"   UE Conformance - Non-Public Networks Phase 2: NG-RAN aspects plus CT1 aspects ","eNPN_Ph2-NGRAN_plus_CT1-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 12/12/25",0.32,"RP-241307","RP-251463","China Telecom ",null,"6/12/24: Compl:0%->5%; Stat Rep: ->RP-242870; ; 6/3/25: FCD:24/06/2025->12/12/2025; Compl:5%->17%; Stat Rep: RP-242870->RP-250379; ; 6/6/25: Compl:17%->32%; Stat Rep: RP-250379->RP-251463; ",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[1185,0,"Rel-18 AM and UE Policy","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1186,840020,"Study on enhancement of 5G UE Policy ","FS_eUEPO",1,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211649",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ","26/6/19: 23.760 added; 21/01/22: moved Rel-17 to Rel-18 at SA#94e. Deletion of 940072, temporarily mistakenly added as FS_eUEPO_Ph2; WID:SP-190449->SP-211649; 12/3/22: 0%->25; 4/6/22: 25%->70; 4/6/22: FCD:12/09/2022->12/22; 12/9/22: 70%->80; 10/12/22: ...","New ; 23.760",84,43,null,null,"Fri 31/05/19","Wed 15/03/23"]
[1187,980114,"Enhancement of 5G UE Policy ","eUEPO",1,"Rel-18",null,"Fri 09/09/22","Thu 06/06/24",1,"SP-220980",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"Fri 23/09/22","NA"]
[1188,970025,"   (Stage 2 of) Enhancement of 5G UE Policy ","eUEPO",2,"Rel-18","S2","Fri 09/09/22","Tue 06/06/23",1,"SP-230094",null,"Changhong Shan, Intel ","chang.hong.shan@intel.com ","; 9/1/23: WID:SP-220980->SP-221342; 15/3/23: 0%->65; 15/3/23: WID:SP-221342->SP-230094; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 65%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Sat 10/12/22","Thu 08/06/23"]
[1189,980081,"   CT1 aspects of eUEPO","eUEPO",2,"Rel-18","C1","Fri 16/12/22","Thu 06/06/24",1,"CP-241076",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->30%; 6/6/23: WID: CP-230276->CP-231192; 23/7/24: WID:CP-240080->CP-241076","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,null,"Fri 23/09/22","Tue 23/07/24"]
[1190,980082,"   CT3 aspects of eUEPO","eUEPO",2,"Rel-18","C3","Fri 16/12/22","Thu 06/06/24",1,"CP-241076",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->40%; 6/6/23: WID: CP-230276->CP-231192","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,null,"Fri 23/09/22","Tue 06/06/23"]
[1191,990093,"   CT4 aspects of eUEPO","eUEPO",2,"Rel-18","C4","Fri 16/12/22","Thu 06/06/24",1,"CP-241076",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 6/6/23: Compl:10%->30%; 6/6/23: WID: CP-230276->CP-231192","24.008.24.301.24.501.24.526.29.512.29.513.29.519.29.520.29.522.29.525.29.244.29.564",97,49,null,null,"Fri 23/09/22","Tue 06/06/23"]
[1192,1000041,"Spending Limits for AM and UE Policies in the 5GC ","TEI18_SLAMUP",1,"Rel-18",null,"Mon 12/09/22","Tue 12/12/23",1,"SP-220794",null,"Baniel, Uriuri dot baniel at oracle dot com ","uri dot baniel at oracle dot com ","; 22/3/23: 0%->80; 22/3/23: FCD:12/12/2022->06/20","23.503; 23.501; 23.502 ",97,49,null,null,"Sun 11/09/22","Wed 22/03/23"]
[1193,970004,"   Stage 2 of TEI18_SLAMUP","TEI18_SLAMUP",2,"Rel-18","S2","Mon 12/09/22","Tue 06/06/23",1,"SP-220794",null,"Baniel, Uriuri dot baniel at oracle dot com ","uri dot baniel at oracle dot com ","; 22/3/23: 0%->80; 22/3/23: FCD:12/12/2022->06/20; 8/6/23: 80%->100","23.503; 23.501; 23.502 ",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[1194,1000040,"   CT3 aspects on TEI18_SLAMUP","TEI18_SLAMUP",2,"Rel-18","C3","Wed 07/06/23","Tue 12/12/23",1,"CP-233125",null,"SUN, Yue, China Telecom ","suny20@chinatelecom.cn ",null,"29.513; 29.519; 29.594 ",100,51,null,null,"Wed 07/06/23","NA"]
[1195,1020048,"   CT4 aspects on TEI18_SLAMUP","TEI18_SLAMUP",2,"Rel-18","C4","Wed 07/06/23","Tue 12/12/23",1,"CP-233125",null,"SUN, Yue, China Telecom ","suny20@chinatelecom.cn ",null,"29.513; 29.519; 29.594 ",102,52,null,null,"Wed 07/06/23","NA"]
[1196,970001,"Rel-18 Enhancements of UE Policy","UEP18",1,"Rel-18",null,"Thu 07/03/19","Wed 13/12/23",1,"CP_233115",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com",null,"29.525; 29.507; 29.513; 29.518",97,49,null,null,"Thu 10/03/22","NA"]
[1197,970045,"   CT3 aspects of UEP18","UEP18",2,"Rel-18","C3","Thu 07/03/19","Tue 12/12/23",1,"CP-233115",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:20%->50%","29.525; 29.507; 29.513",97,49,null,null,"Wed 07/09/22","Tue 06/06/23"]
[1198,970046,"   CT4 aspects of UEP18","UEP18",2,"Rel-18","C4","Mon 11/03/19","Tue 12/12/23",1,"CP-233115",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com",null,29.518000000000001,97,49,null,null,"Wed 07/09/22","NA"]
[1199,990113,"5G AM Policy ","AMP",1,"Rel-18",null,"Thu 07/03/19","Sun 03/03/24",1,"SP-221335",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","; 10/12/22: 0%->80; 9/1/23: WID:SP-220807->SP-221335","23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Mon 09/01/23"]
[1200,940064,"   Study on 5G AM Policy","FS_AMP",2,"Rel-18","S2","Mon 20/12/21","Mon 12/09/22",1,"SP-220647",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","21/1/22: 23.700-89 added;; 4/6/22: 0%->80; 21/6/22: WID:SP-211642->SP-220647; 12/9/22: 80%->100","23.700-89",94,48,null,null,"Sun 19/12/21","Mon 12/09/22"]
[1201,970017,"   Stage 2 of 5G AM Policy ","AMP",2,"Rel-18","S2","Thu 07/03/19","Thu 07/03/19",1,"SP-221335",null,"Chen, Zhuoyi, China Telecom ","chenzy34@chinatelecom.cn ","; 10/12/22: 0%->80; 9/1/23: WID:SP-220807->SP-221335; 15/3/23: 80%->100;","23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Wed 15/03/23"]
[1202,990007,"   CT3 aspects of 5G AM Policy ","AMP",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-232130",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->85%; 6/6/23: CD:16/06/2023->09/09/2023; 6/6/23: WID: CP-230116->CP-231302","29.507; 29.513; 29.274",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1203,990095,"   CT4 aspects of 5G AM Policy ","AMP",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-232130",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->90%; 6/6/23: WID: CP-230116->CP-231302","29.507; 29.513; 29.274",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1204,990114,"Dynamically Changing AM Policies in the 5GC Phase 2 ","TEI18_DCAMP_Ph2",1,"Rel-18",null,"Mon 20/12/21","Sat 09/09/23",1,"SP-220799",null,"Yubing Liu ","liuyb9@chinatelecom.cn ",null,23.501999999999999,97,49,null,null,"Sun 11/09/22","NA"]
[1205,970009,"   Stage 2 of TEI18_DCAMP_Ph2","TEI18_DCAMP_Ph2",2,"Rel-18","S2","Mon 20/12/21","Tue 06/06/23",1,"SP-230102",null,"Yubing Liu ","liuyb9@chinatelecom.cn ","; 16/3/23: FCD:12/09/2022->/23; 16/3/23: WID:SP-220799->SP-230102",23.501999999999999,97,49,null,null,"Sun 11/09/22","Thu 16/03/23"]
[1206,990005,"   CT3 aspects on Dynamically Changing AM Policies in the 5GC Phase 2","TEI18_DCAMP_Ph2",2,"Rel-18","C3","Mon 20/12/21","Sat 09/09/23",1,"CP-233124",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->80%; 6/6/23: CD:12/09/2022->09/09/2023","29.513; 29.519; 29.522; 29.534",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1207,1020047,"   CT4 aspects on Dynamically Changing AM Policies in the 5GC Phase 2","TEI18_DCAMP_Ph2",2,"Rel-18","C4","Mon 20/12/21","Sat 09/09/23",1,"CP-233124",null,"SUN, Yue, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:0%->80%; 6/6/23: CD:12/09/2022->09/09/2023","29.513; 29.519; 29.522; 29.534",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1208,0,"Rel-18 User plane improvements","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1209,1000017,"Study on new HEVC profiles and operating points ","FS_HEVC_Profiles",1,"Rel-18","S4","Thu 08/06/23","Sun 03/03/24",1,"SP-230540",null,"Waqar Zia ","waqar_zia (at) apple.com ","; 7/9/23: 0%->30; 21/9/23: 26.966 added;; 8/12/23: 30%->65; 14/3/24: 65%->100","26.955 ; 26.966",100,51,null,null,"Thu 08/06/23","Thu 14/03/24"]
[1210,940010,"Study on 5G Media Service Enablers ","FS_5G_MSE",1,"Rel-18","S4","Mon 13/12/21","Mon 12/12/22",1,"SP-211338",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@qti.qualcomm.com ","12/3/22: 0%->20; 4/6/22: 20%->30; 12/9/22: 30%->60; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 60%->100",null,94,48,null,null,"Mon 13/12/21","Sun 11/12/22"]
[1211,960043,"UE Testing Phase 2 ","eUET",1,"Rel-18","S4","Thu 02/06/22","Sun 03/03/24",1,"SP-220610",null,"Stéphane Ragot, Orange ","stephane.ragot@orange.com ","; 3/8/22: 26.130 added; 17/8/22: UETest_Ph2-> eUET; 12/9/22: 0%->10; 11/12/22: 10%->15; 17/3/23: 15%->20; 8/6/23: 20%->30; 7/9/23: 30%->35; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 35%->65; 14/3/24: 65%->100","26.131; 26.132; 26.801 ; 26.130",96,49,null,null,"Fri 03/06/22","Thu 14/03/24"]
[1212,980009,"5G Media Streaming Audio codec phase 2 for 5G-Advanced ","5GMS_Audio_Ph2",1,"Rel-18","S4","Fri 09/12/22","Fri 03/03/23",1,"SP-221033",null,"Frédéric Gabin (Dolby Laboratories Inc.) ","frederic.gabin@dolby.com ","17/3/23: 0%->100","26.117; 26.511 ",98,50,null,null,"Fri 09/12/22","Fri 17/03/23"]
[1213,960047,"5G Media Streaming Architecture Phase 2 ","5GMS_Ph2",1,"Rel-18","S4","Thu 02/06/22","Tue 06/06/23",1,"SP-230164",null,"Iraj Sodagar, Tencent ","<irajs@live.com> ","17/8/22: 5GMSA_Ph2-> 5GMS_Ph2; 17/8/22: WID:SP-220614->SP-220667; 12/9/22: 0%->15; 11/12/22: 15%->25; 16/3/23: WID:SP-220667->SP-230164; 16/3/23: FCD:03/03/2023->/23; 17/3/23: 25%->50; 8/6/23: 50%->100",26.501000000000001,96,49,null,null,"Fri 03/06/22","Thu 08/06/23"]
[1214,980007,"Enhanced Multiparty RTT ","MP_RTT",1,"Rel-18","S4","Mon 12/12/22","Sun 03/03/24",1,"SP-231709",null,"Huan-yu Su, Huawei ","su.huanyu@huawei.com ","; 17/3/23: 0%->5; 8/6/23: 5%->30; 7/9/23: 30%->50; 8/12/23: 50%->75; 8/12/23: FCD:12/12/2023->/2024; 8/12/23: WID:SP-221346->SP-231290; 3/1/24: WID:SP-231290->SP-231709; 14/3/24: 75%->100; 3/4/24: 26.982 added;","26.114 ; 26.982",98,50,null,null,"Fri 09/12/22","Wed 03/04/24"]
[1215,870013,"Traffic Models and Quality Evaluation Methods for Media and XR Services in 5G Systems ","FS_XRTraffic",1,"Rel-18","S4","Wed 25/03/20","Sat 09/09/23",1,"SP-210043",null,"Thomas Stockhammer","tsto@qti.qualcomm.com","10/6/20: 0%->15; 28/06/20: Rel-16->Rel-17; 5/12/20: 15%->40; 21/3/21: 40%->50; 21/3/21: FCD:18/06/2020->09/21; 11/6/21: 50%->65. 2/7/21: name change from \"Study on Typical Traffic Characteristics for XR Services and other Media\"; 13/9/21: 65%->70; 13/1...",26.925000000000001,87,44,null,null,"Fri 06/12/19","Thu 07/09/23"]
[1216,1000015,"5G-Advanced media profiles for messaging services ","PROMISE",1,"Rel-18","S4","Thu 08/06/23","Sun 03/03/24",1,"SP-230542",null,"Frédéric Gabin (Dolby Laboratories Inc.) – ","frederic.gabin@dolby.com ","30/6/23: 26.143 added;; 7/9/23: 0%->15; 8/12/23: 15%->40; 14/3/24: 40%->100","26.140; 26.141 ; 26.143",100,51,null,null,"Thu 08/06/23","Thu 14/03/24"]
[1217,1000018,"5G Media Streaming Protocols Phase 2 ","5GMS_Pro_Ph2",1,"Rel-18","S4","Thu 08/06/23","Thu 06/06/24",1,"SP-230976",null,"Thomas Stockhammer, Qualcomm Incorporated, ","tsto@qti.qualcomm.com ","; 7/9/23: WID:SP-230543->SP-230976; 7/9/23: 0%->25; ; 21/9/23: 26.510 added;; 8/12/23: 25%->55; 14/3/24: 55%->75; 14/3/24: FCD:03/03/2024->/24; 13/6/24: 75%->100","26.512; 26.247; 26.517; 26.532 ; 26.510",100,51,null,null,"Thu 08/06/23","Thu 13/06/24"]
[1218,0,"Rel-18 Other topics","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1219,1030040,"AKMA service disabling in roaming ","AKMA_Disable",1,"Rel-18","S3","Fri 02/02/24","Sun 03/03/24",1,"SP-240246",null,"Khare, Saurabh ","saurabh.khare@nokia.com ","15/3/24: 0%->100",null,103,52,null,null,"Thu 14/03/24","Fri 15/03/24"]
[1220,980110,"Support for Wireless and Wireline Convergence Phase 2 ","5WWC_Ph2",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-220904",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","NA"]
[1221,840085,"   Study on the support for 5WWC Phase 2","FS_5WWC_Ph2",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220419",null,"Laurent Thiebaut, Nokia","laurent.thiebaut@nokia.com","26/6/19: 23.700-16 added; 21/01/22: moved Rel-17 to Rel-18 at SA#94e. Deletion of 940062, temporarily mistakenly added as FS_5WWV_Ph3; WID:SP-190562->SP-211640; 12/3/22: 0%->30. 4/6/22: 30%->60; 21/6/22: WID:SP-211640...; 12/9/22: FCD:12/09/2022->12/20...","23.700-17",84,43,null,null,"Sat 03/06/17","Wed 15/03/23"]
[1222,960030,"   Study on Security aspects for 5WWC Phase 2 ","FS_5WWC_Ph2_Sec",2,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-221144",null,"Saurabh Khare, Nokia ","Saurabh.khare@nokia.com ","13/7/22: 33.887 added;; 12/9/22: 0%->30; 11/12/22: 30%->60; 9/1/23: WID:SP-220528->SP-221144; 17/3/23: 60%->80; 8/6/23: 80%->100",33.887,96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[1223,970010,"   Stage 2 of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","S2","Mon 20/12/21","Tue 06/06/23",1,"SP-230367",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","; 15/3/23: 30%->45; 15/3/23: WID:SP-220904->SP-230100; 15/3/23: FCD:12/12/2022->/23; 31/3/23: WID:SP-230100->SP-230367; 8/6/23: 45%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Fri 09/12/22","Thu 08/06/23"]
[1224,980083,"   CT1 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C1","Fri 16/12/22","Sun 03/03/24",1,"CP-233221",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:50%->60%; 30/6/23: WID:CP-223114->CP-231302; 30/6/23: WID:CP-231302->CP-231287","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,null,"Sun 11/09/22","Fri 30/06/23"]
[1225,980084,"   CT3 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C3","Fri 16/12/22","Sun 03/03/24",1,"CP-233221",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 9/6/23: 15%->40","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1226,980085,"   CT4 aspects of 5WWC_Ph2","5WWC_Ph2",2,"Rel-18","C4","Thu 15/12/22","Sun 03/03/24",1,"CP-233221",null,"Nassar, Mohamed A.(Nokia) ","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:40%->65%","24.501; 24.502; 24.526; 29.513; 29.525; 23.003; 29.522",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1227,990035,"   Security aspects for 5WWC Phase 2 ","5WWC_Ph2_Sec",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230148",null,"Khare, Saurabh, Nokia ","saurabh.khare@nokia.com ","; 8/6/23: 0%->80; 15/3/24: 80%->100",33.500999999999998,99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[1228,1010016,"   Charging Aspects of 5WWC phase 2 ","5WWC_Ph2",2,"Rel-18","S5","Wed 06/09/23","Sun 03/03/24",1,"SP-231154",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ","; 8/12/23: 0%->40; 14/3/24: 40%->100","32.255; 32.291; 32.298 ",101,51,null,null,"Wed 06/09/23","Thu 14/03/24"]
[1229,980129,"Enhancement of NSAC for maximum number of UEs with at least one PDU session/PDN connection ","eNSAC",1,"Rel-18",null,"Fri 09/09/22","Tue 12/12/23",1,"SP-220988",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ",null,"23.501; 23.502 ",97,49,null,null,"Fri 23/09/22","NA"]
[1230,970058,"   Stage 2 of eNSAC","eNSAC",2,"Rel-18","S2","Fri 09/09/22","Tue 06/06/23",1,"SP-230113",null,"ZHU Jinguo, ZTE ","zhu.jinguo@zte.com.cn ","; 16/3/23: FCD:03/03/2023->/23; 16/3/23: WID:SP-220988->SP-230113; 8/6/23: 0%->100","23.501; 23.502 ",97,49,null,null,"Mon 12/12/22","Thu 08/06/23"]
[1231,980086,"   CT3 aspects of eNSAC","eNSAC",2,"Rel-18","C3","Thu 15/12/22","Tue 06/06/23",1,"CP-232025",null,"Li, Zhijun, ZTE","li.zhijun3@zte.com.cn",null,"29.510; 29.536; 29.571; 29.122; 29.522",97,49,null,null,"Fri 23/09/22","NA"]
[1232,980087,"   CT4 aspects of eNSAC","eNSAC",2,"Rel-18","C4","Thu 15/12/22","Tue 12/12/23",1,"CP-232025",null,"Li, Zhijun, ZTE","li.zhijun3@zte.com.cn","; 6/6/23: Compl:0%->25%","29.510; 29.536; 29.571; 29.122; 29.522",97,49,null,null,"Fri 23/09/22","Tue 06/06/23"]
[1233,970031,"Management Data Analytics phase 2 ","eMDAS_Ph2",1,"Rel-18","S5","Fri 23/09/22","Sun 03/03/24",1,"SP-240267",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 11/12/22: 0%->5; 17/3/23: 5%->15; 8/6/23: 15%->25; 8/6/23: 25%->25; 7/9/23: 25%->50; 8/12/23: 50%->87; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 87%->100; 2/4/24: WID:SP-220981->SP-240267","28.104; 28.552; 32.425; 28.554; 28.541; 28.622; 28.623; 28.533 ",97,49,null,null,"Sun 11/09/22","Tue 02/04/24"]
[1234,990115,"Application Data Analytics Enablement Service ","ADAES",1,"Rel-18",null,"Mon 13/12/21","Sun 03/03/24",1,"SP-220913",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","; 23/9/22: 23.436 added;; 11/12/22: 0%->45; 11/12/22: 45%->","23.434 ; 23.436",97,49,null,null,"Sun 11/09/22","Sun 11/12/22"]
[1235,940019,"   Study on Application Data Analytics Enablement Service ","FS_ADAES",2,"Rel-18","S6","Mon 13/12/21","Mon 12/09/22",1,"SP-211513",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","7/1/22: 23.700-36 added;; 12/3/22: 0%->15; 4/6/22: 15%->55; 12/9/22: 55%->95; 11/12/22: 95%->100","23.700-36",94,48,null,null,"Mon 13/12/21","Sun 11/12/22"]
[1236,970036,"   Stage 2 of ADAES","ADAES",2,"Rel-18","S6","Mon 12/09/22","Tue 06/06/23",1,"SP-230275",null,"Pateromichelakis, Emmanouil (Manos) ","epateromiche@lenovo.com ","; 23/9/22: 23.436 added;; 11/12/22: 0%->45; 11/12/22: 45%->; 17/3/23: FCD:03/03/2023->/23; 17/3/23: WID:SP-220913->SP-230275; 17/3/23: 45%->80; 8/6/23: 80%->100","23.434 ; 23.436",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[1237,990020,"   CT1 aspects of ADAES","ADAES",2,"Rel-18","C1","Mon 12/09/22","Sun 03/03/24",1,"CP-240268",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","31/3/23: 24.559 added;; 6/6/23: Compl:0%->5%","29.549; 24.559",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1238,990097,"   CT3 aspects of ADAES","ADAES",2,"Rel-18","C3","Mon 12/09/22","Sun 03/03/24",1,"CP-240268",null,"Atarius, Roozbeh, Lenovo","ratarius@motorola.com","9/6/23: 0%->5",29.548999999999999,97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1239,940079,"Study on Seamless UE context recovery ","FS_SUECR",1,"Rel-18","S2","Mon 20/12/21","Mon 12/09/22",1,"SP-211654",null,"Lalith Kumar ","lalith.kumar@samsung.com ","21/1/22: 23.700-61 added;; 12/3/22: 0%->25; 4/6/22: 25%->100","23.700-61",94,48,null,null,"Sun 19/12/21","Sat 04/06/22"]
[1240,980116,"Seamless UE context recovery ","SUECR",1,"Rel-18",null,"Thu 08/09/22","Sat 09/09/23",1,"SP-220810",null,"Lalith kumar, Samsung ","lalith.kumar@samsung.com ",null,"23.501; 23.502 ",97,49,null,null,"Sun 11/09/22","NA"]
[1241,970020,"   Stage 2 of Seamless UE context recovery ","SUECR",2,"Rel-18","S2","Thu 08/09/22","Mon 12/12/22",1,"SP-220810",null,"Lalith kumar, Samsung ","lalith.kumar@samsung.com ","; 10/12/22: 0%->100","23.501; 23.502 ",97,49,null,null,"Sat 10/12/22","Sat 10/12/22"]
[1242,980088,"   CT1 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C1","Fri 16/12/22","Sat 09/09/23",1,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com","; 6/6/23: Compl:90%->95%","24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1243,980089,"   CT3 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C3","Fri 16/12/22","Sat 09/09/23",1,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com","; 9/6/23: 60%->80","24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1244,980090,"   CT4 aspects of Seamless UE context recovery ","SUECR",2,"Rel-18","C4","Fri 16/12/22","Sat 09/09/23",1,"CP-223113",null,"Hashmi, Danish Ehsan, Samsung","danis.hashmi@samsung.com",null,"24.501; 27.007; 29.122; 29.522; 29.518",97,49,null,null,"Sun 11/09/22","NA"]
[1245,980115,"5G System Enabler for Service Function Chaining ","SFC",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-220802",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","NA"]
[1246,970012,"   Stage 2 of 5G System Enabler for Service Function Chaining ","SFC",2,"Rel-18","S2","Fri 09/09/22","Tue 06/06/23",1,"SP-230120",null,"Meghashree Dattatri Kedalagudde, Intel ","meghashree.dattatri.kedalagudde@intel.com ","; 9/1/23: WID:SP-220802->SP-221336; 15/3/23: 0%->60; 15/3/23: WID:SP-221336->SP-230120; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 60%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Sat 10/12/22","Thu 08/06/23"]
[1247,980091,"   CT3 aspects of SFC","SFC",2,"Rel-18","C3","Fri 16/12/22","Sun 03/03/24",1,"CP-231193",null,"Yue Sun, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:10%->90%; 6/6/23: CD:12/12/2023->03/03/2024; 6/6/23: WID: CP-223210->CP-231193. 2/4/23: rapporteur: Thomas Luetzenkirchen, Intel-> Yue Sun, China Telecom","29.244; 29.512; 29.513; 29.514; 29.519; 29.522",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1248,980092,"   CT4 aspects of SFC","SFC",2,"Rel-18","C4","Mon 20/12/21","Tue 12/12/23",1,"CP-231193",null,"Yue Sun, China Telecom","suny20@chinatelecom.cn","; 6/6/23: Compl:100%->80%; 6/6/23: CD:12/12/2022->12/12/2023; 6/6/23: WID: CP-223210->CP-231193. 2/4/23: rapporteur: Thomas Luetzenkirchen, Intel-> Yue Sun, China Telecom","29.244; 29.512; 29.513; 29.514; 29.519; 29.522",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1249,940052,"   Study on System Enabler for Service Function Chaining ","FS_SFC",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220415",null,"Meghashree D Kedalagudde, Intel","meghashree.dattatri.kedalagudde@intel.com","21/1/22: 23.700-18 added;; 12/3/22: 0%->25; 4/6/22: 25%->60; 21/6/22: WID:SP-211594->SP-220415: rap change; 12/9/22: 60%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-18",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[1250,940054,"Study on Extensions to the TSC Framework to support Deterministic Networking (DetNet)","FS_DetNet",1,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211633",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ","21/1/22: 23.700-46 added;; 12/3/22: 0%->10; 4/6/22: 10%->70; 12/9/22: 70%->90; 12/9/22: FCD:12/09/2022->12/22; 15/3/23: 90%->100","23.700-46",94,48,null,null,"Sun 19/12/21","Wed 15/03/23"]
[1251,980119,"Extensions to the TSC Framework to support DetNet ","DetNet",1,"Rel-18",null,"Thu 08/09/22","Sun 03/03/24",1,"SP-220801",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ",null,"23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","NA"]
[1252,970011,"   Stage 2 of Extensions to the TSC Framework to support DetNet ","DetNet",2,"Rel-18","S2","Thu 08/09/22","Tue 06/06/23",1,"SP-230172",null,"Miklós, György, Ericsson ","gyorgy.miklos@ericsson.com ","; 15/3/23: WID:SP-220801->SP-230172; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Sat 10/12/22","Thu 08/06/23"]
[1253,980093,"   CT1 aspects of Detnet","DetNet",2,"Rel-18","C1","Fri 16/12/22","Tue 12/12/23",1,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:90%->100%; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1254,980094,"   CT3 aspects of Detnet","DetNet",2,"Rel-18","C3","Fri 16/12/22","Sun 03/03/24",1,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:50%->80%; 6/6/23: CD:12/12/2023->03/03/2024; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1255,1020064,"      (IETF) CT3 part of DetNet (draft-ietf-detnet-yang)","DetNet",3,"Rel-18","C3-IETF","Fri 16/12/22","Sun 03/03/24",1,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","CT3 part complete. SA2 reference cleanup pending","29.513, 29.565",97,49,null,null,"Sun 11/09/22","Tue 02/04/24"]
[1256,980095,"   CT4 aspects of Detnet","DetNet",2,"Rel-18","C4","Fri 16/12/22","Tue 12/12/23",1,"CP-231195",null,"Fuencisla García, Ericsson","fuencisla.garcia@ericsson.com","; 6/6/23: Compl:10%->80%; 6/6/23: WID: CP-223206->CP-231195","24.539; 29.244; 29.513; 29.512; 29.514",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1257,980117,"Multiple location report for MT-LR Immediate Location Request for regulatory services ","TEI18_MLR",1,"Rel-18",null,"Thu 08/09/22","Tue 06/06/23",1,"SP-220795",null,"Joul, Christopher, T-Mobile USA ","chris.joul@t-mobile.com ",null,23.273,97,49,null,null,"Sun 11/09/22","NA"]
[1258,970005,"   Stage 2 of TEI18_MLR","TEI18_MLR",2,"Rel-18","S2","Thu 08/09/22","Mon 12/12/22",1,"SP-220795",null,"Joul, Christopher, T-Mobile USA ","chris.joul@t-mobile.com ","; 10/12/22: 0%->100",23.273,97,49,null,null,"Sat 10/12/22","Sat 10/12/22"]
[1259,980002,"   CT4 aspects on TEI18_MLR","TEI18_MLR",2,"Rel-18","C4","Fri 16/12/22","Tue 06/06/23",1,"CP-223022",null,"Jones Yunjie, Lu, Ericsson","jones.lu@ericsson.com","; 6/6/23: Compl:80%->100%; 6/6/23: CD:12/12/2023->06/06/2023","29.571; 29.518",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1260,980120,"TEI18 on Enhancement of Application Detection Event Exposure ","TEI18_ADEE",1,"Rel-18",null,"Thu 08/09/22","Tue 06/06/23",1,"SP-220796",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ",null,"23.503; 23.502 ",97,49,null,null,"Sun 11/09/22","NA"]
[1261,970006,"   Stage 2 of TEI18_ADEE","TEI18_ADEE",2,"Rel-18","S2","Thu 08/09/22","Fri 03/03/23",1,"SP-220796",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","; 22/3/23: 0%->100","23.503; 23.502 ",97,49,null,null,"Sat 10/12/22","Wed 22/03/23"]
[1262,980030,"   CT3 aspects of TEI18_ADEE","TEI18_ADEE",2,"Rel-18","C3","Thu 15/12/22","Tue 06/06/23",1,"CP-223202",null,"Zhenning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:0%->100%","29.522; 29.514; 29.512",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1263,980121,"General Support of IPv6 Prefix Delegation in 5GS ","TEI18_IPv6PD",1,"Rel-18",null,"Thu 08/09/22","Tue 12/12/23",1,"SP-220797",null,"Gan, Judy, Ericsson ","Judy.Gan.Juying@ericsson.com ",null,"23.501; 23.502; 23.503; 23.304; 23.316 ",97,49,null,null,"Sun 11/09/22","NA"]
[1264,970007,"   Stage 2 of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","S2","Thu 08/09/22","Fri 03/03/23",1,"SP-220797",null,"Gan, Judy, Ericsson ","Judy.Gan.Juying@ericsson.com ","; 22/3/23: 0%->100","23.501; 23.502; 23.503; 23.304; 23.316 ",97,49,null,null,"Sat 10/12/22","Wed 22/03/23"]
[1265,980096,"   CT1 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C1","Fri 16/12/22","Tue 12/12/23",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ","; 6/6/23: Compl:95%->100%; 6/6/23: WID: CP-223203->CP-230121","24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1266,980097,"   CT3 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C3","Fri 16/12/22","Tue 12/12/23",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ",null,"24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,null,"Sun 11/09/22","NA"]
[1267,980098,"   CT4 aspects of TEI18_IPv6PD","TEI18_IPv6PD",2,"Rel-18","C4","Fri 16/12/22","Tue 12/12/23",1,"CP-230121",null,"Maria Tianmei, Liang, Ericsson","Maria.liang@ericsson.com ",null,"24.501; 29.561; 29.512; 29.521; 29.244; 29.513",97,49,null,null,"Sun 11/09/22","NA"]
[1268,980118,"Secondary DN Authentication and authorization in EPC IWK cases ","TEI18_SDNAEPC",1,"Rel-18",null,"Thu 08/09/22","Sun 03/03/24",1,"SP-220798",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ",null,"23.501; 23.502 ",97,49,null,null,"Sun 11/09/22","NA"]
[1269,970008,"   Stage 2 of Secondary DN Authentication and authorization in EPC IWK cases ","TEI18_SDNAEPC",2,"Rel-18","S2","Thu 08/09/22","Mon 12/12/22",1,"SP-220798",null,"Laurent Thiebaut, Nokia ","Laurent.thiebaut@nokia.com ","; 10/12/22: 0%->100","23.501; 23.502 ",97,49,null,null,"Sat 10/12/22","Sat 10/12/22"]
[1270,980099,"   CT1 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C1","Fri 16/12/22","Sun 03/03/24",1,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ","; 6/6/23: Compl:80%->90%","24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1271,980100,"   CT3 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C3","Fri 16/12/22","Sun 03/03/24",1,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ","; 9/6/23: 96%->","24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,null,"Sun 11/09/22","Fri 09/06/23"]
[1272,980101,"   CT4 aspects of TEI18_SDNAEPC","TEI18_SDNAEPC",2,"Rel-18","C4","Fri 16/12/22","Sun 03/03/24",1,"CP-230188",null,"Nassar, Mohamed A.(Nokia)","mohamed.a.nassar@nokia.com ",null,"24.501; 24.301; 24.008; 29.561; 29.274",97,49,null,null,"Sun 11/09/22","NA"]
[1273,990116,"Message Service within the 5G system (MSGin5G) Phase 2","5GMARCH_Ph2",1,"Rel-18",null,"Thu 10/03/22","Tue 12/12/23",1,"SP-220330",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 4/6/22: 0%->30; 12/9/22: 30%->55; 11/12/22: 55%->70",23.553999999999998,95,48,null,null,"Thu 10/03/22","Sun 11/12/22"]
[1274,950026,"   Stage 2 of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","S6","Thu 10/03/22","Fri 03/03/23",1,"SP-220330",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 4/6/22: 0%->30; 12/9/22: 30%->55; 11/12/22: 55%->70; 17/3/23: 70%->80; 8/6/23: 80%->100",23.553999999999998,95,48,null,null,"Thu 10/03/22","Thu 08/06/23"]
[1275,990019,"   CT1 aspects of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","C1","Mon 13/03/23","Tue 12/12/23",1,"CP-230198",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 6/6/23: Compl:0%->15%","24.538; 24.544; 24.546; 29.538; 29.222",95,48,null,null,"Thu 10/03/22","Tue 06/06/23"]
[1276,990099,"   CT3 aspects of 5GMARCH_Ph2","5GMARCH_Ph2",2,"Rel-18","C3","Mon 13/03/23","Tue 12/12/23",1,"CP-230198",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","9/6/23: 0%->80","24.538; 24.544; 24.546; 29.538; 29.222",95,48,null,null,"Thu 10/03/22","Fri 09/06/23"]
[1277,990041,"   Security aspects of MSGin5G Ph2 ","5GMARCH_Ph2_SEC",2,"Rel-18","S3","Thu 02/02/23","Fri 03/03/23",1,"SP-230154",null,"Huang Xiaoting, China Mobile ","huangxiaoting@chinamobile.com ","; 8/6/23: 0%->100",33.500999999999998,99,50,null,null,"Thu 16/03/23","Thu 08/06/23"]
[1278,910039,"5G Timing Resiliency System ","5TRS",1,"Rel-18",null,"Thu 25/06/20","Sun 03/03/24",1,"SP-210211",null,"Betsy Covell, Nokia ","betsy.covell@nokia.com ",null,"22.261; 22.104 ",91,46,null,null,"Thu 18/03/21","NA"]
[1279,880037,"   Study on 5TRS","FS_5TRS",2,"Rel-18","S1","Thu 25/06/20","Fri 12/03/21",1,"SP-200573",null,"Betsy Covell, Nokia","betsy.covell@nokia.com","28/7/20: 22.878 added;; 12/9/20: 0%->10; 5/12/20: 10%->75; 19/3/21: FCD:16/12/2020->03/21; 19/3/21: 75%->97; 11/6/21: 97%->100",22.878,88,45,null,null,"Thu 25/06/20","Fri 11/06/21"]
[1280,940055,"   Study on 5G Timing Resiliency and TSC&URLLC enhancements ","FS_5TRS_URLLC",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211634",null,"Devaki Chandramouli ","Devaki.chandramouli@nokia.com ","21/1/22: 23.700-25 added;; 12/3/22: 0%->25; 4/6/22: 25%->65; 12/9/22: 65%->83; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 83%->98; 15/3/23: 98%->100","23.700-25",94,48,null,null,"Sun 19/12/21","Wed 15/03/23"]
[1281,910033,"   Stage 1 for 5TRS","5TRS",2,"Rel-18","S1","Thu 18/03/21","Fri 10/09/21",1,"SP-210211",null,"Betsy Covell, Nokia ","betsy.covell@nokia.com ","; 11/6/21: 0%->100","22.261; 22.104 ",91,46,null,null,"Thu 18/03/21","Fri 11/06/21"]
[1282,970024,"   Stage 2 of Timing Resiliency and URLLC enhancements ","TRS_URLLC",2,"Rel-18","S2","Mon 12/09/22","Fri 03/03/23",1,"SP-230107",null,"Devaki Chandramouli ","Devaki.chandramouli@nokia.com ","; 10/12/22: 0%->50; 9/1/23: WID:SP-220814->SP-221341; 15/3/23: 50%->80; 15/3/23: WID:SP-221341->SP-230107; 8/6/23: 80%->100","23.501; 23.502; 23.503 ",97,49,null,null,"Sun 11/09/22","Thu 08/06/23"]
[1283,980102,"   CT1 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C1","Fri 16/12/22","Sun 03/03/24",1,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:70%->95%; 6/6/23: WID: CP-223205->CP-231198; 30/6/23: WID:CP-231198->CP-231360","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244.24.539",97,49,null,null,"Sun 11/09/22","Fri 30/06/23"]
[1284,980103,"   CT3 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C3","Fri 16/12/22","Sun 03/03/24",1,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:25%->75%; 6/6/23: WID: CP-223205->CP-231198","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244.24.539",97,49,null,null,"Sun 11/09/22","Tue 06/06/23"]
[1285,980104,"   CT4 aspects of TRS_URLLC","TRS_URLLC",2,"Rel-18","C4","Fri 16/12/22","Tue 12/12/23",1,"CP-231360",null,"Apostolos Papageorgiou (Nokia) ","apostolos.papageorgiou@nokia.com ","; 6/6/23: Compl:40%->55%; 6/6/23: WID: CP-223205->CP-231198; 30/6/23: 29.585 added;","24.501; 29.122; 29.507; 29.512; 29.513; 29.514; 29.522; 29.534; 29.565; 29.503; 29.504; 29.505; 29.518; 29.571; 29.244; 29.585",97,49,null,null,"Sun 11/09/22","Fri 30/06/23"]
[1286,950028,"Study on Management Aspects of URLLC ","FS_URLLC_Mgt",1,"Rel-18","S5","Thu 10/03/22","Tue 06/06/23",1,"SP-230772",null,"Wang,Zhaoning,China Unicom ","wangzn18@chinaunicom.cn ","5/4/22: 28.832 added;; 4/6/22: 0%->15; 12/9/22: 15%->40; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 40%->60; 17/3/23: 60%->62; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 62%->100; 30/6/23: WID:SP-220146->SP-230772",28.832000000000001,95,48,null,null,"Thu 10/03/22","Fri 30/06/23"]
[1287,940088,"Study on enhancement for resiliency of gNB-CU (Central Unit)-CP (Control Plane)","FS_gNB_CU_CP_resiliency",1,"Rel-18","R3","Mon 13/12/21","Thu 22/09/22",1,"RP-222249","RP-221439","Masato Taniguchi, NTT DOCOMO, INC.","masato.taniguchi.mf@nttdocomo.com","; 22/3/22: CD:12/09/2022->12/09/2023; 22/3/22: Stat Rep: ->RP-2205556/6/22: CD:12/09/2023->22/09/20226/6/22: Stat Rep: RP-220555->RP-221439; 20/6/22: Rapporteur: NTT DOCOMO->Masato Taniguchi, NTT DOCOMO, INC.; Rap eMail: ->masato.taniguchi.mf@nttdocomo...",38.878999999999998,94,48,null,null,"Thu 06/01/22","Fri 23/09/22"]
[1288,991036,"NR Timing Resiliency and URLLC enhancements ","TRS_URLLC-NR",1,"Rel-18","R3","Fri 03/03/23","Tue 12/12/23",1,"RP-232863",null,"Nokia ",null,"2/1/24: WID:RP-230754->RP-232863",null,99,50,null,null,"Wed 29/03/23","Tue 02/01/24"]
[1289,991136,"   Core part: NR Timing Resiliency and URLLC enhancements ","TRS_URLLC-NR-Core",2,"Rel-18","R3","Fri 03/03/23","Tue 12/12/23",1,"RP-232863","RP-232864","Sean Kelley, Nokia","sean.kelley@nokia.com","; ...; 6/9/23: Compl:25%->60%; WID: RP-230754->RP-231106; Stat Rep: ->RP-231581; Rapporteur: Nokia->Sean Kelley, Nokia; Rap eMail: ->sean.kelley@nokia.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-231581->RP-232864; ",null,99,50,null,null,"Wed 29/03/23","Fri 08/12/23"]
[1290,930028,"Vehicle-Mounted Relays ","VMR",1,"Rel-18",null,"Wed 16/09/20","Sun 03/03/24",1,"SP-211054",null,"Francesco Pica, Qualcomm ","fpica@qti.qualcomm.com ",null,22.260999999999999,93,47,null,null,"Fri 10/09/21","NA"]
[1291,890022,"   Study on VMR","FS_VMR",2,"Rel-18","S1","Wed 16/09/20","Wed 08/09/21",1,"SP-200798",null,"Francesco Pica ","fpica@qti.qualcomm.com ","5/12/20: 0%->35; 19/3/21: FCD:11/06/2021->09/21; 19/3/21: 35%->60; 11/6/21: 60%->85; 13/9/21: 85%->100",22.838999999999999,89,45,null,null,"Thu 10/09/20","Mon 13/09/21"]
[1292,930021,"   Stage 1 of VMR","VMR",2,"Rel-18","S1","Fri 10/09/21","Fri 10/12/21",1,"SP-211054",null,"Francesco Pica, Qualcomm ","fpica@qti.qualcomm.com ","; 13/9/21: 0%->95; 14/12/21: 95%->100",22.260999999999999,93,47,null,null,"Fri 10/09/21","Tue 14/12/21"]
[1293,980018,"   (Stage 2 for VMR) Architecture Enhancements for Vehicle Mounted Relays","VMR",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-230105",null,"Cheng, Hong, Qualcomm Incorporated, ","hongc@qti.qualcomm.com ","; 10/12/22: 0%->20; 15/3/23: WID:SP-221328->SP-230105; 15/3/23: 20%->40; 8/6/23: 40%->100; 4/1/24: 28.875 added;","23.501; 23.502; 23.503; 23.273 ; 28.875",98,50,null,null,"Fri 09/12/22","Thu 04/01/24"]
[1294,990013,"   CT1 aspects of VMR","VMR",2,"Rel-18","C1","Mon 13/03/23","Sun 03/03/24",1,"CP-232168",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","; 6/6/23: Compl:0%->20%","23.122.23.041.24.501.24.526.27.007.29.513.29.519.29.522.29.525.23.008.29.503.29.505.29.510.29.515.29.518.29.571.29.572",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1295,990102,"   CT4 aspects of VMR","VMR",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-232168",null,"Kim, Sunghoon, Qualcomm Incorporated","sunghoon@qti.qualcomm.com","; 6/6/23: Compl:0%->25%","23.122.23.041.24.501.24.526.27.007.29.513.29.519.29.522.29.525.23.008.29.503.29.505.29.510.29.515.29.518.29.571.29.572",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1296,940057,"   Study on Architecture Enhancements for Vehicle Mounted Relays ","FS_VMR",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-211636",null,"Cheng, Hong, Qualcomm Incorporated, ","hongc@qti.qualcomm.com ","21/1/22: 23.700-05 added;; 12/3/22: 0%->20; 4/6/22: 20%->55; 12/9/22: 55%->80; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 80%->100","23.700-05",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[1297,941009,"Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB",1,"Rel-18",null,"Mon 13/12/21","Thu 06/06/24",1,"RP-240104",null,"Qualcomm",null,"compare REL-16 WI NR_IAB and REL-17 WI NR_IAB_enh; no Perf. part; 5/4/22: WID:RP-213601->RP-220843; 12/7/22: WID:RP-220843->RP-221815; 23/9/22: WID:RP-221815->RP-222671; 6/10/23: WID:RP-222671->RP-232643; 2/1/24: WID:RP-232643->RP-233320; 2/4/24: WID:RP-2",null,94,48,null,null,"Thu 06/01/22","Tue 02/04/24"]
[1298,941109,"   Core part: Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB-Core",2,"Rel-18","R3","Mon 13/12/21","Tue 12/12/23",1,"RP-240319","RP-241123","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","compare REL-16 WI NR_IAB and REL-17 WI NR_IAB_enh;; 22/3/22: Stat Rep: ->RP-220430 6/6/22: CD:12/12/2023->23/12/2022 6/6/22: Stat Rep: RP- ; 20/6/22: Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com13...;...",null,94,48,null,null,"Thu 06/01/22","Thu 13/06/24"]
[1299,941209,"   Perf. part: Mobile IAB (Integrated Access and Backhaul) for NR","NR_mobile_IAB-Perf",2,"Rel-18","R3","Wed 15/12/21","Thu 06/06/24",1,"RP-240319","RP-241123","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220430 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220430->RP ; 20/6/22: WG: R4->R3; Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualco...",null,94,48,null,null,"Thu 06/01/22","Thu 13/06/24"]
[1300,941008,"Enhancement on NR QoE management and optimizations for diverse services","NR_QoE_enh",1,"Rel-18",null,"Mon 13/12/21","Tue 12/12/23",1,"RP-223488",null,"China Unicom",null,"compare REL-17 WI NR_QoE-Core; QoE = Quality of Experience; no Perf. part; 12/7/22: WID:RP-213594->RP-221803; 9/1/23: WID:RP-221803->RP-223488",null,94,48,null,null,"Thu 06/01/22","Mon 09/01/23"]
[1301,941108,"   Core part: Enhancement on NR QoE management and optimizations for diverse services","NR_QoE_enh-Core",2,"Rel-18","R3","Mon 13/12/21","Tue 12/12/23",1,"RP-223488","RP-233603","Pei Li, China Unicom","lip104@chinaunicom.cn","compare REL-17 WI NR_QoE-Core; QoE = Quality of Experience; no Perf. part; 20/6/22: FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221244; Rapporteur: China Unicom->Pei Li, China Unicom; Rap eMail: ->lip104@chinaunicom.cn13/7/22: FCD:23/12/2022->12/20;...;...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1302,940032,"Study on Key Quality Indicators (KQIs) for 5G service experience ","FS_KQI_5G",1,"Rel-18","S5","Mon 13/12/21","Sun 03/03/24",1,"SP-231432",null,"Man WANG, Huawei ","wangman1@huawei.com ","7/1/22: 28.863 added;; 4/6/22: 0%->10; 12/9/22: 10%->20; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 20%->35; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 35%->; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 35%->65; 8/12/23: 65%->100; 3/1/24: WID:SP-211433->SP-231432",28.863,94,48,null,null,"Mon 13/12/21","Wed 03/01/24"]
[1303,950031,"Additional NRM features phase 2 ","AdNRM_ph2",1,"Rel-18","S5","Thu 10/03/22","Sun 03/03/24",1,"SP-231440",null,"Sean Sun, Nokia ","sean.sun@nokia-sbell.com ","4/6/22: 0%->7; 12/9/22: 7%->30; 12/9/22: FCD:11/03/2022->03/23; 11/12/22: 30%->55; 17/3/23: 55%->65; 8/6/23: 65%->80; 8/6/23: FCD:03/03/2023->/24; 8/6/23: 80%->; 7/9/23: 80%->88; 8/12/23: 88%->99; 3/1/24: WID:SP-220351->SP-231440; 14/3/24: 99%->100",null,95,48,null,null,"Thu 10/03/22","Thu 14/03/24"]
[1304,940031,"MPS when access to EPC/5GC is WLAN ","MPS_WLAN",1,"Rel-18",null,"Fri 10/09/21","Tue 03/03/26",0.79,"SP-211057",null,"Singh, Ray; Peraton Labs ","rsingh@peratonlabs.com ",null,null,94,48,null,null,"Fri 10/09/21","Fri 07/01/22"]
[1305,930024,"   Stage 1 of MPS_WLAN","MPS_WLAN",2,"Rel-18","S1","Fri 10/09/21","Fri 10/12/21",1,"SP-211057",null,"Singh, Ray; Peraton Labs ","rsingh@peratonlabs.com ","10/12/21: 0%->100",22.152999999999999,93,47,null,null,"Fri 10/09/21","Fri 10/12/21"]
[1306,940053,"   Stage 2 of MPS_WLAN","MPS_WLAN",2,"Rel-18","S2","Mon 20/12/21","Tue 06/06/23",1,"SP-230108",null,"Robert C Streijl; Peraton Labs ","rstreijl@peratonlabs.com ","; 10/12/22: 0%->0; 10/12/22: FCD:12/09/2022->03/23; 15/3/23: 0%->50; 15/3/23: WID:SP-211595->SP-230108; 15/3/23: FCD:03/03/2023->/23; 8/6/23: 50%->100","23.401; 23.402; 23.501; 23.502 ",94,48,null,null,"Sun 19/12/21","Thu 08/06/23"]
[1307,1000021,"   CT1 aspects of MPS_WLAN","MPS_WLAN",2,"Rel-18","C1","Wed 07/06/23","Sun 03/03/24",1,"CP-240299",null,"Monnes, Peter, Peraton Labs ","pmonnes@peratonlabs.com ",null,"23.003; 24.302; 24.502; 29.273 ",100,51,null,null,"Wed 07/06/23","NA"]
[1308,1000046,"   CT4 aspects of MPS_WLAN","MPS_WLAN",2,"Rel-18","C4","Wed 07/06/23","Sun 03/03/24",1,"CP-240299",null,"Monnes, Peter, Peraton Labs ","pmonnes@peratonlabs.com ",null,"23.003; 24.302; 24.502; 29.273 ",100,51,null,null,"Wed 07/06/23","NA"]
[1309,1030049,"   CT6 aspects of MPS_WLAN","MPS_WLAN",2,"Rel-18","C6","Wed 07/06/23","Sun 03/03/24",1,"CP-240299",null,"Monnes, Peter, Peraton Labs ","pmonnes@peratonlabs.com ",null,"23.003; 24.302; 24.502; 29.273 ",100,51,null,null,"Wed 07/06/23","NA"]
[1310,1080075,"   UE Conformance - MPS when access to EPC/5GC is WLAN ","MPS_WLAN-UEConTest",2,"Rel-18","R5","Fri 06/06/25","Tue 03/03/26",0,"RP-250893",null,"China Telecom ",null,"MPS = Multimedia Priority Service; tested: CT1 REL-18 WI MPS_WLAN ",null,108,55,null,null,"Fri 18/07/25","NA"]
[1311,941007,"Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh2",1,"Rel-18",null,"Fri 01/01/21","Tue 12/12/23",1,"RP-233438",null,"CMCC",null,"compare REL-16 WI NR_SON_MDT-Core and REL-17 WI NR_ENDC_SON_MDT_enh-Core; no Perf. part; 5/4/22: WID:RP-213553->RP-221000; 12/7/22: WID:RP-221000->RP-221825; 2/1/24: WID:RP-221825->RP-233438",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1312,941107,"   Core part: Further enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh2-Core",2,"Rel-18","R3","Fri 01/01/21","Tue 12/12/23",1,"RP-233438","RP-233437","Liang LIU, CMCC","liuliang@chinamobile.com","compare REL-16 WI NR_SON_MDT-Core and REL-17 WI NR_ENDC_SON_MDT_enh-Core; no Perf. part; 20/6/22: FCD:31/12/2021->23/12/2022; Stat Rep: ->RP-221372; Rapporteur: CMCC->Liang LIU, CMCC; Rap eMail: ->liuliang@chinamobile.com13/7/22: FCD:23/12/2022->12...;...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1313,950064,"   UE Conformance - Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity) ","NR_ENDC_SON_MDT_enh-UEConTest",2,"Rel-17","R5","Tue 15/03/22","Fri 22/09/23",1,"RP-233438","RP-232241","Danni Song, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_ENDC_SON_MDT_enh 6/6/22: Compl:0%->5% 6/6/22: CD:15/06/2 ; 20/6/22: Rapporteur: CMCC->Luting Kong, CMCC; Rap eMail: ->kongluting@chinamobile.com12/7/22: WID:RP-220620->RP-221365 ...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:7%-...",null,95,48,null,null,"Tue 05/04/22","Fri 06/10/23"]
[1314,940030,"Self-Configuration of RAN Network Entities ","RANSC",1,"Rel-18","S5","Fri 10/12/21","Sun 03/03/24",1,"SP-211431",null,"Hu, Yaxi, China Mobile ","huyaxi@cmdi.chinamobile.com ","; 7/1/22: 28.317 added;; 4/6/22: 0%->5; 11/12/22: 5%->45; 17/3/23: 45%->50; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 50%->55; 8/6/23: 55%->55; 7/9/23: 55%->65; 8/12/23: 65%->90; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 90%->100","28.313; ; 28.317",94,48,null,null,"Fri 10/12/21","Thu 14/03/24"]
[1315,900028,"Support for Service Function Chaining ","SFChain",1,"Rel-18","S1","Fri 04/12/20","Fri 12/03/21",1,"SP-201040",null,"Ellen Liao; Intel ","ellen.c.liao at intel.com ","22.261; 22.101; 22.115 ; 5/12/20: 0%->100",null,90,46,null,null,"Fri 04/12/20","Sat 05/12/20"]
[1316,910035,"Data Integrity in 5GS ","DI_5G",1,"Rel-18","S1","Thu 18/03/21","Thu 25/03/21",1,"SP-210213",null,"Qun wei, China Unicom ","Weiqun5 <at> chinaunicom.cn ","; 19/3/21: 0%->100",22.260999999999999,91,46,null,null,"Thu 18/03/21","Fri 19/03/21"]
[1317,920033,"Signal level Enhanced Network Selection ","SENSE",1,"Rel-18","S1","Fri 16/09/22","Fri 01/03/24",1,"SP-210525",null,"Bischinger, Kurt; Deutsche Telekom ","kurt.bischinger@magenta.at ","; 11/6/21: 0%->40; 10/12/21: 40%->100",22.010999999999999,92,47,null,null,"Fri 11/06/21","Fri 10/12/21"]
[1318,970059,"   CT1 aspects of SENSE","SENSE",2,"Rel-18","C1","Fri 16/12/22","Tue 06/06/23",1,"CP-222237",null,"Reinhard Lauster, Deutsche Telekom","reinhard.lauster@magenta.at","; 6/6/23: Compl:65%->95%; 6/6/23: CD:16/12/2022->06/06/2023","23.122; 24.501; 27.007",97,49,null,null,"Mon 19/09/22","Tue 06/06/23"]
[1319,970060,"   CT6 aspects of SENSE","SENSE",2,"Rel-18","C6","Fri 16/09/22","Fri 16/09/22",1,"CP-222237",null,"Reinhard Lauster, Deutsche Telekom","reinhard.lauster@magenta.at",null,31.102,97,49,null,null,"Mon 19/09/22","NA"]
[1320,1010052,"   UE Conformance - Signal level Enhanced Network Selection ","SENSE-UEContest",2,"Rel-18","R5","Sat 09/09/23","Fri 01/03/24",1,"RP-233770","RP-240288","Ya Zhao, Huawei Technologies. Co., Ltd","zhaoya@hisilicon.com","8/12/23: Compl:0%->5%; Stat Rep: ->RP-233769; Rapporteur: Huawei->Ya Zhao, Huawei Technologies. Co., Ltd; Rap eMail: ->zhaoya@hisilicon.com; ; 2/1/24: WID:RP-232362->RP-233770; 14/3/24: FCD:05/06/2024->01/03/2024; Compl:5%->100%; Stat Rep: RP-233769->RP-",null,101,51,null,null,"Fri 06/10/23","Thu 14/03/24"]
[1321,940017,"SECAM and SCAS for 3GPP virtualized network products ","VNP_SECAM_SCAS",1,"Rel-18","S3","Fri 10/12/21","Fri 03/03/23",1,"SP-211365",null,"Qi Minpeng, China Mobile ","qiminpeng@chinamobile.com ","7/1/22: 33.527 added;; 12/9/22: 0%->40; 11/12/22: 40%->65; 17/3/23: 65%->75; 15/3/24: 75%->100","33.527; 33.927; 33.936",94,48,null,null,"Fri 10/12/21","Fri 15/03/24"]
[1322,950016,"Security Assurance Specification (SCAS) for 5G Rel-17 Features ","SCAS_5G_Ph2",1,"Rel-18","S3","Thu 10/03/22","Mon 12/12/22",1,"SP-220192",null,"Rong Wu, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ","; 4/6/22: 0%->10; 17/3/23: 10%->30; 15/3/24: 30%->100","33.926; 33.117; 33.511; 33.512; 33.513; 33.514; 33.515; 33.516; 33.517; 33.518; 33.519; 33.520; 33.521; 33.522; 33.326 ",95,48,null,null,"Thu 10/03/22","Fri 15/03/24"]
[1323,960035,"Study on URSP rules to securely identify applications ","FS_USIA",1,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220533",null,"Andreas Kunz, Lenovo ","akunz@lenovo.com ","13/7/22: 33.892 added;; 12/9/22: 0%->30; 11/12/22: 30%->50; 17/3/23: 50%->80; 7/9/23: 80%->100",33.892000000000003,96,49,null,null,"Thu 02/06/22","Thu 07/09/23"]
[1324,810032,"Study on 5G security enhancement against false base stations","FS_5GFBS",1,"Rel-18","S3","Thu 06/09/18","Fri 09/12/22",1,"SP-180690",null,"Ivy Guo, Apple","ivy_guo@apple.com","7/12/18: 0%->10¦20/3/19: FCD:019->09/19¦20/3/19: 10%->50; 31/5/19: 50%->65; 13/9/19: 65%->66; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 66%->75; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: 75%->80; 26/6/20: FCD:12/03/2020->12/20; ; ","New",81,41,null,null,"Thu 06/09/18","Thu 08/06/23"]
[1325,960040,"Security Enhancement on RRCResumeRequest Message Protection ","SERP",1,"Rel-18","S3","Thu 02/06/22","Mon 12/12/22",1,"SP-220538",null,"Ivy Guo, Apple ","<ivy_guo@apple.com> ","7/9/23: 0%->100",null,96,49,null,null,"Thu 02/06/22","Thu 07/09/23"]
[1326,960055,"Stage-3 5GS NAS protocol development 18 ","5GProtoc18",1,"Rel-18",null,"Fri 03/06/22","Tue 12/12/23",1,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 6/6/23: Compl:30%->40%","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1327,960007,"   Stage-3 5GS NAS protocol development 18 general aspects","5GProtoc18",2,"Rel-18","C1","Fri 03/06/22","Tue 12/12/23",1,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"Fri 03/06/22","NA"]
[1328,960056,"   Stage-3 5GS NAS protocol development 18 non 3GPP aspects","5GProtoc18-non3GPP",2,"Rel-18","C1","Fri 03/06/22","Tue 12/12/23",1,"CP-221268",null,"Sedlacek, Ivo, Ericsson, ","ivo <dot> sedlacek <at> ericsson <dot> com ",null,"23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ",96,49,null,null,"Fri 03/06/22","NA"]
[1329,960057,"Stage-3 SAE Protocol Development ","SAES18",1,"Rel-18",null,"Fri 03/06/22","Tue 12/12/23",1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,"; 6/6/23: Compl:30%->40%","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1330,960008,"   Stage-3 SAE Protocol Development general","SAES18",2,"Rel-18","C1","Fri 03/06/22","Tue 12/12/23",1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"Fri 03/06/22","NA"]
[1331,960058,"   Stage-3 SAE Protocol Development CSFB","SAES18-CSFB",2,"Rel-18","C1","Fri 03/06/22","Tue 12/12/23",1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"Fri 03/06/22","NA"]
[1332,960059,"   Stage-3 SAE Protocol Development non 3GPP","SAES18-non3GPP",2,"Rel-18","C1","Fri 03/06/22","Tue 12/12/23",1,"CP-221269",null,"Sethi, Anuj, InterDigital ",null,null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",96,49,null,null,"Fri 03/06/22","NA"]
[1333,960009,"Protocol enhancements for Mission Critical Services ","MCProtoc18",1,"Rel-18",null,"Fri 03/06/22","Sun 03/03/24",1,"CP-232163",null,"AXELL, Jörgen, Ericsson","jorgen.axell@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"Fri 03/06/22","Mon 20/06/22"]
[1334,980105,"   CT1 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C1","Fri 03/06/22","Sun 03/03/24",1,"CP-233212",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 9/6/23: 30%->40","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"Fri 03/06/22","Fri 09/06/23"]
[1335,980106,"   CT3 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C3","Mon 06/06/22","Sun 03/03/24",1,"CP-233212",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 9/6/23: 10%->30","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"Fri 03/06/22","Fri 09/06/23"]
[1336,980107,"   CT4 aspects of MCProtoc18","MCProtoc18",2,"Rel-18","C4","Fri 03/06/22","Sun 03/03/24",1,"CP-233212",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","; 20/6/22: FCD:12/12/2023->08/12/2023Rapporteur: ->AXELL, Jörgen, EricssonRap eMail: ->jorgen.axell@ericsson.comList of Impacted TS & TR updated; 6/6/23: Compl:...","24.229; 24.281; 24.282; 24.379; 24.380; 24.481; 24.482; 24.483; 24.484; 24.581; 24.582; 29.379; 29.380; 29.582; 29.165; 29.283",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1337,960010,"MPS for Supplementary Services ","MPSSupServ",1,"Rel-18","C1","Fri 03/06/22","Thu 08/12/22",1,"CP-221271",null,"Peter Monnes, Peraton Labs","pmonnes@peratonlabs.com","20/6/22: FCD:12/12/2022->08/12/2022WID: C1-221271->CP-221271Rapporteur: Peter Monnes, Peraton Labs ->Peter Monnes, Peraton LabsRap eMail: pmonnes@peratonlabs.com ->pmonnes@peratonlabs.comList of Impacted TS & TR updated","24.229; 24.173; 24.629; 24.605; 24.239; 24.604; 24.642",96,49,null,null,"Fri 03/06/22","Mon 20/06/22"]
[1338,970035,"IMS Stage-3 IETF Protocol Alignment","IMSProtoc18",1,"Rel-18",null,"Fri 03/06/22","Tue 12/12/23",1,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com",null,"23.218; 24.229; 24.930; 29.163; 29.165; 29.292",96,49,null,null,"Fri 03/06/22","Mon 20/06/22"]
[1339,970047,"   CT1 aspects of IMSProtoc18","IMSProtoc18",2,"Rel-18","C1","Fri 03/06/22","Tue 12/12/23",1,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com","; 6/6/23: Compl:30%->40%","23.218; 24.229; 24.930; 29.163; 29.165; 29.292",97,49,null,null,"Wed 07/09/22","Tue 06/06/23"]
[1340,970048,"   CT3 aspects of IMSProtoc18","IMSProtoc18",2,"Rel-18","C3","Fri 03/06/22","Tue 12/12/23",1,"CP-223102",null,"Won, Sung Hwan, Nokia","sung(dot)won(at)nokia(dot)com","9/6/23: 30%->60","23.218; 24.229; 24.930; 29.163; 29.165; 29.292",97,49,null,null,"Wed 07/09/22","Fri 09/06/23"]
[1341,980004,"Enhancement of Shared Data ID and Handling","ShDatID_H",1,"Rel-18","C4","Mon 07/03/22","Sun 03/03/24",1,"CP-232030",null,"Jing, Hao, Huawei","hao.jing@huawei.com","; 6/6/23: Compl:0%->40%","29.503; 29.504; 29.505",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1342,1050016,"UE conformance test for NB-IoT/eMTC Non-Terrestrial Networks in EPS","IoT_SAT_UEConTest",1,"Rel-18","C6","Mon 09/09/24","Tue 09/09/25",0.6,"CP-242075",null,"Daiwei Zhou, MediaTek Inc","daiwei.zhou@mediatek.com",null,null,96,49,null,"x","Fri 03/06/22","Tue 06/06/23"]
[1343,1050008,"Test method of GBA_U Based APIs","TEST_GBA_U_APIs",1,"Rel-18","C6","Mon 09/09/24","Fri 06/06/25",0.6,"CP-242028",null,"Huo Weijing(China Mobile)","huoweijing@chinamobile.com",null,null,96,49,null,"x","Fri 03/06/22","Tue 06/06/23"]
[1344,980036,"Rel-18 enhancements of session management policy control","SMPC18",1,"Rel-18","C3","Thu 15/12/22","Tue 12/12/23",1,"CP-223208",null,"Xiaoyun Zhou, Huawei","zhouxiaoyun8@huawei.com","; 6/6/23: Compl:25%->60%","29.512; 29.513; 29.514",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1345,960014,"Deleted - SMS over IMS to emergency centre ","SMS2ECdeleted",1,"Rel-18","S1","Thu 02/06/22","Wed 08/06/22",1,"SP-220438",null,"Bruno Tossou, Orange ","bruno.tossou@orange.com ","; 4/6/22: 0%->45; 12/9/22: 45%->100",22.100999999999999,96,49,null,null,"Thu 02/06/22","Mon 12/09/22"]
[1346,990003,"Enhancements on Service-based support for SMS in 5GC","eSMS_SBI",1,"Rel-18","C4","Mon 13/03/23","Fri 15/12/23",1,"CP-230025",null,"Liu, Liu, China Telecom","liuliu66@chinatelecom.cn","; 6/6/23: Compl:0%->50%","23.540; 29.338; 29.329; 29.230",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1347,1010026,"Modified PRINS for roaming service providers in 5G ","Roaming5G",1,"Rel-18","S1","Tue 08/08/23","Sat 09/09/23",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected","22.261; 33.501 ",101,51,null,null,"Wed 20/09/23","NA"]
[1348,1010027,"   Stage 1 of Roaming5G ","Roaming5G",2,"Rel-18","S1","Tue 08/08/23","Sat 09/09/23",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected",22.260999999999999,101,51,null,null,"Wed 20/09/23","NA"]
[1349,1010028,"   Stage 3 of Roaming5G ","Roaming5G",2,"Rel-18","S3","Tue 08/08/23","Sat 09/09/23",1,"SP-231190",null,"Targali, Yousif, Verizon ","yousif.targali@verizon.com ","9/23: company-submitted WID, to be corrected; 8/12/23: 100%->100",33.500999999999998,101,51,null,null,"Wed 20/09/23","Fri 08/12/23"]
[1350,1020001,"NRF API enhancements to avoid signalling and storing of redundant data","NRFe",1,"Rel-18","C4","Tue 12/12/23","Fri 15/03/24",1,"CP-233025",null,"Wiehe, Ulrich, Nokia","ulrich.wiehe@nokia.com",null,"29.510, 29.571, 29.504",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1351,0,"Rel-18 Other Security aspects","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1352,950019,"Security Assurance Specification for AKMA Anchor Function Function (AAnF) ","SCAS_5G_AAnF",1,"Rel-18","S3","Thu 10/03/22","Fri 03/03/23",1,"SP-220197",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 4/6/22: 0%->10; 13/7/22: 33.537 added;; 11/12/22: 10%->70; 17/3/23: 70%->90; 8/6/23: 90%->95; 15/3/24: 95%->100","33.926 ; 33.537",95,48,null,null,"Thu 10/03/22","Fri 15/03/24"]
[1353,990044,"5G Security Assurance Specification (SCAS) for the Policy Control Function (PCF) ","SCAS_5G_PCF",1,"Rel-18","S3","Thu 16/03/23","Tue 12/12/23",1,"SP-230157",null,"Andreas, Joerg, BSI Germany ","joerg.andreas@bsi.bund.de ","; 31/3/23: 33.528 added;; 7/9/23: 0%->40; 7/9/23: FCD:09/09/2023->12/23; 15/3/24: 40%->100","33.926 ; 33.528",99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[1354,980021,"IETF DTLS protocol profile for AKMA and GBA ","AKMA_GBA_DTLS",1,"Rel-18","S3","Fri 09/12/22","Tue 06/06/23",1,"SP-221143",null,"Liu, yuze, ZTE ","liu.yuze@zte.com.cn ","; 8/6/23: 0%->90; 7/9/23: 90%->100","33.535; 33.220; 33.222 ",98,50,null,null,"Fri 09/12/22","Thu 07/09/23"]
[1355,980023,"IETF OSCORE protocol profiles for GBA and AKMA ","AKMA_GBA_OSCORE",1,"Rel-18","S3","Fri 09/12/22","Sat 09/09/23",1,"SP-221146",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","; 8/6/23: 0%->80; 7/9/23: FCD:06/06/2023->/23; 15/3/24: 80%->100","33.535; 33.220; 33.222 ",98,50,null,null,"Fri 09/12/22","Fri 15/03/24"]
[1356,950022,"SCAS for split-gNB product classes ","SCAS_5G_split_gNB",1,"Rel-18","S3","Thu 10/03/22","Fri 03/03/23",1,"SP-220200",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 4/6/22: 0%->5; 13/7/22: 33.742 added;; 12/9/22: 5%->25; 11/12/22: 25%->60; 17/3/23: 60%->85; 17/3/23: 33.523 added;; 8/6/23: 85%->99; 15/3/24: 99%->100","33.926 ; 33.742; 33.523",95,48,null,null,"Thu 10/03/22","Fri 15/03/24"]
[1357,1010019,"Home network triggered primary authentication ","HN_Auth",1,"Rel-18","S3","Thu 10/03/22","Sun 03/03/24",1,"SP-221147",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ","; 15/3/24: 99%->100","33.501; 33.535 ",98,50,null,null,"Fri 09/12/22","Fri 15/03/24"]
[1358,950020,"   Study of Security aspect of home network triggered primary authentication ","FS_HN_Auth",2,"Rel-18","S3","Thu 10/03/22","Mon 12/12/22",1,"SP-220198",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ","4/6/22: 0%->30; 12/9/22: 30%->60; 11/12/22: 60%->80; 17/3/23: 80%->100",null,95,48,null,null,"Thu 10/03/22","Fri 17/03/23"]
[1359,980024,"   Security aspects of home network triggered primary authentication ","HN_Auth",2,"Rel-18","S3","Fri 09/12/22","Tue 06/06/23",1,"SP-221147",null,"He Li, Huawei ","LIHE2@HUAWEI.COM ","; 7/9/23: 0%->100","33.501; 33.535 ",98,50,null,null,"Fri 09/12/22","Thu 07/09/23"]
[1360,1010001,"   CT aspects of home network triggered primary authentication ","HN_Auth",2,"Rel-18","C4","Sat 09/09/23","Sun 03/03/24",1,"CP-232028",null,"Jing, Hao, Huawei","hao.jing@huawei.com",null,"29.503, 29.504, 29.505, 29.518",98,50,null,null,"Fri 09/12/22","NA"]
[1361,950018,"Study on AKMA Phase 2","FS_AKMA_Ph2",1,"Rel-18","S3","Thu 10/03/22","Mon 12/12/22",1,"SP-220991",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","4/6/22: 0%->15; 13/7/22: 33.737 added;; 12/9/22: 15%->35; 23/9/22: WID:SP-220327->SP-220991; 11/12/22: 35%->70; 17/3/23: 70%->80; 8/6/23: 80%->95; 15/3/24: 95%->100",33.737000000000002,95,48,null,null,"Thu 10/03/22","Fri 15/03/24"]
[1362,990040,"AKMA phase 2 ","AKMA_Ph2",1,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230153",null,"Huang Xiaoting, China Mobile ","huangxiaoting@chinamobile.com ","; 8/6/23: 0%->95; 15/3/24: 95%->100",33.534999999999997,99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[1363,940016,"Study of privacy of identifiers over radio access ","FS_Id_Prvc",1,"Rel-18","S3","Mon 13/12/21","Fri 03/03/23",1,"SP-211364",null,"Brusilovsky, Alec, Interdigital ","alec.brusilovsky@interdigital.com ","7/1/22: 33.870 added;; 12/3/22: 0%->5; 4/6/22: 5%->10; 12/9/22: 10%->12; 17/3/23: 12%->25; 8/6/23: 25%->40; 7/9/23: 40%->80; 15/3/24: 80%->100",33.869999999999997,94,48,null,null,"Mon 13/12/21","Fri 15/03/24"]
[1364,820007,"Study on Security Impacts of Virtualisation ","FS_SIV",1,"Rel-18","S3","Thu 13/12/18","Fri 09/12/22",1,"SP-181236",null,"Alex Leadbeater, BT Plc","alex.leadbeater@bt.com","20/3/19: 0%->2¦20/3/19: 0%->2; 31/5/19: 2%->10; 13/9/19: FCD:19/09/2019->12/20; 13/9/19: 10%->12; 6/12/19: 12%->45; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 45%-> ; ",null,82,42,null,null,"Thu 06/12/18","Thu 07/09/23"]
[1365,960038,"Study on Zero Trust Security principles in mobile networks ","FS_ZTS",1,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220674",null,"Sheeba Backia Mary B, Lenovo ","smary@lenovo.com ","13/7/22: 33.894 added; 17/8/22: WID:SP-220536->SP-220674; 12/9/22: 0%->6; 11/12/22: 6%->25; 17/3/23: 25%->30; 8/6/23: 30%->40; 7/9/23: 40%->100",33.893999999999998,96,49,null,null,"Thu 02/06/22","Thu 07/09/23"]
[1366,960039,"Study of Security aspects on User Consent for 3GPP Services Phase 2 ","FS_UC3S_Ph2",1,"Rel-18","S3","Thu 02/06/22","Fri 03/03/23",1,"SP-220537",null,"Rong Wu, Huawei, ","Raina.wu@huawei.com ","13/7/22: 33.896 added;; 12/9/22: 0%->10; 11/12/22: 10%->50; 17/3/23: 50%->100",33.896000000000001,96,49,null,null,"Thu 02/06/22","Fri 17/03/23"]
[1367,1000004,"Security aspects on User Consent for 3GPP services Phase 2 ","UC3S_SEC_Ph2",1,"Rel-18","S3","Mon 01/05/23","Tue 06/06/23",1,"SP-230557",null,"Rong Wu, Huawei Technologies, ","Raina.wu@huawei.com ","; 15/3/24: 0%->100",33.500999999999998,100,51,null,null,"Thu 08/06/23","Fri 15/03/24"]
[1368,1010013,"Security Assurance Specification for 5G Phase 3 ","SCAS_5G_Ph3",1,"Rel-18","S3","Wed 06/09/23","Sun 03/03/24",1,"SP-230867",null,"Wu, Rong, Huawei Technologies Co., Ltd. ","Raina.wu@huawei.com ","; 8/12/23: 0%->10; 15/3/24: 10%->100",33.926000000000002,101,51,null,null,"Wed 06/09/23","Fri 15/03/24"]
[1369,0,"Rel-18 NR-only: topics other than band","-",1,"Rel-18",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1370,950073,"NR demodulation performance evolution ","NR_demod_enh3",1,"Rel-18",null,"Tue 15/03/22","Thu 12/12/24",0.9,"RP-241292",null,"China Telecom ",null,"compare REL-16 NR_perf_enh, REL-17 NR_demod_enh2; no Core part; TR 38.8XX ; 29/3/23: WID:RP-220932->RP-230314; 6/10/23: WID:RP-230314->RP-232685; 2/1/24: WID:RP-232685->RP-233586; 23/7/24: WID:RP-233586->RP-241292",null,95,48,null,null,"Tue 05/04/22","Tue 23/07/24"]
[1371,1001061,"   Core part: NR demodulation performance evolution ","NR_demod_enh3-Core",2,"Rel-18","R4","Wed 07/06/23","Tue 12/12/23",1,"RP-241292","RP-233584","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","6/9/23: Compl:0%->33%; Stat Rep: ->RP-232250; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn; ; 8/12/23: Compl:33%->100%; Stat Rep: RP-232250->RP-233584; ",null,100,51,null,null,"Thu 29/06/23","Fri 08/12/23"]
[1372,950273,"   Perf. part: NR demodulation performance evolution ","NR_demod_enh3-Perf",2,"Rel-18","R4","Tue 15/03/22","Thu 06/06/24",1,"RP-241292","RP-241293","Jingzhou Wu, China Telecom","wujingzhou@chinatelecom.cn","compare REL-16 NR_perf_enh, REL-17 NR_demod_enh2; no Core part; TR 38.8XX ; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221287; Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn12/7/22: WID:RP-2...;...",38.878,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1373,1040105,"   UE Conformance - NR demodulation performance evolution ","NR_demod_enh3-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 12/12/25",0.77,"RP-241298","RP-251462","China Telecom ",null,"4/9/24: FCD:12/12/2025->25/12/2024; Compl:0%->8%; Stat Rep: ->RP-241995; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:8%->41%; Stat Rep: RP-241995->RP-242854; ; 6/3/25: FCD:24/06/2025->12/12/2025; Compl:41%->57%; Stat Rep: RP-242854->RP-250378; ; 6/6/25:",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[1374,991045,"NR channel raster enhancement","NR_channel_raster_enh",1,"Rel-18","R4","Mon 06/03/23","Mon 13/11/23",0.95,"RP-234025",null,"Ericsson",null,"2/1/24: WID:RP-230813->RP-234025",null,99,50,null,null,"Fri 07/04/23","Tue 02/01/24"]
[1375,991145,"   Core part: NR channel raster enhancement","NR_channel_raster_enh-Core",2,"Rel-18","R4","Mon 06/03/23","Mon 13/11/23",0.95,"RP-234025","RP-233392","Christian Bergljung, Ericsson","Christian.Bergljung@ericsson.com","; 7/6/23: Compl:0%->25%; ;...; 6/9/23: Compl:25%->50%; WID: RP-230813->RP-231469; Stat Rep: ->RP-231756; Rapporteur: Ericsson->Christian Bergljung, Ericsson; Rap eMail: ->Christian.Bergljung@ericsson.com; ; 8/12/23: FCD:12/12/2023->01/03/2024; Compl:50%->",null,99,50,null,null,"Fri 07/04/23","Fri 08/12/23"]
[1376,981042,"Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18",1,"Rel-18",null,"Tue 13/12/22","Fri 06/06/25",1,"RP-240251",null,"ZTE ",null,"29/3/23: WID:RP-223541->RP-230137; 6/10/23: WID:RP-230137->RP-231844; 2/1/24: WID:RP-231844->RP-234004; 2/4/24: WID:RP-234004->RP-240251",null,98,50,null,null,"Mon 09/01/23","Tue 02/04/24"]
[1377,981142,"   Core part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18-Core",2,"Rel-18","R4","Tue 13/12/22","Fri 01/03/24",1,"RP-240251","RP-240252","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230138; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 7/6/23: Compl:30%->35%; 6/9/23: Compl:35%->60%; WID: RP-230137->RP-231119; Stat Rep: RP-230138->RP-231845; ; 8/12/23: FCD:12/12/2023-...",null,98,50,null,null,"Mon 09/01/23","Thu 14/03/24"]
[1378,981242,"   Stopped - Perf. part: Rel-18 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18-Perf",2,"Rel-18","R4","Tue 13/12/22","Fri 01/03/24",1,"RP-240251","RP-240252","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","17/3/23: Compl:0%->30%; Stat Rep: ->RP-230138; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 7/6/23: Compl:30%->35%; 6/9/23: Compl:35%->60%; WID: RP-230137->RP-231119; Stat Rep: RP-230138->RP-231845; ; 8/12/23: FCD:12/12/2023-...",null,98,50,null,null,"Mon 09/01/23","Tue 02/04/24"]
[1379,1040102,"   UE Conformance - 4Rx for NR bands for FWA (Fixed Wireless Access) UEs (<2.6GHz) and handheld UEs (1GHz to 2.6GHz) ","4Rx_NR_bands_R18-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 06/06/25",1,"RP-250164","RP-250990","ZTE ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->13%; Stat Rep: ->RP-241772; ; 6/12/24: Compl:13%->52%; Stat Rep: RP-241772->RP-242810; ; 24/1/25: WID:RP-241093->RP-242811; 6/3/25: FCD:14/02/2025->06/06/2025; Compl:52%->95%; Stat Rep: RP-242810->RP-250163; ",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[1380,970085,"High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18",1,"Rel-18",null,"Mon 12/09/22","Fri 06/06/25",0.72,"RP-223499",null,"CMCC ",null,"9/1/23: WID:RP-222351->RP-223499",null,97,49,null,null,"Wed 19/10/22","Mon 09/01/23"]
[1381,970185,"   Core part: High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-Core",2,"Rel-18","R4","Mon 12/09/22","Tue 12/12/23",1,"RP-223499","RP-233448","Chunxia Guo, CMCC","guochunxia@chinamobile.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->30%; Stat Rep: ->RP-223053; Rapporteur: CMCC->Chunxia Guo, CMCC; Rap eMail: ->guochunxia@chinamobile.com; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-223053->RP-230280; 17/3/23: 38.895 added;; ;...;...",38.895000000000003,97,49,null,null,"Wed 19/10/22","Fri 08/12/23"]
[1382,970285,"   Perf. part: High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-Perf",2,"Rel-18","R4","Tue 31/01/23","Tue 12/12/23",0,"RP-223499","RP-223053","Chunxia Guo, CMCC","guochunxia@chinamobile.com","9/12/22: FCD:12/12/2023->01/12/2023; Stat Rep: ->RP-223053; Rapporteur: CMCC->Chunxia Guo, CMCC; Rap eMail: ->guochunxia@chinamobile.com; ",null,97,49,null,null,"Wed 19/10/22","Fri 09/12/22"]
[1383,1000053,"   UE Conformance - High power UE (power class 1.5) for NR FR1 TDD single band ","HPUE_NR_FR1_TDD_R18-UEConTest",2,"Rel-18","R5","Thu 08/06/23","Fri 06/06/25",1,"RP-241199","RP-241200","Dan SONG (CMCC), Yuxin Hao (Huawei), CMCC, Huawei","songdan@chinamobile.com, haoyuxin@huawei.com","21/9/23: Compl:0%->29%; Stat Rep: ->RP-232245; Rapporteur: CMCC->Dan SONG (CMCC), Yuxin Hao (Huawei), CMCC, Huawei; Rap eMail: ->songdan@chinamobile.com, haoyuxin@huawei.com; ; 8/12/23: Compl:29%->35%; Stat Rep: RP-232245->RP-233416; ; 14/3/24: FCD:05/...",null,100,51,null,null,"Thu 29/06/23","Tue 23/07/24"]
[1384,970086,"High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18",1,"Rel-18",null,"Mon 12/09/22","Thu 12/12/24",0.68,"RP-241314",null,"China Unicom ",null,"9/1/23: WID:RP-222625->RP-222967; 29/3/23: WID:RP-222967->RP-230352; 6/10/23: WID:RP-230352->RP-232216; 2/1/24: WID:RP-232216->RP-233031; 2/4/24: WID:RP-233031->RP-240120; 23/7/24: WID:RP-240120->RP-241314",null,97,49,null,null,"Wed 19/10/22","Tue 23/07/24"]
[1385,970186,"   Core part: High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-Core",2,"Rel-18","R4","Mon 12/09/22","Thu 06/06/24",1,"RP-241314","RP-241315","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222965; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222965->RP-230353; 17/3/23: ...;...",38.896000000000001,97,49,null,null,"Wed 19/10/22","Thu 13/06/24"]
[1386,970286,"   Perf. part: High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-Perf",2,"Rel-18","R4","Mon 12/09/22","Thu 06/06/24",1,"RP-241314","RP-241315","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222965; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222965->RP-230353; ;...; 6/9/23:...",null,97,49,null,null,"Wed 19/10/22","Thu 13/06/24"]
[1387,1000051,"   UE Conformance - High power UE (power class 2) for NR FR1 FDD single band ","HPUE_NR_FR1_FDD_R18-UEConTest",2,"Rel-18","R5","Thu 08/06/23","Tue 09/09/25",0.34,"RP-232774","RP-251508","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","6/9/23: Compl:0%->5%; Stat Rep: ->RP-231549; Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn; ; 8/12/23: Stat Rep: RP-231549->RP-232773; ; 2/1/24: WID:RP-230869->RP-232774; 14/3/24: FCD:05/06/2024->12/12/2024; Compl:...",null,100,51,null,null,"Thu 29/06/23","Fri 06/06/25"]
[1388,970087,"High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18",1,"Rel-18",null,"Mon 12/09/22","Thu 06/06/24",1,"RP-241254",null,"Huawei ",null,"9/1/23: WID:RP-222647->RP-223356; 29/3/23: WID:RP-223356->RP-230479; 6/10/23: WID:RP-230479->RP-232377; 2/1/24: WID:RP-232377->RP-233975; 2/4/24: WID:RP-233975->RP-240428; 23/7/24: WID:RP-240428->RP-241254",null,97,49,null,null,"Wed 19/10/22","Tue 23/07/24"]
[1389,970187,"   Core part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18-Core",2,"Rel-18","R4","Mon 12/09/22","Thu 06/06/24",1,"RP-241254","RP-241253","Lingyu Kong, Huawei, HiSilicon","konglingyu4@hisilicon.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->20%; WID: RP-222647->RP- 222647; Stat Rep: ->RP-223355; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->30%; W.....",38.896999999999998,97,49,null,null,"Wed 19/10/22","Thu 13/06/24"]
[1390,970287,"   Stopped - Perf. part: High power UE (power class 1.5 or 2) for intra-band Carrier Aggregation combinations of a single NR FR1 TDD band ","HPUE_NR_FR1_TDD_intra_CA_R18-Perf",2,"Rel-18","R4","Tue 13/09/22","Fri 01/03/24",1,"RP-240428","RP-233204","Lingyu Kong, Huawei, HiSilicon","konglingyu4@hisilicon.com","9/12/22: FCD:12/12/2023->01/12/2023; WID: RP-222647->RP- 222647; Stat Rep: ->RP-223355; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; 17/3/23: WID: RP-223356->RP- 223356; Stat Rep: RP-223355->RP-230478; ; ...",null,97,49,102,null,"Wed 19/10/22","Tue 02/01/24"]
[1391,970089,"Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18",1,"Rel-18",null,"Mon 12/09/22","Thu 06/06/24",1,"RP-241302",null,"China Telecom ",null,"9/1/23: WID:RP-222623->RP-223496; 29/3/23: WID:RP-223496->RP-230309; 6/10/23: WID:RP-230309->RP-232256; 2/1/24: WID:RP-232256->RP-233561; 2/4/24: WID:RP-233561->RP-240763; 23/7/24: WID:RP-240763->RP-241302",null,97,49,null,null,"Wed 19/10/22","Tue 23/07/24"]
[1392,970189,"   Core part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18-Core",2,"Rel-18","R4","Mon 12/09/22","Thu 06/06/24",1,"RP-241302","RP-241303","Lei GAO, China Telecom","gaol8@chinatelecom.cn","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-222941; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-222941->RP-230310; ...;...",38.899000000000001,97,49,null,null,"Wed 19/10/22","Thu 13/06/24"]
[1393,970289,"   Stopped: Perf. part: Rel-18 High power UE (power class 1,5 and 2) for a single FR1 NR TDD band in UL of NR inter-band CA/DC combinations with/without NR SUL (supplementary uplink) with y bands downlink (y=2,3,4,5,6) and x bands uplink (x=1,2) ","HPUE_FR1_TDD_NR_CADC_SUL_R18-Perf",2,"Rel-18","R4","Mon 12/09/22","Mon 12/09/22",1,"RP-241302","RP-241303","Lei GAO, China Telecom","gaol8@chinatelecom.cn","9/12/22: FCD:12/12/2023->01/12/2022; Stat Rep: ->RP-222941; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; 17/3/23: FCD:01/12/2022->12/12/2023; Stat Rep: RP-222941->RP-230310; ;...; 6/9/23: WID: RP-230309->RP-23...",null,97,49,null,null,"Wed 19/10/22","Tue 23/07/24"]
[1394,970090,"Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1)","HPUE_FR1_FDD_NR_CADC_R18",1,"Rel-18",null,"Mon 12/09/22","Thu 06/06/24",1,"RP-241317",null,"China Unicom ",null,"9/1/23: WID:RP-222626->RP-222968; 29/3/23: WID:RP-222968->RP-230354; 2/1/24: WID:RP-230354->RP-234017; 2/4/24: WID:RP-234017->RP-240123; 23/7/24: WID:RP-240123->RP-241317",null,97,49,null,null,"Wed 19/10/22","Tue 23/07/24"]
[1395,970190,"   Core part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1)","HPUE_FR1_FDD_NR_CADC_R18-Core",2,"Rel-18","R4","Mon 12/09/22","Thu 06/06/24",1,"RP-241317","RP-241318","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/06/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222966; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222966->RP-230355; 17/3/23: ...;...",38.85,97,49,null,null,"Wed 19/10/22","Thu 13/06/24"]
[1396,970290,"   Stopped - Perf. Part: Rel-18 High power UE (power class 2) for a single FR1 NR FDD band in UL of NR intra-band and inter-band CA/DC combinations with y bands downlink (y=1,2,3,4,5,6) and x bands uplink (x=1)","HPUE_FR1_FDD_NR_CADC_R18-Perf",2,"Rel-18","R4","Mon 12/09/22","Fri 01/03/24",1,"RP-240123","RP-241318","Basaier Jialade, China Unicom","basejld@chinaunicom.cn","9/12/22: FCD:12/06/2023->01/12/2023; Compl:0%->10%; Stat Rep: ->RP-222966; Rapporteur: China Unicom->Basaier Jialade, China Unicom; Rap eMail: ->basejld@chinaunicom.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Stat Rep: RP-222966->RP-230355; ;...; 6/9/23:...",null,97,49,102,null,"Wed 19/10/22","Thu 13/06/24"]
[1397,970083,"Adding new channel bandwidth(s) support to existing NR bands ","NR_bands_R18_BWs",1,"Rel-18",null,"Thu 08/09/22","Fri 01/03/24",1,"RP-232952",null,"Ericsson ",null,"9/1/23: WID:RP-222629->RP-222898; 29/3/23: WID:RP-222898->RP-230756; 6/10/23: WID:RP-230756->RP-231706; 2/1/24: WID:RP-231706->RP-232952",null,97,49,null,null,"Fri 23/09/22","Tue 02/01/24"]
[1398,970183,"   Core part: Adding new channel bandwidth(s) support to existing NR bands ","NR_bands_R18_BWs-Core",2,"Rel-18","R4","Thu 08/09/22","Fri 01/03/24",1,"RP-232952","RP-240275","Dominique Everaere, Ericsson","dominique.everaere@erisson.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->2%; Stat Rep: ->RP-222899; Rapporteur: Ericsson->Dominique Everaere, Ericsson; Rap eMail: ->dominique.everaere@erisson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:2%->5%; Stat Rep: RP-222899->RP-230.....",null,97,49,null,null,"Fri 23/09/22","Thu 14/03/24"]
[1399,970081,"Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirement for NR UEs ","NR_MIMO_OTA_enh",1,"Rel-18","R4","Thu 08/09/22","Fri 06/06/25",1,"RP-240736",null,"CAICT ",null,"9/1/23: WID:RP-222668->RP-223509; 6/10/23: WID:RP-223509->RP-232679; 6/10/23: 38.761 added;; 2/1/24: WID:RP-232679->RP-233742; 2/4/24: WID:RP-233742->RP-240736",38.761000000000003,97,49,null,null,"Fri 23/09/22","Tue 02/04/24"]
[1400,970181,"   Core part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirement for NR UEs ","NR_MIMO_OTA_enh-Core",2,"Rel-18","R4","Thu 08/09/22","Tue 12/12/23",1,"RP-240736","RP-241290","Zhu, Siting, CAICT","zhusiting@caict.ac.cn","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223185; Rapporteur: CAICT->Zhu, Siting, CAICT; Rap eMail: ->zhusiting@caict.ac.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->35%; Stat Rep: RP-223185->RP-230367; ...; 6/9/23: Com...",null,97,49,null,null,"Fri 23/09/22","Thu 13/06/24"]
[1401,970281,"   Perf. Part: Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirement for NR UEs ","NR_MIMO_OTA_enh-Perf",2,"Rel-18","R4","Mon 12/09/22","Thu 06/06/24",1,"RP-240736","RP-241290","Zhu, Siting, CAICT","zhusiting@caict.ac.cn","9/12/22: FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-223185; Rapporteur: CAICT->Zhu, Siting, CAICT; Rap eMail: ->zhusiting@caict.ac.cn; 17/3/23: Stat Rep: RP-223185->RP-230367; ;...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:20%->30%; Stat Rep: RP-2303...",null,97,49,null,null,"Fri 23/09/22","Thu 13/06/24"]
[1402,1040112,"   UE Conformance - Enhancement of Multiple Input Multiple Output (MIMO) Over-the-Air (OTA) test methodology and requirements for NR UEs ","NR_MIMO_OTA_enh-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 06/06/25",1,"RP-241504","RP-251177","Apple ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->45%; ; 6/12/24: Compl:45%->65%; Stat Rep: ->RP-242479; ; 6/3/25: FCD:14/02/2025->06/06/2025; Compl:65%->80%; Stat Rep: RP-242479->RP-250154; ; 6/6/25: Compl:80%->100%; Stat Rep: RP-250154->RP-251177; ",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[1403,981047,"Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18",1,"Rel-18",null,"Tue 13/12/22","Fri 01/03/24",1,"RP-240796",null,"CMCC ",null,"29/3/23: WID:RP-223553->RP-230719; 6/10/23: WID:RP-230719->RP-232688; 2/1/24: WID:RP-232688->RP-233446; 2/4/24: WID:RP-233446->RP-240796",null,98,50,null,null,"Mon 09/01/23","Tue 02/04/24"]
[1404,981147,"   Core part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18-Core",2,"Rel-18","R4","Tue 13/12/22","Fri 01/03/24",1,"RP-240796","RP-240159","Xiaoran ZHANG, CMCC","zhangxiaoran@chinamobile.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230298; Rapporteur: CMCC->Xiaoran ZHANG, CMCC; Rap eMail: ->zhangxiaoran@chinamobile.com; 17/3/23: 38.718-00-02 added;; 31/3/23: Stat Rep: RP-230298->RP-230718; ;...; 6/9/23: Compl:30%->50%; Stat Rep: RP-230718->...","38.718-00-02",98,50,null,null,"Mon 09/01/23","Thu 14/03/24"]
[1405,981247,"   Stopped - Perf. part: Rel-18 NR Carrier Aggregation (CA) band combinations with two SUL cells ","NR_2SUL_cell_combos_R18-Perf",2,"Rel-18","R4","Tue 13/12/22","Fri 01/03/24",1,"RP-240796","RP-233445","Xiaoran ZHANG, CMCC","zhangxiaoran@chinamobile.com","17/3/23: FCD:12/12/2023->06/06/2024; Compl:0%->10%; Stat Rep: ->RP-230298; Rapporteur: CMCC->Xiaoran ZHANG, CMCC; Rap eMail: ->zhangxiaoran@chinamobile.com; 31/3/23: FCD:06/06/2024->12/12/2023; Stat Rep: RP-230298->RP-230718; ;...; 6/9/23: Compl:30%->...",null,98,50,null,null,"Mon 09/01/23","Tue 02/04/24"]
[1406,941012,"NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.92,"RP-234027",null,"Nokia",null,"5/4/22: WID:RP-213603->RP-220401; 23/9/22: WID:RP-220401->RP-222645; 29/3/23: WID:RP-222645->RP-230186; 6/10/23: WID:RP-230186->RP-231713; 2/1/24: WID:RP-231713->RP-234027",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1407,941112,"   Core part: NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW-Core",2,"Rel-18","R4","Mon 13/12/21","Tue 12/12/23",1,"RP-234027","RP-232749","Man Hung Ng, Nokia","man_hung.ng@nokia.com","; 22/3/22: Stat Rep: ->RP-220402 6/6/22: CD:12/12/2023->13/12/2022 6/6/22: Stat Rep: RP-220402->RP-221415; 20/6/22: FCD:13/12/2022->23/12/2022; Rapporteur: Nokia->Toni L hteensuo, Nokia; Rap eMail: ->toni.h.lahteensuo@nokia.com13/7/22: FCD:23/12/20...;...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1408,941212,"   Perf. part: NR support for dedicated spectrum less than 5MHz for FR1","NR_FR1_lessthan_5MHz_BW-Perf",2,"Rel-18","R4","Wed 15/12/21","Thu 06/06/24",1,"RP-233963","RP-240063","Man Hung Ng, Nokia","man_hung.ng@nokia.com","; 22/3/22: CD:23/06/2023->12/06/2024; 22/3/22: Stat Rep: ->RP-220402 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220402->RP-221415; 20/6/22: Rapporteur: Nokia->Toni L hteensuo, Nokia; Rap eMail: ->toni.h.lahteensuo@nokia.com13/7/22: ...;...",null,94,48,null,null,"Thu 06/01/22","Tue 23/07/24"]
[1409,1030060,"   UE Conformance - NR support for dedicated spectrum less than 5MHz for FR1 ","NR_FR1_lessthan_5MHz_BW-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.78,"RP-250882","RP-250881","Nokia ",null,"13/6/24: Compl:0%->22%; Stat Rep: ->RP-240908; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:22%->43%; Stat Rep: RP-240908->RP-241737; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:43%->46%; Stat Rep: RP-241737->RP-242457; ; 6/3/25: FCD:28/05/2025->12/12/202",null,103,52,null,null,"Tue 02/04/24","Fri 18/07/25"]
[1410,940093,"Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh",1,"Rel-18",null,"Mon 13/12/21","Thu 06/06/24",1,"RP-232957",null,"Ericsson",null,"compare REL-17 WI NR_DSS-Core; 12/7/22: WID:RP-213575->RP-221622; 2/1/24: WID:RP-221622->RP-232957",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1411,940193,"   Core part: Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh-Core",2,"Rel-18","R1","Mon 13/12/21","Tue 12/12/23",1,"RP-232957","RP-232956","Ravikiran Nory, Ericsson","ravikiran.nory@ericsson.com","compare REL-17 WI NR_DSS-Core; 22/3/22: Stat Rep: ->RP-220589 ; 6/6/22: Compl:0%->40% ; 20/6/22: Rapporteur: Ericsson->Ravikiran Nory, Ericsson; Rap eMail: ->ravikiran.nory@ericsson.com13/7/22: FCD:23/12/2022->12/20 ; ...; 9/12/22: FCD:23/12/2022->01...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1412,940293,"   Perf. part: Enhancement of NR Dynamic Spectrum Sharing (DSS)","NR_DSS_enh-Perf",2,"Rel-18","R1","Wed 15/12/21","Thu 06/06/24",1,"RP-232957","RP-241174","Ravikiran Nory, Ericsson","ravikiran.nory@ericsson.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220589 ; 6/6/22: CD:12/06/2024->24/06/2022 ; 6/6/22: Stat Rep: RP-220589->RP-221621; 20/6/22: WG: R4->R1; Rapporteur: Ericsson->Ravikiran Nory, Ericsson; Rap eMail: ->ravikiran.nory@ericsson...",null,94,48,null,null,"Thu 06/01/22","Tue 23/07/24"]
[1413,940094,"Multi-carrier enhancements for NR","NR_MC_enh",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.98,"RP-234012",null,"NTT DOCOMO",null,"5/4/22: WID:RP-213577->RP-220834; 12/7/22: WID:RP-220834->RP-221435; 23/9/22: WID:RP-221435->RP-222251; 2/1/24: WID:RP-222251->RP-234012",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1414,940194,"   Core part: Multi-carrier enhancements for NR","NR_MC_enh-Core",2,"Rel-18","R1","Mon 13/12/21","Tue 12/12/23",1,"RP-240321","RP-241266","Hiroki Harada, NTT DOCOMO, INC.","hiroki.harada.sv@nttdocomo.com","; 22/3/22: CD:23/06/2023->12/06/2023; 22/3/22: Stat Rep: ->RP-220616 ; 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: NTT DOCOMO->Hiroki Harada, NTT DOCOMO, INC.; Rap eMail: ->hiroki.harada@docomo-lab.com13/7/22: FCD:23/12/2022->12/20 ...; 23/9/22: WID:RP-...",null,94,48,null,null,"Thu 06/01/22","Thu 13/06/24"]
[1415,940294,"   Perf. part: Multi-carrier enhancements for NR","NR_MC_enh-Perf",2,"Rel-18","R1","Wed 15/12/21","Thu 06/06/24",1,"RP-240321","RP-241266","Hiroki Harada, NTT DOCOMO, INC.","hiroki.harada.sv@nttdocomo.com","; 22/3/22: Stat Rep: ->RP-220616 6/6/22: CD:12/12/2023->24/06/2022 6/6/22: Stat Rep: RP-220616->RP-221436; 20/6/22: WG: R4->R1; Rapporteur: NTT DOCOMO->Hiroki Harada, NTT DOCOMO, INC.; Rap eMail: ->hiroki.harada@docomo-lab.com13/7/22: FCD:24/06/2...;...",null,94,48,null,null,"Thu 06/01/22","Tue 23/07/24"]
[1416,1030070,"   UE Conformance - Multi-carrier enhancements for NR ","NR_MC_enh-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.95,"RP-251461","RP-251460","China Telecom ",null,"13/6/24: Compl:0%->18%; Stat Rep: ->RP-241301; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:18%->80%; Stat Rep: RP-241301->RP-242000; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:80%->87%; Stat Rep: RP-242000->RP-242852; ; 6/3/25: FCD:28/05/2025->12/12/202",null,103,52,null,null,"Tue 02/04/24","Fri 18/07/25"]
[1417,940095,"Further NR coverage enhancements","NR_cov_enh2",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.91,"RP-241295",null,"China Telecom",null,"compare REL-17 WI NR_cov_enh; 5/4/22: WID:RP-213579->RP-220937; 12/7/22: WID:RP-220937->RP-221858; 2/1/24: WID:RP-221858->RP-233558; 23/7/24: WID:RP-233558->RP-241295",null,94,48,null,null,"Thu 06/01/22","Tue 23/07/24"]
[1418,940195,"   Core part: Further NR coverage enhancements","NR_cov_enh2-Core",2,"Rel-18","R1","Mon 13/12/21","Tue 12/12/23",1,"RP-241295","RP-233557","Nanxi LI, China Telecom","linanxi@chinatelecom.cn","compare REL-17 WI NR_cov_enh; 22/3/22: Stat Rep: ->RP-220566 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: WID: RP-220937->RP- 220937 ; 6/6/22: Stat Rep: RP-220566->RP-221282; 20/6/22: Rapporteur: China Telecom->Nanxi LI, China Telecom; Rap eMail: ->li...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1419,940295,"   Perf. part: Further NR coverage enhancements","NR_cov_enh2-Perf",2,"Rel-18","R1","Wed 15/12/21","Thu 06/06/24",1,"RP-241295","RP-241294","Nanxi LI, China Telecom","linanxi@chinatelecom.cn","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220566 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: WID: RP-220937->RP- 220937 6/6/22: Stat Rep: RP-220566->RP-221282; 20/6/22: WG: R4->R1; Rapporteur: China Telecom->Nanxi LI, China Telecom; R...",null,94,48,null,null,"Thu 06/01/22","Tue 23/07/24"]
[1420,1030069,"   UE Conformance - Further NR coverage enhancements ","NR_cov_enh2-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.76,"RP-240345","RP-251459","China Telecom ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241300; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->28%; Stat Rep: RP-241300->RP-241992; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:28%->29%; Stat Rep: RP-241992->RP-242851; ; 6/3/25: FCD:28/05/2025->12/12/2025;",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[1421,940096,"NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.85,"RP-233028",null,"Samsung",null,"compare REL-16 WI NR_eMIMO and REL-17 WI NR_feMIMO; 9/1/23: WID:RP-213598->RP-223276; 2/1/24: WID:RP-223276->RP-233028",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1422,940196,"   Core part: NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL-Core",2,"Rel-18","R1","Mon 13/12/21","Tue 12/12/23",1,"RP-233028","RP-232913","Eko Onggosanusi, Samsung","eko.o@samsung.com","compare REL-16 WI NR_eMIMO and REL-17 WI NR_feMIMO; 22/3/22: Stat Rep: ->RP-220669 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com13/7/22: FCD:23/12/2022->12/20 ;...; 9/12/22: FCD:23/12/202...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1423,940296,"   Perf. part: NR MIMO evolution for downlink and uplink","NR_MIMO_evo_DL_UL-Perf",2,"Rel-18","R1","Wed 15/12/21","Thu 06/06/24",1,"RP-233028","RP-241282","Eko Onggosanusi, Samsung","eko.o@samsung.com","; 22/3/22: CD:24/06/2024->12/06/2024; 22/3/22: Stat Rep: ->RP-220669 6/6/22: CD:12/06/2024->24/06/2022 6/6/22: Stat Rep: RP-220669->RP-221393; 20/6/22: WG: R4->R1; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.com13/7/...;...",null,94,48,null,null,"Thu 06/01/22","Tue 23/07/24"]
[1424,1030072,"   UE Conformance - NR MIMO evolution for downlink and uplink ","NR_MIMO_evo_DL_UL-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.59,"RP-250103","RP-251019","Samsung ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241279; ; 4/9/24: FCD:12/12/2025->25/12/2024; Compl:5%->19%; Stat Rep: RP-241279->RP-241982; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:19%->37%; Stat Rep: RP-241982->RP-242596; ; 6/3/25: FCD:28/05/2025->12/12/2025;",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[1425,940082,"Study on evolution of NR duplex operation","FS_NR_duplex_evo",1,"Rel-18","R1","Mon 13/12/21","Tue 12/12/23",1,"RP-223041","RP-233435","Fei WANG, CMCC","wangfei@chinamobile.com","21/1/22: 38.858 added;; 22/3/22: Stat Rep: ->RP-220632; 5/4/22: WID:RP-213591->RP-220633 6/6/22: Compl:0%->10% 20/6/22: Rapporteur: CMCC->Fei WANG, CMCC; Rap eMail: ->wangfei@chinamobile.com12/7/22: WID:RP-220633->RP-221352; 13/7/22: FCD:23/12...; 23/...",38.857999999999997,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1426,970079,"NR network-controlled repeaters ","NR_netcon_repeater",1,"Rel-18",null,"Thu 08/09/22","Thu 06/06/24",1,"RP-232886",null,"ZTE ",null,"9/1/23: WID:RP-222673->RP-223505; 29/3/23: WID:RP-223505->RP-230175; 2/1/24: WID:RP-230175->RP-232886",null,97,49,null,null,"Fri 23/09/22","Tue 02/01/24"]
[1427,970179,"   Core part: NR network-controlled repeaters ","NR_netcon_repeater-Core",2,"Rel-18","R1","Thu 08/09/22","Tue 12/12/23",1,"RP-232886","RP-240930","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->80%; Stat Rep: ->RP-222874; Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:80%->90%; WID: RP-222673->RP-223505; Stat Rep: RP-222874->RP.....",null,97,49,null,null,"Fri 23/09/22","Thu 13/06/24"]
[1428,970279,"   Perf. part: NR network-controlled repeaters ","NR_netcon_repeater-Perf",2,"Rel-18","R1","Mon 12/09/22","Thu 06/06/24",1,"RP-232886","RP-240930","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","9/12/22: WG: R4->R1; FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-222874; Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn; 17/3/23: WID: RP-222673->RP-223505; Stat Rep: RP-222874->RP-230174; ...; 6/9/23: FCD:06/06/2023->06/06/2024;...",null,97,49,null,null,"Fri 23/09/22","Tue 23/07/24"]
[1429,940083,"   Study on NR network-controlled repeaters","FS_NR_netcon_repeater",2,"Rel-18","R1","Thu 08/09/22","Wed 05/06/24",1,"RP-221229","RP-221231","Nan Zhang, ZTE","Zhang.nan152@zte.com.cn","compare REL-17 WI NR_repeaters; TR 38.8xx; 21/1/22: 38.867 added;; 22/3/22: Stat Rep: ->RP-220214 6/6/22: Compl:0%->40% ; 20/6/22: Rapporteur: ZTE->Nan Zhang, ZTE; Rap eMail: ->Zhang.nan152@zte.com.cn12/7/22: WID:RP-213700->RP-221229 ;...; 23/9/22: 0%->10",38.866999999999997,94,48,null,null,"Thu 06/01/22","Fri 23/09/22"]
[1430,940098,"Further NR mobility enhancements","NR_Mob_enh2",1,"Rel-18",null,"Mon 13/12/21","Thu 12/12/24",0.9,"RP-233970",null,"MediaTek",null,"compare REL-16 WI NR_Mob_enh; 12/7/22: WID:RP-213565->RP-221799; 23/9/22: WID:RP-221799->RP-222332; 9/1/23: WID:RP-222332->RP-223520; 2/1/24: WID:RP-223520->RP-233970",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1431,940198,"   Core part: Further NR mobility enhancements","NR_Mob_enh2-Core",2,"Rel-18","R2","Mon 13/12/21","Fri 01/03/24",1,"RP-233970","RP-241347","Li-Chuan Tseng, MediaTek Inc.","li-chuan.tseng@mediatek.com","compare REL-16 WI NR_Mob_enh; 22/3/22: CD:12/12/2023->12/09/2023; 22/3/22: Stat Rep: ->RP-220760 6/6/22: CD:12/09/2023->23/09/2022 6/6/22: Stat Re ; 20/6/22: Acronym:NR_Mob_enh2-Core->NR_mob_enh2-Core; Rapporteur: MediaTek->Li-Chuan Tseng, MediaTek Inc...",null,94,48,null,null,"Thu 06/01/22","Thu 13/06/24"]
[1432,940298,"   Perf. part: Further NR mobility enhancements","NR_Mob_enh2-Perf",2,"Rel-18","R2","Wed 15/12/21","Thu 06/06/24",1,"RP-233970","RP-241347","Li-Chuan Tseng, MediaTek Inc.","li-chuan.tseng@mediatek.com","; 22/3/22: CD:24/06/2024->12/12/2023; 22/3/22: Stat Rep: ->RP-220760 ; 6/6/22: CD:12/12/2023->23/12/2022 ; 6/6/22: Stat Rep: RP-220760->RP-221557; 20/6/22: Acronym:NR_Mob_enh2-Perf->NR_mob_enh2-Perf; WG: R4->R2; Rapporteur: MediaTek->Li-Chuan Tseng, Me...",null,94,48,null,null,"Thu 06/01/22","Thu 13/06/24"]
[1433,1040108,"   UE Conformance - Further NR mobility enhancements ","NR_Mob_enh2-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 12/12/25",0.7,"RP-241348","RP-251291","Mediatek ",null,"4/9/24: FCD:12/12/2025->25/12/2024; Compl:0%->20%; Stat Rep: ->RP-242047; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:20%->40%; Stat Rep: RP-242047->RP-242990; ; 6/3/25: FCD:24/06/2025->12/12/2025; Compl:40%->55%; Stat Rep: RP-242990->RP-250475; ; 6/6/2",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[1434,941003,"In-Device Co-existence (IDC) enhancements for NR and MR-DC","NR_IDC_enh",1,"Rel-18",null,"Mon 13/12/21","Fri 05/06/26",0.73,"RP-233485",null,"Xiaomi",null,"MR-DC: Multi-RAT Dual Connectivity; no Perf. part; 12/7/22: WID:RP-213589->RP-221281; 2/1/24: WID:RP-221281->RP-233485",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1435,941103,"   Core part: In-Device Co-existence (IDC) enhancements for NR and MR-DC","NR_IDC_enh-Core",2,"Rel-18","R2","Mon 13/12/21","Tue 12/12/23",1,"RP-233485","RP-233484","Yumin Wu, Xiaomi","wuyumin@xiaomi.com","MR-DC: Multi-RAT Dual Connectivity; no Perf. part; 20/6/22: Acronym:NR_IDC_enh-Core->NR_IDC_Enh-Core; FCD:12/12/2023->23/12/2022; Stat Rep: ->RP-221280; Rapporteur: Xiaomi->Yumin Wu, Xiaomi; Rap eMail: ->wuyumin@xiaomi.com13/7/22: FCD:23/12/2022->1...;...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1436,1040104,"   UE Conformance - In-Device Co-existence (IDC) enhancements for NR and MR-DC ","NR_IDC_enh-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 05/06/26",0.55000000000000004,"RP-251764","RP-251377","CMCC ",null,"4/9/24: FCD:06/06/2026->26/06/2025; Compl:0%->5%; Stat Rep: ->RP-241948; ; 6/12/24: FCD:06/06/2025->05/06/2026; Compl:5%->18%; Stat Rep: RP-241948->RP-242978; ; 6/3/25: FCD:23/10/2025->05/06/2026; Compl:18%->39%; Stat Rep: RP-242978->RP-250252; ; 6/6/25:",null,104,53,null,null,"Tue 23/07/24","Fri 18/07/25"]
[1437,950072,"BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh",1,"Rel-18",null,"Tue 15/03/22","Tue 12/12/23",1,"RP-233976",null,"Ericsson ",null,"compare REL-15 WI AASenh_BS_LTE_UTRA ; 2/1/24: WID:RP-220916->RP-233976",null,95,48,null,null,"Tue 05/04/22","Tue 02/01/24"]
[1438,950172,"   Core part: BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh-Core",2,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-233976","RP-233683","Aurelian Bria, Ericsson","Aurelian.Bria@ericsson.com","compare REL-15 WI AASenh_BS_LTE_UTRA ; 6/6/22: CD:15/06/2023->23/09/2022 ; 6/6/22: Stat Rep: ->RP-221165; 20/6/22: Rapporteur: Ericsson->Aurelian Bria, Ericsson; Rap eMail: ->aurelian.bria@ericsson.com13/7/22: FCD:23/09/2022->09/20 ;...; 9/12/22: FCD...",null,95,48,null,null,"Tue 05/04/22","Fri 08/12/23"]
[1439,950272,"   Perf. part: BS/UE EMC enhancements for NR and LTE ","NR_LTE_EMC_enh-Perf",2,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-233976","RP-233683","Aurelian Bria, Ericsson","Aurelian.Bria@ericsson.com","compare REL-15 WI AASenh_BS_LTE_UTRA 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221165; 20/6/22: Rapporteur: Ericsson->Aurelian Bria, Ericsson; Rap eMail: ->aurelian.bria@ericsson.com13/7/22: FCD:23/12/2022->12/20...; 9/12/22: FCD:23/12...",null,95,48,null,null,"Tue 05/04/22","Fri 08/12/23"]
[1440,950075,"Air-to-ground network for NR ","NR_ATG",1,"Rel-18",null,"Tue 15/03/22","Fri 06/06/25",0.84,"RP-240732",null,"CMCC ",null,"TR 38.8xx ; 12/7/22: WID:RP-220962->RP-221369; 29/3/23: WID:RP-221369->RP-230279; 2/1/24: WID:RP-230279->RP-234023; 2/4/24: WID:RP-234023->RP-240732",null,95,48,null,null,"Tue 05/04/22","Tue 02/04/24"]
[1441,950175,"   Core part: Air-to-ground network for NR ","NR_ATG-Core",2,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-240732","RP-240158","Guo Chunxia, CMCC","guochunxia@chinamobile.com","TR 38.8xx 6/6/22: CD:15/12/2023->23/12/20226/6/22: Stat Rep: ->RP-221370; 20/6/22: Rapporteur: CMCC->Shao Zhe, CMCC; Rap eMail: ->Shaozhe@chinamobile.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep...",null,95,48,null,null,"Tue 05/04/22","Thu 14/03/24"]
[1442,950275,"   Perf. part: Air-to-ground network for NR ","NR_ATG-Perf",2,"Rel-18","R4","Wed 16/03/22","Fri 01/03/24",1,"RP-240732","RP-240158","Guo Chunxia, CMCC","guochunxia@chinamobile.com","6/6/22: CD:15/03/2024->24/03/2023 6/6/22: Stat Rep: ->RP-221370; 20/6/22: Rapporteur: CMCC->Shao Zhe, CMCC; Rap eMail: ->Shaozhe@chinamobile.com13/7/22: FCD:24/03/2023->03/20 ;...; 9/12/22: FCD:24/03/2023->01/03/2024; Stat Rep: RP-221370->RP-2230...",null,95,48,null,null,"Tue 05/04/22","Thu 14/03/24"]
[1443,1020087,"   UE Conformance - Air-to-ground network for NR ","NR_ATG-UEConTest",2,"Rel-18","R5","Wed 13/12/23","Fri 12/12/25",0.64,"RP-240750","RP-251379","Dan SONG, CMCC","songdan@chinamobile.com","14/3/24: Compl:0%->50%; Stat Rep: ->RP-240148; Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com; ; 2/4/24: WID:RP-233412->RP-240750. corrected: Rel-19->Rel-18; 13/6/24: WID: RP-240750->RP-233412; Stat Rep: RP-240148->RP-241201; ; ...",null,102,52,null,null,"Tue 02/01/24","Fri 06/06/25"]
[1444,950076,"NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3",1,"Rel-18",null,"Tue 15/03/22","Mon 03/03/25",0.86,"RP-240940",null,"Nokia ",null,"compare REL-16 WI NR_RF_FR2_req_enh and REL-17 WI NR_RF_FR2_req_enh2 ; 12/7/22: WID:RP-220967->RP-221862; 23/9/22: WID:RP-221862->RP-222228; 9/1/23: WID:RP-222228->RP-222909; 2/1/24: WID:RP-222909->RP-232791; 23/7/24: WID:RP-232791->RP-240940",null,95,48,null,null,"Tue 05/04/22","Tue 23/07/24"]
[1445,950176,"   Core part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-Core",2,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-240940","RP-240939","Primary: Hisashi Onozawa Secondary: Juan Zhang, Nokia Xiaomi","hisashi.onozawa@nokia.com zhangjuan8@xiaomi.com","compare REL-16 WI NR_RF_FR2_req_enh and REL-17 WI NR_RF_FR2_req_enh2 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com13/7/22: FCD:23/12/2022->12/20...;...",38.890999999999998,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1446,950276,"   Perf. part: NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-Perf",2,"Rel-18","R4","Tue 15/03/22","Thu 06/06/24",1,"RP-240940","RP-240939","Primary: Hisashi Onozawa Secondary: Juan Zhang, Nokia Xiaomi","hisashi.onozawa@nokia.com zhangjuan8@xiaomi.com","; 6/6/22: CD:15/03/2024->24/03/2023 ; 6/6/22: Stat Rep: ->RP-221207; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com13/7/22: FCD:24/03/2023->03/20 ; ;...; 9/12/22: FCD:24/03/2023->01/03/2024; Compl:10%...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1447,1030065,"   UE Conformance - NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 ","NR_RF_FR2_req_Ph3-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.65,"RP-240125","RP-251506","Apple ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241175; ; 4/9/24: FCD:03/03/2025->25/03/2025; Compl:5%->15%; Stat Rep: RP-241175->RP-242219; ; 6/12/24: Compl:15%->40%; Stat Rep: RP-242219->RP-242600; ; 6/3/25: FCD:12/11/2024->06/06/2025; Stat Rep: RP-242600->RP-250",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[1448,950077,"Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL",1,"Rel-18",null,"Tue 15/03/22","Thu 30/11/23",0.75,"RP-241534","RP-223153","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","; 12/7/22: WID:RP-220974->RP-221753; 9/12/22: Acronym:NR_FR2_multiRX_DL->FS_NR_FR2_OTA_enh; FCD:01/03/2024->01/12/2023; Compl:11%->25%; WID: RP-221753->RP-222652; Stat Rep: ->RP-223153; Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail:...",null,95,48,null,null,"Tue 05/04/22","Tue 23/07/24"]
[1449,950177,"   Core part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL-Core",2,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-241534","RP-241535","Sumant Iyer, Qualcomm Inc.","sumanti@qti.qualcomm.com","6/6/22: CD:15/09/2023->23/09/2022 6/6/22: WID: RP-220974->R4-220974 6/6/22: Stat Rep: ->RP-221225; 20/6/22: Stat Rep: RP-221225->RP-221225 / 1752; Rapporteur: Qualcomm->Sumant Iyer, Qualcomm Inc.; Rap eMail: ->sumanti@qti.qualcomm.com13/7/22: FC...;...",38.750999999999998,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1450,950277,"   Perf. part: Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL-Perf",2,"Rel-18","R4","Tue 15/03/22","Thu 06/06/24",1,"RP-241534","RP-241535","Sumant Iyer, Qualcomm Inc.","sumanti@qti.qualcomm.com","6/6/22: CD:15/03/2024->24/09/2022 6/6/22: WID: RP-220974->R4-220974 6/6/22: Stat Rep: ->RP-221225; 20/6/22: FCD:24/09/2022->24/03/2023; Stat Rep: RP-221225->RP-221225 / 1752; Rapporteur: Qualcomm->Sumant Iyer, Qualcomm Inc.; Rap eMail: ->sumanti@qt...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1451,1040113,"   UE Conformance - Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception ","NR_FR2_multiRX_DL-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 12/12/25",0.3,"RP-241653","RP-251232","Qualcomm ",null,"4/9/24: FCD:12/12/2025->25/12/2024; Compl:0%->5%; Stat Rep: ->RP-242040; ; 6/12/24: FCD:12/12/2024->12/12/2025; Compl:5%->9%; Stat Rep: RP-242040->RP-242898; ; 6/3/25: FCD:24/06/2025->12/12/2025; Compl:9%->20%; Stat Rep: RP-242898->RP-250396; ; 6/6/25: C",null,104,53,null,null,"Tue 23/07/24","Fri 06/06/25"]
[1452,950078,"Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3",1,"Rel-18",null,"Tue 15/03/22","Thu 06/06/24",1,"RP-233496",null,"Apple ",null,"compare REL-16 WI NR_RRM_enh and REL-17 WI NR_RRM_enh2; RAN1/2 impact to be checked ; 12/7/22: WID:RP-220977->RP-221696; 2/1/24: WID:RP-221696->RP-233496",null,95,48,null,null,"Tue 05/04/22","Tue 02/01/24"]
[1453,950178,"   Core part: Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3-Core",2,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-221696","RP-241267","Jie Cui, Apple","jie_cui@apple.com","compare REL-16 WI NR_RRM_enh and REL-17 WI NR_RRM_enh2; RAN1/2 impact to be checked ; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221697; Rapporteur: Apple->Jie Cui, Apple; Rap eMail: ->jie_cui@apple.com13/7/22: FCD:23/12/2022->12/20; ...; 9/1...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1454,950278,"   Perf. part: Even Further RRM enhancement for NR and MR-DC ","NR_RRM_enh3-Perf",2,"Rel-18","R4","Thu 17/03/22","Thu 06/06/24",1,"RP-221696","RP-241267","Jie Cui, Apple","jie_cui@apple.com","6/6/22: CD:15/06/2024->24/06/2022 6/6/22: Stat Rep: ->RP-221697; 20/6/22: Rapporteur: Apple->Jie Cui, Apple; Rap eMail: ->jie_cui@apple.com13/7/22: FCD:24/06/2022->06/20 ; ...; 9/12/22: FCD:24/06/2023->01/06/2024; WID: RP-220977->RP-221696; Stat ...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1455,950080,"Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2",1,"Rel-18",null,"Tue 15/03/22","Fri 06/06/25",0.82,"RP-233186",null,"Huawei ",null,"compare REL-16 WI NR_RF_FR1 and REL-17 WI NR_RF_FR1_enh ; 12/7/22: WID:RP-220987->RP-221496; 9/1/23: WID:RP-221496->RP-223478; 29/3/23: WID:RP-223478->RP-230753; 6/10/23: WID:RP-230753->RP-232366; 2/1/24: WID:RP-232366->RP-233186",null,95,48,null,null,"Tue 05/04/22","Tue 02/01/24"]
[1456,950180,"   Core part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2-Core",2,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-233186","RP-233185","Primary: Ye Liu Secondary: Yuta Oguma, Huawei NTT DOCOMO, INC.","leo.liuye@huawei.com yuuta.oguma.yt@nttdocomo.com","compare REL-16 WI NR_RF_FR1 and REL-17 WI NR_RF_FR1_enh 6/6/22: CD:15/12/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221495; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com13/7/22: FCD:23/12/2022->12/20; 13/7...;...",38.881,95,48,null,null,"Tue 05/04/22","Fri 08/12/23"]
[1457,950280,"   Perf. part: Further RF requirements enhancement for NR and EN-DC in frequency range 1 (FR1) ","NR_ENDC_RF_FR1_enh2-Perf",2,"Rel-18","R4","Tue 15/03/22","Thu 06/06/24",1,"RP-232366","RP-241240","Primary: Ye Liu Secondary: Yuta Oguma, Huawei NTT DOCOMO, INC.","leo.liuye@huawei.com yuuta.oguma.yt@nttdocomo.com","; 6/6/22: CD:15/06/2024->24/06/2022 ; 6/6/22: Stat Rep: ->RP-221495; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com13/7/22: FCD:24/06/2022->06/20 ; ;...; 9/12/22: FCD:23/06/2023->31/05/2024; Compl:10%->20...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1458,1030066,"   UE Conformance - Further RF requirements enhancement for NR and EN-DC in frequency range 1 ","NR_ENDC_RF_FR1_enh2-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 12/12/25",0.54,"RP-251489","RP-251488","Huawei ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-241377; ; 4/9/24: FCD:06/06/2025->25/06/2025; Compl:5%->12%; Stat Rep: RP-241377->RP-242074; ; 6/12/24: Compl:12%->34%; Stat Rep: RP-242074->RP-243091; ; 6/3/25: FCD:17/01/2025->12/12/2025; Compl:34%->35%; Stat Rep: R",null,103,52,null,null,"Tue 02/04/24","Fri 18/07/25"]
[1459,950081,"Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA",1,"Rel-18",null,"Tue 15/03/22","Tue 12/12/23",0.97,"RP-233513",null,"KDDI ",null,"; 12/7/22: WID:RP-221012->RP-221809; 23/9/22: WID:RP-221809->RP-222309; 29/3/23: WID:RP-222309->RP-230742; 2/1/24: WID:RP-230742->RP-233513",null,95,48,null,null,"Tue 05/04/22","Tue 02/01/24"]
[1460,950181,"   Core part: Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA-Core",2,"Rel-18","R4","Tue 15/03/22","Tue 30/05/23",0.95,"RP-233513","RP-232113","Yasuki Suzuki, KDDI","ui-suzuki@kddi.com","; 20/6/22: FCD:15/09/2023->23/09/2022; Stat Rep: ->RP-221742; Rapporteur: KDDI->Yasuki Suzuki; Rap eMail: ->ui-suzuki@kddi.com13/7/22: FCD:23/09/2022->09/20 ...; 9/12/22: FCD:23/09/2022->01/09/2023; Compl:10%->20%; Stat Rep: RP-221742->RP-222956;...",null,95,48,null,null,"Tue 05/04/22","Wed 06/09/23"]
[1461,950281,"   Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment ","NonCol_intraB_ENDC_NR_CA-Perf",2,"Rel-18","R4","Wed 16/03/22","Tue 12/12/23",1,"RP-233513","RP-232113","Yasuki Suzuki, KDDI","ui-suzuki@kddi.com","; 20/6/22: FCD:15/12/2023->23/12/2022; Stat Rep: ->RP-221742; Rapporteur: KDDI->Yasuki Suzuki; Rap eMail: ->ui-suzuki@kddi.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: RP-221742->RP-222956; Rapporteur: Yas...",null,95,48,null,null,"Tue 05/04/22","Tue 02/04/24"]
[1462,950082,"Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2",1,"Rel-18",null,"Tue 15/03/22","Fri 12/12/25",0.86,"RP-234021",null,"MediaTek ",null,"compare REL-14 WI LTE_meas_gap_enh and REL-17 WI NR_MG_enh ; 5/4/22: WID:RP-221018 ->RP-220772; 23/9/22: WID:RP-220772->RP-222337; 29/3/23: WID:RP-222337->RP-230755; 6/10/23: WID:RP-230755->RP-232440; 2/1/24: WID:RP-232440->RP-234021",null,95,48,null,null,"Tue 05/04/22","Tue 02/01/24"]
[1463,950182,"   Core part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2-Core",2,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-232440","RP-241349","Tsang-Wei (Ato) YU, Meng ZHANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, meng.zhang@intel.com","compare REL-14 WI LTE_meas_gap_enh and REL-17 WI NR_MG_enh ; 20/6/22: FCD:15/12/2023->23/12/2022; WID: RP-220772->RP-221018; Stat Rep: ->RP-221560; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1464,950282,"   Perf. part: Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2-Perf",2,"Rel-18","R4","Tue 15/03/22","Thu 06/06/24",1,"RP-232440","RP-241349","Tsang-Wei (Ato) YU, Meng ZHANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, meng.zhang@intel.com","; 6/6/22: CD:15/06/2024->24/06/2022 ; 6/6/22: WID: RP-220772->RP-221018 ; 6/6/22: Stat Rep: ->RP-221560; 20/6/22: Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato.yu@mediatek.com, rui.huang@int...",null,95,48,null,null,"Tue 05/04/22","Thu 13/06/24"]
[1465,1050132,"   UE Conformance - Further enhancements on NR and MR-DC measurement gaps and measurements without gaps ","NR_MG_enh2-UEConTest",2,"Rel-18","R5","Mon 09/09/24","Fri 12/12/25",0.55000000000000004,"RP-242046","RP-251293","Mediatek ",null,"6/12/24: Compl:0%->10%; Stat Rep: ->RP-242994; ; 24/1/25: WID:RP-242046->RP-242995; 6/3/25: FCD:24/07/2025->12/12/2025; Compl:10%->35%; WID: RP-242995->RP-242046; Stat Rep: RP-242994->RP-250477; ; 6/6/25: Compl:35%->55%; Stat Rep: RP-250477->RP-251293; ",null,105,53,null,null,"Thu 26/09/24","Fri 06/06/25"]
[1466,941001,"Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM",1,"Rel-18","R2","Mon 13/12/21","Fri 06/06/25",1,"RP-233071",null,"vivo",null,"compare REL-17 WI LTE_NR_MUSIM-Core; no Perf. part; 5/4/22: WID:RP-213584->RP-220955; 9/1/23: WID:RP-220955->RP-223492; 29/3/23: WID:RP-223492->RP-230751; 2/1/24: WID:RP-230751->RP-233071",null,94,48,null,null,"Thu 06/01/22","Tue 02/01/24"]
[1467,941101,"   Core part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM-Core",2,"Rel-18","R2","Mon 13/12/21","Tue 12/12/23",1,"RP-233071","RP-233070","Xiaodong Yang, vivo","Yangxiaodong5g@vivo.com","6/6/22: CD:12/09/2023->23/12/2022 6/6/22: Stat Rep: ->RP-221273; 20/6/22: Rapporteur: vivo->Xiaodong Yang, vivo; Rap eMail: ->Yangxiaodong5g@vivo.com13/7/22: FCD:23/12/2022->12/20 ...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: RP...",null,94,48,null,null,"Thu 06/01/22","Fri 08/12/23"]
[1468,950283,"   Perf. Part: Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR","NR_DualTxRx_MUSIM-Perf",2,"Rel-18","R2","Tue 15/03/22","Thu 06/06/24",1,"RP-231461","RP-241045","Xiaodong Yang, vivo","Yangxiaodong5g@vivo.com","20/6/22: WG: R4->R2; FCD:14/06/2024->24/06/2022; Stat Rep: ->RP-221273; Rapporteur: vivo->Xiaodong Yang, vivo; Rap eMail: ->Yangxiaodong5g@vivo.com13/7/22: FCD:24/06/2022->06/20 ;...; 17/3/23: FCD:06/06/2023->06/06/2024; Stat Rep: RP-221273->RP-2303...",null,95,48,null,null,"Sat 04/06/22","Thu 13/06/24"]
[1469,1030061,"   UE Conformance - Dual Transmission/Reception (Tx/Rx) Multi-SIM for NR ","NR_DualTxRx_MUSIM-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Fri 06/06/25",1,"RP-250895","RP-250894","China Telecom ",null,"13/6/24: Compl:0%->5%; Stat Rep: ->RP-240909; ; 4/9/24: FCD:06/06/2025->25/06/2025; Compl:5%->14%; Stat Rep: RP-240909->RP-241957; ; 6/12/24: Compl:14%->72%; Stat Rep: RP-241957->RP-242471; ; 6/3/25: FCD:17/01/2025->06/06/2025; Compl:72%->90%; Stat Rep: R",null,103,52,null,null,"Tue 02/04/24","Fri 18/07/25"]
[1470,0,"Rel-18 NR-only: band related","-",1,"Rel-18",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1471,991042,"Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76",1,"Rel-18","R4","Mon 06/03/23","Tue 12/12/23",1,"RP-233245",null,"Vodafone",null,"6/10/23: WID:RP-230791->RP-232636; 2/1/24: WID:RP-232636->RP-233245",null,99,50,null,null,"Fri 07/04/23","Tue 02/01/24"]
[1472,991142,"   Core part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76-Core",2,"Rel-18","R4","Mon 06/03/23","Tue 12/12/23",1,"RP-233245","RP- 233244","Wael Boukley Hasan, Vodafone","Wael.boukleyhasan@vodafone.com","; 7/6/23: Compl:0%->43%; 6/9/23: FCD:09/09/2023->22/09/2023; Compl:43%->80%; WID: RP-230791->RP-231476; Stat Rep: ->RP-231747; Rapporteur: Vodafone->Wael Boukley Hasan, Vodafone; Rap eMail: ->Wael.boukleyhasan@vodafone.com; ; 21/9/23: FCD:22/09/2023->1...",null,99,50,null,null,"Fri 07/04/23","Fri 08/12/23"]
[1473,991242,"   Perf. part: Addition of FDD NR bands using the uplink from n28 and the downlink of n75 and n76","NR_FDD_ULn28_DLn75_n76-Perf",2,"Rel-18","R4","Mon 06/03/23","Tue 12/12/23",1,"RP-233245","RP- 233244","Wael Boukley Hasan, Vodafone","Wael.boukleyhasan@vodafone.com","6/9/23: FCD:09/09/2023->23/09/2023; WID: RP-230791->RP-231476; Stat Rep: ->RP-231747; Rapporteur: Vodafone->Wael Boukley Hasan, Vodafone; Rap eMail: ->Wael.boukleyhasan@vodafone.com; ; 21/9/23: FCD:23/09/2023->12/12/2023; Stat Rep: RP-231747->RP-232630; ;",null,99,50,null,null,"Fri 07/04/23","Fri 08/12/23"]
[1474,991044,"Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor",1,"Rel-18","R4","Mon 06/03/23","Thu 06/06/24",1,"RP-233999",null,"Vodafone",null,"6/10/23: WID:RP-230805->RP-232677; 2/1/24: WID:RP-232677->RP-233999",null,99,50,null,null,"Fri 07/04/23","Tue 02/01/24"]
[1475,991144,"   Core part: Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor-Core",2,"Rel-18","R4","Mon 06/03/23","Tue 12/12/23",1,"RP-232677","RP-241057","Diogo Martins, Vodafone","diogo.martins@vodafone.com","; 7/6/23: Compl:0%->40%; 6/9/23: Compl:40%->60%; WID: RP-230805->RP-231486; Stat Rep: ->RP-231924; Rapporteur: Vodafone->Diogo Martins, Vodafone; Rap eMail: ->diogo.martins@vodafone.com; ; 8/12/23: Compl:60%->100%; Stat Rep: RP-231924->RP-233039; ; 14/...",null,99,50,null,null,"Fri 07/04/23","Thu 13/06/24"]
[1476,991244,"   Perf. part: Complete the specification support for BandWidth Part operation without restriction in NR","NR_BWP_wor-Perf",2,"Rel-18","R4","Wed 08/03/23","Thu 06/06/24",1,"RP-232677","RP-241057","Diogo Martins, Vodafone","diogo.martins@vodafone.com","; 7/6/23: CD:06/06/2024->06/06/2023; 6/9/23: FCD:06/06/2023->06/06/2024; WID: RP-230805->RP-231486; Stat Rep: ->RP-231924; Rapporteur: Vodafone->Diogo Martins, Vodafone; Rap eMail: ->diogo.martins@vodafone.com; ; 8/12/23: Stat Rep: RP-231924->RP-233039...",null,99,50,null,null,"Fri 07/04/23","Thu 13/06/24"]
[1477,1010055,"Introduction of NR bands n31 and n72 ","NR_bands_n31_n72",1,"Rel-18","R4","Sat 09/09/23","Tue 12/12/23",1,"RP-233950",null,"Nokia ",null,"2/1/24: WID:RP-232691->RP-233950",null,101,51,null,null,"Fri 06/10/23","Tue 02/01/24"]
[1478,1011055,"   Core part: Introduction of NR bands n31 and n72 ","NR_bands_n31_n72-Core",2,"Rel-18","R4","Sat 09/09/23","Tue 12/12/23",1,"RP-233950","RP-233181","Petri Vasenkari, Nokia","petri.j.vasenkari@nokia.com","8/12/23: Compl:0%->100%; Stat Rep: ->RP-233181; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; ",null,101,51,null,null,"Fri 06/10/23","Fri 08/12/23"]
[1479,1012055,"   Perf. part: Introduction of NR bands n31 and n72 ","NR_bands_n31_n72-Perf",2,"Rel-18","R4","Sat 09/09/23","Tue 12/12/23",1,"RP-233950","RP-233181","Petri Vasenkari, Nokia","petri.j.vasenkari@nokia.com","8/12/23: FCD:06/06/2024->12/12/2023; Compl:0%->100%; Stat Rep: ->RP-233181; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; ",null,101,51,null,null,"Fri 06/10/23","Fri 08/12/23"]
[1480,991046,"Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh",1,"Rel-18","R4","Mon 06/03/23","Tue 12/12/23",1,"RP-233991",null,"CATT",null,"6/10/23: WID:RP-230764->RP-232680; 2/1/24: WID:RP-232680->RP-233991",null,99,50,null,null,"Fri 07/04/23","Tue 02/01/24"]
[1481,991146,"   Core part: Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh-Core",2,"Rel-18","R4","Mon 06/03/23","Tue 12/12/23",1,"RP-233991","RP-233005","Shan Huiping, CATT","shanhuiping@catt.cn","; 7/6/23: Compl:0%->50%; 6/9/23: Compl:50%->80%; WID: RP-230764->RP-231450; Stat Rep: ->RP-231833; Rapporteur: CATT->Shan Huiping, CATT; Rap eMail: ->shanhuiping@catt.cn; ; 8/12/23: Compl:80%->100%; Stat Rep: RP-231833->RP-233005; ",null,99,50,null,null,"Fri 07/04/23","Fri 08/12/23"]
[1482,991246,"   Stopped - Perf. part: Enhancement for 700/800/900MHz band combinations for NR","NR_700800900_combo_enh-Perf",2,"Rel-18","R4","Mon 06/03/23","Tue 12/12/23",1,"RP-233991","RP-231833","Shan Huiping, CATT","shanhuiping@catt.cn","6/9/23: WID: RP-230764->RP-231450; Stat Rep: ->RP-231833; Rapporteur: CATT->Shan Huiping, CATT; Rap eMail: ->shanhuiping@catt.cn¦01/24: stopped at 0% at RAN#102",null,99,50,102,null,"Fri 07/04/23","Tue 02/01/24"]
[1483,981044,"Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54",1,"Rel-18",null,"Mon 12/12/22","Fri 03/03/23",1,"RP-230062",null,"Ligado Networks ",null,"29/3/23: WID:RP-223514->RP-230062",null,98,50,null,null,"Mon 09/01/23","Wed 29/03/23"]
[1484,981144,"   Core part: Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54-Core",2,"Rel-18","R4","Mon 12/12/22","Fri 03/03/23",1,"RP-230062","RP-230061","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230061; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ",null,98,50,null,null,"Mon 09/01/23","Fri 17/03/23"]
[1485,981244,"   Perf. part: Introduction of NR TDD band in 1670-1675 MHz (n54) ","NR_TDD_n54-Perf",2,"Rel-18","R4","Mon 12/12/22","Fri 03/03/23",1,"RP-230062","RP-230061","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230061; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ",null,98,50,null,null,"Mon 09/01/23","Fri 17/03/23"]
[1486,981045,"Introduction of 900 MHz NR band in the US ","NR_900MHz_US",1,"Rel-18",null,"Tue 13/12/22","Tue 22/08/23",0.25,"RP-234044",null,"Anterix ",null,"29/3/23: WID:RP-223529->RP-230723; 2/1/24: WID:RP-230723->RP-234044",null,98,50,null,null,"Mon 09/01/23","Tue 02/01/24"]
[1487,981145,"   Core Part: Introduction of 900 MHz NR band in the US ","NR_900MHz_US-Core",2,"Rel-18","R4","Tue 13/12/22","Tue 22/08/23",0.25,"RP-234044","RP-231956","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","17/3/23: Compl:0%->5%; Stat Rep: ->RP-230348; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 21/9/23: Compl:5%->25%; Stat Rep: RP-230348->RP-231956; Rapporteur: Emil Olbrich, Anterix->Gene Fong, Qualcomm Incorporated; Ra",null,98,50,null,null,"Mon 09/01/23","Thu 21/09/23"]
[1488,981245,"   Perf. part: Introduction of 900 MHz NR band in the US ","NR_900MHz_US-Perf",2,"Rel-18","R4","Tue 13/12/22","Tue 22/08/23",0.25,"RP-234044","RP-231956","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","17/3/23: Stat Rep: ->RP-230348; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 21/9/23: Compl:0%->25%; Stat Rep: RP-230348->RP-231956; Rapporteur: Emil Olbrich, Anterix->Gene Fong, Qualcomm Incorporated; Rap eMail: eolbr",null,98,50,null,null,"Mon 09/01/23","Thu 21/09/23"]
[1489,961010,"Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241222",null,"ZTE ",null,"23/9/22: WID:RP-221876->RP-222079; 9/1/23: WID:RP-222079->RP-222904; 29/3/23: WID:RP-222904->RP-230133; 6/10/23: WID:RP-230133->RP-231840; 2/1/24: WID:RP-231840->RP-232920; 2/4/24: WID:RP-232920->RP-240761; 23/7/24: WID:RP-240761->RP-241222",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1490,961110,"   Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241222","RP-241223","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","9/9/22: Comp...; 23/9/22: 38.718-02-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222905; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:2.....","38.718-02-01",96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1491,961210,"   Stopped - Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 2 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_2BDL_xBUL-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-240761","RP-241223","Wubin, Zhou, ZTE","zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222905; Rapporteur: ZTE->Wubin, Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222905->.....",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1492,961011,"Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241089",null,"ZTE ",null,"23/9/22: WID:RP-221877->RP-222092; 9/1/23: WID:RP-222092->RP-222834; 29/3/23: WID:RP-222834->RP-230084; 6/10/23: WID:RP-230084->RP-231860; 2/1/24: WID:RP-231860->RP-233231; 2/4/24: WID:RP-233231->RP-240166; 23/7/24: WID:RP-240166->RP-241089",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1493,961111,"   Core part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241089","RP-241090","Zhifeng Ma, ZTE","ma.zhifeng@zte.com.cn","9/9/22: Comp...; 23/9/22: 38.718-03-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->15%; Stat Rep: ->RP-222835; Rapporteur: ZTE->Zhifeng Ma, ZTE; Rap eMail: ->ma.zhifeng@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:1.....","38.718-03-01",96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1494,961211,"   Perf. part: Rel-18 NR Inter-band Carrier Aggregation/Dual Connectivity for 3 bands DL with x bands UL (x=1,2) ","NR_CADC_R18_3BDL_xBUL-Perf",2,"Rel-18","R4","Thu 16/06/22","Thu 06/06/24",1,"RP-241089","RP-241090","Zhifeng Ma, ZTE","ma.zhifeng@zte.com.cn","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222835; Rapporteur: ZTE->Zhifeng Ma, ZTE; Rap eMail: ->ma.zhifeng@zte.com.cn; 17/3/23: Compl:0%->40%; Stat Rep: RP-222835->RP-230085; ...; 6/9/23: Compl:60%->75%; WID: RP...",null,96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1495,961013,"High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe ","NR_RAIL_HPUE_n100_n101",1,"Rel-18",null,"Thu 01/12/22","Tue 12/12/23",0,"RP-221878",null,"Union Internationale Chemins de Fer (UIC) ",null,null,null,96,49,null,null,"Wed 03/08/22","NA"]
[1496,961113,"   Core part: High Power UE support for NR bands n100 and n101 for Rail Mobile Radio (RMR) in Europe ","NR_RAIL_HPUE_n100_n101-Core",2,"Rel-18","R4","Thu 01/12/22","Tue 12/12/23",0,"RP-221878","RP-222544","Union Internationale Chemins de Fer (UIC) ",null,null,null,96,49,null,null,"Wed 03/08/22","NA"]
[1497,961007,"Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241140",null,"Ericsson ",null,"23/9/22: WID:RP-221835->RP-222105; 9/1/23: WID:RP-222105->RP-222846; 29/3/23: WID:RP-222846->RP-230067; 6/10/23: WID:RP-230067->RP-231623; 2/1/24: WID:RP-231623->RP-233990; 2/4/24: WID:RP-233990->RP-240238; 23/7/24: WID:RP-240238->RP-241140",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1498,961107,"   Core part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241140","RP-241139","Per Lindell, Ericsson","per.lindell@ericsson.com","9/9/22: CD:1...; 23/9/22: 38.718-01-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->71%; Stat Rep: ->RP-222845; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/.....","38.718-01-01",96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1499,961207,"   Stopped - Perf. part: Rel-18 NR intra band Carrier Aggregation for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) ","NR_CA_R18_Intra-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-241140","RP-241139","Per Lindell, Ericsson","per.lindell@ericsson.com","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->71%; Stat Rep: ->RP-222845; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:71%->57%; Stat Rep.....",null,96,49,102,null,"Wed 03/08/22","Thu 13/06/24"]
[1500,961008,"Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241327",null,"Ericsson ",null,"23/9/22: WID:RP-221838->RP-222318; 9/1/23: WID:RP-222318->RP-223438; 29/3/23: WID:RP-223438->RP-230421; 6/10/23: WID:RP-230421->RP-231738; 2/1/24: WID:RP-231738->RP-233696; 2/4/24: WID:RP-233696->RP-240501; 23/7/24: WID:RP-240501->RP-241327",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1501,961108,"   Core part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241327","RP-241328","Reihaneh Malekafzaliardakani, Ericsson","reihaneh.malekafzaliardakani@ericsson.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:25%->29%; Stat Rep: ->RP-222911; Rapporteur: Ericsson->Reihaneh Malekafzaliardakani, Ericsson; Rap eMail: ->reihaneh.malekafzaliardakani@ericsson.com; 17/3/23: FCD:30/11/2023->1.....",null,96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1502,961208,"   Perf. part: Rel-18 NR inter-band Carrier Aggregation/Dual Connectivity for y bands DL (y=4, 5, 6) with x bands UL (x=1, 2) ","NR_CADC_R18_yBDL_xBUL-Perf",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241327","RP-241328","Reihaneh Malekafzaliardakani, Ericsson","reihaneh.malekafzaliardakani@ericsson.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:25%->29%; Stat Rep: ->RP-222911; Rapporteur: Ericsson->Reihaneh Malekafzaliardakani, Ericsson; Rap eMail: ->reihaneh.malekafzaliardakani@ericsson.com; 17/3/23: FCD:30/11/2023->1.....",null,96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1503,960097,"APT 600MHz NR band ","NR_600MHz_APT",1,"Rel-18",null,"Wed 15/06/22","Fri 03/03/23",1,"RP-230060",null,"Spark NZ Ltd ",null,"9/1/23: WID:RP-221778->RP-223265; 29/3/23: WID:RP-223265->RP-230060",null,96,49,null,null,"Wed 03/08/22","Wed 29/03/23"]
[1504,960197,"   Core part: APT 600MHz NR band ","NR_600MHz_APT-Core",2,"Rel-18","R4","Wed 15/06/22","Fri 03/03/23",1,"RP-221778","RP-230053","Mansoor Shafi, Spark New Zealand","Mansoor.shafi@spark.co.nz","9/9/22: Comp...; 23/9/22: 38.892 added;; 9/12/22: FCD:22/12/2022->01/03/2023; Compl:10%->95%; Stat Rep: ->RP-222803; Rapporteur: Spark NZ Ltd->Mansoor Shafi, Spark New Zealand; Rap eMail: ->Mansoor.shafi@spark.co.nz; 17/3/23: Compl:95%->...",38.892000000000003,96,49,null,null,"Wed 03/08/22","Fri 17/03/23"]
[1505,960297,"   Perf. part: APT 600MHz NR band ","NR_600MHz_APT-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 03/03/23",1,"RP-221778","RP-230053","Mansoor Shafi, Spark New Zealand","Mansoor.shafi@spark.co.nz","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:10%->60%; Stat Rep: ->RP-222803; Rapporteur: Spark NZ Ltd->Mansoor Shafi, Spark New Zealand; Rap eMail: ->Mansoor.shafi@spark.co.nz; 17/3/23: Compl:60%->100%; WID: RP-223265->RP...",null,96,49,null,null,"Wed 03/08/22","Fri 17/03/23"]
[1506,960098,"Stopped - Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands",1,"Rel-18",null,"Thu 16/06/22","Tue 12/12/23",1,"RP-222498",null,"Huawei ",null,"23/9/22: WID:RP-221845->RP-22249801/24: stopped at 0% at RAN#102",null,96,49,102,null,"Wed 03/08/22","Tue 02/01/24"]
[1507,960198,"   Stopped - Core part: Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands-Core",2,"Rel-18","R4","Thu 16/06/22","Tue 12/12/23",1,"RP-222498","RP-233184","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","9/9/22: CD:1…; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-221845->RP-222498; Stat Rep: ->RP-223341; Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation¦01/24: stopped at 0% at RAN#102...",null,96,49,102,null,"Wed 03/08/22","Tue 02/01/24"]
[1508,960298,"   Stopped - Perf. part: Introduction of additional 6GHz NR licensed bands ","NR_6GHz_add_bands-Perf",2,"Rel-18","R4","Thu 16/06/22","Tue 12/12/23",1,"RP-222498","RP-233184","Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation","liuliehai@huawei.com, dominique.everaere@ericsson.com, iwajlo.angelow@nokia.com, xue.fei25@zte.com.cn","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-221845->RP-222498; Stat Rep: ->RP-223341; Rapporteur: Huawei->Liehai Liu, Dominique Everaere, Iwajlo Angelow, Fei Xue, Huawei, Ericsson, Nokia, ZTE Corporation; Rap eMail: ->liu...; 8/12/23: S",null,96,49,102,null,"Wed 03/08/22","Tue 02/01/24"]
[1509,960095,"Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18",1,"Rel-18",null,"Wed 15/06/22","Thu 12/12/24",1,"RP-240422",null,"Huawei ",null,"23/9/22: WID:RP-221844->RP-222509; 9/1/23: WID:RP-222509->RP-223516; 6/10/23: WID:RP-223516->RP-232374; 2/1/24: WID:RP-232374->RP-234040; 2/4/24: WID:RP-234040->RP-240422",null,96,49,null,null,"Wed 03/08/22","Tue 02/04/24"]
[1510,960195,"   Core part: Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-Core",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-240422","RP-240421","Xiang Gao, Huawei","gaoxiang74@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->15%; Stat Rep: ->RP-223351; Rapporteur: Huawei->Xiang Gao, Huawei; Rap eMail: ->gaoxiang74@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; Stat Rep: RP-223.....",null,96,49,null,null,"Wed 03/08/22","Thu 14/03/24"]
[1511,960295,"   stopped - Perf. part: Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-240422","RP-233198","Xiang Gao, Huawei","gaoxiang74@huawei.com","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-223351; Rapporteur: Huawei->Xiang Gao, Huawei; Rap eMail: ->gaoxiang74@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; Stat Rep: RP-2233.....; 8/12/23: F",null,96,49,102,null,"Wed 03/08/22","Tue 02/01/24"]
[1512,1000050,"   UE Conformance - Additional NR bands for UL-MIMO in Rel-18 ","NR_bands_UL_MIMO_R18-UEConTest",2,"Rel-18","R5","Thu 08/06/23","Fri 06/06/25",1,"RP-251511","RP-251509","Shi，Yu, China Unicom","shiyu19@chinaunicom.cn","6/9/23: Compl:0%->49%; Stat Rep: ->RP-231550; Rapporteur: China Unicom->Shi，Yu, China Unicom; Rap eMail: ->shiyu19@chinaunicom.cn; ; 8/12/23: Stat Rep: RP-231550->RP-232771; ; 2/1/24: WID:RP-230868->RP-232772; 14/3/24: FCD:05/06/2024->12/12/2024; Stat ...",null,100,51,null,null,"Thu 29/06/23","Fri 18/07/25"]
[1513,960093,"Enhancements of NR shared spectrum bands ","NR_unlic_enh",1,"Rel-18",null,"Wed 15/06/22","Tue 06/06/23",0.99,"RP-230730",null,"Apple ",null,"23/9/22: WID:RP-221813->RP-222174; 29/3/23: WID:RP-222174->RP-230730",null,96,49,null,null,"Wed 03/08/22","Wed 29/03/23"]
[1514,960193,"   Core part: Enhancements of NR shared spectrum bands ","NR_unlic_enh-Core",2,"Rel-18","R4","Wed 15/06/22","Tue 06/06/23",1,"RP-230730","RP-230729","Daniel Popp, Apple Inc.","d_popp@apple.com","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:15%->50%; Stat Rep: ->RP-223194; Rapporteur: Apple->Daniel Popp, Apple Inc.; Rap eMail: ->d_popp@apple.com; 17/3/23: FCD:03/03/2023->08/09/2023; Compl:50%->85%; Stat Rep: RP-223...",null,96,49,null,null,"Wed 03/08/22","Wed 07/06/23"]
[1515,960293,"   Perf. part: Enhancements of NR shared spectrum bands ","NR_unlic_enh-Perf",2,"Rel-18","R4","Wed 15/06/22","Thu 16/02/23",0.99,"RP-230730","RP-230729","Daniel Popp, Apple Inc.","d_popp@apple.com","9/12/22: FCD:15/03/2023->01/03/2023; Compl:0%->50%; Stat Rep: RP-222175->RP-223194; Rapporteur: Apple->Daniel Popp, Apple Inc.; Rap eMail: ->d_popp@apple.com; 17/3/23: Compl:50%->100%; Stat Rep: RP-223194->RP-230152; 31/3/23: FCD:03/03/2023->06/06...",null,96,49,null,null,"Wed 03/08/22","Fri 31/03/23"]
[1516,950071,"Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz",1,"Rel-18",null,"Tue 15/03/22","Tue 12/12/23",1,"RP-222831",null,"Ligado Networks ",null,"9/1/23: WID:RP-220971->RP-222831",null,95,48,null,null,"Tue 05/04/22","Mon 09/01/23"]
[1517,950171,"   Core part: Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz-Core",2,"Rel-18","R4","Tue 15/03/22","Thu 01/12/22",1,"RP-222831","RP-222830","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 6/6/22: Compl:0%->15% ; 6/6 ; 20/6/22: Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com ...; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:50%->100%; Stat Rep: RP-221061->RP-222830; 9/1/23: 100%->100",null,95,48,null,null,"Tue 05/04/22","Mon 09/01/23"]
[1518,950271,"   Perf. part: Introduction of LTE TDD band in 1670-1675 MHz ","LTE_TDD_1670_1675MHz-Perf",2,"Rel-18","R4","Tue 15/03/22","Thu 01/12/22",1,"RP-222831","RP-222830","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 6/6/22: CD:15/12/2022->22/12/2022; 6/6/22: Stat Rep: ->RP-221061; 20/6/22: Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; 9/12/22: FCD:22/12/2022->01/12/2022; Compl:0%->100%; Stat Rep: RP-221061->RP...",null,95,48,null,null,"Tue 05/04/22","Mon 09/01/23"]
[1519,991032,"   UE Conformance - Introduction of LTE TDD band in 1670 – 1675 MHz ","LTE_TDD_1670_1675MHz-UEConTest",2,"Rel-18","R5","Fri 03/03/23","Tue 12/12/23",1,"RP-232783","RP-232784","Ojas Choksi, Ligado Networks","ojas.choksi@ligado.com","; 7/6/23: Compl:0%->83%; 7/6/23: CD:09/09/2023->...; 6/9/23: Compl:83%->99%; WID: RP-230063->RP-230907; Stat Rep: ->RP-231546; Rapporteur: Ligado Networks->Ojas Choksi, Ligado Networks; Rap eMail: ->ojas.choksi@ligado.com; ; 6/10/23: WID:RP-230907->RP...",null,99,50,null,null,"Wed 29/03/23","Tue 02/01/24"]
[1520,960092,"Study on UE support of regionally-defined subsets of an NR band ","FS_NR_subset_band_support",1,"Rel-18","RP","Wed 15/06/22","Fri 03/03/23",1,"RP-223556","RP-230340","Gene Fong, Qualcomm Incorporated","gfong@qti.qualcomm.com","23/9/22: FCD:15/12/2022->12/20; 23/9/22: 0%->40; 23/9/22: WID:RP-221872->RP-222220; 23/9/22: 38.893 added;; 9/1/23: WID:RP-222220->RP-223556; 29/3/23: FCD:12/12/2023->03/23; 29/3/23: 40%->100; 31/3/23: Stat Rep: RP-222222->RP-230340; Rapporteur: Qualcomm-",38.893000000000001,96,49,null,null,"Tue 12/07/22","Fri 31/03/23"]
[1521,1000058,"UE Conformance - New Rel-18 NR licensed bands and extension of existing NR bands ","NR_lic_bands_BW_R18-UEConTest",1,"Rel-18","R5","Thu 08/06/23","Thu 12/12/24",1,"RP-243089","RP-243088","Yuxin Hao, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232360; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ; 6/10/23: WID:RP-231249->RP-232361; 8/12/23: FCD:06/06/2024->06/06/2025; Stat Rep...",null,100,51,null,null,"Thu 29/06/23","Fri 24/01/25"]
[1522,0,"Rel-18 Other NR and LTE","-",1,"Rel-18",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1523,1010053,"Rel-18 basket WI 3Tx NR inter-band UL Carrier Aggregation (CA) and EN-DC ","R18_3Tx_NR_CA_ENDC",1,"Rel-18","R4","Sat 09/09/23","Thu 06/06/24",1,"RP-241149",null,"Oppo ",null,"2/1/24: WID:RP-232674->RP-232941; 2/4/24: WID:RP-232941->RP-240307; 23/7/24: WID:RP-240307->RP-241149",null,101,51,null,null,"Fri 06/10/23","Tue 23/07/24"]
[1524,1011053,"   Core pat: Rel-18 basket WI 3Tx NR inter-band UL Carrier Aggregation (CA) and EN-DC ","R18_3Tx_NR_CA_ENDC-Core",2,"Rel-18","R4","Sat 09/09/23","Thu 06/06/24",1,"RP-241149","RP-241150","Jinqiang Xing, OPPO","xingjinqiang@oppo.com","8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->30%; Stat Rep: ->RP-232940; Rapporteur: Oppo->Jinqiang Xing, OPPO; Rap eMail: ->xingjinqiang@oppo.com; ; 4/1/24: 38.880 added;; 14/3/24: FCD:01/03/2024->06/06/2024; Compl:30%->70%; Stat Rep: RP-232940->RP...",38.880000000000003,101,51,null,null,"Fri 06/10/23","Thu 13/06/24"]
[1525,970088,"Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18",1,"Rel-18",null,"Mon 12/09/22","Thu 06/06/24",1,"RP-241144",null,"Ericsson ",null,"9/1/23: WID:RP-222660->RP-222848; 29/3/23: WID:RP-222848->RP-230069; 6/10/23: WID:RP-230069->RP-231625; 2/1/24: WID:RP-231625->RP-233977; 2/4/24: WID:RP-233977->RP-240241; 23/7/24: WID:RP-240241->RP-241144",null,97,49,null,null,"Wed 19/10/22","Tue 23/07/24"]
[1526,970188,"   Core part: Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18-Core",2,"Rel-18","R4","Mon 12/09/22","Thu 06/06/24",1,"RP-241144","RP-241143","Per Lindell, Ericsson","per.lindell@ericsson.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->14%; Stat Rep: ->RP-222847; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:14%->19%; Stat Rep: RP-222847->RP-230068; 17/...;...",38.898000000000003,97,49,null,null,"Wed 19/10/22","Thu 13/06/24"]
[1527,970288,"   Stopped - Perf. part: Rel-18 High power UE (power class m with 1<m<3) for a single FR1 band in UL of Dual Connectivity (DC) combinations of x bands (x=1,2,3, 4 for y=1 or x=1, 2 for y=2) LTE inter-band CA (xDL/1UL) and y bands NR inter-band CA (yDL/1UL) ","HPUE_FR1_DC_LTE_NR_R18-Perf",2,"Rel-18","R4","Mon 12/09/22","Tue 12/12/23",1,"RP-241144","RP-240240","Per Lindell, Ericsson","per.lindell@ericsson.com","9/12/22: FCD:12/12/2023->01/12/2023; Compl:0%->14%; Stat Rep: ->RP-222847; Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:14%->19%; Stat Rep: RP-222847->RP-230068; ;...; 6...",null,97,49,102,null,"Wed 19/10/22","Tue 23/07/24"]
[1528,1000054,"UE Conformance - Rel-18 High Power UE for NR CA and DC; and NR and LTE DC Configurations; ","HPUE_NR_CADC_NR_LTE_DC_R18-UEConTest",1,"Rel-18","R5","Thu 08/06/23","Fri 12/12/25",0.9,"RP-231199","RP-251458","Lei GAO, China Telecom","gaol8@chinatelecom.cn","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232259; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; ; 8/12/23: FCD:06/06/2024->06/06/2025; Compl:5%->15%; Stat Rep: RP-232259->RP-233565; ; 14/3...",null,100,51,null,null,"Thu 29/06/23","Fri 06/06/25"]
[1529,961012,"High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands ","LTE_NR_HPUE_FWVM_R18",1,"Rel-18",null,"Wed 15/06/22","Thu 12/12/24",1,"RP-240941",null,"Nokia ",null,"19/10/22: acronym corrected; 9/1/23: WID:RP-221841->RP-223424; 6/10/23: WID:RP-223424->RP-231615; 2/1/24: WID:RP-231615->RP-233180; 2/4/24: WID:RP-233180->RP-240361; 23/7/24: WID:RP-240361->RP-240941",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1530,961112,"   Core part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands ","LTE_NR_HPUE_FWVM_R18-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-240941","RP-240942","Petri Vasenkari, Nokia","petri.j.vasenkari@nokia.com","9/9/22: Comp...; 23/9/22: 37.829 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; WID: RP-222058->RP-221841; Stat Rep: ->RP-222825; Rapporteur: Nokia->Petri Vasenkari, Nokia; Rap eMail: ->petri.j.vasenkari@nokia.com; 17/3/23:.....",37.829000000000001,96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1531,1000059,"   UE Conformance - High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands in Rel-18 ","LTE_NR_HPUE_FWVM_R18-UEConTest",2,"Rel-18","R5","Thu 08/06/23","Thu 12/12/24",1,"RP-242837","RP-242836","Tuomo S yn j kangas, Nokia","tuomo.saynajakangas@nokia.com","6/9/23: Compl:0%->18%; Stat Rep: ->RP-231612; Rapporteur: Nokia->Tuomo S yn j kangas, Nokia; Rap eMail: ->tuomo.saynajakangas@nokia.com; ; 6/10/23: WID:RP-231429->RP-231613; 8/12/23: WID: RP-231615->RP-231613; Stat Rep: RP-231612->RP-232856; ; 14/3/24:...",null,100,51,null,null,"Thu 29/06/23","Fri 24/01/25"]
[1532,1000057,"UE Conformance - Rel-18 NR CA and DC; and NR and LTE DC Configurations ","NR_CADC_NR_LTE_DC_R18-UEConTest",1,"Rel-18","R5","Thu 08/06/23","Fri 12/12/25",0.76,"RP-240285","RP-251487","Chunying GU, Huawei Technologies. Co., Ltd.","guchunying@huawei.com","6/9/23: FCD:06/06/2025->06/06/2024; Compl:0%->5%; Stat Rep: ->RP-232359; Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co., Ltd.; Rap eMail: ->haoyuxin@huawei.com; ; 8/12/23: FCD:06/06/2024->06/06/2025; Stat Rep: RP-232359->RP-233767; ; 14/3/24: ...",null,100,51,null,null,"Thu 29/06/23","Fri 06/06/25"]
[1533,981041,"4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC ","4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC",1,"Rel-18",null,"Tue 13/12/22","Tue 12/12/23",1,"RP-234046",null,"Oppo ",null,"29/3/23: WID:RP-223517->RP-230161; 6/10/23: WID:RP-230161->RP-231719; 2/1/24: WID:RP-231719->RP-234046",null,98,50,null,null,"Mon 09/01/23","Tue 02/01/24"]
[1534,981141,"   Core part: 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC ","4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC-Core",2,"Rel-18","R4","Tue 13/12/22","Tue 12/12/23",1,"RP-234046","RP-232937","Jinqiang Xing, OPPO","xingjinqiang@oppo.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230160; Rapporteur: Oppo->Jinqiang Xing, OPPO; Rap eMail: ->xingjinqiang@oppo.com; ; 29/6/23: 10%->70; 6/9/23: Compl:70%->85%; WID: RP-230161->RP-231013; Stat Rep: RP-231012->RP-231718; ; 8/12/23: Compl:85%->100%; S",null,98,50,null,null,"Mon 09/01/23","Fri 08/12/23"]
[1535,1020088,"UE Conformance - 4Rx handheld UE for low NR bands (<1GHz) and/or 3Tx for NR inter-band UL Carrier Aggregation (CA) and EN-DC ","4Rx_low_NR_band_handheld_3Tx_NR_CA_ENDC-UEConTest",1,"Rel-18","R5","Wed 13/12/23","Mon 03/03/25",1,"RP-250447","RP-250446","Yaping ZHANG, Huawei","zhangyaping13@huawei.com","14/3/24: Compl:0%->7%; Stat Rep: ->RP-240289; Rapporteur: Huawei->Yaping ZHANG, Huawei; Rap eMail: ->zhangyaping13@huawei.com; 2/4/24: corrected: rel-19->Rel-18; 13/6/24: Compl:7%->26%; Stat Rep: RP-240289->RP-241376; ; 4/9/24: FCD:06/06/2025->25/06/2025;",null,102,52,null,null,"Tue 02/01/24","Thu 03/04/25"]
[1536,970084,"Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18",1,"Rel-18",null,"Thu 08/09/22","Mon 09/09/24",1,"RP-241251",null,"Huawei ",null,"9/1/23: WID:RP-222648->RP-223354; 2/1/24: WID:RP-223354->RP-234002; 2/4/24: WID:RP-234002->RP-240425; 23/7/24: WID:RP-240425->RP-241251",null,97,49,null,null,"Fri 23/09/22","Tue 23/07/24"]
[1537,970184,"   Core part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18-Core",2,"Rel-18","R4","Thu 08/09/22","Thu 06/06/24",1,"RP-241251","RP-241250","Dan Hu, Huawei","hudan11@huawei.com","9/12/22: Acronym:LTE_NR_Simult_RxTx_R18-Core->LTE_NR _Simult_RxTx_R18-Core; FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223353; Rapporteur: Huawei->Dan Hu, Huawei; Rap eMail: ->hudan11@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; C.....",38.893999999999998,97,49,null,null,"Fri 23/09/22","Thu 13/06/24"]
[1538,970284,"   Stopped - Perf. part: Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18-Perf",2,"Rel-18","R4","Thu 08/09/22","Fri 01/03/24",1,"RP-240425","RP-233201","Dan Hu, Huawei","hudan11@huawei.com","9/12/22: Acronym:LTE_NR_Simult_RxTx_R18-Perf->LTE_NR _Simult_RxTx_R18-Perf; FCD:10/12/2023->01/12/2023; Compl:0%->20%; Stat Rep: ->RP-223353; Rapporteur: Huawei->Dan Hu, Huawei; Rap eMail: ->hudan11@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; C.....",null,97,49,102,null,"Fri 23/09/22","Tue 02/01/24"]
[1539,1030068,"   UE Conformance - Simultaneous Rx/Tx band combinations for NR CA/DC, NR SUL and LTE/NR DC in Rel-18 ","LTE_NR_Simult_RxTx_R18-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Mon 09/09/24",1,"RP-242077","RP-242076","Huawei ",null,"13/6/24: Compl:0%->58%; Stat Rep: ->RP-241379; ; 4/9/24: FCD:06/06/2025->24/09/2024; Compl:58%->100%; Stat Rep: RP-241379->RP-242076; ; 26/9/24: WID:RP-240292->RP-242077",null,103,52,null,null,"Tue 02/04/24","Thu 26/09/24"]
[1540,970082,"Enhancement of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh",1,"Rel-18",null,"Thu 08/09/22","Fri 06/06/25",1,"RP-234064",null,"Vivo ",null,"9/1/23: WID:RP-222669->RP-223112; 2/1/24: WID:RP-223112->RP-234064",null,97,49,null,null,"Fri 23/09/22","Tue 02/01/24"]
[1541,970182,"   Core part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh-Core",2,"Rel-18","R4","Thu 08/09/22","Mon 23/12/24",1,"RP-234064","RP-241829","Wang, Ruixin, vivo","ruixin.wang@vivo.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->15%; Stat Rep: ->RP-223111; Rapporteur: Vivo->Wang, Ruixin, vivo; Rap eMail: ->ruixin.wang@vivo.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Rep: RP-223111->RP-230375; 17/3/23: 38.87...;...",38.869999999999997,97,49,null,null,"Fri 23/09/22","Wed 04/09/24"]
[1542,970282,"   Perf. Part: Enhancement of UE TRP and TRS requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh-Perf",2,"Rel-18","R4","Mon 12/09/22","Mon 09/09/24",1,"RP-242327","RP-241829","Wang, Ruixin, vivo","ruixin.wang@vivo.com","9/12/22: FCD:10/06/2024->01/06/2024; Stat Rep: ->RP-223111; Rapporteur: Vivo->Wang, Ruixin, vivo; Rap eMail: ->ruixin.wang@vivo.com; 17/3/23: Compl:0%->5%; Stat Rep: RP-223111->RP-230375; ;...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:20%->30%; Stat ...",null,97,49,null,null,"Fri 23/09/22","Thu 26/09/24"]
[1543,1040111,"   UE Conformance - Enhancement of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS_enh-UEConTest",2,"Rel-18","R5","Thu 06/06/24","Fri 06/06/25",1,"RP-251502","RP-251178","Apple ",null,"4/9/24: FCD:06/06/2025->25/06/2025; Compl:0%->5%; Stat Rep: ->RP-241899; ; 6/12/24: Compl:5%->30%; Stat Rep: RP-241899->RP-242480; ; 24/1/25: WID:RP-241503->RP-242602; 6/3/25: FCD:14/02/2025->06/06/2025; Compl:30%->70%; WID: RP-242602->RP-241503; Stat Re",null,104,53,null,null,"Tue 23/07/24","Fri 18/07/25"]
[1544,961009,"Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241248",null,"Huawei ",null,"23/9/22: WID:RP-221839->RP-222507; 9/1/23: WID:RP-222507->RP-223537; 29/3/23: WID:RP-223537->RP-230475; 6/10/23: WID:RP-230475->RP-232372; 2/1/24: WID:RP-232372->RP-233197; 2/4/24: WID:RP-233197->RP-240420; 23/7/24: WID:RP-240420->RP-241248",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1545,961109,"   Core part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241248","RP-241247","Zhang, Peng, Huawei","zhangpeng169@huawei.com","9/9/22: Comp...; 23/9/22: 37.718-00-00 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->20%; Stat Rep: ->RP-223349; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023.....","37.718-00-00",96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1546,961209,"   Stopped - Perf. Part: Rel-18 single SUL band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R18-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-241248","RP-241247","Zhang, Peng, Huawei","zhangpeng169@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->20%; Stat Rep: ->RP-223349; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP.....",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1547,961001,"Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241233",null,"CHTTL ",null,"23/9/22: WID:RP-221264->RP-222091; 9/1/23: WID:RP-222091->RP-223078; 29/3/23: WID:RP-223078->RP-230338; 6/10/23: WID:RP-230338->RP-232302; 2/1/24: WID:RP-232302->RP-233242; 2/4/24: WID:RP-233242->RP-240482; 23/7/24: WID:RP-240482->RP-241233",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1548,961101,"   Core part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241233","RP-241219","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","9/9/22: Comp...; 23/9/22: 37.718-11-11 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; WID: RP-222091->RP-222091 Revised WID: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL); Stat Rep: ->RP-223077;...","37.718-11-11",96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1549,961201,"   Perf. part: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_1BLTE_1BNR_2DL2UL-Perf",2,"Rel-18","R4","Thu 16/06/22","Thu 06/06/24",1,"RP-241233","RP-241219","Bo-Han Hsieh (Tank), CHTTL","pohanhsieh@cht.com.tw","9/9/22: CD:1...; 9/12/22: FCD:23/12/2022->01/12/2023; WID: RP-222091->RP-222091 Revised WID: Rel-18 Dual Connectivity (DC) of 1 band LTE (1DL/1UL) and 1 NR band (1DL/1UL); Stat Rep: ->RP-223077; Rapporteur: CHTTL->Bo-Han Hsieh (Tank), CHTT...",null,96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1550,961002,"Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",0.87,"RP-241274",null,"Samsung ",null,"23/9/22: WID:RP-221400->RP-222237; 2/1/24: WID:RP-222237->RP-233989; 2/4/24: WID:RP-233989->RP-240374; 23/7/24: WID:RP-240374->RP-241274",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1551,961102,"   Core part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241274","RP-241273","Yuanyuan Zhang, Samsung","Tina55.zhang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222924; Rapporteur: Samsung->Yuanyuan Zhang, Samsung; Rap eMail: ->Tina55.zhang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Re.....",null,96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1552,961202,"   Perf. part: Rel-18 Dual Connectivity (DC) of x LTE bands and y NR bands with z bands DL and 3 bands UL (x=1, 2, 3, 4; y=1, 2; 3<=z<=6) ","DC_R18_xBLTE_yBNR_zDL3UL-Perf",2,"Rel-18","R4","Wed 15/06/22","Tue 27/06/23",0.7,"RP-241274","RP-241273","Yuanyuan Zhang, Samsung","Tina55.zhang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222924; Rapporteur: Samsung->Yuanyuan Zhang, Samsung; Rap eMail: ->Tina55.zhang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30%; Stat Re.....",null,96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1553,961003,"Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) ","DC_R18_xBLTE_2BNR_yDL2UL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241052",null,"LG Electronics ",null,"23/9/22: WID:RP-221800->RP-221944; 9/1/23: WID:RP-221944->RP-222840; 29/3/23: WID:RP-222840->RP-230725; 6/10/23: WID:RP-230725->RP-231723; 2/1/24: WID:RP-231723->RP-233488; 2/4/24: WID:RP-233488->RP-240758; 23/7/24: WID:RP-240758->RP-241052",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1554,961103,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL) ","DC_R18_xBLTE_2BNR_yDL2UL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241052","RP-241053","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","9/9/22: Comp...; 23/9/22: 37.718-11-21 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222841; Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; 17/3/23: FCD:30/11/2.....","37.718-11-21",96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1555,961203,"   Stopped - Perf. Part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R18_xBLTE_2BNR_yDL2UL-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-241052","RP-241053","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222841; Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->30.....",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1556,961004,"Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241245",null,"Huawei ",null,"23/9/22: WID:RP-221832->RP-222505; 9/1/23: WID:RP-222505->RP-223348; 29/3/23: WID:RP-223348->RP-230473; 6/10/23: WID:RP-230473->RP-232370; 2/1/24: WID:RP-232370->RP-233987; 2/4/24: WID:RP-233987->RP-240417; 23/7/24: WID:RP-240417->RP-241245",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1557,961104,"   Core part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241245","RP-241244","Liehai Liu, Huawei","liuliehai@huawei.com","9/9/22: Comp...; 23/9/22: 37.718-21-11 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; Stat Rep: ->RP-223347; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Co.....","37.718-21-11",96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1558,961204,"   Stopped - Perf. part: Rel-18 Dual Connectivity (DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_2BLTE_1BNR_3DL2UL-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-241245","RP-233192","Liehai Liu, Huawei","liuliehai@huawei.com","9/9/22: Comp…; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:10%->30%; Stat Rep: ->RP-223347; Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:30%->50%¦01/24: stopped at 85% at RAN#102",null,96,49,102,null,"Wed 03/08/22","Tue 02/01/24"]
[1559,961005,"Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241166",null,"Nokia ",null,"23/9/22: WID:RP-221833->RP-222312; 9/1/23: WID:RP-222312->RP-222876; 29/3/23: WID:RP-222876->RP-230090; 6/10/23: WID:RP-230090->RP-232248; 2/1/24: WID:RP-232248->RP-233988; 2/4/24: WID:RP-233988->RP-240384; 23/7/24: WID:RP-240384->RP-241166",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1560,961105,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241166","RP-241165","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->15%; Stat Rep: ->RP-222875; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:15%->25%; S.....",null,96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1561,961205,"   Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=3,4,5) LTE inter-band CA (xDL/1UL) and 1 NR band (1DL/1UL) ","DC_R18_xBLTE_1BNR_yDL2UL-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-241166","RP-240382","Johannes Hejselbaek, Nokia","johannes.hejselbaek@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222875; Rapporteur: Nokia->Johannes Hejselbaek, Nokia; Rap eMail: ->johannes.hejselbaek@nokia.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:5%->10%; Stat Rep: RP-2228.....",null,96,49,null,null,"Wed 03/08/22","Thu 14/03/24"]
[1562,961006,"Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241225",null,"ZTE ",null,"23/9/22: WID:RP-221834->RP-222094; 9/1/23: WID:RP-222094->RP-222906; 29/3/23: WID:RP-222906->RP-230135; 6/10/23: WID:RP-230135->RP-231842; 2/1/24: WID:RP-231842->RP-232923; 2/4/24: WID:RP-232923->RP-240760; 23/7/24: WID:RP-240760->RP-241225",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1563,961106,"   Core part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241225","RP-24xxxx","Wubin Zhou, ZTE","Zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222907; Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->Cao.aijun@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222907->RP-.....",null,96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1564,961206,"   Stopped - Perf. part: Rel-18 Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and y bands (3<=y<=5 and x+y <= 6) NR inter-band CA (yDL/1UL) ","DC_R18_xBLTE_yBNR_zDL2UL-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-240760","RP-24xxxx","Wubin Zhou, ZTE","Zhou.wubin@zte.com.cn","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->20%; Stat Rep: ->RP-222907; Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->Cao.aijun@zte.com.cn; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:20%->40%; Stat Rep: RP-222907->RP-.....",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1565,960096,"Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18",1,"Rel-18",null,"Wed 15/06/22","Tue 12/12/23",1,"RP-230390",null,"CATT ",null,"23/9/22: WID:RP-221879->RP-222385; 29/3/23: WID:RP-222385->RP-230390",null,96,49,null,null,"Wed 03/08/22","Wed 29/03/23"]
[1566,960196,"   Core part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18-Core",2,"Rel-18","R4","Wed 15/06/22","Tue 12/12/23",1,"RP-230390","RP-233006","Qiuge Guo, CATT","guoqiuge@catt.cn","9/9/22: Comp...; 23/9/22: 37.878 added;; 17/3/23: FCD:23/12/2022->12/12/2023; Compl:5%->50%; Stat Rep: ->RP-230389; Rapporteur: CATT->Qiuge Guo, CATT; Rap eMail: ->guoqiuge@catt.cn; ; 6/9/23: Stat Rep: RP-230389->RP-231834; ; 8/12/23: Compl:5",37.878,96,49,null,null,"Wed 03/08/22","Fri 08/12/23"]
[1567,960296,"   Perf. part: Rel-18 band combinations for concurrent operation of NR/LTE Uu bands/band combinations and one NR/LTE V2X PC5 band ","NR_LTE_V2X_PC5_combos_R18-Perf",2,"Rel-18","R4","Wed 15/06/22","Tue 12/12/23",1,"RP-230390","RP-233006","Qiuge Guo, CATT","guoqiuge@catt.cn","9/9/22: CD:1...; 9/12/22: Acronym:NR_LTE_V2X_PC5_combos_R18-Perf->NR_LTE_V2X_PC5_combos_R18-Core; FCD:23/12/2022->01/12/2023; Compl:0%->50%; Stat Rep: ->RP-223146; Rapporteur: CATT->Qiuge Guo, CATT; Rap eMail: ->guoqiuge@catt.cn; 17/3/23.....",null,96,49,null,null,"Wed 03/08/22","Fri 08/12/23"]
[1568,960094,"Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18",1,"Rel-18",null,"Wed 15/06/22","Fri 06/06/25",1,"RP-233588",null,"China Telecom ","LTE, NR ","23/9/22: WID:RP-221843->RP-222288; 2/1/24: WID:RP-222288->RP-233588",null,96,49,null,null,"Wed 03/08/22","Tue 02/01/24"]
[1569,960194,"   Core part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18-Core",2,"Rel-18","R4","Wed 15/06/22","Tue 12/12/23",1,"RP-233588","RP-233587","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","9/9/22: Comp...; 23/9/22: 37.877 added;; 17/3/23: FCD:23/12/2022->12/12/2023; Compl:10%->99%; WID: RP-222288->RP-221843 RP-222288; Stat Rep: ->RP-230319; Rapporteur: China Telecom->Liu, Bo, China Telecom; Rap eMail: LTE, NR->liubo1@chinate...",37.877000000000002,96,49,null,null,"Wed 03/08/22","Fri 08/12/23"]
[1570,960294,"   Perf. part: Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18-Perf",2,"Rel-18","R4","Wed 15/06/22","Tue 12/12/23",1,"RP-233588","RP-233587","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","9/9/22: CD:1...; 9/12/22: Acronym:DL_intrpt_combos_TxSW_R18-Perf->DL_intrpt_combos_TxSW_R18-Core; FCD:23/12/2022->01/12/2023; Compl:0%->20%; WID: RP-222288->RP-221843 RP-222288; Stat Rep: ->RP-222939; Rapporteur: China Telecom->Liu, Bo, Ch...",null,96,49,null,null,"Wed 03/08/22","Fri 08/12/23"]
[1571,1050129,"   UE Conformance - Rel-18 downlink interruption for NR and EN-DC band combinations at dynamic Tx Switching in Uplink ","DL_intrpt_combos_TxSW_R18-UEConTest",2,"Rel-18","R5","Mon 09/09/24","Fri 06/06/25",1,"RP-251465","RP-251464","China Telecom ",null,"6/12/24: Compl:0%->67%; Stat Rep: ->RP-242853; ; 6/3/25: FCD:24/07/2025->12/12/2025; Compl:67%->69%; Stat Rep: RP-242853->RP-250380; ; 6/6/25: FCD:Fri 12/12/25->Fri 06/06/25; Compl:69%->100%; Stat Rep: RP-250380->RP-251464; ; 18/7/25: WID:RP-242001->RP-2",null,105,53,null,null,"Thu 26/09/24","Fri 18/07/25"]
[1572,0,"Rel-18 Other LTE-only","-",1,"Rel-18",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1573,960099,"Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL",1,"Rel-18",null,"Wed 15/06/22","Thu 06/06/24",1,"RP-241242",null,"Huawei ","LTE ","23/9/22: WID:RP-221831->RP-222503; 9/1/23: WID:RP-222503->RP-223489; 29/3/23: WID:RP-223489->RP-230471; 6/10/23: WID:RP-230471->RP-232368; 2/1/24: WID:RP-232368->RP-233927; 2/4/24: WID:RP-233927->RP-240414; 23/7/24: WID:RP-240414->RP-241242",null,96,49,null,null,"Wed 03/08/22","Tue 23/07/24"]
[1574,960199,"   Core part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 06/06/24",1,"RP-241242","RP-241241","Mohammad Abdi Abyaneh, Huawei- HiSilicon","Mohammad.abdi.abyaneh@huawei.com","9/9/22: Comp...; 23/9/22: 36.718-02-01 added;; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:20%->35%; Stat Rep: ->RP-223345; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei; Rap eMail: LTE->Mohammad.abdi.abyaneh@huawei.com; 17/3/23: FCD:.....","36.718-02-01",96,49,null,null,"Wed 03/08/22","Thu 13/06/24"]
[1575,960299,"   Stopped - Perf. part: Rel-18 LTE-Advanced Carrier Aggregation for x bands (2<=x<= 6) DL with y bands (y=1, 2) UL ","LTE_CA_R18_xBDL_yBUL-Perf",2,"Rel-18","R4","Wed 15/06/22","Fri 01/03/24",1,"RP-240414","RP-233189","Mohammad Abdi Abyaneh, Huawei- HiSilicon","Mohammad.abdi.abyaneh@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:20%->35%; Stat Rep: ->RP-223345; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei; Rap eMail: LTE->Mohammad.abdi.abyaneh@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Stat R.....; 2/1/24: St",null,96,49,102,null,"Wed 03/08/22","Tue 02/01/24"]
[1576,961000,"LTE intra-band contiguous Carrier Aggregation for band 8 ","LTE_CA_intra_B8",1,"Rel-18","R4","Wed 15/06/22","Thu 22/12/22",1,"RP-221846",null,"China Mobile ","LTE ",null,null,96,49,null,null,"Wed 03/08/22","NA"]
[1577,961100,"   Core part: LTE intra-band contiguous Carrier Aggregation for band 8 ","LTE_CA_intra_B8-Core",2,"Rel-18","R4","Wed 15/06/22","Thu 22/12/22",1,"RP-221846",null,"China Mobile ","LTE ","9/9/22: Comp...; 9/1/23: 99%->100",null,96,49,null,null,"Wed 03/08/22","Mon 09/01/23"]
[1578,1080079,"UE Conformance - Rel-18 LTE CA Configurations ","LTE_CA_R18-UEConTest",1,"Rel-18","R5","Fri 06/06/25","Wed 09/09/26",0,"RP-251457",null,"China Telecom ",null,"tested: REL-18 WI LTE_CA_R18_xBDL_yBUL-Core; compare: LTE_CA_R17, LTE_CA_R16, LTE_CA_R15, LTE_CA_R14 ",null,108,55,null,null,"Fri 18/07/25","NA"]
[1579,1010054,"High Power UE (Power Class 2) for LTE FDD Band 14 ","HPUE_LTE_FDD_B14",1,"Rel-18","R4","Sat 09/09/23","Fri 01/03/24",1,"RP-232946",null,"AT&T ",null,"2/1/24: WID:RP-232676->RP-232946",null,101,51,null,null,"Fri 06/10/23","Tue 02/01/24"]
[1580,1011054,"   Core part: High Power UE (Power Class 2) for LTE FDD Band 14 ","HPUE_LTE_FDD_B14-Core",2,"Rel-18","R4","Sat 09/09/23","Fri 01/03/24",1,"RP-232946","RP-240075","Borsato, Ron","ronald.borsato@att.com","8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->50%; Stat Rep: ->RP-232945; Rapporteur: AT&T->Borsato, Ron; Rap eMail: ->ronald.borsato@att.com; ; 4/1/24: 36.770 added;; 14/3/24: Compl:50%->100%; Stat Rep: RP-232945->RP-240075; List of Impacted TS & TR up",36.770000000000003,101,51,null,null,"Fri 06/10/23","Thu 14/03/24"]
[1581,1012054,"   Perf. part: High Power UE (Power Class 2) for LTE FDD Band 14 ","HPUE_LTE_FDD_B14-Perf",2,"Rel-18","R4","Sat 09/09/23","Fri 01/03/24",1,"RP-232946","RP-240075","Borsato, Ron","ronald.borsato@att.com","8/12/23: FCD:12/12/2023->01/03/2024; Compl:0%->80%; Stat Rep: ->RP-232945; Rapporteur: AT&T->Borsato, Ron; Rap eMail: ->ronald.borsato@att.com; ; 14/3/24: Compl:80%->100%; Stat Rep: RP-232945->RP-240075; ",null,101,51,null,null,"Fri 06/10/23","Thu 14/03/24"]
[1582,981048,"Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2",1,"Rel-18",null,"Tue 13/12/22","Tue 12/12/23",1,"RP-232892",null,"Ericsson ",null,"2/1/24: WID:RP-222824->RP-232892",null,98,50,null,null,"Mon 09/01/23","Tue 02/01/24"]
[1583,981148,"   Core part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2-Core",2,"Rel-18","R4","Tue 13/12/22","Tue 12/12/23",1,"RP-232892","RP- 232891","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","17/3/23: Compl:0%->99%; Stat Rep: ->RP-230462; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 6/9/23: Stat Rep: RP-230462->RP-231880; ; 8/12/23: Compl:99%->100%; Stat Rep: RP-231880->RP- 232891; ",null,98,50,null,null,"Mon 09/01/23","Fri 08/12/23"]
[1584,981248,"   Perf. part: Additional LTE bands for UE categories M1/M2/NB1/NB2 in Rel-18 ","LTE_bands_R18_M1_M2_NB1_NB2-Perf",2,"Rel-18","R4","Tue 13/12/22","Tue 12/12/23",1,"RP-232892","RP- 232891","Chunhui Zhang, Ericsson","Chunhui.Zhang@ericsson.com","17/3/23: Compl:0%->99%; Stat Rep: ->RP-230462; Rapporteur: Ericsson->Chunhui Zhang, Ericsson; Rap eMail: ->Chunhui.Zhang@ericsson.com; ; 6/9/23: Stat Rep: RP-230462->RP-231880; ; 8/12/23: Compl:99%->100%; Stat Rep: RP-231880->RP- 232891; ",null,98,50,null,null,"Mon 09/01/23","Fri 08/12/23"]
[1585,981046,"Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US",1,"Rel-18",null,"Mon 12/12/22","Mon 03/03/25",0.83,"RP-230722",null,"Anterix ",null,"29/3/23: WID:RP-223530->RP-230722",null,98,50,null,null,"Mon 09/01/23","Wed 29/03/23"]
[1586,981146,"   Core part: Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US-Core",2,"Rel-18","R4","Mon 12/12/22","Tue 06/06/23",1,"RP-230722","RP-231218","Emil Olbrich, Anterix","eolbrich@anterix.com","17/3/23: Compl:0%->20%; Stat Rep: ->RP-230264; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ; 29/6/23: 20%->100",null,98,50,null,null,"Mon 09/01/23","Thu 29/06/23"]
[1587,981246,"   Perf. part: Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US-Perf",2,"Rel-18","R4","Mon 12/12/22","Thu 13/04/23",0.1,"RP-230722","RP-231218","Emil Olbrich, Anterix","eolbrich@anterix.com","17/3/23: Compl:0%->10%; Stat Rep: ->RP-230264; Rapporteur: Anterix->Emil Olbrich, Anterix; Rap eMail: ->eolbrich@anterix.com; ",null,98,50,null,null,"Mon 09/01/23","Fri 17/03/23"]
[1588,1030064,"   UE Conformance - Introduction of 900 MHz LTE band in the US ","LTE_900MHz_US-UEConTest",2,"Rel-18","R5","Sun 03/03/24","Tue 09/09/25",0.96,"RP-240096","RP-250888","Nokia ",null,"13/6/24: Compl:0%->85%; Stat Rep: ->RP-240915; ; 4/9/24: FCD:03/03/2025->25/03/2025; Stat Rep: RP-240915->RP-241747; ; 6/12/24: Stat Rep: RP-241747->RP-242838; ; 6/3/25: FCD:12/11/2024->06/06/2025; Stat Rep: RP-242838->RP-250081; ; 6/6/25: FCD:Fri 06/06/2",null,103,52,null,null,"Tue 02/04/24","Fri 06/06/25"]
[1589,981040,"Maximum Power Reduction Requirements (MPR) for LTE intra-band Carrier Aggregation (CA) with a Component Carrier (CC) gap larger than 35 MHz ","LTE_intra_CA_MPR_35MHz_gap",1,"Rel-18",null,"Mon 12/12/22","Fri 03/03/23",1,"RP-230705",null,"Huawei ",null,"29/3/23: WID:RP-223511->RP-230705",null,98,50,null,null,"Mon 09/01/23","Wed 29/03/23"]
[1590,981140,"   Core part: Maximum Power Reduction Requirements (MPR) for LTE intra-band Carrier Aggregation (CA) with a Component Carrier (CC) gap larger than 35 MHz ","LTE_intra_CA_MPR_35MHz_gap-Core",2,"Rel-18","R4","Mon 12/12/22","Fri 03/03/23",1,"RP-230705","RP-230480","Mohammad Abdi Abyaneh, Huawei, HiSilicon","Mohammad.abdi.abyaneh@huawei.com","17/3/23: FCD:06/06/2023->03/03/2023; Compl:0%->100%; Stat Rep: ->RP-230480; Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei, HiSilicon; Rap eMail: ->Mohammad.abdi.abyaneh@huawei.com; ",null,98,50,null,null,"Mon 09/01/23","Fri 17/03/23"]
[1591,991040,"Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW",1,"Rel-18","R4","Mon 29/05/23","Tue 12/12/23",0,"RP-230745",null,"T-Mobile USA ",null,null,null,99,50,null,null,"Wed 29/03/23","NA"]
[1592,991140,"   Core part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW-Core",2,"Rel-18","R4","Mon 29/05/23","Tue 12/12/23",0,"RP-230745",null,"T-Mobile USA ",null,"; 7/6/23: CD:06/06/2023->12/12/2023",null,99,50,null,null,"Wed 29/03/23","Wed 07/06/23"]
[1593,991240,"   Perf. part: Introduction of 600MHz US LTE band with 1.4 and 3MHz channel bandwidths ","LTE600_US_lowCBW-Perf",2,"Rel-18","R4","Mon 29/05/23","Tue 12/12/23",0,"RP-230745",null,"T-Mobile USA ",null,"; 7/6/23: CD:09/09/2023->12/12/2023",null,99,50,null,null,"Wed 29/03/23","Wed 07/06/23"]
[1594,0,"Rel-18 RAN Studies","-",1,"Rel-18",null,"Fri 15/12/17","Fri 15/12/17",0.34,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1595,991031,"Study on enhancement for sub-1GHz NR band combinations ","FS_NR_sub1GHz_combo_enh",1,"Rel-18","R4","Fri 03/03/23","Fri 08/09/23",1,"RP-231141","RP-232661","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 7/6/23: Compl:0%->86%; 7/6/23: CD:06/06/2023->09/09/2023; 6/9/23: FCD:09/09/2023->12/12/2023; Compl:86%->80%; WID: RP-230789->RP-231141; Stat Rep: ->RP-232378; Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ; 21/9/23: FC",null,99,50,null,null,"Wed 29/03/23","Thu 21/09/23"]
[1596,991030,"Study on self-evaluation towards the IMT-2020 submission of the 3GPP Satellite Radio Interface Technology ","FS_IMT2020_SAT_eval",1,"Rel-18","RP","Fri 03/03/23","Tue 12/12/23",1,"RP-231945","RP-231944","Asbj rn Gr vlen, Ericsson","asbjorn.grovlen@ericsson.com","29/6/23: 0%->20; 21/9/23: Compl:20%->40%; WID: RP-230736->RP-231945; Stat Rep: RP-231291->RP-231944; Rapporteur: Asbjörn Grövlen, Ericsson->Asbj rn Gr vlen, Ericsson; ; 21/9/23: 37.911 added;; 2/1/24: 40%->100",37.911000000000001,99,50,null,null,"Wed 29/03/23","Tue 02/01/24"]
[1597,970078,"Study on Ambient IoT (Internet of Things) in RAN ","FS_Ambient_IoT_RAN",1,"Rel-18","RP","Thu 08/09/22","Fri 08/09/23",1,"RP-232404","RP-232403","Matthew Webb, Huawei","matthew.webb@huawei.com","9/1/23: WID:RP-222685->RP-223396; 17/3/23: 38.848 added;; 31/3/23: Compl:0%->50%; WID: RP-223396->RP-222685; Stat Rep: ->RP-230669; Rapporteur: Huawei->Matthew Webb, Huawei; Rap eMail: ->matthew.webb@huawei.com; ; 29/6/23: 50%->60; 29/6/23: FCD:06/06/...",38.847999999999999,97,49,null,null,"Fri 23/09/22","Fri 06/10/23"]
[1598,950067,"Study on simplification of band combination specification for NR and LTE ","FS_SimBC",1,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-231468","RP-233234","Zhifeng Ma, ZTE Corporation","ma.zhifeng@zte.com.cn","TR 37.8xx; LTE only combos will not be considered ; 20/6/22: FCD:15/06/2023->23/06/2022; Stat Rep: ->RP-221266 / 1769; Rapporteur: ZTE->Zhifeng Ma, ZTE Corporation; Rap eMail: ->ma.zhifeng@zte.com.cn12/7/22: WID:RP-220956->RP-221790; 13/7/22: FCD:...;...",38.845999999999997,95,48,null,null,"Tue 05/04/22","Fri 08/12/23"]
[1599,950068,"Study on NR frequency range 2 (FR2) Over-the-Air (OTA) testing enhancements ","FS_NR_FR2_OTA_enh",1,"Rel-18","R4","Tue 15/03/22","Tue 12/12/23",1,"RP-233171","RP-233170","Bin Han, Qualcomm Incorporated","binhan@qti.qualcomm.com","compare REL-16 SI FS_NR_test_methods and REL-17 SI FS_FR2_enhTestMethods; TR 38.3xx ; 6/6/22: CD:15/12/2023->23/12/2022; 6/6/22: Stat Rep: ->RP-221391; 20/6/22: Rapporteur: Qualcomm->Bin Han, Qualcomm Incorporated; Rap eMail: ->binhan@qti.qualcomm.com...",38.871000000000002,95,48,null,null,"Tue 05/04/22","Tue 02/01/24"]
[1600,950069,"Study on NR base station (BS) RF requirement evolution ","FS_NR_BS_RF_evo",1,"Rel-18","R4","Tue 15/03/22","Tue 06/06/23",1,"RP-222501","RP-230469","Liehai Liu, Huawei","liuliehai@huawei.com","for NR FR2 mmWave BSs; TR 38.8xx 6/6/22: CD:15/06/2023->23/06/20226/6/22: Stat Rep: ->RP-221530; 20/6/22: Rapporteur: Huawei->Richard Kybett, Huawei; Rap eMail: ->Richard.kybett@huawei.com13/7/22: FCD:23/06/2022->06/20; 13/7/22: 38.877 added;;...; 23/...",38.877000000000002,95,48,null,null,"Tue 05/04/22","Wed 07/06/23"]
[1601,950070,"Study on enhancement for 700/800/900MHz band combinations for NR ","FS_NR_700800900_combo_enh",1,"Rel-18","R4","Thu 03/03/22","Fri 03/03/23",1,"RP-222554","RP-230388","Huiping Shan, CATT","shanhuiping@catt.cn","TR 38.8xx ; 6/6/22: CD:08/06/2021->23/03/2023; 6/6/22: Stat Rep: ->RP-221460; 20/6/22: Rapporteur: CATT->Yuexia Song, CATT; Rap eMail: ->songyuexia@catt.cn12/7/22: WID:RP-221016->RP-221464; 13/7/22: 38.872 added ; ;...; 23/9/22: WID:RP-221464->RP-2225...",38.872,95,48,null,null,"Tue 05/04/22","Fri 17/03/23"]
[1602,850071,"Study on enhanced test methods for FR2 NR UEs","FS_FR2_enhTestMethods",1,"Rel-18","R4","Thu 19/09/19","Wed 22/06/22",1,"RP-221574","RP-221575","Anatoliy IOFFE, Ruixin WANG, Aida Vera LOPEZ, Apple Inc., vivo, Intel Corporation","aioffe@apple.com, ruixin.wang@vivo.com, aida.l.vera.lopez@intel.com","TR 38.8XX; 14/1/20: WID:RP-192322->RP-192430; 28/7/20: WID:RP-192430->RP-201110; 25/9/20: WID:RP-201110->RP-201862; 7/4/21: WID:RP-201862->RP-210633; 2/7/21: WID:RP-210633->RP-211600; ; 04/22: Rel-17->Rel-18 ; ; 20/6/22: Rapporteur: Apple->Anatoliy ...",null,85,43,null,null,"Tue 08/10/19","Tue 12/07/22"]
[1603,890040,"Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths ","FS_NR_eff_BW_util",1,"Rel-18","R4","Thu 17/09/20","Fri 03/03/23",1,"RP-222618","RP-230579","Esther Sienkiewicz, Ericsson","esther dot sienkiewicz at ericsson dot com","TR 38.8xx ; 6/1/21: WID:RP-202103->RP-202339; 7/4/21: WID:RP-202339->RP-210706; 2/7/21: WID:RP-210706->RP-211468; 13/9/21: Compl:0%->50%; ; 6/1/22: WID:RP‑211468->RP-213657 ; 5/4/22: WID:RP-213657->RP-220461; 04/22: Rel-17->Rel-18; ; 20/6/22: Rappor...",38.844000000000001,89,45,null,null,"Fri 25/09/20","Fri 17/03/23"]
[1604,0,"Rel-18 Network automation","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1605,990118,"Enablers for Network Automation for 5G phase 3 ","eNA_Ph3",1,"Rel-18",null,"Mon 20/12/21","Sun 03/03/24",1,"SP-221345",null,"Aihua Li, China Mobile ","liaihua@chinamobile ","10/12/22: 0%->25","23.501; 23.502; 23.503; 23.288 ",99,50,null,null,"Fri 09/12/22","Sat 10/12/22"]
[1606,940073,"   Study on Enablers for Network Automation for 5G - phase 3 ","FS_eNA_Ph3",2,"Rel-18","S2","Mon 20/12/21","Mon 12/12/22",1,"SP-220678",null,"Aihua Li, China Mobile ","liaihua@chinamobile.com ","21/1/22: 23.700-81 added;; 21/1/22: 23.700-85 added;; 12/3/22: 0%->13; 4/6/22: 13%->50; 21/6/22: WID:SP-211650->SP-220678; 12/9/22: 50%->75; 12/9/22: FCD:12/09/2022->12/22; 10/12/22: 75%->100","23.700-81; 23.700-85",94,48,null,null,"Sun 19/12/21","Sat 10/12/22"]
[1607,950021,"   Study on security aspects of enablers for Network Automation for 5G - phase 3 ","FS_eNA_SEC_Ph3",2,"Rel-18","S3","Thu 10/03/22","Fri 03/03/23",1,"SP-220199",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","4/6/22: 0%->10; 13/7/22: 33.738 added;; 12/9/22: 10%->35; 11/12/22: 35%->60; 17/3/23: 60%->80; 8/6/23: 80%->95; 15/3/24: 95%->100",33.738,95,48,null,null,"Thu 10/03/22","Fri 15/03/24"]
[1608,990042,"   Security aspects of enablers for Network Automation for 5G - phase 3 ","eNA_Ph3_SEC",2,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230155",null,"Chang Liu, China Mobile ","liuchangyjy@chinamobile.com ","; 8/6/23: 0%->65; 15/3/24: 65%->100",33.500999999999998,99,50,null,null,"Thu 16/03/23","Fri 15/03/24"]
[1609,980020,"   (stage 2 of eNA_Ph3) Enablers for Network Automation for 5G phase 3 ","eNA_Ph3",2,"Rel-18","S2","Fri 09/12/22","Tue 06/06/23",1,"SP-230110",null,"Aihua Li, China Mobile ","liaihua@chinamobile ","10/12/22: 0%->25; 15/3/23: 13%->65; 15/3/23: WID:SP-221345->SP-230110; 8/6/23: 65%->100","23.501; 23.502; 23.503; 23.288 ",98,50,null,null,"Fri 09/12/22","Thu 08/06/23"]
[1610,990010,"   CT3 aspects of eNA_Ph3","eNA_Ph3",2,"Rel-18","C3","Mon 13/03/23","Sun 03/03/24",1,"CP-240079",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:15%->65%","29.507.29.508.29.122.29.513.29.517.29.519.29.520.29.522.29.523.29.525.29.551.29.552.29.574.29.575.29.576.29.591.29.503.29.504.29.505.29.510.29.515.29.518.29.564.29.571",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1611,990104,"   CT4 aspects of eNA_Ph3","eNA_Ph3",2,"Rel-18","C4","Mon 13/03/23","Sun 03/03/24",1,"CP-240079",null,"Zhennning Huang, China Mobile","huangzhenning@chinamobile.com","; 6/6/23: Compl:5%->30%","29.507.29.508.29.122.29.513.29.517.29.519.29.520.29.522.29.523.29.525.29.551.29.552.29.574.29.575.29.576.29.591.29.503.29.504.29.505.29.510.29.515.29.518.29.564.29.571",99,50,null,null,"Fri 09/12/22","Tue 06/06/23"]
[1612,980039,"Enhancement of Network Automation Enablers","eNetAE",1,"Rel-18","C3","Thu 15/12/22","Sun 03/03/24",1,"CP-231191",null,"Xuefei Zhang, Huawei","summer.xuefei@huawei.com","; 6/6/23: Compl:70%->90%; 6/6/23: CD:12/12/2023->03/03/2024; ;...","29.517; 29.520; 29.522; 29.552; 29.574; 29.575; 29.576; 29.591",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1613,0,"Rel-18 other Studies","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1614,860010,"Guidelines for Extra-territorial 5G Systems ","FS_5GET",1,"Rel-18","S1","Fri 06/12/19","Fri 10/12/21",1,"SP-191042",null,"Cyril MICHEL,Thales ","cyril.michel@thalesaleniaspace.com ","12/9/20: 0%->20; 5/12/20: 20%->40; 19/3/21: FCD:11/09/2020->12/21; 19/3/21: 40%->50; 11/6/21: 50%->60; 13/9/21: 60%->80; 10/12/21: 80%->100",null,86,44,null,null,"Fri 06/12/19","Fri 10/12/21"]
[1615,960002,"Study on NRF API enhancements to avoid signalling and storing of redundant data","FS_NRFe",1,"Rel-18","C4","Thu 02/06/22","Sat 09/09/23",1,"CP-231022",null,"Wiehe, Ulrich, Nokia","Ulrich.wiehe@nokia.com","13/7/22: 29.831 added;; 6/6/23: Compl:50%->60%; 30/6/23: WID:CP-221088->CP-231022","29.xxx; 29.831",96,49,null,null,"Mon 20/06/22","Fri 30/06/23"]
[1616,0,"Rel-18 Management-only Features","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1617,1000007,"Management of cloud-native Virtualized Network Functions ","MCVNF",1,"Rel-18","S5","Fri 30/06/23","Sun 03/03/24",1,"SP-230764",null,"China Mobile Guangjing Cao ","caoguangjing@chinamobile.com ","; 7/9/23: 0%->30; 8/12/23: 30%->95; 14/3/24: 95%->100","28.531; 28.533; 28.526 ",100,51,null,null,"Fri 30/06/23","Thu 14/03/24"]
[1618,1000011,"Charging enhancement for Network Slice based wholesale in roaming ","CHNSWO",1,"Rel-18","S5","Mon 01/05/23","Tue 06/06/23",1,"SP-230625",null,"Maryse Gardella, MATRIXX Software, ","Maryse dot Gardella at Matrixx dot com ","; 8/12/23: 0%->100","32.240; 32.255; 32.256; 32.291; 32.298 ",100,51,null,null,"Thu 08/06/23","Fri 08/12/23"]
[1619,1000014,"Network and Service Operations for Energy Utilities ","NSOEU",1,"Rel-18","S5","Thu 08/06/23","Sun 03/03/24",1,"SP-230632",null,"Erik Guttman , Samsung; ","<erik.guttman@samsung.com ","; 30/6/23: 28.318 added;; 7/9/23: 0%->30; 8/12/23: 30%->60; 4/1/24: 28.879 added;; 14/3/24: 60%->100","28.552; 28.554; 28.622 ; 28.318; 28.879",100,51,null,null,"Thu 08/06/23","Thu 14/03/24"]
[1620,980026,"Study on CHF Segmentation ","FS_CHFSeg",1,"Rel-18","S5","Mon 12/12/22","Sun 03/03/24",1,"SP-221160",null,"João Rodrigues, Nokia ","joao.a.rodrigues@nokia.com ","17/3/23: 0%->5; 17/3/23: 28.840 added;; 8/6/23: 5%->12; 7/9/23: 12%->18; 8/12/23: 18%->55; 8/12/23: FCD:09/09/2023->/2024; 14/3/24: 55%->100",28.84,98,50,null,null,"Fri 09/12/22","Thu 14/03/24"]
[1621,980029,"Management of Trace/MDT phase 2 ","5GMDT_Ph2",1,"Rel-18","S5","Mon 12/12/22","Sun 03/03/24",1,"SP-230777",null,"Swaminathan, Sivaramakrishnan, Nokia ","sivaramakrishnan<dot>swaminathan<at>nokia<dot>com ","; 8/6/23: 0%->; 30/6/23: WID:SP-221163->SP-230777; 7/9/23: 0%->40; 7/9/23: FCD:12/12/2023->/24; 8/12/23: 40%->90; 14/3/24: 90%->100","28.621; 28.622; 28.623; 32.421; 32.422; 32.423 ",98,50,null,null,"Fri 09/12/22","Thu 14/03/24"]
[1622,940037,"Enhancements of EE for 5G Phase 2 ","EE5GPLUS_Ph2",1,"Rel-18","S5","Fri 10/12/21","Tue 12/12/23",1,"SP-211441",null,"Cornily Jean-Michel, Huawei","jean.michel.cornily@huawei.com","; 12/9/22: 0%->10; 12/9/22: FCD:10/03/2023->06/23; 11/12/22: 10%->25; 17/3/23: 25%->30; 17/3/23: FCD:06/06/2023->12/23; 8/6/23: 30%->35; 7/9/23: 35%->55; 8/12/23: 55%->100","28.310; 28.552; 28.554; 28.541 ",94,48,null,null,"Fri 10/12/21","Fri 08/12/23"]
[1623,940014,"Security Assurance Specification for Management Function (MnF) ","SCAS_5G_MF",1,"Rel-18","S3","Fri 10/12/21","Fri 09/12/22",1,"SP-211362",null,"Noamen Ben Henda, Huawei Technologies Co., Ltd. ","noamen.ben.henda@huawei.com ","; 7/1/22: 33.526 added;; 12/3/22: 0%->10; 4/6/22: 10%->30; 12/9/22: 30%->60; 11/12/22: 60%->75; 17/3/23: 75%->85; 8/6/23: 85%->95; 7/9/23: 95%->100","33.926 ; 33.526",94,48,null,null,"Fri 10/12/21","Thu 07/09/23"]
[1624,960023,"Multimedia Messaging Service Charging using service-based interface","MMS_CH_SBI",1,"Rel-18","S5","Thu 02/06/22","Mon 12/12/22",1,"SP-220689",null,"Törnkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericson(dot)com ","; 17/8/22: WID:SP-220486->SP-220689; 12/9/22: 0%->25; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 25%->100","32.240; 32.270; 32.290; 32.291; 32.298 ",96,49,null,null,"Thu 02/06/22","Sun 11/12/22"]
[1625,960025,"5G performance measurements and KPIs phase 3","PM_KPI_5G_Ph3",1,"Rel-18","S5","Thu 02/06/22","Sun 03/03/24",1,"SP-240271",null,"Chen, Xiumin, China Telecom ","(chenxiumin<at>chinatelecom<dot>cn) ","; 17/8/22: WID:SP-220489->SP-220690; 12/9/22: 0%->15; 11/12/22: 15%->50; 17/3/23: 50%->60; 8/6/23: 60%->70; 8/6/23: 70%->; 7/9/23: 70%->80; 8/12/23: 80%->99; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-220690->SP-231710; 4/1/24: 28.558 added;; 14/3...","28.552; 32.425; 28.554; 28.550 ; 28.558",96,49,null,null,"Thu 02/06/22","Tue 02/04/24"]
[1626,870027,"Enhancement of QoE Measurement Collection ","eQoE",1,"Rel-18","S5","Wed 25/03/20","Tue 12/12/23",1,"SP-200193",null,"Bagher Zadeh, Ericsson ","Bagher Zadeh <at>ericsson<dot>ericsson ","; 5/12/20: 0%->5; 21/3/21: 5%->15; 11/6/21: 15%->20; 13/9/21: 20%->40; 13/9/21: FCD:Thu 16/09/->03/22; 13/12/21: 40%->60; 12/3/22: 60%->90; 4/6/22: 90%->95; 4/6/22: FCD:11/03/2022->12/22; Rel-17->Rel-18; 12/9/22: 95%->70; 12/9/22: FCD:12/12/2022->12/2...","28.307; 28.308; 28.309; 28.404; 28.405; 28.406; 28.622; 28.623; 28.533 ",87,44,null,null,"Fri 06/12/19","Thu 08/06/23"]
[1627,950036,"Enhanced Edge Computing Management ","eECM",1,"Rel-18","S5","Thu 10/03/22","Sun 03/03/24",1,"SP-230775",null,"Deepanshu Gautam, Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 4/6/22: 0%->10; 12/9/22: 10%->35; 11/12/22: 35%->50; 17/3/23: 50%->50; 17/3/23: FCD:03/03/2023->12/23; 17/3/23: FCD:12/12/2023->/23; 17/3/23: 50%->100; 30/6/23: WID:SP-220154->SP-230775; 8/12/23: 100%->70; 8/12/23: FCD:03/03/2023->/2024; 14/3/24: 70%->","28.541; 28.538; 28.552; 28.554; 28.531; 28.532 ",95,48,null,null,"Thu 10/03/22","Thu 14/03/24"]
[1628,890016,"Study on access control for management service ","FS_MNSAC",1,"Rel-17","S5","Wed 16/09/20","Wed 08/09/21",1,"SP-200853",null,"Jing Ping, Nokia ","jing.ping@nokia-sbell.com ","25/9/20: WID:SP-200764->SP-200853; 5/12/20: 0%->5; 21/3/21: 5%->35; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 35%->80; 11/6/21: FCD:Wed 08/09/->09/21; 13/9/21: 80%->100",null,89,45,null,null,"Fri 11/09/20","Mon 13/09/21"]
[1629,930010,"Access control for management service ","MSAC",1,"Rel-18","S5","Fri 10/09/21","Sun 03/03/24",1,"SP-231711",null,"Clifton Fernandes, Nokia ","Clifton.fernandes@nokia.com ","; 12/3/22: 0%->60; 4/6/22: 60%->67; 4/6/22: FCD:10/12/2021->12/22; Rel-17->Rel-18; 11/12/22: 67%->68; 11/12/22: FCD:12/12/2022->12/23; 17/3/23: 68%->69; 8/6/23: 69%->72; 7/9/23: 72%->73; 8/12/23: 73%->75; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP...",28.318999999999999,93,47,null,null,"Fri 10/09/21","Thu 14/03/24"]
[1630,940033,"Network slice provisioning enhancement ","eNETSLICE_PRO",1,"Rel-18","S5","Fri 10/09/21","Tue 12/12/23",1,"SP-211434",null,"Deepanshu Gautam , Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 12/3/22: 0%->50; 4/6/22: 50%->85; 4/6/22: FCD:11/03/2022->09/22; Rel=-17->Rel-18; 12/9/22: 85%->85; 12/9/22: FCD:12/09/2022->12/12/22; 11/12/22: 85%->90; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 90%->90; 17/3/23: FCD:03/03/2023->12/23; 7/9/23: 90%->100","28.531; 28.541 ",94,48,null,null,"Fri 10/12/21","Thu 07/09/23"]
[1631,890017,"Study on YANG PUSH ","FS_YANG",1,"Rel-18","S5","Wed 16/09/20","Thu 10/03/22",1,"SP-200765",null,"Lengyel, Balazs, Ericsson ","balazs.lengyel@ericsson.com ","5/12/20: 0%->5; 21/3/21: 5%->10; 21/3/21: FCD:12/03/2021->09/21; 11/6/21: 10%->10; 13/9/21: FCD:Wed 08/09/->12/21; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 8/12/23: 10%->100",null,89,45,null,null,"Thu 10/09/20","Fri 08/12/23"]
[1632,910028,"Study on Continuous integration continuous delivery support for 3GPP NFs. ","FS_CICDNS",1,"Rel-18","S5","Thu 18/03/21","Fri 11/03/22",1,"SP-211427",null,"Vaishnavi, Ishan, Lenovo ","ivaishnavi@lenovo.com ","; 11/6/21: 0%->15; 13/9/21: 15%->30; 13/9/21: FCD:Fri 10/09/->12/21; 13/12/21: 30%->75; 13/12/21: FCD:Fri 10/12/->03/22; 7/1/22: 28.901 added;12/3/22: Rel-17->Rel-18; 4/6/22: 75%->100","New ; 28.901",91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1633,910031,"Study on Enhancement of service-based management architecture ","FS_eSBMA",1,"Rel-18","S5","Thu 18/03/21","Tue 06/06/23",1,"SP-210136",null,"Lan Zou, Huawei ","zoulan@huawei.com ","; 11/6/21: 0%->10; 13/9/21: 10%->15; 13/12/21: 15%->45; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: Rel-17->Rel-18; 4/6/22: 45%->60; 12/9/22: 60%->75; 12/9/22: FCD:11/03/2022->03/23; 11/12/22: 75%->80; 17/3/23: 80%->85; 17/3/23: FCD:03/03/2023->/23; 8/6/23","New ",91,46,null,null,"Thu 18/03/21","Thu 08/06/23"]
[1634,990026,"Service based management architecture ","eSBMA",1,"Rel-18","S5","Thu 16/03/23","Sun 03/03/24",1,"SP-231443",null,"Zhang Kai, Huawei ","kai.zhangkai@huawei.com","; 31/3/23: 28.111 added;; 30/6/23: WID:SP-230174->SP-230776; 7/9/23: 0%->10; 21/9/23: 32.161 added;; 8/12/23: 10%->55; 8/12/23: FCD:12/12/2023->/2024; 3/1/24: WID:SP-230776->SP-231443; 4/1/24: 28.871 added;; 14/3/24: 55%->100","32.404; 28.622; 28.623; 32.300; 28.532; 28.545; 28.532; 28.532; 28.532; 28.158; 28.532 ; 28.111; 32.161; 28.871",99,50,null,null,"Thu 16/03/23","Thu 14/03/24"]
[1635,940034,"Study on Enhancement of the management aspects related to NWDAF ","FS_MANWDAF",1,"Rel-18","S5","Mon 13/12/21","Tue 06/06/23",1,"SP-211435",null,"ZHAO, Song, China Telecom ","zhaosong1@chinatelecom.cn ","7/1/22: 28.864 added;; 4/6/22: 0%->30; 12/9/22: 30%->65; 11/12/22: 65%->75; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 75%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 75%->100",28.864000000000001,94,48,null,null,"Mon 13/12/21","Thu 08/06/23"]
[1636,990031,"Management Aspects related to NWDAF ","MANWDAF",1,"Rel-18","S5","Thu 16/03/23","Tue 12/12/23",1,"SP-230181",null,"Niu, Yuxia, China Telecom ","niuyx@chinatelecom.cn ","; 8/6/23: 0%->50; 7/9/23: 50%->75; 8/12/23: 75%->100; 4/1/24: 28.877 added;","28.541; 28.552; 28.554 ; 28.877",99,50,null,null,"Thu 16/03/23","Thu 04/01/24"]
[1637,940035,"Study on enhancement of management of non-public networks ","FS_OAM_eNPN",1,"Rel-18","S5","Mon 13/12/21","Fri 03/03/23",1,"SP-230185",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","7/1/22: 28.907 added;; 4/6/22: 0%->40; 12/9/22: 40%->80; 11/12/22: 80%->90; 11/12/22: FCD:12/12/2022->/23; 16/3/23: WID:SP-211436->SP-230185; 17/3/23: 90%->100",28.907,94,48,null,null,"Mon 13/12/21","Fri 17/03/23"]
[1638,940036,"Study on new aspects of EE for 5G networks Phase 2 ","FS_EE5G_Ph2",1,"Rel-18","S5","Mon 13/12/21","Tue 06/06/23",1,"SP-211440",null,"Cornily Jean-Michel, Orange ","jean.michel.cornily@huawei.com","7/1/22: 28.913 added;; 4/6/22: 0%->10; 12/9/22: 10%->25; 11/12/22: 25%->50; 17/3/23: 50%->50; 8/6/23: 50%->100",28.913,94,48,null,null,"Mon 13/12/21","Thu 08/06/23"]
[1639,940038,"Study on Deterministic Communication Service Assurance ","FS_DCSA",1,"Rel-18","S5","Mon 13/12/21","Sun 03/03/24",1,"SP-240269",null,"<Zhang>, <Jian>, <Huawei> ","justincn.zhang@huawei.com ","7/1/22: 28.865 added;; 4/6/22: 0%->30; 12/9/22: 30%->32; 12/9/22: FCD:12/12/2023->12/22; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 32%->45; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 45%->60; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 60%->; 8/12/23: 60%->92; 14/3/...",28.864999999999998,94,48,null,null,"Mon 13/12/21","Tue 02/04/24"]
[1640,940041,"Study on evaluation of autonomous network levels ","FS_ANLEVA",1,"Rel-18","S5","Mon 13/12/21","Sun 03/03/24",1,"SP-211445",null,"Cao Xi, China Mobile ","caoxi@chinamobile.com ","7/1/22: 28.909 added;; 4/6/22: 0%->10; 11/12/22: 10%->10; 8/6/23: 10%->60; 8/6/23: FCD:10/03/2023->12/24; 7/9/23: 60%->70; 7/9/23: FCD:12/12/2024->/24; 8/12/23: 70%->80; 14/3/24: 80%->100",28.908999999999999,94,48,null,null,"Mon 13/12/21","Thu 14/03/24"]
[1641,940042,"Study on enhancement of autonomous network levels ","FS_eANL",1,"Rel-18","S5","Mon 13/12/21","Tue 12/12/23",1,"SP-211446",null,"Cao Xi, China Mobile ","caoxi@chinamobile.com ","7/1/22: 28.910 added;; 4/6/22: 0%->25; 12/9/22: 25%->30; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 30%->30; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 30%->75; 8/6/23: FCD:03/03/2023->12/23; 7/9/23: 75%->85; 8/12/23: 85%->100",28.91,94,48,null,null,"Mon 13/12/21","Fri 08/12/23"]
[1642,940046,"Study on enhanced intent driven management services for mobile networks ","FS_eIDMS_MN",1,"Rel-18","S5","Mon 13/12/21","Tue 06/06/23",1,"SP-211450",null,"Xu Ruiyue, Huawei ","Xuruiyue@huawei.com ","7/1/22: 28.912 added;; 4/6/22: 0%->40; 12/9/22: 40%->80; 12/9/22: FCD:12/09/2022->12/22; 11/12/22: 80%->90; 11/12/22: FCD:12/12/2022->/23; 8/6/23: 90%->; 8/6/23: FCD:03/03/2023->/23; 8/6/23: 90%->100",28.911999999999999,94,48,null,null,"Mon 13/12/21","Thu 08/06/23"]
[1643,950027,"Study on Basic SBMA enabler enhancements ","FS_eSBMAe",1,"Rel-18","S5","Thu 10/03/22","Tue 06/06/23",1,"SP-230774",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","5/4/22: 28.831 added;; 4/6/22: 0%->10; 12/9/22: 10%->25; 11/12/22: 25%->35; 11/12/22: FCD:12/12/2022->/23; 17/3/23: 35%->70; 8/6/23: 70%->100; 30/6/23: WID:SP-220145->SP-230774",28.831,95,48,null,null,"Thu 10/03/22","Fri 30/06/23"]
[1644,950029,"Study on alignment with ETSI MEC for Edge computing management ","FS_MEC_ECM",1,"Rel-18","S5","Thu 10/03/22","Tue 06/06/23",1,"SP-220147",null,"Shitao Li, Huawei ","lishitao<at>huawei<dot>com ","5/4/22: 28.903 added;; 4/6/22: 0%->15; 12/9/22: 15%->50; 12/9/22: FCD:12/09/2022->03/23; 17/3/23: 50%->70; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 70%->100",28.902999999999999,95,48,null,null,"Thu 10/03/22","Thu 08/06/23"]
[1645,950030,"Study on Management Aspect of 5GLAN ","FS_5GLAN_Mgt",1,"Rel-18","S5","Thu 10/03/22","Fri 03/03/23",1,"SP-220324",null,"Xiaowen Sun, CMCC ","sunxiaowen@chinamobile.com ","5/4/22: 28.833 added;; 4/6/22: 0%->25; 12/9/22: 25%->65; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 65%->98; 17/3/23: 98%->100; 8/6/23: 100%->",28.832999999999998,95,48,null,null,"Thu 10/03/22","Thu 08/06/23"]
[1646,990027,"Management Aspect of 5GLAN ","5GLAN_Mgt",1,"Rel-18","S5","Thu 16/03/23","Tue 12/12/23",1,"SP-230175",null,"Yushuang Hu, CMCC, ","huyushuang@chinamobile.com ","; 8/6/23: 0%->45; 7/9/23: 45%->90; 8/12/23: 90%->100","28.541; 28.552; 28.554 ",99,50,null,null,"Thu 16/03/23","Fri 08/12/23"]
[1647,950032,"Study on Management of Cloud Native Virtualized Network Functions ","FS_MCVNF",1,"Rel-18","S5","Thu 10/03/22","Tue 06/06/23",1,"SP-220150",null,"China Mobile Guangjing Cao ","caoguangjing@chinamobile.com ","5/4/22: 28.834 added;; 4/6/22: 0%->5; 12/9/22: 5%->30; 11/12/22: 30%->70; 17/3/23: 70%->95; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 95%->100; 4/1/24: 28.869 added;","28.834; 28.869",95,48,null,null,"Thu 10/03/22","Thu 04/01/24"]
[1648,950033,"Study on Management Aspects of 5G MOCN Network Sharing Phase2 ","FS_MANS_ph2",1,"Rel-18","S5","Thu 10/03/22","Tue 06/06/23",1,"SP-220151",null,"Zhaoning Wang, ChinaUnicom ","wangzn18@chinaunicom.cn ","5/4/22: 28.835 added;; 4/6/22: 0%->30; 12/9/22: 30%->75; 12/9/22: FCD:12/09/2022->03/23; 11/12/22: 75%->90; 17/3/23: 90%->94; 17/3/23: FCD:03/03/2023->/23; 8/6/23: 94%->100; 4/1/24: 28.878 added;","28.835; 28.878",95,48,null,null,"Thu 10/03/22","Thu 04/01/24"]
[1649,1000012,"Management Aspects of 5G Network Sharing Phase2 ","MANS_ph2",1,"Rel-18","S5","Thu 08/06/23","Sun 03/03/24",1,"SP-230629",null,"Wang Zhaoning, China Unicom, ","wangzn18@chinaunicom.cn, ","; 7/9/23: 0%->30; 8/12/23: 30%->60; 14/3/24: 60%->100","32.130; 28.541; 28.552 ",100,51,null,null,"Thu 08/06/23","Thu 14/03/24"]
[1650,950034,"Study on Management of Trace/MDT phase 2 ","FS_5GMDT_Ph2",1,"Rel-18","S5","Thu 10/03/22","Tue 06/06/23",1,"SP-230773",null,"Sivaramaskrishnan Swaminathan, Nokia ","sivaramakrishnan.swaminathan@nokia.com","5/4/22: 28.837 added;; 4/6/22: 0%->15; 12/9/22: 15%->25; 12/9/22: FCD:12/12/2022->03/23; 11/12/22: 25%->35; 11/12/22: FCD:10/03/2023->/23; 17/3/23: 35%->60; 8/6/23: 60%->100; 30/6/23: WID:SP-220152->SP-230773",28.837,95,48,null,null,"Thu 10/03/22","Fri 30/06/23"]
[1651,950035,"Study on Fault Supervision Evolution ","FS_FSEV",1,"Rel-18","S5","Thu 10/03/22","Sun 03/03/24",1,"SP-220153",null,"Deng LingLi (China Mobile)",null,"5/4/22: 28.830 added;; 4/6/22: 0%->10; 12/9/22: 10%->20; 8/6/23: 20%->; 8/6/23: 20%->30; 8/6/23: FCD:03/03/2023->/24; 7/9/23: 30%->40; 8/12/23: 40%->65; 14/3/24: 65%->100",28.83,95,48,null,null,"Thu 10/03/22","Thu 14/03/24"]
[1652,960024,"Study on measurement data collection to support RAN intelligence ","FS_MEDACO_RAN",1,"Rel-18","S5","Thu 02/06/22","Mon 12/12/22",1,"SP-220488",null,"Chou, Joey, Intel ","joey<dot>chou<at>intel<dot>com ","12/9/22: 0%->10; 11/12/22: 10%->100; 8/6/23: 100%->",null,96,49,null,null,"Thu 02/06/22","Thu 08/06/23"]
[1653,920020,"Study on Nchf charging services phase 2","FS_NCHF_Ph2",1,"Rel-18","S5","Fri 11/06/21","Tue 12/12/23",1,"SP-210390",null,"Tornkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","12/3/22: 0%->40; 4/6/22: 40%->60; 4/6/22: FCD:11/03/2022->03/23; 21/6/22: 60%->100. 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->70; 11/12/22: 70%->94; 11/12/22: 94%->75; 17/3/23: 75%->98; 17/3/23: 98%->88; 8/6/23...",null,92,47,null,null,"Fri 11/06/21","Fri 08/12/23"]
[1654,990029,"CHF Distributed Availability ","DIST_CH",1,"Rel-18","S5","Thu 16/03/23","Sat 09/09/23",1,"SP-230179",null,"João Rodrigues, Nokia ","joao.a.rodrigues@nokia.com ","; 8/12/23: 0%->100","32.240; 32.290 ",99,50,null,null,"Thu 16/03/23","Fri 08/12/23"]
[1655,920021,"Study on 5G roaming charging architecture for wholesale and retail scenarios ","FS_CHROAM",1,"Rel-18","S5","Fri 11/06/21","Sat 09/09/23",1,"SP-210391",null,"Tornkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","13/9/21: 0%->10; 12/3/22: 10%->50; 4/6/22: 50%->100; 4/6/22: FCD:11/03/2022->03/23; 4/6/22: 100%->75; 4/6/22: 0%->75; 21/6/22: 75%->100 13/7/22: moved Rel-17->Rel-18, as per Gerald e-mail 21/06/22, 15:03; 12/9/22: 100%->85; 11/12/22: 85%->90; 17/3/23: ...",null,92,47,null,null,"Fri 11/06/21","Thu 07/09/23"]
[1656,1010017,"Charging for roaming and additional actor using CHF to CHF interface ","CHRACHF",1,"Rel-18","S5","Wed 06/09/23","Sun 03/03/24",1,"SP-231153",null,"Törnkvist, Robert, Ericsson AB ","robert(dot)tornkvist(at)Ericsson(dot)com ","; 8/12/23: 0%->40; 14/3/24: 40%->100","32.240; 32.255; 32.256; 32.290; 32.291; 32.298 ",101,51,null,null,"Wed 06/09/23","Thu 14/03/24"]
[1657,970030,"Methodology for deprecation ","OAM_MetDep",1,"Rel-18","S5","Mon 12/09/22","Fri 10/03/23",1,"SP-220843",null,"Lengyel, Balázs, Ericsson ","balazs.lengyel@ericsson.com ","; 11/12/22: 0%->95; 17/3/23: 95%->100","32.156; 32.160 ",97,49,null,null,"Sun 11/09/22","Fri 17/03/23"]
[1658,970029,"Study on Data management phase 2 ","FS_MADCOL_ph2",1,"Rel-18","S5","Mon 12/09/22","Sun 03/03/24",1,"SP-220842",null,"Pollakowski, Olaf, Nokia ","olaf.pollakowski@nokia.com ","; 23/9/22: 28.842 added;; 11/12/22: 0%->5; 11/12/22: FCD:12/06/2023->/23; 17/3/23: 5%->10; 8/6/23: 10%->25; 8/6/23: FCD:06/06/2023->/24; 7/9/23: 25%->45; 8/12/23: 45%->80; 4/1/24: 28.873 added;; 14/3/24: 80%->100","; 28.842; 28.873",97,49,null,null,"Sun 11/09/22","Thu 14/03/24"]
[1659,970032,"Study on Time Sensitive Networking (TSN) Charging ","FS_TSNCH",1,"Rel-18","S5","Mon 12/09/22","Tue 12/12/23",1,"SP-220979",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","23/9/22: 28.839 added;; 11/12/22: 0%->10; 17/3/23: 10%->25; 8/6/23: 25%->70; 8/6/23: FCD:06/06/2023->12/23; 7/9/23: 70%->100",28.838999999999999,97,49,null,null,"Sun 11/09/22","Thu 07/09/23"]
[1660,1010014,"Charging Aspects of TSN ","TSN_CH",1,"Rel-18","S5","Wed 06/09/23","Sun 03/03/24",1,"SP-240268",null,"Deng, Yimeng, Huawei, ","dengyimeng at huawei dot com ","; 21/9/23: 32.282 added;; 8/12/23: 0%->60; 14/3/24: 60%->100; 2/4/24: WID:SP-231151->SP-240268","32.240; 32.254; 32.255; 32.291; 32.298; 32.297 ; 32.282",101,51,null,null,"Wed 06/09/23","Tue 02/04/24"]
[1661,990032,"Charging Aspects for NSSAA ","NSSAA_CH",1,"Rel-18","S5","Thu 16/03/23","Sun 03/03/24",1,"SP-230182",null,"Gerald Görmer, MATRIXX Software ","Gerald dot Goermer at Matrixx dot com ","; 31/3/23: 28.204 added;; 8/6/23: 0%->10; 7/9/23: 10%->40; 8/12/23: 40%->80; 14/3/24: 80%->100","32.240; 32.290; 32.291; 32.298; 32.297 ; 28.204",99,50,null,null,"Thu 16/03/23","Thu 14/03/24"]
[1662,990033,"Management Aspects of NTN ","OAM_NTN",1,"Rel-18","S5","Thu 16/03/23","Tue 12/12/23",1,"SP-230183",null,"Sun Mingrui, China Unicom ","sunmr19@chinaunicom.cn ","; 7/9/23: 0%->30; 8/12/23: 30%->100","28.541; 28.552; 28.554; 28.658 ",99,50,null,null,"Thu 16/03/23","Fri 08/12/23"]
[1663,990034,"Management of non-public networks phase 2 ","OAM_NPN_Ph2",1,"Rel-18","S5","Thu 16/03/23","Sun 03/03/24",1,"SP-230184",null,"ZHANG, Kai, Huawei ","kai.zhangkai@huawei.com ","; 8/6/23: 0%->10; 7/9/23: 10%->40; 8/12/23: 40%->65; 8/12/23: FCD:12/12/2023->/2024; 14/3/24: 65%->100","28.557; 28.541; 28.531; 28.533; 28.552 ",99,50,null,null,"Thu 16/03/23","Thu 14/03/24"]
[1664,0,"Rel-18 service-based aspects","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1665,920022,"Study on Standardising Automated Certificate Management in SBA ","FS_ACM_SBA",1,"Rel-18","S3","Fri 11/06/21","Fri 03/03/23",1,"SP-220325",null,"BT, Niraj Rathod ","Niraj.rathod@bt.com ","Was previously listed under Rel-18 but according to SA#92 report, it is Rel-17; 1/10/21: 33.876 added;; 10/3/22: WID:SP-210419->SP-220195. Rel-17->Rel-18; 12/3/22: 0%->5; 12/3/22: FCD:10/06/2022->9/22; 4/6/22: 5%->35; 12/9/22: 35%->60; 17/3/23: 60%->90...",33.875999999999998,92,47,null,null,"Fri 11/06/21","Thu 08/06/23"]
[1666,990037,"Automated certificate management in SBA ","ACM_SBA",1,"Rel-18","S3","Thu 16/03/23","Sat 09/09/23",1,"SP-230768",null,"Peinado, German, Nokia ","german.peinado@nokia.com ","; 8/6/23: 0%->35; 30/6/23: WID:SP-230150->SP-230768; 7/9/23: 35%->100",33.31,99,50,null,null,"Thu 16/03/23","Thu 07/09/23"]
[1667,980022,"Security Aspects of the 5G Service Based Architecture Phase 2 ","5G_eSBA_Ph2",1,"Rel-18","S3","Fri 09/12/22","Fri 03/03/23",1,"SP-221145",null,"Anja Jerichow, Nokia ","anja.jerichow@nokia.com ","; 8/6/23: 0%->95; 15/3/24: 95%->100",33.500999999999998,98,50,null,null,"Fri 09/12/22","Fri 15/03/24"]
[1668,960052,"Service Based Interface Protocol Improvements Release 18 ","SBIProtoc18",1,"Rel-18",null,"Fri 03/06/22","Tue 12/12/23",1,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,null,"29.507; 29.508; 29.512; 29.514; 29.517; 29.519; 29.520; 29.521; 29.523; 29.525; 29.534; 29.535; 29.537; 29.551; 29.554; 29.557; 29.565; 29.574; 29.575; 29.576; 29.580; 29.591; 29.594; 29.675 ",96,49,null,null,"Fri 03/06/22","NA"]
[1669,960001,"   CT4 aspects of SBIProtoc18","SBIProtoc18",2,"Rel-18","C4","Fri 03/06/22","Tue 12/12/23",1,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,"; 6/6/23: Compl:25%->50%","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.515; 29.518; 29.524; 29.531; 29.532; 29.536; 29.540; 29.541; 29.542; 29.544; 29.550; 29.555; 29.556; 29.559; 29.562; 29.563; 29.564; 29.571; 29.572; 29.573; 29.577; 29.578; 29.579;",96,49,null,null,"Fri 03/06/22","Tue 06/06/23"]
[1670,960060,"   CT3 aspects of SBIProtoc18","SBIProtoc18",2,"Rel-18","C3","Fri 03/06/22","Tue 12/12/23",1,"CP-221083",null,"Wang Rong, China Mobile, wangrongyjy@chinamobile.com ",null,"; 9/6/23: 30%->60","29.507; 29.508; 29.512; 29.514; 29.517; 29.519; 29.520; 29.521; 29.523; 29.525; 29.534; 29.535; 29.537; 29.551; 29.554; 29.557; 29.565; 29.574; 29.575; 29.576; 29.580; 29.591; 29.594; 29.675 ",96,49,null,null,"Fri 03/06/22","Fri 09/06/23"]
[1671,960004,"Study on GBA_U Based APIs ","FS_GBA_U_API",1,"Rel-18","C6","Fri 03/06/22","Fri 03/03/23",1,"CP-221185",null,"Huo Weijing, China Mobile ","huoweijing@chinamobile.com ","13/7/22: 31.822 added","31.121 ; 31.822",96,49,null,null,"Fri 03/06/22","Wed 13/07/22"]
[1672,1000003,"GBA_U Based APIs ","GBA_U_APIs",1,"Rel-18","C6","Wed 07/06/23","Sun 03/03/24",1,"CP-231353",null,"Huo Weijing(China Mobile) ","huoweijing@chinamobile.com ","; 30/6/23: 31.122 added;","31.102; 31.130; 31.116 ; 31.122",100,51,null,null,"Wed 07/06/23","Fri 30/06/23"]
[1673,800045,"Study on IETF QUIC Transport for Service Based Interfaces","FS_QUIC",1,"Rel-18","C4","Tue 12/12/23","Tue 12/12/23",1,"CP-183245",null,"Qi Caixia, Huawei","caixia.qi@huawei.com","6/8/18: 29.893 added;¦10/9/18: 0%->40¦10/12/18: FCD:03/19->06/19¦10/12/18: WID:CP-181194->CP-183245¦14/3/19: 50%->75; 31/5/19: 75%->80. 02/07/20: moved Rel-16->Rel-17; 13/9/20: FCD:12/06/2019->09/21; 13/9/21: FCD:Wed 08/09/->03/22; 12/3/22:rel-17->18","New; 29.893",80,41,null,null,"Wed 06/06/18","Mon 13/09/21"]
[1674,0,"Rel-18 other aspects","-",1,"Rel-18",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1675,920042,"(Small) Technical Enhancements and Improvements for Rel-18","TEI18",1,"Rel-18",null,"Fri 12/03/21","Sun 24/07/22",0,null,null,null,null,null,null,92,47,null,null,"Mon 15/06/15","Mon 15/06/15"]
[1676,920003,"Lawful Interception Rel-18 ","LI18",1,"Rel-18","S3LI","Fri 12/03/21","Fri 02/12/22",0.96,"SP-230241",null,"Koen Jaspers, PIDS","kbj@xs4all.nl","10/9/21: WID:SP-210300->SP-210830; 4/6/22: 0%->5; 12/9/22: 5%->15; 11/12/22: 15%->20; 16/3/23: FCD:03/03/2023->/2023; 16/3/23: WID:SP-210830->SP-230241. Rapporteur changed from Alex Leadbeater; 31/3/23: 33.928 added;; 5/9/24: 20%->90; 5/12/24: 90%->96","33.128;33.127;33.126;33.108;33.107 ; 33.928",92,47,null,null,"Fri 11/06/21","Thu 05/12/24"]
[1677,959999,"Limbo: code to be used for not-approved CRs related to never-approved WIDs ","Limbo",1,"-",null,"Thu 07/03/19","Thu 07/03/19",0,"-","-","-","-","\"Dummy\" is a temporary code for CRs related to not-yet-approved WIDs. If a WID ended up not being approved at pleanry, then all related CRs have to be changed from \"Dummy\" to \"Limbo\"",null,95,48,null,null,"Sun 13/03/22","NA"]
[1678,999999,"Test - (Small) Technical Enhancements and Improvements for Rel-18 ","TEI18_Test",1,"Rel-18","R5","Wed 05/01/22","Thu 16/03/23",1,null,null,null,null,"8/6/23: 0%->100",null,99,50,null,null,"Thu 08/06/23","Thu 08/06/23"]
[1679,1040002,"Update of conformance test specifications to Rel-18","UEConTest_R18",1,"Rel-18","C6","Thu 29/06/23","Fri 06/06/25",0.4,"CP-241022",null,"Arne Marquordt, COMPRION GmbH","amarquordt@comprion.com",null,null,92,47,null,null,"Thu 12/08/21","NA"]
[{"$f":"A1680+1","v":1680},0,"--- RELEASE 17 ---","-",1,"Rel-17",null,"Tue 15/03/16","Tue 15/03/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[{"$f":"A1681+1","v":1681},0,"Rel-17 on Use of 5G by different sectors (\"verticals\")","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1682,840050,"Enhancements for cyber-physical control applications in vertical domains ","eCAV",1,"Rel-17",null,"Thu 07/03/19","Thu 12/12/19",1,"SP-190310",null,"Bahr, Michael, Siemens AG ","bahr et siemens dod com ",null,"22.104; 22.261 ",84,43,null,null,"Fri 31/05/19","NA"]
[1683,830020,"   Study on eCAV","FS_eCAV",2,"Rel-17","S1","Thu 07/03/19","Thu 05/09/19",1,"SP-190092","-","Michael Bahr, Siemens AG","bahr et siemens dod com ","14/3/19: 0%->5; 31/5/19: 5%->60; 13/9/19: 60%->85; 6/12/19: 85%->95; 26/6/20: 95%->100","New",83,42,null,null,"Thu 14/03/19","Fri 26/06/20"]
[1684,840041,"   Stage 1 of eCAV","eCAV",2,"Rel-17","S1","Thu 06/06/19","Thu 12/12/19",1,"SP-191043",null,"Bahr, Michael, Siemens AG ","bahr et siemens dod com ","31/5/19: 0%->10; 13/9/19: 10%->80; 20/9/19: WID:SP-190310->SP-190945; 6/12/19: 80%->95; 12/12/19: WID:SP-190945->SP-191043; 26/6/20: 95%->100","22.104; 22.261 ",84,43,null,null,"Fri 31/05/19","Fri 26/06/20"]
[1685,840024,"Study on enhanced support of Non-Public Networks ","FS_eNPN",1,"Rel-17","S2","Thu 06/06/19","Fri 12/03/21",1,"SP-200094",null,"Peter Hedman ","peter . hedman @ ericsson . com ","8/10/19: 23.700-07 added;; 6/12/19: 0%->15; 25/3/20: WID:SP-190453->SP-200094; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 15%->35; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 35%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/ ","New ; 23.700-07",84,43,null,null,"Fri 31/05/19","Fri 19/03/21"]
[1686,910065,"Enhanced support of Non-Public Networks ","eNPN",1,"Rel-17",null,"Fri 12/06/20","Fri 10/06/22",1,"SP-200980",null,"Hedman, Peter, Ericsson ","peter dot hedman at ericsson dot com ",null,"23.501; 23.502; 23.503; 23.228; 23.167 ",90,46,null,null,"Thu 03/12/20","NA"]
[1687,900015,"   Stage 2 for eNPN","eNPN",2,"Rel-17","S2","Thu 03/12/20","Wed 08/09/21",1,"SP-200980",null,"Hedman, Peter, Ericsson ","peter dot hedman at ericsson dot com ","19/3/21: 0%->20; 14/6/21: 20%->85; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->95; 10/12/21: 95%->97; 12/3/22: 97%->100","23.501; 23.502; 23.503; 23.228; 23.167 ",90,46,null,null,"Thu 03/12/20","Sat 12/03/22"]
[1688,910016,"   CT aspects of eNPN","eNPN",2,"Rel-17","ct","Thu 18/03/21","Fri 11/03/22",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 10/9/21: WID:CP-210139->CP-212103","23.003; 23.122; 24.008; 24.167; 24.229; 24.368; 24.501; 24.526; 27.007; 29.503; 29.505; 29.509; 29.513; 29.522; 29.525; 29.561 ",91,46,null,null,"Thu 18/03/21","Fri 10/09/21"]
[1689,910066,"      CT1 aspects of eNPN","eNPN",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 11/6/21: 0%->20; 13/9/21: 20%->40; 13/12/21: 40%->65; 12/3/22: 65%->93; 4/6/22: 93%->99; 20/6/22: Compl:99%->100%",null,91,46,null,null,"Thu 18/03/21","Mon 20/06/22"]
[1690,910067,"      CT3 aspects of eNPN","eNPN",3,"Rel-17","C3","Thu 18/03/21","Fri 11/03/22",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 13/9/21: 0%->45; 13/12/21: 45%->75; 13/12/21: WID:CP-212103->CP-213072; 12/3/22: 75%->100",null,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1691,910068,"      CT4 aspects of eNPN","eNPN",3,"Rel-17","C4","Thu 18/03/21","Fri 11/03/22",1,"CP-212103",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","; 11/6/21: 0%->30; 13/9/21: 30%->40; 13/12/21: 40%->80; 12/3/22: 80%->98; 4/6/22: 98%->100",null,91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1692,920025,"   Security Aspects of eNPN ","eNPN",2,"Rel-17","S3","Fri 11/06/21","Fri 10/06/22",1,"SP-210422",null,"Jost, Christine, Ericsson ","christine.jost@ericsson.com ","; 13/9/21: 0%->50; 13/12/21: 50%->90; 12/3/22: 90%->95; 12/3/22: FCD:10/12/2021->6/22; 4/6/22: 95%->100",33.500999999999998,92,47,null,null,"Fri 11/06/21","Sat 04/06/22"]
[1693,880008,"   Study on enhanced security support for Non-Public Networks ","FS_eNPN_SEC",2,"Rel-17","S3","Fri 12/06/20","Fri 10/06/22",1,"SP-200353",null,"Normann, Henrik, Ericsson ","henrik.normann@ericsson.com ","28/7/20: 33.857 added;; 12/9/20: 0%->10; 5/12/20: 10%->35; 5/12/20: FCD:11/12/2020->03/20; 19/3/21: 35%->65; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 65%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->90; 12/3/22: 90%->90; 12/3/22: FCD:10/12/2021-> ",33.856999999999999,88,45,null,null,"Thu 25/06/20","Sat 04/06/22"]
[1694,840045,"Audio-Visual Service Production ","AVPROD",1,"Rel-17",null,"Wed 06/06/18","Thu 12/12/19",1,"SP-190304",null,"Wagdin, Ian, BBC ","ian.wagdin@bbc.co.uk ",null,22.260999999999999,84,43,null,null,"Fri 31/05/19","NA"]
[1695,800014,"   Study on AVPROD","FS_AVPROD",2,"Rel-17","S1","Wed 06/06/18","Wed 12/06/19",1,"SP-181015",null,"Roland Beutler, EBU","Roland.Beutler@swr.de","6/8/18: 22.827 added;¦10/9/18: 0%->10¦4/12/18: 10%->50¦14/12/18: WID:SP-180340->SP-181015¦14/12/18: FCD:03/19->06/19¦14/3/19: 50%->80; 31/5/19: 80%->95; 13/9/19: 95%->100",22.827000000000002,80,41,null,null,"Wed 06/06/18","Fri 13/09/19"]
[1696,840031,"   Stage 1 of AVPROD","AVPROD",2,"Rel-17","S1","Thu 06/06/19","Thu 12/12/19",1,"SP-191041",null,"Wagdin, Ian, BBC ","ian.wagdin@bbc.co.uk ","13/9/19: 0%->80; 6/12/19: 80%->100; 12/12/19: WID:SP-190304->SP-191041",22.260999999999999,84,43,null,null,"Fri 31/05/19","Thu 12/12/19"]
[1697,910001,"Study on Media Production over 5G NPN ","FS_NPN4AVProd",1,"Rel-17","S4","Thu 18/03/21","Fri 10/06/22",1,"SP-210241",null,"Lohmar, Thorsten, Ericsson ","Thorsten.Lohmar@ericsson.com ","; 9/4/21: 26.805 added;; 11/6/21: 0%->15; 13/9/21: 15%->30; 13/12/21: 30%->60; 12/3/22: 60%->80; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 80%->100","New 26.805",91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1698,820025,"Study on application layer support for Factories of the Future in 5G network","FS_FFAPP",1,"Rel-17","S6","Thu 07/03/19","Fri 11/06/21",1,"SP-200836",null,"Shao Weixiang, ZTE Corporation","shao.weixiang@zte.com.cn","14/3/19: 0%->5; 31/5/19: 5%->15; 13/9/19: 15%->20; 13/9/19: FCD:12/03/2020->09/20; 20/9/19: WID:SP-181139->SP-190724; 6/12/19: 20%->40; 26/3/20: 40%->50; 25/6/20: WID:SP-190724->; 28/6/20: 50%->60; 13/9/20: 60%->70; 13/9/20: WID:->SP-200836; 13/9/20: F ","new",82,42,null,null,"Thu 06/12/18","Mon 13/09/21"]
[1699,840025,"Stopped - Study on enhancement of support for 5G LAN-type service ","FS_5GLAN_enh",1,"Rel-17","S2","Thu 06/06/19","Thu 12/03/20",1,"SP-190626",null,"Runze Zhou, Huawei ","zhourunze@huawei.com ","20/9/19: WID:SP-190454->SP-190626; 8/10/19: 23.762 added;; 22/3/22: Stopped at 0% (Puneet: deprioritized as part of the Rel-17 prioritization exercise)","New ; 23.762",84,43,96,null,"Fri 31/05/19","Tue 22/03/22"]
[1700,900022,"Study on Charging Aspect of 5G LAN-type Services ","FS_5GLAN_CH",1,"Rel-17","S5","Fri 04/12/20","Fri 10/12/21",1,"SP-201081",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","21/3/21: 0%->10; 2/7/21: 28.822 added;; 13/9/21: 10%->60; 13/9/21: FCD:Fri 11/06/->12/21; 12/3/22: 60%->100",28.821999999999999,90,46,null,null,"Fri 04/12/20","Sat 12/03/22"]
[1701,940029,"Charging Aspects of 5G LAN VN Group ","5GLAN_CH",1,"Rel-17","S5","Fri 10/12/21","Fri 10/06/22",1,"SP-220291",null,"CHEN SHAN, Huawei ","chenshan@huawei.com ","; 12/3/22: 0%->35; 22/3/22: WID:SP-211430->SP-220291; 4/6/22: 35%->100","32.240; 32.255; 32.291; 32.298 ",94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[1702,840042,"Complete Gap Analysis for Railways Mobile Communication System ","MONASTERYEND",1,"Rel-17","S1","Thu 06/06/19","Thu 12/12/19",1,"SP-190312",null,"Gach, Guillaume, UIC ","ext.gach@uic.org ","31/5/19: 0%->20; 13/9/19: 20%->80; 6/12/19: 80%->100","22.280; 22.281; 22.282; 22.179; 22.289 ",84,43,null,null,"Fri 31/05/19","Fri 06/12/19"]
[1703,890035,"Enhancements to Application Architecture for the Mobile Communication System for Railways Phase 2 ","eMONASTERY2",1,"Rel-17",null,"Thu 06/06/19","Fri 11/03/22",1,"SP-191104",null,"Oettl, Martin, Nokia ","martin(dot)oettl(at)nokia(dot)com ","13/9/19: 0%->70; 6/12/19: 70%->50; 6/12/19: FCD:10/12/2019->03/20; 6/12/19: WID:SP-190565->SP-191104; 26/3/20: 50%->60; 26/3/20: FCD:12/03/2020->09/20; 28/6/20: 60%->85","23.280; 23.379; 23.281; 23.282; 23.283 ",84,43,null,null,"Fri 31/05/19","Sun 28/06/20"]
[1704,840037,"   Stage 2 of eMONASTERY2","eMONASTERY2",2,"Rel-17","S6","Thu 06/06/19","Fri 11/09/20",1,"SP-191104",null,"Oettl, Martin, Nokia ","martin(dot)oettl(at)nokia(dot)com ","13/9/19: 0%->70; 6/12/19: 70%->50; 6/12/19: FCD:10/12/2019->03/20; 6/12/19: WID:SP-190565->SP-191104; 26/3/20: 50%->60; 26/3/20: FCD:12/03/2020->09/20; 28/6/20: 60%->85; 13/9/20: 85%->100","23.280; 23.379; 23.281; 23.282; 23.283 ",84,43,null,null,"Fri 31/05/19","Sun 13/09/20"]
[1705,890063,"   Stage 3 of eMONASTERY2 ","eMONASTERY2",2,"Rel-17","C1","Wed 16/09/20","Fri 11/03/22",1,"CP-202256",null,"Gkatzikis, Lazaros, Nokia(Nokia) ","lazaros(dot)gkatzikis(at)nokia(dot)com ","; 5/12/20: 0%->10; 21/3/21: 10%->30; 11/6/21: 30%->50; 13/9/21: 50%->55; 13/9/21: FCD:Wed 08/09/->03/22; 13/12/21: 55%->70; 12/3/22: 70%->80; 4/6/22: 80%->98","24.379 ; 24.282 ; 24.481 ; 24.483 ; 24.484 ; 24.582 ",89,45,null,null,"Fri 25/09/20","Sat 04/06/22"]
[1706,840043,"Study on Future Railway Mobile Communication System3 ","FS_FRMCS3",1,"Rel-17","S1","Thu 06/06/19","Thu 12/12/19",1,"SP-200578",null,"Gach, Guillaume, UIC, ","ext.gach@uic.org ","31/5/19: 0%->40; 13/9/19: 40%->80; 6/12/19: 80%->100; 25/6/20: WID:SP-190321->SP-200578",22.989000000000001,84,43,null,null,"Fri 31/05/19","Thu 25/06/20"]
[1707,850046,"Asset Tracking for 5G ","ATRAC",1,"Rel-17",null,"Thu 06/09/18","Thu 12/12/19",1,"SP-190816",null,"Thierry Berisot, NOVAMINT ","tberisot@novamint.com ",null,22.260999999999999,85,43,null,null,"Fri 13/09/19","NA"]
[1708,810017,"   Study on ATRAC","FS_5G_ATRAC",2,"Rel-17","S1","Thu 06/09/18","Fri 14/06/19",1,"SP-180922",null,"Thierry Berisot, NOVAMINT","tberisot@novamint.com","4/12/18: 0%->15¦14/3/19: 15%->45; 31/5/19: 45%->50; 13/9/19: 50%->100",22.835999999999999,81,41,null,null,"Thu 06/09/18","Fri 13/09/19"]
[1709,850037,"   Stage 1 of ATRAC","ATRAC",2,"Rel-17","S1","Thu 19/09/19","Thu 12/12/19",1,"SP-190931",null,"Thierry Berisot, NOVAMINT ","tberisot@novamint.com ","; 13/9/19: 0%->95; 6/12/19: 95%->100",22.260999999999999,85,43,null,null,"Fri 13/09/19","Fri 06/12/19"]
[1710,910052,"Enhancement to the 5GC LoCation Services-Phase 2 ","5G_eLCS_ph2",1,"Rel-17",null,"Wed 25/03/20","Fri 11/03/22",1,"SP-200082",null,"Ming Ai, CATT ","aiming@catt.cn ","5/12/20: 0%->20; 5/12/20: FCD:17/09/2020->06/20",23.273,87,44,null,null,"Fri 31/05/19","Sat 05/12/20"]
[1711,870001,"   Stage 2 of 5G_eLCS_ph2","5G_eLCS_ph2",2,"Rel-17","S2","Wed 25/03/20","Wed 08/09/21",1,"SP-200082",null,"Ming Ai, CATT ","aiming@catt.cn ","5/12/20: 0%->20; 5/12/20: FCD:17/09/2020->06/20; 19/3/21: 20%->40; 11/6/21: 40%->70; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 70%->95; 10/12/21: 95%->100",23.273,87,44,null,null,"Fri 31/05/19","Fri 10/12/21"]
[1712,910006,"   CT aspects of 5G_eLCS_ph2","5G_eLCS_ph2",2,"Rel-17","ct","Thu 18/03/21","Fri 11/03/22",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","11/6/21: WID:CP-210075->CP-211090",null,91,46,null,null,"Thu 18/03/21","Fri 11/06/21"]
[1713,910053,"      CT1 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","13/12/21: 0%->50; 12/3/22: 50%->98; 20/6/22: Compl:98%->100%","24.501; 24.571; 27.007",91,46,null,null,"Thu 18/03/21","Mon 20/06/22"]
[1714,910054,"      CT3 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C3","Thu 18/03/21","Fri 11/03/22",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","13/9/21: 0%->10; 13/12/21: 10%->60; 12/3/22: 60%->100","29.522; 29.122",91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1715,910055,"      CT4 aspects of 5G_eLCS_ph2","5G_eLCS_ph2",3,"Rel-17","C4","Thu 18/03/21","Fri 11/03/22",1,"CP-211090",null,"Chenxi Bao, CATT ","baochenxi@catt.cn ","11/6/21: 0%->20; 13/9/21: 20%->35; 13/12/21: 35%->75; 12/3/22: 75%->98; 4/6/22: 98%->100; 20/6/22: Compl:99%->100%","29.515; 29.572; 24.080; 29.518; 29.503; 29.571",91,46,null,null,"Thu 18/03/21","Mon 20/06/22"]
[1716,900060,"RAN aspects of NR positioning enhancements ","NR_pos_enh",1,"Rel-17",null,"Thu 07/03/19","Thu 12/12/24",1,"RP-210903",null,"Intel ",null,"follow-up WI of REL-17 SI FS_NR_pos_enh (not yet completed at RAN #90e) ; 7/4/21: WID:RP-202900->RP-210903",null,90,46,null,null,"Wed 06/01/21","Wed 07/04/21"]
[1717,860034,"   Study on NR positioning enhancements","FS_NR_pos_enh",2,"Rel-17","R1","Thu 07/03/19","Wed 03/06/20",1,"RP-202094",null,"CATT",null,"affects: NR. compare REL-16 NR_pos WI; TR 38.8xx; 26/3/20: WID:RP-193237->RP-200218; 28/7/20: WID:RP-200218->RP-200928; 25/9/20: WID:RP-200928->RP-202094; 7/4/21: 0%->100",null,86,44,null,null,"Tue 14/01/20","Wed 07/04/21"]
[1718,900160,"   Core part: NR positioning enhancements ","NR_pos_enh-Core",2,"Rel-17","R1","Mon 14/12/20","Tue 22/03/22",1,"RP-210903","RP-221586","Yi GUO, Intel Corporation","yi.guo@intel.com","follow-up WI of REL-17 SI FS_NR_pos_enh (not yet completed at RAN #90e) ; 20/6/22: FCD:12/03/2022->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-221586; Rapporteur: Intel->Yi GUO, Intel Corporation; Rap eMail: ->yi.guo@intel.com; ",null,90,46,null,null,"Wed 06/01/21","Mon 20/06/22"]
[1719,900260,"   Perf. part: NR positioning enhancements ","NR_pos_enh-Perf",2,"Rel-17","R1","Mon 14/12/20","Thu 22/09/22",1,"RP-210903","RP-221586","Yi GUO, Intel Corporation","yi.guo@intel.com","follow-up WI of REL-17 SI FS_NR_pos_enh ; 20/6/22: WG: R4->R1; FCD:08/09/2022->22/09/2022; Compl:0%->40%; Stat Rep: ->RP-221586; Rapporteur: Intel->Yi GUO, Intel Corporation; Rap eMail: ->yi.guo@intel.com ; ;...; 23/9/22: 100%->100",null,90,46,null,null,"Wed 06/01/21","Fri 23/09/22"]
[1720,970075,"   UE Conformance - NR Positioning Enhancements ","NR_pos_enh-UEConTest",2,"Rel-17","R5","Thu 08/09/22","Thu 12/12/24",1,"RP-243120","RP-243119","Xiaoyang TIAN, CATT","tianxiaoyang@catt.cn","9/12/22: FCD:10/06/2024->31/05/2024; Compl:0%->5%; Stat Rep: ->RP-223137; Rapporteur: CATT->Xiaoyang TIAN, CATT; Rap eMail: ->tianxiaoyang@catt.cn; 17/3/23: Compl:5%->7%; Stat Rep: RP-223137->RP-230394; ...; 6/9/23: FCD:06/06/2023->06/06/2024; Compl:1...",null,97,49,null,null,"Fri 23/09/22","Fri 24/01/25"]
[1721,840047,"Communication Service Requirements for Critical Medical Applications ","CMED",1,"Rel-17",null,"Thu 06/09/18","Thu 12/12/19",1,"SP-190306",null,"Lagrange, Mathieu, b<>com ","mathieu.lagrange@b-com.com ",null,"22.261; 22.104 ",84,43,null,null,"Fri 31/05/19","NA"]
[1722,810016,"   Study on CMED","FS_CMED",2,"Rel-17","S1","Thu 06/09/18","Fri 13/09/19",1,"SP-180783",null,"Mathieu Lagrange, b<>com","mathieu.lagrange@b-com.com ","4/12/18: 0%->15¦14/3/19: 15%->65; 31/5/19: 65%->90; 6/12/19: 90%->100",22.826000000000001,81,41,null,null,"Thu 06/09/18","Fri 06/12/19"]
[1723,840033,"   Stage 1 of CMED","CMED",2,"Rel-17","S1","Thu 06/06/19","Thu 12/12/19",1,"SP-190306",null,"Lagrange, Mathieu, b<>com ","mathieu.lagrange@b-com.com ","13/9/19: 0%->80; 6/12/19: 80%->100","22.261; 22.104 ",84,43,null,null,"Fri 31/05/19","Fri 06/12/19"]
[{"$f":"A1724+1","v":1724},0,"Rel-17 drone/UAS/UAV/EAV","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-","06/21: \"unmanned\" changed to \"uncrewed\" as per SA#91 discussions","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1725,840083,"5G Enhancement for UAVs ","EAV",1,"Rel-17",null,"Thu 06/09/18","Fri 13/12/19",1,"SP-190308",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ",null,"22.125; 22.261 ",84,43,null,null,"Fri 31/05/19","NA"]
[1726,810019,"   Study on EAV","FS_EAV",2,"Rel-17","S1","Thu 06/09/18","Fri 13/12/19",1,"SP-180909",null,"Qun Wei, China Unicom","weiqun5@chinaunicom.cn","-; 31/5/19: 70%->90; 13/9/19: 90%->100",22.829000000000001,81,41,null,null,"Thu 06/09/18","Fri 13/09/19"]
[1727,840039,"   Stage 1 of EAV","EAV",2,"Rel-17","S1","Thu 06/06/19","Thu 12/12/19",1,"SP-190308",null,"Qun Wei, China Unicom ","weiqun5@chinaunicom.cn ","26.118¦26.247 ; 13/9/19: 0%->80; 6/12/19: 80%->100","26.118; 26.247¦22.125",84,43,null,null,"Fri 31/05/19","Fri 06/12/19"]
[1728,820011,"Study on supporting Uncrewed Aerial Systems Connectivity, Identification, and Tracking","FS_ID_UAS_SA2",1,"Rel-17","S2","Thu 06/12/18","Tue 15/12/20",1,"SP-200097",null,"Qualcomm Incorporated, Stefano Faccin ","sfaccin@qti.qualcomm.com","25/3/20: WID:SP-181114->SP-200097; 25/3/20: 0%->25; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 25%->50; 12/9/20: 50%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->100",null,82,42,null,null,"Thu 06/12/18","Sat 05/12/20"]
[1729,820026,"Study on application layer support for Uncrewed Aerial System (UAS) ","FS_UASAPP",1,"Rel-17","S6","Thu 06/12/18","Fri 12/03/21",1,"SP-200111",null,"Niranth Amogh, Huawei","namogh@huawei.com ","31/5/19: 0%->10; 13/9/19: 10%->25; 6/12/19: 25%->35; 6/12/19: FCD:13/12/2019->03/20; 25/3/20: WID:SP-181252->SP-200111; 25/3/20: FCD:12/03/2020->09/20; 28/6/20: 35%->45; 13/9/20: 45%->55; 5/12/20: 55%->75; 5/12/20: FCD:11/09/2020->03/20; 21/3/21: 75%->100","new 23.755",82,42,null,null,"Thu 06/12/18","Sun 21/03/21"]
[1730,920045,"Application layer support for Uncrewed Aerial System (UAS) ","UASAPP",1,"Rel-17",null,"Fri 04/12/20","Fri 11/03/22",1,"SP-200988",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","23.434 ; 21/3/21: 0%->25",null,90,46,null,null,"Fri 04/12/20","Sun 21/03/21"]
[1731,900025,"   Stage 2 of Application layer support for Uncrewed Aerial System (UAS) ","UASAPP",2,"Rel-17","S6","Fri 04/12/20","Fri 11/06/21",1,"SP-200988",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","21/3/21: 0%->25; 11/6/21: 25%->100; 2/7/21: 23.255 added;","23.434 ; new 23.255",90,46,null,null,"Fri 04/12/20","Fri 02/07/21"]
[1732,920004,"   CT1 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) ","UASAPP",2,"Rel-17","C1","Fri 11/06/21","Fri 11/03/22",1,"CP-211111",null,"Lin Shu, Huawei, ","shulin@huawei.com ","; 2/7/21: 24.257 added;; 13/9/21: 0%->40; 13/12/21: 40%->80; 12/3/22: 80%->100","24.548;24.545;27.007 ; 24.257",92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[1733,920046,"   CT3 Aspects of Application Layer Support for Uncrewed Aerial Systems (UAS) ","UASAPP",2,"Rel-17","C3","Fri 11/06/21","Fri 11/03/22",1,"CP-220303",null,"Lin Shu, Huawei ","shulin@huawei.com ","; 11/6/21: 0%->5; 2/7/21: 29.257 added;; 13/9/21: 5%->30; 13/12/21: 30%->75; 13/12/21: WID:CP-211111->CP-213076; 12/3/22: 75%->100; 12/3/22: WID:CP-213076->CP-220303","29.549 ; 29.257",92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[1734,880007,"Study on security aspects of Uncrewed Aerial Systems (UAS)","FS_UAS_SEC",1,"Rel-17","S3","Fri 12/06/20","Fri 10/12/21",1,"SP-200352",null,"Adrian Escott, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","12/9/20: 0%->15; 12/9/20: FCD:15/01/2021->03/21; 5/12/20: 15%->30; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 30%->65; 11/6/21: 65%->90; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 90%->90; 31/3/23: 90%->100",33.853999999999999,88,45,null,null,"Thu 25/06/20","Fri 31/03/23"]
[1735,810049,"Remote Identification of Uncrewed Aerial Systems","ID_UAS",1,"Rel-17",null,"Thu 06/09/18","Thu 12/12/24",1,"SP-180771",null,"Eddy HALL, Qualcomm incorporated","edhall@qti.qualcomm.com",null,null,81,41,null,null,"Thu 06/09/18","NA"]
[1736,810013,"   Stage 1 of Remote Identification of Uncrewed Aerial Systems","ID_UAS",2,"Rel-17","S1","Thu 06/09/18","Fri 14/12/18",1,"SP-180771",null,"Eddy HALL, Qualcomm incorporated","edhall@qti.qualcomm.com","10/9/18: 0%->5¦4/12/18: 5%->100. Initially Rel-16",22.125,81,41,null,null,"Thu 06/09/18","Tue 04/12/18"]
[1737,900014,"   (Stage 2 of) Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking ","ID_UAS",2,"Rel-17","S2","Thu 03/12/20","Wed 08/09/21",1,"SP-200979",null,"Faccin, Stefano, Qualcomm Incorporated ","sfaccin@qti.qualcomm.com ","19/3/21: 0%->15; 14/6/21: 15%->80; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 80%->98; 10/12/21: 98%->100","23.501; 23.502; 23.503; 23.401 ",90,46,null,null,"Thu 03/12/20","Fri 10/12/21"]
[1738,910017,"   CT aspects for ID_UAS","ID_UAS",2,"Rel-17","ct","Thu 18/03/21","Fri 11/03/22",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: WID:CP-210287->CP-211112","24.501; 24.301; 24.008; 27.007; 29.502; 29.503; 29.504; 29.505; 29.510; 29.518; 29.571; 29.274; 29.522; 29.122; 29.512; 29.513; 29.514; 29.561; 29.519 ",91,46,null,null,"Thu 18/03/21","Fri 11/06/21"]
[1739,910069,"      CT1 aspects for ID_UAS","ID_UAS",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: 0%->20; 13/9/21: 20%->30; 13/12/21: 30%->70; 12/3/22: 70%->100",null,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1740,910070,"      CT3 aspects for ID_UAS","ID_UAS",3,"Rel-17","C3","Thu 18/03/21","Fri 11/03/22",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 2/7/21: 29.255 added;; 2/7/21: 29.257 added;; 13/9/21: 0%->20; 13/12/21: 20%->80; 12/3/22: 80%->100","29.255; 29.257",91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1741,910071,"      CT4 aspects for ID_UAS","ID_UAS",3,"Rel-17","C4","Thu 18/03/21","Fri 11/03/22",1,"CP-211112",null,"Sunghoon Kim, Qualcomm Incorporated ","sunghoon@qti.qualcomm.com ","; 11/6/21: 0%->20; 13/9/21: 20%->30; 13/12/21: 30%->80; 12/3/22: 80%->100",null,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1742,920028,"   Security aspects of Uncrewed Aerial Systems ","ID_UAS",2,"Rel-17","S3","Fri 11/06/21","Fri 11/03/22",1,"SP-210425",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","1/10/21: 33.256 added;; 13/12/21: 0%->50; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 50%->100",33.256,92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[1743,991034,"   UE Conformance - Support of Uncrewed Aerial Systems Connectivity, Identification, and Tracking ","ID_UAS-UEConTest",2,"Rel-17","R5","Fri 03/03/23","Thu 12/12/24",1,"RP-241591","RP-241126","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","; 7/6/23: Compl:0%->6%; 7/6/23: CD:12/12/2024->12/12/2023; 6/9/23: Compl:6%->40%; Stat Rep: ->RP-231997; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com; ; 14/3/24: FCD:12/12/2023->12/12/2024; Compl:40%->95%; ...",null,99,50,null,null,"Wed 29/03/23","Tue 23/07/24"]
[1744,0,"Rel-17 Satellite/Non-Terrestrial (NTN) related ","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1745,890034,"Integration of satellite components in the 5G architecture ","5GSAT_ARCH",1,"Rel-17",null,"Wed 06/06/18","Fri 11/03/22",1,"SP-191335",null,"Cyril MICHEL, thales ","cyril.michel@thalesaleniaspace.com ",null,"23.501; 23.502; 23.503 ",86,44,null,null,"Fri 06/12/19","NA"]
[1746,800048,"   Stage 1 of 5GSAT","5GSAT",2,"Rel-17","S1","Wed 06/06/18","Fri 14/09/18",1,"SP-180326",null,"MICHEL, Cyril, Thales","cyril.michel@thalesaleniaspace.com","10/9/18: 0%->95¦4/12/18: 95%->100. 09/20: moved to Rel-17 since St 2 and 3 are Rel-17",22.260999999999999,80,41,null,null,"Wed 06/06/18","Tue 04/12/18"]
[1747,800026,"   Study on architecture aspects for using satellite access in 5G","FS_5GSAT_ARCH",2,"Rel-17","S2","Wed 06/06/18","Thu 25/06/20",1,"SP-181253",null,"MICHEL, Cyril","cyril.michel@thalesaleniaspace.com","10/9/18: 0%->15¦10/9/18: FCD:06/19->03/19¦7/12/18: 15%->35¦14/12/18: WID:SP-180505->SP-181253¦14/12/18: FCD:03/19->09/19¦14/3/19: 35%->50; 5/6/19: 50%->60; 13/9/19: 60%->70. Moved to R17.; 6/12/19: 70%->85; 26/6/20: FCD:12/09/2019->06/20; 26/6/20: 85%- ","New",80,41,null,null,"Wed 06/06/18","Fri 26/06/20"]
[1748,860005,"   (Stage 2 of) Integration of satellite components in the 5G architecture ","5GSAT_ARCH",2,"Rel-17","S2","Fri 06/12/19","Wed 08/09/21",1,"SP-191335",null,"Cyril MICHEL, thales ","cyril.michel@thalesaleniaspace.com ","12/9/20: 0%->10; 12/9/20: FCD:11/09/2020->03/21; 5/12/20: 10%->50; 19/3/21: FCD:12/03/2021->06/21; 19/3/21: 50%->75; 11/6/21: 75%->98; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 98%->99; 10/12/21: 99%->100","23.501; 23.502; 23.503 ",86,44,null,null,"Fri 06/12/19","Fri 10/12/21"]
[1749,911030,"   CT aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",2,"Rel-17","ct","Wed 16/09/20","Fri 11/03/22",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: WID:CP-202244->CP-210149","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"Sat 12/09/20","Fri 11/06/21"]
[1750,890005,"      CT1 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C1","Wed 16/09/20","Fri 11/03/22",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 25%->80; 13/9/21: 80%->60; 13/12/21: 60%->75; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 75%->85; 4/6/22: 85%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"Sat 12/09/20","Sat 04/06/22"]
[1751,920057,"      CT3 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C3","Wed 16/09/20","Fri 10/09/21",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 25%->80; 11/6/21: 0%->60; 13/9/21: 60%->80; 13/12/21: 80%->95; 12/3/22: 95%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"Sat 12/09/20","Sat 12/03/22"]
[1752,911031,"      CT4 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C4","Wed 16/09/20","Fri 11/03/22",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","; 25/9/20: WID:CP-202189->CP-202244; 5/12/20: 0%->20; 21/3/21: 20%->25; 11/6/21: 0%->80; 13/9/21: FCD:Fri 10/09/->03/22; 13/12/21: 80%->90; 12/3/22: 90%->100","23.122; 24.501; 24.008; 24.301 ",89,45,null,null,"Sat 12/09/20","Sat 12/03/22"]
[1753,930044,"      CT6 aspects of 5GC architecture for satellite networks ","5GSAT_ARCH-CT",3,"Rel-17","C6","Mon 13/09/21","Fri 11/03/22",1,"CP-210149",null,"Catovic, Amer, Qualcomm Incorporated ","amerc@qti.qualcomm.com ","CT6 aspects introduced as per CT6 report in CP-212127; 12/3/22: 0%->96; 4/6/22: 96%->97",null,93,47,null,null,"Sat 12/09/20","Sat 04/06/22"]
[1754,860046,"Solutions for NR to support non-terrestrial networks (NTN)","NR_NTN_solutions",1,"Rel-17",null,"Mon 16/12/19","Thu 12/12/24",0.97,"RP-220208",null,"Thales",null,"affects: NR. Follow-up WI of REL-16 SI FS_NR_NTN_solutions; 28/7/20: WID:RP-193234->RP-201256; 6/1/21: WID:RP-201256->RP-202908; 7/4/21: WID:RP-202908->RP-210908; 1/10/21: 38.108 & 38.181 added;; 5/4/22: WID:RP-210908->RP-220208","38.108; 38.181",86,44,null,null,"Tue 14/01/20","Tue 05/04/22"]
[1755,860146,"   Core part: Solutions for NR for NTN","NR_NTN_solutions-Core",2,"Rel-17","R4","Mon 16/12/19","Mon 06/06/22",1,"RP-221169","RP-230115","Nicolas Chuberre, Thales","nicolas.chuberre@thalesaleniaspace.com","affects: NR. follow-up WI of REL-16 SI FS_NR_NTN_solutions; 1/10/21: 38.863 added;; 7/1/22: 38.101-5 added ; ; 6/6/22: Compl:90%->0% ; 20/6/22: Compl:0%->100%; Stat Rep: RP-221168->RP-221168 / 1745; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap e...","38.863; 38.101-5",86,44,null,null,"Tue 14/01/20","Fri 17/03/23"]
[1756,860246,"   Perf. Part: Solutions for NR for NTN","NR_NTN_solutions-Perf",2,"Rel-17","R4","Mon 16/12/19","Fri 03/03/23",1,"RP-222556","RP-230115","Nicolas Chuberre, Thales","nicolas.chuberre@thalesaleniaspace.com","affects: NR.; ; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/12/2022; Compl:40%->20%; WID: RP-220208->RP-213691; Stat Rep: RP-220132->RP-221168 / 1745; Rapporteur: Thales->Nicolas Chuberre, Thales; Rap eMail: ->nicolas.chuberre@thalesaleniaspace.com; ;...;...",null,86,44,null,null,"Tue 14/01/20","Fri 17/03/23"]
[1757,960074,"   UE Conformance - Solutions for NR to support non-terrestrial networks (NTN) plus CT aspects ","NR_NTN_solutions_plus_CT-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Fri 12/12/25",0.93,"RP-221241","RP-251229","Vijay Balasubramanian, Qualcomm","vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 23/9/22: WID:RP-221241->RP-222537; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:5%->13%; WID: RP-222537->RP-221241; Stat Rep: ->RP-223386; Rapporteur: Qualcomm->Vijay Balasubramanian, Qualcomm; Rap eMail: ->vijayb[at]qti.qual...","38.521-5",96,49,null,null,"Tue 12/07/22","Fri 06/06/25"]
[1758,920069,"NB-IoT/eMTC support for Non-Terrestrial Networks ","LTE_NBIOT_eMTC_NTN",1,"Rel-17","R1","Tue 15/06/21","Fri 01/03/24",1,"RP-211601",null,"MediaTek ",null,"follow-up WI of REL-17 SI FS_LTE_NBIOT_eMTC_NTN; no Perf. part ",null,92,47,null,null,"Fri 02/07/21","NA"]
[1759,920169,"   Core part: NB-IoT/eMTC support for Non-Terrestrial Networks ","LTE_NBIOT_eMTC_NTN-Core",2,"Rel-17","R1","Tue 15/06/21","Wed 22/06/22",1,"RP-211601","RP-221546","Gilles Charbit, MediaTek","Gilles.charbit@mediatek.com","follow-up WI of REL-17 SI FS_LTE_NBIOT_eMTC_NTN; no Perf. part ; 20/6/22: Release: Rel-17->Rel-18; Rapporteur: MediaTek->Gilles Charbit, MediaTek; Rap eMail: ->Gilles.charbit@mediatek.com; ",null,92,47,null,null,"Fri 02/07/21","Mon 20/06/22"]
[1760,960087,"   UE Conformance - NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) including EPS aspects ","LTE_NBIOT_eMTC_NTN_plus_EPS-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Fri 01/03/24",1,"RP-233250","RP-240442","Daiwei Zhou, MediaTek Inc.","daiwei.zhou@mediatek.com","9/9/22: Comp...; 9/12/22: FCD:23/09/2022->01/09/2023; Compl:45%->95%; Stat Rep: ->RP-223229; Rapporteur: MediaTek->Daiwei Zhou, MediaTek Inc.; Rap eMail: ->daiwei.zhou@mediatek.com; 17/3/23: FCD:09/09/2023->08/09/2023; Compl:95%->96%; Sta.....",null,96,49,null,null,"Tue 12/07/22","Thu 14/03/24"]
[1761,930019,"   Architecture support for NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","S2","Fri 10/09/21","Fri 10/12/21",1,"SP-211306",null,"SEBIRE, Guillaume, MediaTek Inc. ","guillaume dot sebire at mediatek dot com ","; 7/1/22: WID:SP-211124->SP-211306; 7/1/22: 0%->95; 12/3/22: 95%->100","23.203; 23.271; 23.401; 23.682 ",93,47,null,null,"Fri 10/09/21","Sat 12/03/22"]
[1762,940001,"   CT1 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C1","Mon 13/12/21","Tue 15/03/22",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 4/6/22: 20%->80;; 20/6/22: FCD:13/12/2021->15/03/2022Compl:80%->95%","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",94,48,null,null,"Sat 12/03/22","Mon 20/06/22"]
[1763,970049,"   CT3 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C3","Mon 13/12/21","Tue 15/03/22",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 12/3/22: 0%->100","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"Sat 12/03/22","Sat 12/03/22"]
[1764,950045,"   CT4 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C4","Mon 13/12/21","Tue 15/03/22",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 12/3/22: 0%->100","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"Sat 12/03/22","Sat 12/03/22"]
[1765,950046,"   CT6 aspects of NB-IoT/eMTC Non-Terrestrial Networks in EPS ","IoT_SAT_ARCH_EPS",2,"Rel-17","C6","Mon 13/12/21","Tue 15/03/22",1,"CP-213273",null,"NIEMI, Marko, MediaTek Inc., ","marko.niemi at mediatek dot com ","; 12/3/22: 0%->20; 4/6/22: 0%->80","23.122; 23.008; 24.008; 24.301; 27.007; 29.212; 29.272; 29.274; 31.102; 31.111 ",95,48,null,null,"Sat 12/03/22","Sat 04/06/22"]
[1766,830025,"Study on management and orchestration aspects with integrated satellite components in a 5G network","FS_5GSAT_MO",1,"Rel-17","S5","Thu 07/03/19","Fri 12/03/21",1,"SP-190138",null,"Floris Drijver, TNO","floris.drijver@tno.nl ","31/5/19: 0%->10; 31/5/19: 0%->10; 13/9/19: 10%->30; 26/3/20: 30%->60; 26/3/20: FCD:05/12/2019->06/20; 28/6/20: 60%->65; 13/9/20: 65%->70; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 70%->90; 5/12/20: FCD:15/12/2020->03/20; 21/3/21: 90%->100","New",83,42,null,null,"Thu 14/03/19","Sun 21/03/21"]
[1767,860033,"Study on NB-IoT/eMTC support for NTN","FS_LTE_NBIOT_eMTC_NTN",1,"Rel-17","R1","Mon 16/12/19","Tue 15/06/21",1,"RP-202689",null,"MediaTek",null,"affects: LTE. connecting LTE NB-IoT and LTE eMTC to NTN of NR; TR 36.7xx; 25/9/20: 36.763 added;; 6/1/21: WID:RP-193235->RP-202689; 2/7/21: 0%->100",36.762999999999998,86,44,null,null,"Tue 14/01/20","Fri 02/07/21"]
[1768,0,"Rel-17 IoT related ","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1769,850012,"Study on enhanced support of Industrial IoT ","FS_IIoT",1,"Rel-17","S2","Thu 19/09/19","Fri 12/03/21",1,"SP-200298",null,"Nokia, Devaki Chandramouli, ","devaki.chandramouli@nokia.com ","; 8/10/19: 23.700-20 added;; 6/12/19: 0%->20; 25/3/20: WID:SP-190932->SP-200298; 25/3/20: FCD:12/03/2020->06/20; 25/3/20: 20%->40; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 40%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->95; 5/ ","New ; 23.700-20",85,43,null,null,"Fri 13/09/19","Fri 11/06/21"]
[1770,880010,"Study on security for enhanced support of Industrial IoT ","FS_IIoT_SEC",1,"Rel-17","S3","Fri 12/06/20","Fri 11/06/21",1,"SP-200355",null,"Nokia, Anja Jerichow ","anja.jerichow@nokia.com ","28/7/20: 33.851 added;; 12/9/20: 0%->15; 5/12/20: 15%->60; 5/12/20: FCD:11/12/2020->06/20; 19/3/21: 60%->90; 11/6/21: 90%->100",33.850999999999999,88,45,null,null,"Thu 25/06/20","Fri 11/06/21"]
[1771,920024,"Security for enhanced support of Industrial IoT ","IIoT_SEC",1,"Rel-17","S3","Fri 11/06/21","Fri 18/06/21",1,"SP-210421",null,"Nokia, Anja Jerichow ","anja.jerichow@nokia.com ","; 24/3/22: 0%->100",33.500999999999998,92,47,null,null,"Fri 11/06/21","Thu 24/03/22"]
[1772,910059,"Support of Enhanced Industrial IIoT ","IIoT",1,"Rel-17",null,"Thu 03/12/20","Fri 11/03/22",1,"SP-200973",null,"Devaki Chandramouli, Nokia ","Devaki.chandramouli@nokia.com ",null,null,90,46,null,null,"Thu 03/12/20","NA"]
[1773,900008,"   Stage 2 for IIoT","IIoT",2,"Rel-17","S2","Thu 03/12/20","Wed 08/09/21",1,"SP-200973",null,"Devaki Chandramouli, Nokia ","Devaki.chandramouli@nokia.com ","19/3/21: 0%->35; 11/6/21: 35%->90; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->100","23.501; 23.502; 23.503 ",90,46,null,null,"Thu 03/12/20","Mon 13/09/21"]
[1774,910014,"   CT aspects of support of enhanced Industrial IoT ","IIoT",2,"Rel-17","ct","Thu 18/03/21","Fri 11/03/22",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 10/9/21: WID:CP-211114->CP-212100","24.501; 24.519; 24.535; 29.512; 29.513; 29.514; 29.519; 29.522; 29.591; 29.244 ",91,46,null,null,"Thu 18/03/21","Fri 10/09/21"]
[1775,910060,"      CT1 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->65; 2/7/21: 24.539 added;; 13/9/21: 65%->90; 13/12/21: 90%->95; 12/3/22: 95%->100",24.539000000000001,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1776,910061,"      CT3 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C3","Thu 18/03/21","Fri 11/03/22",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->45; 11/6/21: WID:CP-210279->CP-211114; 13/9/21: 45%->65; 1/10/21: 29.565 added;; 13/12/21: 65%->85; 12/3/22: 85%->98; 4/6/22: 98%->100",29.565000000000001,91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1777,910062,"      CT4 aspects of support of enhanced Industrial IoT ","IIoT",3,"Rel-17","C4","Thu 18/03/21","Fri 11/03/22",1,"CP-212100",null,"Won, Sung Hwan, Nokia ","sung.won@nokia.com ","; 11/6/21: 0%->60; 13/9/21: 60%->90; 13/12/21: 90%->95; 12/3/22: 95%->100",null,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1778,940044,"Charging enhancements for 5G CIoT ","5G_CIoT_CH",1,"Rel-17","S5","Fri 10/12/21","Fri 10/06/22",1,"SP-211448",null,"Zhu, Lei, Huawei ","Lei.zhu@huawei.com ","; 12/3/22: 0%->60; 4/6/22: 60%->100","32.255; 32.291; 32.298 ",94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[1779,860044,"Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6",1,"Rel-17",null,"Thu 07/03/19","Thu 22/09/22",1,"RP-220529",null,"Huawei",null,"affects: LTE. compare NB_IOT, LTE_MTCe2_L1 in REL-13,NB_IOTenh, LTE_feMTC in REL-14, WTC; 28/7/20: WID:RP-193264->RP-201306; 2/7/21: WID:RP-201306->RP-211340; 5/4/22: WID:RP-211340->RP-220529",null,86,44,null,null,"Tue 14/01/20","Tue 05/04/22"]
[1780,860144,"   Core part: Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6-Core",2,"Rel-17","R1","Tue 21/12/21","Tue 22/03/22",1,"RP-220529","RP-221499","Yubo YANG Emre YAVUZ, Huawei Ericsson","yangyubo1@huawei.com emre.yavuz@ericsson.com","affects: LTE. compare NB_IOT, LTE_MTCe2_L1 in REL-13,NB_IOTenh, LTE_feMTC in REL-14, WTC; 13/9/21: Com ; 20/6/22: Rapporteur: Huawei->Yubo YANG Emre YAVUZ, Huawei Ericsson; Rap eMail: ->yangyubo1@huawei.com emre.yavuz@ericsson.com20/6/22: 1...",null,86,44,null,null,"Tue 14/01/20","Mon 20/06/22"]
[1781,860244,"   Perf. part: Additional enhancements for NB-IoT and LTE-MTC","NB_IOTenh4_LTE_eMTC6-Perf",2,"Rel-17","R1","Thu 07/03/19","Thu 22/09/22",1,"RP-220529","RP-221499","Yubo YANG Emre YAVUZ, Huawei Ericsson","yangyubo1@huawei.com emre.yavuz@ericsson.com","affects: LTE.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21 ; 22/3/22: Compl:0%->30% ; 20/6/22: WG: R4->R1; Rapporteur: Huawei->Yubo YANG Emre YAVUZ, Huawei Ericsson; Rap eMail: ->yangyubo1@huawei.com emre.yavuz@ericsson.com20/6/22: 0%->70; 20/6/22...",null,86,44,null,null,"Tue 14/01/20","Fri 09/09/22"]
[1782,860051,"NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE",1,"Rel-17",null,"Mon 16/12/19","Thu 12/12/24",1,"RP-222364",null,"ZTE",null,"affects: NR.; 28/7/20: WID:RP-193252->RP-201305; 7/4/21: WID:RP-201305->RP-210870; 29/9/21: WID:RP-210870->RP-212594; 23/9/22: WID:RP-212594->RP-222364",null,86,44,null,null,"Tue 14/01/20","Fri 23/09/22"]
[1783,860151,"   Core part: NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE-Core",2,"Rel-17","R2","Mon 16/12/19","Tue 22/03/22",1,"RP-222364","RP-221309","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","affects: NR.; 13/9/21: Compl:0%->50%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; ; 20/6/22: Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->eswar.vutukuri@zte.com.cn; ",null,86,44,null,null,"Tue 14/01/20","Mon 20/06/22"]
[1784,860251,"   Perf. part: NR small data transmissions in INACTIVE state","NR_SmallData_INACTIVE-Perf",2,"Rel-17","R2","Mon 16/12/19","Wed 21/12/22",1,"RP-222364","RP-221309","Eswar Vutukuri, ZTE Corporation","eswar.vutukuri@zte.com.cn","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211871; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-211871->RP-220153 20/6/22: WG: R4->R2; Rapporteur: ZTE->Eswar Vutukuri, ZTE Corporation; Rap eMail: ->es...; 9/",null,86,44,null,null,"Tue 14/01/20","Mon 09/01/23"]
[1785,960072,"   UE Conformance - NR small data transmissions in INACTIVE state ","NR_SmallData_INACTIVE-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Thu 12/12/24",1,"RP-221238","RP-242497","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:15%->30%; Stat Rep: ->RP-223385; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:30%->75%; S.....",null,96,49,null,null,"Tue 12/07/22","Fri 24/01/25"]
[1786,860045,"Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR","NR_IIOT_URLLC_enh",1,"Rel-17",null,"Mon 16/12/19","Tue 12/12/23",1,"RP-220152",null,"Nokia",null,"affects: NR. no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC; 7/4/21: WID:RP-201310->RP-210854; 5/4/22: WID:RP-210854->RP-220152",null,86,44,null,null,"Tue 14/01/20","Tue 05/04/22"]
[1787,860145,"   Core part: Enhanced IoT and URLLC support for NR","NR_IIOT_URLLC_enh-Core",2,"Rel-17","R2","Mon 16/12/19","Tue 01/03/22",1,"RP-220152","RP-223027","Chunli Wu, Nokia","Chunli.wu@nokia-sbell.com","affects: NR. no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC; 28/7/20: WID:RP-193233->RP-201310; 13/9/21: Compl:0%->55% ; ; 20/6/22: Rapporteur: Nokia->Chunli Wu, Nokia; Rap eMail: ->Chunli.wu@nokia-sbell.com; 9/12/22: FCD:22/03/2022->...",null,86,44,null,null,"Tue 14/01/20","Fri 09/12/22"]
[{"$f":"A1788+1","v":1788},860245,"   Perf. Part: Enhanced IoT and URLLC support for NR","NR_IIOT_URLLC_enh-Perf",2,"Rel-17","R2","Mon 15/06/20","Thu 01/12/22",1,"RP-220152","RP-223027","Chunli Wu, Nokia","Chunli.wu@nokia-sbell.com","; 13/9/21: CD:Tue 15/03/22->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211938; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-211938->RP-220151 20/6/22: WG: R4->R2; Rapporteur: Nokia->Chunli Wu, Nokia; Rap eMail: ->Chunli.wu@nokia-sbell.com; ...; 9/",null,86,44,null,null,"Fri 25/09/20","Fri 09/12/22"]
[1789,960082,"   UE Conformance - Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR ","NR_IIOT_URLLC_enh-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Tue 12/12/23",1,"RP-221416","RP-232885","Matti Kangas, Nokia, Nokia Shanghai Bell","matti.kangas@nokia.com","9/9/22: Comp...; 9/12/22: FCD:23/06/2023->01/06/2023; Stat Rep: ->RP-223013; Rapporteur: Nokia->Matti Kangas, Nokia, Nokia Shanghai Bell; Rap eMail: ->matti.kangas@nokia.com; 31/3/23: Compl:5%->74%; Stat Rep: RP-223013->RP-230700; ;...; 6/9...",null,96,49,null,null,"Tue 12/07/22","Fri 08/12/23"]
[1790,0,"Rel-17 V2V/D2D/Sidelink related ","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-","-","-",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1791,860042,"NR Sidelink enhancement","NR_SL_enh",1,"Rel-17",null,"Mon 16/12/19","Mon 03/03/25",0.76,"RP-202846",null,"LG Electronics",null,"affects: NR. compare REL-16 WI 5G_V2X_NRSL; 28/7/20: WID:RP-193257->RP-201385; 25/9/20: WID:RP-201385->RP-201516; 6/1/21: WID:RP-201516->RP-202846",null,86,44,null,null,"Tue 14/01/20","Wed 06/01/21"]
[1792,860142,"   Core part: NR Sidelink enhancement","NR_SL_enh-Core",2,"Rel-17","R1","Mon 16/12/19","Fri 11/03/22",1,"RP-202846","RP-220520","LG Electronics",null,"affects: NR. compare REL-16 WI 5G_V2X_NRSL; 13/9/21: Compl:0%->63%; ; ",null,86,44,null,null,"Tue 14/01/20","Tue 22/03/22"]
[1793,860242,"   Perf. part: NR Sidelink enhancement","NR_SL_enh-Perf",2,"Rel-17","R4","Mon 16/12/19","Thu 22/09/22",1,"RP-221863","RP-221186","Seungmin Lee, LG Electronics","Edison.lee@lge.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; ; 22/3/22: Compl:0%->10%; 22/3/22: CD:22/09/2021->12/09/2022 20/6/22: FCD:12/09/2022->22/09/2022; Compl:10%->95%; Stat Rep: RP-220520->RP-221186; Rapporteur: LG Electronics->Seungmin Lee, LG El...; 23",null,86,44,null,null,"Tue 14/01/20","Fri 23/09/22"]
[1794,960084,"   UE Conformance - NR Sidelink enhancement ","NR_SL_enh-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Tue 09/09/25",0.5,"RP-221448","RP-251628","Xiaozhong CHEN, CATT","chenxiaozhong@catt.cn","9/9/22: Comp...; 9/12/22: FCD:23/09/2022->01/09/2023; Stat Rep: ->RP-223140; Rapporteur: CATT->Xiaozhong CHEN, CATT; Rap eMail: ->chenxiaozhong@catt.cn; 17/3/23: FCD:09/09/2023->08/09/2023; Stat Rep: RP-223140->RP-230396; ...; 6/9/23: FCD:0...",null,96,49,null,null,"Tue 12/07/22","Fri 06/06/25"]
[1795,860038,"Study on NR Sidelink relay","FS_NR_SL_relay",1,"Rel-17","R2","Mon 16/12/19","Tue 15/09/20",1,"RP-202208",null,"OPPO",null,"affects: NR. TR 38.8xx; 25/9/20: WID:RP-193253->RP-201474; 6/1/21: WID:RP-201474->RP-202208; 7/4/21: 0%->100",null,86,44,null,null,"Tue 14/01/20","Wed 07/04/21"]
[1796,840035,"Study on enhancements to application layer support for V2X services ","FS_eV2XAPP",1,"Rel-17","S6","Thu 06/06/19","Fri 12/06/20",1,"SP-200110",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","13/9/19: 0%->25; 8/10/19: 23.764 added;; 6/12/19: 25%->35; 25/3/20: WID:SP-190477->SP-200110; 25/3/20: FCD:12/03/2020->06/20; 26/3/20: 35%->50; 28/6/20: 50%->75; 13/9/20: 75%->95; 22/3/22: 95%->100",23.763999999999999,84,43,null,null,"Fri 31/05/19","Tue 22/03/22"]
[1797,910075,"Enhanced application layer support for V2X services ","eV2XAPP",1,"Rel-17",null,"Wed 16/09/20","Fri 11/03/22",1,"SP-200831",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 5/12/20: 0%->35; 10/2/21: FCD:12/03/2021->06/21","23.286; 23.434 ",89,45,null,null,"Fri 11/09/20","Wed 10/02/21"]
[1798,890036,"   Stage 2 of eV2XAPP","eV2XAPP",2,"Rel-17","S6","Wed 16/09/20","Tue 15/06/21",1,"SP-200831",null,"Niranth Amogh, Huawei Telecommunications India ","namogh@huawei.com ","; 5/12/20: 0%->35; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 35%->55; 11/6/21: 55%->100","23.286; 23.434 ",89,45,null,null,"Fri 11/09/20","Fri 11/06/21"]
[1799,910019,"   CT aspects of eV2XAPP","eV2XAPP",2,"Rel-17","ct","Thu 18/03/21","Fri 11/03/22",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: WID:CP-210273->CP-211109","24.486; 24.544; 24.545; 24.546; 24.547; 24.548; 29.549 ",91,46,null,null,"Thu 18/03/21","Fri 11/06/21"]
[1800,910076,"      CT1 aspects of eV2XAPP","eV2XAPP",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: 0%->35; 13/9/21: 35%->65; 13/12/21: 65%->85; 12/3/22: 85%->100",null,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1801,910077,"      CT3 aspects of eV2XAPP","eV2XAPP",3,"Rel-17","C3","Thu 18/03/21","Fri 11/03/22",1,"CP-211109",null,"Herrero Veron, Christian (Huawei) ",null,"; 11/6/21: 0%->50; 13/12/21: 50%->90; 12/3/22: 90%->100",null,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1802,910037,"Support of advanced V2X services - Phase 2 ","eV2XARC_Ph2",1,"Rel-17",null,"Thu 19/09/19","Fri 11/03/22",1,"SP-210090",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ",null,23.286999999999999,91,46,null,null,"Thu 18/03/21","NA"]
[1803,850013,"   Study on V2X services – Phase 2 ","FS_eV2XARC_Ph2",2,"Rel-17","S2","Thu 19/09/19","Fri 12/03/21",1,"SP-190631",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ","; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->25; 12/9/20: 25%->70; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 70%->86; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 86%->100","New ",85,43,null,null,"Fri 13/09/19","Fri 19/03/21"]
[1804,910021,"   Stage 2 of eV2XARC_Ph2 ","eV2XARC_Ph2",2,"Rel-17","S2","Thu 18/03/21","Wed 08/09/21",1,"SP-210090",null,"LaeYoung Kim, LG Electronics ","laeyoung.kim@lge.com ","; 14/6/21: 0%->70; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 70%->95; 10/12/21: 95%->100",23.286999999999999,91,46,null,null,"Thu 18/03/21","Fri 10/12/21"]
[1805,920005,"   CT1 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C1","Fri 11/06/21","Fri 11/03/22",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","; 13/9/21: 0%->45; 13/12/21: 45%->90; 12/3/22: 90%->100","24.588;24.587 ",92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[1806,920047,"   Deleted- CT3 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C3","Fri 11/06/21","Fri 11/03/22",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","03/22: No task for CT3; 22/3/22: 0%->100","31.102;29.522;29.525;29.519 ",92,47,null,null,"Fri 11/06/21","Tue 22/03/22"]
[1807,920048,"   CT6 aspects of eV2XARC_Ph2","eV2XARC_Ph2",2,"Rel-17","C6","Fri 11/06/21","Fri 11/03/22",1,"CP-211116",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","; 4/6/22: 0%->100",31.102,92,47,null,null,"Fri 11/06/21","Sat 04/06/22"]
[1808,0,"Rel-17 NR enhancements","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1809,920070,"UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD",1,"Rel-17","R4","Tue 15/06/21","Fri 22/09/23",1,"RP-211940",null,"Qualcomm ",null,"TR38.8xx; impact on REL-15/16? ; 29/9/21: WID:RP-211597->RP-211940",null,92,47,null,null,"Fri 02/07/21","Wed 29/09/21"]
[1810,920170,"   Core part: UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD-Core",2,"Rel-17","R4","Tue 15/06/21","Fri 11/03/22",1,"RP-211940","RP-220467","Qualcomm ",null,"TR38.8xx; impact on REL-15/16? ; 13/9/21: Compl:0%->50%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; 1/10/21: 38.837 added ; ",38.837000000000003,92,47,null,null,"Fri 02/07/21","Tue 22/03/22"]
[1811,920270,"   Perf. part: UE RF requirements for Transparent Tx Diversity (TxD) for NR ","NR_RF_TxD-Perf",2,"Rel-17","R4","Tue 15/06/21","Fri 11/03/22",1,"RP-211940","RP-220467","Qualcomm ",null,"; 13/9/21: Compl:0%->10%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22 ; ; ",null,92,47,null,null,"Fri 02/07/21","Tue 22/03/22"]
[1812,940092,"   UE Conformance - UE RF requirements for Transparent Tx Diversity (TxD) for NR","NR_RF_TxD-UEConTest",2,"Rel-17","R5","Mon 13/12/21","Fri 22/09/23",1,"RP-231240","RP-232351","Yaping ZHANG, Huawei","zhangyaping13@huawei.com","tested: REL-17 WI NR_RF_TxD; 22/3/22: Compl:0%->5%; 22/3/22: Stat Rep: ->RP-220420 6/6/22: Compl:5%->23% 20/6/22: Rapporteur: Huawei->Chunying GU, Huawei; Rap eMail: ->guchunying@huawei.com12/7/22: WID:RP-213229->RP-221491 ...; 9/12/22: FCD:22/12/202...",null,94,48,null,null,"Thu 06/01/22","Wed 06/09/23"]
[1813,860040,"Further enhancements on MIMO for NR","NR_feMIMO",1,"Rel-17",null,"Mon 16/12/19","Mon 09/09/24",1,"RP-212535",null,"Samsung",null,"affects: NR. compare REL-16 WI NR_eMIMO; 25/9/20: WID:RP-193133->RP-202024; 2/7/21: WID:RP-202024->RP-211586; 29/9/21: WID:RP-211586->RP-212535",null,86,44,null,null,"Tue 14/01/20","Wed 29/09/21"]
[1814,860140,"   Core part: Further enhancements on MIMO for NR","NR_FeMIMO-Core",2,"Rel-17","R1","Mon 16/12/19","Tue 22/03/22",1,"RP-212535","RP-221403","Eko Onggosanusi, Samsung","eko.o@samsung.com","affects: NR. compare REL-16 WI NR_eMIMO; 13/9/21: Compl:0%->70%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211788 ; 20/6/22: Acronym:NR_feMIMO-Core->NR_FeMIMO-Core; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ...",null,86,44,null,null,"Tue 14/01/20","Mon 20/06/22"]
[1815,860240,"   Perf. part: Further enhancements on MIMO for NR","NR_feMIMO-Perf",2,"Rel-17","R1","Mon 16/12/19","Thu 01/12/22",1,"RP-212535","RP-222928","Eko Onggosanusi, Samsung","eko.o@samsung.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211788; 22/3/22: Compl:0%->25%; 20/6/22: Acronym:NR_feMIMO-Perf->NR_FeMIMO-Perf; WG: R4->R1; Rapporteur: Samsung->Eko Onggosanusi, Samsung; Rap eMail: ->eko.o@samsung.c...;...",null,86,44,null,null,"Tue 14/01/20","Mon 09/01/23"]
[1816,960079,"   UE Conformance - Further enhancements on MIMO for NR ","NR_feMIMO-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Mon 09/09/24",1,"RP-241983","RP-241980","Runsen Tang, Samsung","runsen.tang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->R5-226804; Rapporteur: Samsung->Runsen Tang, Samsung; Rap eMail: ->runsen.tang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:5%->10%; Stat Rep: R5-226804->RP-2301.....",null,96,49,null,null,"Tue 12/07/22","Thu 26/09/24"]
[1817,860043,"NR Dynamic spectrum sharing (DSS)","NR_DSS",1,"Rel-17",null,"Mon 16/12/19","Tue 22/03/22",1,"RP-211345",null,"Ericsson",null,"affects: NR. no Perf. part; 2/7/21: WID:RP-193260->RP-211345",null,86,44,null,null,"Tue 14/01/20","Fri 02/07/21"]
[1818,860143,"   Core part: NR DSS","NR_DSS-Core",2,"Rel-17","R1","Mon 16/12/19","Tue 22/03/22",1,"RP-211345","RP-220463","Ravikiran Nory","ravikiran.nory@ericsson.com","affects: NR. no Perf. part; 20/6/22: FCD:15/03/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220463; Rapporteur: Ericsson->Ravikiran Nory; Rap eMail: ->ravikiran.nory@ericsson.com; ",null,86,44,null,null,"Tue 14/01/20","Mon 20/06/22"]
[1819,860047,"UE power saving enhancements for NR","NR_UE_pow_sav_enh",1,"Rel-17",null,"Mon 16/12/19","Fri 01/03/24",1,"RP-221543",null,"MediaTek",null,"affects: NR. compare REL-16 WI NR_UE_pow_sav; 26/3/20: WID:RP-193239->RP-200494; 30/6/20: WID:RP-200494->RP-193239; 28/7/20: WID:RP-193239->RP-200938; 29/9/21: WID:RP-200938->RP-212630; 5/4/22: WID:RP-212630->RP-220748; 12/7/22: WID:RP-220748->RP-221543",null,86,44,null,null,"Tue 14/01/20","Tue 12/07/22"]
[1820,860147,"   Core part: UE power saving enhancements for NR","NR_UE_pow_sav_enh-Core",2,"Rel-17","R2","Mon 16/12/19","Tue 22/03/22",1,"RP-221543","RP-221542","Weide Wu / Dapeng Li","weide.wu@mediatek.com / dapeng@zte.com.cn","affects: NR. compare REL-16 WI NR_UE_pow_sav; ; 20/6/22: FCD:11/03/2022->22/03/2023; Stat Rep: RP-220747->RP-221542; Rapporteur: MediaTek->Weide Wu / Dapeng Li; Rap eMail: ->weide.wu@mediatek.com / dapeng@zte.com.cn; ",null,86,44,null,null,"Tue 14/01/20","Mon 20/06/22"]
[1821,860247,"   Perf. part: UE power saving enhancements for NR","NR_UE_pow_sav_enh-Perf",2,"Rel-17","R2","Mon 16/12/19","Thu 22/09/22",1,"RP-221543","RP-221542","Weide Wu / Dapeng Li","weide.wu@mediatek.com / dapeng@zte.com.cn","affects: NR.; ; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/09/2022; Compl:35%->65%; Stat Rep: RP-220747->RP-221542; Rapporteur: MediaTek->Weide Wu / Dapeng Li; Rap eMail: ->weide.wu@mediatek.com / dapeng@zte.com.cn9/9/22: 65%->100; 23/9/22: 100%->100",null,86,44,null,null,"Tue 14/01/20","Fri 23/09/22"]
[1822,880071,"   UE Conformance Test Aspects -UE Power Saving in NR","NR_UE_pow_sav-UEConTest",2,"Rel-16","R5","Mon 22/06/20","Thu 01/12/22",1,"RP-213291","RP-223138","Huiying ZHANG, CATT","zhanghuiying@catt.cn","8/10/20: 0%->5; 6/1/21: WID:RP-200930->RP-202726; 8/4/21: 5%->39; 2/7/21: FCD:Mon 21/06/->09/21; 2/7/21: 39%->52; 6/1/22: WID:RP-202726->RP-213291; 20/6/22: Rapporteur: CATT->Huiying ZHANG, CATT; Rap eMail: ->zhanghuiying@catt.cn ; ...; 9/12/22: FCD...",null,88,45,null,null,"Tue 28/07/20","Mon 09/01/23"]
[1823,960086,"   UE Conformance - UE power saving enhancements for NR ","NR_UE_pow_sav_enh_plus_CT-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Fri 01/03/24",1,"RP-233247","RP-233246","Eniko Sokondar, Vijay Balasubramanian, MediaTek, Qualcomm","eniko.sokondar[at]mediatek.com, vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Compl:3%->20%; Stat Rep: ->RP-223228; Rapporteur: MediaTek->Eniko Sokondar, Vijay Balasubramanian, MediaTek, Qualcomm; Rap eMail: ->eniko.sokondar[at]mediatek.com, vijayb[at]qti.qualcomm...",null,96,49,null,null,"Tue 12/07/22","Tue 02/04/24"]
[1824,860049,"Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2",1,"Rel-17",null,"Mon 16/12/19","Thu 06/06/24",1,"RP-201040",null,"Huawei",null,"affects: LTE, NR. compare REL-16 WI LTE_NR_DC_CA_enh; 28/7/20: WID:RP-193249->RP-201040",null,86,44,null,null,"Tue 14/01/20","Tue 28/07/20"]
[1825,860149,"   Core part: Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2-Core",2,"Rel-17","R2","Mon 16/12/19","Fri 11/03/22",1,"RP-201040","RP-220409","Huawei",null,"affects: LTE, NR. compare REL-16 WI LTE_NR_DC_CA_enh; ",null,86,44,null,null,"Tue 14/01/20","Tue 22/03/22"]
[1826,860249,"   Perf. part: Further Multi-RAT Dual-Connectivity enhancements","LTE_NR_DC_enh2-Perf",2,"Rel-17","R4","Mon 16/12/19","Thu 22/09/22",1,"RP-201040","RP-220409","Matti Kangas","matti.kangas@nokia.com","affects: LTE, NR.; 22/3/22: CD:15/12/2021->12/09/2022; 22/3/22: Stat Rep: ->RP-220409; 20/6/22: WG: R4->R2; FCD:12/09/2022->22/09/2022; Compl:0%->30%; Stat Rep: RP-220409->RP-221500; Rapporteur: Huawei->David Lecompte, Huawei; Rap eMail: ->david.lecomp...",null,86,44,null,null,"Tue 14/01/20","Fri 09/09/22"]
[1827,991033,"   UE Conformance - Further Multi-RAT Dual-Connectivity enhancement ","LTE_NR_DC_enh2-UEConTest",2,"Rel-17","R5","Fri 03/03/23","Thu 06/06/24",1,"RP-233764","RP-241372","Yaping ZHANG, Huawei","zhangyaping13@huawei.com","; 7/6/23: Compl:0%->5%; 6/9/23: Compl:5%->46%; Stat Rep: ->RP-232355; Rapporteur: Huawei->Yaping ZHANG, Huawei; Rap eMail: ->zhangyaping13@huawei.com; ; 8/12/23: FCD:03/03/2024->01/03/2024; Compl:46%->94%; Stat Rep: RP-232355->RP-233763; ; 2/1/24: WID...",null,99,50,null,null,"Wed 29/03/23","Thu 13/06/24"]
[1828,860050,"Enhancements to Integrated Access and Backhaul (IAB) for NR","NR_IAB_enh",1,"Rel-17",null,"Mon 11/03/19","Thu 22/09/22",1,"RP-221177",null,"Qualcomm",null,"affects: NR. compare REL-16 WI NR_IAB; 28/7/20: WID:RP-193251->RP-201293; 7/4/21: WID:RP-201293->RP-210758; 2/7/21: WID:RP-210758->RP-211548; 6/1/22: WID:RP-211548->RP-213668; 12/7/22: WID:RP-213668->RP-221177",null,86,44,null,null,"Tue 14/01/20","Tue 12/07/22"]
[1829,860150,"   Core part: Enhancements to IAB for NR","NR_IAB_enh-Core",2,"Rel-17","R2","Mon 16/12/19","Wed 22/06/22",1,"RP-221177","RP-221176","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","affects: NR. compare REL-16 WI NR_IAB; 13/9/21: Compl:0%->41%; 13/9/21: CD:Tue 15/06/21->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211767 ; 20/6/22: Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com; ",null,86,44,null,null,"Tue 14/01/20","Mon 20/06/22"]
[1830,860250,"   Perf. part: Enhancements to IAB for NR","NR_IAB_enh-Perf",2,"Rel-17","R2","Mon 16/12/19","Thu 22/09/22",1,"RP-221177","RP-221176","Georg Hampel, Qualcomm Incorporated","ghampel@qti.qualcomm.com","affects: NR.; 13/9/21: CD:Wed 15/12/21->Wed 22/09/21; 13/9/21: Stat Rep: ->RP-211767; 22/3/22: Compl:0%->20%; 22/3/2 20/6/22: WG: R4->R2; Rapporteur: Qualcomm->Georg Hampel, Qualcomm Incorporated; Rap eMail: ->ghampel@qti.qualcomm.com9/9/22: ...",null,86,44,null,null,"Tue 14/01/20","Fri 09/09/22"]
[1831,830021,"   Study on Security for NR_IAB","FS_NR_IAB_Sec",2,"Rel-17","S3","Mon 11/03/19","Fri 10/12/21",1,"SP-201016",null,"Rajavelsamy Rajadurai, Samsung, ","rajvel{@]samsung.com ","31/5/19: 0%->20; 13/9/19: 20%->50; 13/9/19: FCD:09/09/2019->12/20; 26/6/20: FCD:12/12/2019->12/20; 12/9/20: 50%->75; 5/12/20: FCD:15/12/2020->03/20; 5/12/20: WID:SP-190106->SP-201016, Rel-16->17; 9/4/21: FCD:12/03/2021->06/21; 11/6/21: 75%->78; 11/6/21 ",33.823999999999998,83,42,null,null,"Thu 14/03/19","Sat 12/03/22"]
[1832,860052,"Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN","LTE_NR_arch_evo_enh",1,"Rel-17",null,"Mon 16/12/19","Wed 09/03/22",1,"RP-213667",null,"China Unicom",null,"affects: LTE, NR. No Perf. Part; compare REL-16 WI LTE_NR_arch_evo; 2/7/21: WID:RP-193181->RP-211409; 6/1/22: WID:RP-211409->RP-213667; 7/1/22: 37.483 added;; 7/1/22: 37.480 added;","37.483; 37.482; 37.481; 37.480; 37.480; ",86,44,null,null,"Tue 14/01/20","Fri 21/01/22"]
[1833,860152,"   Core part: LTE_NR_arch_evo_enh","LTE_NR_arch_evo_enh-Core",2,"Rel-17","R3","Mon 16/12/19","Wed 09/03/22",1,"RP-213667","RP-220557","Gen Cao","caogen@chinaunicom.cn","affects: LTE, NR. no Perf. part; compare REL-16 WI LTE_NR_arch_evo; 6/1/22: WID:RP-211409->RP-213667; 20/6/22: FCD:15/12/2020->22/03/2023; Compl:0%->100%; Stat Rep: ->RP-220557; Rapporteur: China Unicom->Gen Cao; Rap eMail: ->caogen@chinaunicom.cn2...",null,86,44,null,null,"Tue 14/01/20","Mon 20/06/22"]
[1834,890055,"Further enhancement on NR demodulation performance ","NR_demod_enh2",1,"Rel-17",null,"Tue 15/09/20","Mon 09/09/24",1,"RP-221285",null,"China Telecom ",null,"demodulation aspects were introduced in REL-15 WI NR_newRAT and enhanced in REL-16 WI NR_perf_enh-Perf; no Core part ; 6/1/21: WID:RP-202000->RP-202828; 7/4/21: WID:RP-202828->RP-210920; 2/7/21: WID:RP-210920->RP-211135; 29/9/21: WID:RP-211135->RP-2126 ; ",null,89,45,null,null,"Sun 11/10/20","Tue 12/07/22"]
[1835,941114,"   Core part: Further enhancement on NR demodulation performance","NR_demod_enh2-Core",2,"Rel-17","R4","Tue 14/12/21","Wed 22/06/22",1,"RP-221285","RP-221284","Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation","yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com","; 20/6/22: Rapporteur: China Telecom->Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation; Rap eMail: ->yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com; ",null,94,48,null,null,"Tue 22/03/22","Mon 20/06/22"]
[1836,890255,"   Perf. part: NR_demod_enh2","NR_demod_enh2-Perf",2,"Rel-17","R4","Tue 15/09/20","Thu 22/09/22",1,"RP-221285","RP-221284","Shan YANG, Tricia LI, Dmitry BELOV, China Telecom, Huawei, Intel Corporation","yangshan@chinatelecom.cn, tricia.li@huawei.com, dmitry.belov@intel.com","demodulation aspects were introduced in REL-15 WI NR_newRAT and enhanced in REL-16 WI NR_perf_enh-Perf; no Core part ; 2/7/21: 38.833 added;; 13/9/21: Compl:0%->45%; 13/9/21: C ; 6/1/22: WID:RP-212636->RP-213656 20/6/22: FCD:10/06/2022->22/09/2022;...",38.832999999999998,89,45,null,null,"Sun 11/10/20","Fri 09/09/22"]
[1837,960075,"   UE Conformance - Further enhancement on NR demodulation performance ","NR_demod_enh2-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Mon 09/09/24",1,"RP-241994","RP-241993","Wu Jingzhou, Balasubramanian Vijay, China Telecom, Qualcomm Inc","wujingzhou@chinatelecom.cn, vijayb@qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-222947; Rapporteur: ChinaTelecom->Wu Jingzhou, Balasubramanian Vijay, China Telecom, Qualcomm Inc; Rap eMail: ->wujingzhou@chinatelecom.cn, vijayb@qti.qualcomm.com; 17/3.....",null,96,49,null,null,"Tue 12/07/22","Thu 26/09/24"]
[1838,890056,"Introduction of DL 1024QAM for NR frequency range 1 (FR1)","NR_DL1024QAM_FR1",1,"Rel-17",null,"Tue 15/09/20","Tue 12/12/23",1,"RP-213654",null,"Ericsson ",null,"; 6/1/21: WID:RP-202044->RP-202886; 6/1/22: WID:RP-202886->RP-213654",null,89,45,null,null,"Sun 11/10/20","Thu 06/01/22"]
[1839,890156,"   Core part: Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-Core",2,"Rel-17","R4","Tue 15/09/20","Tue 22/03/22",1,"RP-213654","RP-220190","Yi GUO","yi.guo@intel.com","; 20/6/22: FCD:08/09/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220190; Rapporteur: Ericsson->Yi GUO; Rap eMail: ->yi.guo@intel.com; ",null,89,45,null,null,"Sun 11/10/20","Mon 20/06/22"]
[1840,890256,"   Perf. part: Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-Perf",2,"Rel-17","R4","Tue 15/09/20","Wed 22/06/22",1,"RP-213654","RP-221226 /1771","Wanuga, Kevin (RAN1); Uesaka, Kazuyoshi (RAN4), Nokia, Ericsson","kevin (dot) wanuga (at) nokia (dot) com; kazuyoshi (dot) uesaka (at) ericsson (dot) com","; 13/9/21: Compl:0%->90%; 13/9/21: CD:Sat 12/03/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211770; ; 20/6/22: FCD:11/03/2022->22/06/2022; Stat Rep: RP-220190->RP-221226 /1771; Rapporteur: Ericsson->Wanuga, Kevin (RAN1); Uesaka, Kazuyoshi (RAN4), Nokia, ",null,89,45,null,null,"Sun 11/10/20","Mon 20/06/22"]
[1841,960073,"   UE Conformance - Introduction of DL 1024QAM for NR FR1 ","NR_DL1024QAM_FR1-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Tue 12/12/23",1,"RP-221240","RP-233873","Vijay Balasubramanian, Qualcomm","vijayb[at]qti.qualcomm.com","9/9/22: Comp...; 9/12/22: FCD:23/03/2023->01/03/2023; Compl:5%->34%; Stat Rep: ->RP-223384; Rapporteur: Qualcomm->Vijay Balasubramanian, Qualcomm; Rap eMail: ->vijayb[at]qti.qualcomm.com; 17/3/23: FCD:03/03/2023->08/09/2023; Stat Rep: RP-.....",null,96,49,null,null,"Tue 12/07/22","Fri 08/12/23"]
[1842,890057,"NR RRM further enhancement ","NR_RRM_enh2",1,"Rel-17",null,"Tue 15/09/20","Thu 22/09/22",1,"RP-213067",null,"Apple ",null,"LTE impacts? ; 6/1/21: WID:RP-202053->RP-202874; 6/1/22: WID:RP-202874->RP-213067",null,89,45,null,null,"Sun 11/10/20","Thu 06/01/22"]
[1843,890157,"   Core part: Further RRM enhancement for NR and MR-DC ","NR_RRM_enh2-Core",2,"Rel-17","R4","Tue 15/09/20","Tue 22/03/22",1,"RP-213067","RP-221699","Jie Cui, Apple Corporation","jie_cui@apple.com","LTE impacts? ; 4/6/22: 0%->100; 20/6/22: FCD:08/09/2021->22/03/2023; Stat Rep: ->RP-221699; Rapporteur: Apple->Jie Cui, Apple Corporation; Rap eMail: ->jie_cui@apple.com; ",null,89,45,null,null,"Sun 11/10/20","Mon 20/06/22"]
[1844,890257,"   Perf. part: Further RRM enhancement for NR and MR-DC ","NR_RRM_enh2-Perf",2,"Rel-17","R4","Tue 15/09/20","Thu 22/09/22",1,"RP-213067","RP-221699","Jie Cui, Apple Corporation","jie_cui@apple.com","LTE impacts? ; 13/9/21: Compl:0%->60%; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22 ; ; 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->50%; Rapporteur: Apple->Jie Cui, Apple Corporation; Rap eMail: ->jie_cui@apple.com 9/9...",null,89,45,null,null,"Sun 11/10/20","Fri 09/09/22"]
[1845,890058,"Enhanced NR support for high speed train scenario for frequency range 1 (FR1) ","NR_HST_FR1_enh",1,"Rel-17",null,"Tue 15/09/20","Tue 06/06/23",1,"RP-210833",null,"CMCC ",null,"follow-up WI of REL-16 WI NR_HST ; 6/1/21: WID:RP-202106->RP-202335; 7/4/21: WID:RP-202335->RP-210833",null,89,45,null,null,"Sun 11/10/20","Wed 07/04/21"]
[1846,890158,"   Core part: Enhanced NR support for high speed train scenario for FR1","NR_HST_FR1_enh-Core",2,"Rel-17","R4","Tue 15/09/20","Tue 22/03/22",1,"RP-210833","RP-221353","Jingjing Chen, CMCC","chenjingjing@chinamobile.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->70%; 13/9/ ; ; 20/6/22: Rapporteur: CMCC->Jingjing Chen, CMCC; Rap eMail: ->chenjingjing@chinamobile.com; ",null,89,45,null,null,"Sun 11/10/20","Mon 20/06/22"]
[1847,890258,"   Perf. part: Enhanced NR support for high speed train scenario for FR1","NR_HST_FR1_enh-Perf",2,"Rel-17","R4","Tue 15/09/20","Thu 22/09/22",1,"RP-210833","RP-221353","Jingjing Chen, CMCC","chenjingjing@chinamobile.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->50%; 1 ; 22/3/22: Compl:50%->70%; 20/6/22: Rapporteur: CMCC->Jingjing Chen, CMCC; Rap eMail: ->chenjingjing@chinamobile.com ; 9/9/22: Compl:85%->100%",null,89,45,null,null,"Sun 11/10/20","Fri 09/09/22"]
[1848,960077,"   UE Conformance - Enhanced NR support for high speed train scenario for frequency range 1 (FR1) ","NR_HST_FR1_enh-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Tue 06/06/23",1,"RP-221359","RP-230283","Dan SONG, CMCC","songdan@chinamobile.com","9/9/22: Comp...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:23%->62%; Stat Rep: ->RP-223063; Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com; 17/3/23: Compl:62%->71%; Stat Rep: RP-223063->RP-230283; ...",null,96,49,null,null,"Tue 12/07/22","Wed 07/06/23"]
[1849,890059,"Further enhancements of NR RF requirements for frequency range 2 (FR2) ","NR_RF_FR2_req_enh2",1,"Rel-17",null,"Tue 15/09/20","Fri 01/03/24",1,"RP-221784",null,"Nokia ",null,"compare REL-16 WI NR_RF_FR2_req_enh ; 6/1/21: WID:RP-202107->RP-202409; 7/4/21: WID:RP-202409->RP-210914; 2/7/21: WID:RP-210914->RP-211538; 2/7/21: 38.851 added;; 29/9/21: WID:RP-211538->RP-212092; 6/1/22: WID:RP-212092->RP-213666; 5/4/22: WID:RP-21366 ; ",38.850999999999999,89,45,null,null,"Sun 11/10/20","Tue 12/07/22"]
[1850,890159,"   Core part: NR_RF_FR2_req_enh2","NR_RF_FR2_req_enh2-Core",2,"Rel-17","R4","Tue 15/09/20","Wed 22/06/22",1,"RP-220968","RP-221205","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","compare REL-16 WI NR_RF_FR2_req_enh ; 13/9/21: Compl:0%->55%; ; 22/3/22: Compl:55%->75%; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com; ",null,89,45,null,null,"Sun 11/10/20","Mon 20/06/22"]
[1851,890259,"   Perf. part: NR_RF_FR2_req_enh2","NR_RF_FR2_req_enh2-Perf",2,"Rel-17","R4","Tue 15/09/20","Thu 22/09/22",1,"RP-221784","RP-221205","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","compare REL-16 WI NR_RF_FR2_req_enh ; 13/9/21: Compl:0%->25%; ; 22/3/22: CD:22/06/2022->10/06/2022 ; 20/6/22: Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@nokia.com 9/9/22: Compl:80%...",null,89,45,null,null,"Sun 11/10/20","Fri 09/09/22"]
[{"$f":"A1852+1","v":1852},970070,"   UE Conformance - Further enhancements of NR RF requirements for frequency range 2 (FR2) ","NR_RF_FR2_req_enh2-UEConTest",2,"Rel-17","R5","Thu 08/09/22","Fri 01/03/24",1,"RP-240751","RP-240092","Tuomo S yn j kangas, Ashwin Mohan, Nokia, Apple","tuomo.saynajakangas@nokia.com ashwin_mohan@apple.com","9/12/22: FCD:10/12/2023->01/12/2023; Compl:0%->6%; Stat Rep: ->RP-222732; Rapporteur: Nokia->Tuomo S yn j kangas, Ashwin Mohan, Nokia, Apple; Rap eMail: ->tuomo.saynajakangas@nokia.com ashwin_mohan@apple.com; 17/3/23: FCD:30/11/2023->12/12/2023; Com.....",null,97,49,null,null,"Fri 23/09/22","Tue 02/04/24"]
[1853,890060,"NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2",1,"Rel-17",null,"Tue 15/09/20","Thu 12/12/24",0.82,"RP-210800",null,"Samsung ",null,"follow-up WI of REL-16 WI NR_HST; TR 38.8xx ; 6/1/21: WID:RP-202118->RP-202538; 7/4/21: WID:RP-202538->RP-210800",null,89,45,null,null,"Sun 11/10/20","Wed 07/04/21"]
[1854,890160,"   Core part: NR support for high speed train scenario in FR2","NR_HST_FR2-Core",2,"Rel-17","R4","Tue 15/09/20","Tue 22/03/22",1,"RP-210800","RP-221404","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","follow-up WI of REL-16 WI NR_HST; TR 38.8xx ; 13/9/21: Compl:0%->50%; ; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com; ",null,89,45,null,null,"Sun 11/10/20","Mon 20/06/22"]
[1855,890260,"   Perf. Part: NR support for high speed train scenario in FR2","NR_HST_FR2-Perf",2,"Rel-17","R4","Tue 15/09/20","Thu 22/09/22",1,"RP-210800","RP-221404","WANG, He (Jackson), Samsung","h0809.wang@samsung.com","follow-up WI of REL-16 WI NR_HST ; 13/9/21: Compl:0%->20% ; 22/3/22: Compl:20%->50%; 20/6/22: Rapporteur: Samsung->WANG, He (Jackson), Samsung; Rap eMail: ->h0809.wang@samsung.com ; 9/9/22: Compl:80%->100%",null,89,45,null,null,"Sun 11/10/20","Fri 09/09/22"]
[1856,960080,"   UE Conformance - NR support for high speed train scenario in frequency range 2 (FR2) ","NR_HST_FR2-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Fri 12/12/25",0.7,"RP-221402","RP-251016","Runsen Tang, Samsung","runsen.tang@samsung.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->R5-226806; Rapporteur: Samsung->Runsen Tang, Samsung; Rap eMail: ->runsen.tang@samsung.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:7%->18%; Stat Rep: R5-226806->RP-2301.....",null,96,49,null,null,"Tue 12/07/22","Fri 06/06/25"]
[1857,890061,"NR measurement gap enhancements ","NR_MG_enh",1,"Rel-17",null,"Tue 15/09/20","Thu 06/06/24",1,"RP-213658",null,"MediaTek ",null,"measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 6/1/21: WID:RP-202119->RP-202658; 7/4/21: WID:RP-202658->RP-210679; 2/7/21: WID:RP-210679->RP-211591; 6/1/22: WID:RP-211591->RP-213658",null,89,45,null,null,"Sun 11/10/20","Thu 06/01/22"]
[1858,890161,"   Core part: NR and MR-DC measurement gap enhancements ","NR_MG_enh-Core",2,"Rel-17","R4","Tue 15/09/20","Tue 22/03/22",1,"RP-220772","RP-221549","Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, rui.huang@intel.com","measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 20/6/22: FCD:08/09/2021->22/03/2023; Compl:0%->100%; WID: RP-213658->RP-220772; Stat Rep: ->RP-221549; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation;",null,89,45,null,null,"Sun 11/10/20","Mon 20/06/22"]
[1859,890261,"   Perf. part: NR and MR-DC measurement gap enhancements ","NR_MG_enh-Perf",2,"Rel-17","R4","Tue 15/09/20","Thu 22/09/22",1,"RP-220772","RP-221549","Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation","ato.yu@mediatek.com, rui.huang@intel.com","measurement gaps were introduced for NR in REL-15 WI NR_newRAT ; 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->40%; Rapporteur: MediaTek->Ato (Tsang-Wei) YU, Rui HUANG, MediaTek Inc., Intel Corporation; Rap eMail: ->ato.yu@mediatek.com, rui....",null,89,45,null,null,"Sun 11/10/20","Fri 09/09/22"]
[1860,981035,"   UE Conformance - NR and MR-DC measurement gap enhancements ","NR_MG_enh-UEConTest",2,"Rel-17","R5","Wed 14/12/22","Thu 06/06/24",1,"RP-223246","RP-241346","Daiwei Zhou, MediaTek Inc.","daiwei.zhou@mediatek.com","17/3/23: FCD:03/03/2024->01/03/2024; Compl:0%->31%; Stat Rep: ->RP-230638; Rapporteur: MediaTek->Daiwei Zhou, MediaTek Inc.; Rap eMail: ->daiwei.zhou@mediatek.com; ;...; 6/9/23: Compl:55%->63%; Stat Rep: RP-230638->RP-232306; ; 8/12/23: FCD:03/03/2024...",null,98,50,null,null,"Mon 09/01/23","Thu 13/06/24"]
[1861,890062,"RF requirements enhancement for NR frequency range 1 (FR1) ","NR_RF_FR1_enh",1,"Rel-17",null,"Tue 15/09/20","Fri 01/03/24",1,"RP-220681",null,"Huawei ",null,"compare REL-16 WI NR_RF_FR1 ; 6/1/21: WID:RP-202088->RP-202799; 7/4/21: WID:RP-202799->RP-210899; 29/9/21: WID:RP-210899->RP-212527; 5/4/22: WID:RP-212527->RP-220681",null,89,45,null,null,"Sun 11/10/20","Tue 05/04/22"]
[1862,890162,"   Core part: RF requirements enhancement for NR FR1","NR_RF_FR1_enh-Core",2,"Rel-17","R4","Tue 15/09/20","Tue 22/03/22",1,"RP-220681","RP-221501","Liu Ye, Huawei, HiSilicon","leo.liuye@huawei.com","compare REL-16 WI NR_RF_FR1 ; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->90%; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com; ",null,89,45,null,null,"Sun 11/10/20","Mon 20/06/22"]
[1863,890262,"   Perf. part: RF requirements enhancement for NR FR1","NR_RF_FR1_enh-Perf",2,"Rel-17","R4","Tue 15/09/20","Thu 22/09/22",1,"RP-221502","RP-221501","Liu Ye, Huawei, HiSilicon","leo.liuye@huawei.com","compare REL-16 WI NR_RF_FR1 ; 13/9/21: CD:Sat 11/12/21->Wed 22/09/21; ; 22/3/22: CD:22/09/2021->12/09/2022; 22/3/22: Stat Rep: RP-212170->RP-220680 ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei, HiSilicon; Rap eMail: ->leo.liuye@huawei.com12/7/22...",null,89,45,null,null,"Sun 11/10/20","Fri 09/09/22"]
[1864,960090,"   UE Conformance - RF requirements enhancement for NR frequency range 1 (FR1) ","NR_RF_FR1_enh-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Fri 01/03/24",1,"RP-221848","RP-240280","Chunying GU, Huawei","guchunying@huawei.com","9/9/22: Comp...; 9/12/22: FCD:23/12/2022->01/12/2023; Stat Rep: ->RP-223222; Rapporteur: Huawei->Chunying GU, Huawei; Rap eMail: ->guchunying@huawei.com; 17/3/23: FCD:30/11/2023->12/12/2023; Compl:11%->20%; Stat Rep: RP-223222->RP-230702;.....",null,96,49,null,null,"Tue 12/07/22","Thu 14/03/24"]
[1865,941013,"4Rx support for NR band n8","NR_4Rx_Bn8_FWA",1,"Rel-17","R4","Mon 13/12/21","Thu 22/09/22",1,"RP-220395",null,"CHTTL",null,"5/4/22: WID:RP-213659->RP-220395",null,94,48,null,null,"Thu 06/01/22","Tue 05/04/22"]
[1866,941113,"   Core part: 4Rx support for NR band n8","NR_4Rx_Bn8_FWA-Core",2,"Rel-17","R4","Mon 13/12/21","Fri 11/03/22",1,"RP-220395","RP-220394","CHTTL",null,"; ",null,94,48,null,null,"Thu 06/01/22","Tue 22/03/22"]
[1867,941213,"   Perf. part: 4Rx support for NR band n8","NR_4Rx_Bn8_FWA-Perf",2,"Rel-17","R4","Mon 13/12/21","Fri 11/03/22",1,"RP-220395","RP-220394","CHTTL",null,"; ",null,94,48,null,null,"Thu 06/01/22","Tue 22/03/22"]
[1868,960071,"   UE Conformance - 4Rx support for NR band n8 ","NR_4Rx_Bn8_FWA-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Thu 22/09/22",1,"RP-222137",null,"ChinaUnicom ",null,"9/9/22: Comp...; 23/9/22: WID:RP-221159->RP-222137",null,96,49,null,null,"Tue 12/07/22","Fri 23/09/22"]
[1869,0,"Rel-17 Self-Organizing (SON)/Autonomous Networks","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1870,860053,"Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC","NR_ENDC_SON_MDT_enh",1,"Rel-17",null,"Mon 16/12/19","Tue 22/03/22",1,"RP-220821",null,"CMCC",null,"affects: LTE, NR. no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes; 6/1/22: WID:RP-193255->RP-213574; 5/4/22: WID:RP-213574->RP-220821",null,86,44,null,null,"Tue 14/01/20","Tue 05/04/22"]
[1871,860153,"   Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR standalone and MR-DC (Multi-Radio Dual Connectivity)","NR_ENDC_SON_MDT_enh-Core",2,"Rel-17","R3","Mon 16/12/19","Tue 22/03/22",1,"RP-213574","RP-220820","Liang LIU, AngeloCentonza","liuliang@chinamobile.com, angelo.centonza@ericsson.com","affects: LTE, NR. no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes; 28/7/20: WID:RP-193255->RP-201281; ; 6/1/22: WID:RP-193255->RP-213574; 20/6/22: Compl:65%",null,86,44,null,null,"Tue 14/01/20","Mon 20/06/22"]
[1872,910029,"Plug and connect support for management of Network Functions ","PACMAN",1,"Rel-17","S5","Thu 18/03/21","Fri 11/03/22",1,"SP-210260",null,"Per Elmdahl, Ericsson ","Per.elmdahl@ericsson.com ","; 11/6/21: 0%->10; 13/9/21: 10%->20; 13/12/21: 20%->70; 13/12/21: FCD:Fri 10/06/->03/22; 12/3/22: 70%->100",28.312999999999999,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1873,870028,"Enhancements of Self-Organizing Networks (SON) for 5G networks ","eSON_5G",1,"Rel-17","S5","Wed 25/03/20","Fri 11/03/22",1,"SP-200194",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","; 13/9/20: 0%->2; 5/12/20: 2%->5; 21/3/21: 5%->15; 11/6/21: 15%->35; 11/6/21: FCD:Thu 17/06/->12/21; 13/9/21: 35%->70; 13/12/21: 70%->90; 13/12/21: FCD:Fri 10/12/->03/22; 21/6/22: 90%->100","28.313; 28.552; 28.541; 28.545 ",87,44,null,null,"Fri 06/12/19","Tue 21/06/22"]
[1874,850032,"Study on autonomous network levels ","FS_ANL",1,"Rel-17","S5","Thu 19/09/19","Mon 14/09/20",1,"SP-190928",null,"China Mobile ","caoxi@chinamobile.com ","; 8/10/19: 28.810 added;; 26/3/20: 0%->50; 26/3/20: FCD:12/03/2020->06/20; 28/6/20: 50%->85; 13/9/20: 85%->100; 13/9/20: FCD:12/06/2020->09/20. 9/4/21: Rel-16->Rel-17","New ; 28.810",85,43,null,null,"Fri 13/09/19","Sun 13/09/20"]
[1875,880027,"Autonomous network levels ","ANL",1,"Rel-17","S5","Fri 12/06/20","Fri 10/12/21",1,"SP-200464",null,"Cao, Xi, China Mobile ","caoxi@chinamobile.com ","28.533; 28.313; 28.535; 28.809; 28.312; 28.541 ; 13/9/20: 0%->5; 13/9/20: FCD:11/12/2020->06/21; 5/12/20: 5%->30; 21/3/21: 30%->50; 11/6/21: 50%->70; 13/9/21: 70%->71; 13/9/21: FCD:Fri 11/06/->12/21; 13/12/21: 71%->100",null,88,45,null,null,"Fri 26/06/20","Mon 13/12/21"]
[1876,0,"Rel-17 Multicast-broadcast Services (MBS) and Mission Critical (MC)","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1877,870014,"Study on Multicast Architecture Enhancements for 5G Media Streaming","FS_5GMS_Multicast",1,"Rel-17","S4","Wed 25/03/20","Fri 11/06/21",1,"SP-200238",null,"Peng Tan, Telus","peng.tan@telus.com","10/6/20: 0%->5; 5/12/20: 5%->25; 5/12/20: FCD:17/12/2020->06/20; 21/3/21: 25%->60; 11/6/21: 60%->100","new",87,44,null,null,"Fri 31/05/19","Fri 11/06/21"]
[1878,810055,"Study on location enhancements for mission critical services ","FS_enhMCLoc",1,"Rel-17","S6","Fri 14/09/18","Thu 12/03/20",1,"SP-190725",null,"Dom Lazara, Motorola Solutions","dom.lazara@motorolasolutions.com","7/12/18: 0%->20¦14/3/19: 20%->45¦14/3/19: FCD:03/19->09/19; 31/5/19: 45%->60; 13/9/19: 60%->70; 13/9/19: FCD:12/09/2019->03/20; 20/9/19: WID:SP-180921->SP-190725; 6/12/19: 70%->75; 28/6/20: 75%->90. Moved from Rel-16; 5/12/20: 90%->100",23.744,81,41,null,null,"Fri 14/09/18","Sat 05/12/20"]
[1879,880006,"Study on Security Aspects of Enhancements for 5G Multicast-Broadcast Services ","FS_5MBS_SEC",1,"Rel-17","S3","Fri 12/06/20","Fri 10/12/21",1,"SP-200351",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","28/7/20: 33.850 added;; 12/9/20: 0%->15; 5/12/20: 15%->30; 19/3/21: 30%->60; 19/3/21: FCD:25/03/2021->06/21; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->100",33.85,88,45,null,null,"Thu 25/06/20","Sat 12/03/22"]
[1880,850035,"Study on Mission Critical services over 5G multicast-broadcast system ","FS_MC5MBS",1,"Rel-17","S6","Thu 19/09/19","Thu 12/03/20",1,"SP-190929",null,"Val Oprescu, AT&T ",null,"; 13/9/19: 0%->20; 8/10/19: 23.774 added;; 8/10/19: 33.524 added;; 6/12/19: 20%->55; 26/3/20: 55%->100","New ; 23.774; 33.524",85,43,null,null,"Fri 13/09/19","Thu 26/03/20"]
[1881,900038,"Multicast-broadcast services in 5G","5MBS",1,"Rel-17",null,"Thu 07/03/19","Sun 03/03/24",1,"SP-201106",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"Thu 03/12/20","NA"]
[1882,830030,"   Study on Architectural enhancements for 5MBS","FS_5MBS",2,"Rel-17","S2","Thu 07/03/19","Fri 12/03/21",1,"SP-200690",null,"Meng Li, Huawei","raymond.limeng@huawei.com","7/6/19: WID:SP-190253->SP-190442; 20/9/19: WID:SP-190442->SP-190625; 6/12/19: 0%->15; 25/3/20: WID:SP-190625->SP-200092; 25/3/20: 15%->35; 26/6/20: FCD:12/06/2020->09/20; 26/6/20: 35%->50; 12/9/20: 50%->65; 12/9/20: FCD:15/09/2020->12/20; 13/9/20: WID: ",23.757000000000001,83,42,null,null,"Thu 14/03/19","Fri 19/03/21"]
[1883,900009,"   Stage 2 for 5MBS","5MBS",2,"Rel-17","S2","Thu 03/12/20","Fri 10/09/21",1,"SP-201106",null,"Meng Li, Huawei ","raymond.limeng@huawei.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->20; 14/6/21: 20%->75; 13/9/21: 75%->85; 10/12/21: 85%->95; 12/3/22: 95%->99; 4/6/22: 99%->100",null,90,46,null,null,"Thu 03/12/20","Sat 04/06/22"]
[1884,920043,"   CT1 aspects of 5MBS","5MBS",2,"Rel-17","C1","Fri 11/06/21","Fri 11/03/22",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","; 13/9/21: 0%->45; 13/12/21: 45%->80; 12/3/22: 80%->95; 22/3/22: 24.575 added;; 22/3/22: WID:CP-212022->CP-220402; 4/6/22: 95%->97","24.501 ; 24.575",92,47,null,null,"Fri 11/06/21","Sat 04/06/22"]
[1885,920044,"   CT3 aspects of 5MBS","5MBS",2,"Rel-17","C3","Fri 11/06/21","Fri 11/03/22",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","; 13/12/21: 0%->40; 13/12/21: WID:CP-212022->CP-213078; 12/3/22: WID:CP-213078->CP-220099; 12/3/22: 40%->65; 22/3/22: 29.580 added;; 4/6/22: 65%->85; 4/6/22: WID:CP-220402->CP-221084; 20/6/22: WID: eSEALCP-221084->CP-220402","29.561;29.525;29.522;29.521;29.520;29.519;29.514;29.513;29.512;29.508 ; 29.580",92,47,null,null,"Fri 11/06/21","Mon 20/06/22"]
[1886,910002,"   CT4 aspect of 5MBS","5MBS",2,"Rel-17","C4","Fri 11/06/21","Fri 11/03/22",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ","UID in 91xx range but presented to CT#92; 2/7/21: 29.532 added;; 10/9/21: WID:CP-211093->CP-212022; 13/9/21: 0%->15; 13/12/21: 15%->75; 7/1/22: 29.537 added;; 12/3/22: 75%->80; 22/3/22: 29.581 added;; 20/6/22: Compl:80%->99%","29.571;29.518;29.510;29.503;29.502;29.281;29.244;23.003 ; 29.532; 29.537; 29.581",91,46,null,null,"Fri 11/06/21","Mon 20/06/22"]
[1887,960067,"   CT6 aspects of 5MBS","5MBS",2,"Rel-17","C6","Fri 11/06/21","Fri 11/03/22",1,"CP-220402",null,"Gulbani, Giorgi, Huawei ","giorgi.gulbani@huawei.com ",null,null,96,49,null,null,"Mon 20/06/22","NA"]
[1888,920023,"   Security Aspects of Enhancements for 5G Multicast-Broadcast Services ","5MBS",2,"Rel-17","S3","Fri 11/06/21","Fri 10/06/22",1,"SP-210420",null,"Longhua Guo, Huawei Technologies ","guolonghua@huawei.com ","; 12/3/22: 0%->95; 12/3/22: FCD:10/12/2021->6/22; 4/6/22: 95%->100",33.500999999999998,92,47,null,null,"Fri 11/06/21","Sat 04/06/22"]
[1889,1000010,"   Charging Aspects for SMF and MB-SMF to Support 5G Multicast-broadcast Services ","5MBS_CH",2,"Rel-18","S5","Thu 08/06/23","Sun 03/03/24",1,"SP-231712",null,"Dong, Jia, China Mobile, ","dongjia at chinamobile dot com ","; 7/9/23: 0%->20; 7/9/23: 20%->30; 8/12/23: 30%->65; 3/1/24: WID:SP-230623->SP-231712; 14/3/24: 65%->100","32.240; 32.255; 32.298; 32.291; 33.279; 33.290",100,51,null,null,"Thu 08/06/23","Thu 14/03/24"]
[1890,850040,"Broadcast / Multicast requirements supporting Mission Critical Services in 5G ","5MBS_eMC",1,"Rel-17","S1","Mon 02/09/19","Thu 12/12/19",1,"SP-190942",null,"Toobe, Jens, BDBOS ","jens.toobe at bdbos.bmi.bund.de ","; 13/9/19: 0%->80; 20/9/19: FCD:19/09/2019->12/19; 6/12/19: 80%->100",22.260999999999999,85,43,null,null,"Fri 13/09/19","Fri 06/12/19"]
[1891,940008,"5G Multicast-Broadcast Protocols ","5MBP3",1,"Rel-17","S4","Fri 10/12/21","Fri 10/06/22",1,"SP-211335",null,"Thomas Stockhammer, Qualcomm Incorporated ","tsto@QTI.QUALCOMM.COM ","; 12/3/22: 0%->40; 12/3/22: FCD:15/03/2022->6/22; 4/6/22: 40%->100","26.346; 26.347; 26.512 ",94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[1892,860048,"NR multicast and broadcast services","NR_MBS",1,"Rel-17","R2","Mon 16/12/19","Tue 12/12/23",1,"RP-220428",null,"Huawei",null,"affects: NR. no Perf. part; 5/4/22: WID:RP-193248->RP-220428",null,86,44,null,null,"Tue 14/01/20","Tue 05/04/22"]
[1893,860148,"   Core part: NR multicast and broadcast services","NR_MBS-Core",2,"Rel-17","R2","Mon 16/12/19","Fri 11/03/22",1,"RP-220428","RP-220407","Huawei",null,"affects: NR. no Perf. part; 28/7/20: WID:RP-193248->RP-201038 ; ",null,86,44,null,null,"Tue 14/01/20","Tue 22/03/22"]
[1894,950061,"   UE Conformance - NR Multicast and Broadcast Services including CT and SA aspects ","NR_MBS_5MBS_5MBUSA-UEConTest",2,"Rel-17","R5","Tue 15/03/22","Tue 12/12/23",1,"RP-220423","RP-233760","Ya Zhao, Huawei Technologies. Co., Ltd","zhaoya@hisilicon.com","tested: REL-17 WI NR_MBS-Core, SA/CT REL-17 WI 5MBS, SA4 REL-17 WI 5MBUSA ; 6/6/22: Compl:0%->5% ; 20/6/22: Rapporteur: Huawei->Ya Zhao, Huawei Technologies. Co., Ltd; Rap eMail: ->zhaoya@hisilicon.com ...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl...",null,95,48,null,null,"Tue 05/04/22","Fri 08/12/23"]
[1895,920051,"Mission Critical Services over 5GS ","MCOver5GS",1,"Rel-17",null,"Wed 16/09/20","Fri 11/03/22",1,"SP-200833",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","25/9/20: 23.289 added;; 5/12/20: 0%->30; 5/12/20: FCD:11/12/2020->03/20; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 30%->65",23.289000000000001,89,45,null,null,"Fri 11/09/20","Sun 21/03/21"]
[1896,890027,"   Stage 2 of MCOver5GS","MCOver5GS",2,"Rel-17","S6","Wed 16/09/20","Tue 15/06/21",1,"SP-200833",null,"Wendler, Ingo, UIC ","ingo.wendler@sbb.ch ","25/9/20: 23.289 added;; 5/12/20: 0%->30; 5/12/20: FCD:11/12/2020->03/20; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 30%->65; 11/6/21: 65%->100",23.289000000000001,89,45,null,null,"Fri 11/09/20","Fri 11/06/21"]
[1897,920007,"   CT1 aspects of MCOver5GS","MCOver5GS",2,"Rel-17","C1","Fri 11/06/21","Fri 11/03/22",1,"CP-211118",null,"Gkatzikis, Lazaros, Nokia ","lazaros(dot)gkatzikis(at)nokia(dot)com ","; 13/12/21: 0%->25; 12/3/22: 25%->40; 4/6/22: 40%->100","24.582;24.581;24.484;24.483;24.481;24.380;24.379;24.282;24.281 ",92,47,null,null,"Fri 11/06/21","Sat 04/06/22"]
[1898,890039,"Mission Critical Data ","eMCData3",1,"Rel-17",null,"Fri 06/12/19","Fri 11/03/22",1,"SP-191106",null,"Shih, Jerry, AT&T ","jerry.shih@att.com ","; 26/3/20: 0%->15; 28/6/20: 15%->45; 13/9/20: 45%->70","23.280; 23.282 ",86,44,null,null,"Fri 06/12/19","Sun 13/09/20"]
[1899,860007,"   Stage 2 of MCData3","eMCData3",2,"Rel-17","S6","Fri 06/12/19","Tue 15/06/21",1,"SP-191106",null,"Shih, Jerry, AT&T ","jerry.shih@att.com ","; 26/3/20: 0%->15; 28/6/20: 15%->45; 13/9/20: 45%->70; 5/12/20: 70%->85; 10/2/21: FCD:11/09/2020->06/21; 21/3/21: 85%->90; 11/6/21: 90%->100","23.280; 23.282 ",86,44,null,null,"Fri 06/12/19","Fri 11/06/21"]
[1900,890038,"   CT aspects of eMCData3","eMCData3",2,"Rel-17","C1","Wed 17/06/20","Fri 11/03/22",1,"CP-201177",null,null,null,"5/12/20: 0%->10; 21/3/21: 10%->40; 11/6/21: 40%->45; 13/9/21: 45%->50; 13/12/21: 50%->65; 12/3/22: FCD:15/09/2021->3/22; 12/3/22: 65%->97; 4/6/22: 97%->100",null,89,45,null,null,"Fri 25/09/20","Sat 04/06/22"]
[1901,820040,"Mission Critical system migration and interconnection ","MCSMI_CT",1,"Rel-17","C1","Thu 13/12/18","Fri 11/03/22",1,"CP-190143",null,"Dom Lazara, Motorola Solutions ","dom.lazara@motorolasolutions.com ","¦18/3/19: FCD:019->12/19¦18/3/19: WID:CP-183244->CP-190143; 13/9/19: 0%->5. 1/7/20: Rel-16->Rel-17 (comments during CT#88e presentation); 13/9/21: 5%->10; 13/12/21: 10%->30; 12/3/22: 30%->90; 12/3/22: FCD:12/12/2019->3/22; 4/6/22: 90%->100","24.379; 24.380; 24.282; 24.481; 24.483; 24.484; 24.482 ",82,42,null,null,"Fri 07/12/18","Sat 04/06/22"]
[1902,890003,"CT aspects of Enhanced Mission Critical Communication Interworking with Land Mobile Radio Systems ","eMCCI_CT",1,"Rel-17","C1","Wed 16/09/20","Wed 08/09/21",1,null,null,"Mike Dolan, FirstNet ","michael.dolan@firstnet.gov ","5/12/20: 0%->60; 13/9/21: 60%->65","29.379; 29.380; 29.582 ",89,45,null,null,"Fri 25/09/20","Mon 13/09/21"]
[1903,0,"Rel-17 Edge computing","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1904,880042,"Architecture for enabling Edge Applications ","EDGEAPP",1,"Rel-17",null,"Thu 07/03/19","Tue 07/06/22",1,"SP-200109",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","25/3/20: WID:SP-191105->SP-200109; 26/3/20: 0%->20","23.222; 23.558",86,44,null,null,"Fri 06/12/19","Thu 26/03/20"]
[1905,830008,"   Study on Application Architecture for enabling Edge Applications","FS_EDGEAPP",2,"Rel-17","S6","Thu 07/03/19","Thu 05/12/19",1,"SP-190065",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","31/5/19: 0%->35; 13/9/19: 35%->70; 6/12/19: 70%->95; 26/3/20: 95%->100","New",83,42,null,null,"Thu 14/03/19","Thu 26/03/20"]
[1906,860006,"   Architecture for enabling Edge Applications ","EDGEAPP",2,"Rel-17","S6","Fri 06/12/19","Tue 15/06/21",1,"SP-200886",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com","25/3/20: WID:SP-191105->SP-200109; 26/3/20: 0%->20; 28/6/20: 20%->50; 13/9/20: 50%->70; 13/9/20: WID:SP-200109->SP-200834; 13/9/20: FCD:11/09/2020->12/20; 25/9/20: WID:SP-200834->SP-200886; 5/12/20: 70%->85; 10/2/21: FCD:11/12/2020->06/21; 21/3/21: 85% ","23.222; 23.558",86,44,null,null,"Fri 06/12/19","Fri 11/06/21"]
[1907,900006,"   CT aspects for Enabling Edge Applications ","EDGEAPP",2,"Rel-17",null,"Mon 07/12/20","Tue 07/06/22",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 11/6/21: WID:CP-203106->CP-211196",null,90,46,null,null,"Sat 05/12/20","Fri 11/06/21"]
[1908,900034,"      CT1 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C1","Mon 07/12/20","Fri 11/03/22",1,"CP-221106",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 21/3/21: 0%->5; 11/6/21: 5%->30; 13/9/21: 30%->55; 13/12/21: 55%->68; 12/3/22: FCD:10/09/2021->3/22; 12/3/22: 68%->85; 4/6/22: 85%->99; 4/6/22: WID:CP-211196->CP-221106",null,90,46,null,null,"Sat 05/12/20","Sat 04/06/22"]
[1909,900035,"      CT3 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C3","Mon 07/12/20","Fri 11/03/22",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","29.222 ; 21/3/21: 0%->20; 11/6/21: FCD:Fri 10/09/->12/21; 11/6/21: 20%->50; 13/9/21: 50%->60; 13/12/21: 60%->75; 12/3/22: FCD:10/12/2021->3/22; 12/3/22: 75%->90",null,90,46,null,null,"Sat 05/12/20","Sat 12/03/22"]
[1910,960066,"      CT4 aspects for EDGEAPP","EDGEAPP",3,"Rel-17","C4","Mon 07/12/20","Tue 07/06/22",1,"CP-211196",null,"Narendranath Durga Tangudu ","n.tangudu@samsung.com ","CT4 chair input (07/06/2022); 3/8/22: 0%->100",null,90,46,null,null,"Mon 20/06/22","Wed 03/08/22"]
[1911,830032,"Study on enhancement of support for Edge Computing in 5GC","FS_enh_EC",1,"Rel-17","S2","Thu 07/03/19","Tue 15/12/20",1,"SP-200093",null,"Hui Ni, Huawei","Hui.ni@huawei.com","6/12/19: 0%->20; 25/3/20: WID:SP-190185->SP-200093; 25/3/20: FCD:05/03/2020->06/20; 25/3/20: 20%->40; 26/6/20: FCD:15/06/2020->09/20; 26/6/20: 40%->60; 12/9/20: 60%->70; 12/9/20: FCD:11/09/2020->12/20; 5/12/20: 70%->100","New",83,42,null,null,"Thu 14/03/19","Sat 05/12/20"]
[1912,910048,"Enhancement of support for Edge Computing in 5G Core network ","eEDGE_5GC",1,"Rel-17",null,"Thu 03/12/20","Fri 11/03/22",1,"SP-201107",null,"Hui Ni, Huawei Technologies ","hui.ni@huawei.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"Thu 03/12/20","NA"]
[1913,900016,"   Stage 2 of eEDGE_5GC","eEDGE_5GC",2,"Rel-17","S2","Thu 03/12/20","Wed 08/09/21",1,"SP-201107",null,"Hui Ni, Huawei Technologies ","hui.ni@huawei.com ","23.501; 23.502; 23.503 ; 19/3/21: 0%->35; 11/6/21: 35%->75; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 75%->95; 10/12/21: 95%->100",null,90,46,null,null,"Thu 03/12/20","Fri 10/12/21"]
[1914,910005,"   CT aspects of 5G eEDGE ","eEDGE_5GC",2,"Rel-17","ct","Thu 18/03/21","Fri 11/03/22",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","10/9/21: WID:CP-211092->CP-212021",null,91,46,null,null,"Thu 18/03/21","Fri 10/09/21"]
[1915,910049,"      CT1 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->40; 13/9/21: 40%->65; 13/12/21: 65%->85; 12/3/22: 85%->95; 4/6/22: 95%->100","24.008; 24.501; 24.526; 27.007",91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[{"$f":"A1916+1","v":1916},910050,"      CT3 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C3","Thu 18/03/21","Fri 11/03/22",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->40; 11/6/21: WID:CP-210284->CP-211092; 13/9/21: 40%->65; 13/12/21: 65%->85; 12/3/22: 85%->100","29.508; 29.512; 29.514; 29.513; 29.522; 29.519; 29.561",91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1917,910051,"      CT4 aspects of 5G eEDGE ","eEDGE_5GC",3,"Rel-17","C4","Thu 18/03/21","Fri 11/03/22",1,"CP-212021",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","11/6/21: 0%->25; 13/9/21: 25%->45; 1/10/21: 29.564 added;; 13/12/21: 45%->80; 12/3/22: 80%->98; 4/6/22: 98%->100","29.244; 29.510; 29.502; 29.503; 29.505; 29.571; 29.564",91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1918,920026,"   Security Aspects of Enhancements of Support for Edge Computing in 5GC ","eEDGE_5GC",2,"Rel-17","S3","Fri 11/06/21","Fri 10/12/21",1,"SP-210423",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","; 13/9/21: 0%->30; 1/10/21: 33.558 added;; 13/12/21: 30%->50; 12/3/22: 50%->100","33.501 ; 33.558",92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[1919,920019,"Edge Computing Management ","ECM",1,"Rel-17","S5","Fri 11/06/21","Fri 11/03/22",1,"SP-210388",null,"Deepanshu Gautam, Samsung ","deepanshu<dot>g<at>samsung<dot>com ","; 13/9/21: 0%->10; 13/12/21: 10%->50; 12/3/22: 50%->90; 4/6/22: 90%->100","28.532;28.531;28.554;28.552;28.541 ",92,47,null,null,"Fri 11/06/21","Sat 04/06/22"]
[1920,880002,"Study on Security Aspects of Enhancement of Support for Edge Computing in 5GC ","FS_eEDGE_Sec",1,"Rel-17","S3","Fri 12/06/20","Fri 10/12/21",1,"SP-200347",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","12/9/20: 0%->15; 5/12/20: 15%->50; 19/3/21: FCD:25/03/2021->06/21; 19/3/21: 50%->60; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 75%->85; 12/3/22: 85%->100",33.838999999999999,88,45,null,null,"Thu 25/06/20","Sat 12/03/22"]
[1921,940009,"Edge Extensions to 5GMS Stage 3 ","5GMS_EDGE_3",1,"Rel-17","S4","Fri 10/12/21","Fri 10/06/22",1,"SP-211336",null,"Bouazizi, Imed, Qualcomm Inc. ","bouazizi@qti.qualcomm.com ","; 12/3/22: 0%->60; 12/3/22: FCD:11/03/2022->6/22; 4/6/22: 60%->100","26.512; ",94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[1922,930034,"Charging aspects of Edge Computing ","EDGE_CH",1,"Rel-17","S5","Thu 25/06/20","Fri 11/03/22",1,"SP-210861",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 22/3/22: 32.257 added;","32.240; 32.291; 32.298; 32.297 ; 32.257",93,47,null,null,"Fri 10/09/21","Tue 22/03/22"]
[1923,880030,"   Study on charging aspects of Edge Computing ","FS_EDGE_CH",2,"Rel-17","S5","Thu 25/06/20","Fri 10/12/21",1,"SP-200467",null,"Yizhi Yao, Intel ","yizhi<dot>yao<at>intel<dot>com ","5/12/20: 0%->30; 21/3/21: 30%->60; 21/3/21: FCD:19/03/2021->09/21; 13/9/21: 60%->90; 13/9/21: FCD:Wed 08/09/->12/21; 21/6/22: 90%->100",28.815000000000001,88,45,null,null,"Fri 26/06/20","Tue 21/06/22"]
[1924,930011,"   Charging aspects of Edge Computing ","EDGE_CH",2,"Rel-17","S5","Fri 10/09/21","Fri 11/03/22",1,"SP-210861",null,"Yao, Yizhi, Intel ","yizhi<dot>yao<at>intel<dot>com ","; 12/3/22: 0%->70; 4/6/22: 70%->100","32.240; 32.291; 32.298; 32.297 ",93,47,null,null,"Fri 10/09/21","Sat 04/06/22"]
[1925,870029,"Study on enhancements of edge computing management ","FS_eEDGE_Mgt",1,"Rel-17","S5","Wed 25/03/20","Wed 08/09/21",1,"SP-200195",null,"Joey Chou, Intel ","joey<dot>chou<at>intel<dot>com ","13/9/20: 0%->15; 5/12/20: 15%->25; 5/12/20: FCD:17/12/2020->03/20; 21/3/21: 25%->75; 11/6/21: 75%->90; 11/6/21: FCD:Fri 12/03/->09/21; 13/9/21: 90%->100","New",87,44,null,null,"Fri 06/12/19","Mon 13/09/21"]
[1926,0,"Rel-17 Slicing","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1927,920058,"Rel-17 Enhancements of 3GPP Northbound Interfaces and Application Layer APIs ","NBI17",1,"Rel-17",null,"Fri 11/06/21","Fri 11/03/22",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","01/22: Rapp changed from yanyali@huawei.com ; 28/4/22: WID:CP-211197->CP-220058",null,92,47,null,null,"Fri 11/06/21","Thu 28/04/22"]
[1928,920013,"   CT1 aspects of NBI17 ","NBI17",2,"Rel-17","C1","Fri 11/06/21","Fri 11/03/22",1,"CP-211197",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 13/9/21: 0%->85; 13/12/21: 85%->95; 12/3/22: 95%->99; 4/6/22: 99%->100; 20/6/22: WID: CP-220058->CP-211197",24.558,92,47,null,null,"Fri 11/06/21","Mon 20/06/22"]
[1929,920053,"   CT3 aspects of NBI17 ","NBI17",2,"Rel-17","C3","Fri 11/06/21","Fri 11/03/22",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 11/6/21: 0%->35; 13/9/21: 35%->65; 13/12/21: 65%->85; 13/12/21: WID:CP-211197->CP-213262; 12/3/22: 85%->100; 12/3/22: FCD:10/03/2023->3/22","29.558;29.549;29.522;29.486;29.343;29.222;29.122;29.116 ",92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[1930,920054,"   CT4 aspects of NBI17 ","NBI17",2,"Rel-17","C4","Fri 11/06/21","Fri 11/03/22",1,"CP-220058",null,"Abdessamad El Moatamid, Huawei ","abdessamad.el.moatamid@huawei.com","; 12/3/22: 0%->100","29.518;29.503;29.272;29.336;29.571 ",92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[1931,920012,"Enhancement of 5G PCC related services in Rel-17 ","en5GPccSer17",1,"Rel-17","C3","Fri 11/06/21","Fri 11/03/22",1,"CP-211193",null,"Xiaoyun Zhou, Huawei ","zhouxiaoyun8@huawei.com ","; 11/6/21: 0%->20; 13/9/21: 20%->35; 13/12/21: 35%->70; 12/3/22: 70%->100","29.214;29.519;29.594;29.521;29.514;29.513;29.512 ",92,47,null,null,"Fri 11/06/21","Sat 12/03/22"]
[1932,900032,"Enhancement of Network Slicing Phase 2 ","eNS_Ph2",1,"Rel-17",null,"Thu 19/09/19","Tue 06/06/23",1,"SP-200976",null,"ZTE, Jinguo Zhu ","Zhu dot Jinguo at zte dot com dot cn ","23.501; 23.502; 23.503 ",null,90,46,null,null,"Thu 03/12/20","NA"]
[1933,850010,"   Study on Enhancement of Network Slicing Phase 2 ","FS_eNS_Ph2",2,"Rel-17","S2","Thu 19/09/19","Fri 12/03/21",1,"SP-190931",null,"So, Tricci, ZTE ","tso@ztetx.com ","; 8/10/19: 23.700-40 added;; 6/12/19: 0%->15; 25/3/20: 15%->35; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 35%->55; 12/9/20: 55%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 90%->100","New ; 23.700-40",85,43,null,null,"Fri 13/09/19","Fri 19/03/21"]
[1934,900011,"   Stage 2 for Enhancement of Network Slicing Phase 2 ","eNS_Ph2",2,"Rel-17","S2","Thu 03/12/20","Wed 08/09/21",1,"SP-200976",null,"ZTE, Jinguo Zhu ","Zhu dot Jinguo at zte dot com dot cn ","23.501; 23.502; 23.503 ; 19/3/21: 0%->5; 14/6/21: 5%->85; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 85%->97; 10/12/21: 97%->99; 22/3/22: 99%->100",null,90,46,null,null,"Thu 03/12/20","Tue 22/03/22"]
[1935,920059,"   Stage 3 for Enhancement of Network Slicing Phase 2 ","eNS_Ph2",2,"Rel-17","ct","Thu 18/03/21","Tue 06/06/23",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","1/10/21: WID:CP-210288->CP-211091",null,91,46,null,null,"Thu 18/03/21","Fri 01/10/21"]
[1936,910041,"      CT1 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->45; 13/12/21: 45%->80; 12/3/22: 80%->100",24.501000000000001,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1937,910042,"      CT3 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C3","Thu 18/03/21","Fri 11/03/22",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->40; 13/12/21: 40%->80; 12/3/22: 80%->96; 4/6/22: 96%->100",29.521999999999998,91,46,null,null,"Thu 18/03/21","Sat 04/06/22"]
[1938,910043,"      CT4 aspects of eNS_Ph2","eNS_Ph2",3,"Rel-17","C4","Thu 18/03/21","Fri 11/03/22",1,"CP-211091",null,"Hannah Wang, ZTE ","wang.menghan@zte.com.cn ","11/6/21: 0%->30; 13/9/21: 30%->45; 1/10/21: WID:CP-210288->CP-211091; 13/12/21: 45%->80; 12/3/22: 80%->100","29.510; 29.518; 29.502; 29.524",91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1939,950065,"      UE Conformance - Enhancement of Network Slicing Phase 2 ","eNS_Ph2-UEConTest",3,"Rel-17","R5","Tue 15/03/22","Tue 06/06/23",1,"RP-230289","RP-230286","Danni Song, Xiaozhong Chen, CMCC, CATT","songdan@chinamobile.com, chenxiaozhong@catt.cn","tested: SA/CT REL-17 WI eNS_Ph2 (note: This WI is not testing NR_slice-Core) 6/6/22: Compl:0%->10% ; ; 20/6/22: Rapporteur: CMCC->Luting Kong, Xiaozhong Chen, CMCC, CATT; Rap eMail: ->kongluting@chinamobile.com, chenxiaozhong@catt.cn ; ;...; 9/12/22:...",null,95,48,null,null,"Tue 05/04/22","Wed 07/06/23"]
[1940,911007,"Enhancement of RAN slicing for NR ","NR_slice",1,"Rel-17","R2","Thu 07/03/19","Fri 22/09/23",1,"RP-221377",null,"CMCC ",null,"follow-up WI of RAN2 REL-17 SI FS_NR_slice; no Perf. part ; 2/7/21: WID:RP-210912->RP-211290; 29/9/21: WID:RP-211290->RP-212534; 12/7/22: WID:RP-212534->RP-221377",null,91,46,null,null,"Wed 07/04/21","Tue 12/07/22"]
[1941,911107,"   Core part: Enhancement of RAN slicing for NR ","NR_slice-Core",2,"Rel-17","R2","Fri 12/03/21","Wed 22/06/22",1,"RP-221377","RP-221375","Ningyu Chen, CMCC","chenningyu@chinamobile.com","follow-up WI of RAN2 REL-17 SI FS_NR_slice; no Perf. part ; 20/6/22: FCD:12/03/2022->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221375; Rapporteur: CMCC->Ningyu Chen, CMCC; Rap eMail: ->chenningyu@chinamobile.com; ",null,91,46,null,null,"Wed 07/04/21","Mon 20/06/22"]
[1942,960078,"   UE Conformance - Enhancement of RAN slicing for NR ","NR_slice-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Fri 22/09/23",1,"RP-223067","RP-232242","Danni Song, CMCC","songdan@chinamobile.com","9/9/22: Comp...; 23/9/22: WID:RP-221364->RP-222118; 9/12/22: FCD:22/09/2022->01/09/2023; Compl:12%->13%; Stat Rep: ->RP-223068; Rapporteur: CMCC->Danni Song, CMCC; Rap eMail: ->songdan@chinamobile.com; 9/1/23: WID:RP-222118->RP-223067; 17...; ",null,96,49,null,null,"Tue 12/07/22","Wed 06/09/23"]
[1943,960006,"   CT1 aspects of enhancement of RAN Slicing for NR ","NRslice",2,"Rel-17","C1","Fri 03/06/22","Mon 20/06/22",1,"C1-221266",null,"Chen Xu, China Mobile ","chenxu@chinamobile.com ","; 4/6/22: 0%->100","24.501; 29.531; 29.571 ",96,49,null,null,"Fri 03/06/22","Sat 04/06/22"]
[1944,960069,"   CT4 aspects on enhancement of RAN slicing for NR","NRslice",2,"Rel-17","C4","Thu 07/03/19","Thu 07/03/19",1,"C1-221266",null,"Chen Xu, China Mobile ","chenxu@chinamobile.com ","; 4/6/22: 0%->100; 3/8/22: 99%->100","24.501; 29.531; 29.571 ",96,49,null,null,"Mon 20/06/22","Wed 03/08/22"]
[1945,860022,"Study on network slice management enhancement ","FS_NSMEN",1,"Rel-17","S5","Fri 06/12/19","Fri 10/12/21",1,"SP-200766",null,"Brendan Hassett, Huawei Technologies Sweden AB, ","brendan.t.hassett@huawei.com","13/9/20: 0%->5; 13/9/20: WID:SP-191192->SP-200766; 5/12/20: 5%->20; 21/3/21: 20%->40; 11/6/21: 40%->80; 11/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 80%->90; 13/9/21: FCD:Wed 08/09/->12/21; 13/12/21: 90%->100",null,86,44,null,null,"Fri 06/12/19","Mon 13/12/21"]
[1946,950038,"Network Slice charging based on 5G Data Connectivity ","NETSLICE_DC_CH",1,"Rel-17","S5","Thu 10/03/22","Fri 11/03/22",1,"SP-220158",null,"MATRIXX Software, Gerald Görmer ","Gerald dot Goermer at Matrixx dot com ","; 12/3/22: 0%->100",32.255000000000003,95,48,null,null,"Thu 10/03/22","Sat 12/03/22"]
[1947,0,"Rel-17 Multi-(U)SIM","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1948,840049,"Support for Multi-USIM Devices ","MUSIM",1,"Rel-17",null,"Thu 07/03/19","Fri 11/03/22",1,"SP-190309",null,"Liao, Ellen C, Intel ","ellen.c.liao@intel.com ",null,"22.261; 22.278; 22.101 ",84,43,null,null,"Fri 31/05/19","NA"]
[1949,830019,"   Study on MUSIM","FS_MUSIM",2,"Rel-17","S1","Thu 07/03/19","Fri 06/09/19",1,"SP-190091","-","Liao, Ellen C, Intel","ellen.c.liao@intel.com","14/3/19: 0%->5; 31/5/19: 5%->95; 13/9/19: 95%->98; 6/12/19: 98%->100","New",83,42,null,null,"Thu 14/03/19","Fri 06/12/19"]
[1950,840040,"   Stage 1 of MUSIM","MUSIM",2,"Rel-17","S1","Thu 06/06/19","Thu 12/12/19",1,"SP-190309",null,"Liao, Ellen C, Intel ","ellen.c.liao@intel.com ","13/9/19: 0%->50; 6/12/19: 50%->100","22.261; 22.278; 22.101 ",84,43,null,null,"Fri 31/05/19","Fri 06/12/19"]
[1951,820012,"   Study on Stage 2 (System Enablers) for MUSIM","FS_MUSIM",2,"Rel-17","S2","Thu 07/03/19","Fri 12/03/21",1,"SP-200297",null,"Sašo Stojanovski, Intel ","saso stojanovski intel com)","21/3/19: WID:SP-181251->SP-190248; 6/12/19: 0%->29; 25/3/20: WID:SP-190248->SP-200297; 25/3/20: 29%->45; 26/6/20: FCD:11/06/2020->09/20; 26/6/20: 45%->60; 12/9/20: 60%->80; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 80%->90; 5/12/20: FCD:15/12/2020->03/2 ",23.760999999999999,82,42,null,null,"Thu 06/12/18","Mon 13/09/21"]
[1952,900013,"   System enablers for Multi-USIM devices ","MUSIM",2,"Rel-17","S2","Thu 03/12/20","Wed 08/09/21",1,"SP-210091",null,"Sašo Stojanovski, Intel ","saso stojanovski intel com ","23.501; 23.502; 23.401; 23.228 ; 19/3/21: 0%->20; 13/6/21: WID:SP-200978->SP-210091; 14/6/21: 20%->90; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->98; 10/12/21: 98%->100",null,90,46,null,null,"Thu 03/12/20","Fri 10/12/21"]
[1953,910015,"   CT aspects of MUSIM","MUSIM",2,"Rel-17","ct","Thu 18/03/21","Fri 11/03/22",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 10/9/21: WID:CP-210280->CP-212102; 01/22: rapporteur changed from Vivek Gupta","24.501; 24.301; 27.007; 29.274 ",91,46,null,null,"Thu 18/03/21","Fri 10/09/21"]
[1954,910063,"      CT1 aspects of Enabling Multi-USIM Devices ","MUSIM",3,"Rel-17","C1","Thu 18/03/21","Fri 11/03/22",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 11/6/21: 0%->40; 13/9/21: 40%->65; 13/12/21: 65%->90; 12/3/22: 90%->100",null,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1955,910064,"      CT4 aspects of Enabling Multi-USIM Devices ","MUSIM",3,"Rel-17","C4","Thu 18/03/21","Fri 11/03/22",1,"CP-212102",null,"Thomas Luetzenkirchen, Intel","thomas.luetzenkirchen@intel.com","; 11/6/21: 0%->40; 13/12/21: 40%->90; 12/3/22: 90%->100",null,91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1956,900017,"   Study on the security of the system enablers for devices having multiple Universal Subscriber Identity Modules (USIM) ","FS_MUSIM_SEC",2,"Rel-17","S3","Fri 04/12/20","Fri 10/12/21",1,"SP-201018",null,"Abhijeet Kolekar, Intel Corporation ","abhijeet.kolekar@intel.com ","5/12/20: 0%->10; 10/2/21: 33.873 added;; 19/3/21: 10%->35; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 35%->96; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 96%->100",33.872999999999998,90,46,null,null,"Fri 04/12/20","Mon 13/09/21"]
[1957,860063,"Support for Multi-SIM devices for LTE/NR","LTE_NR_MUSIM",1,"Rel-17",null,"Mon 09/12/19","Fri 22/09/23",1,"RP-213679",null,"Vivo",null,"28/7/20: WID:RP-193263->RP-201309. 6/1/21: WID:RP-193263->RP-202895; 7/4/21: WID:RP-202895->RP-210316; 2/7/21: WID:RP-210316->RP-211561; 29/9/21: WID:RP-211561->RP-212610; 6/1/22: WID:RP-212610->RP-213679",null,86,44,null,null,"Wed 10/06/20","Thu 06/01/22"]
[1958,860163,"   Core part: Support for Multi-SIM devices for LTE/NR","LTE_NR_MUSIM-Core",2,"Rel-17","R2","Mon 09/12/19","Tue 22/03/22",1,"RP-213679","RP-220603","Xiaodong Yang","Yangxiaodong5g@vivo.com","20/6/22: FCD:17/06/2021->22/03/2023; Compl:0%->100%; Stat Rep: ->RP-220603; Rapporteur: Vivo->Xiaodong Yang; Rap eMail: ->Yangxiaodong5g@vivo.com20/6/22: 0%->100",null,86,44,null,null,"Wed 10/06/20","Mon 20/06/22"]
[1959,950060,"   UE Conformance - Multi-SIM devices for LTE/NR ","LTE_NR_MUSIM_plus_CT1-UEConTest",2,"Rel-17","R5","Tue 15/03/22","Fri 22/09/23",1,"RP-220127","RP-231824","Jing Zhao, China telecom","Zhaoj16@chinatelecom.cn","tested: REL-17 WI LTE_NR_MUSIM-Core and REL-17 CT1 WI MUSIM 6/6/22: Compl:0%->5% 6/6/ ; 20/6/22: Rapporteur: China Telecom->Jing Zhao, China telecom; Rap eMail: ->Zhaoj16@chinatelecom.cn12/7/22: WID:RP-220127->RP-221193; 23/9/22: 5%->25; 23/9/22: FCD:...",null,95,48,null,null,"Tue 05/04/22","Wed 06/09/23"]
[1960,0,"Rel-17 other cross-TSG Features","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[1961,930030,"Support of the 5GMSG Service ","FS_5GMARCH",1,"Rel-17",null,"Thu 06/06/19","Fri 10/12/21",1,"SP-200835",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","13/9/19: 0%->20; 8/10/19: 23.700-24 added;; 6/12/19: 20%->35; 26/3/20: 35%->40; 28/6/20: 40%->50; 13/9/20: 50%->65; 13/9/20: WID:SP-190559->SP-200835; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 65%->80; 21/3/21: 80%->95; 11/6/21: 95%->100","23.700-24",84,43,null,null,"Fri 31/05/19","Fri 11/06/21"]
[1962,840036,"   Study on support of the 5GMSG Service ","FS_5GMARCH",2,"Rel-17","S6","Thu 06/06/19","Fri 11/12/20",1,"SP-200835",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","13/9/19: 0%->20; 8/10/19: 23.700-24 added;; 6/12/19: 20%->35; 26/3/20: 35%->40; 28/6/20: 40%->50; 13/9/20: 50%->65; 13/9/20: WID:SP-190559->SP-200835; 13/9/20: FCD:12/06/2020->12/20; 5/12/20: 65%->80; 21/3/21: 80%->95; 11/6/21: 95%->100","23.700-24",84,43,null,null,"Fri 31/05/19","Fri 11/06/21"]
[1963,890010,"   Study on security aspects of the 5GMSG Service (St1 in Rel16)","FS_SEC_5GMSG",2,"Rel-17","S3","Wed 16/09/20","Fri 10/12/21",1,"SP-200878",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","25/9/20: WID:SP-200717->SP-200878; 5/12/20: 0%->10; 19/3/21: 10%->40; 11/6/21: 40%->45; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 45%->75; 12/3/22: 75%->100",33.862000000000002,89,45,null,null,"Thu 10/09/20","Sat 12/03/22"]
[1964,930005,"   Security aspects of the 5GMSG Service ","5GMSG",2,"Rel-17","S3","Fri 10/09/21","Fri 10/12/21",1,"SP-210835",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 12/3/22: 0%->100",33.500999999999998,93,47,null,null,"Fri 10/09/21","Sat 12/03/22"]
[1965,930040,"Application Architecture for MSGin5G Service ","5GMARCH",1,"Rel-17",null,"Wed 16/09/20","Fri 11/03/22",1,"SP-200832",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","Stage 1 in Rel-16, UID 810014",23.553999999999998,89,45,null,null,"Fri 11/09/20","Fri 11/06/21"]
[1966,890026,"   Application Architecture for MSGin5G Service ","5GMARCH",2,"Rel-17","S6","Wed 16/09/20","Tue 15/06/21",1,"SP-200832",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","25/9/20: 23.554 added;; 5/12/20: 0%->5; 10/2/21: FCD:12/03/2021->06/21; 21/3/21: 5%->25; 11/6/21: 25%->75; 13/9/21: 75%->90; 13/12/21: 90%->100",23.553999999999998,89,45,null,null,"Fri 11/09/20","Mon 13/12/21"]
[1967,930004,"   CT aspects for enabling MSGin5G Service ","5GMARCH",2,"Rel-17","ct","Fri 10/09/21","Fri 11/03/22",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ",null,29.222000000000001,93,47,null,null,"Fri 10/09/21","NA"]
[1968,930041,"      CT1 aspects for enabling MSGin5G Service ","5GMARCH",3,"Rel-17","C1","Fri 10/09/21","Fri 11/03/22",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 1/10/21: 24.538 added;; 13/12/21: 0%->30; 12/3/22: 30%->75; 4/6/22: 75%->100",24.538,93,47,null,null,"Fri 10/09/21","Sat 04/06/22"]
[1969,930042,"      CT3 aspects for enabling MSGin5G Service ","5GMARCH",3,"Rel-17","C3","Fri 10/09/21","Fri 11/03/22",1,"CP-212106",null,"Liu, Yue, China Mobile ","liuyueyjy@chinamobile.com ","; 1/10/21: 29.538 added;; 13/12/21: 0%->30; 12/3/22: 30%->100",29.538,93,47,null,null,"Fri 10/09/21","Sat 12/03/22"]
[1970,930002,"IMS voice service support and network usability guarantee for UE s E-UTRA capability disabled scenario in SA 5GS ","ING_5GS",1,"Rel-17","ct","Wed 29/09/21","Thu 06/06/24",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ",null,null,93,47,null,null,"Wed 29/09/21","NA"]
[1971,930047,"   CT1 aspects of ING_5GS","ING_5GS",2,"Rel-17","C1","Wed 29/09/21","Fri 11/03/22",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","13/12/21: 0%->85; 12/3/22: 85%->100","24.301; 24.368; 24.501",93,47,null,null,"Wed 29/09/21","Sat 12/03/22"]
[1972,930046,"   CT6 aspects of ING_5GS","ING_5GS",2,"Rel-17","C6","Wed 29/09/21","Fri 11/03/22",1,"CP-212231",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","12/3/22: 0%->100; 4/6/22: 100%->",31.102,93,47,null,null,"Wed 29/09/21","Sat 04/06/22"]
[1973,1000052,"   UE Conformance - ING_5GS","ING_5GS-UEConTest",2,"Rel-17","R5","Thu 08/06/23","Thu 06/06/24",1,"RP-230873","RP-240910","Jing Zhao, China telecom","Zhaoj16@chinatelecom.cn","6/9/23: FCD:06/06/2024->03/03/2024; Compl:0%->5%; Stat Rep: ->RP-231826; Rapporteur: China Telecom->Jing Zhao, China telecom; Rap eMail: ->Zhaoj16@chinatelecom.cn; ; 14/3/24: FCD:03/03/2024->06/06/2024; Compl:5%->74%; Stat Rep: RP-231826->RP-240115; ; ...",null,100,51,null,null,"Thu 29/06/23","Thu 13/06/24"]
[1974,930031,"User Consent for 3GPP services ","UC3S",1,"Rel-17",null,"Wed 16/09/20","Thu 09/06/22",1,"SP-200885",null,"Rong Wu, Huawei Technologies ","raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21",33.866999999999997,89,45,null,null,"Fri 25/09/20","Fri 11/06/21"]
[1975,890037,"   Study on User Consent for 3GPP services ","FS_UC3S",2,"Rel-17","S3","Wed 16/09/20","Thu 09/06/22",1,"SP-200885",null,"Rong Wu, Huawei Technologies ","raina.wu@huawei.com ","5/12/20: 0%->5; 19/3/21: 5%->40; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 40%->50; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 50%->80; 12/3/22: 80%->95; 12/3/22: FCD:10/12/2021->6/22; 31/3/23: 95%->100",33.866999999999997,89,45,null,null,"Fri 25/09/20","Fri 31/03/23"]
[1976,930006,"   Security aspects on User Consent for 3GPP services ","UC3S_SEC",2,"Rel-17","S3","Fri 10/09/21","Thu 09/06/22",1,"SP-210836",null,"Rong Wu, Huawei Technologies ","Raina.wu@huawei.com ","; 13/12/21: 0%->85; 12/3/22: 85%->95; 12/3/22: FCD:10/12/2021->6/22; 31/3/23: 95%->100",33.500999999999998,93,47,null,null,"Fri 10/09/21","Fri 31/03/23"]
[1977,910025,"User Plane Integrity Protection for LTE ","UPIP_SEC_LTE",1,"Rel-17","S3","Thu 18/03/21","Fri 10/12/21",1,"SP-210105",null,"Evans, Tim, Vodafone ","tim.evans1@vodafone.com ","; 11/6/21: 0%->85; 11/6/21: FCD:Fri 11/06/->12/21; 13/12/21: 85%->100","33.401; 33.501 ",91,46,null,null,"Thu 18/03/21","Mon 13/12/21"]
[1978,941011,"User Plane Integrity Protection support for EPC connected architectures","UPIP_SEC_LTE-RAN",1,"Rel-17","R3","Mon 13/12/21","Fri 01/03/24",1,"RP-230070",null,"Vodafone",null,"no Perf. part; UPIP_SEC_LTE is an SA3 REL-17 WI; WI is addressing LTE and LTE link in EN-DC case; 29/3/23: WID:RP-213669->RP-230070",null,94,48,null,null,"Thu 06/01/22","Wed 29/03/23"]
[1979,941111,"   Core part: User Plane Integrity Protection support for EPC connected architectures","UPIP_SEC_LTE-RAN-Core",2,"Rel-17","R3","Mon 13/12/21","Tue 22/03/22",1,"RP-230070",null,"Vodafone",null,"no Perf. part; UPIP_SEC_LTE is an SA3 REL-17 WI; WI is addressing LTE and LTE link in EN-DC case; 4/6/22: 0%->100",null,94,48,null,null,"Thu 06/01/22","Sat 04/06/22"]
[{"$f":"A1980+1","v":1980},970074,"   UE Conformance - User Plane Integrity Protection support for EPC connected architectures (incl. CT/SA aspects) ","UPIP_SEC_LTE-RAN-UEConTest",2,"Rel-17","R5","Thu 08/09/22","Fri 01/03/24",1,"RP-240048","RP-240047","Petra RAUER, Vodafone","Petra[dot]Rauer[at]Vodafone[dot]com","17/3/23: FCD:09/09/2023->08/09/2023; Compl:0%->5%; Stat Rep: ->RP-230071; Rapporteur: Vodafone->Petra RAUER, Vodafone; Rap eMail: ->Petra[dot]Rauer[at]Vodafone[dot]com; ...; 6/9/23: FCD:09/09/2023->12/12/2023; Compl:28%->62%; Stat Rep: RP-230071->RP-2...",null,97,49,null,null,"Fri 23/09/22","Tue 02/04/24"]
[1981,910007,"Start of Pause of Charging via User Plane ","SPOCUP",1,"Rel-17","C4","Thu 18/03/21","Fri 11/06/21",1,"CP-210076",null,"YONG, YANG, Ericsson, frank ","yong.yang@ericsson.com ","; 21/3/21: 0%->85; 11/6/21: 85%->100","29.244; 29.060; 29.281; 29.274; 29.502 ",91,46,null,null,"Thu 18/03/21","Fri 11/06/21"]
[1982,920060,"NPN support of PWS ","NPN_PWS",1,"Rel-17","S1","Sat 12/06/21","Sat 12/06/21",1,"SP-210585",null,"Francesco Pica, Qualcomm","fpica <at> qti.qualcomm.com","11/3/22: 0%->100",22.260999999999999,92,47,null,null,"Thu 12/08/21","Fri 11/03/22"]
[1983,940048,"Enhancements of 3GPP profiles for cryptographic algorithms and security protocols ","eCryptPr",1,"Rel-17",null,"Thu 18/03/21","Fri 11/03/22",1,"SP-210107",null,"Pinar Comak, Ericsson ","pinar.comak@ericsson.com ","; 11/6/21: 0%->35; 11/6/21: FCD:Fri 10/09/->12/21; 13/9/21: 35%->85","33.141; 33.203; 33.210; 33.220; 33.222; 33.310; 33.328; 33.501 ",91,46,null,null,"Thu 18/03/21","Mon 13/09/21"]
[1984,910024,"   Stage 2 for eCryptPr","eCryptPr",2,"Rel-17","S3","Thu 18/03/21","Fri 10/12/21",1,"SP-210107",null,"Pinar Comak, Ericsson ","pinar.comak@ericsson.com ","; 11/6/21: 0%->35; 11/6/21: FCD:Fri 10/09/->12/21; 13/9/21: 35%->85; 13/12/21: 85%->95; 12/3/22: 95%->100","33.141; 33.203; 33.210; 33.220; 33.222; 33.310; 33.328; 33.501 ",91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[1985,940007,"   Stage 3 CT1 for eCryptPr","eCryptPr",2,"Rel-17","C1","Fri 10/12/21","Fri 11/03/22",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 12/3/22: 0%->97; 4/6/22: 97%->100","24.109; 24.141; 24.229; 24.259; 24.424; 24.481; 24.482; 24.486; 24.545; 24.547; 24.548; 24.623",94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[1986,940049,"   Stage 3 CT3 for eCryptPr","eCryptPr",2,"Rel-17","C3","Fri 10/12/21","Fri 11/03/22",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 12/3/22: 0%->100","29.079; 29.116; 29.122; 29.155; 29.201; 29.222; 29.486; 29.517; 29.522; 29.549",94,48,null,null,"Fri 10/12/21","Sat 12/03/22"]
[1987,940050,"   Stage 3 CT4 for eCryptPr","eCryptPr",2,"Rel-17","C4","Fri 10/12/21","Fri 11/03/22",1,"CP-213083",null,"Biondic, Nevenka, Ericsson ","nevenka.biondic@ericsson.com ","; 7/1/22: 0%->60; 12/3/22: 60%->90; 4/6/22: 90%->100","23.008; 29.228; 29.229; 29.240; 23.333; 23.334; 29.334; 29.335 ",94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[1988,950043,"AKMA TLS protocol profiles ","AKMA_TLS",1,"Rel-17","S3","Fri 11/06/21","Fri 10/06/22",1,"SP-210424",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 13/12/21: 0%->95; 13/12/21: FCD:Fri 10/09/->12/21; 4/6/22: 95%->100; 12/9/22: 100%->",33.534999999999997,92,47,null,null,"Fri 11/06/21","Mon 12/09/22"]
[1989,920027,"   Security aspects of AKMA_TLS","AKMA_TLS",2,"Rel-17","S3","Fri 11/06/21","Fri 10/06/22",1,"SP-210424",null,"Escott, Adrian, Qualcomm Incorporated ","aescott@qti.qualcomm.com ","; 13/12/21: 0%->95; 13/12/21: FCD:Fri 10/09/->12/21; 12/3/22: FCD:15/12/2021->6/22; 4/6/22: 100%->100",33.534999999999997,92,47,null,null,"Fri 11/06/21","Sat 04/06/22"]
[1990,950010,"   CT aspects of AKMA_TLS","AKMA_TLS",2,"Rel-17","C1","Thu 10/03/22","Fri 11/03/22",1,"CP-220307",null,"Chaponniere, Lena, Qualcomm Incorporated ","lguellec@qti.qualcomm.com ","; 12/3/22: 0%->80; 4/6/22: 100%->100",24.109000000000002,95,48,null,null,"Thu 10/03/22","Sat 04/06/22"]
[1991,900002,"Restoration of PDN Connections in PGW-C/SMF Set ","RPCPSET",1,"Rel-17","C4","Mon 07/12/20","Fri 18/12/20",1,"CP-203020",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","23.007; 29.274; 29.303; 23.003 ; 5/12/20: 0%->100; 5/12/20: 0%->100",null,90,46,null,null,"Sat 05/12/20","Sat 05/12/20"]
[1992,900037,"Enhancement of Inter-PLMN Roaming ","EoIPR",1,"Rel-17","C4","Mon 07/12/20","Fri 11/03/22",1,"CP-203021",null,"Caixia Qi, Huawei ","Caixia.qi@huawei.com ","29.510; 29.531; 29.573 ; 21/3/21: 0%->30; 11/6/21: 30%->35; 13/12/21: 35%->80; 13/12/21: FCD:Fri 10/09/->03/22; 12/3/22: 80%->100",null,90,46,null,null,"Sat 05/12/20","Sat 12/03/22"]
[1993,911037,"Reliable Data Service Serialization Indication ","RDSSI",1,"Rel-17",null,"Thu 07/03/19","Fri 10/09/21",1,"SP-190446",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ",null,"23.682; 23.501; 23.502 ",84,43,null,null,"Fri 31/05/19","Thu 06/06/19"]
[1994,840017,"   Stage 2 of RDSSI","RDSSI",2,"Rel-17","S2","Thu 09/05/19","Thu 06/06/19",1,"SP-190446",null,"Starsinic, Michael, Convida Wireless LLC ","starsinic.michael@convidawireless.com ","6/6/19: 0%->100. 9/4/21: Rel-16->Rel-17","23.682; 23.501; 23.502 ",84,43,null,null,"Fri 31/05/19","Thu 06/06/19"]
[1995,900005,"   CT aspects of RDSSI","RDSSI",2,"Rel-17","C1","Thu 07/03/19","Fri 10/09/21",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","24.250; 29.122 ; 21/3/21: 0%->100",null,90,46,null,null,"Sat 05/12/20","Sun 21/03/21"]
[1996,970050,"      CT1 aspects of RDSSI","RDSSI",3,"Rel-17","C1","Thu 07/03/19","Fri 10/09/21",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","23/9/22: 99%->100",null,97,49,null,null,"Wed 07/09/22","Fri 23/09/22"]
[1997,970051,"      CT3 aspects of RDSSI","RDSSI",3,"Rel-17","C3","Thu 07/03/19","Fri 10/09/21",1,"CP-203234",null,"Vivek Gupta, Intel ","vivek.g.gupta@intel.com ","23/9/22: 99%->100",null,97,49,null,null,"Wed 07/09/22","Fri 23/09/22"]
[1998,900019,"Adapting BEST for use in 5G networks ","BEST_5G",1,"Rel-17","S3","Fri 04/12/20","Fri 10/12/21",1,"SP-201020",null,"Keesmaat, Iko, KPN ","iko.keesmaat@tno.nl ","33.163 ; 19/3/21: 0%->40; 11/6/21: 40%->70; 11/6/21: FCD:Fri 11/06/->12/21; 13/9/21: 70%->85; 13/12/21: 85%->100",null,90,46,null,null,"Fri 04/12/20","Mon 13/12/21"]
[1999,920049,"Enhanced Service Enabler Architecture Layer for Verticals ","eSEAL",1,"Rel-17",null,"Fri 04/12/20","Fri 11/03/22",1,"SP-200987",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","23.434 ; 5/12/20: 0%->10; 10/2/21: FCD:11/06/2021->06/21; 21/3/21: 10%->35",null,92,47,null,null,"Fri 04/12/20","Sun 21/03/21"]
[2000,900024,"   Stage 2 of eSEAL","eSEAL",2,"Rel-17","S6","Fri 04/12/20","Tue 15/06/21",1,"SP-200987",null,"Basavaraj (Basu) Pattan, Samsung ","basavarajjp@samsung.com ","23.434 ; 5/12/20: 0%->10; 10/2/21: FCD:11/06/2021->06/21; 21/3/21: 10%->35; 11/6/21: 35%->80; 13/9/21: 80%->100",null,90,46,null,null,"Fri 04/12/20","Mon 13/09/21"]
[2004,900033,"Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 2 ","ATSSS_Ph2",1,"Rel-17",null,"Thu 07/03/19","Thu 06/06/24",1,"SP-200977",null,"Apostolis Salkintzis, Lenovo ","y1026c@lenovo.com ","23.501; 23.502; 23.503 ",null,90,46,null,null,"Thu 03/12/20","NA"]
[2009,910057,"      CT3 aspects of ATSSS_Ph2","ATSSS_Ph2",3,"Rel-17","C3","Thu 18/03/21","Fri 11/03/22",1,"CP-210136",null,"ZHOU Xingyue (Joy), ZTE ","zhou.xingyue@zte.com.cn ","11/6/21: 0%->50; 13/9/21: 50%->80; 13/12/21: 80%->100",29.512,91,46,null,null,"Thu 18/03/21","Mon 13/12/21"]
[2012,900031,"Enablers for Network Automation for 5G - phase 2 ","eNA_Ph2",1,"Rel-17",null,"Thu 06/06/19","Fri 11/03/22",1,"SP-200975",null,"TBD ",null,"23.501; 23.502; 23.503; 23.288 ",null,90,46,null,null,"Thu 03/12/20","NA"]
[2015,900010,"   Stage 2 of eNA_Ph2 ","eNA_Ph2",2,"Rel-17","S2","Thu 03/12/20","Wed 08/09/21",1,"SP-200975",null,"TBD ",null,"23.501; 23.502; 23.503; 23.288 ; 19/3/21: 0%->40; 14/6/21: 40%->90; 14/6/21: FCD:Fri 11/06/->09/21; 13/9/21: 90%->99; 10/12/21: 99%->100",null,90,46,null,null,"Thu 03/12/20","Fri 10/12/21"]
[2018,910089,"      CT4 aspects of eNA_Ph2 ","eNA_Ph2",3,"Rel-17","C4","Fri 19/03/21","Fri 11/03/22",1,"CP-211191",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","; 11/6/21: 0%->5; 14/6/21: 5%->60; 13/9/21: 60%->80; 13/12/21: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"Fri 19/03/21","Sat 12/03/22"]
[2020,900030,"Proximity based Services in 5GS ","5G_ProSe",1,"Rel-17",null,"Thu 07/03/19","Fri 10/06/22",1,"SP-200972",null,"TBD ",null,null,null,88,45,null,null,"Thu 03/12/20","NA"]
[2023,910018,"   CT aspects of proximity based services in 5GS ","5G_ProSe",2,"Rel-17","ct","Thu 18/03/21","Fri 11/03/22",1,"CP-212105",null,"Yong Jiang, CATT ","jiangyong@catt.cn ","; 11/6/21: WID:CP-210292->CP-211110; 10/9/21: WID:CP-211110->CP-212105; 13/7/22: 29.533 added;","23.122; 24.501; 27.007; 29.513; 29.519; 29.522; 29.525; 23.008; 29.502; 29.503; 29.505; 29.510; 29.518; 29.527; 29.571; 31.102 ; 29.533",91,46,null,null,"Thu 18/03/21","Wed 13/07/22"]
[2028,890018,"   Study on charging aspects of Proximity-based Services in 5GS","FS_5G_Prose_CH",2,"Rel-17","S5","Wed 16/09/20","Fri 10/12/21",1,"SP-200767",null,"Shu, Min, CATT ","shumin@catt.cn ","25/9/20: 32.846 added;; 5/12/20: 0%->15; 21/3/21: 15%->40; 13/9/21: 40%->80; 13/9/21: FCD:Wed 08/09/->12/21; 21/6/22: 80%->100",32.845999999999997,89,45,null,null,"Thu 10/09/20","Tue 21/06/22"]
[2031,930008,"   Security Aspects of Proximity based Services in 5GS","5G_ProSe",2,"Rel-17","S3","Fri 10/09/21","Thu 09/06/22",1,"SP-211120",null,"Wei Zhou, CATT ","zhouwei@catt.cn ","; 13/12/21: 0%->45; 13/12/21: FCD:Fri 10/12/->03/22; 12/3/22: 45%->65; 12/3/22: FCD:11/03/2022->6/22; 22/3/22: 33.503 added;; 4/6/22: 65%->92; 12/9/22: 92%->83; 31/3/23: 83%->100","New ; 33.503",93,47,null,null,"Fri 10/09/21","Fri 31/03/23"]
[2036,850021,"   SA3 aspects of AKMA","AKMA",2,"Rel-17","S3","Thu 19/09/19","Fri 12/06/20",1,"SP-190711",null,"Xiaoting Huang, China Mobile ","huangxiaoting@chinamobile.com ","; 8/10/19: 33.535 added; 6/12/19: 0%->20; 25/3/20: 20%->60; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 60%->95; 12/9/20: 95%->96; 25/09/20: Rel-16->Rel-17; 5/12/20: 96%->97; 19/3/21: 97%->98; 12/3/22: 98%->100","New ; 33.535",85,43,null,null,"Fri 13/09/19","Sat 12/03/22"]
[2039,890032,"      CT3 aspects of AKMA","AKMA-CT",3,"Rel-17","C3","Wed 16/09/20","Fri 11/03/22",1,"CP-203107",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","5/12/20: 0%->15; 21/3/21: 15%->95; 11/6/21: 95%->97; 13/9/21: 97%->95; 13/9/21: FCD:Fri 12/03/->03/22; 13/12/21: 95%->99; 12/3/22: 99%->100",29.521999999999998,89,45,null,null,"Fri 11/09/20","Sat 12/03/22"]
[2042,890149,"   Core part: Enhancement of Private Network support for NG-RAN ","NG_RAN_PRN_enh-Core",2,"Rel-17","R3","Thu 17/09/20","Fri 11/03/22",1,"RP-212585","RP-220561","China Telecom ",null,"follow-up WI of REL-16 WI NG_RAN_PRN-Core which was completed in June 20; no Perf. part; related SA2 SI? ; 13/9/21: Compl:0%->50%; 13/9/21: CD:Thu 17/06/21->Tue 22/03/22; 13/9/21: ; ",null,89,45,null,null,"Fri 25/09/20","Tue 22/03/22"]
[2045,780005,"   Study on MPS2","FS_MPS2",2,"Rel-17","S1","Fri 15/12/17","Thu 12/09/19",1,"SP-190315",null,"Singh, Ray P; Vencore Labs","rsingh@vencorelabs.com","16/3/18: 0%->10¦7/6/18: 10%->30¦10/9/18: 30%->50¦4/12/18: 50%->65¦12/12/18: FCD:03/19->09/19. Rel-16->Rel-17¦14/3/19: 65%->80; 31/5/19: 80%->90; 7/6/19: WID:SP-170996->SP-190315; 17/8/20: 90%->100",22.853999999999999,78,40,null,null,"Fri 15/12/17","Mon 17/08/20"]
[2047,840032,"   Stage 1 of MPS2","MPS2",2,"Rel-17","S1","Thu 06/06/19","Thu 12/12/19",1,"SP-190561",null,"Singh, Ray P; Perspecta Labs ","rsingh@perspectalabs.com ","13/9/19: 0%->85; 6/12/19: 85%->100","22.953; 22.153 ",84,43,null,null,"Fri 31/05/19","Fri 06/12/19"]
[2050,880050,"      CT1 aspects of MPS2 ","MPS2",3,"Rel-17","C1","Thu 25/06/20","Fri 11/03/22",1,"CP-201207",null,"Peter Monnes, Perspecta Labs ","pmonnes@perspectalabs.com ","24.229; 2/7/20: FCD:16/12/2020->03/21; 13/9/20: 0%->50; 5/12/20: 50%->75; 21/3/21: 75%->80; 13/9/21: 80%->90; 13/12/21: 90%->95; 12/3/22: FCD:15/03/2021->3/22; 12/3/22: 95%->100",null,88,45,null,null,"Fri 26/06/20","Sat 12/03/22"]
[2055,890071,"   CT1 aspects of PAP/CHAP protocols usage in 5GS ","PAP_CHAP",2,"Rel-17","C1","Wed 16/09/20","Fri 10/09/21",1,"CP-202251",null,"Mingxue Li, China Telecom ","limx36@chinatelecom.cn ","24.501; 5/12/20: 0%->90; 5/12/20: FCD:12/03/2021->09/20; 21/3/21: 90%->95; 11/6/21: 95%->100",null,89,45,null,null,"Fri 25/09/20","Fri 11/06/21"]
[2058,890028,"   CT1 aspects of SMS_SBI ","SMS_SBI",2,"Rel-17","C1","Wed 16/09/20","Fri 11/03/22",1,"CP-212023",null,"HAOUARI, Wafa, Orange ","wafa.haouari@orange.com ","12/3/22: FCD:12/03/2021->3/22; 12/3/22: 0%->100",23.04,89,45,null,null,"Fri 11/09/20","Sat 12/03/22"]
[2063,840044,"Network Controlled Interactive Service ","NCIS",1,"Rel-17",null,"Wed 06/06/18","Thu 12/12/19",1,"SP-190303",null,"Ning YANG, oppo ","yangning@oppo.com ",null,22.260999999999999,84,43,null,null,"Fri 31/05/19","NA"]
[2066,840019,"5G System Enhancement for Advanced Interactive Services ","5G_AIS",1,"Rel-17","S2","Thu 06/06/19","Fri 11/06/21",1,"SP-190564",null,"Lei Yixue, Tencent ","yixuelei@tencent.com ","5/12/20: 0%->10; 5/12/20: FCD:10/09/2020->06/20; 19/3/21: 10%->40; 11/6/21: 40%->100","23.501; 23.502; 23.503 ",84,43,null,null,"Fri 31/05/19","Fri 11/06/21"]
[2068,880043,"Multi-Device and multi-identity Enhancements (MuDE)","MuDE",1,"Rel-17",null,"Mon 02/09/19","Fri 11/12/20",1,"SP-190823",null,"Adrian.buckley@vivo.com ",null,"; 13/9/19: 0%->100",22.172999999999998,85,43,null,null,"Fri 13/09/19","Fri 13/09/19"]
[2071,920055,"Best Practice of Packet Forwarding Control Protocol (PFCP) ","BEPoP",1,"Rel-17","ct","Thu 25/06/20","Fri 11/03/22",1,"CP-212024",null,"Song Yue, China Mobile ","songyue@chinamobile.com ","29.244; 29.510 ; 2/7/20: 0%->5; 13/9/20: 5%->10; 25/9/20: 29.820 added;; 5/12/20: 10%->20; 21/3/21: 20%->30; 11/6/21: WID:CP-201076->CP-210074; 10/9/21: WID:CP-210074->CP-212024",29.82,88,45,null,null,"Fri 26/06/20","Fri 10/09/21"]
[2074,880012,"Extension for headset interface tests of UE ","HInT",1,"Rel-17","S4","Thu 25/06/20","Fri 10/09/21",1,"SP-200398",null,"Jan Reimes, HEAD acoustics GmbH, ","jan.reimes@head-acoustics.com ","26.131; 26.132 ; 12/9/20: 0%->10; 5/12/20: 10%->25; 21/3/21: 25%->50; 11/6/21: 50%->70; 13/9/21: 70%->75; 13/12/21: 75%->100",null,88,45,null,null,"Thu 25/06/20","Mon 13/12/21"]
[2077,820003,"Support of Immersive Teleconferencing and Telepresence for Remote Terminals ","ITT4RT",1,"Rel-17","S4","Thu 13/12/18","Fri 11/03/22",1,"SP-180985",null,"Ozgur Oyman, Intel","Ozgur.Oyman@Intel.com","7/3/19: 0%->5%; 31/5/19: 0%->10; 13/9/19: 10%->20; 6/12/19: 20%->25; 25/3/20: 25%->35; 10/6/20: 35%->45; 26/6/20: 45%->45; 12/9/20: 45%->50; 5/12/20: 50%->55; 5/12/20: FCD:18/12/2020->06/20; 21/3/21: 55%->60; 11/6/21: 60%->75; 11/6/21: FCD:Fri 11/06/-> ","26.114; 26.223; 26.962; 26.862",82,42,null,null,"Thu 14/03/19","Sat 12/03/22"]
[2082,920009,"Edge Extensions to the 5G Media Streaming Architecture ","5GMS_EDGE",1,"Rel-17","S4","Fri 11/06/21","Wed 08/09/21",1,"SP-210375",null,"Bouazizi, Imed, Qualcomm Inc. ","bouazizi@qti.qualcomm.com ","; 13/9/21: 0%->30; 13/12/21: 30%->100",26.501000000000001,92,47,null,null,"Fri 11/06/21","Mon 13/12/21"]
[2085,830017,"Verification-modified Calling Name Display ","VMOD_DISPLAY",1,"Rel-17","S1","Thu 07/03/19","Thu 21/03/19",1,"SP-190085",null,"Hala Mowafy, Ericsson","Hala.Mowafy@ericsson.com","14/3/19: 0%->100",22.172999999999998,83,42,null,null,"Fri 15/12/17","Thu 14/03/19"]
[2090,900036,"   Stage 3 (CT4) of eCPSOR_CON","eCPSOR_CON",2,"Rel-17","C4","Thu 25/06/20","Fri 11/03/22",1,"CP-210148",null,"Al-Bakri Ban, NTT DOCOMO ","ban.albakri@meadowcom.com ","23.122; 24.501; 29.503; 29.505; 29.550; 29.509; 29.571; 31.102; 31.111 ; 13/9/20: 0%->5; 13/9/20: WID:CP-201166->CP-202186; 5/12/20: 0%->5; 21/3/21: 5%->5; 11/6/21: 5%->10; 13/12/21: 10%->70; 13/12/21: FCD:Fri 18/06/->03/22; 12/3/22: 70%->100",null,90,46,null,null,"Fri 26/06/20","Sat 12/03/22"]
[2093,910090,"Integration of Generic Bootstrapping Architecture (GBA) into 5GC ","GBA_5G",1,"Rel-17",null,"Wed 06/06/18","Fri 11/03/22",1,"SP-190714",null,"Vlasios Tsiatsis, Ericsson ","vlasios.tsiatsis@ericsson.com ","26/6/20: FCD:12/06/2020->09/20; 26/6/20: 0%->5; 12/9/20: 5%->50; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 50%->55; 5/12/20: FCD:15/12/2020->03/20","33.220; 33.222; 33.223; 33.501 ",85,43,null,null,"Fri 13/09/19","Sat 05/12/20"]
[2095,910004,"   CT aspects of Integration of GBA into SBA ","GBA_5G",2,"Rel-17","C4","Thu 18/03/21","Fri 11/03/22",1,"CP-210283",null,"de Gregorio, Jesús (Ericsson) ","jesus.de.gregorio@ericsson.com ","; 21/3/21: 0%->5; 11/6/21: 5%->15; 13/9/21: 15%->60; 13/12/21: 60%->80; 12/3/22: 80%->100","29.503; 29.505; 29.510; 29.562; 29.571 ",91,46,null,null,"Thu 18/03/21","Sat 12/03/22"]
[2098,830018,"   Study on MINT","FS_MINT",2,"Rel-17","S1","Thu 07/03/19","Thu 05/09/19",1,"SP-190090","-","SungDuck Chun; LG Electronics","sungduck.chun@lge.com","31/5/19: 0%->65; 13/9/19: 65%->100","New",83,42,null,null,"Thu 14/03/19","Fri 13/09/19"]
[2101,900004,"   Study on the CT aspects of Support for Minimization of service Interruption ","FS_MINT-CT",2,"Rel-17","C1","Mon 07/12/20","Fri 12/03/21",1,"CP-203232",null,"Sang Min Park, LG Electronics ","sangmin2.park@lge.com ","21/3/21: 0%->60; 11/6/21: 60%->95; 13/9/21: 95%->100",null,90,46,null,null,"Sat 05/12/20","Mon 13/09/21"]
[2104,930045,"      CT4 aspects of MINT","MINT",3,"Rel-17","C4","Wed 29/09/21","Fri 11/03/22",1,"CP-212166",null,"Hyunsook Kim, LG Electronics","hyuns.kim@lge.com","; 12/3/22: 0%->80; 20/6/22: Compl:80%->100%","23.122; 24.501; 31.102; 31.111 ",93,47,null,null,"Wed 29/09/21","Mon 20/06/22"]
[2109,860016,"Assurance Specification for IMS ","SCAS_IMS",1,"Rel-17","S3","Fri 06/12/19","Fri 11/06/21",1,"SP-191128",null,"Bo Zhang, Huawei Technologies ","zhangbo6@huawei.com ","; 26/6/20: 0%->15; 12/9/20: 15%->40; 5/12/20: 40%->60; 5/12/20: FCD:11/12/2020->03/20; 19/3/21: 60%->80; 19/3/21: FCD:12/03/2021->06/21; 11/6/21: 80%->90; 13/12/21: 90%->100",33.926000000000002,86,44,null,null,"Fri 06/12/19","Mon 13/12/21"]
[2113,870018,"   eSCAS_5G for 5G NWDAF","SCAS_5G_NWDAF",2,"Rel-17","S3","Wed 25/03/20","Fri 10/06/22",1,"SP-200147",null,"QI Minpeng, China Mobile","qiminpeng@chinamobile.com","26/6/20: 0%->10; 5/12/20: 10%->60; 19/3/21: 60%->70; 19/3/21: FCD:17/03/2021->06/21; 11/6/21: 70%->85; 11/6/21: FCD:Fri 11/06/->12/21; 11/6/21: 85%->; 13/9/21: 85%->90; 12/3/22: FCD:10/12/2021->06/22; 4/6/22: 90%->100","33.521; 33.926",87,44,null,null,"Wed 25/03/20","Sat 04/06/22"]
[2116,870034,"Enhanced Mission Critical Push-to-talk architecture phase 3 ","enh3MCPTT",1,"Rel-17",null,"Wed 25/03/20","Wed 08/09/21",1,"SP-200108",null,"Dom Lazara; Motorola Solutions ","Dom.Lazara@motorolasolutions.com ","; 28/6/20: 0%->20","23.379; 23.280; 23.281; 23.282; 23.283 ",87,44,null,null,"Fri 06/12/19","Sun 28/06/20"]
[2120,1050128,"UE Conformance - Protocol enhancements for Mission Critical Services (MCPTT, MCVideo, MCData) for Rel-17 ","MCProtoc17_enh3MCPTT_eMCData3_MCOver5GS-UEConTest",1,"Rel-17","R5","Mon 09/09/24","Fri 12/12/25",0.47,"RP-242768","RP-251338","Ericsson ",null,"6/12/24: Compl:0%->16%; Stat Rep: ->RP-242642; ; 24/1/25: WID:RP-241755->RP-242768; 6/3/25: FCD:24/07/2025->12/12/2025; Compl:16%->23%; Stat Rep: RP-242642->RP-250286; ; 3/4/25: WID:RP-242768->RP-250287; 6/6/25: Compl:23%->47%; WID: RP-250287->RP-242768;",null,null,null,null,null,"Thu 26/09/24","Fri 06/06/25"]
[2122,820006,"Study on User Plane Integrity Protection","FS_UP_IP_Sec",1,"Rel-17","S3","Thu 13/12/18","Fri 12/03/21",1,"SP-181035",null,"Evans, Tim, Vodafone","tim.evans1@vodafone.com","20/3/19: 0%->15¦20/3/19: 0%->15; 31/5/19: 15%->25; 13/9/19: 25%->50; 13/9/19: FCD:19/09/2019->12/20; 6/12/19: 50%->65; 6/12/19: FCD:12/12/2019->03/20; 25/03/20: Rel-16->Rel-17; 26/6/20: FCD:12/03/2020->12/20; 26/6/20: 65%->75; 12/9/20: 75%->85; 5/12/20 ",null,82,42,null,null,"Thu 06/12/18","Fri 11/06/21"]
[2125,910091,"   Study on non-seamless WLAN Offload in 5GS using 3GPP credentials ","FS_NSWO_5G",2,"Rel-17","S3","Tue 25/05/21","Wed 08/09/21",1,"SP-210262",null,"Nair, Suresh, Nokia ","suresh.p.nair@nokia.com ","11/6/21: 0%->25; 13/9/21: 25%->70; 1/10/21: 33.881 added;; 4/6/22: 70%->100",33.881,91,46,null,null,"Tue 25/05/21","Sat 04/06/22"]
[2128,950002,"   CT4 aspects of NSWO","NSWO_5G",2,"Rel-17","C4","Thu 10/03/22","Fri 11/03/22",1,"CP-220095",null,"Wiehe, Ulrich, Nokia ","ulrich.wiehe@nokia.com ","; 12/3/22: 0%->98; 4/6/22: 98%->100","24.302; 24.368; 24.501; 24.502; 29.503; 29.509; 29.273; 29.510; 31.102; 31.111; 31.101 ",95,48,null,null,"Thu 10/03/22","Sat 04/06/22"]
[2131,860025,"   Lawful Interception Rel-17 general aspects","LI17",2,"Rel-17","S3","Tue 10/12/19","Fri 10/06/22",1,"SP-190983",null,"Alex Leadbeater, BT","alex.leadbeater@bt.com","19/3/21: FCD:12/06/2021->03/22; 19/3/21: 0%->5; 11/6/21: 5%->20; 13/9/21: 20%->87; 12/3/22: 87%->98; 12/3/22: FCD:11/03/2022->06/22; 4/6/22: 98%->100","33.107; 33.108; 33.126; 33.127; 33.128",86,44,null,null,"Fri 06/12/19","Sat 04/06/22"]
[2136,870003,"      Stage 2 for TEI17_IMSGID","TEI17_IMSGID",3,"Rel-17","S2","Wed 25/03/20","Fri 12/06/20",1,"SP-200452",null,"Foti, George, Ericsson","George.foti@ericsson.com","19/3/21: 0%->100",23.228000000000002,87,44,null,null,"Wed 10/06/20","Fri 19/03/21"]
[2140,910003,"      CT aspects on TEI17_SPSFAS","TEI17_SPSFAS",3,"Rel-17","ct","Thu 18/03/21","Wed 08/09/21",1,"CP-211184",null,"Yue Sun, China Telecom ","suny20@chinatelecom.cn ",null,null,91,46,null,null,"Thu 18/03/21","NA"]
[2144,880017,"      Stage 2 for TEI17_SE_RPS","TEI17_SE_RPS",3,"Rel-17","S2","Wed 25/03/20","Fri 12/06/20",1,"SP-200448",null,"Devaki Chandramouli ","devaki.chandraouli@nokia.com ","; 11/6/21: 0%->100","23.501; 23.502",88,45,null,null,"Thu 25/06/20","Fri 11/06/21"]
[2147,930038,"         CT3 aspects of TEI17_SE_RPS","TEI17_SE_RPS",4,"Rel-17","C3","Fri 10/09/21","Fri 11/03/22",1,"CP-212099",null,"WON, Sung Hwan, Nokia ","sung.won@nokia.com ","; 13/12/21: 0%->50; 12/3/22: 50%->100","29.513; 29.525; 29.561",93,47,null,null,"Fri 10/09/21","Sat 12/03/22"]
[2149,910078,"   Support for Signed Attestation for Priority and Emergency Sessions ","TEI17_SAPES",2,"Rel-17",null,"Wed 25/03/20","Fri 10/09/21",1,"SP-200453",null,"Foti, George, Ericsson ","George.foti@ericsson.com ",null,null,87,44,null,null,"Wed 10/06/20","NA"]
[2152,910079,"         CT1 aspects on TEI17_SAPES","TEI17_SAPES",4,"Rel-17","C1","Fri 19/03/21","Fri 10/09/21",1,"CP-210272",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 11/6/21: 0%->100",null,91,46,null,null,"Fri 19/03/21","Fri 11/06/21"]
[2158,910083,"         CT4 aspects on TEI17_DCAMP","TEI17_DCAMP",4,"Rel-17","C4","Fri 19/03/21","Fri 11/03/22",1,"CP-212163",null,"Garcia Azorero, Fuencisla. Ericsson ","fuencisla.garcia@ericsson.com ","; 13/12/21: 0%->70; 12/3/22: 70%->100",null,91,46,null,null,"Fri 19/03/21","Sat 12/03/22"]
[2159,870006,"   IP address pool information from UDM ","TEI17_IPU",2,"Rel-17","S2","Wed 11/03/20","Thu 25/06/20",1,"SP-200454",null,"Stefan Rommer ","stefan . rommer @ ericsson . com ","19/3/21: 0%->100",null,87,44,null,null,"Wed 10/06/20","Fri 19/03/21"]
[2163,910085,"         CT3 aspects on TEI17_GEM ","TEI17_GEM",4,"Rel-17","C3","Fri 19/03/21","Fri 11/03/22",1,"CP-212165",null,"Maria Tianmei, Liang, Ericsson ","maría.liang@ericsson.com ","; 11/6/21: 0%->35; 13/9/21: 35%->80; 13/12/21: 80%->90; 12/3/22: 90%->100",null,91,46,null,null,"Fri 19/03/21","Sat 12/03/22"]
[2167,930099,"      CT1 aspects of TEI17_N3SLICE","TEI17_N3SLICE",3,"Rel-17","C1","Fri 11/06/21","Fri 18/06/21",1,"CP-211089",null,"LANDAIS, Bruno, Nokia ","bruno.landais@nokia.com ","; 11/6/21: 0%->100; 1/10/21: 0%->100","24.501;29.571;29.510 ",92,47,null,null,"Fri 11/06/21","Fri 01/10/21"]
[2171,890019,"      SA5 aspects of N40 Interface Enhancements to Support GERAN and UTRAN ","TEI17_NIESGU",3,"Rel-17","S5","Wed 16/09/20","Wed 08/09/21",1,"SP-200854",null,"Dong, Jia, China Mobile ","dongjia@chinamobile.com ","25/09/20: acronym: \"NIESGU\"->\"TEI17_NIESGU\"; 25/9/20: WID:SP-200768->SP-200854; 5/12/20: FCD:11/06/2021->09/20; 5/12/20: 0%->5; 21/3/21: 5%->10; 13/9/21: 10%->100","32.240; 32.251; 32.255; 32.290; 32.291; 32.298 ",89,45,null,null,"Fri 11/09/20","Mon 13/09/21"]
[2174,950099,"(Small) Test Technical Enhancements and Improvements for Rel-17","TEI17_Test",1,"Rel-17","R5","Fri 10/12/21","Tue 22/03/22",1,"-",null,null,null,"Added as per Ingo's request on 02/04/22",null,95,48,null,null,"Thu 21/04/22","NA"]
[2176,880044,"   Stage-3 5GS NAS protocol development 17 general aspects ","5GProtoc17",2,"Rel-17","C1","Thu 25/06/20","Fri 11/03/22",1,"CP-201163",null,"Sedlacek, Ivo, Ericsson ","ivo <dot> sedlacek <at> ericsson <dot> com ","23.040; 23.041; 23.122; 24.007; 24.008; 24.011; 24.173; 24.229; 24.301; 24.302; 24.305; 24.341; 24.368; 24.501; 24.502; 24.526; 27.007 ; 13/9/20: 0%->10; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->70; 13/9/21: FCD:Mon 20/09/->0 ",null,88,45,null,null,"Fri 26/06/20","Sat 12/03/22"]
[2179,880046,"   Stage-3 SAE Protocol Development general aspects","SAES17",2,"Rel-17","C1","Thu 25/06/20","Fri 11/03/22",1,"CP-201165",null,"Aghili, Behrouz, InterDigital Communications ","behrouz.aghili@interdigital.com ","13/9/20: 0%->10; 5/12/20: 10%->30; 21/3/21: 30%->40; 11/6/21: 40%->50; 13/9/21: 50%->65; 13/12/21: 65%->90; 12/3/22: FCD:20/09/2021->3/22; 12/3/22: 90%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ; ",88,45,null,null,"Fri 26/06/20","Sat 12/03/22"]
[2185,1000055,"   STOPPED - UE Conformance - IMS Data Channel ","IMSProtoc17_dataCH-UEContest",2,"Rel-17","R5","Wed 07/06/23","Thu 06/06/24",1,"RP-240283","RP-241373","Zhaobing Yang, Huawei Technologies. Co., Ltd","yangzhaobing@huawei.com","6/9/23: FCD:12/12/2023->22/09/2023; Compl:0%->5%; Stat Rep: ->RP-232356; Rapporteur: HiSilicon->Zhaobing Yang, Huawei Technologies. Co., Ltd; Rap eMail: ->yangzhaobing@hisilicon.com; ; 6/10/23: WID:RP-231246->RP-232357; 8/12/23: FCD:22/09/2023->09/09/2...",null,100,51,null,null,"Thu 29/06/23","Thu 13/06/24"]
[2187,880013,"Service Based Interface Protocol Improvements Release 17 ","SBIProtoc17",1,"Rel-17",null,"Thu 25/06/20","Fri 11/03/22",1,"CP-211088",null,"Song Yue, China Mobile ","songyue@chinamobile.com ",null,null,88,45,null,null,"Fri 26/06/20","NA"]
[2190,900001,"Study on restoration of profiles related to UDR ","FS_ReP_UDR",1,"Rel-17","C4","Mon 07/12/20","Fri 11/03/22",1,"CP-203271",null,"Ishikawa, Hiroshi, NTT DOCOMO ","hiroshi.ishikawa.ev (at) nttdocomo.com ","21/3/21: 0%->20; 11/6/21: 20%->40; 13/9/21: FCD:Fri 10/09/->12/21; 13/9/21: 40%->60; 1/10/21: WID:CP-203019->CP-203271; 13/12/21: 60%->95; 12/3/22: FCD:10/12/2021->3/22; 12/3/22: 95%->100",null,90,46,null,null,"Sat 05/12/20","Sat 12/03/22"]
[2194,940004,"Multi-device enhancements for device transfers ","MuDTran",1,"Rel-17","C1","Fri 10/12/21","Fri 10/06/22",1,"CP-220352",null,"Axell, Jörgen, Ericsson ","Jorgen.Axell@ericsson.com ","; 12/3/22: 0%->90; 22/3/22: WID:CP-213080->CP-220352; 22/3/22: FCD:11/03/2022->06/22; 4/6/22: 90%->100","24.174; 24.175; 24.229 ",94,48,null,null,"Fri 10/12/21","Sat 04/06/22"]
[2198,950001,"Repository for the 3GPP Allocated Port Numbers for New 3GPP Interfaces ","PortAl",1,"Rel-17","C4","Thu 10/03/22","Fri 11/03/22",1,"CP-220094",null,"Giorgi Gulbani, Huawei ","giorgi.gulbani@huawei.com ","; 12/3/22: 0%->100",29.940999999999999,95,48,null,null,"Thu 10/03/22","Sat 12/03/22"]
[2199,950009,"Modifying PASSporT signing and verification for Spoofed calls ","SPECTRE_Ph3",1,"Rel-17","C1","Thu 10/03/22","Fri 11/03/22",1,"CP-220381",null,"Politz, Ken, Neustar ","ken.politz@team.neustar ","; 4/6/22: 0%->35; 20/6/22: Compl:35%->100%",24.228999999999999,95,48,null,null,"Thu 10/03/22","Mon 20/06/22"]
[2205,930032,"Improved support for NSA in the service-based management architecture ","NSA_SBMA",1,"Rel-17","S5","Fri 10/09/21","Fri 11/03/22",1,"SP-211121",null,"Lan Zou, Huawei ","zoulan@huawei.com ",null,"28.623; 28.622; 28.659; 28.663 ",91,46,null,null,"Fri 10/09/21","NA"]
[2206,930009,"   Improved support for NSA in the service-based management architecture ","NSA_SBMA",2,"Rel-17","S5","Fri 10/09/21","Fri 11/03/22",1,"SP-210858",null,"Lan Zou, Huawei ","zoulan@huawei.com ","; 13/12/21: 0%->20; 12/3/22: 20%->100","28.623; 28.622; 28.659; 28.663 ",93,47,null,null,"Fri 10/09/21","Sat 12/03/22"]
[2212,820035,"Discovery of management services in 5G ","5GDMS",1,"Rel-17","S5","Thu 13/12/18","Fri 11/03/22",1,"SP-200770",null,"Brendan Hassett, Huawei Technologies Sweden AB ","brendan.t.hassett@huawei.com","¦14/3/19: 0%->25; 31/5/19: 25%->35; 13/9/19: 35%->65; 13/9/19: FCD:19/06/2019->12/20; 26/3/20: 65%->80; 28/6/20: 80%->90. 09/20: moved from Rel-16; 13/9/20: WID:SP-181072->SP-200770; 13/9/20: FCD:12/12/2019->09/21; 25/9/20: 90%->50; 21/3/21: 50%->70; ","28.533; 28.532; 28.531 ",82,42,null,null,"Fri 07/12/18","Sat 12/03/22"]
[2214,850028,"Study on enhancement of Management Data Analytics Service ","FS_eMDAS",1,"Rel-17","S5","Thu 19/09/19","Fri 12/03/21",1,"SP-190930",null,"Yao, Yizhi, Intel ","yizhi.yao@intel.com ","; 20/9/19: WID:SP-190783->SP-190930; 8/10/19: 28.809 added;; 26/3/20: 0%->30; 28/6/20: 30%->50; 13/9/20: 50%->70; 13/9/20: FCD:11/09/2020->03/21; 5/12/20: 70%->90; 21/3/21: 90%->100","New ; 28.809",85,43,null,null,"Fri 13/09/19","Sun 21/03/21"]
[2217,870021,"Study on new aspects of EE for 5G networks ","FS_EE5G",1,"Rel-17","S5","Wed 25/03/20","Fri 10/12/21",1,"SP-200187",null,"Jean-Michel CORNILY, ORANGE","jeanmichel.cornily@orange.com ","28/6/20: 0%->10; 13/9/20: 10%->25; 13/9/20: FCD:16/06/2021->09/21; 5/12/20: 25%->45; 21/3/21: 45%->70; 11/6/21: 70%->75; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 75%->80; 13/12/21: 80%->100",null,87,44,null,null,"Fri 06/12/19","Mon 13/12/21"]
[2221,870030,"Enhanced Closed loop SLS Assurance ","eCOSLA",1,"Rel-17","S5","Wed 25/03/20","Fri 11/03/22",1,"SP-200196",null,"Groenendijk, Jan, Ericsson ","jan.groenendijk@ericsson.com ","13/9/20: 0%->5; 5/12/20: 5%->10; 5/12/20: FCD:11/12/2020->03/20; 21/3/21: 10%->30; 11/6/21: 30%->50; 11/6/21: FCD:Fri 12/03/->09/21; 13/9/21: 50%->60; 13/9/21: FCD:Wed 08/09/->03/22; 13/12/21: 60%->80; 12/3/22: 80%->90; 4/6/22: 90%->100; 4/1/24: 28.867 ad","28.535; 28.536; 28.533; 28.541; 28.546; 28.552; 28.553 ; 28.867",87,44,null,null,"Fri 06/12/19","Thu 04/01/24"]
[2225,911008,"NR QoE magement and optimizations for diverse services ","NR_QoE",1,"Rel-17",null,"Fri 01/01/21","Mon 09/09/24",1,"RP-211406",null,"China Unicom ",null,"follow-up WI of RAN3 REL-17 SI FS_NR_QoE; no Perf. part ; 2/7/21: WID:RP-210913->RP-211406",null,91,46,null,null,"Fri 04/06/21","Fri 02/07/21"]
[2226,911108,"   Core part: NR QoE management and optimizations for diverse services ","NR_QoE-Core",2,"Rel-17","R3","Fri 01/01/21","Tue 22/03/22",1,"RP-211406","RP-220554","Gen Cao","caogen@chinauincom.cn","follow-up WI of RAN3 REL-17 SI FS_NR_QoE; no Perf. part ; 20/6/22: FCD:31/12/2021->22/03/2022; Compl:0%->100%; Stat Rep: ->RP-220554; Rapporteur: China Unicom->Gen Cao; Rap eMail: ->caogen@chinauincom.cn; ",null,91,46,null,null,"Wed 07/04/21","Mon 20/06/22"]
[2232,911010,"Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) ","NR_FR1_TRP_TRS",1,"Rel-17",null,"Fri 12/03/21","Tue 12/12/23",1,"RP-212030",null,"Vivo ",null,"compare LTE_UTRA_TRP_TRS; related to OTA; TR 38.8xx ; 2/7/21: WID:RP-210807->RP-211158; 29/9/21: WID:RP-211158->RP-212030; 1/10/21: 38.161 added;; ",38.161000000000001,91,46,null,null,"Wed 07/04/21","Sat 04/06/22"]
[2233,911110,"   Core part: NR_FR1_TRP_TRS","NR_FR1_TRP_TRS-Core",2,"Rel-17","R4","Fri 12/03/21","Tue 22/03/22",1,"RP-212030","RP-221276","Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC","ruixin.wang@vivo.com liuqifei@oppo.com shaozhe@CHINAMOBILE.COM","compare LTE_UTRA_TRP_TRS; related to OTA; TR 38.8xx ; 2/7/21: 38.834 added ; 20/6/22: Rapporteur: Vivo->Wang, Ruixin; Liu, Qifei; Shaozhe, vivo, OPPO, CMCC; Rap eMail: ->ruixin.wang@vivo.com liuqifei@oppo.com shaozhe@CHINAMOBILE.COM; ",38.834000000000003,91,46,null,null,"Wed 07/04/21","Mon 20/06/22"]
[2239,930052,"   UE Conformance - High power UE (power class 1.5) for NR band n79 ","NR_UE_PC1_5_n79-UEConTest",2,"Rel-17","R5","Fri 17/09/21","Thu 01/12/22",1,"RP-211979","RP-223061","Dan SONG, CMCC","songdan@chinamobile.com","tested: REL-17 WI NR_UE_PC1_5_n79-Core ; 6/1/22: WID:RP-211979->RP-213033; 22/3/22: Compl:0%->57% ; 20/6/22: Rapporteur: CMCC->Dan SONG, CMCC; Rap eMail: ->songdan@chinamobile.com ; ;...; 9/12/22: FCD:23/03/2023->01/12/2022; Compl:84%->100%; Stat R...",null,93,47,null,null,"Wed 29/09/21","Mon 09/01/23"]
[2241,911113,"   Core part: NR_UE_PC2_n34","NR_UE_PC2_n34-Core",2,"Rel-17","R4","Fri 12/03/21","Wed 08/09/21",1,"RP-210844",null,"CMCC ",null,"; 2/7/21: 0%->100",null,91,46,null,null,"Wed 07/04/21","Fri 02/07/21"]
[2244,911014,"High power UE (power class 2) for NR band n39 ","NR_UE_PC2_n39",1,"Rel-17",null,"Fri 12/03/21","Fri 22/09/23",1,"RP-210845",null,"CMCC ",null,null,null,91,46,null,null,"Wed 07/04/21","NA"]
[2248,911015,"Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP of 23dBm for band n259 ","NR_FR2_FWA_Bn259",1,"Rel-17",null,"Fri 12/03/21","Wed 08/09/21",1,"RP-210875",null,"SoftBank Corp., KDDI, NTT DOCOMO, Rakuten Mobile, Qualcomm ",null,"compare REL-17 WI NR_FR2_FWA_Bn257_Bn258 ",null,91,46,null,null,"Wed 07/04/21","NA"]
[2252,911106,"   Core part: NR_UDC","NR_UDC-Core",2,"Rel-17","R2","Fri 12/03/21","Fri 11/03/22",1,"RP-220140","RP-220141","CATT ",null,"no Perf. Part; compare RAN2 REL-15 WI LTE_UDC-Core ; ;…; 5/4/22: WID:RP-211203->RP-220140",null,91,46,null,null,"Wed 07/04/21","Tue 05/04/22"]
[2253,960085,"   UE Conformance - NR Uplink Data Compression (UDC) ","NR_UDC-UEConTest",2,"Rel-17","R5","Wed 15/06/22","Tue 06/06/23",1,"RP-221449","RP-230395","Huiying ZHANG, CATT","zhanghuiying@catt.cn","9/9/22: Comp...; 9/12/22: FCD:23/06/2023->01/06/2023; Compl:7%->33%; Stat Rep: ->RP-223139; Rapporteur: CATT->Huiying ZHANG, CATT; Rap eMail: ->zhanghuiying@catt.cn; 17/3/23: Compl:33%->67%; Stat Rep: RP-223139->RP-230395; ;...",null,96,49,null,null,"Tue 12/07/22","Wed 07/06/23"]
[2257,880178,"   Core part: NR_MIMO_OTA","NR_MIMO_OTA-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-213101","RP-221382","Zhu, Siting; Xing, Jinqiang, CAICT, OPPO","zhusiting@caict.ac.cn xingjinqiang@oppo.com","25/9/20: 38.151 added;; 13/9/21: Compl:0%->83%; ; 20/6/22: Rapporteur: CAICT->Zhu, Siting; Xing, Jinqiang, CAICT, OPPO; Rap eMail: ->zhusiting@caict.ac.cn xingjinqiang@oppo.com; ",38.151000000000003,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2260,870064,"Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258","NR_FR2_FWA_Bn257_Bn258",1,"Rel-17",null,"Wed 25/03/20","Thu 12/12/24",0.79,"RP-202565",null,"Softbank",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-200503->RP-201215; 25/9/20: WID:RP-201215->RP-201598; 6/1/21: WID:RP-201598->RP-202565",null,87,44,null,null,"Thu 26/03/20","Wed 06/01/21"]
[2266,880093,"Introduction of channel bandwidths 35MHz and 45MHz for NR FR1","NR_FR1_35MHz_45MHz_BW",1,"Rel-17",null,"Thu 19/03/20","Fri 19/03/21",1,"RP-211386",null,"Huawei",null,"25/9/20: WID:RP-201321->RP-201722; 6/1/21: WID:RP-201722->RP-202607; 7/4/21: WID:RP-202607->RP-210722; 2/7/21: WID:RP-210722->RP-211386",null,88,45,null,null,"Tue 28/07/20","Fri 02/07/21"]
[2268,880293,"   Perf. Part: NR_FR1_35MHz_45MHz_BW","NR_FR1_35MHz_45MHz_BW-Perf",2,"Rel-17","R4","Thu 19/03/20","Fri 19/03/21",1,"RP-211386",null,"Huawei",null,"29/9/21: 0%->100",null,88,45,null,null,"Tue 28/07/20","Wed 29/09/21"]
[2271,880297,"   Perf. Part: NR_SAR_PC2_interB_SUL_2BUL","NR_SAR_PC2_interB_SUL_2BUL-Perf",2,"Rel-17","R4","Thu 19/03/20","Mon 21/03/22",1,"RP-212530","RP-211830","China Telecom",null,"7/4/21: 0%->100; 13/9/21: CD:Fri 19/03/21->Mon 21/03/22; 13/9/21: WID: RP-211494->RP-201337 RP-201584 RP-211494; 13/9/21: Stat Rep: ->RP-211830",null,88,45,null,null,"Tue 28/07/20","Mon 13/09/21"]
[2275,900161,"   Core part: NR_cov_enh","NR_cov_enh-Core",2,"Rel-17","R1","Mon 14/12/20","Fri 11/03/22",1,"RP-211566","RP-220563","China Telecom ",null,"follow-up WI of REL-17 SI FS_NR_cov_enh ; 13/9/21: Compl:0%->60%; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211826 ; ",null,90,46,null,null,"Wed 06/01/21","Tue 22/03/22"]
[2279,860035,"   Study on support of reduced capability NR devices","FS_NR_redcap",2,"Rel-17","R1","Mon 16/12/19","Mon 15/06/20",1,"RP-220966",null,"Ericsson",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-193238->RP-201386; 25/9/20: WID:RP-201386->RP-201677; 6/1/21: WID:RP-201677->RP-202704; 7/4/21: 0%->100",null,86,44,null,null,"Tue 14/01/20","Wed 07/04/21"]
[2280,900162,"   Core part: NR_redcap","NR_redcap-Core",2,"Rel-17","R1","Mon 14/12/20","Wed 22/06/22",1,"RP-220966","RP-221162","Johan BERGMAN, Ericsson","johan.bergman@ericsson.com","follow-up WI of REL-17 SI FS_NR_redcap (not yet completed at RAN #90e) ; 22/ 20/6/22: Rapporteur: Ericsson->Johan BERGMAN, Ericsson; Rap eMail: ->johan.bergman@ericsson.com; ",null,90,46,null,null,"Wed 06/01/21","Mon 20/06/22"]
[2284,940005,"   CT1 aspects of NR_redcap","ARCH_NR_REDCAP",2,"Rel-17","C1","Fri 10/12/21","Fri 11/03/22",1,"CP-213081",null,"Chen Xu, China Mobile","chenxu@chinamobile.com","12/3/22: 0%->98; 12/3/22: FCD:10/06/2022->3/22; 4/6/22: 98%->100","24.501; 23.122; 24.008; 24.368",94,48,null,null,"Fri 07/01/22","Sat 04/06/22"]
[2289,900064,"Additional NR bands for UL-MIMO power class 3 (PC3) in Rel-17 ","NR_bands_UL_MIMO_PC3_R17",1,"Rel-17",null,"Mon 14/12/20","Tue 06/06/23",1,"RP-221518",null,"Huawei ",null,"basket WI ; 7/4/21: WID:RP-202819->RP-210557; 2/7/21: WID:RP-210557->RP-211380; 29/9/21: WID:RP-211380->RP-212184; 6/1/22: WID:RP-212184->RP-213137; 5/4/22: WID:RP-213137->RP-220704; 12/7/22: WID:RP-220704->RP-221518",null,90,46,null,null,"Wed 06/01/21","Tue 12/07/22"]
[2291,900264,"   Perf. part: NR_bands_UL_MIMO_PC3_R17","NR_bands_UL_MIMO_PC3_R17-Perf",2,"Rel-17","R4","Mon 14/12/20","Wed 22/06/22",1,"RP-221518","RP-221517","Liu Ye, Huawei","leo.liuye@huawei.com","basket WI ; 13/9/21: CD:Sun 12/06/22->Tue 22/03/22; ; 20/6/22: WID: ->RP-213136; Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,90,46,null,null,"Wed 06/01/21","Mon 20/06/22"]
[2295,900168,"   Core part: DL_intrpt_combos_TxSW_R17","DL_intrpt_combos_TxSW_R17-Core",2,"Rel-17","R4","Mon 14/12/20","Fri 11/03/22",1,"RP-210478","RP-220570","China Telecom ",null,"basket WI; TR 37.8xx ; 13/9/21: Compl:0%->60%; 13/9/21: CD:Sat 12/03/22->Tue 22/03/22; 13/9/21: WID: RP-210478->RP-202885 RP-210478 ; ; ",null,90,46,null,null,"Wed 06/01/21","Tue 22/03/22"]
[2298,900069,"High-power UE (power class 1.5) operation in NR bands n77 and n78 ","HPUE_PC1_5_n77_n78",1,"Rel-17",null,"Mon 14/12/20","Thu 01/12/22",1,"RP-202912",null,"Qualcomm ",null,"no Perf. part ",null,90,46,null,null,"Wed 06/01/21","NA"]
[2302,900170,"   Core part: HPUE_PC1_5_n77_n78","NR_repeaters-Core",2,"Rel-17","R4","Mon 14/12/20","Tue 22/03/22",1,"RP-212129","RP-221566","Valentin Gheorghiu","vgheorgh@qti.qualcomm.com","no Perf. part ; 2/7/21: 38.114 added;; 2/7/21: 38.106 added;; 20/6/22: FCD:12/12/2021->22/03/2023; Compl:0%->100%; WID: RP-213514->RP-212129; Stat Rep: ->RP-221566; Rapporteur: Qualcomm->Valentin Gheorghiu; Rap eMail: ->vgheorgh@qti.qualcomm.com; ","38.114; 38.106",90,46,null,null,"Wed 06/01/21","Mon 20/06/22"]
[2306,981036,"   UE Conformance - Increasing UE power high limit for CA and DC ","Power_Limit_CA_DC-UEConTest",2,"Rel-17","R5","Tue 13/12/22","Fri 22/09/23",1,"RP-221302","RP-232018","Kevin Wang / Jingzhou wu, Qualcomm / China Telecom","kevinw@qti.qualcomm.com /wujingzhou@chinatelecom.cn","17/3/23: FCD:09/09/2023->08/09/2023; Compl:0%->52%; Stat Rep: ->RP-230101; Rapporteur: Qualcomm->Kevin Wang / Jingzhou wu, Qualcomm / China Telecom; Rap eMail: ->kevinw@qti.qualcomm.com /wujingzhou@chinatelecom.cn; ...; 6/9/23: FCD:09/09/2023->22/09/2023",null,98,50,null,null,"Mon 09/01/23","Wed 06/09/23"]
[2307,930057,"Introduction of upper 700MHz A block E-UTRA band for the US ","LTE_upper_700MHz_A",1,"Rel-17","R4","Fri 17/09/21","Thu 01/12/22",1,"RP-212917",null,"Puloli ",null,"specs in [ ]; TR 36.8xx ; 6/1/22: WID:RP-212618->RP-212917",null,93,47,null,null,"Wed 29/09/21","Thu 06/01/22"]
[2311,930058,"High power UE (power class 2) for one NR FDD band ","NR_PC2_UE_FDD",1,"Rel-17","R4","Fri 17/09/21","Thu 01/12/22",1,"RP-212633",null,"China Unicom ",null,"follow-up WI of SI FS_NR_PC2_UE_FDD; for NR bands n1 and n3 ",null,93,47,null,null,"Wed 29/09/21","NA"]
[2316,0,"   Rel-17 NR intra band Carrier Aggregation (itrabCA)","-",2,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[2318,881105,"   Core part: NR_CA_R17_Intra","NR_CA_R17_Intra-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221319","RP-221314","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->24%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211752 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2322,900163,"   Core part: NR_intra_HPUE_R17","NR_intra_HPUE_R17-Core",2,"Rel-17","R4","Wed 10/02/21","Wed 22/06/22",1,"RP-221774","RP-221513 / 1773","Lingyu Kong, Huawei, HiSilicon","konglingyu4@hisilicon.com","; 13/9/21: Compl:0%->5% ; 22/3/22: Compl:5%->10%; 22/3/22: CD:22/03/2022->10/06/2022 ; 20/6/22: Stat Rep: RP-221513->RP-221513 / 1773; Rapporteur: Huawei->Lingyu Kong, Huawei, HiSilicon; Rap eMail: ->konglingyu4@hisilicon.com; ",null,90,46,null,null,"Wed 10/02/21","Mon 20/06/22"]
[2325,881106,"   Core part: NR_CADC_R17_2BDL_xBUL","NR_CADC_R17_2BDL_xBUL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221250","RP-221251","Aijun Cao, ZTE","cao.aijun@zte.com.cn","; 20/6/22: Rapporteur: ZTE->Aijun Cao, ZTE; Rap eMail: ->cao.aijun@zte.com.cn; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2330,881008,"NR iterbCA/Dual Connectivity for 3 bands DL with 2 bands UL","NR_CADC_R17_3BDL_2BUL",1,"Rel-17",null,"Mon 22/06/20","Wed 22/06/22",1,"RP-221253",null,"ZTE",null,"25/9/20: WID:RP-201374->RP-201541; 6/1/21: WID:RP-201541->RP-202201; 7/4/21: WID:RP-202201->RP-210497; 2/7/21: WID:RP-210497->RP-211060; 29/9/21: WID:RP-211060->RP-212512; 6/1/22: WID:RP-212512->RP-212889; 5/4/22: WID:RP-212889->RP-220146; 12/7/22: WID:RP",null,88,45,null,null,"Tue 28/07/20","Tue 12/07/22"]
[2334,881109,"   Core part: NR_CA_R17_4BDL_1BUL","NR_CA_R17_4BDL_1BUL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221321","RP-221316","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->45%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211754 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2337,881110,"   Core part: NR_CADC_R17_4BDL_2BUL","NR_CADC_R17_4BDL_2BUL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221396","RP-221397","Yue Wu, Samsung","yue.wu@samsung.com","20/6/22: FCD:15/09/2021->22/06/2022; Compl:0%->100%; Stat Rep: ->RP-221397; Rapporteur: Samsung->Yue Wu, Samsung; Rap eMail: ->yue.wu@samsung.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2338,881210,"   Perf. part: NR_CADC_R17_4BDL_2BUL","NR_CADC_R17_4BDL_2BUL-Perf",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221396","RP-221397","Yue Wu, Samsung","yue.wu@samsung.com","; 13/9/21: Compl:0%->70%; ; 22/3/22: Compl:70%->90%; 20/6/22: Rapporteur: Samsung->Yue Wu, Samsung; Rap eMail: ->yue.wu@samsung.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2343,890154,"   Core part: NR_PC2_CA_R17_2BDL_2BUL","NR_PC2_CA_R17_2BDL_2BUL-Core",2,"Rel-17","R4","Thu 17/09/20","Wed 22/06/22",1,"RP-221866","RP-221301","Liu, Bo, China Telecom","liubo1@chinatelecom.cn","basket WI; related to generic WI NR_SAR_PC2_interB_SUL_2BUL-Core; TR 38.8xx ; 13/9/21: Compl:0%->70%; 13/9/21: CD:Fri 17/12/21->Tue 22/03/22; 13/9/21: WID: RP-211 ; 20/6/22: WID: RP-202102 RP-202373 RP-210476 RP-211131 RP-211831 RP‑213649 RP-220...",null,89,45,null,null,"Fri 25/09/20","Mon 20/06/22"]
[2345,920066,"   UE Conformance - Rel-17 High power UE for NR inter-band Carrier Aggregation with 2 bands downlink and x bands uplink (x=1,2) ","NR_PC2_CA_R17_2BDL_2BUL-UEConTest",2,"Rel-17","R5","Tue 15/06/21","Tue 12/12/23",1,"RP-233581","RP-233580","Jingzhou Wu, Dan Song, China Telecom, China Mobile","wujingzhou@chinatelecom.cn, songdan@chinamobile.com","tested: REL-17 WI NR_PC2_CA_R17_2BDL_2BUL-Core ; 13/9/21: Compl:0%->15%; 13/9/21: CD:Tue 15/03/22->Tue 22/03/22; 1 ; 22/3/22: Compl:15%->18%; 20/6/22: Rapporteur: China Telecom->Jingzhou Wu, China Telecom; Rap eMail: ->wujingzhou@chinatelecom.cn...;...",null,92,47,null,null,"Fri 02/07/21","Tue 02/01/24"]
[2349,940089,"   UE Conformance - LTE/NR spectrum sharing in Band 34/n34 and Band 39/n39","DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39-UEConTest",2,"Rel-17","R5","Mon 13/12/21","Fri 11/03/22",1,"RP-213036","RP-220625","CMCC",null,"tested: REL-17 WI DSS_LTE_B34_NR_Bn34_LTE_B39_NR_Bn39-Core; ",null,94,48,null,null,"Thu 06/01/22","Tue 22/03/22"]
[2352,920273,"   Perf. Part: High-power UE operation for fixed-wireless/vehicle-mounted use cases in LTE bands and NR bands","LTE_NR_HPUE_FWVM-Perf",2,"Rel-17","R4","Wed 15/09/21","Wed 22/06/22",1,"RP-221795","RP-221199 / 1775","Vasenkari, Petri, Nokia","Petri.j.vasenkari@nokia.com","this is not a basket WI ; 13/9/21: CD:Wed 15/06/22->Wed 22/06/22; ; 22/3/22: Compl:0%->50% ; 20/6/22: FCD:22/09/2022->22/06/2022; Stat Rep: RP-221199->RP-221199 / 1775; Rapporteur: Nokia->Vasenkari, Petri, Nokia; Rap eMail: ->Petri.j.vasenkari@n...",null,92,47,null,null,"Fri 02/07/21","Mon 20/06/22"]
[2357,911119,"   Core part: ENDC_R17_1BLTE_1BNR_MSD","ENDC_R17_1BLTE_1BNR_MSD-Core",2,"Rel-17","R4","Thu 25/03/21","Thu 25/03/21",0.99,"RP-220709",null,"Huawei, HiSilicon",null,"20/6/22: WG: ->R4; FCD:25/03/2022->22/03/2023; Compl:0%->100%; WID: RP-220709->RP-213140; Stat Rep: ->RP-220858; Rapporteur: Huawei, HiSilicon->Zhang, Peng; Rap eMail: ->zhangpeng169@huawei.com20/6/22: 0%->100",null,91,46,null,null,"Fri 09/04/21","Mon 20/06/22"]
[2361,911211,"   Perf. Part: ENDC_PC2_R17_xLTE_yNR","ENDC_PC2_R17_xLTE_yNR-Perf",2,"Rel-17","R4","Fri 12/03/21","Wed 22/06/22",1,"RP-221322","RP-221318","Per Lindell, Ericsson","per.lindell@ericsson.com","compare REL-16 WI ENDC_UE_PC2_TDD_TDD and REL-16 WI ENDC_UE_PC2_FDD_TDD ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,91,46,null,null,"Wed 07/04/21","Mon 20/06/22"]
[{"$f":"A2364+1","v":2364},911118,"   Core part: LTE_NR_Simult_RxTx","LTE_NR_Simult_RxTx-Core",2,"Rel-17","R4","Fri 12/03/21","Wed 22/06/22",1,"RP-221521","RP-221520","Liu Ye, Huawei","leo.liuye@huawei.com","; 13/9/21: Compl:0%->70% ; 1/10/21: 38.839 added; ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",38.838999999999999,91,46,null,null,"Wed 07/04/21","Mon 20/06/22"]
[2365,911218,"   Stopped - Perf. part: LTE_NR_Simult_RxTx","LTE_NR_Simult_RxTx-Perf",2,"Rel-17","R4","Fri 12/03/21","Wed 22/06/22",1,"RP-221521","RP-221520","Liu Ye, Huawei","leo.liuye@huawei.com","; 13/9/21: Compl:0%->70% ; 6/6/22: Compl:70%->0%6/6/22: CD:22/03/2022->22/06/20226/6/22: WID: RP-220707->RP-2113826/6/22: Stat Rep: RP-212185->RP-221520; 20/6/22: Compl:0%->100%; Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; Sto",null,91,46,96,null,"Wed 07/04/21","Mon 20/06/22"]
[2370,890153,"   Core part: DC_R17_xBLTE_2BNR_yDL3UL","DC_R17_xBLTE_2BNR_yDL3UL-Core",2,"Rel-17","R4","Thu 17/09/20","Fri 11/03/22",1,"RP-220674","RP-220675","Samsung ",null,"basket WI; TR 37.717-21-22 ; 13/9/21: Compl:0%->70% ; ; ",null,89,45,null,null,"Fri 25/09/20","Tue 22/03/22"]
[2373,880180,"   Core part: NR_LTE_V2X_PC5_combos","NR_LTE_V2X_PC5_combos-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-213297","RP-221461","Yuan Gao, CATT","gaoyuan@catt.cn","25/9/20: 37.875 added;; 22/3/22: Compl:0%->95%; 20/6/22: Rapporteur: CATT->Yuan Gao, CATT; Rap eMail: ->gaoyuan@catt.cn; ",37.875,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2375,880094,"High power UE (power class 2) for EN-DC with 1 LTE band + 1 NR TDD band","ENDC_UE_PC2_R17_NR_TDD",1,"Rel-17",null,"Mon 22/06/20","Tue 06/06/23",1,"RP-221227",null,"China Unicom",null,"25/9/20: WID:RP-201328->RP-202079; 6/1/21: WID:RP-202079->RP-202838; 7/4/21: WID:RP-202838->RP-210327; 2/7/21: WID:RP-210327->RP-211073; 29/9/21: WID:RP-211073->RP-211853; 5/4/22: WID:RP-211853->RP-220388; 12/7/22: WID:RP-220388->RP-221227",null,88,45,null,null,"Tue 28/07/20","Tue 12/07/22"]
[2380,880195,"   Core part: DSS_LTE_B38_NR_Bn38","DSS_LTE_B38_NR_Bn38-Core",2,"Rel-17","R4","Wed 17/06/20","Tue 15/09/20",1,"RP-201314",null,"Vodafone",null,"25/9/20: 0%->100",null,88,45,null,null,"Tue 28/07/20","Fri 25/09/20"]
[2384,880098,"Dual Connectivity (DC) of 1 LTE band (1DL/1UL) and 1 NR band (1DL/1UL)","DC_R17_1BLTE_1BNR_2DL2UL",1,"Rel-17",null,"Mon 22/06/20","Wed 22/06/22",1,"RP-221257",null,"CHTTL",null,"25/9/20: WID:RP-201368->RP-201553; 6/1/21: WID:RP-201553->RP-202545; 7/4/21: WID:RP-202545->RP-210204; 2/7/21: WID:RP-210204->RP-211162; 29/9/21: WID:RP-211162->RP-212096; 6/1/22: WID:RP-212096->RP-213060; 5/4/22: WID:RP-213060->RP-220398; 12/7/22: WID:RP",null,88,45,null,null,"Tue 28/07/20","Tue 12/07/22"]
[2388,880199,"   Core part: DC_R17_2BLTE_1BNR_3DL2UL","DC_R17_2BLTE_1BNR_3DL2UL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221508","RP-221507","Liehai Liu, Huawei","liuliehai@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->85%; 20/6/22: Rapporteur: Huawei->Liehai Liu, Huawei; Rap eMail: ->liuliehai@huawei.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2391,881100,"   Core part: DC_R17_3BLTE_1BNR_4DL2UL","DC_R17_3BLTE_1BNR_4DL2UL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221320","RP-221315","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->74%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211753 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2392,881200,"   Perf. part: DC_R17_3BLTE_1BNR_4DL2UL","DC_R17_3BLTE_1BNR_4DL2UL-Perf",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221320","RP-221315","Per Lindell, Ericsson","per.lindell@ericsson.com","13/9/21: Compl:0%->74%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211753 ; 20/6/22: Rapporteur: Ericsson->Per Lindell, Ericsson; Rap eMail: ->per.lindell@ericsson.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2397,881102,"   Core part: DC_R17_xBLTE_2BNR_yDL2UL","DC_R17_xBLTE_2BNR_yDL2UL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221182","RP-221183","Sang-Wook Lee, LG Electronics","sangwook1.lee@lge.com","13/9/21: Compl:0%->80%13/9/21: CD:Wed 15/09/21->Tue 22/03/2213/9/21: Stat Rep: ->RP-211751; 20/6/22: Rapporteur: LG Electronics->Sang-Wook Lee, LG Electronics; Rap eMail: ->sangwook1.lee@lge.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2400,881103,"   Core part: DC_R17_xBLTE_yBNR_3DL3UL","DC_R17_xBLTE_yBNR_3DL3UL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-220202","RP-221233","Wubin Zhou, ZTE","zhou.wubin@zte.com.cn","; 6/6/22: Compl:0%->100% ; 20/6/22: Rapporteur: ZTE->Wubin Zhou, ZTE; Rap eMail: ->zhou.wubin@zte.com.cn; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2402,881004,"Dual Connectivity (DC) of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and 3 bands NR inter-band CA (3DL/1UL)","DC_R17_xBLTE_3BNR_yDL2UL",1,"Rel-17",null,"Mon 22/06/20","Wed 22/06/22",1,"RP-221235",null,"ZTE",null,"25/9/20: WID:RP-200715->RP-201712; 6/1/21: WID:RP-201712->RP-202194; 7/4/21: WID:RP-202194->RP-210346; 2/7/21: WID:RP-210346->RP-211056; 29/9/21: WID:RP-211056->RP-211805; 6/1/22: WID:RP-211805->RP-212885; 5/4/22: WID:RP-212885->RP-220205; 12/7/22: WID:RP",null,88,45,null,null,"Tue 28/07/20","Tue 12/07/22"]
[2407,881212,"   Perf. part: NR_SUL_combos_R17","NR_SUL_combos_R17-Perf",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221512","RP-221511","Zhang, Peng, Huawei","zhangpeng169@huawei.com","; 13/9/21: Compl:0%->60%; ; 22/3/22: Compl:60%->80%; 20/6/22: Rapporteur: Huawei->Zhang, Peng, Huawei; Rap eMail: ->zhangpeng169@huawei.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2411,911116,"   Core part: NR_RAIL_EU_900MHz","NR_RAIL_EU_900MHz-Core",2,"Rel-17","R4","Fri 12/03/21","Thu 22/09/22",1,"RP‑211495","RP-221071/1071/1808/1816","Ingo Wendler, UIC","ingo dot wendler at sbb dot ch","FDD: UL: 874.4-880MHz, DL: 919.4-925MHz ; 1/10/21: 38.853 added;; 22/3/22: Compl:0 20/6/22: FCD:22/03/2023->22/09/2022; Compl:100%->95%; Stat Rep: RP-221071->RP-221071/1071/1808/1816; Rapporteur: Union Internationale Chemins de Fer (UIC)->Ingo Wen...",38.853000000000002,91,46,null,null,"Wed 07/04/21","Fri 09/09/22"]
[2415,911217,"   Perf. part: NR_RAIL_EU_1900MHz_TDD","NR_RAIL_EU_1900MHz_TDD-Perf",2,"Rel-17","R4","Fri 12/03/21","Fri 11/03/22",1,"RP‑211496","RP-220148","Union Internationale Chemins de Fer (UIC) ",null,"; ",null,91,46,null,null,"Wed 07/04/21","Tue 22/03/22"]
[2418,860241,"   Perf. part: Extending current NR operation to 71GHz","NR_ext_to_71GHz-Perf",2,"Rel-17","R1","Mon 16/12/19","Fri 03/03/23",1,"RP-222656","RP-230662","Jing Sun (RAN1); Aida Vera Lopez (RAN4), Qualcomm Incorporated; Intel Corporation","jingsun@qti.qualcomm.com; aida.l.vera.lopez@intel.com","affects: NR.; 13/9/21: CD:Wed 15/09/21->Wed 22/06/22; ; 22/3/22: Compl:0%->25%; 22/3/22: 6/6/22: CD:12/09/2022->22/12/2022 ; 20/6/22: WG: R4->R1; Stat Rep: RP-221349->RP-221349 / 1749; Rapporteur: Qualcomm->Jing Sun (RAN1); Aida Vera Lopez (RAN4), ...",null,86,44,null,null,"Tue 14/01/20","Fri 17/03/23"]
[2420,870060,"Study on IMT parameters for 6.425-7.025GHz, 7.025-7.125GHz and 10.0-10.5GHz","FS_NR_IMT_param",1,"Rel-17","R4","Wed 25/03/20","Tue 15/12/20",1,"RP-202276",null,"Ericsson",null,"affects: NR. TR 38.8xx; 6/1/21: WID:RP-200513->RP-202276; 7/4/21: 0%->100",null,87,44,null,null,"Tue 14/01/20","Wed 07/04/21"]
[2423,870263,"   Perf. part: Introduction of NR band n13","NR_n13-Perf",2,"Rel-17","R4","Wed 25/03/20","Tue 15/09/20",1,"RP-200480",null,"Huawei",null,"affects: NR. TR 38.8xx; 6/1/21: 0%->100",null,87,44,null,null,"Tue 14/01/20","Wed 06/01/21"]
[2427,880084,"Introduction of NR band 24","NR_band_n24",1,"Rel-17","R4","Thu 19/03/20","Fri 19/03/21",1,"RP-211505",null,"Ligado Networks",null,"2/7/21: WID:RP-201357->RP-211505",null,88,45,null,null,"Tue 28/07/20","Fri 02/07/21"]
[2429,880284,"   Perf. part: Introduction of NR band 24","NR_band_n24-Perf",2,"Rel-17","R4","Thu 19/03/20","Fri 19/03/21",1,"RP-211505",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"Tue 28/07/20","Wed 07/04/21"]
[2434,920175,"   Core part: Introduction of operation in full unlicensed band 5925-7125MHz for NR ","NR_6GHz_unlic_full-Core",2,"Rel-17","R4","Tue 15/06/21","Tue 22/03/22",1,"RP-212683","RP-220450","Alexander Sayenko","asayenko@apple.com","in contrast to NR_6GHz_unlic_EU this WI targets Region 2 (Canada, Brazil, Peru, Chile) and Region 3 (South Korea); TR 38.8xx ; 20/6/22: FCD:15/03/2022->22/03/2022; Compl:0%->100%; WID: RP-213683->RP-212683; Stat Rep: ->RP-220450; Rapporteur: Apple->Alexa",null,92,47,null,null,"Fri 02/07/21","Mon 20/06/22"]
[2438,890251,"   Perf. part: Introduction of lower 6GHz NR unlicensed operation for Europe ","NR_6GHz_unlic_EU-Perf",2,"Rel-17","R4","Thu 17/09/20","Fri 11/03/22",1,"RP-213604","RP-220325","Nokia ",null,"missing target dates to be updated ; 13/9/21: Compl:0%->15%; 13/9/21: CD:Fri 17/06/22->Tue 21/12/21; 13/9/21: Stat Rep: ->RP-211822; ",null,89,45,null,null,"Fri 25/09/20","Tue 22/03/22"]
[2442,900066,"Introduction of NR band n85 ","NR_n85",1,"Rel-17","R4","Mon 14/12/20","Fri 11/06/21",1,"RP-210707",null,"Ericsson ",null,"; 7/4/21: WID:RP-202830->RP-210707",null,90,46,null,null,"Wed 06/01/21","Wed 07/04/21"]
[2443,900166,"   Core part: Introduction of NR band n85 ","NR_n85-Core",2,"Rel-17","R4","Mon 14/12/20","Fri 11/06/21",1,"RP-210707",null,"Ericsson ",null,"; 2/7/21: 0%->100",null,90,46,null,null,"Wed 06/01/21","Fri 02/07/21"]
[2447,880283,"   Perf. part: NR_SUL_UL_n24","NR_SUL_UL_n24-Perf",2,"Rel-17","R4","Thu 19/03/20","Fri 19/03/21",1,"RP-210341",null,"Ligado Networks",null,"7/4/21: 0%->100",null,88,45,null,null,"Tue 28/07/20","Wed 07/04/21"]
[2450,880285,"   Perf. part: NR_SUL_band_1880_1920MHz","NR_SUL_band_1880_1920MHz-Perf",2,"Rel-17","R4","Mon 22/06/20","Tue 15/12/20",1,"RP-201363",null,"CMCC",null,"6/1/21: 0%->100",null,88,45,null,null,"Tue 28/07/20","Wed 06/01/21"]
[2454,900055,"UE Conformance - New Rel-17 NR licensed bands and extension of existing NR bands ","NR_lic_bands_BW_R17-UEConTest",1,"Rel-17","R5","Mon 14/12/20","Thu 01/12/22",1,"RP-223434","RP-223215","Yuxin Hao, Huawei Technologies. Co., Ltd","haoyuxin@huawei.com","tested: REL-17 WIs: NR_n13, NR_47GHz_band, NR_band_n24, NR_SUL_UL_n24, NR_SUL_band_1880_1920MHz, NR_SUL_band_2300_2400MHz, NR_bands_R17_BWs, NR_FR1_35MHz_45MHz_BW ; 8/4/21: 0%->16 ; 20/6/22: Rapporteur: Huawei->Yuxin Hao, Huawei Technologies. Co.,...;...",null,90,46,null,null,"Wed 06/01/21","Mon 09/01/23"]
[2456,911020,"New bands and bandwidth allocation for 5G terrestrial broadcast - part 1","LTE_terr_bcast_bands_part1",1,"Rel-17","R1,R2,R3","Fri 01/01/21","Tue 22/03/22",1,"RP-211144",null,"EBU",null,"13/09/21: \"-part 1|\" added' R4->R1, R2, R3",null,91,46,null,null,"Thu 08/04/21","Fri 02/07/21"]
[2461,880081,"Modification of LTE Band 24 Specifications to comply with updated regulatory emission limits","LTE_B24_mod",1,"Rel-17",null,"Mon 15/06/20","Wed 15/12/21",1,"RP-211507",null,"Ligado Networks",null,"2/7/21: WID:RP-201356->RP-211507",null,88,45,null,null,"Tue 28/07/20","Fri 02/07/21"]
[2465,0,"Rel-17 LTE inter-band Carrier Aggregation (LTE iterbCA)","-",1,"Rel-17",null,"Thu 09/06/16","Thu 09/06/16",1,"-","-","-","-",null,"26.234; 26.247 ",null,null,null,null,"Fri 29/08/14","Fri 29/08/14"]
[2469,880088,"LTE iterbCA for 3 bands DL with 1 band UL","LTE_CA_R17_3BDL_1BUL",1,"Rel-17",null,"Mon 22/06/20","Wed 22/06/22",1,"RP-221526",null,"Huawei",null,"25/9/20: WID:RP-201244->RP-201730; 6/1/21: WID:RP-201730->RP-202615; 7/4/21: WID:RP-202615->RP-210540; 2/7/21: WID:RP-210540->RP-211388; 29/9/21: WID:RP-211388->RP-212192; 6/1/22: WID:RP-212192->RP-213144; 5/4/22: WID:RP-213144->RP-220715; 12/7/22: WID:RP",null,88,45,null,null,"Tue 28/07/20","Tue 12/07/22"]
[2470,880188,"   Core part: LTE_CA_R17_3BDL_1BUL","LTE_CA_R17_3BDL_1BUL-Core",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221526","RP-221525","Mohammad Abdi Abyaneh, Huawei, HiSilicon","mohammad.abdi.abyaneh@huawei.com","; 22/3/22: Compl:0%->67%; 20/6/22: Rapporteur: Huawei->Mohammad Abdi Abyaneh, Huawei, HiSilicon; Rap eMail: ->mohammad.abdi.abyaneh@huawei.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2474,880289,"   Perf. part: LTE_CA_R17_xBDL_1BUL","LTE_CA_R17_xBDL_1BUL-Perf",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221305","RP-221306","Iwajlo ANGELOW, Nokia","iwajlo.angelow@nokia.com","; 13/9/21: Compl:0%->85%; 13/9/21: CD:Wed 15/09/21->Tue 22/03/22; ; 20/6/22: Rapporteur: Nokia->Iwajlo ANGELOW, Nokia; Rap eMail: ->iwajlo.angelow@nokia.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2477,880290,"   Perf. part: LTE_CA_R17_2BDL_2BUL","LTE_CA_R17_2BDL_2BUL-Perf",2,"Rel-17","R4","Mon 22/06/20","Wed 22/06/22",1,"RP-221528","RP-221527","Liu Ye, Huawei","leo.liuye@huawei.com","22/3/22: CD:15/09/2021->12/06/202222/3/22: Stat Rep: ->RP-220716 ; 20/6/22: Rapporteur: Huawei->Liu Ye, Huawei; Rap eMail: ->leo.liuye@huawei.com; ",null,88,45,null,null,"Tue 28/07/20","Mon 20/06/22"]
[2481,1010051,"UE Conformance - Rel-17 LTE CA Configurations ","LTE_CA_R17-UEConTest",1,"Rel-17","R5","Sat 09/09/23","Thu 12/12/24",1,"RP-242869","RP-242868","Lei GAO, China Telecom","gaol8@chinatelecom.cn","8/12/23: Compl:0%->5%; Stat Rep: ->RP-233566; Rapporteur: China Telecom->Lei GAO, China Telecom; Rap eMail: ->gaol8@chinatelecom.cn; ; 14/3/24: FCD:11/12/2024->12/12/2024; Compl:5%->30%; Stat Rep: RP-233566->RP-240360; ; 13/6/24: Compl:30%->50%; Stat ...",null,101,51,null,null,"Fri 06/10/23","Fri 24/01/25"]
[2483,890014,"Study on the security of AMF re-allocation ","FS_AMFREAL_SEC",1,"Rel-17","S3","Wed 16/09/20","Fri 10/12/21",1,"SP-200721",null,"Tsiatsis, Vlasios, Ericsson ","vlasios.tsiatsis@ericsson.com ","5/12/20: 0%->30; 19/3/21: 30%->50; 19/3/21: FCD:12/03/2021->09/21; 11/6/21: 50%->70; 11/6/21: FCD:Wed 08/09/->12/21; 13/9/21: 70%->75; 12/3/22: 75%->100",33.863999999999997,89,45,null,null,"Thu 10/09/20","Sat 12/03/22"]
[2489,900029,"Study on 5G media streaming extensions ","FS_5GMS_EXT",1,"Rel-17","S4","Fri 04/12/20","Fri 11/03/22",1,"SP-200937",null,"Iraj Sodagar, Company, Tencent ","irajs@live.com ","21/3/21: 0%->5; 11/6/21: 5%->40; 2/7/21: 26.804 added;; 13/9/21: 40%->50; 13/12/21: 50%->60; 13/12/21: FCD:Wed 08/09/->03/22; 12/3/22: 60%->100",26.803999999999998,90,46,null,null,"Thu 03/12/20","Sat 12/03/22"]
[{"$f":"A2492+1","v":2492},870012,"Study on the use of NBMP in FLUS ","FS_FLUS_NBMP",1,"Rel-17","S4","Wed 25/03/20","Wed 08/09/21",1,"SP-200053",null,"Iraj Sodagar","irajsodagar@tencent.com ","; 10/6/20: 0%->10; 5/12/20: 10%->30; 5/12/20: FCD:11/12/2020->09/20; 21/3/21: 30%->40; 11/6/21: 40%->96; 13/9/21: 96%->100",26.939,87,44,null,null,"Fri 06/12/19","Mon 13/09/21"]
[2496,911033,"   CT4 aspects of FS_eIMS5G2","FS_eIMS5G2",2,"Rel-17","C4","Fri 25/09/20","Fri 11/03/22",1,"CP-201358",null,"Haitao Wei (Huawei) ","weihaitao@huawei.com ","13/9/20: 0%->5; 13/9/20: FCD:19/03/2021->09/21; 25/9/20: 23.700-10 added;; 5/12/20: 5%->10; 5/12/20: 10%->70; 21/3/21: 70%->15; 8/4/21: 15%->30; 11/6/21: 30%->40; 11/6/21: 40%->30; 14/6/21: 30%->40; 13/9/21: 40%->50; 13/9/21: FCD:Wed 08/09/->12/21; 13/ ","23.700-10",88,45,null,null,"Fri 26/06/20","Sat 12/03/22"]
[2497,890002,"Study on Port Number Allocation Alternatives for New 3GPP Interfaces ","FS_PortAl",1,"Rel-17","C4","Wed 16/09/20","Fri 11/03/22",1,"CP-220391",null,"Giorgi Gulbani, Huawei","giorgi.gulbani@huawei.com ","13/9/20: FCD:11/06/2021->09/21; 25/9/20: WID:CP-202029->CP-202243; 5/12/20: 0%->30; 21/3/21: 30%->50; 11/6/21: 50%->70; 13/9/21: 70%->85; 13/9/21: FCD:Wed 08/09/->03/22; 13/12/21: 85%->100; 22/3/22: WID:CP-202243->CP-220391",null,89,45,null,null,"Fri 11/09/20","Tue 22/03/22"]
[2501,880076,"Study on enhancement for data collection for NR and ENDC","FS_NR_ENDC_data_collect",1,"Rel-17","R3","Mon 22/06/20","Fri 11/03/22",1,"RP-201304","RP-220634","CMCC",null,"25/9/20: WID:RP-201304->RP-201620; 25/9/20: 37.817 added;; 25/9/20: 38.817 added;; 13/9/21: Compl:0%->60% ; ; 5/4/22: 100%->100","37.817; 38.817",88,45,null,null,"Tue 28/07/20","Tue 05/04/22"]
[2504,900059,"Study on extended 600MHz NR band ","FS_NR_600MHz_ext",1,"Rel-17","R4","Mon 14/12/20","Wed 08/09/21",1,"RP-202924",null,"Spark ",null,"TR 38.8xx ; 29/9/21: 0%->100",null,90,46,null,null,"Wed 06/01/21","Wed 29/09/21"]
[2510,0,"--- RELEASE 16 ---","-",1,"Rel-16",null,"2016-03-15","2016-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2512,0,"Enhancement of Ultra-Reliable (UR) Low Latency Communications (URLLC)","-",1,"Rel-16",null,"2017-12-15","2017-12-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2516,820019,"   Stage 2 of 5G_URLLC ","5G_URLLC",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181233",null,"Hui Ni, Huawei","Hui.ni@huawei.com","14/3/19: 0%->50; 31/5/19: 50%->80; 13/9/19: 80%->100","23.501; 23.502; 23.503",82,42,null,null,"2018-12-06","2019-09-13"]
[2519,870059,"      CT1 Aspects of 5G_URLLC","5G_URLLC",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-192022",null,"Qi Caixia, Huawei ","caixia.qi@huawei.com ","26/3/20: CT1 aspects added as per Peter's e-mail; 26/3/20: 0%->100",null,87,44,null,null,"2019-05-31","2020-03-26"]
[2523,1000013,"   Management Aspects of URLLC ","URLLC_Mgt",2,"Rel-18","S5","2023-06-08","2024-03-03",1,"SP-230631",null,"Wang Zhaoning, China Unicom, ","wangzn18@chinaunicom.cn ","; 7/9/23: 0%->10; 8/12/23: 10%->20; 14/3/24: 20%->100","28.541; 28.552; 28.554 ",100,51,null,null,"2023-06-08","2024-03-14"]
[2524,780030,"   Stopped - Study on EPC support for Mobility with Low Latency Communication","FS_LLC_Mob",2,"Rel-16","S2","2017-12-15","2018-09-14",1,"SP-171069",null,"Chris PUDNEY","chris dot pudney at vodafone dot com","16/3/18: 0%->35¦7/6/18: 35%->75¦6/6/19: stopped at 75% as per SP-190395","new 23.739",78,40,84,null,"2017-12-15","2018-06-07"]
[2528,830174,"   Core part: Physical Layer Enhancements for NR URLLC","NR_L1enh_URLLC-Core",2,"Rel-16","R1","2019-03-01","2020-02-28",1,"RP-190726",null,"Huawei",null,"26/3/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-03-26"]
[2531,830080,"Support of NR Industrial Internet of Things (IoT)","NR_IIOT",1,"Rel-16","R2","2018-06-15","2022-03-11",1,"RP-192590",null,"Nokia",null,"26/6/19: WID:RP-190728->RP-191561; 8/10/19: WID:RP-191561->RP-192324; 14/1/20: WID:RP-192324->RP-192590",null,83,42,null,null,"2019-03-26","2020-01-14"]
[2537,750004,"Study on Communication for Automation in Vertical Domains","FS_CAV",1,"Rel-16","S1","2017-03-02","2018-03-15",1,"SP-170169",null,"Walewski, Joachim, Siemens AG","joachim.walewski@siemens.com ","7/6/17: 0%->30¦25/8/17: FCD:12/17->03/18¦11/9/17: 30%->65¦15/12/17: 65%->85¦16/3/18: 85%->95¦7/6/18: 95%->100",22.803999999999998,75,38,null,null,"2017-03-02","2018-06-07"]
[2539,830042,"5GS Enhanced support of Vertical and LAN Services","Vertical_LAN",1,"Rel-16",null,"2018-06-06","2020-03-12",1,"SP-181120",null,"Devaki Chandramouli, Nokia","Devaki.chandramouli@nokia.com",null,null,82,42,null,null,"2018-12-06","2018-06-14"]
[2543,840027,"   Security for Vertical_LAN ","Vertical_LAN_SEC",2,"Rel-16","S3","2019-06-06","2020-03-12",1,"SP-190352",null,"Jerichow, Anja, Nokia ","anja.jerichow@nokia.com ","13/9/19: 0%->30; 6/12/19: 30%->95; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 95%->100",33.500999999999998,84,43,null,null,"2019-05-31","2020-06-26"]
[2546,830036,"      CT3 aspects of Vertical_LAN","Vertical_LAN",3,"Rel-16","C3","2019-03-14","2020-03-12",1,"CP-201174",null,"WON, Sung Hwan, Nokia","sung.won@nokia.com","31/5/19: FCD:12/12/2019->03/20; 3/6/19: WID:CP-190195->CP-191157; 13/9/19: 0%->30; 6/12/19: 30%->60; 6/12/19: WID:CP-192258->CP-193142; 26/3/20: 60%->100; 26/6/20: WID:CP-193272->CP-201174","29.122; 29.507; 29.508; 29.512; 29.513; 29.514; 29.519; 29.520; 29.521; 29.522; 29.523; 29.525; 29.554; 29.561; 29.594; 29.061",83,42,null,null,"2018-12-06","2020-06-26"]
[2550,850019,"   Security aspects of SEAL","SEAL",2,"Rel-16","S3","2019-09-19","2020-06-12",1,"SP-190901",null,"Rajavelsamy Rajadurai (Samsung) ","rajvel@samsung.com ","; 6/12/19: 0%->40; 25/3/20: 40%->65; 25/3/20: FCD:12/03/2020->06/20; 26/6/20: 65%->100","New ",85,43,null,null,"2019-09-13","2020-06-26"]
[2551,850006,"   CT aspects of SEAL ","SEAL",2,"Rel-16","ct","2019-09-19","2020-03-12",1,"CP-192255",null,"Sapan Shah (Samsung Electronics) ","sapan.shah@samsung.com ",null,"New ",85,43,null,null,"2019-09-13","NA"]
[2555,750045,"   Study on NR-based access to unlicensed spectrum","FS_NR_unlic",2,"Rel-16","R1","2017-03-15","2018-12-14",1,"RP-181339",null,"Qualcomm",null,"TR 38.8XX19/6/17: WID: RP-170828->RP-171416¦30/6/17: 32.889 added;¦19/9/17: WID: RP-171416->RP-17202127/3/18: Compl:0%->10%¦27/6/18: Compl:10%->40%¦27/6/18: CD:Fri 15/06/18->Sat 15/12/18¦16/1/19: 40%->100",32.889000000000003,75,38,null,null,"2017-03-21","2019-01-16"]
[2559,800006,"LAN support in 5G","5GLAN",1,"Rel-16","S1","2017-06-05","2018-12-14",1,"SP-180593",null,"Almodovar Chico, Jose Luis, KPN","jose.almodovarchico@tno.nl","11/3/22: 99%->100","22.261; 22.278",80,41,null,null,"2018-06-06","2022-03-11"]
[2564,830043,"Cellular IoT support and evolution for the 5G System","5G_CIoT",1,"Rel-16",null,"2017-09-08","2020-06-12",1,"SP-181118",null,null,null,null,null,83,42,null,null,"2018-12-06","NA"]
[2566,820015,"   Stage 2 of 5G_CIoT","5G_CIoT",2,"Rel-16","S2","2018-12-13","2019-06-20",1,"SP-181118",null,"Sebastian Speicher ","sspeiche@qti.qualcomm.com","14/3/19: 0%->50; 31/5/19: 50%->95; 13/9/19: 95%->98; 22/3/22: 98%->100","23.501; 23.502",82,42,null,null,"2018-12-06","2022-03-22"]
[2570,830040,"      CT4 aspects of 5G_CIoT","5G_CIoT",3,"Rel-16","C4","2019-03-14","2020-03-12",1,"CP-200147",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com","31/5/19: 0%->10; 3/6/19: WID:CP-190198->CP-111158; 3/6/19: FCD:12/12/2019->03/20; 13/9/19: 10%->25; 6/12/19: 25%->60; 26/3/20: 60%->90; 26/6/20: 90%->100","23.008; 29.274; 29.502; 29.503; 29.505; 29.518",83,42,null,null,"2018-12-06","2020-06-26"]
[2573,800033,"Study on evolution of Cellular IoT security for the 5G System","FS_CIoT_sec_5G",1,"Rel-16","S3","2018-06-06","2019-12-12",1,"SP-180440",null,"Noamen Ben Henda ","noamen.ben.henda@ericsson.com","6/8/18: 33.861 added;¦7/12/18: 5%->30¦20/3/19: 30%->75¦20/3/19: FCD:019->09/19; 31/5/19: 75%->80; 13/9/19: FCD:12/09/2019->12/20; 13/9/19: 80%->90; 6/12/19: 90%->95; 26/6/20: 95%->100","New; 33.861",80,41,null,null,"2018-06-06","2020-06-26"]
[2577,800283,"   Perf. part: Additional MTC enhancements for LTE","LTE_eMTC5-Perf",2,"Rel-16","R4","2018-06-15","2020-06-15",1,"RP-192875",null,"Ericsson",null,"26/3/19: WID:RP-182891->RP-190770; 6/1/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-01-06"]
[2578,800084,"Additional enhancements for NB-IoT","NB_IOTenh3",1,"Rel-16","R1","2018-06-15","2020-06-15",1,"RP-200293",null,"Huawei",null,"RAN3 impact?¦16/1/19: WID:RP-181451->RP-182902¦26/3/19: WID:RP-182902->RP-190757; 26/6/19: WID:RP-190757->RP-191576; 8/10/19: WID:RP-191576->RP-192313; 14/1/20: WID:RP-192313->RP-193224; 26/3/20: WID:RP-193224->RP-200293",null,80,41,null,null,"2018-06-27","2020-03-26"]
[2582,770004,"   Study on 5G message service for MIoT","FS_5GMSG",2,"Rel-16","S1","2016-06-18","2018-09-14",1,"SP-170704",null,"Zheng, Jianping, China Mobile","zhengjianping@chinamobile.com","15/12/17: 22.824 added;¦15/12/17: 0%->25¦16/3/18: 25%->60¦10/9/18: 60%->95¦4/12/18: 95%->100","New; 22.824",77,39,null,null,"2017-09-08","2018-12-04"]
[2586,820024,"Improvement of V2X service Handling ","V2XIMP",1,"Rel-16","S1","2018-10-25","2018-12-04",1,"SP-181013",null,"SungDuck Chun; LG Electronics","sungduck.chun@lge.com","4/12/18: 0%->95¦14/3/19: 95%->100",22.186,82,42,null,null,"2018-12-04","2019-03-14"]
[2591,840075,"      CT1 aspects of V2XAPP ","V2XAPP",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-192077",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","13/9/19: 0%->10; 6/12/19: 10%->30; 26/3/20: 30%->65; 26/6/20: 65%->100","24.386; 27.007",84,43,null,null,"2019-05-31","2020-06-26"]
[2593,840077,"      CT4 aspects of V2XAPP ","V2XAPP",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-192077",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","26/3/20: 0%->100","23.003; 23.008",84,43,null,null,"2019-05-31","2020-03-26"]
[2596,820018,"   Stage 2 of eV2XARC","eV2XARC",2,"Rel-16","S2","2018-12-13","2019-06-14",1,"SP-181121",null,"LaeYoung Kim, LG Electronics","laeyoung.kim@lge.com ","14/3/19: 0%->30; 31/5/19: 30%->75; 26/6/19: 24.588 added;; 13/9/19: 75%->90; 6/12/19: 90%->96; 25/3/20: 96%->100","23.501; 23.502; 23.503; 23.285; 24.588",82,42,null,null,"2018-12-06","2020-03-25"]
[2601,840082,"      CT6 aspects of eV2XARC ","eV2XARC",3,"Rel-16","C6","2019-06-06","2020-03-12",1,"CP-201343",null,"Herrero Veron, Christian (Huawei) ","Christian.Herrero at huawei.com ","26/3/20: 0%->100",31.102,84,43,null,null,"2019-05-31","2020-03-26"]
[2604,770029,"Study on V2X Media Handling and Interaction","FS_mV2X",1,"Rel-16","S4","2017-09-08","2019-09-12",1,"SP-170799",null,"Jung, Kyunghun, Samsung Electronics Co., Ltd","kyunghun.jung@samsung.com","15/12/17: 26.985 added;¦15/12/17: 0%->30¦16/3/18: 30%->50¦22/3/18: FCD:09/18->12/18¦7/6/18: 50%->60. 14/06/18: Moved from Rel-15¦10/9/18: 60%->80¦13/12/18: 80%->60¦13/12/18: FCD:12/18->09/19¦12/3/19: 60%->70; 31/5/19: 70%->80; 26/6/20: 80%->100","New; 26.985",77,39,null,null,"2017-09-08","2020-06-26"]
[2605,830023,"Study on Security Aspects of 3GPP support for Advanced V2X Services ","FS_eV2X_Sec",1,"Rel-16","S3","2019-03-07","2020-03-12",1,"SP-190108",null,"Joonwoong Kim, LG Electronics","joonwoong.kim@lge.com","31/5/19: 0%->20; 13/9/19: 20%->60; 13/9/19: FCD:05/09/2019->12/20; 6/12/19: 60%->75; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: 75%->100","New",83,42,null,null,"2019-03-14","2020-06-26"]
[2609,880069,"   UE Conformance Test Aspects - 5G V2X with NR sidelink","5G_V2X_NRSL_eV2XARC-UEConTest",2,"Rel-16","R5","2020-06-22","2025-06-06",0.87,"RP-200894","RP-250440","Xuesong Wang, Huawei Technologies. Co., Ltd","wangxuesong743@huawei.com","8/10/20: 0%->5; 8/4/21: 5%->11; 2/7/21: 11%->18; 22/3/22: Compl:18%->43%; ; 5/4/22: WID:RP-200894->RP-220744 20/6/22: Rapporteur: Huawei->Xuesong Wang, Huawei Technologies. Co., Ltd; Rap eMail: ->wangxuesong743@huawei.com12/7/22: WID:RP-20089...; 9/1...",null,88,45,null,null,"2020-07-28","2025-03-06"]
[2613,800049,"   Stage 1 of 5G_HYPOS","5G_HYPOS",2,"Rel-16","S1","2018-06-06","2018-12-14",1,"SP-180329",null,"Ries, Lionel, ESA","lionel.ries at esa.int ","10/9/18: 0%->50¦10/9/18: FCD:09/18->12/18¦4/12/18: 50%->100",22.260999999999999,80,41,null,null,"2018-06-06","2018-12-04"]
[2618,830003,"   CT aspects of 5G_eLCS","5G_eLCS",2,"Rel-16","ct","2019-03-07","2019-12-05",1,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","17/9/19: WID:CP-190014->CP-192260",null,83,42,null,null,"2018-12-06","2019-09-17"]
[{"$f":"A2620+1","v":2620},830045,"      CT3 aspects of 5G_eLCS","5G_eLCS",3,"Rel-16","C3","2019-03-07","2019-12-05",1,"CP-192260",null,"Tingfang Tang, CATT","tangtingfang@catt.cn","3/6/19: WID:CP-190190->CP-191064; 26/3/20: 0%->25; 26/6/20: 25%->85","29.522; 29.122",83,42,null,null,"2018-12-06","2020-06-26"]
[2623,830077,"NR positioning support","NR_pos",1,"Rel-16","R1","2018-06-15","2023-09-08",0.99,"RP-192581",null,"Intel",null,"26/6/19: WID:RP-190752->RP-191156; 14/1/20: WID:RP-191156->RP-192581",null,83,42,null,null,"2019-03-26","2020-01-14"]
[2628,900057,"   UE Conformance Test Aspects - NR positioning support ","NR_pos-UEConTest",2,"Rel-16","R5","2020-12-14","2023-09-08",1,"RP-212227","RP-231835","Xiaoyang TIAN, CATT","tianxiaoyang@catt.cn","tested: REL-16 WI NR_pos-Core ; 8/4/21: 0%->5; 29/9/21: WID:RP-202727->RP-212227; 22/3/22: Compl:5%->54%; ; 20/6/22: Rapporteur: CATT->Xiaoyang TIAN, CATT; Rap eMail: ->tianxiaoyang@catt.cn12/7/22: WID:RP-212227->RP-221450 ; ;...; 9/12/22: FCD:22/12...",null,90,46,null,null,"2021-01-06","2023-09-06"]
[2629,0,"UE radio capability signalling optimization","-",1,"Rel-16",null,"2018-06-06","2018-06-06",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2632,830027,"   Stage 2 of RACS","RACS",2,"Rel-16","S2","2019-03-07","2019-06-06",1,"SP-190180",null,"Haris Zisimopoulos ","harisz@qti.qualcomm.com","31/5/19: 0%->90; 26/6/19: 29.673 added;; 13/9/19: 90%->100","23.501; 23.502; 23.401; 29.673",83,42,null,null,"2019-03-14","2019-09-13"]
[2636,840057,"      CT4 aspects of RACS","RACS",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-200058",null,"Waqar Zia; Qualcomm Incorporated","wzia@qti.qualcomm.com ","13/9/19: 0%->20; 6/12/19: 20%->75; 26/3/20: 75%->90; 26/6/20: 90%->100","23.003; 23.008; 29.230; 29.274; 29.510; 29.518",84,43,null,null,"2019-05-31","2020-06-26"]
[2641,800099,"Study on solutions for NR to support non-terrestrial networks (NTN)","FS_NR_NTN_solutions",1,"Rel-16","R3","2018-06-15","2019-12-13",1,"RP-190710",null,"Thales",null,"TR 38.xx1¦compare REL-15 SI FS_NR_nonterr_nw¦26/3/19: WID:RP-181370->RP-190710; 14/1/20: 0%->100",38.820999999999998,80,41,null,null,"2018-06-27","2023-03-17"]
[2644,760047,"   Study of enablers for Network Automation for 5G ","FS_eNA",2,"Rel-16","S2","2017-06-05","2018-12-14",1,"SP-180792",null,"Xiaobo Wu, Huawei Technologies ","wuxiaobo@huawei.com","16/3/18: FCD:09/18->06/18¦16/3/18: 0%->15¦7/6/18: 15%->30¦15/6/18: WID:SP-170383->SP-180613¦15/6/18: FCD:06/18->09/18¦10/9/18: 30%->50¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP-180613->SP-180792¦7/12/18: 50%->90¦14/3/19: 90%->94; 31/5/19: 94%->100","new 23.791",76,39,null,null,"2017-06-03","2019-05-31"]
[2647,830048,"      CT3 aspects of eNA","eNA",3,"Rel-16","C3","2019-03-07","2020-03-12",1,"CP-192259",null,"Yali Yan, Huawei","yanyali@huawei.com","31/5/19: 0%->20; 3/6/19: WID:CP-190194->CP-191111; 13/9/19: 20%->55; 6/12/19: 55%->85; 6/12/19: FCD:05/12/2019->03/20; 26/3/20: 85%->100","29.122; 29.508; 29.514; 29.520; 29.522; 29.523; 29.554",83,42,null,null,"2018-12-06","2020-03-26"]
[2650,760044,"Study on the Wireless and Wireline Convergence for the 5G system architecture ","FS_5WWC",1,"Rel-16","S2","2017-06-05","2018-12-14",1,"SP-170380",null,"Marco Spini, Huawei Technologies","m.spini@huawei.com","11/9/17: 0%->15¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: 15%->25¦7/6/18: 25%->35¦10/9/18: 35%->60¦10/9/18: FCD:06/18->12/18¦7/12/18: 60%->100",23.716000000000001,76,39,null,null,"2017-06-03","2018-12-07"]
[2655,829911,"      CT1 aspects of 5WWC","5WWC",3,"Rel-16","C1","2019-03-07","2020-03-12",1,"CP-192079",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","31/5/19: 0%->30; 3/6/19: WID:CP-190200->CP-191156; 3/6/19: FCD:05/12/2019->03/20; 13/9/19: 30%->60; 6/12/19: 60%->80; 26/3/20: 80%->95; 30/6/20: 95%->100","24.501; 24.502; 24.526",82,42,null,null,"2018-12-06","2020-06-30"]
[2656,829912,"      CT3 aspects of 5WWC","5WWC",3,"Rel-16","C3","2019-03-07","2020-03-12",1,"CP-192079",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","31/5/19: 0%->15; 3/6/19: WID:CP-190200->CP-191156; 3/6/19: FCD:05/12/2019->03/20; 13/9/19: 15%->50; 6/12/19: 50%->70; 6/12/19: WID:CP-192079->CP-193145; 26/3/20: 70%->95; 26/6/20: 95%->100","29.512; 29.513; 29.514; 29.507; 29.122; 29.522",82,42,null,null,"2018-12-06","2020-06-26"]
[2659,860019,"   Charging Aspect for 5WWC ","5WWC",2,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191188",null,"ZHU, Lei, Huawei ","lei.zhu@huawei.com ","; 26/3/20: 0%->35; 28/6/20: 35%->100","32.240; 32.255; 32.291; 32.298 ",86,44,null,null,"2019-12-06","2020-06-28"]
[2663,790024,"Study on MC services access aspects ","FS_MCSAA",1,"Rel-16","S6","2018-03-15","2019-06-12",1,"SP-181135",null,"Joakim Åkesson, Ericsson","Joakim.akesson@ericsson.com","19/4/18: 0%->5¦14/6/18: 5%->15¦15/6/18: WID:SP-180163->SP-180385¦15/6/18: FCD:12/18->03/19¦6/8/18: 23.778 added;¦10/9/18: 15%->25¦7/12/18: 25%->70¦14/12/18: WID:SP-180385->SP-181135¦14/3/19: FCD:03/19->06/19¦14/3/19: 70%->75; 31/5/19: 75%->100","new 23.xxx; 23.778",79,40,null,null,"2018-03-15","2019-05-31"]
[2668,830051,"Enhancements to Functional architecture and information flows for Mission Critical Data","eMCData2",1,"Rel-16","S6","2018-06-06","2020-03-12",1,"SP-180378",null,"Shih, Jerry, AT&T","jerry.shih@att.com","10/9/18: 0%->10¦7/12/18: 10%->40",null,83,42,null,null,"2018-06-06","2018-12-07"]
[2671,850051,"MCData File Distribution support over xMB","MC_XMB",1,"Rel-16",null,"2018-09-06","2020-03-12",1,"SP-180665",null,"Thiénot Cédric, Expway","cedric.thienot@expway.com","7/12/18: 0%->80¦7/3/19: 80%->90¦7/3/19: FCD:03/19->06/19; 31/5/19: 90%->100",26.347999999999999,85,43,null,null,"2018-09-06","2019-05-31"]
[2675,970077,"Conformance Test Aspects - Protocol enhancements for Mission Critical Services for Rel-16 (MCPTT, MCVideo, MCData) ","MCProtoc16_enh2MCPTT_eMCData2-ConTest",1,"Rel-16","R5","2022-09-08","2024-09-09",1,"RP-242148","RP-242140","Jason Kahn, NIST","jason.kahn@nist.gov","9/12/22: Acronym:MCProtoc16_enh2MCPTT_eMCData2-ConTest->MCProtoc16_enh2MCPTT_eMCData2-UEConTest; FCD:08/09/2024->30/08/2024; Compl:0%->5%; Stat Rep: ->RP-222804; Rapporteur: NIST->Jason Kahn, NIST; Rap eMail: ->jason.kahn@nist.gov; 10/1/23: acronym re...","36.579-9; 36.579-8",97,49,null,null,"2022-09-23","2024-09-26"]
[2677,760051,"   Study on MBMS APIs for MC Services","FS_MBMSAPI_MC",2,"Rel-16","S6","2017-06-05","2018-06-15",1,"SP-180237",null,"Ling Zhang, TD Tech Ltd","zhangling@td-tech.com","12/7/17: WID:SP-170596->SP-170598¦11/9/17: 0%->10¦15/12/17: 10%->20¦15/12/17: Changed Rel-15->Rel-16¦16/3/18: 20%->60¦23/3/18: WID:SP-170598->SP-180237¦23/3/18: FCD:03/18->06/18¦14/6/18: 60%->100","new 23.792",76,39,null,null,"2017-06-03","2018-06-14"]
[2682,800019,"Enhanced Mission Critical System Migration and Interconnection","eMCSMI",1,"Rel-16","S6","2018-06-06","2019-06-12",1,"SP-180379",null,"Chater-Lea, David; Motorola Solutions","david.chater-lea@motorolasolutions.com ","10/9/18: 0%->5¦7/12/18: 5%->10¦7/12/18: FCD:03/19->06/19¦14/3/19: 10%->50; 31/5/19: 50%->100. ","23.280; 23.379; 23.281; 23.282; 23.283",80,41,null,null,"2018-06-06","2019-05-31"]
[2686,800032,"Mission Critical Services Security Enhancements","MCXSec",1,"Rel-16","S3","2018-06-06","2020-06-11",1,"SP-180596",null,"Woodward, Tim, Motorola Solutions, Inc",null,"10/9/18: 0%->40¦7/12/18: 40%->50¦20/3/19: FCD:019->09/19¦20/3/19: 50%->0; 31/5/19: 0%->45; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 45%->55; 6/12/19: FCD:12/12/2019->03/20; 25/3/20: 55%->75; 26/6/20: 75%->80; 12/9/20: FCD:12/03/2020->06/20; 9/4/21: 80% ",33.18,80,41,null,null,"2018-06-06","2021-04-09"]
[2687,780003,"Enhancements of Public Warning System ","ePWS",1,"Rel-16",null,"2016-09-19","2020-03-12",1,"SP-170998",null,"Hyounhee Koo, SyncTechno Inc. ","koo at synctechno dot com","16/3/18: 0%->100",null,80,41,null,null,"2017-12-15","2018-03-16"]
[2690,810012,"   CT aspects of enhancements of Public Warning System ","ePWS",2,"Rel-16","ct","2018-09-06","2020-03-12",1,"CP-191155",null,"Hyounhee Koo, SyncTechno Inc.","koo at synctechno dot com","3/6/19: WID:CP-182228->CP-191155",null,81,41,null,null,"2018-09-06","2019-06-03"]
[2695,760005,"   Study on MONASTERY2","FS_FRMCS2",2,"Rel-16","S1","2017-06-05","2019-06-14",1,"SP-170588",null,"Merkel, Juergen, Nokia","juergen.merkel@nokia.com","15/12/17: 35%->50¦16/3/18: 50%->80¦7/6/18: 80%->85¦10/9/18: FCD:06/18->06/19¦4/12/18: 85%->100","New 22.889",76,39,null,null,"2017-06-03","2018-12-04"]
[2698,830007,"   Application Architecture for MONASTERY2","MONASTERY2",2,"Rel-16","S6","2019-03-14","2019-06-13",1,"SP-190064",null,"Oettl, Martin, Nokia","martin(dot)oettl(at)nokia(dot)com","31/5/19: 0%->100","23.280; 23.379; 23.281; 23.282",83,42,null,null,"2019-03-14","2019-05-31"]
[2702,840092,"NR support for high speed train scenario","NR_HST",1,"Rel-16","R4","2019-06-17","2022-06-22",1,"RP-191788",null,"CMCC",null,"8/10/19: WID:RP-191512->RP-191788",null,84,43,null,null,"2019-06-26","2019-10-08"]
[2704,840292,"   Perf. part: NR support for high speed train scenario","NR_HST-Perf",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-202320",null,"CMCC",null,"6/1/21: WID:RP-191788->RP-202320; 6/1/21: 0%->100",null,84,43,null,null,"2019-06-26","2021-01-06"]
[2709,0,"Streaming and TV","-",1,"Rel-16",null,"2016-12-01","2019-06-05",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2713,800001,"Enhancements to Framework for Live Uplink Streaming","E_FLUS",1,"Rel-16","S4","2018-06-06","2019-11-12",0.95,"SP-180285",null,"Lo, Charles, Qualcomm Incorporated","clo@qti.qualcomm.com","10/9/18: 0%->20¦7/12/18: 20%->40¦7/3/19: 40%->45¦7/3/19: FCD:03/19->09/19; 31/5/19: 45%->55; 13/9/19: FCD:20/09/2019->12/20; 13/9/19: 55%->75; 6/12/19: 75%->85; 25/3/20: 85%->90; 25/3/20: FCD:12/12/2019->06/20; 10/6/20: 90%->100; 26/6/20: FCD:12/06/202 ","26.238; 26.939",80,41,null,null,"2018-06-06","2020-06-26"]
[2714,810003,"Coverage and Handoff Enhancements for Multimedia ","CHEM",1,"Rel-16","S4","2018-09-06","2019-06-07",1,"SP-180664",null,"Nikolai Leung","nleung@qti.qualcomm.com","7/12/18: 0%->70¦7/3/19: 70%->80¦7/3/19: FCD:03/19->06/19; 31/5/19: 80%->90; 13/9/19: 90%->100",26.114000000000001,81,41,null,null,"2018-09-06","2019-09-13"]
[2717,820002,"Media streaming architecture ","5GMSA",1,"Rel-16","S4","2018-12-06","2019-06-12",1,"SP-180984",null,"Frédéric GABIN ","Frederic.gabin@ericsson.com ","; 31/5/19: 0%->100","26.501; 26.233 ",82,42,null,null,"2018-12-07","2019-05-31"]
[2722,770031,"Study on EVS Float Conformance Non Bit-Exact","FS_EVS_FCNBE",1,"Rel-16","S4","2017-09-08","2018-09-14",1,"SP-170618",null,"Fabrice Plante, Intel","fabrice.m.plante@intel.com","15/12/17: 26.843 added;¦15/12/17: 0%->50¦16/3/18: 50%->60¦16/3/18: FCD:03/18->06/18¦7/6/18: 60%->70¦7/6/18: FCD:06/18->09/18. 14/06/18: Moved from Rel-15¦10/9/18: 70%->100","New; 26.843",77,39,null,null,"2017-09-08","2018-09-10"]
[2725,0,"User Identities, Authentication, multi-device","-",1,"Rel-16",null,"2017-12-15","2017-12-15",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2727,780004,"   Study on a Layer for User Centric Identifiers and Authentication","FS_LUCIA",2,"Rel-16","S1","2017-12-15","2018-06-14",1,"SP-170995",null,"Bischinger, Kurt; Deutsche Telekom","kurt.bischinger@t-mobile.at","16/3/18: 0%->60¦7/6/18: 60%->90¦10/9/18: 90%->100",22.904,78,40,null,null,"2017-12-15","2018-09-10"]
[2733,810046,"      CT3 aspects of Multi-device and multi-identity","MuD",3,"Rel-16","C3","2018-09-06","2020-06-15",1,"CP-200148",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com","7/12/18: 0%->5; 13/9/19: 5%->95; 6/12/19: 95%->98; 26/3/20: 98%->100; 2/7/20: FCD:25/03/2020->06/20",29.164999999999999,81,41,null,null,"2018-06-06","2020-07-02"]
[2736,790011,"   Study on Enhancement of Network Slicing","FS_eNS",2,"Rel-16","S2","2018-03-15","2018-12-14",1,"SP-180503",null,"ZTE, Tricci So ","tso at ztetx dot com","7/6/18: 0%->10¦15/6/18: WID:SP-180121->SP-180503¦6/8/18: 23.740 added;¦10/9/18: 10%->50¦7/12/18: 50%->85¦7/12/18: 85%->¦14/3/19: 85%->100","new; 23.740",79,40,null,null,"2018-03-15","2019-03-14"]
[2740,830053,"      CT3 aspects of eNS","eNS",3,"Rel-16","C3","2019-03-07","2019-12-05",1,"CP-201161",null,"Fei Lu, ZTE","lu.fei1@zte.com.cn","6/12/19: 0%->80; 26/3/20: 80%->98; 26/6/20: 98%->100","29.061; 29.561",83,42,null,null,"2018-12-06","2020-06-26"]
[2741,830054,"      CT4 aspects of eNS","eNS",3,"Rel-16","C4","2019-03-07","2019-12-05",1,"CP-201161",null,"Fei Lu, ZTE","lu.fei1@zte.com.cn","31/5/19: 0%->30; 13/9/19: 30%->50; 6/12/19: 50%->95; 26/3/20: 95%->85 (went down); 26/6/20: 85%->100","29.502; 29.503; 29.505; 29.509; 29.518",83,42,null,null,"2018-12-06","2020-06-26"]
[2745,810051,"Business Role Models for Network Slicing ","BRMNS",1,"Rel-16","S1","2017-09-08","2018-12-13",1,"SP-180773",null,"Covell, Betsy, Nokia","betsy.covell@nokia.com",null,22.260999999999999,81,41,null,null,"2018-09-06","NA"]
[2749,810031,"Enhancement of performance assurance for 5G networks including network slicing","5G_SLICE_ePA",1,"Rel-16","S5","2018-09-06","2020-03-12",1,"SP-190247",null,"Xiaowei Sun (China Mobile)",null,"7/12/18: 0%->30¦17/1/19: WID:SP-180843->SP-180906¦14/3/19: 30%->60¦21/3/19: FCD:06/19->12/19¦21/3/19: WID:SP-180906(->SP-190141)->SP-190247; 31/5/19: 60%->70","28.550; 28.532; 28.552; 28.554; 32.425; 32.426; 32.450; 32.451; 32.455; 28.622; 28.623",81,41,null,null,"2018-09-06","2019-05-31"]
[2752,820029,"Study on Charging Aspects of Network Slicing ","FS_NETSLICE_CH",1,"Rel-16","S5","2018-12-13","2019-12-12",1,"SP-181065",null,"Chen Shan, Huawei","chenshan@huawei.com ","14/3/19: 0%->30¦14/3/19: FCD:06/19->09/19; 31/5/19: 30%->45; 13/9/19: 45%->85; 13/9/19: FCD:12/09/2019->12/20; 6/12/19: 85%->100",null,82,42,null,null,"2018-12-07","2019-12-06"]
[2754,760003,"Provision of Access to Restricted Local Operator Services by Unauthenticated UEs","PARLOS",1,"Rel-16",null,"2016-12-01","2019-12-13",1,"SP-170449",null,"Covell, Betsy Nokia","betsy.covell@nokia.com","16/03/18: Moved to Rel-16 as per SA2 chair indication that St 2 work to be shifted from Rel-15 to Rel-16","22.115; 22.101; 22.228",76,38,null,null,"2017-06-03","2017-06-07"]
[2760,830012,"   CT aspects of PARLOS","PARLOS",2,"Rel-16","ct","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com",null,null,83,42,null,null,"2018-09-06","NA"]
[2763,830064,"      CT4 aspects of PARLOS","PARLOS",3,"Rel-16","C4","2019-03-14","2019-12-12",1,"CP-190197",null,"Liu, Jennifer; Nokia ","Jennifer.Liu@nokia.com","6/12/19: 0%->100","29.228; 29.229; 29.274",83,42,null,null,"2018-09-06","2019-12-06"]
[2767,770039,"   Study on ETSUN","FS_ETSUN",2,"Rel-16","S2","2017-09-08","2018-12-14",1,"SP-180731",null,"Laurent Thiebaut (Nokia)","Laurent.thiebaut@nokia.com","15/12/17: 23.726 added;¦16/3/18: 0%->25¦7/6/18: 25%->40¦10/9/18: 40%->65¦10/9/18: FCD:09/18->12/18¦2/10/18: WID:SP-170743->SP-180731¦2/10/18: FCD:12/18->12/18¦7/12/18: 65%->100",23.725999999999999,77,39,null,null,"2017-09-08","2018-12-07"]
[2768,820013,"   Stage 2 of ETSUN","ETSUN",2,"Rel-16","S2","2018-12-07","2019-06-17",1,"SP-181116",null,null,null,"14/3/19: 0%->45; 31/5/19: 45%->90; 13/9/19: 90%->100",null,82,42,null,null,"2018-12-05","2019-09-13"]
[2772,850024,"   Charging aspects of ETSUN ","ETSUN",2,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190880",null,"Dong, Jia, China Mobile ","dongjia@chinamobile.com ","; 6/12/19: 0%->70; 26/3/20: 70%->100","32.255; 32.291; 32.298 ",85,43,null,null,"2019-09-13","2020-03-26"]
[2776,830016,"   CT aspects of ATSSS","ATSSS",2,"Rel-16","ct","2019-03-11","2019-12-09",1,"CP-190201",null,"ZHOU, Xingyue (Joy), ZTE","zhou.xingyue@zte.com.cn",null,null,83,42,null,null,"2018-12-06","NA"]
[2779,830059,"      CT4 aspects of ATSSS","ATSSS",3,"Rel-16","C4","2019-03-11","2019-12-09",1,"CP-190201",null,"ZHOU, Xingyue (Joy), ZTE","zhou.xingyue@zte.com.cn","31/5/19: 0%->25; 13/9/19: 25%->45; 6/12/19: 45%->75; 26/3/20: 75%->85; 26/6/20: 85%->100","29.244; 29.502; 29.503; 29.505; 29.518; 29.510; 23.008",83,42,null,null,"2018-12-06","2020-06-26"]
[2781,840998,"      (IETF) 0-RTT TCP Convert Protocol (draft-ietf-tcpm-converters)","ATSSS",3,"Rel-16","S2-IETF","2019-06-26","2019-12-09",1,null,null,null,null,"23/4/20: 30%->90; 25/9/20: 90%->100; 9/4/21: RFC 8803 added;","RFC 8803",84,43,null,null,"2019-06-26","2021-04-09"]
[2787,820008,"   Security aspects of single radio voice continuity from 5GS to UTRAN ","5GS_UTRAN_SEC",2,"Rel-16","S3","2018-12-13","2019-06-12",1,"SP-190703",null,"Feng Gao, China Unicom ","gaofeng149@chinaunicom.cn ","20/3/19: 0%->20; 13/9/19: 20%->100; 20/9/19: WID:SP-181037->SP-190703","33.501; 33.401; 33.220",82,42,null,null,"2018-12-13","2019-09-20"]
[2790,830270,"      Perf. part: Single Radio Voice Call Continuity from 5G to 3G","SRVCC_NR_to_UMTS-Perf",3,"Rel-16","R4","2019-03-01","2020-06-01",1,"RP-200151",null,"China Unicom",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2794,860027,"      CT3 aspect of 5G_SRVCC","5G_SRVCC",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-193014",null,"Chi Ren, China Unicom ","renchi1@chinaunicom.cn ","6/12/19: created, 0%->60; 26/3/20: 60%->100",null,86,44,null,null,"2019-05-31","2020-03-26"]
[2795,840059,"      CT4 aspect of 5G_SRVCC","5G_SRVCC",3,"Rel-16","C4","2019-06-06","2020-03-12",1,"CP-193014",null,"Chi Ren, China Unicom ","renchi1@chinaunicom.cn ","13/9/19: 0%->60; 6/12/19: 60%->80; 26/3/20: 80%->100","29.303; 29.503; 29.504; 29.505; 29.518; 29.274",84,43,null,null,"2019-05-31","2020-03-26"]
[2799,790007,"   Study on Enhancements to the Service-Based 5G System Architecture","FS_eSBA",2,"Rel-16","S2","2018-03-15","2018-12-14",1,"SP-180231",null,"Tao Sun (China Mobile)","suntao@chinamobile.com","7/6/18: 0%->15¦6/8/18: 23.742 added;¦10/9/18: 15%->60¦7/12/18: 60%->100","23.xxx; 23.742",79,40,null,null,"2018-03-15","2018-12-07"]
[2803,830061,"      CT4 aspects of 5G_eSBA","5G_eSBA",3,"Rel-16","C4","2019-03-14","2019-12-12",1,"CP-190191",null,"Song Yue (China Mobile)","songyue at chinamobile dot com","31/5/19: 0%->10; 13/9/19: 10%->40; 6/12/19: 40%->70; 26/3/20: 70%->95; 26/6/20: 95%->100","29.500; 29.501; 29.502; 29.503; 29.504; 29.505; 29.509; 29.510; 29.511; 29.518; 29.531; 29.540; 29.571; 29.572; 29.573",83,42,null,null,"2018-12-06","2020-06-26"]
[2806,840062,"SBA aspects of enhanced IMS to 5GC integration","eIMS5G_SBA",1,"Rel-16",null,"2019-03-14","2019-06-13",1,"SP-190181",null,"T-Mobile USA, Christopher Joul",null,null,"23.501; 23.502; 23.503; 23.228",84,42,null,null,"2019-03-14","NA"]
[2808,840006,"   CT aspects of eIMS5G_SBA","eIMS5G_SBA",2,"Rel-16","ct","2019-06-06","2020-03-12",1,"CP-192023",null,"de Gregorio, Jesus. Ericsson ","jesus.de.gregorio@ericsson.com ","16/9/19: WID:CP-191065->CP-192023",null,84,43,null,null,"2019-05-31","2019-09-16"]
[2814,880072,"   UE Conformance Test Aspects - Private Network Support for NG-RAN","NG_RAN_PRN_Vertical_LAN-UEConTest",2,"Rel-16","R5","2020-06-22","2022-12-21",1,"RP-201152","RP-221246","Yogesh Tugnawat, Qualcomm","yogesht[at]qti.qualcomm.com","8/10/20: 0%->5; 8/4/21: 5%->10; 2/7/21: 10%->31; 20/6/22: FCD:15/12/2021->22/12/2022; Compl:31%->89%; Stat Rep: ->RP-221246; Rapporteur: Qualcomm->Yogesh Tugnawat, Qualcomm; Rap eMail: ->yogesht[at]qti.qualcomm.com 9/9/22: Compl:89%->97%; 29/3/23: 97%->10",null,88,45,null,null,"2020-07-28","2023-03-29"]
[2817,810001,"   Stage 2 of E2E_DELAY","E2E_DELAY",2,"Rel-16","S4","2018-09-06","2019-06-07",1,"SP-180662",null,"Oyman, Ozgur, Company: Intel","ozgur.oyman@intel.com ","7/12/18: 0%->75¦7/3/19: 75%->85¦7/3/19: FCD:03/19->06/19; 31/5/19: 85%->100",26.114000000000001,81,41,null,null,"2018-09-06","2019-05-31"]
[2819,830066,"      CT1 Aspects of E2E_DELAY","E2E_DELAY",3,"Rel-16","C1","2019-03-14","2019-12-12",1,"CP-190193",null,"Luetzenkirchen, Thomas, Intel","Thomas.luetzenkirchen@intel.com","31/5/19: 0%->100; 13/9/19: 100%->100",24.228999999999999,83,42,null,null,"2018-09-06","2019-09-13"]
[2822,830069,"Enhancements for Common API Framework for 3GPP Northbound APIs ","eCAPIF",1,"Rel-16",null,"2018-03-15","2020-03-12",1,"SP-181137",null,"Basavaraj Pattan, Samsung","basavarajjp@samsung.com ","7/6/18: 0%->15¦10/9/18: 15%->30¦7/12/18: 30%->45¦7/12/18: FCD:12/18->06/19¦13/12/18: WID:SP-180161->SP-181137",23.222000000000001,83,42,null,null,"2018-03-15","2018-12-13"]
[2826,840065,"User data interworking, Coexistence and Migration","UDICOM",1,"Rel-16","S2","2019-03-14","2019-06-14",1,"SP-190182",null,"Alessio Casati, Nokia","Alessio.casati@nokia.com ",null,"23.501; 23.502; 23.228",84,42,null,null,"2019-03-14","NA"]
[2830,910008,"UICC-terminal interface testing for UEs with non-removable UICCs ","nrUICC_UEConTest",1,"Rel-16","C6","2021-03-18","2022-03-10",1,"CP-210285",null,"Marquordt, Arne, COMPRION GmbH ","amarquordt@comprion.com ",null,"TS 31.121,TS 31.124,TS 31.127",91,46,null,null,"2021-03-18","2023-06-06"]
[2833,0,"NR-related Release 16 Features","-",1,"Rel-16",null,"2019-03-07","2019-03-07",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[2835,860158,"   Core part: Addition of wider channel bandwidth in NR band n3","NR_n3_BW-Core",2,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-200305",null,"Ericsson",null,"affects: NR.; 28/7/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-07-28"]
[2841,800094,"   Study on UE power saving in NR","FS_NR_UE_pow_sav",2,"Rel-16","R1","2018-06-15","2019-06-14",1,"RP-181463",null,"CATT",null,"TR 38.8xx; 26/6/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-06-26"]
[2844,800072,"Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R16",1,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201018",null,"Huawei",null,"basket WI¦TR 37.716-00-00¦note: WI covers for SA NR: 1 NR SUL band (already defined) + 1 or more NR bands and for NSA NR: 1 NR SUL band (already defined) + 1 or more NR bands + 1 or more LTE bands¦26/3/19: WID:RP-182559->RP-190714; 26/6/19: WID:RP-1907 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2846,800272,"   Perf. part: Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP)","NR_SUL_combos_R16-Perf",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201018",null,"Huawei",null,"basket WI¦26/3/19: WID:RP-182559->RP-190714; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2849,800173,"      Core part: Rel-16 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y)","NR_CA_R16_intra-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200656",null,"Ericsson",null,"basket WI¦TR 38.716-01-01¦26/3/19: WID:RP-182256->RP-190689; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2853,800274,"      Perf. part: Rel-16 NR inter-band CA/Dual Connectivity for 2 bands DL with x bands UL (x=1, 2)","NR_CADC_R16_2BDL_xBUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201253",null,"ZTE",null,"basket WI¦26/3/19: WID:RP-182501->RP-190494; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[2857,830195,"      Core part: Rel16 NR inter-band Carrier Aggregation for 3 bands DL with 1 band UL","NR_CA_R16_3BDL_1BUL-Core",3,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200918",null,"CATT",null,"26/6/19: 38.716-03-01 added;; 28/7/20: 0%->100","38.716-03-01",83,42,null,null,"2019-03-26","2020-07-28"]
[2862,831000,"New bands for New Radio",null,1,"Rel-16","R4","2018-06-15","2022-12-01",0.99,"RP-182258",null,"Dish Network",null,"16/1/19: WID:RP-181445->RP-182258",null,83,42,null,null,"2018-06-27","2019-01-16"]
[2865,800177,"      Core part: Band 65 for New Radio","NR_band_n65-Core",3,"Rel-16","R4","2018-06-15","2018-12-14",1,"RP-190360",null,"Dish Network",null,"26/3/19: WID:RP-182258->RP-190360; 26/6/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-06-26"]
[2868,820173,"      Core part: Introduction of NR band n18","NR_n18-Core",3,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-190173",null,"KDDI",null,"26/3/19: WID:RP-182826->RP-190173; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2871,820177,"      Core part: Introduction of NR band n48","NR_n48-Core",3,"Rel-16","R4","2018-12-13","2019-03-18",1,"RP-182865",null,"US Cellular",null,"26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2873,830090,"   Introduction of NR band n14","NR_n14",2,"Rel-16","R4","2019-03-01","2019-05-31",1,"RP-190965",null,"AT&T",null,"26/6/19: WID:RP-190165->RP-190965",null,83,42,null,null,"2019-03-26","2019-06-26"]
[{"$f":"A2876+1","v":2876},830091,"   Introduction of NR band n30","NR_n30",2,"Rel-16","R4","2019-03-01","2019-05-31",1,"RP-190967",null,"AT&T",null,"26/6/19: WID:RP-190166->RP-190967",null,83,42,null,null,"2019-03-26","2019-06-26"]
[2880,830197,"      Core part: Introduction of NR band n259","NR_n259-Core",3,"Rel-16","R4","2019-03-01","2019-12-13",1,"RP-191880",null,"Ericsson",null,"28/7/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-07-28"]
[2884,850267,"      Perf. part: Introduction of NR band n26","NR_n26-Perf",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192736",null,"Sprint",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[2889,850168,"      Core part: Introduction of 2010-2025MHz SUL (supplemental uplink) band for NR","NR_SUL_band_2010_2025MHz-Core",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192584",null,"CMCC",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2892,860156,"      Core part: Introduction of band n53","NR_n53-Core",3,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-192409",null,"Globalstar",null,"affects: NR.; 18/2/20: FCD:15/06/2020->03/20. Rel17->Rel-16; 26/3/20: 0%->100",null,86,44,null,null,"2020-01-14","2020-03-26"]
[2895,830087,"   RF requirements for NR frequency range 1 (FR1)","NR_RF_FR1",2,"Rel-16","R4","2019-03-01","2023-12-12",0.99,"RP-193266",null,"Huawei",null,"26/6/19: WID:RP-190759->RP-191114; 8/10/19: WID:RP-191114->RP-192282; 14/1/20: WID:RP-192282->RP-193266",null,83,42,null,null,"2019-03-26","2020-01-14"]
[2898,870061,"      UE Conformance Test Aspects - RF requirements for NR FR1","NR_RF_FR1-UEConTest",3,"Rel-16","R5","2020-03-25","2023-12-12",1,"RP-230427","RP-233756","Yuxin HAO, Huawei Technologies. Co., Ltd.","haoyuxin@huawei.com","affects: NR. TR 38.8xx; 8/10/20: 0%->15; 8/4/21: 15%->43; ; 6/6/22: CD:10/06/2022->22/12/2022 ; 20/6/22: Rapporteur: Huawei->Chunying Gu, Huawei Technologies. Co., Ltd.; Rap eMail: ->guchunying@huawei.com9/9/22: Compl:64%->69%; 9/12/22: FCD:22/12/20...",null,87,44,null,null,"2020-01-14","2023-12-08"]
[2900,830188,"      Core part: Add support of NR DL 256QAM for FR2","NR_DL256QAM_FR2-Core",3,"Rel-16","R4","2019-03-01","2020-02-28",1,"RP-200124",null,"China Telecom",null,"8/10/19: 38.883 added;; 28/7/20: 0%->100",38.883000000000003,83,42,null,null,"2019-03-26","2020-07-28"]
[2903,830089,"   NR RF requirement enhancements for frequency range 2 (FR2)","NR_RF_FR2_req_enh",2,"Rel-16","R4","2019-03-01","2023-09-22",0.99,"RP-201606",null,"Nokia",null,"26/6/19: WID:RP-190761->RP-191290; 8/10/19: WID:RP-191290->RP-192227; 14/1/20: WID:RP-192227->RP-192653; 26/3/20: WID:RP-192653->RP-200246; 28/7/20: WID:RP-200246->RP-200668; 25/9/20: WID:RP-200668->RP-201606",null,83,42,null,null,"2019-03-26","2020-09-25"]
[2908,830192,"      Core part: Introduction of an NR SUL band with same uplink frequency range as NR band n5","NR_SUL_UL_n5-Core",3,"Rel-16","R4","2019-03-01","2019-09-13",1,"RP-192080",null,"Huawei",null,"8/10/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-10-08"]
[2911,820174,"      Core part: Adding wider channel bandwidths in NR band n7","NR_n7_BW-Core",3,"Rel-16","R4","2018-12-13","2019-09-13",1,"RP-190137",null,"BT",null,"no Perf. part¦26/3/19: WID:RP-182827->RP-190137; 8/10/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-10-08"]
[2916,850163,"      Core part: Addition of further channel bandwidths in NR band 38","NR_n38_BW2-Core",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192513",null,"Ericsson",null,"compare REL-16 WI NR_n38_BW; 26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[2919,820175,"      Core part: Addition of 30MHz channel bandwidth for NR band n41","NR_n41_BW-Core",3,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-191681",null,"KDDI",null,"26/3/19: WID:RP-182828->RP-190174; 8/10/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-10-08"]
[2922,820176,"      Core part: Adding wider channel bandwidths in NR band n50","NR_n50_BW-Core",3,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-182829",null,"Huawei",null,"no Perf. part; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[2925,850264,"      Perf. part: Addition of wider channel bandwidths in NR band n75","NR_n75_BW-Perf",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192216",null,"Ericsson",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2927,850165,"      Core part: Addition of 25, 30, 35 and 40 MHz channel bandwidth for NR band n25","NR_n25_BW-Core",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192401",null,"Nokia",null,"14/1/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-01-14"]
[2930,850166,"      Core part: Addition of wider channel bandwidths in NR band n28","NR_n28_BW-Core",3,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192656",null,"CBN",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[2935,850070,"   Addition of asymmetric channel bandwidth for NR band n66","NR_n66_BW",2,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-200265",null,"Huawei",null,"no Perf. Part; 14/1/20: WID:RP-192276->RP-192808; 26/3/20: WID:RP-192808->RP-200265",null,85,43,null,null,"2019-10-08","2020-03-26"]
[2938,800185,"   Core part: Enhancements on MIMO for NR","NR_eMIMO-Core",2,"Rel-16","R1","2018-06-15","2019-12-13",1,"RP-200474",null,"Samsung",null,"25/9/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-09-25"]
[2943,800287,"   Perf. part: NR mobility enhancements","NR_Mob_enh-Perf",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-192534",null,"Intel",null,"26/3/19: WID:RP-181433->RP-190489; 6/1/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-01-06"]
[2946,820168,"   Core part: 2-step RACH for NR","NR_2step_RACH-Core",2,"Rel-16","R1","2018-12-15","2019-12-15",1,"RP-200085",null,"ZTE",null,"WI was created after REL-16 SI FS_NR_NOMA was completed¦26/3/19: WID:RP-182894->RP-190711; 28/7/20: 0%->100; 28/7/20: 100%->100",null,82,42,null,null,"2019-01-16","2020-07-28"]
[2948,911001,"   UE Conformance Test Aspects - 2-step RACH for NR ","NR_2step_RACH-UEConTest",2,"Rel-16","R5","2021-03-12","2022-09-22",1,"RP-210612","RP-221195","Wei Ma, Jing Zhao, ZTE, China Telecom","ma.wei4@zte.com.cn, zhaoj16@chinatelecom.cn","tested REL-16 WI NR_2step_RACH-Core ; 2/7/21: 0%->25; 13/9/21: Compl:25%->54%; 13/9/21: CD:Fri 11/03/22->Tue 22/03/22; 13/9/21: Stat Rep: ->RP-211763; 20/6/22: Rapporteur: ZTE->Wei Ma, Jing Zhao, ZTE, China Telecom; Rap eMail: ->ma.wei4@zte.com...",null,91,46,null,null,"2021-04-07","2022-09-09"]
[2951,890043,"   UE Conformance Test Aspects - SON (Self-Organising Networks) and MDT (Minimization of Drive Tests) support for NR ","NR_SON_MDT-UEConTest",2,"Rel-16","R5","2020-09-17","2022-06-22",1,"RP-210377","RP-221368","Wenjia DONG, Leif Mattisson, CMCC, Ericsson","dongwenjia@chinamobile.com, leif.mattisson@ericsson.com","tested: REL-16 WI NR_SON_MDT-Core ; 7/4/21: WID:RP-201625->RP-210377; 8/4/21: 0%->37; 2/7/21: 37%->71; 13/9/21: Compl:71%->85%; ; 20/6/22: Rapporteur: CMCC->Wenjia DONG, Leif Mattisson, CMCC, Ericsson; Rap eMail: ->dongwenjia@chinamobile.com, ...",null,89,45,null,null,"2020-09-25","2022-06-20"]
[2954,840093,"RRM requirement for CSI-RS based L3 measurement in NR","NR_CSIRS_L3meas",1,"Rel-16","R4","2019-06-17","2020-09-15",1,"RP-210590",null,"CATT",null,"8/10/19: WID:RP-191580->RP-191992; 26/3/20: WID:RP-191992->RP-200240; 28/7/20: WID:RP-200240->RP-201345; 25/9/20: WID:RP-201345->RP-201975; 6/1/21: WID:RP-201975->RP-202723; 7/4/21: WID:RP-202723->RP-210590",null,84,43,null,null,"2019-06-26","2021-04-07"]
[2957,840094,"NR performance requirement enhancement","NR_perf_enh",1,"Rel-16","R4","2019-06-17","2022-06-22",1,"RP-200472",null,"China Telecom",null,"no Core part; 8/10/19: WID:RP-191587->RP-192281; 14/1/20: WID:RP-192281->RP-192532; 26/3/20: WID:RP-192532->RP-200472",null,84,43,null,null,"2019-06-26","2020-03-26"]
[2962,840295,"   Perf. part: NR RRM enhancement","NR_RRM_enh-Perf",2,"Rel-16","R4","2019-06-17","2020-06-15",1,"RP-202655",null,"Intel",null,"6/1/21: WID:RP-201883->RP-202655; 7/4/21: 0%->100",null,84,43,null,null,"2019-06-26","2021-04-07"]
[2965,840196,"   Core part: Rel-16 NR inter-band Carrier Aggregation for 4 bands DL with 1 band UL","NR_CA_R16_4BDL_1BUL-Core",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-200658",null,"Ericsson",null,"basket WI; TR 38.716-04-01; 28/7/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-07-28"]
[2970,840099,"Addition of channel bandwidths in Band n77 and n78","NR_n77_n78_BW",1,"Rel-16","R4","2019-06-17","2019-12-13",1,"RP-191606",null,"Huawei",null,"no Perf. part",null,84,43,null,null,"2019-06-26","NA"]
[2973,841100,"   Core part: Dual Connectivity (EN-DC) with 3 bands DL and 3 bands UL","DC_R16_LTE_NR_3DL3UL-Core",2,"Rel-16","R4","2019-06-17","2020-03-13",1,"RP-201254",null,"ZTE",null,"max. 2 NR bands for DL and UL; min. 1 NR FR2 band; TR 37.716-xx-xx; 28/7/20: 0%->100",null,84,43,null,null,"2019-06-26","2020-07-28"]
[2975,841001,"Introduction of NR FDD bands with variable duplex and corresponding framework","NR_FDD_bands_varduplex",1,"Rel-16","R4","2019-06-17","2019-12-13",1,"RP-192820",null,"Huawei",null,"no Perf. part as no Perf. part objectives; NR FDD bands are based on NR SDL/SUL bands; framework part will consider interworking with LTE but without normative changes (they may follow later in EN-DC basket WIs; 8/10/19: WID:RP-191567->RP-192285; 14/1/ ",null,84,43,null,null,"2019-06-26","2020-01-14"]
[2978,841002,"Common RF requirement configured output power for EN-DC with 3 uplink CC and 2 different bands (2CC LTE, 1CC NR FR1)","DC_Pcmax_3UL_CC",1,"Rel-16","R4","2019-10-08","2022-06-22",0.46,"RP-191604",null,"Huawei",null,"no Perf. Part; note: Some combinations were removed from REL-15 due to missing Pc,max; the combinations will be covered in existing REL-16 basket Wis once Pc,max is specified in this WI",null,84,43,null,null,"2019-07-31","NA"]
[2981,880074,"Addition of NR UE measurements to enable OTA conformance testing","NR_OTA_Uemeas",1,"Rel-16","R1","2020-06-22","2020-07-28",1,"RP-200824",null,"Keysight Technologies",null,null,null,88,45,null,null,"2020-07-28","NA"]
[2984,860054,"Over the air (OTA) base station (BS) testing TR","OTA_BS_testing",1,"Rel-16","R4","2019-03-07","2019-06-05",1,"RP-193225",null,"Huawei",null,"affects: UTRA, LTE, NR. no Core part; note: WI will introduce TR 37.9xx for REL-15 and REL-16",null,86,44,null,null,"2020-02-18","NA"]
[2989,860057,"Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band","DC_R16_xBLTE_2BNR_yDL3UL",1,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-200905",null,"NTT DOCOMO",null,"affects: LTE, NR. basket WI; suggested TR 37.716-41-22; 26/3/20: WID:RP-192784->RP-200228; 28/7/20: WID:RP-200228->RP-200905",null,86,44,null,null,"2020-01-14","2020-07-28"]
[2993,860160,"   Core part: LTE/NR spectrum sharing in band 48/n48 frequency range","NR_n48_LTE_48_coex-Core",2,"Rel-16","R4","2019-12-16","2020-03-13",1,"RP-201858",null,"Apple",null,"affects: LTE, NR. no Perf. part; 6/1/21: 0%->100",null,86,44,null,null,"2020-01-14","2021-01-06"]
[2997,911004,"   UE Conformance Test Aspects - LTE-NR & NR-NR Dual Connectivity and NR CA enhancements ","LTE_NR_DC_CA_enh-UEConTest",2,"Rel-16","R5","2021-03-12","2023-06-06",1,"RP-231105","RP-230915","Matti Kangas","matti.kangas@nokia.com","lested: REL-16 WI LTE_NR_DC_CA_enh-Core ; 2/7/21: WID:RP-210746->RP-211442; 2/7/21: 0%->5; 5/4/22: WID:RP-211442->RP-220801; 20/6/22: FCD:11/03/2022->22/12/2022; Compl:5%->40%; WID: RP-220801->RP-211442; Stat Rep: ->RP-221416; Rapporteur: Nokia->Matti...",null,91,46,null,null,"2021-04-07","2023-08-09"]
[3000,820179,"   Core part: High power UE (power class 2) for EN-DC (1 LTE TDD band + 1 NR TDD band)","ENDC_UE_PC2_TDD_TDD-Core",2,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-190315",null,"CMCC",null,"26/3/19: WID:RP-182877->RP-190315; 14/1/20: 0%->100",null,82,42,null,null,"2019-01-16","2020-01-14"]
[3002,870062,"   UE Conformance Test Aspects - High power UE (power class 2) for EN-DC (1 LTE TDD band + 1 NR TDD band)","ENDC_UE_PC2_TDD_TDD-UEConTest",2,"Rel-16","R5","2019-03-07","2020-03-18",1,"RP-202066",null,"CMCC",null,"affects: NR. TR 38.8xx; 28/7/20: WID:RP-200434->RP-200761; 25/9/20: WID:RP-200761->RP-202066; 25/9/20: 0%->100",null,87,44,null,null,"2020-01-14","2020-09-25"]
[3005,820080,"LTE/NR spectrum sharing in Band 41/n41 frequency range","NR_n41_LTE_41_coex",1,"Rel-16","R4","2018-12-13","2019-06-18",1,"RP-191588",null,"KDDI",null,"no Perf. part¦changes will happen only on NR side¦26/3/19: WID:RP-182883->RP-190175; 26/6/19: WID:RP-190175->RP-191588",null,82,42,null,null,"2019-03-26","2019-06-26"]
[3008,800178,"   Core part: 29 dBm UE Power Class for LTE band 41 and NR Band n41","LTE_NR_B41_Bn41_PC29dBm-Core",2,"Rel-16","R4","2018-06-15","2019-06-14",1,"RP-201134",null,"Sprint",null,"no Perf. part¦7/3/19: WID:RP-181460->RP-181655¦26/3/19: WID:RP-181655->RP-190502; 25/9/20: 0%->100; 25/9/20: 100%->100",null,80,41,null,null,"2018-06-27","2020-09-25"]
[3011,800066,"   Dual Connectivity (EN-DC) of 1 LTE band (1UL/1DL) and 1 NR band (1DL/1UL)","DC_R16_1BLTE_1BNR_2DL2UL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200752",null,"NTT DOCOMO",null,"basket WI¦TR 37.716-01-01¦16/1/19: WID:RP-181447->RP-182567¦26/3/19: WID:RP-182567->RP-190705; 26/6/19: WID:RP-190705->RP-191568; 8/10/19: WID:RP-191568->RP-191752; 14/1/20: WID:RP-191752->RP-192742; 26/3/20: WID:RP-192742->RP-200221; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[3016,800267,"      Perf. part: Dual Connectivity (EN-DC) of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_2BLTE_1BNR_3DL2UL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201278",null,"Huawei",null,"basket WI¦26/3/19: WID:RP-182557->RP-190379; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[3020,800069,"   Dual Connectivity (EN-DC) of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_4BLTE_1BNR_5DL2UL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200648",null,"Nokia",null,"basket WI¦TR 37.716-04-01¦16/1/19: WID:RP-181001->RP-182534¦26/3/19: WID:RP-182534->RP-190294; 26/6/19: WID:RP-190294->RP-191205; 8/10/19: WID:RP-191205->RP-191728; 14/1/20: WID:RP-191728->RP-192768; 26/3/20: WID:RP-192768->RP-200134; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[3024,800170,"      Stopped : Core part: Dual Connectivity (EN-DC) of 5 bands LTE inter-band CA (5DL/1UL) and 1 NR band (1DL/1UL)","DC_R16_5BLTE_1BNR_6DL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-180997",null,"Samsung",null,"basket WI¦TR 37.716-05-01; 14/1/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-01-14"]
[3027,800171,"      Core part: Dual Connectivity (EN-DC) of x bands (x=2, 3, 4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)","DC_R16_xBLTE_2BNR_yDL2UL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200744",null,"LG Electronics",null,"basket WI¦TR 37.716-00-02¦26/3/19: WID:RP-182302->RP-190151; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[3029,0,"LTE-related Release 16 Features","-",1,"Rel-16",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3032,790257,"   Perf. part: E-UTRA 2.4 GHz TDD Band for US","LTE_TDD_2400_US-Perf",2,"Rel-16","R4","2018-03-15","2018-12-14",1,"RP-182405",null,"Globalstar",null,"new LTE TDD band for 2483.5 to 2495MHz¦compare band 41: 2,496-2,69GHz introduced by WI LTE_TDD_2600_US¦16/1/19: 0%->100",null,79,40,null,null,"2018-03-27","2019-01-16"]
[3038,800061,"   Rel-16 LTE inter-band CA for 2 bands DL with 1 band UL","LTE_CA_R16_2BDL_1BUL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201263",null,"Qualcomm",null,"basket WI¦TR 36.716-02-01¦16/1/19: WID:RP-181441->RP-182345¦26/3/19: WID:RP-182345->RP-190500; 26/6/19: WID:RP-190500->RP-191085; 8/10/19: WID:RP-191085->RP-191733; 14/1/20: WID:RP-191733->RP-192525; 26/3/20: WID:RP-192525->RP-200231; 28/7/20: WID:RP-2 ",null,80,41,null,null,"2018-06-27","2020-07-28"]
[3040,800261,"      Perf. part: Rel-16 LTE inter-band CA for 2 bands DL with 1 band UL","LTE_CA_R16_2BDL_1BUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201263",null,"Qualcomm",null,"basket WI¦TR 36.716-02-01¦16/1/19: WID:RP-181441->RP-182345¦26/3/19: WID:RP-182345->RP-190500; 26/6/19: WID:RP-190500->RP-191085; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[3043,800262,"      Perf. part: Rel-16 LTE inter-band CA for 3 bands DL with 1 band UL","LTE_CA_R16_3BDL_1BUL-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201012",null,"Huawei",null,"basket WI¦26/3/19: WID:RP-182553->; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[3047,800064,"   Rel-16 LTE inter-band CA for 2 bands DL with 2 band UL","LTE_CA_R16_2BDL_2BUL",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201014",null,"Huawei",null,"basket WI¦TR 36.716-02-02¦16/1/19: WID:RP-181356->RP-182555¦26/3/19: WID:RP-182555->RP-190377; 8/10/19: WID:RP-190377->RP-192085; 14/1/20: WID:RP-192085->RP-192813; 26/3/20: WID:RP-192813->RP-200269; 28/7/20: WID:RP-200269->RP-201014",null,80,41,null,null,"2018-06-27","2020-07-28"]
[3051,800165,"      Core part: Rel-16 LTE inter-band CA for x bands DL (x= 3, 4, 5) with 2 band UL","LTE_CA_R16_xBDL_2BUL-Core",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200740",null,"LG Electronics",null,"basket WI¦TR 36.716-00-02¦26/3/19: WID:RP-182301->RP-190150; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[3054,830076,"LTE-based 5G terrestrial broadcast","LTE_terr_bcast",1,"Rel-16","R1","2018-06-15","2020-06-01",1,"RP-193050",null,"Qualcomm",null,"8/10/19: WID:RP-190732->RP-191924; 8/10/19: 36.276 added;; 14/1/20: WID:RP-191924->RP-193050","36.276; 36.476",83,42,null,null,"2019-03-26","2020-01-14"]
[3056,830176,"   Core part: LTE-based 5G terrestrial broadcast","LTE_terr_bcast-Core",2,"Rel-16","R1","2019-03-01","2019-12-13",1,"RP-193050",null,"Qualcomm",null,"26/3/20: 0%->100",null,83,42,null,null,"2019-03-26","2020-03-26"]
[3059,830194,"   Core part: Power class 2 UE for LTE bands 31 and 72","LTE_PC2_B31_B72-Core",2,"Rel-16","R4","2019-03-01","2019-09-13",1,"RP-190665",null,"Nokia",null,"8/10/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-10-08"]
[3065,800275,"      Perf. part: Additional LTE bands for UE category M1 and/or NB1 in Rel-16","LTE_bands_R16_M1_NB1-Perf",3,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-201200",null,"Ericsson",null,"basket WI¦26/3/19: WID:RP-182768->RP-190332; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[3067,800076,"   Additional LTE bands for UE category M2 and/or NB2 in Rel-16","LTE_bands_R16_M2_NB2",2,"Rel-16","R4","2018-06-15","2021-09-21",1,"RP-202523","RP-211864","Ericsson",null,"basket WI¦no Perf. part¦16/1/19: WID:RP-181007->RP-182769¦26/3/19: WID:RP-182769->RP-190333; 14/1/20: WID:RP-190333->RP-192454; 26/3/20: WID:RP-192454->RP-200154; 13/9/21: Compl:86%->100% ; ",null,80,41,null,null,"2018-06-27","2021-09-13"]
[3070,800079,"Further performance enhancement for LTE in high speed scenario","LTE_high_speed_enh2",1,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-181482",null,"NTT DOCOMO",null,null,null,80,41,null,null,"2018-06-27","NA"]
[3074,800182,"   Core part: Cross Link Interference (CLI) handling and Remote Interference Management (RIM) for NR","NR_CLI_RIM-Core",2,"Rel-16","R1","2018-06-15","2019-06-14",1,"RP-193190",null,"LG Electronics",null,"26/3/19: WID:RP-182864->RP-190700; 28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[3078,800186,"   Core part: DL MIMO efficiency enhancements for LTE","LTE_DL_MIMO_EE-Core",2,"Rel-16","R1","2018-06-15","2019-12-13",1,"RP-192766",null,"Huawei",null,"26/3/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-03-26"]
[3079,800286,"   Perf. part: DL MIMO efficiency enhancements for LTE","LTE_DL_MIMO_EE-Perf",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-192766",null,"Huawei",null,"28/7/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-07-28"]
[3083,820172,"   Core part: Direct data forwarding between NG-RAN and E-UTRAN nodes for inter-system mobility","Direct_data_fw_NR-Core",2,"Rel-16","R3","2018-12-13","2019-06-18",1,"RP-182886",null,"Ericsson",null,"no Perf. part; 26/6/19: 0%->100",null,82,42,null,null,"2019-01-16","2019-06-26"]
[3086,800289,"   Perf. part: Even further mobility enhancement in E-UTRAN","LTE_feMob-Perf",2,"Rel-16","R4","2018-06-15","2019-12-13",1,"RP-200148",null,"China Telecom",null,"26/3/19: WID:RP-181475->RP-190272; 7/4/21: 0%->100",null,80,41,null,null,"2018-06-27","2021-04-07"]
[3092,850072,"Support for NavIC Navigation Satellite System for LTE","LCS_NAVIC",1,"Rel-16","R2","2019-09-19","2020-03-13",1,"RP-192408",null,"Reliance Jio",null,"introduction of Indian GNSS; 14/1/20: WID:RP-192350->RP-192408",null,85,43,null,null,"2019-10-08","2020-01-14"]
[3094,850272,"   Perf. part: Support for NavIC Navigation Satellite System for LTE","LCS_NAVIC-Perf",2,"Rel-16","R4","2019-09-19","2020-03-13",1,"RP-192408",null,"Reliance Jio",null,"26/3/20: 0%->100",null,85,43,null,null,"2019-10-08","2020-03-26"]
[3097,880009,"User Plane Integrity Protection ","UPIP_SEC",1,"Rel-16","S3","2020-06-12","2020-06-25",1,"SP-200656",null,"Tim Evans, Vodafone Group ","tim.evans1@vodafone.com ","33.501; 33.401 ; 26/6/20: 0%->100; 25/9/20: WID:SP-200354->SP-200656",null,88,45,null,null,"2020-06-25","2020-09-25"]
[3101,830286,"   Perf. Part: Introduction of GSM, UTRA, E-UTRA and NR CS(s) to the MSR specifications","MSR_GSM_UTRA_LTE_NR-Perf",2,"Rel-16","R4","2019-03-01","2019-09-13",1,"RP-190642",null,"Ericsson",null,"8/10/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-10-08"]
[3105,840067,"      Stopped - CT1 aspects of VBCLTE","VBCLTE",3,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-191110",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","2/7/20: 0%->100",24.228999999999999,84,43,84,null,"2019-05-31","2020-07-02"]
[3106,840068,"      CT3 aspects of VBCLTE","VBCLTE",3,"Rel-16","C3","2019-06-06","2020-03-12",1,"CP-201206",null,"Huang Zhenning (China Mobile) ","huangzhenning (at) chinamobile (dot) com ","6/12/19: 0%->100; 26/6/20: WID:CP-191110->CP-201206","29.212; 29.213; 29.214",84,43,null,null,"2019-05-31","2020-06-26"]
[3110,850060,"      Stage 2 of IABARC","IABARC",3,"Rel-16","S2","2019-09-19","2019-12-12",1,"SP-190627",null,"Hong Cheng, Qualcomm Incorporated ","hongc@qti.qualcomm.com ","13/9/19: 0%->33; 6/12/19: 33%->100","23.501; 23.502; 23.401 ",85,43,null,null,"2019-09-13","2019-12-06"]
[3113,820170,"   Core part: NR_IAB","NR_IAB-Core",2,"Rel-16","R2","2019-03-07","2020-03-06",1,"RP-210442",null,"Qualcomm",null,"follow-up WI of REL-16 SI FS_NR_IAB¦26/3/19: WID:RP-182882->RP-190712; 8/10/19: WID:RP-190712->RP-192188; 28/7/20: WID:RP-200084->RP-200840; 25/9/20: 0%->100; 25/9/20: 38.175 added;; 25/9/20: 38.809 added;","38.175; 38.809",82,42,null,null,"2019-01-16","2020-09-25"]
[3119,810023,"Energy efficiency of 5G","EE_5G",1,"Rel-16","S5","2018-09-06","2020-03-12",1,"SP-191193",null,"CORNILY, Jean-Michel, ORANGE","jeanmichel.cornily@orange.com ","7/12/18: 0%->20¦14/3/19: 20%->40; 31/5/19: 40%->45; 13/9/19: 45%->70; 12/12/19: WID:SP-180819->SP-191193; 12/12/19: FCD:13/12/2019->03/20; 26/3/20: 70%->95; 28/6/20: 95%->100","28.540; 28.541; 28.552; 28.554",81,41,null,null,"2018-09-06","2020-06-28"]
[3121,790001,"New Services and Markets Technology Enablers – Phase 2 ","SMARTER_Ph2",1,"Rel-16","S1","2018-03-15","2018-12-14",1,"SP-180589",null,"Li, Alice, Vodafone","alice.li@vodafone.com","7/6/18: WID:SP-180138->SP-180313¦7/6/18: 0%->10¦10/9/18: 10%->40¦4/12/18: 40%->100","22.261; 22.278",79,40,null,null,"2018-03-15","2018-12-04"]
[3124,840069,"5GS Transfer of Policies for Background Data Transfer","xBDT",1,"Rel-16",null,"2019-03-07","2020-03-12",1,"SP-180509",null,"Takeshi　Usui KDDI ","ta-usui@kddi.com",null,"23.501; 23.502; 23.503",84,43,null,null,"2018-06-06","NA"]
[3129,850057,"      CT4 aspects of xBDT","xBDT",3,"Rel-16","C4","2019-09-17","2020-03-12",1,"CP-192182",null,"Yan Xiaojian, ZTE ","yan.xiaojian@zte.com.cn ","26/3/20: 0%->100",null,85,43,null,null,"2019-05-31","2020-03-26"]
[{"$f":"A3132+1","v":3132},800046,"Shared Data Handling on Nudm and Nudr","Shared_Data",1,"Rel-16","C4","2018-06-06","2018-12-14",1,"CP-181136",null,"Wiehe, Ulrich, Nokia","ulrich.wiehe@nokia.com","10/9/18: 0%->90¦10/12/18: 90%->100","29.503; 29.505; 29.504",80,41,null,null,"2018-06-06","2018-12-10"]
[3133,790019,"Usage of CAPIF for xMB API","CAPIF4xMB",1,"Rel-16","S4","2018-03-15","2018-12-14",1,"SP-180031",null,"Thorsten Lohmar, Ericsson LM ","Thorsten.lohmar@ericsson.com","7/6/18: 0%->25¦6/8/18: 26.348 added;¦10/9/18: 25%->40¦7/12/18: 40%->100","26.346; new; 26.348",79,40,null,null,"2018-03-15","2018-12-07"]
[3137,760058,"Management of QoE measurement collection","QOED",1,"Rel-16","S5","2017-06-05","2019-12-12",1,"SP-181069",null,"Petersen, Robert, Ericsson","robert <dot> petersen <at>ericsson<dot>ericsson","30/6/17: 28.309 added;¦30/6/17: 28.308 added;¦30/6/17: 28.307 added;¦30/6/17: 28.406 added;¦11/9/17: 0%->5¦15/12/17: 5%->15¦16/3/18: 15%->25¦7/6/18: FCD:06/18->12/18. 16/6/16: moved from Rel-15¦10/9/18: 25%->30¦7/12/18: 30%->40¦13/12/18: FCD: ; 31/5/ ","32.101; 32.103; 6 new TS; 28.309; 28.308; 28.307; 28.406; 28.405; 28.404",76,39,null,null,"2017-06-07","2020-09-13"]
[3140,810024,"OAM aspects of LTE and WLAN integration","OAM_LTE_WLAN",1,"Rel-16","S5","2018-09-06","2019-06-14",1,"SP-180820",null,"Yizhi Yao, Intel Corporation ","yizhi dot yao at intel dot com","7/12/18: 0%->50¦14/3/19: 50%->100","32.425; 28.621; 28.622; 28.623; 28.657; 28.658; 28.659",81,41,null,null,"2018-09-06","2019-03-14"]
[3146,820034,"Charging AMF in 5G System Architecture Phase 1 ","5GS_Ph1_AMFCH",1,"Rel-16","S5","2018-12-13","2019-12-19",1,"SP-181071",null,"Gardella, Maryse, Nokia ","maryse.gardella@nokia.com","¦14/3/19: 0%->20; 31/5/19: 20%->50; 13/9/19: 50%->70; 6/12/19: 70%->100","32.240; 32.290; 32.291; 32.298; 32.297 ",82,42,null,null,"2018-12-07","2019-12-06"]
[3148,820005,"Lawful Interception Rel-16 ","LI16",1,"Rel-16","S3LI","2018-12-13","2021-06-11",1,"SP-181210",null,"Alex Leadbeater, BT ","alex.leadbeater@bt.com ","31/5/19: 0%->15; 13/9/19: 15%->40; 6/12/19: 40%->55; 25/3/20: 55%->60; 25/3/20: FCD:19/12/2019->03/20; 26/6/20: FCD:13/03/2020->09/20; 26/6/20: 60%->85; 12/9/20: 85%->92; 5/12/20: 92%->97; 19/3/21: 97%->99; 19/3/21: FCD:15/09/2020->06/21; 11/6/21: 99%- ","33.107; 33.108; 33.126; 33.127; 33.128 ",82,42,null,null,"2018-12-07","2021-06-11"]
[3151,880060,"   CT3 aspects of IMSProtoc16","IMSProtoc16",2,"Rel-16","C3","2018-12-13","2019-12-13",1,"CP-183084",null,"Leis, Peter, Nokia ","peter.leis@nokia.com ","¦14/3/19: 0%->25; 31/5/19: 25%->45; 13/9/19: 45%->65; 6/12/19: 65%->90; 26/3/20: 90%->100; 23/4/20: FCD:19/12/2019->","23.218; 24.229; 24.930; 29.163; 29.165; 29.292 ",87,44,null,null,"2018-12-07","2020-04-23"]
[3156,820042,"Stage-3 SAE Protocol Development for Rel16","SAES16",1,"Rel-16","C1","2018-12-13","2019-12-19",1,"CP-183088",null,"Aghili, Behrouz, InterDigital Communications","behrouz.aghili@interdigital.com ",null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",82,42,null,null,"2018-12-07","NA"]
[3159,820048,"   Stage-3 SAE Protocol Development Rel16 for support for non-3GPP accesses","SAES16-non3GPP",2,"Rel-16","C1","2018-12-13","2019-12-19",1,"CP-183088",null,"Aghili, Behrouz, InterDigital Communications","behrouz.aghili@interdigital.com ","14/3/19: 0%->25; 31/5/19: 25%->50; 30/6/20: 50%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368 ",82,42,null,null,"2018-12-07","2020-06-30"]
[3160,840018,"S6b Optional for ePDG connected to 5GS ","5GS_S6b_Optional",1,"Rel-16","S2","2019-05-09","2019-06-06",1,"SP-190447",null,"Irfan Ali, Cisco ","irfaali at cisco dot com ","6/6/19: 0%->100","23.501; 23.502 ",84,43,null,null,"2019-05-31","2019-06-06"]
[3164,840008,"Withdrawal of TS 24.323 from Rel-11, Rel-12, Rel-13 ","ISAT-MO-WITHDRAW",1,"Rel-16","C1","2019-06-06","2020-03-12",1,"CP-191151",null,"Dawes, Peter, Vodafone ","peter(dot)dawes(at)vodafone(dot)com ","; 13/9/19: 0%->100",24.323,84,43,null,null,"2019-05-31","2019-09-13"]
[3169,850027,"Streaming trace reporting ","OAM_RTT",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-190782",null,"Andrianov, Anatoly, Nokia ","anatoly.andrianov@nokia.com ","; 26/3/20: 0%->25; 28/6/20: 25%->100","32.421; 32.422; 32.423; 28.532; 28.533 ",85,43,null,null,"2019-09-13","2020-06-28"]
[3172,850034,"Management Aspects of 5G Service-Level Agreement ","MA5SLA",1,"Rel-16","S5","2019-09-19","2020-03-12",1,"SP-200185",null,"Hu, Yushuang, CMCC ","huyushuang@chinamobile.com ","; 25/3/20: WID:SP-190789->SP-200185; 26/3/20: 0%->100","28.540; 28.541 ",85,43,null,null,"2019-09-13","2020-03-26"]
[3175,850052,"   Deleted: C3 aspects of LOLC (TBD)","LOLC",2,"Rel-16","C3","2019-09-19","2020-03-12",1,"CP-200059",null,"Giorgi Gulbani (Huawei) ","giorgi.gulbani@huawei.com ","2/7/20: deleted, put at 100% (was at 0)","TBD",85,43,null,null,"2019-09-13","NA"]
[3178,880057,"   C1 aspects of 5GS_OTAF","5GS_OTAF",2,"Rel-16","C1","2019-09-19","2020-03-12",1,"CP-192257",null,"Wiehe, Ulrich, Nokia ","Ulrich.Wiehe@nokia.com ","; 6/12/19: 0%->65; 26/3/20: 65%->100","23.122; 29.503 ; 29.510 ",85,43,null,null,"2019-09-13","2020-03-26"]
[3183,860020,"CHF-controlled quota management ","CHFCQM",1,"Rel-16","S5","2019-12-06","2020-03-12",1,"SP-191189",null,"Lagha, Naceur, Amdocs ","nlagha@amdocs.com ","; 26/3/20: 0%->50; 28/6/20: 50%->100","32.255; 32.290; 32.291 ",86,44,null,null,"2019-12-06","2020-06-28"]
[3186,860001,"Nudsf Service Based Interface ","NUDSF",1,"Rel-16","C4","2019-12-06","2020-03-12",1,"CP-193270",null,"Askerup, Anders, Hewlett Packard Enterprise, ","Anders.Askerup@hpe.com. ","; 6/12/19: 0%->5; 26/3/20: 5%->85; 2/7/20: 85%->100","29.510; 29.500 ",86,44,null,null,"2019-12-06","2020-07-02"]
[3187,840029,"Study on Nudsf Service Based Interface ","FS_NUDSF",1,"Rel-16","C4","2019-06-06","2019-12-12",1,"CP-191236",null,"Askerup, Anders, Hewlett Packard Enterprise ","Anders.Askerup@hpe.com ","31/5/19: 0%->10; 6/12/19: 10%->100",29.808,84,43,null,null,"2019-05-31","2019-12-06"]
[3191,890045,"UE Conformance Test Aspects - B1C Signal in BDS Positioning System Support for LTE and NR ","B1C_BDS_pos_UEConTest",1,"Rel-16","R5","2020-09-17","2021-09-08",1,"RP-201777",null,"CATT ",null,"tested: REL-16 TEI16 CR set (R2-2000238, R2-2002121, R2-2000240) of RP-200357 and (R4-2008551, R4-2008540) of RP-201055 ; 8/4/21: 0%->71; 2/7/21: FCD:Thu 17/06/->09/21; 29/9/21: 71%->100",null,89,45,null,null,"2020-09-25","2021-09-29"]
[{"$f":"A3196+1","v":3196},860099,"   (Small) Test Technical Enhancements and Improvements for Rel-16","TEI16_Test",2,"Rel-16","R5","2020-03-13","2020-06-30",0,null,null,null,null,null,null,86,41,null,null,"2018-06-27","NA"]
[3199,800029,"Stopped - Study on system architecture for next generation real time communication services","FS_NG_RTC",1,"Rel-16","S2","2018-06-06","2019-03-14",1,"SP-180508",null,"Yi Jiang ","jiangyi at chinamobile dot com","03/22: stopped at 0% (\"deprioritised\"in SA2 language)","New",80,41,84,null,"2018-06-06","2022-03-22"]
[3202,780001,"Study on User Plane Protocol in 5GC","FS_UPPS",1,"Rel-16","C4","2017-12-15","2019-06-14",1,"CP-182052",null,"Satoru Matsushima, SoftBank Corp","satoru.matsushima@g.softbank.co.jp","16/3/18: 0%->5¦2/10/18: WID:CP-173160->CP-182052¦2/10/18: FCD:09/18->06/19¦14/3/19: 20%->70; 31/5/19: 70%->90; 14/1/20: 90%->100",29.891999999999999,78,40,null,null,"2017-12-15","2020-01-14"]
[3205,800093,"Study on remote interference management for NR","FS_NR_RIM",1,"Rel-16","R1","2018-06-15","2018-12-14",1,"RP-181430",null,"CMCC",null,"TR 38.8xx¦see follow-up REL-16 WI NR_CLI_RIM¦16/1/19: 0%->100",null,80,41,null,null,"2018-06-27","2019-01-16"]
[3210,750046,"Study on Non-Orthogonal Multiple Access (NOMA) for NR","FS_NR_NOMA",1,"Rel-16","R1","2017-03-15","2018-12-14",1,"RP-181403",null,"ZTE",null,"TR 38.8XX¦19/6/17: WID: RP-170829->RP-171043¦30/6/17: 32.812 added;¦27/6/18: Compl:0%->40%¦27/6/18: CD:Fri 15/06/18->Sat 15/12/18¦27/6/18: WID: RP-171043->RP-181403;¦16/1/19: 40%->100",32.811999999999998,75,38,null,null,"2017-03-21","2019-01-16"]
[3214,820060,"Study on 7 - 24 GHz frequency range for NR","FS_7to24GHz_NR",1,"Rel-16","R4","2018-12-13","2019-12-13",1,"RP-192076",null,"Huawei",null,"TR. 38.8xx¦26/3/19: WID:RP-182884->RP-190373; 8/10/19: WID:RP-190373->RP-192076; 28/7/20: 0%->100",null,82,42,null,null,"2019-01-16","2020-07-28"]
[3215,830006,"Study on UEs Supporting Handset Mode with Non-Traditional Earpieces","FS_HaNTE",1,"Rel-16","S4","2019-03-07","2019-09-05",1,"SP-190041",null,"Schevciw, Andre, Qualcomm Incorporated","aschevci@qti.qualcomm.com ","31/5/19: 0%->10; 13/9/19: 10%->100","New",83,42,null,null,"2019-03-14","2019-09-13"]
[3218,0,"Release 16 other Studies","-",1,"Rel-16",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3223,780031,"Study on integration of ONAP DCAE and 3GPP management architecture ","FS_ONAPDCAE",1,"Rel-16","S5","2017-12-15","2019-03-15",1,"SP-181074",null,"ORANGE (Jean-Michel Cornily","jeanmichel.cornily@orange.com","16/3/18: 0%->10¦27/3/18: 28.900 added;¦7/6/18: 10%->20¦7/6/18: FCD:09/18->03/19¦15/6/18: WID:SP-170948->SP-180389¦10/9/18: 20%->35¦7/12/18: 35%->80¦14/12/18: WID:SP-180389->SP-181074¦14/3/19: 80%->100",28.9,78,40,null,null,"2017-12-15","2019-03-14"]
[3226,810029,"Study on management aspects of communication services","FS_CSMAN",1,"Rel-16","S5","2018-09-06","2019-06-14",1,"SP-180923",null,"Groenendijk, Jan, Ericsson","jan<dot>Groenendijk<at>ericsson<dot>com.","7/12/18: 0%->40¦14/3/19: 40%->70; 31/5/19: 70%->75; 13/9/19: 75%->100","New",81,41,null,null,"2018-09-06","2019-09-13"]
[3229,820004,"Study on ambient noise test methodology for evaluation of acoustic UE performance ","FS_ANTeM",1,"Rel-16","S4","2018-12-06","2019-12-12",1,"SP-180986",null,"Jan Reimes, HEAD acoustics GmbH","jan.reimes@head-acoustics.de ","12/3/19: 0%->10; 31/5/19: 0%->10; 31/5/19: 0%->10; 13/9/19: 10%->70; 25/3/20: 70%->100",null,82,42,null,null,"2018-12-07","2020-03-25"]
[3232,850018,"Study on storage and transport of 5GC security parameters for ARPF authentication ","FS_5GC_SEC_ARPF",1,"Rel-16","S3","2019-09-19","2021-03-12",1,"SP-190708",null,"Evans, Timothy, Vodafone ","tim.evans1@vodafone.com ","; 8/10/19: 33.502 added;; 6/12/19: 0%->30; 6/12/19: FCD:12/12/2019->03/20; 26/6/20: FCD:12/03/2020->09/20; 26/6/20: 30%->60; 12/9/20: 60%->75; 12/9/20: FCD:15/09/2020->12/20; 5/12/20: 75%->90; 5/12/20: FCD:15/12/2020->03/20; 19/3/21: 90%->98; 11/6/21: ","New ; 33.502",85,43,null,null,"2019-09-13","2021-06-11"]
[3237,720005,"   (Stage 1 of 5G) New Services and Markets Technology Enablers","SMARTER",2,"Rel-15","S1","2016-06-09","2017-03-15",1,"SP-160364",null,"Li, Alice","alice.li@vodafone.com","Resulting from FS_SMARTER¦19/9/16: 0%->55¦6/10/16: 22.261 added¦1/12/16: FCD:09/16->03/20¦1/12/16: 55%->75¦2/3/17: 75%->90¦7/6/17: 90%->100",22.260999999999999,72,37,null,null,"2016-06-09","2017-06-07"]
[3241,750025,"   CT aspects of 5G System - Phase 1","5GS_Ph1-CT",2,"Rel-15","ct","2017-03-03","2018-06-14",1,"CP-183243",null,"Song Yue (China Mobile)","songyue at chinamobile.com","6/17: WID:CP-170204->CP-171105¦9/17: WID:CP-171105->CP-172034. Rapp changed, impacted TS clarified¦12/17: added: 24.501 ¦24.502 ¦29.520 added¦29.514¦29.513 ¦29.520a¦29.514a¦12/17: 29.519 added¦29.516 added;¦: 2.. 3/18: 29.554 added;29.59¦6/ ","24.501; 24.502; 29.520; 29.514; 29.513; ; 29.520a; 29.514a; 29.519; 29.516; 29.512; 29.508; 29.507; 29.551; 29.554; 29.522; 24.568; 29.521; 29.525; 29.524; 29.523",75,38,null,null,"2017-03-03","2018-12-10"]
[3242,750026,"      Studies on CT1 aspects of 5G System - Phase 1","5GS_Ph1-CT",3,"Rel-15",null,"2017-03-03","2017-12-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","18/12/17: WID:CP-172034->CP-173161","23.122; 23.040; 23.041; 24.007; 24.301; 24.008; 24.302; 24.011; 24.312; 24.305; 24.368; 27.007",75,38,null,null,"2017-03-03","2017-12-18"]
[3245,770044,"         Study on 5G Session management","5GS_Ph1-CT",4,"Rel-15","C1","2017-03-03","2017-12-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","Task introduced as per CT1's chair e-mail¦11/9/17: 35%->75¦15/12/17: 75%->100",null,77,39,null,null,"2017-03-03","2017-12-15"]
[3250,780008,"      CT1 aspects of 5G System - Phase 1 (normative work)","5GS_Ph1-CT",3,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,"23.122; 23.040; 23.041; 24.007; 24.301; 24.008; 24.302; 24.011; 24.312; 24.305; 24.368; 27.007",75,38,null,null,"2017-03-03","2017-09-08"]
[3253,780011,"         5G Session management","5GS_Ph1-CT",4,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->35¦16/3/18: 35%->85¦7/6/18: 85%->100",null,77,39,null,null,"2017-03-03","2018-06-07"]
[3255,780013,"         5G Interworking with EPC","5GS_Ph1-CT",4,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-183243",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->20¦16/3/18: 20%->60¦7/6/18: 60%->100",null,77,39,null,null,"2017-03-03","2018-06-07"]
[3261,870080,"      (IETF) Improved Extensible Authentication Protocol Method for 3GPP Mobile Network Authentication and Key Agreement (EAP-AKA') (draft-ietf-emu-rfc5448bis)","5GS_Ph1-CT",3,"Rel-15","C4-IETF","2017-03-03","2017-12-14",1,null,null,null,null,"20/6/22: Compl:80%->100%",null,87,44,null,null,"2017-03-03","2022-06-20"]
[3264,800081,"   UE Conformance Test Aspects – 5G System Non-3GPP Access","5GS_Ph1-CT_n3GPPA-UEConTest",2,"Rel-15","R5","2018-06-15","2019-03-15",1,"RP-181032",null,"Motorola",null,"tested: non-3GPP Access part of REL-15 WI 5GS_Ph1-CT (note: 3GPP Access part of 5GS_Ph1-CT is already covered in REL-15 WI 5GS_NR_LTE-UEConTest);; 26/3/20: 0%->100",null,80,41,null,null,"2018-06-27","2020-03-26"]
[3268,770019,"      CT4 aspects of IMSo5G","5GS_Ph1-IMSo5G",3,"Rel-15","C4","2017-09-04","2018-06-15",1,"CP-180094",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","7/6/18: 0%->100","23.008; 29.228; 29.229; 29.328; 29.329; 23.003",77,39,null,null,"2017-03-03","2018-06-07"]
[3269,780034,"   Service Based Interface for 5G Charging","5GS_Ph1-SBI_CH",2,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-170951",null,"Chen, Shan, Huawei","chenshan@huawei.com","16/3/18: 0%->15¦7/6/18: 15%->55¦7/6/18: FCD:06/18->09/18¦10/9/18: 55%->100","32.240; 32.298",78,40,null,null,"2017-12-15","2018-09-10"]
[3272,800040,"   Charging for IMS over 5G System Architecture Phase 1","5GS_Ph1_IMSCH",2,"Rel-15","S5","2018-05-07","2018-06-15",1,"SP-180391",null,"Gardella, Maryse, Nokia","maryse.gardella@nokia.com","7/6/18: 0%->100","32.240; 32.260; 32.299; 32.298",80,41,null,null,"2018-06-06","2018-06-07"]
[3277,760001,"   CT aspects of EDCE5","EDCE5-CT",2,"Rel-15","ct","2017-06-05","2017-12-14",1,"CP-173038",null,"Jesús de Gregorio, Ericsson ","jesus.de.gregorio@ericsson.com","18/12/17: WID:CP-171045->CP-173038",null,76,39,null,null,"2017-06-05","2017-12-18"]
[3280,760070,"      CT4 aspects of EDCE5","EDCE5-CT",3,"Rel-15","C4","2017-06-05","2017-12-14",1,"CP-173038",null,"Jesús de Gregorio, Ericsson ","jesus.de.gregorio@ericsson.com","11/9/17: 0%->50¦15/12/17: 50%->100","23.008; 29.272; 29.230; 29.002; 29.305; 29.274",76,39,null,null,"2017-06-05","2017-12-15"]
[3282,750067,"New Radio Access Technology","NR_newRAT",1,"Rel-15","R1","2017-03-15","2019-06-14",1,"RP-190213",null,"NTT DOCOMO",null,"follow-up WI of REL-14 SI FS_NR_newRAT completed at RAN #75¦30/6/17: 38.425 added;¦14/9/17: WID:RP-170855->RP-171485¦15/12/17: added: 38.305¦38.113¦37.863-04-01¦37.863-03-01¦37.863-02-01¦38.820-04-01¦38.820-03-01¦38.820-02-01¦15/12/17: 37.32 ","38.425; 38.424; 38.423; 38.422; 38.421; 38.420; 38.305; 38.113; 37.863-04-01; 37.863-03-01; 37.863-02-01; 38.820-04-01; 38.820-03-01; 38.820-02-01; 37.324; 37.872; 37.864-11-22; 37.866-00-02",75,38,null,null,"2017-03-21","2019-03-26"]
[3288,760087,"UE Conformance Test Aspects - 5G system with NR and LTE","5GS_NR_LTE-UEConTest",1,"Rel-15","R5","2017-06-15","2021-12-14",0.87,"RP-211228",null,"Ericsson",null,"¦19/9/17: Compl:0%->2%¦15/12/17: impacted specs add¦15/12/17: 38.508-2 added;¦ ;; 8/10/19: WID:RP-181206->RP-192123; 8/10/19: 34.229-5 added;; 24/4/20: FCD:14/12/2018->12/20; 24/4/20: 15%->69; 8/10/20: 69%->79; 8/10/20: FCD:15/12/2020->12/20; 7/4/21: W ","38.507-1; 38.533; 38.522; 38.521-1-2-3; 38.508; 38.509; 38.903; 38.905; 38.523-1-2-3; ; 38.508-2; 34.229-5",76,39,null,null,"2017-06-16","2021-07-02"]
[3291,720003,"   Study on Enhancement of 3GPP support for V2X services","FS_eV2X",2,"Rel-15","S1","2016-06-09","2016-12-15",1,"SP-160370",null,"LG Electronics, SungDuck Chun","sungduck.chun@lge.com","19/9/16: 30%->70¦6/10/16: 22.886 added¦1/12/16: 70%->95¦2/3/17: 95%->100",22.885999999999999,72,37,null,null,"2016-06-09","2017-03-02"]
[3295,750062,"Enhancements on LTE-based V2X Services","LTE_eV2X",1,"Rel-15","R1","2017-03-15","2018-12-14",0.99,"RP-171069",null,"Huawei",null,"follow-up WI of REL-14 WI LTE_V2X for which the Core part was completed at RAN #75¦14/9/17: WID:RP-170798->RP-171069",null,75,38,null,null,"2017-03-21","2017-09-14"]
[3296,750162,"   Core part: V2X phase 2 based on LTE","LTE_eV2X-Core",2,"Rel-15","R1","2017-03-15","2018-09-14",0.99,"RP-171740","RP-180858","Huawei",null,"follow-up WI of REL-14 WI LTE_V2X for which the Core part was completed at RAN #75¦19/6/17: Compl:0%->15%¦ 30/6/17: 36.788 added;¦19/9/17: Compl:15%->30% 8/1/18: Compl:30%->55%27/3/18: Compl:55%->75%",36.787999999999997,75,38,null,null,"2017-03-21","2018-06-27"]
[3300,770037,"EPC support for E-UTRAN Ultra Reliable Low Latency Communication ","EPS_URLLC",1,"Rel-15","S2","2017-09-08","2018-03-15",1,"SP-170811",null,"Chris PUDNEY","chris dot pudney at vodafone dot com","15/12/17: WID:SP-170797->SP-170811¦15/12/17: 0%->15¦20/3/18: 15%->100","23.401; 23.214; 23.203",77,39,null,null,"2017-09-08","2018-03-20"]
[3304,0,"Release 15 Features on improvements of Mission Critical (MC)","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3307,720083,"Study on MC Security Enhancements","FS_MC_Sec",1,"Rel-15","S3","2016-06-17","2018-03-15",1,"SP-170416",null,"Haigh, Peter, CESG","peter.haigh@cesg.gsi.gov.uk ","28/7/16: 33.280 added¦28/7/16: 39.880 added¦19/9/16: WID:SP-160374->SP-160567. FCD: 12/16->03/17¦1/12/16: 0%->35¦6/3/17: FCD:03/17->06/17¦6/3/17: 35%->60¦7/6/17: FCD:06/17->12/17 (Rel-14->Rel-15);60%->65¦8/6/17: WID:SP-160567->SP-170416¦11/9/17","33.xxx; 33.280; 39.880",72,37,null,null,"2016-06-17","2018-03-16"]
[3309,780002,"Removal of 'over LTE' limitation from Mission Critical Specifications","MCOver",1,"Rel-15","S1","2017-11-15","2017-12-15",1,"SP-180354",null,"Kees Verweij ;The Police of the Netherlands","KeesdotVerweijatPolitiedotNL","7/6/18: WID:SP-170986->SP-180354","22.179; 22.280; 22.281; 22.282; 22.468",78,40,null,null,"2017-12-15","2018-06-07"]
[3315,770011,"   Stage 3 of eMCData","eMCData-CT",2,"Rel-15","C1","2017-09-08","2018-06-15",1,"CP-172146",null,"HASON, Baruh","Baruh.Hason@motorolasolutions.com","20/3/18: 0%->30¦7/6/18: 30%->85¦10/12/18: 85%->100","24.282; 24.582; 24.481; 24.483; 24.484",77,39,null,null,"2017-03-03","2018-12-10"]
[3318,770013,"   Stage 3 of eMCVideo","eMCVideo-CT",2,"Rel-15","ct","2017-09-08","2018-06-15",1,"CP-181084",null,"WEI, Haitao","weihaitao@huawei.com","7/6/18: WID:CP-172032->CP-181084",null,77,39,null,null,"2017-06-03","2018-06-07"]
[3322,760067,"MC Security Enhancements","eMCSec",1,"Rel-15","S3","2017-06-05","2018-06-15",1,"SP-170415",null,"Haigh, Peter, NCSC",null,"15/12/17: 0%->80¦15/12/17: FCD:12/17->03/18¦21/12/17: FCD:03/18->05/18. Exception in SP-171056¦16/3/18: 80%->90¦16/3/18: FCD:05/18->06/18¦7/6/18: 90%->100",33.18,76,39,null,null,"2017-06-07","2018-06-07"]
[3323,750023,"MBMS usage for MC communication services ","MBMS_Mcservices",1,"Rel-15","S6","2017-03-03","2018-06-07",1,"SP-170686",null,"Magnus Tränk, Ericsson","magnus.trank@ericsson.com","21/3/17: impacted TS/TR added¦7/6/17: 0%->45¦8/9/17: WID:SP-170075->SP-170686¦8/9/17: FCD:09/17->12/17¦11/9/17: 45%->70¦15/12/17: 70%->95¦16/3/18: 95%->100. Problem with % complete when set as Parent Feature. Has to be left as independent item…","23.280 + 23.281 + 23.282 + 23.379",75,38,null,null,"2017-03-03","2018-03-16"]
[3327,770007,"Protocol enhancements for Mission Critical Services","MCProtoc15",1,"Rel-15","C1","2017-09-08","2018-06-15",1,"CP-172145",null,"Jörgen Axell",null,"14/9/17: 0%->15¦15/12/17: 15%->40¦20/3/18: 40%->70¦7/6/18: 70%->100",null,77,39,null,null,"2017-09-08","2018-06-07"]
[3331,780016,"AT Commands for CIoT-Ext","AT_CIoT-Ext",1,"Rel-15","C1","2017-12-15","2018-06-14",1,"CP-173083",null,"Bakker, John-Luc (Blackberry)","jbakker@blackberry.com","20/3/18: 0%->20¦7/6/18: 20%->100",27.007000000000001,78,40,null,null,"2017-12-15","2018-06-07"]
[3334,750259,"   Perf. part: Even further enhanced MTC for LTE","LTE_eMTC4-Perf",2,"Rel-15","R4","2017-03-15","2018-12-14",1,"RP-172811",null,"Ericsson",null,"note: RAN #75 approved WID RP-170732 with working agreement19/6/17: WID: RP-170732->RP-171427¦8/1/18: WID: RP-171427->RP-172811¦27/6/18: Compl:0%->50%¦16/1/19: 50%->100",null,75,38,null,null,"2017-03-21","2019-01-16"]
[3336,750066,"Further NB-IoT enhancements","NB_IOTenh2",1,"Rel-15","R1","2017-03-15","2021-09-08",0.98,"RP-182389",null,"Huawei",null,"follow-up WI of REL-14 WI NB_IOTenh which got an exception granted at RAN #75 to complete by RAN #76¦note: RAN #75 approved WID RP-170852 with working agreement¦14/9/17: WID:RP-170852->RP-171428",null,75,38,null,null,"2017-03-21","2019-01-16"]
[3342,740003,"   Stage 1 of ProSe_WLAN_DD","ProSe_WLAN_DD",2,"Rel-15","S1","2016-11-15","2016-12-15",1,"SP-160957",null,"Intel Corporation; Ana Lucia Pinheiro","ana.lucia.a.pinheiro@intel.com","1/12/16: 0%->100",22.277999999999999,74,38,null,null,"2016-12-01","2016-12-01"]
[3345,760027,"      CT1 aspects of ProSe_WLAN_DD","ProSe_WLAN_DD_Stage3",3,"Rel-15","C1","2017-06-02","2017-12-06",1,"CP-173084",null,"Intel, Vivek Gupta ","vivek.g.gupta@intel.com","14/9/17: 0%->60¦15/12/17: 60%->100",24.334,76,39,null,null,"2017-06-02","2017-12-15"]
[3347,780045,"   Charging of ProSe_WLAN_DD","ProSe_WLAN_DD-CH",2,"Rel-15","S5","2017-12-15","2018-03-15",1,"SP-170947",null,"Yizhi Yao, Intel Corporation ","yizhi.yao@intel.com","15/12/17: 0%->40¦16/3/18: 40%->100","32.277; 32.298; 32.299",74,38,null,null,"2016-12-01","2018-03-16"]
[3350,760021,"   Stage 2 of VoWLAN","VoWLAN",2,"Rel-15","S2","2017-05-09","2017-06-08",1,"SP-170378",null,"Drevon Nicolas, Nokia","nicolas.drevon@nokia.com ","15/12/17: 0%->100",23.402000000000001,76,39,null,null,"2017-06-02","2017-12-15"]
[3354,760025,"      CT6 aspects of VoWLAN","VoWLAN-CT",3,"Rel-15","C6","2017-06-02","2018-06-14",1,"CP-181083",null,"Jennifer Liu (Nokia)","Jennifer.Liu at nokia.com","7/6/18: 0%->100",31.102,76,39,null,null,"2017-06-02","2018-06-07"]
[3358,770022,"Test Methodologies for the Evaluation of Perceived Listening Quality in Immersive Audio Systems","LiQuImAS",1,"Rel-15","S4","2017-09-08","2018-09-14",1,"SP-170609",null,"Schevciw, Andre – Qualcomm Incorporated ","aschevci@qti.qualcomm.com","15/12/17: added: 26.861¦26.261¦26.260¦26.259¦15/12/17: 0%->15¦16/3/18: 15%->20¦7/6/18: 20%->35¦7/6/18: FCD:06/18->09/18¦10/9/18: 35%->100","New; 26.861; 26.261; 26.260; 26.259",77,39,null,null,"2017-09-08","2018-09-10"]
[3361,0,"Release 15 other Features","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3363,790017,"Diameter Overload Control Mechanisms for Charging","DOCME_CH",1,"Rel-15","S5","2018-03-15","2018-09-14",1,"SP-180077",null,"Törnkvist, Robert, Ericsson","robert(dot)tornkvist(at)Ericsson(dot)com ","7/6/18: 0%->10¦7/6/18: FCD:06/18->09/18¦10/9/18: 10%->100",32.298999999999999,79,40,null,null,"2018-03-15","2018-09-10"]
[3369,790027,"   CT3 aspects of bSRVCC_MT","bSRVCC_MT",2,"Rel-15","C3","2018-03-15","2018-06-14",1,"CP-180153",null,"Song Yue (China Mobile)","songyue (at) chinamobile (dot) com","22/3/18: 0%->95¦10/9/18: 95%->100",29.164999999999999,79,40,null,null,"2018-03-16","2018-09-10"]
[3372,790036,"   Stage 3 of INOBEAR","INOBEAR-CT",2,"Rel-15","ct","2018-03-16","2018-06-15",1,"CP-180098",null,"Samsung, Lalith Kumar ","lalith.kumar@samsung.com",null,null,79,40,null,null,"2017-12-15","NA"]
[3374,790038,"      CT4 aspects of INOBEAR","INOBEAR-CT",3,"Rel-15","C4","2018-03-16","2018-06-15",1,"CP-180098",null,"Samsung, Lalith Kumar ","lalith.kumar@samsung.com","7/6/18: 0%->100",29.274000000000001,79,40,null,null,"2017-12-15","2018-06-07"]
[3377,780019,"Remote UE access via relay UE","REAR",1,"Rel-15",null,"2016-03-01","2018-06-15",1,"SP-160511",null,"Huawei, Laurence Meriau","laurence.meriau@huawei.com","Previously known as \"wearable devices\"¦9/6/16: 0%->100¦9/6/16: WID:SP-160231->SP-160371","22.278; 22.115",71,36,null,null,"2016-03-11","2016-06-09"]
[3381,780046,"Enhanced VoLTE performance","eVoLP",1,"Rel-15",null,"2016-12-01","2018-06-15",1,null,null,null,null,null,null,78,40,null,null,"2017-12-15","NA"]
[3385,780043,"      CT4 aspects of EvoLP","eVoLP-CT",3,"Rel-15","C4","2017-12-15","2018-06-14",1,"CP-173109",null,"Yan, Yali, Huawei","yanyali@huawei.com","7/6/18: 0%->100",29.274000000000001,78,40,null,null,"2017-12-15","2018-06-07"]
[3390,740008,"   Study on unlicensed spectrum offloading system enhancements","FS_USOS",2,"Rel-15","S2","2016-12-01","2017-06-15",1,"SP-160835",null,"Haris Zisimopoulos, Qualcomm Incorporated","harisz@qti.qualcomm.com","1/12/16: 0%->10¦6/3/17: 10%->30¦7/6/17: 30%->90¦11/9/17: 90%->100",23.728999999999999,74,38,null,null,"2016-12-01","2017-09-11"]
[3392,770036,"   Stage 2 of USOS","USOS",2,"Rel-15","S2","2017-09-08","2017-12-15",1,"SP-170740",null,"Haris Zisimopoulos ","harisz@qti.qualcomm.com","15/12/17: 0%->100","23.401; 23.203",77,39,null,null,"2017-09-08","2017-12-15"]
[3396,750024,"   Study on Application Architecture for the Future Railway Mobile Communication System (stage 2) ","FS_FRMCS_ARCH",2,"Rel-15","S6","2017-03-03","2017-12-14",1,"SP-170269",null,"Oettl, Martin, Nokia","martin(dot)oettl(at)nokia(dot)com ","21/3/17: added impacted TR¦7/6/17: 0%->10¦11/9/17: 10%->50¦15/12/17: 50%->100","new 23.790",75,38,null,null,"2017-03-03","2017-12-15"]
[3399,790031,"   Stage 3 of MONASTERY","MONASTERY",2,"Rel-15","ct","2018-03-16","2018-06-15",1,"CP-182202",null,"Leis, Peter (Nokia) ","peter(dot)leis(at)nokia(dot)com ","10/9/18: WID:CP-180097->CP-182202",null,79,40,null,null,"2018-03-16","2018-09-10"]
[3401,790033,"      CT3 aspects of MONASTERY","MONASTERY",3,"Rel-15","C3","2018-03-16","2018-06-15",1,"CP-182202",null,"Leis, Peter (Nokia) ","peter(dot)leis(at)nokia(dot)com ","10/9/18: 0%->100",29.164999999999999,79,40,null,null,"2018-03-16","2018-09-10"]
[3404,760030,"PS Data Off Phase 2 ","PS_DATA_OFF2",1,"Rel-15",null,"2017-03-02","2018-06-14",1,"SP-170246",null,"Murhammer, Leopold, Deutsche Telekom AG","leopold.murhammer@t-mobile.at",null,null,75,38,null,null,"2017-03-02","NA"]
[3408,760033,"      CT4 aspects of PS Data Off Phase 2 ","PS_DATA_OFF2-CT",3,"Rel-15","C4","2017-06-02","2018-06-14",1,"CP-181082",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","15/12/17: 0%->100","29.272; 29.274; 29.328; 29.329; 29.228; 29.229; 23.008",76,39,null,null,"2017-06-02","2017-12-15"]
[3412,780006,"   Stage 3 of NAPS","NAPS-CT",2,"Rel-15","C3","2017-06-02","2018-06-14",1,"CP-173112",null,"Yan, Yali, Huawei, ","yanyali@huawei.com","5/6/17: 0%->25¦8/9/17: WID:CP-171143->CP-172057¦11/9/17: 25%->40¦11/9/17: 40%->90. 18/12/17: WID corrected¦18/12/17: WID:CP-171143 ->CP-173112","29.336; 29.128; 29.230",78,40,null,null,"2017-06-02","2017-12-18"]
[3417,770049,"Common API Framework for 3GPP Northbound APIs ","CAPIF",1,"Rel-15",null,"2017-03-10","2018-06-15",1,"SP-170798",null,"Suresh Chitturi, Samsung","s.chitturi@samsung.com","15/12/17: 23.222 added;","New; 23.222",77,39,null,null,"2017-09-08","2017-12-15"]
[3420,790042,"   Stage 3 of CAPIF","CAPIF-CT",2,"Rel-15","C3","2018-03-16","2018-06-15",1,"CP-180151",null,"Nishant Gupta, Samsung","nishant.gup@samsung.com ","16/3/18: 0%->10¦27/3/18: 29.222 added¦19/4/18: CAPIF->CAPIF-CT¦7/6/18: 10%->35¦7/6/18: 35%->85¦10/9/18: 85%->100","29.122; 29.116; 29.222",79,40,null,null,"2018-03-16","2018-09-10"]
[3423,780056,"   General aspects of NETSLICE","NETSLICE",2,"Rel-15","S5","2016-06-13","2018-09-14",1,"SP-180816",null,"Jan Groenendijk, Ericsson","jan<dot>groenendijk<at>ericsson<dot>com","21/12/17: created from the Feature level, since SP-170960 contains its own specs and completions¦16/3/18: 46%->60¦7/6/18: 60%->85¦7/6/18: FCD:06/18->09/18¦8/8/18: WID:SP-170960->SP 180124¦10/9/18: 85%->100","32.101; 32.103; 28.530",76,39,null,null,"2017-06-05","2018-09-10"]
[3426,760065,"   Provisioning of network slicing for 5G networks and services","NETSLICE-PRO_NS",2,"Rel-15","S5","2017-06-05","2018-09-14",1,"SP-180818",null,"Zhang Kai, Huawei","kai.zhangkai@huawei.com","15/12/17: 0%->15¦21/12/17: WID:SP-170580->SP-170955¦16/3/18: 15%->40¦27/3/18: 28.532 added;¦7/6/18: 40%->80¦7/6/18: FCD:06/18->09/18¦10/9/18: 80%->100¦2/10/18: WID:SP-170955->SP-180818",28.530999999999999,76,39,null,null,"2017-06-05","2018-10-02"]
[3428,780038,"   Performance Assurance for 5G networks including network slicing","NETSLICE-ADPM5G",2,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-180814",null,"Yizhi Yao, Intel Corporation ","yizhi dot yao at intel dot com","16/3/18: 0%->10¦7/6/18: 10%->50¦7/6/18: FCD:06/18->09/18¦10/9/18: 50%->100¦2/10/18: WID:SP-170957->SP-180814",32.404000000000003,78,40,null,null,"2017-12-15","2018-10-02"]
[3431,810009,"   CT aspects of 5G Trace management ","NETSLICE-5GTRACE-CT",2,"Rel-15","ct","2018-09-06","2018-09-06",1,"CP-182051",null,"Landais, Bruno, Nokia","bruno.landais@nokia.com",null,null,81,41,null,null,"2018-09-06","NA"]
[3435,790039,"Policy and Charging for Volume Based Charging","PC_VBC",1,"Rel-15",null,"2016-12-01","2018-06-15",1,null,null,null,null,null,null,78,40,null,null,"2018-03-16","NA"]
[3439,790040,"   CT1 aspects of PV_VBC","PC_VBC",2,"Rel-15","C1","2018-03-16","2018-06-15",1,"CP-180051",null,"Huang Zhenning (China Mobile)","huangzhenning (at) chinamobile (dot) com","7/6/18: 0%->100","24.605; 24.147",79,40,null,null,"2018-03-16","2018-06-07"]
[3444,770021,"SAND for MBMS","SAND4M",1,"Rel-15","S4","2017-09-08","2018-06-15",1,"SP-170827",null,"Thomas Stockhammer, Qualcomm Incorporated","tsto@qti.qualcomm.com","15/12/17: 0%->50¦15/12/17: FCD:12/17->03/18¦21/12/17: WID:SP-170608->SP-170827¦16/3/18: 50%->60¦16/3/18: FCD:03/18->06/18¦7/6/18: 60%->100","26.247; 26.346; 26.347; TR26.946",77,39,null,null,"2017-09-08","2018-06-07"]
[3447,760012,"Enhanced Calling Name Service","eCNAM",1,"Rel-15",null,"2016-09-15","2018-03-14",1,"SP-160548",null,"Hala Mowafy, Ericsson",null,"1/12/16: 0%->100",22.172999999999998,73,37,null,null,"2016-09-19","2016-12-01"]
[3450,760014,"      CT1 aspects of eCNAM","eCNAM-CT",3,"Rel-15","C1","2017-06-02","2018-03-14",1,"CP-171181",null,"Mowafy, Hala. Ericsson","hala.mowafy@ericsson.com","14/9/17: 0%->40¦15/12/17: 40%->85¦20/3/18: 85%->100","24.259; 24.604; 24.606; 24.607; 24.608; 24.610; 24.611; 24.615; 24.616; 24.629; 24.642; 24.647; 24.654",76,39,null,null,"2017-06-02","2018-03-20"]
[3453,760016,"Stage-3 SAE Protocol Development - Phase 6","SAES6",1,"Rel-15","C1","2017-06-02","2018-06-18",1,"CP-171100",null,"Interdigital, Aghili, Behrouz","Behrouz.aghili@interdigital.com",null,"23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368",76,39,null,null,"2016-03-02","NA"]
[3455,760018,"   SAES6 for support for non-3GPP accesses","SAES6-non3GPP",2,"Rel-15","C1","2017-06-02","2018-06-18",1,"CP-171100",null,"Interdigital, Aghili, Behrouz","Behrouz.aghili@interdigital.com","14/9/17: 0%->20¦15/12/17: 20%->55¦16/3/18: 55%->80¦7/6/18: 80%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118; 24.368",76,39,null,null,"2016-03-02","2018-06-07"]
[3458,720075,"Security Assurance Specification for PGW network product class","SCAS_PGW",1,"Rel-15","S3","2016-06-17","2017-12-12",1,"SP-160481",null,"Peng Jin, China Mobile","pengjin@chinamobile.com","28/7/16: 33.250 added¦19/9/16: 0%->10¦6/10/16: 33.216 added¦1/12/16: 10%->40. 06/03/17: moved from Rel-14.¦6/3/17: 40%->80¦7/6/17: FCD:06/17->12/17¦7/6/17: 80%->95¦11/9/17: 95%->100","33.250; 33.216",72,37,null,null,"2016-06-17","2017-09-11"]
[3463,780047,"      (IETF) Content-ID header field in SIP (draft-ietf-sipcore-content-id)","IMSProtoc9",3,"Rel-15","C1-IETF","2017-06-02","2018-06-15",1,null,null,"Christer Holmberg","christer.holmberg@ericsson.com","22/3/18: 0%->100; 9/4/21: RFC 8262 added;","RFC 8262",78,40,null,null,"2017-12-18","2021-04-09"]
[3466,760011,"   CT3 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc9",2,"Rel-15","C3","2017-06-02","2018-06-13",1,"CP-171098",null,"Dr. Belling, Thomas, Nokia","Thomas.Belling@nokia.com","15/12/17: 0%->40¦7/6/18: 40%->85¦10/9/18: 85%->100","29.163; 29.165; 29.949",76,39,null,null,"2015-04-02","2018-09-10"]
[3471,750168,"   Core part: DL interference mitigation for UMTS","UTRA_DL_IM-Core",2,"Rel-14","R2","2017-03-15","2017-06-15",1,"RP-171136","RP-171135","Qualcomm",null,"no Perf. part19/6/17: Compl:0%->100%",null,75,38,null,null,"2017-03-21","2017-06-19"]
[3474,750077,"   Study on a simplified HS-SCCH for UMTS","FS_UTRA_simple_HSSCCH",2,"Rel-15","R1","2017-03-15","2017-06-15",1,"RP-171477",null,"gerardo.agni.medina.acosta@ericsson.com ","gerardo.agni.medina.acosta@ericsson.com ","19/6/17: Compl:0%->100%¦30/6/17: 25.709 added;",25.709,75,38,null,null,"2017-03-21","2017-06-30"]
[3476,760057,"Charging for enhancement to Flexible Mobile Service Steering (eFMSS) ","eFMSS_CH",1,"Rel-15","S5","2017-06-05","2017-12-14",1,"SP-170482",null,"Long,Biao, China Telecom","longb.gd@chinatelecom.cn. ","11/9/17: 0%->70¦15/12/17: 70%->100","32.251; 32.298; 32.299",76,39,null,null,"2017-06-03","2017-12-15"]
[3481,780033,"   REST Solution Sets (normative work)","REST_SS",2,"Rel-15","S5","2017-12-15","2018-09-14",1,"SP-170950",null,"Pollakowski, Olaf, Nokia","olaf.pollakowski@nokia.com","16/3/18: 0%->20¦7/6/18: 20%->70¦7/6/18: FCD:06/18->09/18¦10/9/18: 70%->100",32.100999999999999,78,40,null,null,"2017-12-15","2018-09-10"]
[3482,800114,"   deleted - (IETF) JSON Schema: A Media Type for Describing JSON Documents (draft-handrews-json-schema)","REST_SS",2,"Rel-15","S5-IETF","2017-12-15","2019-09-16",1,"SP-170950",null,"Pollakowski, Olaf, Nokia","olaf.pollakowski@nokia.com","16/7/24: 0%->100",null,80,41,null,null,"2018-07-10","2024-07-16"]
[3485,790028,"Enhancements to Call spoofing functionality ","eSPECTRE",1,"Rel-15","C1","2018-03-15","2019-03-07",1,"CP-180096",null,"Axell, Jörgen, Ericsson","Jorgen.Axell@ericsson.com",null,null,79,41,null,null,"2018-03-16","NA"]
[3490,750033,"(Small) Technical Enhancements and Improvements for Rel-15","TEI15",1,"Rel-15",null,"2017-03-17","2018-06-15",1,null,null,null,null,null,null,68,35,null,null,"2015-06-15","2015-06-15"]
[3493,0,"Release 15 Features on LTE improvements","-",1,"Rel-15",null,"2000-01-01","2000-01-01",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3498,770168,"   Core part:LTE Advanced inter-band CA (4DL/4UL) of Band 41C and Band 42C","LTE_CA_4DL4UL_B41_B41_B42_B42-Core",2,"Rel-15","R4","2017-09-15","2018-03-15",1,"RP-180151",null,"KDDI",null,"15/12/17: 36.715-04 added;¦8/1/18: Compl:0%->80%27/3/18: Compl:80%->100%;","36.715-04",77,39,null,null,"2017-09-19","2018-03-27"]
[3501,770169,"   Core part: Additional LTE bands for UE category M1 and/or NB1 in Rel-15","LTE_bands_R15_M1_NB1-Core",2,"Rel-15","R4","2017-09-15","2018-06-15",1,"RP-180262",null,"Ericsson",null,"¦8/1/18: Compl:0%->99%27/3/18: WID: RP-172077->RP-180262¦27/6/18: Compl:99%->100%",null,77,39,null,null,"2017-09-19","2018-06-27"]
[3503,780066,"   UE Conformance Test aspects - LTE bands with UE category M1 and/or NB1 in Rel-15","LTE_bands_R15_M1_NB1-UEConTest",2,"Rel-15","R5","2017-12-15","2018-06-15",1,"RP-172713",null,"Ericsson",null,"tested: REL-15 WI LTE_bands_R15_M1_NB1-Core27/3/ ;",null,78,40,null,null,"2018-01-08","2018-06-27"]
[3508,830084,"   UE Conformance Test Aspects - Extended-Band12 new E-UTRA Band (Band 85)","Ext_B12_LTE-UEConTest",2,"Rel-15","R5","2019-03-01","2019-05-31",1,"RP-190937",null,"Ericsson",null,"26/6/19: WID:RP-190510->RP-190937; 26/6/19: 0%->100",null,83,42,null,null,"2019-03-26","2019-06-26"]
[3509,710073,"Stopped - Signalling reduction to enable light connection for LTE","LTE_LIGHT_CON",1,"Rel-15",null,"2016-03-15","2018-03-15",1,"RP-171459",null,"Huawei",null,"no Perf. part¦14/9/17: WID:RP-160540->RP-160937¦14/9/17: WID:RP-160937->RP-171459",null,71,36,80,null,"2016-03-22","2017-09-14"]
[3512,740045,"   Stopped - Stage 3 of LTE_LIGHT_CON","LTE_LIGHT_CON-CT",2,"Rel-15","ct","2016-12-01","2017-03-14",1,"CP-160703",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com",null,null,74,38,80,null,"2016-12-01","NA"]
[3517,710174,"   Core part: Enhancements of Base Station (BS) RF and EMC requirements for Active Antenna System (AAS)","AASenh_BS_LTE_UTRA-Core",2,"Rel-15","R4","2016-03-15","2017-12-15",1,"RP-171745","RP-172345","Huawei",null,"follow-up WI of REL-13 WI AAS_BS_LTE_UTRA1/7/16: Compl:0%->5%1/7/16: CD:Fri 15/09/17->Wed 15/03/1726/9/16: Compl:5%->10% 20/12/16: Compl:10%->20%21/3/17: Compl:20%->40% ;",null,71,36,null,null,"2016-03-22","2018-01-08"]
[3521,720291,"   Perf. part: Shortened TTI and processing time for LTE","LTE_sTTIandPT-Perf",2,"Rel-15","R4","2016-09-14","2018-09-14",1,"RP-171468",null,"Ericsson",null,"¦26/9/16: WID: RP-161299->RP-161922¦20/12/16: WID: RP-161922->RP-16201421/3/17: WID: RP-162014->RP-170113¦19/6/17: CD:Thu 15/03/18->Fri 15/06/1827/3/18: Compl:0%->33%¦27/6/18: Compl:33%->60%¦26/3/19: 60%->100",null,72,37,null,null,"2016-07-01","2019-03-26"]
[3524,740172,"   Core part: 450MHz E-UTRA FDD Band for LTE PPDR and PMR/PAMR in Europe","LTE450_Europe_PPDR-Core",2,"Rel-15","R4","2016-12-15","2017-09-15",1,"RP-162514",null,"Airbus",null,"21/3/17: Compl:0%->10%¦19/6/17: Compl:10%->75%¦19/9/17: Compl:75%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[3528,740174,"   Core part: E-UTRA 700MHz in Europe for Broadband-PPDR","LTE700_Europe_PPDR-Core",2,"Rel-15","R4","2016-12-15","2017-09-15",1,"RP-170212",null,"Airbus",null,"21/3/17: Compl:0%->25%¦19/6/17: Compl:25%->80%¦19/9/17: Compl:80%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[3530,770066,"   UE Conformance Test Aspects - E-UTRA 700MHz in Europe for Broadband-PPDR","LTE700_Europe_PPDR-UEConTest",2,"Rel-15","R5","2017-09-15","2018-03-15",1,"RP-180529",null,"Airbus",null,"¦8/1/18: Compl:0%->64%27/3/18: Compl:64%->100%;",null,77,39,null,null,"2017-09-19","2018-03-27"]
[3533,740275,"   Perf. part: FDD operating band in the L-band for LTE","LTE_FDD_L_Band-Perf",2,"Rel-15","R4","2016-12-15","2017-09-15",1,"RP-171403",null,"NTT DOCOMO",null,"19/6/17: Compl:0%->99%19/6/17: CD:Thu 15/06/19/9/17: Compl:99%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[3536,740176,"   Core part: LTE Extended 1.5 GHz SDL band (1427 – 1518 MHz) and LTE CA (2DL/1UL) with Band 20","LTE_SDL_1500ext-Core",2,"Rel-15","R4","2016-12-15","2017-09-15",1,"RP-171389",null,"Qualcomm",null,"21/3/17: Compl:0%->20%19/6/17: Compl:20%->50%;19/9/17: Compl:50%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[3539,740177,"   Core part: Add UE Power Class 2 to band 41 intra-band contiguous LTE CA","LTE_CA_C_B41_PC2-Core",2,"Rel-15","R4","2016-12-15","2017-12-15",1,"RP-172295",null,"Sprint",null,"21/3/17: Compl:0%->5%¦19/6/17: Compl:5%->50%¦19/9/17: Compl:50%->90%¦8/1/18: Compl:90%->100%;",null,74,38,null,null,"2016-12-20","2018-01-08"]
[3544,740180,"   Core part: TDD operating band in the L-band for LTE","LTE_TDD_L_Band-Core",2,"Rel-15","R4","2016-12-15","2017-09-15",1,"RP-170304",null,"Huawei",null,"21/3/17: Compl:0%->15%¦19/6/17: Compl:15%->70%¦ 19/9/17: Compl:70%->100%",null,74,38,null,null,"2016-12-20","2017-09-19"]
[3548,750260,"   Perf. part: Further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE","feCOMP_LTE-Perf",2,"Rel-15","R4","2017-03-15","2018-06-15",1,"RP-180584",null,"Intel",null,"follow-up WI of REL-14 SI FS_feCOMP_LTE completed at RAN #7519/6/17: WID: RP-170750->RP-171031¦8/1/18: Compl:0%->65%¦8/1/18: CD:Thu 15/03/18->Fri 15/06/1827/3/18: Compl:65%->80%27/3/ ¦27/6/18: Compl:80%->100%",null,75,38,null,null,"2017-03-21","2018-06-27"]
[3551,750263,"   Perf. part: UE Positioning Accuracy Enhancements for LTE","LCS_LTE_acc_enh-Perf",2,"Rel-15","R4","2017-03-15","2018-06-15",1,"RP-181298",null,"Nokia",null,"¦19/6/17: WID: RP-170813->RP-171508¦8/1/18: Compl:0%->30%¦8/1/18: WID: RP-171508->RP-172313¦27/6/18: Compl:30%->100%¦27/6/18: WID: RP-17231",null,75,38,null,null,"2017-03-21","2018-06-27"]
[3555,750065,"Enhancements to LTE operation in unlicensed spectrum","LTE_unlic",1,"Rel-15","R1","2017-03-15","2018-12-14",0.99,"RP-180402",null,"Nokia",null,"note: The is actually a further LAA enhancement",null,75,38,null,null,"2017-03-21","2017-03-21"]
[3557,750265,"   Perf. part: Enhancements to LTE operation in unlicensed spectrum","LTE_unlic-Perf",2,"Rel-15","R4","2017-12-14","2018-12-14",1,"RP-180402",null,"Nokia",null,"19/6/17: CD:Thu 15/03/18->Sat 15/12/18¦8/1/18: WID: RP-170848->RP-17284127/3/18: WID: RP-172841->RP-180402¦16/1/19: 0%->100",null,75,38,null,null,"2017-03-21","2019-01-16"]
[3560,750070,"Quality of Experience (QoE) Measurement Collection for streaming services in E-UTRAN","LTE_QMC_Streaming",1,"Rel-15","R2","2017-03-15","2018-12-14",0.99,"RP-170786",null,"China Unicom",null,"compare REL-14 WI UMTS_QMC_Streaming-Core",null,75,38,null,null,"2017-03-21","2017-03-21"]
[3566,820066,"   UE Conformance Test Aspects - Enhancing LTE CA Utilization","LTE_euCA-UEConTest",2,"Rel-15","R5","2018-12-15","2021-09-08",1,"RP-182619",null,"Nokia",null,"tested: REL-15 WI LTE_euCA-Core; 8/10/20: 0%->35; 8/10/20: FCD:15/12/2019->12/20; 8/4/21: 0%->56; 8/4/21: FCD:12/12/2020->09/20; 2/7/21: 0%->82; 29/9/21: 0%->100",null,82,42,null,null,"2019-01-16","2021-09-29"]
[3567,750073,"450 MHz Band for LTE in Region 3","LTE450_Reg3",1,"Rel-15","R4","2017-03-15","2019-03-15",1,"RP-170952",null,"China Unicom",null,"14/9/17: WID:RP-170159->RP-170952",null,75,38,null,null,"2017-03-21","2017-09-14"]
[3571,750074,"US 600 MHz Band for LTE","LTE600_US",1,"Rel-15","R4","2017-03-15","2017-12-15",1,"RP-170740",null,"Ericsson",null,null,null,75,38,null,null,"2017-03-21","2017-03-21"]
[3575,750076,"LAA/eLAA for the CBRS 3.5GHz band in the United States","LTE_3550_CBRS_US_LAA",1,"Rel-15","R4","2017-03-15","2017-12-15",1,"RP-170804",null,"AT&T",null,"compare REL-14 WI LTE_TDD_3550_CBRS_US¦related to LTE band 48, intending a new band definition¦includes 2DL/2UL CA with B2 Acronym changed, was \"LTE_TDD_3550_CBRS_US_LAA\"",null,75,38,null,null,"2017-03-21","2017-06-19"]
[3578,760097,"Introduction new band support for 4Rx antenna ports for LTE for REL-15","LTE_4Rx_AP_DL_bands_R15",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171131",null,"Huawei",null,null,null,76,39,null,null,"2017-06-19","NA"]
[3582,760198,"   Core part: Addition of band 28 and 40 to LTE MTC cat.0","LC_MTC_LTE_cat0_B28_B40-Core",2,"Rel-15","R4","2017-06-15","2017-09-15",1,"RP-171132",null,"Huawei",null,"19/9/17: Compl:0%->100%",null,76,39,null,null,"2017-06-16","2017-09-19"]
[3584,760199,"   Core part: LTE Advanced high power TDD UE (power class 2) for Rel-15","LTE_TDD_HPUE_R15-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171755",null,"Huawei",null,"19/9/17: Compl:0%->10%¦ 15/12/17: 36.760 added;¦8/1/18: Compl:10%->40%27/3/18: Compl:40%->99%¦27/6/18: Comp",36.76,76,39,null,null,"2017-06-16","2018-06-27"]
[3587,761100,"   Core part: New LTE band for 3.3-3.4 GHz for Africa","LTE_TDD_3300_Africa-Core",2,"Rel-15","R4","2017-06-15","2018-03-15",1,"RP-180247",null,"Huawei",null,"12/7/17: 36.758 added;19/9/17: Compl:0%->10%¦ 8/1/18: Compl:10%->70%27/3/18: Compl:70%->100%;",36.758000000000003,76,39,null,null,"2017-06-16","2018-03-27"]
[3593,780168,"   Core part: Bluetooth/WLAN measurement collection in LTE Minimization of Drive Tests (MDT)","LTE_MDT_BT_WLAN-Core",2,"Rel-15","R2","2017-12-15","2018-09-14",0.95,"RP-180306","RP-180867","CMCC",null,"MDT = Minimization of Drive Tests¦no Perf. part¦may have SA5 impact27/3/18: Compl:0%->30%2 ¦27/6/18: Compl:30%->95%",null,78,40,null,null,"2018-01-08","2018-06-27"]
[3594,820065,"   UE Conformance Test Aspects - Bluetooth/WLAN measurement collection in LTE Minimization of Drive Tests (MDT)","LTE_MDT_BT_WLAN-UEConTest",2,"Rel-15","R5","2018-12-15","2019-12-15",1,"RP-182509",null,"CMCC",null,"tested: REL-15 WI LTE_MDT_BT_WLAN-Core; 14/1/20: 0%->100; 14/1/20: 100%->100",null,82,42,null,null,"2019-01-16","2020-01-14"]
[3598,820062,"   UE Conformance Test Aspects - Enhanced LTE Support for Aerial Vehicles","LTE_Aerial-UEConTest",2,"Rel-15","R5","2018-12-15","2019-06-19",1,"RP-192747",null,"NTT DOCOMO",null,"tested: REL-15 WI LTE_Aerial-Core; 8/10/19: WID:RP-182324->RP-191747; 14/1/20: WID:RP-191747->RP-192747; 14/1/20: 0%->100",null,82,42,null,null,"2019-01-16","2020-01-14"]
[3602,780172,"   Core part: UE requirements for LTE DL 8Rx antenna ports","LTE_8Rx_AP_DL-Core",2,"Rel-15","R4","2017-12-15","2018-06-15",1,"RP-180960","RP-180959","Huawei",null,"follow-up WI of REL-15 SI FS_LTE_8Rx_AP_DL27/3/18: Compl:0%->40%¦27/6/18: Compl:40%->100%",null,78,40,null,null,"2018-01-08","2018-06-27"]
[3606,810063,"   UE Conformance Test Aspects - ProSe Support for Band 72 in LTE","LTE450_B72_Europe_ProSe-UEConTest",2,"Rel-15","R5","2018-09-14","2018-12-14",1,"RP-181630",null,"Airbus",null,"16/1/19: 0%->100",null,81,41,null,null,"2018-09-25","2019-01-16"]
[3607,780074,"LTE Advanced inter-band CA Rel-15 for xDL/1UL with x>5","LTE_CA_R15_xDL1UL",1,"Rel-15","R4","2017-12-15","2018-12-14",1,"RP-172839",null,"Qualcomm",null,"basket CA WI¦TR 36.715-00-01",null,78,40,null,null,"2018-01-08","2018-01-08"]
[3613,761203,"   Perf. part: LTE CRS-Interference Mitigation performance requirements for single RX chain UEs","LTE_1RX_CRS_IM-Perf",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-N1122",null,"Intel",null,"¦19/9/17: Compl:0%->20%¦19/9/17: WID: RP-171465->RP-171831¦8/1/18: Compl:20%->60%¦27/3/18: Compl:60%->85%¦27/6/18: Compl:85%->100%",null,76,39,null,null,"2017-06-16","2018-06-27"]
[3614,760090,"LTE Advanced intra-band CA Rel-15 for xDL/yUL including contiguous and non-contiguous spectrum","LTE_CA_R15_intra",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-170962",null,"Ericsson",null,null,null,76,39,null,null,"2017-06-19","NA"]
[3620,760092,"LTE Advanced inter-band CA Rel-15 for 3DL/1UL","LTE_CA_R15_3DL1UL",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171126",null,"Huawei",null,null,null,76,39,null,null,"2017-06-19","NA"]
[3621,760192,"   Core part:LTE Advanced inter-band CA Rel-15 for 3DL/1UL","LTE_CA_R15_3DL1UL-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180955",null,"Huawei",null,"12/7/17: 36.715-03-01 added;¦19/9/17: Compl:0%->20%¦ 8/1/18: Compl:20%->40%¦27/3/18: Compl:40%->65%¦ ¦27/6/18: Compl:65%->100%;","36.715-03-01",76,39,null,null,"2017-06-16","2018-06-27"]
[3625,760293,"   Perf. part:LTE Advanced inter-band CA Rel-15 for 4DL/1UL","LTE_CA_R15_4DL1UL-Perf",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180801",null,"Ericsson",null,"19/9/17: Compl:0%->54%¦ 8/1/18: Compl:54%->65%¦27/3/18: Compl:65%->63% ¦27/6/18: Compl:63%->100%;",null,76,39,null,null,"2017-06-16","2018-06-27"]
[3629,760095,"LTE Advanced inter-band CA Rel-15 for 2DL/2UL","LTE_CA_R15_2DL2UL",1,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-171127",null,"Huawei",null,null,null,76,39,null,null,"2017-06-19","NA"]
[3633,760196,"   Core part:LTE Advanced inter-band CA Rel-15 for xDL/2UL with x=3,4,5","LTE_CA_R15_xDL2UL-Core",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180770",null,"LG Electronics",null,"12/7/17: 36.715-00-02 added;¦19/9/17: Compl:0%->20% 8/1/18: Compl:20%->50%¦27/3/18: Compl:50%->80%¦ ¦27/6/18: ","36.715-00-02",76,39,null,null,"2017-06-16","2018-06-27"]
[3634,760296,"   Perf. part:LTE Advanced inter-band CA Rel-15 for xDL/2UL with x=3,4,5","LTE_CA_R15_xDL2UL-Perf",2,"Rel-15","R4","2017-06-15","2018-06-15",1,"RP-180770",null,"LG Electronics",null,"19/9/17: CD:Sat 15/09/18->Fri 15/06/18¦ 8/1/18: Compl:0%->50%¦27/3/18: Compl:50%->80% ¦27/6/18: Compl:80%->100%;",null,76,39,null,null,"2017-06-16","2018-06-27"]
[3640,790153,"   Core part: Further enhancements for Extended Coverage GSM for support of Cellular Internet of Things","CIoT_EC_GSM_fenh-Core",2,"Rel-15","R6","2018-03-15","2018-09-14",0.8,"RP-180541",null,"Nokia",null,"follow-up WI of REL-14 WI CIoT_EC_GSM_radio_enh¦27/6/18: Compl:0%->80%;",null,79,40,null,null,"2018-03-27","2018-06-27"]
[3641,790253,"   Perf. part: Further enhancements for Extended Coverage GSM for support of Cellular Internet of Things","CIoT_EC_GSM_fenh-Perf",2,"Rel-15","R6","2018-03-15","2018-09-14",1,"RP-180541",null,"Nokia",null,"follow-up WI of REL-14 WI CIoT_EC_GSM_radio_enh¦27/6/18: Compl:0%->80%;¦10/9/18: 80%->100",null,79,40,null,null,"2018-03-27","2018-09-10"]
[3647,810062,"   UE Conformance Test Aspects - Addition of Power Class 1 UE to bands B31/B72 for LTE","LTE_PC1_B31_B72-UEConTest",2,"Rel-15","R5","2018-09-14","2018-12-14",1,"RP-181629",null,"Airbus",null,"16/1/19: 0%->100",null,null,null,null,null,"2018-09-25","2019-01-16"]
[3649,0,"Release 15 Studies on 5G","-",1,"Rel-15",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3652,750040,"Study on NR to support non-terrestrial networks","FS_NR_nonterr_nw",1,"Rel-15","R1","2017-03-15","2018-06-15",1,"RP-171450",null,"Thales",null,"TR 38.8XX19/6/17: Compl:0%->25%19/6/17: CD:Fri 15/12/17->Thu 15/03/1819/6/17: WID: RP-170717->RP-171450¦30/6/17: 38.811 added;¦19/9/17: Compl:25%->40%¦8/1/18: CD:Thu 15/03/18->Fri 15/06/18¦27/3/18: Compl:40%->45%¦27/6/18: Compl:4",38.811,75,38,null,null,"2017-03-21","2018-06-27"]
[3656,710064,"Stopped - Study on LTE bandwidth flexibility enhancements","FS_LTE_BW_flex",1,"Rel-15","R4","2016-03-15","2017-03-15",1,"RP-161670",null,"Huawei",null,"1/7/16: Compl:0%->50%¦28/7/16: 36.740 added¦26/9/16: WID: RP-161328->RP-161670¦20/12/16: CD:Thu 15/0;21/3/17: CD:Fri 15 12/7/17: 50%->100 since declared as stopped",36.74,71,36,80,null,"2016-03-22","2017-07-12"]
[3660,0,"Other Release 15 Studies","-",1,"Rel-15",null,"2017-09-08","2018-03-16",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3661,770026,"Study on Update to fixed-point basic operators","FS_BASOP",1,"Rel-15","S4","2017-09-08","2018-03-15",1,"SP-170613",null,"Jelinek, Milan, VoiceAge Corporation","Milan.Jelinek@USherbrooke.ca","15/12/17: 26.973 added;¦15/12/17: 0%->80¦16/3/18: 80%->100","New; 26.973",77,39,null,null,"2017-09-08","2018-03-16"]
[3667,740016,"Study on Management Enhancement of CUPS of EPC Nodes","FS_MECUPS",1,"Rel-15","S5","2016-12-01","2017-12-12",1,"SP-160925",null,"Huawei; Jiang, Junyi","jiangjunyi@huawei.com","6/3/17: 0%->5¦7/6/17: 5%->40¦7/6/17: FCD:09/17->12/17¦11/9/17: 40%->50¦15/12/17: 50%->100",32.866999999999997,74,38,null,null,"2016-12-01","2017-12-15"]
[3668,720041,"Study on Technical Requirements for a new secure platform for 3GPP applications","FS_NG_SP",1,"Rel-15","C6","2016-06-13","2017-09-12",1,"CP-160371",null,"Heiko Kruse","heiko.kruse@safrangroup.com","16/9/16: 0%->15. ¦5/6/17: 15%->70. 5/6/17: moved to Rel-15 (talks with P. Jolivet)¦5/6/17: FCD:12/16->09/20¦15/12/17: 70%->100",31.800999999999998,72,37,null,null,"2016-06-13","2017-12-15"]
[3674,700047,"Study on OAM support for assessment of energy efficiency in mobile access networks","FS_OAM_EE",1,"Rel-15","S5","2015-11-02","2017-06-09",1,"SP-160430",null,"Cornily,Jean-Michel, ORANGE","jeanmichel.cornily@orange.com","13/6/16: WID:SP-150674->SP-160430¦13/6/16: 0%->55¦1/12/16: 55%->80¦6/3/17: FCD:03/17->06/17¦6/3/17: 80%->90¦21/3/17: moved from rel-14¦7/6/17: 90%->100",32.856000000000002,70,36,null,null,"2015-12-07","2017-06-07"]
[3676,700048,"Study on OAM aspects of SON for AAS-based deployments","FS_OAM_SON_AAS",1,"Rel-15","S5","2015-11-02","2017-06-09",1,"SP-150677",null,"Nokia Networks (Yizhi Yao)","Yizhi.yao@nokia.com","13/6/16: 0%->40¦19/9/16: FCD:09/16->12/16¦19/9/16: 40%->60¦1/12/16: FCD:12/16->03/17¦1/12/16: 60%->70¦6/3/17: FCD:03/17->06/17¦21/3/17: moved from rel-14¦7/6/17: 70%->100","(new)",70,36,null,null,"2015-12-07","2017-06-07"]
[3679,730053,"Study on forward compatibility for 3GPP Diameter Charging Applications","FS_FWDCA",1,"Rel-15","S5","2016-09-19","2017-06-15",1,"SP-160608",null,"Nokia, Maryse <dot> Gardella <at> Nokia <dot> com","Nokia, Maryse <dot> Gardella <at> Nokia <dot> com","6/10/16: 32.870 added¦1/12/16: 0%->10¦21/3/17: moved from rel-14¦11/9/17: 10%->40¦15/12/17: 40%->100",32.869999999999997,73,37,null,null,"2016-09-19","2017-12-15"]
[3683,720063,"Study on SON for eCoMP for LTE","FS_LTE_SON_eCOMP",1,"Rel-15","R3","2016-06-15","2017-06-15",1,"RP-161181",null,"Nokia",null,"26/9/16: Compl:0%->10%. ¦20/12/16: Compl:10%->40%21/3/17: Compl:40%->60%¦19/6/17: Compl:60%->100%",null,72,37,null,null,"2016-07-01","2017-06-19"]
[3687,780061,"Study on UE Application Layer Data Throughput Performance Expansion for CA","FS_UE_App_Data_Perf_CA",1,"Rel-15","R5","2017-12-15","2018-06-15",1,"RP-180203",null,"PCTEST Engineering Lab",null,"compare REL-11 SI FS_UE_App_Data_Perf¦note: SI FS_UE_App_Data_Perf_CA is addressing 2DL/1UL involving also an unlicensed carrier of REL-13 LTE_LAA¦instead of a new TR, the TR 37.901 will be updated for REL-15¦ ;",null,78,40,null,null,"2018-01-08","2018-06-27"]
[3688,760064,"Study on system and functional aspects of Energy Efficiency in 5G networks ","FS_EE_5G",1,"Rel-15","S5","2017-06-05","2018-12-14",1,"SP-170489",null,"CORNILY, Jean-Michel, ORANGE","jeanmichel.cornily@orange.com","30/6/17: 32.872 added;¦11/9/17: 0%->5¦15/12/17: 32.972 added;¦15/12/17: 5%->40¦16/3/18: 40%->60¦7/6/18: 60%->65¦7/6/18: FCD:06/18->12/18¦10/9/18: 65%->85¦7/12/18: 85%->100","new; 32.872; 32.972",76,39,null,null,"2017-06-05","2018-12-07"]
[3694,720056,"      Stage 2 of Enhancements for Mission Critical Push To Talk","MCImp-eMCPTT",3,"Rel-14","S6","2016-06-13","2016-12-15",1,"SP-160490",null,"Lazara, Dom","dom.lazara@motorolasolutions.com","28/7/16: 23.379 added¦19/9/16: 0%->35¦1/12/16: 35%->100","23.379; 23.280; 23.281; 23.282; 23.379",72,37,null,null,"2016-06-13","2016-12-01"]
[3697,740025,"         CT3 aspects of Enhancements for Mission Critical Push To Talk","MCImp-eMCPTT-CT",4,"Rel-14","C3","2016-12-01","2017-03-14",1,"CP-160824",null,"FREDERICKS, Bob","bobfredericks@motorolasolutions.com ","5/6/17: 0%->100","29.165; 29.213; 29.214",74,38,null,null,"2016-12-01","2017-06-05"]
[3699,740027,"         CT6 aspects of Enhancements for Mission Critical Push To Talk","MCImp-eMCPTT-CT",4,"Rel-14","C6","2016-12-01","2017-06-14",1,"CP-160824",null,"FREDERICKS, Bob","bobfredericks@motorolasolutions.com ","5/6/17: 0%->100. No work identified for CT6.","31.102; 31.103",74,38,null,null,"2016-12-01","2017-06-05"]
[3703,670006,"      Study on Mission Critical Video over LTE","FS_MCVideo",3,"Rel-14","S1","2015-04-14","2015-12-15",1,"SP-150048",null,"Villebrun, Emmanuelle (French MoI)","emmanuelle.villebrun@gendarmerie.interieur.gouv.fr","1/4/15:TR number added¦June2015: Compl:0%->50¦07/09/15: 50%->70¦7/12/15: 70%->100","New 22.879",67,34,null,null,"2015-03-04","2015-12-07"]
[3706,750018,"      MCVideo codecs and media handling","MCImp-MCVideo",3,"Rel-14","S4","2017-01-11","2017-03-16",1,"SP-170244",null,"John Lambrou (Motorola Solutions)","john (dot) lambrou (at) motorolasolutions (dot) com","6/3/17: 0%->100",26.280999999999999,75,38,null,null,"2017-03-03","2017-03-06"]
[3710,740036,"         CT4 aspects 3 of MCVideo","MCImp-MCVIDEO-CT",4,"Rel-14","C4","2016-12-01","2017-03-15",1,"CP-160827",null,"PATEL, Milan","milan.patel@huawei.com ","6/3/17: 0%->100","23.003; 23.335; 29.283",74,38,null,null,"2016-12-01","2017-03-06"]
[3714,700031,"      Stage 1 of MCData","MCImp-MCData",3,"Rel-14","S1","2015-12-07","2016-06-15",1,"SP-150850",null,"Emmanuelle Villebrun","Emmanuelle.villebrun@gendarmerie.interieur.gouv.fr","2/3/16: FCD: 03/16->06/16. ES in SP-160109¦0->80%¦9/6/16: 80%->100","New 22.282",70,36,null,null,"2015-12-07","2016-06-09"]
[3715,720052,"      Stage 2 for MCData","MCImp-MCData",3,"Rel-14","S6","2016-06-13","2016-12-15",1,"SP-160492",null,"David Freeman (UK Home Office)","david@dnf-consulting.co.uk ","28/7/16: 23.282 added¦19/9/16: 0%->10¦1/12/16: 10%->95¦3/3/17: 95%->100",23.282,72,37,null,null,"2016-06-13","2017-03-03"]
[3719,740031,"         CT4 aspects of MCData","MCImp-MCDATA-CT",4,"Rel-14","C4","2016-12-01","2017-03-15",1,"CP-160826",null,"HASON, Baruh","baruh.hason@motorolasolutions.com ","6/3/17: 0%->100","23.003; 23.335; 29.283",74,38,null,null,"2016-12-01","2017-03-06"]
[3724,730009,"   CT1 aspects of MCPTTProtoc1","MCPTTProtoc1",2,"Rel-14","C1","2016-09-16","2017-03-15",1,"CP-160581",null,"Ricky Kaura","ricky.kaura@samsung.com","6/3/17: 5%->100","24.229; 24.379; 24.380; 24.381; 24.382; 24.383; 24.384; 24.980",73,37,null,null,"2016-09-16","2017-03-06"]
[3726,730011,"   CT4 aspects of MCPTTProtoc1","MCPTTProtoc1",2,"Rel-14","C4","2016-09-16","2017-03-15",1,"CP-160581",null,"Ricky Kaura","ricky.kaura@samsung.com","6/3/17: 0%->100","23.003; 23.008; 29.283",73,37,null,null,"2016-09-16","2017-03-06"]
[3730,690035,"   Stage 1 for LTE support for V2X services","V2XLTE",2,"Rel-14","S1","2015-09-09","2016-03-17",1,"SP-150573",null,null,null,"7/12/15: 0%->5¦28/1/16: 22.185 added¦2/3/16: 5%->90¦9/6/16: 90%->100","22.278; 22.185",68,35,null,null,"2015-09-09","2016-06-09"]
[3733,720090,"   RAN aspects of LTE-based V2X Services","LTE_V2X",2,"Rel-14",null,"2016-06-15","2018-12-14",1,"RP-161298",null,"LG Electronics",null,"follow-up WI of REL-14 SI FS_LTE_V2X",null,72,37,null,null,"2016-07-08","2016-06-22"]
[3737,730026,"   CT aspects of V2X Services","V2X-CT",2,"Rel-14","ct","2016-09-16","2017-03-15",1,"CP-160584",null,"Taehun Kim","taehun78.kim@lge.com",null,null,73,37,null,null,"2016-09-16","2016-09-16"]
[3742,700019,"   Study on LTE support for V2X services","FS_V2XLTE",2,"Rel-14",null,"2015-02-09","2016-06-17",1,"SP-150051",null,"Ki-Dong Lee (LG electronics)","kidong.lee@lge.com","1/4/15:TR number added¦June2015: Compl:25%->50¦07/09/15: 50%->75","New 22.885",67,34,null,null,"2015-03-04","2015-09-07"]
[3745,760072,"      Study on Security of LTE support for V2X services","FS_V2XARC_S3",3,"Rel-14","S3","2015-09-07","2016-06-17",1,"SP-150852",null,null,null,"Introduced at 100% completion, as per SA3 report to SA#76",33.884999999999998,70,36,null,null,"2015-12-07","2016-09-19"]
[3746,680058,"      RAN1 Study on LTE-based V2X Services","FS_LTE_V2X",3,"Rel-14","R1","2015-06-15","2016-06-15",1,"RP-161263",null,"LG Electronics",null,"29/09/15: Compl:0%->5% 29/09/15: Stat Rep: -->RP-151311 ¦28/1/16: 33.885 added;22/3/16: Compl:35%->50%22/3/16: CD:Wed 15/06/16->Thu 15/09/1622/3/16: WID: RP-15¦",33.884999999999998,68,35,null,null,"2015-07-03","2016-07-01"]
[3751,0,"Release 14 on CIoT","-",1,"Rel-14",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3753,710024,"   Non-IP for Cellular IoT for EC-EGPRS ","NonIP_GPRS",2,"Rel-14","S2","2016-03-02","2016-06-15",1,"SP-160196",null,"Hans Ronneke, Ericsson","hans . Ronneke (a) ericsson . Com","9/6/16: 0%->50¦19/9/16: 50%->100","23.060; 23.682; 23.401?",71,36,null,null,"2016-03-02","2016-09-19"]
[3757,710027,"      CT4 aspects for Non-IP for Cellular Internet of Things for EC-EGPRS ","NonIP_GPRS-CT",3,"Rel-14","C4","2016-03-02","2016-09-15",1,"CP-160293",null,"Orange, Youssef CHADLI","youssef.chadli@orange.com","11/6/16: WID:CP-160161->CP-160293¦13/6/16: 0%->65¦2/12/16: 65%->100","29.060; 29.274; 29.002; 29.303; 23.008; 29.128; 29.272; 23.007",71,36,null,null,"2016-03-02","2016-12-02"]
[3760,720292,"   Perf. part: Further enhanced MTC for LTE","LTE_feMTC-Perf",2,"Rel-14","R4","2016-06-15","2017-12-15",1,"RP-170532",null,"Ericsson",null,"¦26/9/16: WID: RP-161321->RP-161464¦20/12/16: WID: RP-161464->RP-162520¦20/12/16: Stat Rep: ->RP-16252021/3/17: CD:Fri 15/09/17->Fri 15/12/1721/3/17 19/6/17: Compl:0%->35%19/9/17: Compl:35%->60%¦8/1/18: Compl:60%->100%",null,72,37,null,null,"2016-07-01","2018-01-08"]
[3765,770061,"   UE Conformance Test Aspects - Enhancements of NB-IoT","NB_IOTenh-UEConTest",2,"Rel-14","R5","2017-09-15","2018-12-14",1,"RP-171781",null,"Huawei",null,"¦8/1/18: Compl:0%->5%27/3/18: Compl:5%->30%¦27/6/18: C; 11/10/20: 60%->100",null,77,39,null,null,"2017-09-19","2020-10-11"]
[3769,730059,"   Stage 2 of Extended architecture support for Cellular Internet of Things","CIoT_Ext",2,"Rel-14","S2","2016-09-15","2016-12-16",1,"SP-160830",null,"Intel : Puneet Jain","puneet.jain@intel.com","1/12/16: 0%->100¦1/12/16: WID:SP-160732->SP-160830","23.401; 23.682; 23.060; 23.271",73,37,null,null,"2016-09-19","2016-12-01"]
[{"$f":"A3772+1","v":3772},740040,"      CT4 aspects of extended architecture enhancements for Cellular Internet of Things","CIoT_Ext-CT",3,"Rel-14","C4","2016-12-01","2017-03-14",1,"CP-160701",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","6/3/17: 0%->90¦5/6/17: 90%->100","23.008; 29.272; 29.002; 29.336; 29.128; 29.171; 29.172; 29.173",74,38,null,null,"2016-12-01","2017-06-05"]
[3773,730077,"Radio Interface Enhancements for Extended Coverage GSM for support of Cellular Internet of Things","CIoT_EC_GSM_radio_enh",1,"Rel-14","R6","2016-09-15","2018-06-15",1,"RP-161806",null,"Nokia",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[3778,730283,"   Perf. part: New band support for Rel-14 Narrowband Internet of Things (NB-IOT)","NB_IOT_R14_bands-Perf",2,"Rel-14","R4","2016-09-15","2017-06-15",1,"RP-170139",null,"Ericsson",null,"¦20/12/16: Compl:0%->99% 21/3/17: Compl:99%->70% 19/6/17: Compl:70%->100%",null,73,37,null,null,"2016-09-26","2017-06-19"]
[3780,720006,"Enhancements of Dedicated Core Networks selection mechanism","eDecor",1,"Rel-14",null,"2015-09-17","2017-12-15",1,"SP-160310","SP-170537","Roland Gustafsson","Roland.Gustafsson@ericsson.com","7/12/15: 0%->70¦7/3/16: 70%->80¦9/6/16: 80%->95",23.710999999999999,69,35,null,null,"2015-09-17","2016-06-09"]
[3783,730013,"   CT aspects of eDecor","eDecor-CT",2,"Rel-14","ct","2016-09-16","2016-12-15",1,"CP-160475",null,"Mikael Wass","Mikael.wass@ericsson.com",null,null,73,37,null,null,"2016-09-16","2016-09-16"]
[3788,740167,"      Core part: RAN aspects of eDECOR for UMTS and LTE","eDECOR-UTRA_LTE-Core",3,"Rel-14","R3","2016-12-15","2017-03-15",1,"RP-162543","RP-170547","Ericsson",null,"21/3/17: Compl:0%->100%21/3/17: Stat Rep: ->RP-170547",null,74,38,null,null,"2016-12-20","2017-03-21"]
[3792,740178,"   Core part: Addition of band 25 and 26 to LTE MTC cat.0","LC_MTC_LTE_cat0_B25_B26-Core",2,"Rel-14","R4","2016-12-15","2017-03-15",1,"RP-162572",null,"Sprint",null,"¦21/3/17: Compl:0%->100%",null,74,38,null,null,"2016-12-20","2017-03-21"]
[3796,700039,"   Stage 2 of EWE","EWE",2,"Rel-14","S2","2015-11-02","2016-06-17",1,"SP-150624",null,"Alcatel-Lucent, Nicolas Drevon","Nicolas.Drevon@alcatel-lucent.com","7/3/16: 45%->60¦9/6/16: 60%->100","23.002; 23.402",70,36,null,null,"2015-12-07","2016-06-09"]
[3799,720033,"      CT4 aspects of EWE","EWE-CT",3,"Rel-14","C4","2016-06-13","2016-09-15",1,"CP-160244",null,"Nokia, Bruno Landais","bruno.landais@nokia.com","2/12/16: 0%->100",29.273,72,37,null,null,"2016-06-13","2016-12-02"]
[3800,730048,"Support of EAP Re-authentication Protocol for WLAN Interworking","ERP",1,"Rel-14",null,"2016-09-16","2017-03-16",1,"SP-160568",null,"ORANGE, Todor Gamishev","Todor dot Gamishev at Orange dot com",null,null,73,37,null,null,"2016-09-16","2016-09-16"]
[3805,720019,"Phase 2 of the Support of Emergency services over WLAN","SEW2",1,"Rel-14",null,"2015-09-01","2017-03-15",1,"SP-160307",null,"Nicolas Drevon","nicolas.drevon@nokia.com",null,"new 23.771; 23.402; 23.167",72,37,null,null,"2015-04-01","2016-06-09"]
[3807,720018,"   Support of Emergency services over WLAN - phase 2","SEW2",2,"Rel-14","S2","2016-06-13","2016-09-15",1,"SP-160307",null,"Nicolas Drevon","nicolas.drevon@nokia.com","11/6/16: 0%->45¦19/9/16: 45%->100","23.402; 23.167",72,37,null,null,"2015-04-01","2016-09-19"]
[3810,730019,"      CT4 aspects of SEW2","SEW2-CT",3,"Rel-14","C4","2016-09-16","2017-03-15",1,"CP-160694",null,"Jennifer Liu","jennifer.liu@nokia.com","2/12/16: 0%->100","23.003; 29.272; 29.273; 29.274; 29.328",73,37,null,null,"2016-09-16","2016-12-02"]
[3815,0,"Release 14 on IMS","-",1,"Rel-14",null,"2016-06-09","2016-06-09",1,"-","-","-","-","-","-",null,null,null,null,"2014-08-29","2014-08-29"]
[3819,710020,"   CT aspects of evolution to and interworking with eCall in IMS","EIEI-CT",2,"Rel-14",null,"2016-03-02","2016-09-15",1,"CP-160053",null,"Lena Chaponniere","lguellec@qti.qualcomm.com",null,null,71,36,null,null,"2016-03-02","2016-03-02"]
[3823,760084,"   UE Conformance Test Aspects - Evolution to and Interworking with eCall in IMS (EIEI)","EIEI-UEConTest",2,"Rel-14","R5","2017-06-15","2018-03-15",1,"RP-171057",null,"Qualcomm",null,"¦19/9/17: Compl:0%->45%¦8/1/18: Compl:45%->80%¦27/3/18: Compl:80%->100%",null,76,39,null,null,"2017-06-16","2018-03-27"]
[3826,720034,"   CT aspects for PWDIMS","PWDIMS-CT",2,"Rel-14","ct","2016-06-13","2016-12-15",1,"CP-160295",null,"Axell, Jörgen",null,null,null,72,37,null,null,"2016-06-11","NA"]
[3828,720036,"      CT3 aspects for PWDIMS","PWDIMS-CT",3,"Rel-14","C3","2016-06-13","2016-12-15",1,"CP-160295",null,"Axell, Jörgen",null,"5/6/17: 0%->100",29.292000000000002,72,37,null,null,"2016-06-11","2017-06-05"]
[3831,651003,"   (IETF) IMS Signalling Activated Trace (draft-ietf-insipid-logme-marking) --> RFC 8497","ISAT",2,"Rel-14","C1-IETF","2014-09-12","2016-03-11",1,"CP-150091",null,"Vodafone","peter.dawes @vodafone.com","CP66: moved to Rel-13. Mar 15: WID: CP-140195->CP-150091. ES in CP-150637¦13/6/16: 25%->28; 26/6/19: 28%->100","draft-dawes-sipping-debug",65,33,null,null,"2014-09-02","2019-06-26"]
[3835,630307,"   CT4 part of IMS Signalling Activated Trace","ISAT",2,"Rel-14","C4","2014-03-05","2016-03-11",1,"CP-150091",null,"Vodafone","peter.dawes @vodafone.com","CP66: moved to Rel-13. Mar.15: 90%. ES in CP-150615. 7/3/16: Rel-13->Rel-14¦5/6/17: 90%->100","23.008; 29.228; 29.229; 29.328; 29.329",63,32,null,null,"2014-01-29","2017-06-05"]
[3837,740017,"User Controlled Spoofed Call Treatment","SPECTRE",1,"Rel-14",null,"2016-08-23","2018-06-15",1,"SP-160898",null,"Greg Schumacher, Sprint",null,"1/12/16: moved from Rel-15 to Rel-14¦1/12/16: WID:SP-160729->SP-160898",null,73,37,null,null,"2016-09-19","2016-12-01"]
[3842,700032,"Enhancement for TV service","EnTV",1,"Rel-14",null,"2015-04-14","2017-06-09",1,"SP-150756","SP-170532","Zhiming Li","Lizhiming@huawei.com","2/3/16: 0%->100",22.100999999999999,70,36,null,null,"2015-12-07","2016-03-02"]
[3846,730058,"      System Architecture Enhancements for TV service","AE_enTV",3,"Rel-14","S2","2016-08-25","2016-12-15",1,"SP-160730",null,"Miguel Griot, Qualcomm","mgriot@qti.qualcomm.com","19/9/16: 0%->85¦1/12/16: FCD:09/16->12/16¦1/12/16: 85%->100",23.245999999999999,73,37,null,null,"2016-09-19","2016-12-01"]
[3850,740050,"      CT1 aspects of system architecture enhancements for TV service ","AE_enTV-CT",3,"Rel-14","C1","2016-12-01","2017-03-14",1,"CP-160816",null,"Catovic, Amer","amerc@qti.qualcomm.com","2/12/16: 0%->40¦6/3/17: 40%->75¦5/6/17: 75%->100",24.007999999999999,74,38,null,null,"2016-12-01","2017-06-05"]
[3853,740053,"      CT6 aspects of system architecture enhancements for TV service ","AE_enTV-CT",3,"Rel-14","C6","2016-12-01","2017-03-14",1,"CP-160816",null,"Catovic, Amer","amerc@qti.qualcomm.com","7/3/17: 0%->100",31.102,74,38,null,null,"2016-12-01","2017-03-07"]
[3855,670003,"Multimedia Priority Service Modifications","MPS_Mods",1,"Rel-14","S1","2015-03-11","2016-06-15",1,"SP-150043",null,"Ray P. Singh (Applied Communications Science)","rsingh@appcomsci.com","1/4/15: rapporteur added, Impacted TS added. 6/15: 0->25%¦07/09/15: 25%->40¦7/12/15: 40%->70¦2/3/16: 70%->80¦9/6/16: 80%->100",22.152999999999999,67,34,null,null,"2015-03-04","2016-06-09"]
[3858,730032,"   CT1 aspects of SIP Reason header extension","REAS_EXT",2,"Rel-14","C1","2016-09-16","2017-03-15",1,"CP-160481",null,"Mohali, Marianne","marianne.mohali@orange.com","2/12/16: 0%->50¦6/3/17: 50%->85¦5/6/17: 85%->100",24.228999999999999,73,37,null,null,"2016-09-16","2017-06-05"]
[3862,730002,"Diameter Load Control Mechanism","DLoCMe",1,"Rel-14","ct","2014-12-03","2017-03-15",1,"CP-160645","CP-171049","Nokia, Ulrich Wiehe","ulrich.wiehe@nokia.com","5/12/16: WID:CP-160412->CP-160645",null,73,37,null,null,"2016-09-16","2016-12-05"]
[3864,730042,"   CT4 aspects of Diameter Load Control Mechanism","DLoCMe",2,"Rel-14","C4","2016-09-16","2016-12-15",1,"CP-160645",null,"Nokia, Ulrich Wiehe","ulrich.wiehe@nokia.com","2/12/16: 0%->100","29.153; 29.154; 29.212; 29.214; 29.215; 29.217; 29.219; 29.213",73,37,null,null,"2016-09-16","2016-12-02"]
[3869,740055,"      CT3 aspects of Diameter Base Protocol Specification Update","DBPU",3,"Rel-14","C3","2016-12-01","2017-03-14",1,"CP-160823",null,"Huawei, Peter Schmitt","Peter.Schmitt@huawei.com","6/3/17: 0%->100","29.061; 29.153; 29.154; 29.212; 29.214; 29.215; 29.217; 29.219; 29.368; 29.468; 29.213; 29.155; 29.201",74,38,null,null,"2016-12-01","2017-03-06"]
[3873,720029,"   Overall aspects of MMCMH_Enh","MMCMH_Enh",2,"Rel-14","S4","2016-06-13","2017-03-10",1,"SP-160596",null,"Nikolai Leung","nleung@qti.qualcomm.com","19/9/16: WID:SP-160272->SP-160785¦19/9/16: 0%->50¦1/12/16: 50%->80¦1/12/16: FCD:12/16->03/17¦6/3/17: 80%->100","26.114; 26.980",72,37,null,null,"2016-06-11","2017-03-06"]
[3877,720067,"      CT4 aspects of MMCMH_Enh","MMCMH_Enh-CT",3,"Rel-14","C4","2016-03-02","2017-03-15",1,"CP-160369",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","3/6/16: WID:CP-160117->CP-160250. FCD: 09/16->03/17¦13/6/16: WID:CP-160250->CP-160369¦2/12/16: 0%->35¦6/3/17: 35%->75¦5/6/17: 75%->100","23.333; 29.333; 23.334; 29.334; 29.238",72,37,null,null,"2016-03-02","2017-06-05"]
[3880,710002,"Stopped - CT aspects of (or \"Enhancements of\") MTSI Extension on Multi-stream","MMCMH-CT",1,"Rel-14","ct","2016-03-02","2016-09-15",1,"CP-160117",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","Deleted, \"replaced\" by MMCMH_Enh-CT",null,71,36,"CP-72",null,"2016-03-02","2016-06-13"]
[3882,710029,"   deleted -CT3 aspects of MTSI Extension on Multi-stream","MMCMH-CT",2,"Rel-14","C3","2016-03-02","2016-09-15",1,"CP-160117",null,"Ericsson, Nevenka Biondic","nevenka.biondic@ericsson.com","Deleted, \"replaced\" by MMCMH_Enh-CT","29.162; 29.213; 29.214; 29.165",71,36,"CP-72",null,"2016-03-02","2016-06-13"]
[3885,690052,"   Study on Control and User Plane Separation of EPC nodes","FS_CUPS",2,"Rel-14","S2","2015-09-17","2016-06-17",1,"SP-150519",null,"Huawei, Mirko Schramm","mirko.schramm@huawei.com","7/12/15: 0%->20¦7/3/16: 20%->40¦9/6/16: 40%->100",23.713999999999999,69,35,null,null,"2015-09-17","2016-06-09"]
[3889,730040,"      CT4 aspects for CUPS","CUPS-CT",3,"Rel-14","C4","2016-09-16","2017-03-15",1,"CP-160579",null,"Huawei, Peter Schmitt","peter.schmitt@huawei.com","2/12/16: 0%->40¦6/3/17: 40%->75¦5/6/17: 75%->100","23.007; 29.274; 29.281; 29.303; 23.008",73,37,null,null,"2016-09-16","2017-06-05"]
[3891,680035,"   Management of mobile networks that include virtualized network functions","OAM14-MAMO_VNF",2,"Rel-14","S5","2015-06-15","2017-12-12",1,"SP-150362",null,"Jinglei Liu, China Mobile","liujinglei@chinamobile.com","June2015: WID:SP-150308->SP-150362",null,68,35,null,null,"2015-06-15","2015-06-18"]
[3896,690042,"      Lifecycle management for mobile networks that include virtualized network functions","OAM14-MAMO_VNF-LCM",3,"Rel-14","S5","2015-09-16","2017-06-09",1,"SP-160427",null,"Anatoly Andrianov (anatoly.andrianov@nokia.com), Nokia Networks","anatoly.andrianov@nokia.com","5/10/15: 28.528¦28.527¦28.526¦28.525 added¦7/12/15: 0%->10¦7/3/16: 10%->15¦13/6/16: 15%->25¦13/6/16: WID:SP-150403->SP-160427¦19/9/16: 25%->40¦1/12/16: 40%->60¦1/12/16: FCD:12/16->03/17¦6/3/17: FCD:03/17->06/17¦6/3/17: 60%->80¦7/6/17: 80%-","28.525; 28.526; 28.527; 28.528; 28.704; 28.705; 28.706; 28.707; 28.708; 28.709",69,35,null,null,"2015-06-15","2017-06-07"]
[{"$f":"A3900+1","v":3900},680050,"Development of super-wideband and fullband P.835","DESUDAPS",1,"Rel-14","S4","2015-06-16","2017-06-15",1,"SP-150215","SP-170346","Scott Isabelle (Knowles, Inc.)","sisabelle@audience.com","06/15: FCD corrected to Dec.15¦Aug2015: 0%->5¦07/09/15: 5%->20, FCD: 12/15->06.16¦7/12/15: 20%->40, MOVED TO REL-14¦7/3/16: 40%->50. 15/4/16: 6/16->12/16¦11/6/16: 50%->60¦19/9/16: 60%->70, fcd: 12/16->06/17¦1/12/16: 70%->75¦6/3/17: 75%->80¦7/6","26.131; 26.132",68,35,null,null,"2015-06-18","2017-06-07"]
[3904,720080,"PS Data Off Services","PS_Data_Off",1,"Rel-14",null,"2015-11-09","2017-06-09",1,"SP-150823","SP-170708","Orange, Bruno Tossou","bruno.tossou@orange.com","2/3/16: 0%->100",22.03,70,36,null,null,"2015-12-07","2016-03-02"]
[3905,700033,"   PS Data Off Services","PS_Data_Off",2,"Rel-14","S1","2015-11-09","2016-03-15",1,"SP-150823",null,"Orange, Bruno Tossou","bruno.tossou@orange.com","2/3/16: 0%->100",22.03,70,36,null,null,"2015-12-07","2016-03-02"]
[3909,740042,"      CT1 aspects of PS Data Off","PS_DATA_OFF-CT",3,"Rel-14","C1","2016-12-01","2017-03-14",1,"CP-160702",null,"Herrero Veron, Christian (Huawei)","Christian.Herrero at huawei.com","6/3/17: 0%->95¦5/6/17: 95%->100","24.008; 24.301; 27.007; 24.229; 24.368; 24.167",74,38,null,null,"2016-12-01","2017-06-05"]
[3912,740014,"   Charging Aspect for 3GPP PS Data off Function ","PS_DATA_OFF-CH",2,"Rel-14","S5","2016-12-01","2017-06-09",1,"SP-160839",null,"Huawei， Chen, Shan","chenshan@huawei.com","6/3/17: 0%->70¦6/3/17: FCD:03/17->06/17¦7/6/17: 70%->100","32.251; 32.298; 32.299",74,38,null,null,"2016-12-01","2017-06-07"]
[3918,720078,"   Stage 2 of Enhancement to Flexible Mobile Service Steering ","eFMSS",2,"Rel-14","S2","2016-06-17","2016-09-15",1,"SP-160314",null,"ZTE, Tricci So",null,"19/9/16: 0%->100",23.202999999999999,72,37,null,null,"2016-03-01","2016-09-19"]
[3920,721005,"   S4 aspects of Media Handling Extensions of IMS-based Telepresence","IMS_TELEP_EXT",2,"Rel-14","S4","2016-03-01","2016-12-01",1,"SP-160081",null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","11/6/16: 0%->10¦19/9/16: 10%->60¦1/12/16: 60%->100",26.222999999999999,72,37,null,null,"2016-03-01","2016-12-01"]
[3923,800104,"      (IETF) Framework for Telepresence Multi-Streams (draft-ietf-clue-framework)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",1,null,null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8845 added;","RFC 8845",80,41,null,null,"2018-06-27","2021-04-09"]
[3927,800108,"      (IETF) Protocol for Controlling Multiple Streams for Telepresence (CLUE) (draft-ietf-clue-protocol)","IMS_TELEP_EXT",3,"Rel-14","S4-IETF","2016-03-01","2016-12-01",1,null,null,"Ozgur Oyman, Intel","ozgur.oyman@intel.com","23/4/20: 25%->90; 9/4/21: RFC 8847 added;","RFC 8847",80,41,null,null,"2018-06-27","2021-04-09"]
[3931,710011,"Improved Streaming QoE Reporting in 3GPP","IQoE",1,"Rel-14","S4","2016-03-01","2017-03-15",1,"SP-160082","SP-170521","Zhiming Li, Huawei","Lizhiming@huawei.com","11/6/16: 0%->10¦19/9/16: 10%->55. FDC: 12/16->03/17¦1/12/16: 55%->65¦6/3/17: 65%->100","New 26.909; 26.247; 26.346",71,36,null,null,"2016-03-01","2017-03-06"]
[3932,710085,"New GPRS algorithms for EASE","EASE_ALGOs_SA3",1,"Rel-14","S3","2016-03-15","2016-06-15",1,"SP-160203",null,"Tim Evans, Vodafone",null,"Discussion whether it should be Rel-13. To be concluded at SA#72.¦13/6/16: 0%->60¦1/12/16: 60%->70¦6/3/17: 70%->100","55.241; 55.242; 55.243; 55.251; 55.252; 55.253",71,36,null,null,"2016-03-22","2017-03-06"]
[3936,720017,"   S8 Home Routing Architecture for VoLTE","V8",2,"Rel-14","S2","2016-06-13","2016-12-15",1,"SP-160315",null,"Motohiro ABE","motohiro(dot)abe(dot)cu(at) nttdocomo (dot) com","11/6/16: 0%->60¦19/9/16: 60%->95¦1/12/16: FCD:09/16->12/16¦1/12/16: 95%->100","23.228; 23.167; 23.203",72,37,null,null,"2015-06-18","2016-12-01"]
[3939,730025,"      CT3 Aspects of V8","V8-CT",3,"Rel-14","C3","2016-09-16","2016-12-15",1,"CP-160479",null,"Tsuyoshi Takakura (NTT DOCOMO)","tsuyoshi.takakura.ey@s1.nttdocomo.com","2/12/16: 40%->100","29.212; 29.213; 29.214",73,37,null,null,"2016-09-16","2016-12-02"]
[3945,730035,"      CT3 Aspect of AULC","AULC-CT",3,"Rel-14","C3","2016-09-16","2016-12-15",1,"CP-160466",null,"Huawei, Wu Yizhuang","wuyizhuang@huawei.com","2/12/16: 0%->10¦6/3/17: 10%->100","29.212; 29.213",73,37,null,null,"2016-09-16","2017-03-06"]
[3947,730054,"   Charging Aspects of Improvements of AULC","AULC-CH",2,"Rel-14","S5","2016-09-19","2017-06-09",1,"SP-160609",null,"Huawei， Chen, Shan","chenshan@huawei.com","1/12/16: 0%->40¦6/3/17: 40%->80¦6/3/17: FCD:03/17->06/17¦7/6/17: 80%->100","TS32.251; TS32.298; TS32.299",73,37,null,null,"2016-09-19","2017-06-07"]
[3951,720014,"Sponsored data connectivity improvements","SDCI",1,"Rel-14",null,"2015-11-02","2016-12-15",1,"SP-160309","SP-170523","Yang Xu","xuyang49@chinaunicom.cn",null,null,72,37,null,null,"2015-12-07","2016-06-09"]
[3954,730037,"   CT Aspects of SDCI","SDCI-CT",2,"Rel-14","ct","2016-09-16","2016-12-15",1,"CP-160580",null,"China Unicom, Xu, Yang","xuyang49@chinaunicom.cn","6/10/16: 29.251 added;",29.251000000000001,73,37,null,null,"2016-09-16","2016-10-06"]
[3958,710019,"   SAES5 for support for non-3GPP accesses","SAES5-non3GPP",2,"Rel-14","C1","2016-03-02","2017-03-15",1,"CP-160052",null,"Interdigital, Aghili, Behrouz","Behrouz.aghili@interdigital.com","11/6/16: 0%->15¦16/9/16: 15%->20¦2/12/16: 20%->85¦6/3/17: 85%->100","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118",71,36,null,null,"2016-03-02","2017-03-06"]
[3959,720073,"   SAE Protocol Development (Stage 3) - Phase 5","SAES5",2,"Rel-14","C1","2016-03-02","2017-03-15",1,"CP-160052",null,null,null,"Added following CT1's chair e-mail 14/06/16¦16/9/16: 0%->20¦2/12/16: 20%->85¦6/3/17: 85%->100",null,72,37,null,null,"2015-03-24","2017-03-06"]
[3963,720084,"Robust Call Setup for VoLTE subscriber in LTE","RobVoLTE",1,"Rel-14",null,"2015-11-02","2018-09-14",1,"SP-160312",null,null,null,null,null,72,37,null,null,"2015-12-07","NA"]
[3966,730022,"   CT Aspects of RobVoLTE","RobVoLTE-CT",2,"Rel-14","C1","2016-09-16","2017-03-16",1,"CP-160478",null,"PATEL, Milan","Milan.Patel@huawei.com","2/12/16: 0%->80¦6/3/17: 80%->100","24.229; 24.292",73,37,null,null,"2016-09-16","2017-03-06"]
[3972,720037,"Improved operator control using new UE configuration parameters","IOC_UE_conf",1,"Rel-14",null,"2016-06-13","2017-03-15",1,"CP-160828","CP-171176","Sedlacek, Ivo","ivo.sedlacek@ericsson.com","11/6/16: 0%->10¦17/10/16: WID:CP-160296->CP-160374¦5/12/16: WID:CP-160374->CP-160828","24.167; 24.229; 24.301; 24.302; 24.312; 24.341; 24.368; 24.607; 24.623; 24.XXX; 24.YYY",72,37,null,null,"2016-06-11","2016-12-05"]
[3974,720039,"   CT6 aspects of IOC_UE_conf","IOC_UE_conf",2,"Rel-14","C6","2016-06-13","2017-03-15",1,"CP-160828",null,"Adrian Buckley","abuckley@blackberry.com","11/6/16: 0%->10¦14/12/16: 0%->15¦7/3/17: 15%->85¦5/6/17: 85%->100","31.102; 31.103",72,37,null,null,"2016-06-11","2017-06-05"]
[3978,740015,"   Charging for SMS via T4 ","CH14-SMST4",2,"Rel-14","S5","2016-12-01","2017-06-09",1,"SP-160840",null,"Nokia","Maryse <dot> Gardella <at> Nokia <dot> com","6/3/17: 0%->20¦6/3/17: FCD:03/17->06/17¦7/6/17: 20%->100","32.274; 32.250 ; 32.298; 32.299",74,38,null,null,"2016-12-01","2017-06-07"]
[3981,720045,"   Determination of Completeness of Charging Information in IMS","CH14-DCCII",2,"Rel-14","S5","2016-06-13","2017-06-09",1,"SP-160398","SP-170344","Jesske, Roland (Deutsche Telekom)",null,"19/9/16: 0%->10¦6/3/17: FCD:03/17->06/17¦7/6/17: 10%->100","32.240; 32.260; 32.298; 32.299",72,37,null,null,"2016-06-13","2017-06-07"]
[3985,700060,"Enhanced LAA for LTE","LTE_eLAA",1,"Rel-14",null,"2015-12-15","2018-09-14",1,"RP-152272",null,"Ericsson",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[3986,700160,"   Core part: Enhanced LAA for LTE","LTE_eLAA-Core",2,"Rel-14","R1","2015-12-15","2017-03-15",1,"RP-162235","RP-170269","Ericsson",null,"22/3/16: Compl:0%->20%22/3/16: WID: RP-152272->RP-1604071/7/16: Compl:20%->60%1/7/16: WID: RP-160407->RP-160881¦26/9/16: Compl:60%->92%¦26/9/16: CD:Thu 15/09/16->Thu 15/12/16¦26/9/16: WID: ¦20/12/16: Compl:92%->97%¦20/12/16:21/3/17: Compl:",null,70,36,null,null,"2016-01-01","2017-03-21"]
[3990,700162,"   Core part: RRC optimization for UMTS","UTRA_RRCopt-Core",2,"Rel-14","R2","2015-12-15","2016-09-15",1,"RP-160287","RP-172758","Ericsson",null,"22/3/16: Compl:0%->8%¦ 1/7/16: Compl:8%->70%26/9/16: Compl:70%->100%¦8/1/18: Stat Rep: ->RP-172758",null,70,36,null,null,"2016-01-01","2018-01-08"]
[3993,700077,"AWS-3/4 Band for LTE","LTE_AWS_3_4",1,"Rel-14",null,"2015-12-15","2016-12-15",1,"RP-151731",null,"Dish Network",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[3999,740073,"Addition of 1.4 and 3 MHz Channel Bandwidth to E-UTRA operating band 65 for CGC (Complementary Ground Component) operations in Region 1","LTE_1980_2170_REG1_addBWs",1,"Rel-14","R4","2016-12-15","2017-09-15",1,"RP-162515",null,"Hughes Network Systems",null,null,null,74,38,null,null,"2016-12-20","2016-12-20"]
[4001,760083,"   UE Conformance Test Aspects – Addition of 1.4 and 3 MHz Channel Bandwidth to E-UTRA operating band 65 for CGC (Complementary Ground Component) operations in Region 1","LTE_1980_2170_REG1_addBWs-UEConTest",2,"Rel-14","R5","2017-06-15","2017-09-15",1,"RP-170931",null,"Dish Network",null,"¦19/9/17: Compl:0%->100%",null,76,39,null,null,"2017-06-16","2017-09-19"]
[4004,700279,"   Perf. part: LTE 2.6 GHz FDD Supplemental DL band (2570-2620 MHz) and LTE Carrier Aggregation (2DL/1UL) with Band 3 for region 1","LTE_FDD_2600_CA_B3-Perf",2,"Rel-14","R4","2015-12-15","2016-06-15",1,"RP-161200",null,"Orange",null,"¦22/3/16: WID: RP-152253->RP-1603781/7/16: Compl:0%->100%1/7/16",null,70,36,null,null,"2016-01-01","2016-07-01"]
[4009,700081,"Performance enhancements for high speed scenario in LTE","LTE_high_speed",1,"Rel-14","R4","2015-12-15","2018-09-14",1,"RP-152263",null,"NTT DOCOMO",null,null,null,70,36,null,null,"2016-01-07","2015-12-22"]
[4012,750056,"   UE Conformance Test Aspects - Performance enhancements for high speed scenario in LTE","LTE_high_speed-UEConTest",2,"Rel-14","R5","2017-03-15","2018-09-14",1,"RP-170367",null,"CMCC",null,"tested: REL-14 LTE_high_speed-Core;¦19/6/17: Compl: 1 8/1/18:27/3/ ;; 11/10/20: 95%->100",null,75,38,null,null,"2017-03-21","2020-10-11"]
[4013,710072,"Further Indoor Positioning Enhancements for UTRA and LTE","UTRA_LTE_iPos_enh2",1,"Rel-14","R2","2016-03-15","2017-12-15",1,"RP-160538",null,"Huawei",null,"follow-up WI of REL-13 WI UTRA_LTE_iPos_enh",null,71,36,null,null,"2016-03-22","2016-03-22"]
[4017,710076,"Radiated performance requirements for the verification of multi-antenna reception of UEs in LTE","LTE_MIMO_OTA",1,"Rel-14","R4","2016-03-15","2018-03-15",1,"RP-160603",null,"Intel",null,"follow-up WI of REL-13 WI UTRA_LTE_MIMO_OTA-Core¦no Perf. part",null,71,36,null,null,"2016-03-22","2016-03-22"]
[4021,710177,"   Core part: Enhancements on Full-Dimension (FD) MIMO for LTE","LTE_eFDMIMO-Core",2,"Rel-14","R1","2016-03-15","2017-03-15",1,"RP-160623","RP-170173","Samsung",null,"¦1/7/16: Compl:0%->25%26/9/16: Compl:25%->40%¦20/12/16: Compl:40%->80%¦20/12/16: Stat Rep: -->¦21/3/17: Compl:80%->100%¦21/3/17: Stat Rep: ->RP-170173",null,71,36,null,null,"2016-03-22","2017-03-21"]
[4026,740265,"   Perf. Part: Further mobility enhancements in LTE","LTE_eMob-Perf",2,"Rel-14","R4","2016-12-15","2017-06-15",1,"RP-162503",null,"ZTE",null,null,null,74,38,null,null,"2017-06-19","NA"]
[{"$f":"A4028+1","v":4028},710179,"   Core part: Uplink Capacity Enhancements for LTE","LTE_UL_CAP_enh-Core",2,"Rel-14","R1","2016-03-15","2017-03-15",1,"RP-162488","RP-170115","Ericsson",null,"1/7/16: Compl:0%->25%26/9/16: Compl:25%->40%¦20/12/16: Compl:40%->85%¦20/12/16: WID: RP-160664->RP-162488¦20/12/16: Stat Rep: -->21/3/17: Compl:85%->100%21/3/17: Stat Rep: ->RP-170115",null,71,36,null,null,"2016-03-22","2017-03-21"]
[4031,710080,"L2 latency reduction techniques for LTE","LTE_LATRED_L2",1,"Rel-14","R2","2016-03-15","2018-03-15",1,"RP-160667",null,"Ericsson",null,"no Perf. part¦follow-up WI of SI FS_LTE_LATRED",null,71,36,null,null,"2016-03-22","2016-03-22"]
[4036,710281,"   Perf. part: eMBMS enhancements for LTE","MBMS_LTE_enh2-Perf",2,"Rel-14","R4","2016-03-15","2017-09-15",1,"RP-170199",null,"Ericsson",null,"¦1/7/16: CD:Wed 15/06/16->Fri 15/09/17¦1/7/16: WID: RP-160675->RP-161297¦20/12/16: WID: RP-161297->RP-162231¦20/12/16: Stat Rep: --> ¦21/3/17: WID: RP-162231->RP-17019919/6/17: Compl:0%->70%¦19/9/17: Compl:70%->100%",null,71,36,null,null,"2016-03-22","2017-09-19"]
[4039,710282,"   Perf. part: SRS (sounding reference signal) switching between LTE component carriers","LTE_SRS_switch-Perf",2,"Rel-14","R4","2016-03-15","2017-06-15",1,"RP-160935",null,"Huawei",null,"1/7/16: WID: RP-160676->RP-160935¦20/12/16: Stat Rep: --> 21/3/17: Compl:0%->25% 21/3/17: CD:Wed 15/03/17->Thu 15/06/17¦19/6/17: Compl:25%->100%",null,71,36,null,null,"2016-03-22","2017-06-19"]
[4040,750054,"   UE Conformance Test Aspects - SRS (sounding reference signal) switching between LTE component carriers","LTE_SRS_switch-UEConTest",2,"Rel-14","R5","2017-03-15","2018-06-15",1,"RP-180848",null,"Huawei",null,"tested: REL-14 LTE_SRS_switch-Core;¦19/6/17: Compl:0%->5%¦8/1/18: Compl:27/3/ ;",null,75,38,null,null,"2017-03-21","2018-06-27"]
[4044,720040,"IMS Stage-3 IETF Protocol Alignment","IMSProtoc8",1,"Rel-14","C1","2016-06-14","2017-03-15",1,"CP-160294",null,null,null,"11/6/16: 0%->15¦5/6/17: 67%->100",null,72,37,null,null,"2016-06-11","2017-06-05"]
[4049,720094,"Multi-Carrier Enhancements for UMTS","UTRA_MCe",1,"Rel-14","R2","2015-12-15","2016-12-15",1,"RP-161259",null,"Huawei, HiSilicon",null,"no Perf. part¦follow-up WI of REL-14 SI FS_UTRA_MCe",null,72,37,null,null,"2016-07-08","2016-06-22"]
[4052,720095,"Citizens Broadband Radio Service (CBRS) 3.5GHz band for LTE in the United States","LTE_TDD_3550_CBRS_US",1,"Rel-14","R4","2016-06-15","2017-06-15",1,"RP-161219",null,"Nokia",null,null,null,72,37,null,null,"2016-07-08","2016-06-22"]
[4055,740069,"   UE Conformance Test Aspects – Citizens Broadband Radio Service (CBRS) 3.5GHz Band for LTE in the United States (Band 48)","LTE_TDD_3550_CBRS_US-UEConTest",2,"Rel-14","R5","2016-12-15","2017-06-15",1,"RP-162254",null,"Nokia",null,"21/3/17: Compl:0%->60% ¦ 19/6/17: Compl:60%->100%",null,74,38,null,null,"2016-12-20","2017-06-19"]
[4058,720296,"   Perf. part: LTE Band 41 UE power class 2 operation","LTE_B41_UE_PC2-Perf",2,"Rel-14","R4","2016-06-15","2016-12-15",1,"RP-161221",null,"Sprint",null,"26/9/16: Compl:0%->80%¦20/12/16: Compl:80%->100%",null,72,37,null,null,"2016-07-01","2016-12-20"]
[4063,721103,"   Core part: Positioning Enhancements for GERAN","ePOS_GERAN-Core",2,"Rel-14","R6","2016-06-15","2017-06-15",1,"RP-171052","RP-170920","Ericsson",null,"26/9/16: Compl:0%->30%¦20/12/16: Compl:30%->50% 21/3/17: Compl:50%->80% ¦19/6/17: Compl:80%->100%;",null,72,37,null,null,"2016-07-01","2017-06-19"]
[4066,660037,"   Study on KQIs for Service Experience","FS_KQISE",2,"Rel-14","S5","2014-12-03","2016-03-11",1,"SP-150676",null,"Li, Hui (hui.li(at)huawei.com)","hui.li(at)huawei.com","Mar 15: 0->5%¦June2015: Compl:0%->40¦07/09/15: 40%->50¦14/09/15: WID:SP-140784->SP-150405¦7/12/15: 50%->75¦7/12/15: WID:SP-150405->SP-150676 ¦7/3/16: 75%->100. 22/3/16: FCD: 09/15->03/16. Rel-13->Rel-14","32.8xy",66,34,null,null,"2014-12-04","2016-03-22"]
[4067,730179,"   Core part:Quality of Experience (QoE) Measurement Collection for streaming services in UTRAN","UMTS_QMC_Streaming-Core",2,"Rel-14","R2","2016-09-15","2017-03-15",1,"RP-161917","RP-170259","China Unicom",null,"¦20/12/16: Compl:0%->60% ¦21/3/17: Compl:60%->100%",null,73,37,null,null,"2016-09-26","2017-03-21"]
[4071,730180,"   Core part: Flexible eNB-ID and Cell-ID in E-UTRAN","LTE_FNBID-Core",2,"Rel-14","R3","2016-09-15","2017-03-15",1,"RP-161896","RP-170478","China Telecom",null,"¦20/12/16: Compl:0%->80%21/3/17: Compl:80%->100%21/3/17: Stat Rep: ->RP-170478",null,73,37,null,null,"2016-09-26","2017-03-21"]
[4076,740171,"      Core part: Introduction of new band support for 4Rx antenna ports for LTE","LTE_4Rx_AP_DL_bands-Core",3,"Rel-14","R4","2016-12-15","2017-06-15",1,"RP-170307",null,"Huawei",null,"¦21/3/17: Compl:0%->80% ¦2119/6/17: Compl:80%->100%",null,74,38,null,null,"2016-12-20","2017-06-19"]
[4079,730185,"   Core part: Requirements for a new UE category with single receiver based on Category 1 for LTE","LTE_UE_cat_1RX-Core",2,"Rel-14","R4","2016-09-15","2017-06-15",1,"RP-171149","RP-171317","Qualcomm",null,"¦20/12/16: Compl:0%->70%¦20/12/16: CD:Thu 15/12/16->Wed 15/03/17 ¦21/3/17: Compl:70%->95% 21/3/17: CD:Wed 15/03/17->Thu 15/06/1 19/6/17: Compl:95%->100%;",null,73,37,null,null,"2016-09-26","2017-06-19"]
[4082,730086,"Enhanced LTE WLAN Radio Level Integration with IPsec Tunnel (eLWIP)","LTE_WLAN_eLWIP",1,"Rel-14","R3","2016-09-15","2017-03-15",1,"RP-161929",null,"Nokia",null,null,null,73,37,null,null,"2016-09-26","2016-09-26"]
[4085,710183,"   Core part: LTE Measurement Gap Enhancement","LTE_meas_gap_enh-Core",2,"Rel-14","R4","2016-03-15","2017-06-15",1,"RP-160912","RP-171330","Intel",null,"¦1/7/16: Compl:0%->10%¦1/7/16: CD:Thu 15/06/17->Wed 15/03/17¦1/7/16: WID: RP-160678->RP-160912¦26/9/16: Compl:10%->25%26/9/16: R¦20/12/16: Compl:25%->60% 21/3/17: Compl:60%->95% 19/6/17: Compl:95%->100%",null,71,36,null,null,"2016-03-22","2017-06-19"]
[4090,870066,"   (IETF) T.140 Real-time Text Conversation over WebRTC Data Channels (draft-ietf-mmusic-t140-usage-data-channel)","TEI14_IETF",2,"Rel-14","CT1-IETF","2020-02-06","2020-06-05",1,null,null,null,null,"9/4/21: RFC 8865 added;; 16/7/24: 100%->100","RFC 8865",78,40,null,null,"2017-12-18","2024-07-16"]
[4094,870068,"   (IETF) Negotiating Media Multiplexing Using the Session Description Protocol (SDP) (draft-ietf-mmusic-sdp-bundle-negotiation) ","TEI14_IETF",2,"Rel-14","C1-IETF","2020-03-23","2020-04-23",1,null,null,null,null,"9/4/21: RFC 8843 added;","RFC 8843",87,44,null,null,"2020-04-23","2021-04-09"]
[4095,870069,"   (IETF) Indicating Exclusive Support of RTP/RTCP Multiplexing using SDP (draft-ietf-mmusic-mux-exclusive) ","TEI14_IETF",2,"Rel-14","C1-IETF","2020-03-23","2020-04-23",1,null,null,null,null,"9/4/21: RFC 8858 added;","RFC 8858",87,44,null,null,"2020-04-23","2021-04-09"]
[4098,620162,"   STOPPED - TR on Pilot development of Security Assurance Specification for MME network product class","SCAS-SA3Pil_TR",2,"Rel-14","S3","2013-12-09","2014-12-12",1,"SP-130718","-","NTT DOCOMO","Alf Zugenmaier (alf.zugenmaier@hm.edu)","This TR collects input for the new TS 33.116. Dec.14: 55->70%. 3/3/15: 70->55%. 10/03/15: 55->75%¦June2015: Compl:75%->80¦7/12/15: STOPPED AT 80% (marked as 100% here since no more work expected)","New 33.806",62,32,80,null,"2013-11-22","2015-12-07"]
[4103,709998,"Rel-14 LTE Carrier Aggregation","LTE_CA_Rel14",1,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"-","-","-","-","Acronym changed from \"LTE_CA_Rel-13\" to \"LTE_CA_Rel13\"",null,58,30,null,null,"2012-12-14","2015-01-15"]
[4106,690286,"      Perf. part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 5, Band 12 and Band 12","LTE_CA_B4_B5_B12_B12-Perf",3,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151521","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","2016-01-01"]
[4109,690287,"      Perf. part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 12","LTE_CA_B4_B4_B12_B12-Perf",3,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151522","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","2016-01-01"]
[4112,690288,"      Perf. part: LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 12","LTE_CA_B2_B4_B12_B12-Perf",3,"Rel-14","R4","2015-09-15","2016-03-15",0.9,"RP-151523","-","US Cellular",null,null,null,"RP-69","PCG-35",null,null,"2015-09-29","2016-01-01"]
[4117,700070,"   LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/1UL","LTE_CA_R14_2DL1UL",2,"Rel-14","R4","2015-12-15","2017-06-15",0.8,"RP-152196",null,"Qualcomm",null,null,null,"RP-70","PCG-36",null,null,"2016-01-07","2015-12-22"]
[4121,700171,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/2UL","LTE_CA_R14_2DL2UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.9,"RP-170312",null,"Huawei",null,"28/1/16: 36.714-02-02 added;22/3/16: Compl:0%->20%22/3/16: WID: RP-152237->RP-160192¦1/7/16: Compl:20%->40%¦26/9/16: Compl:40%->60%¦20/12/16: C ¦21/3/17:","36.714-02-02","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[4122,700271,"      Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 2DL/2UL","LTE_CA_R14_2DL2UL-Perf",3,"Rel-14","R4","2015-12-15","2017-06-15",0.9,"RP-170312",null,"Huawei",null,"¦22/3/16: WID: RP-152237->RP-1601921/7/16: WID: RP-160192->RP-16094726/9/16: WID: RP-160947->RP-161676¦20/12/16: Compl:0%->80%¦21/3/17: Compl:80%->90",null,"RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[4125,700272,"      Perf. part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/3UL","LTE_CA_R14_3DL3UL-Perf",3,"Rel-14","R4","2015-12-15","2017-03-15",1,"RP-152241",null,"Nokia Networks",null,"¦1/7/16: Compl:0%->15%21/3/17: Compl:15%->100%",null,"RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[4130,700174,"      Core part: LTE Advanced inter-band Carrier Aggregation Rel-14 for 4DL/1UL","LTE_CA_R14_4DL1UL-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.95,"RP-170189",null,"Ericsson",null,"28/1/16: 36.714-04-01 added;22/3/16: Compl:0%->30%22/3/16: WID: RP-152249->RP-1606141/7/16: Compl:30%->38%¦26/9/16: Compl:38%->74%¦20/12/16: Compl:74%->9521/3/1","36.714-04-01","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[4133,700175,"      Core part: LTE Advanced intra-band Carrier Aggregation for xDL/yUL including contiguous and non-contiguous spectrum","LTE_CA_R14_intra-Core",3,"Rel-14","R4","2015-12-15","2017-06-15",0.82,"RP-170188",null,"Ericsson",null,"28/1/16: 36.714-00-00 added;22/3/16: Compl:0%->60%22/3/16: WID: RP-152250->RP-160613¦1/7/16: Compl:60%->50%¦1/7/16: WID: RP-160613¦26/9/16: Compl:50%->44%¦20/12/16:21/3/1","36.714-00-00","RP-70","PCG-36",null,null,"2016-01-01","2017-03-21"]
[4135,700076,"   LTE Advanced inter-band Carrier Aggregation Rel-14 for 3DL/1UL","LTE_CA_R14_3DL1UL",2,"Rel-14","R4","2015-12-15","2017-06-15",0.9,"RP-152278",null,"Huawei",null,null,null,"RP-70","PCG-36",null,null,"2016-01-07","2015-12-22"]
[4141,700058,"Study on Scenarios and Requirements for Next Generation Access Technologies","FS_NG_SReq",1,"Rel-14","RP","2015-12-15","2016-12-15",1,"RP-160811",null,"CMCC",null,"22/3/16: Compl:0%->80%1/7/16: WID: RP-152257->RP-160811. 18/9/16: FCD: Sept 16, 80->95%26/9/16: Compl:95%->100%¦14/12/16: FCD:09/16->12/16¦14/12/16: 100%->9820/12/16: Compl:98%->100%20/12/16: CD:Mon 12/12/16->Thu 15/12/1620/12/16: Release: Rel-15->Re","38.xxx",70,36,null,null,"2016-01-01","2016-12-20"]
[4144,620071,"Study on Multimedia Broadcast Supplement for Public Warning System","FS_MBSP",1,"Rel-14","S1","2013-12-11","2014-12-12",1,"SP-130599",null,"Qualcomm","Eddy Hall (edhall@qti.qualcomm.com)","SP#65 completion 09/14=>12/14. Moved to Rel-14. TR 22.815v100 for Information. Linked to Rel-9 Feature PWS. Dec.14:70->100%",22.815000000000001,62,32,null,null,"2013-11-26","2014-12-03"]
[4148,670011,"Study on Paging Policy Enhancements and Procedure Optimizations in LTE","FS_PPEPO_LTE",1,"Rel-14","S1","2015-04-14","2015-12-15",1,"SP-150053",null,"Zhuoyun Zhang (China Unicom)","zhangzy910@chinaunicom.cn","1/4/15:TR number added¦June2015: Compl:0%->40¦07/09/15: 40%->60¦7/12/15: 60%->100","New 22.838",67,34,null,null,"2015-03-04","2015-12-07"]
[4149,670041,"Study on Latency reduction techniques for LTE","FS_LTE_LATRED",1,"Rel-14","R2","2015-03-16","2016-06-15",1,"RP-150465",null,"Ericsson",null,"03/07/15: Compl:0%->10% 03/07/15: Stat Rep: -->RP-150780 03/07/15: Release: Rel-13->Rel-14 29/09/15: Compl:10%->25% 29/09/15: Stat Rep: RP-150780->RP-151286 22/3/16: Compl:50%->60%;",36.881,67,34,null,null,"2015-04-01","2016-07-01"]
[4152,720085,"Stopped - Study on SON for eCoMP for LTE","delFS_LTE_SON_eCOMP",1,"Rel-14","R3","2016-06-14","2016-06-16",1,"RP-161181",null,"Nokia",null,"26/9/16: Compl:0%->10%. 1/12/16: Deleted: 720085 was allocated twice: to FS_LTE_SON-ECOMP (now in 720063) and to ROBVOLTE (now in 720301)","23.228; 23.237",72,37,80,null,"2015-12-07","2016-09-26"]
[4157,710058,"Study on HSPA and LTE Joint Operation","FS_UTRA_LTE_JOP",1,"Rel-14","R3","2016-03-15","2016-12-15",1,"RP-160571",null,"China Unicom",null,"¦1/7/16: Compl:0%->30%¦26/9/16: Compl:30%->80%¦ 20/12/16: Compl:80%->100%¦","New 37.805",71,36,null,null,"2016-03-22","2016-12-20"]
[4160,710061,"Study on further enhancements to Coordinated Multi-Point (CoMP) Operation for LTE","FS_feCOMP_LTE",1,"Rel-14","R1","2016-03-15","2017-03-15",1,"RP-160954",null,"Intel",null,"¦1/7/16: Compl:0%->15%¦26/9/16: Compl:15%->30%¦20/12/16: Compl:30%->80%21/3/17: Compl:80%->100%",null,71,36,null,null,"2016-03-22","2017-03-21"]
[4162,660058,"Study on Interactivity Support for 3GPP-based Streaming and Download Services","FS_IS3",1,"Rel-14","S4","2014-12-12","2017-03-10",1,"SP-140742",null,"Lo, Charles, Qualcomm ","clo@qti.qualcomm.com","TR number added. Mar. 15: 0->5%¦June2015: Compl:5%->10¦Aug2015: 10%->15¦07/09/15: 15%->30, FCD: 12/15->03/16¦7/3/16: 30%->40. 15/4/16: moved from Rel-13. FCD: 11/3/16->23/9/16¦11/6/16: 40%->50¦19/9/16: 50%->70, FCD:09/16->12/16¦1/12/16: 70%->80;",26.952999999999999,66,34,null,null,"2014-12-12","2017-03-06"]
[4168,700022,"Study on Stage 1 for New Services and Markets Technology Enablers","FS_SMARTER",1,"Rel-14","S1","2015-02-02","2016-06-10",1,"SP-150142",null,"Adrian Neal (Vodafone)","adrian.neal@vodafone.com",null,"New 22.891",67,34,null,null,"2015-03-04","2015-09-07"]
[4171,700024,"   FS_SMARTER – Critical Communications","FS_SMARTER-CRIC",2,"Rel-14","S1","2015-11-02","2016-06-10",1,"SP-150818",null,"Kanerva, Mikko","mikko.kanerva@nokia.com","2/3/16: 15%->60¦9/6/16: 60%->95¦7/6/17: 95%->100","New 22.862",70,36,null,null,"2015-12-07","2017-06-07"]
[4175,710062,"Study on New Radio (NR) Access Technology","FS_NR_newRAT",1,"Rel-14","R1","2016-03-15","2017-03-15",1,"RP-170379",null,"NTT DOCOMO",null,"includes RAN TR 38.801¦1/7/16: Compl:0%->10%¦1/7/16: CD:Thu 15/06/17->Wed 15/03/17¦1/7/16: WID: RP-160671->RP-161214¦1/7/16: Release: Rel-15->Rel-14¦28/7/16: 38.802 added¦26/9/16: Compl:10%->20%¦26/9/16: WID: RP-161214->RP-161596. 2/12/16: Moved","38.801; 38.912; 38.802; 38.901; 38.805",71,36,null,null,"2016-03-22","2017-03-21"]
[4176,0,"--- RELEASE 13 ---","-",1,"Rel-13","SP,RP,CP,GP","2013-12-11","2014-11-25",1,"-","-",null,null,"-","-",null,null,null,null,"2013-03-04","2013-03-04"]
[4180,670032,"   Study on Security Enhancements for MCPTT","MCPTT",2,"Rel-13","S3","2015-03-13","2016-03-11",1,"SP-150356",null,"Peter Haigh (peter.haigh at cesg.gsi.gov.uk)","Peter Haigh (peter.haigh at cesg.gsi.gov.uk)","Mar 2015: WID: SP-140879->SP-150164. Name clarified.6/15: WID updated¦7/12/15: 0%->75¦10/12/15: FCD->March, ES in SP-150729¦7/3/16: 75%->80¦28/7/16: 33.280 added¦28/7/16: 39.880 added¦1/12/16: 80%->100","33.879; 33.280; 39.880",67,34,null,null,"2015-03-13","2016-12-01"]
[4184,660053,"   Security of MCPTT","MCPTT",2,"Rel-13","S3","2014-12-12","2016-03-11",1,"SP-150356",null,"Peter Haigh (peter.haigh at cesg.gsi.gov.uk)","Peter Haigh (peter.haigh at cesg.gsi.gov.uk)","Mar 2015: WID: SP-140879->SP-150164. Name clarified. FCD: 03/2016->12/2015¦June2015: Compl:5%->15, WID updated. 7/9/15: TS number added¦7/12/15: 15%->60. FCD -> 03/16, ES in SP-150729¦7/3/16: 60%->85¦1/12/16: 85%->98¦6/3/17: 98%->100",33.179000000000002,66,34,null,null,"2014-12-12","2017-03-06"]
[4187,690017,"      CT1 aspects for MCPTT protocol aspects","MCPTT-CT",3,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","7/12/15: WID:CP-150587->CP-150793¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817","24.379; 24.380 24.38; 24.382; 24.383; 24.384; 24.229",69,35,null,null,"2015-09-07","2016-12-05"]
[4189,690097,"         Call Control – Off Network","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->75¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 75%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817",24.379000000000001,69,35,null,null,"2015-09-29","2016-12-05"]
[4195,691003,"         Management Object","MCPTT-CT",4,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-160817",null,"Samsung, Ricky Kaura","ricky.kaura@samsung.com","Proposed by Atle after some talks with several interested parties¦7/12/15: 0%->10¦7/12/15: WID:CP-150587->CP-150863. FCD->03/16, ES in CP-150721¦7/3/16: 10%->100. Name changed from \"Configuration management\"¦7/3/16: WID:CP-150863->CP-160160¦5/12/1",24.382999999999999,69,35,null,null,"2015-09-29","2016-12-05"]
[4198,690018,"      CT4 aspects for MCPTT protocol aspects","MCPTT-CT",3,"Rel-13","C4","2015-09-07","2016-03-11",1,"CP-160817",null,"Alcatel-Lucent, Keith Drage","keith.drage@alcatel-lucent.com","7/12/15: WID:CP-150587->CP-150863. FCD -> 03/16, ES in CP-150864¦7/3/16: 0%->100¦7/3/16: WID:CP-150863->CP-160160¦5/12/16: WID:CP-160160->CP-160817","23.003; 23.008; 29.283",69,35,null,null,"2015-09-07","2016-12-05"]
[4202,690019,"   IMS Profile to support MCPTT","MCPTT-Prof",2,"Rel-13","C1","2015-09-14","2016-03-11",1,"CP-150794",null,"Huawei, PATEL Milan","Milan.Patel@huawei.com","12/15: TR # added¦7/12/15: 0%->60¦7/12/15: WID:CP-150500->CP-150794. FCD -> 03/16, ES in CP-150722¦7/3/16: 60%->100",24.98,69,35,null,null,"2015-09-09","2016-03-07"]
[4203,740070,"   UE Conformance Test Aspects - Support for Mission Critical Push To Talk over LTE (MCPTT)","MCPTT-ConTest",2,"Rel-13","R5","2016-12-15","2018-06-15",1,"RP-180132",null,"US Department of Commerce",null,"6/1/17: acronym changed from \"MCPTT-UEConTest\" ¦21/3/17: Compl:0%->5%¦21/3/17: 36.579-5 added;","36.579-5",74,38,null,null,"2016-12-20","2018-06-27"]
[4207,670024,"MBMS Extensions and Profiling","MEPRO",1,"Rel-13","S4","2015-03-05","2015-12-11",1,"SP-150439",null,"Imed Bouazizi, Samsung and Thorsten Lohmar, Ericsson","i.bouazizi@samsung.com, thorsten.lohmar@ericsson.com","1/4/15: TS number added¦14/09/15: WID:SP-150099->SP-150439","26.346; new 26.852",67,34,null,null,"2015-03-05","2015-09-14"]
[4211,680047,"   Stage 1 fo Isolated E-UTRAN Operation for Public Safety","IOPS",2,"Rel-13","S1","2014-03-07","2014-09-17",1,"SP-150463","S1-143304","General Dynamics","paul.piggin@gd-broadband.com","SP#65 completed. TS 22.346v100 for 1-step Approval. Triggered by Rel-13 TR 22.897 (FS_IOPS)¦14/09/15: WID:SP 150358->SP-150463","New 22.346",63,32,null,null,"2014-02-05","2015-09-14"]
[4214,700037,"   CT aspects for IOPS","IOPS-CT",2,"Rel-13","C6","2015-11-02","2016-03-11",1,"CP-150876",null,"Heiko Kruse, Morpho Cards GmbH","heiko.kruse@mrpho.com",null,null,70,36,null,null,"2015-12-07","2015-12-07"]
[4216,640042,"Service Requirements Maintenance for Group Communication System Enablers for LTE","SRM_GCSE_LTE",1,"Rel-13","S1","2014-06-18","2014-09-17",1,"SP-140228","S1-143307","Nokia Networks","Juergen.Merkel@nsn.com","SP#65 completed. Some Rel-12 service reqs have no Stage 2/3 implementation",22.468,64,33,null,null,"2014-05-27","2014-09-03"]
[4222,690024,"   CT3 Aspect of Flexible Mobile Service Steering","FMSS-CT",2,"Rel-13","C3","2015-09-09","2016-03-11",1,"CP-150799",null,"ZTE,Zhou Xiaoyun","zhou.xiaoyun@zte.com.cn","07/09/15: 0%->20¦14/09/15: WID:CP-150488->CP-150577¦7/12/15: 20%->90¦7/12/15: WID:CP-150577->CP-150799. FCD -> 03/16. ES in CP-150646¦7/3/16: 90%->100","29.abc; 29.212; 29.213",69,35,null,null,"2015-09-09","2016-03-07"]
[4225,660013,"   Stage 1 for Application specific Congestion control for Data Communication","ACDC-ST1",2,"Rel-13","S1","2014-06-18","2014-09-17",1,"SP-140234","S1-143305","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","Results from MCC Split of the SA1 feature into F+BB for stage 1",22.010999999999999,64,33,null,null,"2014-05-27","2014-08-29"]
[4227,660139,"      CT1 part of Stage 3 for Application specific Congestion control for Data Communication","ACDC-CT",3,"Rel-13","C1","2014-12-04","2015-12-16",1,"CP-150282",null,"Kim, Jaehyun, LGE","jaehyun7.kim@lge.com","Presented at CT#66¦June2015: Compl:0%->10. June 2015: FCD: June->Dec 2015, WID: CP-140999-> CP-150282¦07/09/15: 5%->70¦7/12/15: 70%->100","24.105; 24.301; 24.008; 27.007; 23.122",66,34,null,null,"2015-05-05","2015-12-07"]
[4230,670159,"      Core part: RAN aspects of Application specific Congestion control for Data Communication","ACDC-RAN-Core",3,"Rel-13","R2","2015-03-16","2015-12-15",1,"RP-150662","RP-151275","LG Electronics",null,"03/07/15: Compl:0%->25% 03/07/15: WID: RP-150512->RP-150662 03/07/15: Stat Rep: ->RP-150661 29/09/15: Compl:25%->70% 29/09/15: Stat Rep: RP-150661->RP-151275¦1/1/16: Compl:70%->100%",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4234,580058,"   Deleted - Stage 2 for User Plane Congestion management","UPCON-SA2Del",2,"Rel-13","S2","2012-12-19","2013-12-11",1,"SP-140631","-","NEC","andreas.maeder@neclab.eu","SP#62 stopped at 0% completion","TBD",58,30,"SP-62","PCG-32","2012-11-13","2014-09-16"]
[4238,650107,"         CT3 part of CT aspects of User Plane Congestion Management for BB1","UPCON-DOTCON-CT",4,"Rel-13","C3","2014-03-18","2015-03-13",1,"CP-150365","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","Dec.14: 0->60¦WID: CP-140734->CP-140929. Mar.15: 60->95%¦June2015: Compl:95%->100. WID: CP-140929-> CP-150365.","29.201; 29.212; 29.213; 29.214; 29.215; 29.219; New 29.217 (PCC over Np)",65,33,null,null,"2014-07-29","2015-06-15"]
[4241,630021,"   Deleted - BB3: Uplink traffic and attended/unattended traffic","UPCON-TRAFDEL",2,"Rel-13","S2","2014-03-07","2014-09-17",1,"SP-140631","-","Allot","Alla Goldner (agoldner@allot.com)","SP#65 updated WID SP-140153=>SP-140631 (BBII & BBIII stopped). IncludES in CP-150Uplink Congestion Management, Un/Attended UE Information","TBD",63,32,"SP-65","PCG-33","2014-03-04","2014-09-16"]
[4243,650128,"   TR on Media Handling Aspects of IMS-based Telepresence","IMS_TELEP_S4",2,"Rel-13","S4","2014-09-09","2015-09-16",1,"SP-140483","-","Intel","ozgur.oyman@intel.com","Dec.14: 0->10%. 8/4/15: 20%¦June2015: Compl:20%->30¦Aug2015: 30%->35¦07/09/15: 35%->60¦7/12/15: 60%->100","New 26.9xy",65,33,null,null,"2014-09-05","2015-12-07"]
[4249,600045,"RAN Sharing Enhancements","RSE",1,"Rel-13","S1,R3","2013-06-19","2015-12-15",1,"SP-130330","-","NEC","joerg.swetina@neclab.eu","Triggered by Rel-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE)","-",60,31,null,null,"2013-06-03","2013-11-26"]
[4252,650121,"      Core part: RAN aspects of RAN Sharing Enhancements for LTE","RSE-RAN_LTE-Core",3,"Rel-13","R3","2014-09-12","2015-12-15",1,"RP-151827","RP-151295","NEC","Siva.Vakeesar@emea.nec.com","¦CD:Mon 15/06/15->Tue 15/09/15¦Stat Rep: -->RP-141891 1st Apr 15: Compl:15%->20% 1st Apr 15: Stat Rep: RP-141891->RP-150289 03/07/15: Compl:20%->75% 03/07/15: Stat Rep: RP-150289->RP-150875 29/09/15: Compl:75%->80% 29/09/15: CD:Tue 15/09/15->Tue 15/1","36.300; 36.413; 36.423",65,33,null,null,"2014-06-16","2016-01-01"]
[4254,630114,"   Stage 1 for Enhancements to WEBRTC interoperability","eWebRTCi",2,"Rel-13","S1","2014-03-07","2014-09-17",1,"SP-140630","S1-143303","Alcatel-Lucent","betsy.covell@alcatel-lucent.com","SP#65 completed. Updated WID SP-140286=>SP-140630",22.228000000000002,63,32,null,null,"2014-02-05","2014-09-16"]
[4257,650122,"   TR on Security for Enhancements to WEBRTC interoperability","eWebRTCi",2,"Rel-13","S3","2014-09-17","2015-09-30",1,"SP-140630","-","Ericsson","vesa.lehtovirta@ericsson.com","SP#65 updated WID SP-14028=>SP-140630 (added SA3 part). Dec.14: 0->20%, TR number added. 3/3/15: 30%.¦June2015: Compl:30%->75¦11/12/15: 54%->100¦11/12/15: 100%->100","New 33.872 ",65,33,null,null,"2014-09-04","2015-12-11"]
[4261,690015,"      CT1 aspects 3 for Enhancements to WebRTC interoperability","eWebRTCi-CT",3,"Rel-13","C1","2015-09-07","2015-12-18",1,"CP-150767",null,"China Mobile, Song Yue","songyue@chinamobile.com","7/12/15: 0%->100¦7/12/15: WID:CP-150498->CP-150790->CP-150767","24.371; 24.229",69,35,null,null,"2015-09-07","2015-12-07"]
[4265,710040,"      (IETF) MSRP over Data Channels (draft-ietf-mmusic-msrp-usage-data-channel)","eWebRTCi-CT",3,"Rel-13","C1-IETF","2015-12-08","2016-03-11",1,null,null,"Ericsson","christer.holmberg@ericsson.com","7/3/16: Introduced by IETF updates","24.371; 24.229; 26.223",71,36,null,null,"2016-03-07","2016-03-07"]
[4268,870076,"       (IETF) Session Traversal Utilities for NAT (STUN) Extension for Third-Party Authorization (draft-ietf-tram-turn-third-party-authz) --> RFC 7635","eWebRTCi-CT",3,"Rel-13","S3-IETF","2015-12-08","2016-06-16",1,null,null,null,null,null,null,87,44,null,null,"2016-03-07","2020-04-23"]
[4270,630116,"   TR on Stage 2 for Improvements to CS/PS coordination in UTRAN/GERAN Shared Networks","CSPS_Coord-SA2TR",2,"Rel-13","S2","2014-03-07","2014-09-17",1,"SP-140168","-","Ericsson","roland.gustafsson@ericsson.com","SP#65 completed. TR 23.704v200 for Approval","New 23.704",63,32,null,null,"2014-02-05","2014-08-04"]
[4276,640141,"   TR on Stage 2 for Enhancements to Proximity-based Services - Extensions","eProSe-Ext-SA2TR",2,"Rel-13","S2","2014-06-18","2015-03-13",1,"SP-150028","-","Qualcomm","Haris Zisimopoulos (harisz@qti.qualcomm.com)","SP#65 updated WID SP-140385=>SP-140573 (added SA3 part). Acronym corrected: eProSe-Ex-SA2TRt->eProSe-Ext-SA2TR. Mar15: 60% Mar15: WID: SP-140573 ->SP-150028¦June2015: Compl:60%->90¦07/09/15: 90%->95¦07/09/15: 95%->100","New 23.713",64,33,null,null,"2014-06-17","2015-09-07"]
[4279,680007,"      CT1 aspects of enhancements to Proximity-based","eProSe-Ext-CT",3,"Rel-13","C1","2015-06-15","2016-03-11",1,"CP-150370",null,"Lena Chaponniere","lguellec@qti.qualcomm.com","07/09/15: 0%->40¦7/12/15: 40%->90. FCD -> 03/16, ES in CP-150724¦7/3/16: 90%->100",29.343,68,35,null,null,"2015-06-15","2016-03-07"]
[4281,680009,"      CT4 aspects of enhancements to Proximity-based","eProSe-Ext-CT",3,"Rel-13","C4","2015-06-15","2016-03-11",1,"CP-150370",null,"Lena Chaponniere","lguellec@qti.qualcomm.com","07/09/15: 0%->10¦7/12/15: 10%->80. FCD->03/16. ES in CP-150616¦7/3/16: 80%->100","31.102; 31.111",68,35,null,null,"2015-06-15","2016-03-07"]
[{"$f":"A4284+1","v":4284},729999,"   Note: Charging Aspects done in Rel-14 under CH14-Prose (UID 720049)","eProSe",2,"Rel-13","S5","2015-06-17","2015-06-17",1,null,null,null,null,null,null,72,37,null,null,"2016-06-13","2016-12-01"]
[4288,650003,"   CT aspects of voice over E-UTRAN Paging Policy Differentiation","voE_UTRAN_PPD-CT",2,"Rel-13","C4,C1,C3","2014-09-16","2014-12-09",1,"CP-140491","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","Stage 3","Stage 3",65,33,null,null,"2014-07-29","2014-07-29"]
[4292,640047,"IP Flow Mobility support for S2a and S2b Interfaces","NBIFOM",1,"Rel-13","S2","2014-06-18","2016-06-15",1,"SP-150250","-","Tricci So, ZTE","tso@zte.com.cn","06/15: WID: SP-140279->SP-150250","Stage 2",64,33,null,null,"2014-05-30","2015-06-18"]
[4297,680020,"      CT1 aspects of IP Flow Mobility support for S2a and S2b Interfaces ","NBIFOM-CT",3,"Rel-13","C1","2015-06-15","2016-03-11",1,"CP-150874",null,"Xingyue(Joy) Zhou, ZTECorporation. ES in 641","zhou.xingyue@zte.com.cn","07/09/15: 0%->25¦14/09/15: WID:CP-150285->CP-150497¦7/12/15: 25%->75¦7/12/15: WID:CP-150497->CP-150791->874. FCD -> 03/16. ES in CP-150725¦7/3/16: 75%->100","24.301; 24.302; 24.244; 24.008",68,35,null,null,"2015-06-15","2016-03-07"]
[4300,640053,"Double Resource Reuse for Multiple Media Sessions","DRuMS",1,"Rel-13","S2","2014-03-14","2015-03-13",1,"SP-140393","-","Ericsson","George.Foti@ericsson.com","-","Stage 2",64,33,null,null,"2014-05-30","2014-06-11"]
[4303,660047,"      CT1 aspects of Double Resource Reuse for Multiple Media Sessions","DRuMS-CT",3,"Rel-13","C1","2014-12-03","2015-03-13",1,"CP-140926",null,"Ericsson",null,"5/5/15: C3 corrected in C1¦June2015: Compl:65%->90¦07/09/15: 90%->100","24.229; 24.615; 24.610; 24.605",66,34,null,null,"2014-12-09","2015-09-07"]
[4306,640055,"STOPPED - Study on Lawful Interception Service Evolution","FS_LISE",1,"Rel-13","S3","2014-06-23","2015-12-09",1,"SP-140303","-","Alcatel-Lucent","terry.jacobson@alcatel-lucent.com","Linked to LI13 which defines existing LI service requirements in TS 33.106 as well as existing HI1, HI2 & HI3 reference points. 3/3/15: 0->5%¦7/12/15: 5%->10. Stoppped at 10% in March 2017.¦6/3/17: 10%->100",33.826000000000001,64,33,80,null,"2014-06-11","2017-03-06"]
[4308,680031,"   SA4 aspects of Video enhancements by Region-Of-Interest information signalling","ROI",2,"Rel-13","S4","2014-06-18","2015-09-16",1,"SP-140219","-","Intel","ozgur.oyman@intel.com","Created by MCC as the structure of the Feature get expanded to include CT aspects¦June2015: Compl:40%->90, FCD: 06/15->09/15¦Aug2015: Compl:90%->95",26.114000000000001,64,33,null,null,"2015-06-15","2015-08-12"]
[4311,680033,"      CT3 Aspects of Video Enhancements by Region-Of-Interest information signalling","ROI-CT",3,"Rel-13","C3","2015-06-15","2015-12-16",1,"CP-150425",null,"Vivek Gupta, Intel","vivek.g.gupta@intel.com","07/09/15: 100%->10¦14/09/15: WID:CP-150241->CP-150425¦7/12/15: 10%->100",29.161999999999999,68,35,null,null,"2015-06-15","2015-12-07"]
[4315,650226,"   Specification on TV video profile","TVProf-SA4",2,"Rel-13","S4","2014-09-09","2016-03-11",1,"SP-140481","-","Orange","gilles.teniou@orange.com","Dec.14: 0->5%¦June2015: Compl:15%->30¦Aug2015: 30%->45¦07/09/15: 45%->70¦7/12/15: 70%->85, FCD: 12/15->03/16. ES in SP-150650¦7/3/16: 85%->100","26.234; 26.244; 26.346; 26.247; New 26.xyz; ES in SP-150650",65,33,null,null,"2014-09-05","2016-03-07"]
[4319,670016,"   SA4 aspects of EVS in 3G Circuit-Switched networks","EVSoCS-S4",2,"Rel-13","S4","2014-09-09","2016-03-11",1,"SP-140485","-","Qualcomm","Imre Varga (ivarga@qti.qualcomm.com)","Created by MCC (duplicated from previously single-line Feature) due to the introduction of the CT BB. Mar. 15: 10%¦Aug2015: 10%->20¦07/09/15: 20%->40¦7/12/15: 40%->60, FCD:12/15->03/16. ES in SP-150655¦28/1/16: 26.454 added¦28/1/16: 26.453 added;","26.103; 28.062; New 26.454; New 26.453",65,33,null,null,"2014-09-05","2016-03-07"]
[4324,660073,"   Support of EVS over UTRAN CS","EVSoCS_UTRAN",2,"Rel-13","R2,R1,R3","2015-06-16","2015-12-15",1,"RP-142282",null,"Qualcomm","Qualcomm",null,null,66,34,null,null,"2015-01-12","2015-01-15"]
[4327,650032,"QoS End-to-end Multimedia Telephony Service for IMS (MTSI) extensions (Stage 3)","QOSE2EMTSI",1,"Rel-13","S4,C3,C1,C4","2013-03-06","2016-03-11",1,"SP-140601","-","Ericsson","tomas.frankkila@ericsson.com","SP#65 updated WID SP-130670=>SP-140601 (moved work from Rel-12 incl. new TR to Rel-13). Co-ordinate with SA2, CT1/3/4, IETF MMUSIC. Linked to SA4 Rel-7 Media handling and interaction in MTSI (MTSI-MHI) UID_7040","-",59,30,null,null,"2013-02-20","2014-09-20"]
[4330,660043,"   CT Aspects of QoS End-to-End MTSI Extensions","QOSE2EMTSI-CT",2,"Rel-13","C3,C1,C4","2014-11-05","2016-03-11",1,"CP-140925",null,"Ericsson",null,null,null,66,34,null,null,"2014-12-09","2014-12-09"]
[4333,660046,"      CT4 Aspects of QoS End-to-End MTSI Extensions","QOSE2EMTSI-CT",3,"Rel-13","C4","2014-11-05","2016-03-11",1,"CP-140925",null,"Ericsson",null,"FCD -> 03/16, ES in CP-150620¦7/3/16: 0%->100","23.333; 23.334; 29.238; 29.332; 29.333; 29.334",66,34,null,null,"2014-12-09","2016-03-07"]
[4335,710042,"   Codec aspects for MMCMH","MMCMH",2,"Rel-13","S4","2014-12-12","2015-12-17",1,"SP-150660",null,"Tomas Frankkila, Ericsson LM","tomas.frankkila@ericsson.com","Introduced by MCC to dissociate S4 from IeTF aspects","26.114; New 26.980",66,34,null,null,"2014-12-12","2015-12-10"]
[4338,660051,"Video Telephony Robustness Improvements Extensions","VTRI_EXT",1,"Rel-13","S4","2014-12-12","2015-09-11",1,"SP-140739",null,"Muhammed Coban, Qualcomm Incorporated","mcoban@qti.qualcomm.com","New TR added. 3/3/15: \"extensions\" added in the title. Mar. 15: 0->10%","26.922 (new); 26.114",66,34,null,null,"2014-12-12","2015-03-05"]
[4343,630010,"Rel-13 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM13",1,"Rel-13","S5","2012-06-20","2016-03-11",1,"SP-150305","-","-","-","OAM13 is an umbrella Feature for changes that are not part of any other dedicated feature/WI¦June2015: WID:-->SP-150305¦5/10/15: 28.683 added;",28.683,63,32,null,null,"2014-02-27","2015-10-05"]
[4346,560134,"      TR on Compliance of 3GPP SA5 specifications to the NGMN Top Operational Efficiency (OPE) Recommendations","OAM-NGMN_OPE",3,"Rel-13","S5","2012-06-20","2015-03-18",1,"SP-140538","-","Huawei","christian.toche@huawei.com","SP#65 updated WID SP-120349=>SP-140538. Completion 12/14=>03/15. Moved to Rel-13.. Dec.14: 72->78. Mar 15: 80%¦June2015: Compl:80%->85¦07/09/15: 85%->90¦7/12/15: 90%->100","New 32.838",56,29,null,null,"2012-05-14","2015-12-07"]
[4351,560236,"      WLAN measurements defined in IEEE and IETF WLAN performance measurements for use on Type-2 interface","WLAN-OAM-SA5ietf",3,"Rel-13","S5","2012-06-27","2015-06-17",1,"SP-140535","-","Intel","joey.chou@intel.com","SP#65 updated WID SP-130042=>SP-140535. Completion 09/14=>06/15. Moved to Rel-13. 22/01:Acronym modified¦June2015: Compl:5%->20¦07/09/15: 20%->60¦7/12/15: 60%->100","new 28.403",56,29,null,null,"2012-06-12","2015-12-07"]
[4354,641000,"Rel-13 Charging","CH13",1,"Rel-13","S5","2014-06-19","2015-12-16",1,"SP-150307","-","-","-","CH13 is an umbrella Feature for changes that are not part of any other dedicated feature/WI¦June2015: WID:-->SP-150307","-",64,33,null,null,"2014-06-06","2015-06-18"]
[4357,640259,"      Specification of Inter-PLMN PS domain online charging","iPLMN-PS-OCH",3,"Rel-13","S5","2014-06-23","2015-12-16",1,"SP-140324","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","07/09/15: 0%->80¦7/12/15: 80%->100","32.251; 32.299",64,33,null,null,"2014-06-06","2015-12-07"]
[4360,680037,"   Announcements for IMS Online Charging","ANIMO",2,"Rel-13","S5","2015-06-15","2015-12-14",1,"SP-150675",null,"Amdocs, Naceur <dot> Lagha <at> Amdocs <dot> com",null,"07/09/15: 0%->30¦7/12/15: 30%->100¦7/12/15: WID:SP-150307->SP-150675","32.260; 32.275; 32.299; 32.240; 32.281",68,35,null,null,"2015-06-14","2015-12-07"]
[4362,610005,"Support of Real-time Transport Protocol (RTP) / Real-time Transport Control Protocol (RTCP) multiplexing (signalling) in IMS","RTCP_MUX",1,"Rel-13","C4,C1,C3","2013-09-09","2015-12-11",1,"CP-130436","-","Alcatel-Lucent","Albrecht.Schwarz@alcatel-lucent.com","CP#65 moved to Rel-13. Stage 2/3","Stage 2/3",61,31,null,null,"2013-08-10","2014-09-03"]
[4365,610305,"   CT3 part of Support of RTP / RTCP multiplexing (signalling) in IMS","RTCP_MUX",2,"Rel-13","C3","2013-09-13","2015-12-11",1,"CP-130436","-","Alcatel-Lucent","Albrecht.Schwarz@alcatel-lucent.com","CP#65 moved to Rel-13. Completion 09/14=>12/15¦8/12/15: 0%->100","29.213; 29.214",61,31,null,null,"2013-08-10","2015-12-08"]
[4370,640119,"   Core part: Enhanced Signalling for Inter-eNB Coordinated Multi-Point (CoMP) for LTE","COMP_LTE_IeNB_sig-Core",2,"Rel-13","R3","2014-06-18","2015-09-15",1,"RP-141032","RP-151213","Samsung","sunghwan.won@samsung.com","CD:Thu 11/12/14->Mon 15/06/15¦Compl:0%->15%¦Stat Rep: -->RP-141805 1st Apr 15: Compl:15%->30% 1st Apr 15: Stat Rep: RP-141805->RP-150162 03/07/15: Compl:30%->90% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150162->RP-150846 29/09/1","36.300; 36.423",64,33,null,null,"2014-06-16","2015-09-29"]
[4373,640236,"   Perf. Part: 2GHz FDD LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands)","LTE_1980_2170_REG1-Perf",2,"Rel-13","R4","2014-06-18","2015-12-15",1,"RP-151732","RP-151299","DISH Network","johny.kim@dish.com, mariam.sorond@dish.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: RP-141627->RP-141795 1st Apr 15: WID: RP-141710->RP-150424 1st Apr 15: Stat Rep: RP-141795->RP-150106 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150106->RP-150705 29/09/15: Stat","36.101; 36.104; 36.133; 36.141; 36.307; 36.862",64,33,null,null,"2014-06-16","2016-01-01"]
[4378,660022,"   Stage 2 of Usage Monitoring Control PCC Extension","eUMONC-SA2",2,"Rel-13","S2","2014-12-03","2015-06-16",1,"SP-140709",null,"China Telecom, Jinyan Li","lijy@ctbri.com.cn","June2015: Compl:6%->100. Verbal indication from SA2 chair",23.202999999999999,66,34,null,null,"2014-12-03","2015-06-15"]
[4381,660014,"   CT1 aspects of Enhanced P-CSCF discovery using signalling for access to EPC via WLAN","ePCSCF_WLAN",2,"Rel-13","C1","2014-12-03","2015-03-13",1,"CP-140813",null,"Ericsson",null,". 12/12:0->100%. 5/5/15: acronym changed from ePCSCF_WLAN-CT1 to ePCSCF_WLAN","24.229; 24.302",66,34,null,null,"2014-12-04","2015-05-05"]
[4383,660028,"P-CSCF Restoration Enhancements with WLAN","PCSCF_RES_WLAN",1,"Rel-13","C4","2014-12-03","2015-12-14",1,"CP-150275",null,"Jean-Jacques Trottin, Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com ","WID added, acronym. June 2015: WID: CP-140995-> CP-150275",null,66,34,null,null,"2014-12-04","2014-12-09"]
[4386,680012,"Mobile Equipment Identity signalling over WLAN ","MEI_WLAN",1,"Rel-13","C4","2015-06-15","2015-09-17",1,"CP-150236",null,"Bruno Landais, Alcatel-Lucent","bruno.landais@alcatel-lucent.com",null,"24.244; 24.302; 29.273; 29.274; 29.275; 23.008",68,35,null,null,"2015-06-15","2015-06-15"]
[4389,680041,"Authentication Signalling Improvements for WLAN","ASI_WLAN",1,"Rel-13","C1","2015-06-15","2016-03-11",1,"CP-150330",null,"Youyang Yu","yuyouyang@huawei.com","07/09/15: 0%->40¦7/12/15: 40%->95. FCD -> 03/16, ES in CP-150727¦7/3/16: 95%->100","24.302; 24.244",68,35,null,null,"2015-06-15","2016-03-07"]
[4392,670038,"   CS Fallback in EPS - Phase 4","SAES4-CSFB",2,"Rel-13","C1","2014-12-03","2015-12-11",1,"CP-140814",null,"interdigital",null,"WP Structure created 24/03/15 to avoid confusion in Acronyms¦June2015: Compl:0%->30¦07/09/15: 30%->70¦7/12/15: 70%->100",null,66,34,null,null,"2015-03-24","2015-12-07"]
[4397,660021,"   CT3 aspects of Interworking solution for Called IN number and original called IN number ISUP parameters ","INNB_IW",2,"Rel-13","C3","2014-12-03","2015-03-13",1,"CP-140928",null,"Orange",null,"Mar.15: 80->90%. WID changed from INNB_IW-CT3¦June2015: Compl:0%->98¦07/09/15: 98%->99¦7/12/15: 99%->100",null,66,34,null,null,"2014-12-04","2015-12-07"]
[4400,660029,"   CT4 aspects of Warning Status Report in EPS","WSR_EPS",2,"Rel-13","C4","2014-12-03","2015-09-14",1,"CP-150792",null,"one2many",null,"2/4/15: acronym changed to WSR_EP. 5/5/15: acronym changed from \"WSR_EP\"¦7/12/15: 0%->100¦7/12/15: WID:CP-140998->CP-150792",null,66,34,null,null,"2014-12-04","2015-12-07"]
[4405,670097,"   CT3 aspects of IMS Stage-3 IETF Protocol Alignment","IMSProtoc7",2,"Rel-13","C3","2014-12-03","2015-12-11",1,"CP-140815",null,"Alcatel-Lucent","Keith Drage","2/4/15: added, following CT3 chair's info that the WID also has a CT3 part¦June2015: Compl:0%->20¦07/09/15: 20%->40¦7/12/15: 40%->100",null,67,34,null,null,"2015-04-02","2015-12-07"]
[4408,670001,"   CT4 Aspect of H.248 Aspects of WebRTC Data Channel on IMS Access Gateway","WebRTCH248DC",2,"Rel-13","C4","2015-03-04","2016-03-11",1,"CP-150185",null,"China Mobile, Xiaoning Du. ES in 639","duxiaoning@chinamobile.com","June2015: Compl:0%->10¦07/09/15: 10%->20¦7/12/15: 20%->90¦7/3/16: 90%->100",23.334,67,34,null,null,"2015-03-04","2016-03-07"]
[4410,670026,"Review of dedicated 3GPP UICC features","Red_UCe",1,"Rel-13","C6","2015-03-09","2015-12-11",1,"CP-150152",null,"Blackberry, Adrian Buckley","abuckley@blackberry.com","Results from the homonymous Study¦June2015: Compl:0%->60¦07/09/15: 60%->75¦7/3/16: 75%->100","31.102; 31.111; 31.121; 31.124",67,34,null,null,"2015-03-09","2016-03-07"]
[4413,680043,"   CT4 aspects of Controlling IMS Media Plane with SDP Capability","SDPCN_IMS",2,"Rel-13","C4","2015-06-15","2016-03-11",1,"CP-150238",null,"Weiwei(Tommy) Yang, Huawei. ES in 640","tommy@huawei.com","07/09/15: 0%->5¦7/12/15: 5%->70. FCD->03/16. ES in CP-150614¦7/3/16: 70%->100","23.334; 29.334; 29.238; 23.333; 29.333; 29.332; 29.232",68,35,null,null,"2015-06-15","2016-03-07"]
[4416,640051,"Enhanced CS Fallback (CSFB)","eCSFB",1,"Rel-13","S2,S3","2014-06-18","2015-03-13",1,"SP-140579","-","China Unicom","Yang Xu (xuyang49@chinaunicom.cn)","SP#65 updated ID SP-140285=>SP-140579 (added SA3 part). Linked to Rel-8 WIs Single Radio Voice Call Continuity for 3GPP (SAES-SRVCC) and CS Fallback in EPS (SAES-CSFB)","Stage 2",64,33,null,null,"2014-05-30","2014-12-12"]
[4419,650024,"   Deleted - Security for Enhanced CS Fallback (CSFB)","eCSFB",2,"Rel-13","S3","2014-09-18","2014-09-18",1,"SP-140579","-","China Unicom","Feng Gao (gaofeng149@chinaunicom.cn)","SP#65 updated ID SP-140285=>SP-140579¦14/09/15: 0%->100. SA#69: deleted, since SA2 has stopped the work.",null,65,33,"SP-69",null,"2014-09-15","2015-09-14"]
[4424,590130,"   Core part: Base Station (BS) RF requirements for Active Antenna System (AAS)","AAS_BS_LTE_UTRA-Core",2,"Rel-13","R4","2013-03-04","2016-03-15",1,"RP-160188","RP-151241","Huawei","ronnie.zhang@huawei.com","¦CD:Thu 11/12/14->Tue 15/12/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141249->RP-141908¦Release: Rel-12->Rel-13 03/07/15: Stat Rep: RP-141908->RP-150687 29/09/15: Compl:75%->80% 29/09/15: Stat Rep: RP-150687->RP-151241¦","New 37.142 (AAS BS Tx & Rx); New 37.842; 37.114; 37.145-1; 37.145-2",59,30,null,null,"2013-02-26","2016-03-22"]
[4428,660274,"   Perf. part: Enhanced LTE Device to Device Proximity Services","LTE_eD2D_Prox-Perf",2,"Rel-13","R4","2014-12-15","2016-09-15",1,"RP-150441","RP-151337","Qualcomm","Qualcomm","1st Apr 15: WID: RP-142311->RP-150441 1st Apr 15: Stat Rep: ->RP-150095 03/07/15: Stat Rep: RP-150095->RP-150795 29/09/15: Stat Rep: RP-150795->RP-151337¦1/1/16: CD¦22/3/16: Compl:0%->10%;26/9/16: Compl:85%->100%",null,66,34,null,null,"2015-01-12","2016-09-26"]
[4432,660177,"   Core part: UE core requirements for uplink 64 QAM","LTE_UL64QAM-Core",2,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-150691","RP-151244","Huawei","Huawei","1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150232 03/07/15: Compl:10%->90% 03/07/15: WID: RP-142222->RP-150691 03/07/15: Stat Rep: RP-150232->RP-150688 29/09/15: Compl:90%->100% 29/09/15: Stat Rep: RP-150688->RP-151244",null,66,34,null,null,"2015-01-12","2015-09-29"]
[4435,660278,"   Perf. part: Performance requirements of MMSE-IRC receiver for LTE BS","LTE_MMSE_IRC_BS-Perf",2,"Rel-13","R4","2014-12-15","2016-06-15",1,"RP-150206","RP-151215","China Telecom","China Telecom","1st Apr 15: Compl:0%->10% 1st Apr 15: WID: RP-142223->RP-150206 1st Apr 15: Stat Rep: ->RP-150204 03/07/15: Compl:10%->35% 03/07/15: Stat Rep: RP-150204->RP-150630 29/09/15: Compl:35%->50% 29/09/15: Stat Rep: RP-150630->RP-151215¦",null,66,34,null,null,"2015-01-12","2016-07-01"]
[4437,660279,"   Perf. part: CRS Interference Mitigation for LTE Homogenous Deployments","LTE_CRSIM-Perf",2,"Rel-13","R4","2014-12-15","2016-03-15",1,"RP-142263","RP-151171","Ericsson","Ericsson","1st Apr 15: Compl:0%->10% 1st Apr 15: CD:Mon 15/06/15->Tue 15/03/16 1st Apr 15: Stat Rep: ->RP-150061 03/07/15: Compl:10%->20% 03/07/15: Stat Rep: RP-150061->RP-150584 29/09/15: Compl:20%->30% 29/09/15: Stat Rep: RP-150584->RP-151171 ",null,66,34,null,null,"2015-01-12","2016-03-22"]
[4440,670255,"   Perf. part: Dual Connectivity enhancements for LTE","LTE_dualC_enh-Perf",2,"Rel-13","R4","2015-03-16","2016-06-15",1,"RP-151739","RP-151330","NTT DOCOMO",null,"03/07/15: Stat Rep: ->RP-150744 29/09/15: Stat Rep: RP-150744->RP-151330 ¦1/1/16: WID: RP-150490->RP-15173922/3/16: Compl:0%->50%;",null,67,34,null,null,"2015-04-01","2016-07-01"]
[4443,670256,"   Perf. part: Multicarrier Load Distribution of UEs in LTE","LTE_MC_load-Perf",2,"Rel-13","R4","2015-03-16","2016-09-15",1,"RP-161699","RP-151190","ZTE",null,"03/07/15: WID: RP-150491->RP-150611 03/07/15: Stat Rep: ->RP-150610 29/09/15: WID: RP-150611->RP-151206 29/09/15: Stat Rep: RP-150610->RP-1511901/1/16:22/3/16: Compl:70%->75%¦26/9/16: Compl:90%->100%¦26/9/16: WID: RP-152181",null,67,34,null,null,"2015-04-01","2016-09-26"]
[4446,670258,"   Perf. part: LTE-WLAN Radio Level Integration and Interworking Enhancement","LTE_WLAN_radio-Perf",2,"Rel-13","R4","2015-03-16","2016-03-15",1,"RP-160521","RP-151563","Intel",null,"03/07/15: WID: RP-150510->RP-151114 03/07/15: Stat Rep: ->RP-151081 29/09/15: Stat Rep: RP-151081->RP-1515631/1/16: Compl:0%->10% ¦22/3/16: Compl:10%->100%¦",null,67,34,null,null,"2015-04-01","2016-03-22"]
[4451,670161,"   Core part: LTE DL 4 Rx antenna ports","LTE_4Rx_AP_DL-Core",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150427","RP-151265","Ericsson",null,"03/07/15: Compl:0%->25% 03/07/15: Stat Rep: ->RP-150803 29/09/15: Compl:25%->50% 29/09/15: Stat Rep: RP-150803->RP-151265¦1/1/16: Compl:50%->100%",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4455,670162,"   Core part: AWS-Extension Band for LTE","LTE_AWS_EXT-Core",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150800","RP-151343","Ericsson",null,"03/07/15: Compl:0%->20% 03/07/15: WID: RP-150428->RP-150800 03/07/15: Stat Rep: ->RP-150796 29/09/15: Compl:20%->50% 29/09/15: Stat Rep: RP-150796->RP-151343 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4459,670163,"   Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7","LTE_CA_B5_B7_BWset-Core",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150602","RP-150536","Nokia Networks",null,"03/07/15: Compl:0%->100% 03/07/15: WID: RP-150171->RP-150602 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4462,670164,"   Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5","LTE_CA_B3_B5_BWset-Core",2,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150425","RP-150536","Samsung",null,"03/07/15: Compl:0%->100% 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4464,670054,"Multiflow Enhancements for UTRA","HSDPA_MFTX_enh",1,"Rel-13","R2","2015-03-16","2015-09-15",1,"RP-150288",null,"Nokia","alexander.sayenko@nokia.com",null,null,67,34,null,null,"2015-05-05","2015-05-05"]
[4467,680045,"   CT1 aspects of Message interworking during PS to CS SRVCC ","mSRVCC",2,"Rel-13","C1","2015-06-15","2015-09-16",1,"CP-150401",null,"Ivo Sedlacek, Ericsson","ivo.sedlacek@ericsson.com","07/09/15: 0%->25¦7/12/15: 25%->100","24.237; 24.292",68,35,null,null,"2015-06-15","2015-12-07"]
[4473,690025,"      CT3 aspects of Support of Emergency services over WLAN – phase 1","SEW1-CT",3,"Rel-13","C3","2015-09-07","2015-12-11",1,"CP-150571",null,"Alcatel-Lucent, Jennifer Liu (CT1)","jennifer.liu@alcatel-lucent.com","7/12/15: 0%->100","29.212; 29.214",69,35,null,null,"2015-09-07","2015-12-07"]
[4475,690036,"      CT6 aspects of Support of Emergency services over WLAN – phase 1","SEW1-CT",3,"Rel-13","C6","2015-09-07","2015-12-11",1,"CP-150571",null,"Alcatel-Lucent, Jennifer Liu (CT1)","jennifer.liu@alcatel-lucent.com","7/3/16: 0%->100",31.102,69,35,null,null,"2015-09-07","2016-03-07"]
[4478,690046,"   MBMS Enhancements","MBMS_enh_St2",2,"Rel-13","S2","2015-08-10","2015-09-16",1,"SP-150520",null,"Nokia Networks, Curt Wong",null,"SA#69: no normative work, moved as Study only. 14/10/15: corrected: was mentioned as FS_","23.246; 23.468",69,35,null,null,"2015-09-16","2015-10-14"]
[4482,660011,"   Deleted (not approved) - MBMS Enhancements - Stage 2","MBMS_enh_TS",2,"Rel-13","S2","2015-03-13","2015-03-13",1,"SP-140883",null,"Rainer Liebhart",null,"Commented during RAN#67 that it should have never beeen here. 07/09/15: \"undeleted\", acronym changed from \"MBMS_enh-del\" to \"MBMS_enh_TS\". 14/10/15: SP-140883 was never approved so this line should have never appeared in the WP.","23.246; 23.468",66,34,"SP-69",null,"2014-12-03","2015-09-16"]
[4486,700008,"Diameter Message Priority","DiaPri",1,"Rel-13","C4","2015-11-02","2016-06-16",1,"CP-150613",null,"Alcatel-Lucent, Jean-Jacques Trottin","jean-jacques.trottin@alcatel-lucent.com",null,null,70,36,null,null,"2015-12-07","NA"]
[4489,710044,"   (IETF) Diameter Routing Message Priority (draft-ietf-dime-drmp)","DiaPri",2,"Rel-13","C4-IETF","2015-12-08","2016-06-16",1,null,null,"Alcatel-Lucent, Jean-Jacques Trottin","jean-jacques.trottin@alcatel-lucent.com","02/2016: publication requested¦2/12/16: 85%->100; 9/4/21: RFC 7944 added; 7/3/16:introducedbyIETFinputs","29.227; 29.272; 29.273; 29.229; RFC 7944",71,36,null,null,"2016-03-07","2021-04-09"]
[4491,680159,"   Core part: Downlink TPC Enhancements for UMTS","UTRA_EDL_TPC-Core",2,"Rel-13","R1,R2,R3","2015-10-15","2015-12-15",1,"RP-151880","RP-151564","Huawei",null,"follow-up WI of REL-13 SI FS_UTRA_EDL¦TPC = Transmit Power Control 29/09/15: Compl:0%->35% 29/09/15: Stat Rep: -->RP-1515641/1/16: Compl:35%->100%1/1/16: WID: ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4494,680160,"   Core part: Licensed-Assisted Access using LTE","LTE_LAA-Core",2,"Rel-13","R1","2015-06-15","2015-12-15",1,"RP-151045","RP-151390","Ericsson",null,"follow-up WI of REL-13 SI FS_LTE_LAA 29/09/15: Compl:0%->25% 29/09/15: Stat Rep: -->RP-1513901/1/16: Compl:25%->100%",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4500,770062,"   UE Conformance Test Aspects - Elevation Beamforming/Full-Dimension MIMO for LTE","LTE_EBF_FDMIMO-UEConTest",2,"Rel-13","R5","2017-09-15","2018-12-14",1,"RP-172651",null,"Ericsson",null,"¦8/1/18: Compl:0%->5%¦27/3/18: Compl:5%->10%¦27/6/18: CD:Fri 15/06/18-; 26/3/20: 10%->100",null,77,39,null,null,"2017-09-19","2020-03-26"]
[4502,680162,"   Core part: L2/L3 Downlink enhancements for UMTS","UTRA_EDL_L23-Core",2,"Rel-13","R2","2015-06-15","2015-12-15",1,"RP-152184","RP-151238","Huawei",null,"no Perf. part¦follow-up of Rel-13 SI FS_UTRA_EDL 29/09/15: Compl:0%->35% 29/09/15: WID: RP-151043->RP-151249 29/09/15: Stat Rep: -->RP-1512381/1/16: Compl:35%->100% ¦",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4505,680264,"   Perf. part: Support of single-cell point-to-multipoint transmission in LTE","LTE_SC_PTM-Perf",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151110","RP-151237","Huawei",null,"follow-up WI of REL-13 SI FS_LTE_SC_PTM 29/09/15: Stat Rep: -->RP-1512371/1/16: Compl:0%->100% ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4509,680067,"RAN sharing enhancements for UMTS","RSE_UTRA_GUSH",1,"Rel-13","R3","2015-06-15","2015-12-15",1,"RP-151086","-","Huawei",null,"no Perf. part¦follow-up WI for Rel-13 SI FS_RSE_UTRA_GUSH¦note: GUSH was a REL-13 SA1 WI¦there is an ongoing REL-13 WI for LTE: RSE-RAN_LTE;",null,68,35,null,null,"2015-08-12","2015-07-03"]
[4513,750051,"   UE Conformance Test Aspects - Interference Mitigation for Downlink Control Channels of LTE","LTE_IM_DLCCH-UEConTest",2,"Rel-13","R5","2017-03-15","2018-09-14",1,"RP-180176",null,"Intel",null,"tested: REL-13 LTE_IM_DLCCH-Perf (note: WI had no Core part);19/6/171 8/1/18: C 27/3/18 ;¦26/3/19: 84%->100",null,75,38,null,null,"2017-03-21","2019-03-26"]
[4514,690062,"Network-Assisted Interference Cancellation and Suppression for UMTS","UTRA_NAICS",1,"Rel-13","R1","2015-09-15","2015-12-15",1,"RP-151577","-","Huawei",null,"no Perf. part¦follow-up WI REL-13 RAN1 SI FS_UTRA_NAICS",null,69,35,null,null,"2015-09-29","NA"]
[4518,690065,"Further Enhancements of Minimization of Drive Tests for E-UTRAN","LTE_eMDT2",1,"Rel-13","R2","2015-03-16","2017-03-15",1,"RP-151611","-","CMCC",null,"no Perf. part¦follow-up WI of REL-13 SI FS_LTE_eMDT2",null,69,35,null,null,"2015-09-29","NA"]
[4521,721000,"   UE Conformance Test Aspects – Further Enhancements of Minimization of Drive Tests for E-UTRAN","LTE_eMDT2-UEConTest",2,"Rel-13","R5","2016-06-15","2017-03-15",1,"RP-161071",null,"Intel",null,"tested REL-13 WI: LTE_eMDT2-Core26/9/16: Com;21/3/17: Compl:5%->100%",null,72,37,null,null,"2016-07-01","2017-03-21"]
[4527,700011,"   CT aspects of Indoor Positionning","UTRA_LTE_iPos_enh-CT",2,"Rel-13","C4","2015-10-12","2015-12-07",1,"CP-150612",null,"Ericsson, Jesús de Gregorio","jesus.de.gregorio@ericsson.com",null,"29.171; 29.172; 29.230; 29.002",70,36,null,null,"2015-12-07","NA"]
[4529,720099,"   UE Conformance Test Aspects – Indoor Positioning Enhancement Support for LTE and UMTS","UTRA_LTE_iPos_enh-UEConTest",2,"Rel-13","R5","2016-06-15","2017-03-15",1,"RP-170233",null,"NextNav",null,"tested REL-13 WI: UTRA_LTE_iPos_enh-Core¦26/9/1¦20/12/16:21/3/17: Compl:",null,72,37,null,null,"2016-07-01","2017-03-21"]
[4532,700256,"   Perf. Part: Power saving enhancements for UMTS","UTRA_SDATA_POWSAV-Perf",2,"Rel-13","R4","2015-12-15","2016-03-15",1,"RP-151998",null,"Ericsson",null,"¦22/3/16: Compl:0%->100%",null,70,36,null,null,"2016-01-01","2016-03-22"]
[4536,680075,"European 700 Supplemental Downlink band (738-758 MHz) in E-UTRA and LTE Carrier Aggregation (2DL/1UL) with Band 20","LTE_CA_700EU_B20",1,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150861","-","TeliaSonera",null,"introduction of new DL only band and 2DL/1UL CA with it",null,68,35,null,null,"2015-07-03","2015-07-03"]
[{"$f":"A4540+1","v":4540},620063,"Service Requirements Maintenance for Machine-Type Communications (MTC)","SRMMTC",1,"Rel-13","S1","2015-09-15","2016-06-10",1,"SP-130600","-","KPN","toon.norp@tno.nl","SP#65 completed. Linked to Rel-13 SEES, Rel-12 Support for Interworking with M2M Service Enablement (MTCe-SIMSE), Service Requirement Maintenance (MTCe-SRM). Decide which MTC reqs with no Stage 2 should be removed/maintained in Rel-13.",22.367999999999999,62,32,null,null,"2013-11-26","2014-09-03"]
[4541,700012,"Cellular (Narrowband) Internet of Things","CIoT",1,"Rel-13",null,"2015-09-15","2017-12-15",1,null,null,null,null,null,null,70,36,null,null,"2015-12-07","NA"]
[4545,700014,"      CT1 aspects of CIoT","CIoT-CT",3,"Rel-13","C1","2015-12-07","2016-03-11",1,"CP-160292",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","7/3/16: 0%->35¦11/6/16: 35%->100¦11/6/16: WID:CP-150795->CP-160292","24.301; 24.008; 23.122",70,36,null,null,"2015-12-07","2016-06-11"]
[4548,700052,"      CT6 aspects of CIoT","CIoT-CT",3,"Rel-13","C6","2015-12-07","2016-06-15",1,"CP-160292",null,"Intel, Vivek Gupta","vivek.g.gupta@intel.com","11/6/16: WID:CP-150795->CP-160292¦13/6/16: 0%->100",31.102,70,36,null,null,"2015-12-07","2016-06-13"]
[4554,710065,"   UE Conformance Test Aspects - Narrowband Internet of Things (NB-IOT)","NB_IOT-UEConTest",2,"Rel-13","R5","2016-03-15","2017-12-15",1,"RP-160047",null,"CMCC",null,"testing REL-13 NB_IOT-Core1/7/16: Compl:0%->5%¦26/9¦20/12/1¦21/3/17: Compl: ;",null,71,36,null,null,"2016-03-22","2018-01-08"]
[4556,700003,"   Extended Coverage GSM (EC-GSM) for support of Cellular Internet of Things Core part","CIoT_EC_GSM-Core",2,"Rel-13","G1,G2","2015-09-25","2016-05-12",1,"GP-151039",null,"Marteen Sunberg, Ericsson","Marteen.Sunberg@Ericsson.com","7/12/15:created by MCC to distinguish core versus test parts. 2/3/16: FCD: 11/15->05/16, 40->90%¦13/6/16: 90%->100",null,70,36,null,null,"2015-09-07","2016-06-13"]
[4559,720097,"   MS Conformance Test Aspects - Extended Coverage GSM (EC-GSM) for support of Cellular Internet of Things","CIoT_EC_GSM-MSConTest",2,"Rel-13","R5","2016-06-15","2016-09-15",1,"RP-160753",null,"Ericsson",null,"tested REL-13 WI: CIoT_EC_GSM-Core26/9/16: Compl",null,72,37,null,null,"2016-07-01","2016-09-26"]
[4564,690020,"      CT1 aspects of extended DRX cycle","eDRX-CT",3,"Rel-13","C1","2015-09-07","2016-03-11",1,"CP-150541",null,"Catovic, Amer, Qualcomm","Catovic, Amer, Qualcomm","14/09/15: WID:CP-150499->CP-150541¦7/12/15: 25%->80. FCD ->03/16. ES in CP-150723¦7/3/16: 80%->100","24.301; 24.008; 29.118",69,35,null,null,"2015-09-07","2016-03-07"]
[4567,700034,"      CT6 aspects of extended DRX cycle","eDRX-CT",3,"Rel-13","C6","2015-09-07","2016-03-11",1,"CP-150541",null,"Catovic, Amer, Qualcomm","Catovic, Amer, Qualcomm","7/12/15: Added. FCD ->03/16. ES in CP-150723¦8/3/16: 0%->100",null,70,36,null,null,"2015-09-07","2016-03-08"]
[4568,670057,"   RAN enhancements for extended DRX in LTE","LTE_extDRX",2,"Rel-13","R2","2015-03-16","2016-03-15",1,"RP-150493",null,"Qualcomm",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4572,700001,"      Core Part: Extended DRX (eDRX) for GSM","eDRX_GSM-Core",3,"Rel-13","G2,G1","2015-08-28","2015-11-20",1,"GPC150624",null,"John Diachina, Ericsson LM","John.Diachina@Ericsson.com","7/12/15: created by MCC to distinguish Core versus test parts","43.064; 44.018; 44.060; 45.008; 48.018; 43.022",70,36,null,null,"2015-08-12","2015-12-07"]
[4575,650035,"   Study on Optimizations to support High Latency communications","FS_HLcom",2,"Rel-13","S2","2014-09-19","2015-06-17",1,"SP-140635","-","Ericsson","hans.ronneke@ericsson.com","Dec.14: 0->30%. Mar15: 70%¦June2015: Compl:70%->100","New 23.709",65,33,null,null,"2014-08-05","2015-06-15"]
[4581,710067,"   UE Conformance Test Aspects - Further LTE Physical Layer Enhancements for MTC","LTE_MTCe2_L1-UEConTest",2,"Rel-13","R5","2016-03-15","2017-09-15",1,"RP-171156",null,"Ericsson",null,"testing REL-13 LTE_MTCe2_L1-Core¦1/7/16: Compl:0%->6%¦26/¦2¦21/3/17: Compl:70% ;",null,71,36,null,null,"2016-03-22","2017-09-19"]
[4583,640050,"Group based Enhancements","GROUPE",1,"Rel-13","S2,S3","2014-06-18","2015-12-16",1,"SP-140706","-","Huawei","ZhangWanqiang@huawei.com","-","Stage 2",64,33,null,null,"2014-05-30","2014-12-12"]
[4586,640350,"   TR on Security for Group based Enhancements","GROUPE",2,"Rel-13","S3","2014-06-18","2015-06-12",1,"SP-140706","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs. 3/3/15: 5->10%.¦June2015: Compl:10%->60¦11/12/15: 60%->100","New 33.889",64,33,null,null,"2014-05-30","2015-12-11"]
[4591,680030,"      CT4 aspects of Group based Enhancements","GROUPE-CT",3,"Rel-13","C4","2015-06-15","2015-12-16",1,"CP-150816",null,"Peter Schmitt, Huawei","Peter.Schmitt@huawei.com","07/09/15: 0%->80¦7/12/15: 80%->100¦7/12/15: WID:CP-150240->CP-150816","29.272; 23.008; 29.336; 29.303; 29.002; 29.230; 29.305; 23.003",68,35,null,null,"2015-06-15","2015-12-07"]
[4594,640249,"   Stage 2 for Monitoring Enhancements","MONTE",2,"Rel-13","S2","2014-06-23","2015-06-17",1,"SP-140705","-","Intel, Puneet Jain","puneet.jain@intel.com","-¦June2015: Compl:0%->100","23.682; TBD",64,33,null,null,"2014-05-30","2015-06-15"]
[4595,640349,"   TR on Security for Monitoring Enhancements","MONTE",2,"Rel-13","S3","2014-06-18","2015-06-12",1,"SP-140705","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","TR 33.8xy will capture requirements, solution alternatives, evaluations and conclusions for the AESE, MONTE and GROUPE WIDs.3/3/15: 5->10%.¦June2015: Compl:10%->15¦11/12/15: 15%->100","New 33.889",64,33,null,null,"2014-05-30","2015-12-11"]
[4599,680025,"      CT1 aspects of Monitoring Enhancements","MONTE-CT",3,"Rel-13","C1","2015-06-15","2015-12-16",1,"CP-150422",null,"Peter Schmitt, Huawei","peter.schmitt@huawei.com","07/09/15: 0%->95¦14/09/15: WID:CP-150396->CP-150422¦7/12/15: 95%->100","24.301; 24.008",68,35,null,null,"2015-06-15","2015-12-07"]
[{"$f":"A4604+1","v":4604},640246,"   Stage 2 for Dedicated Core Networks","DECOR",2,"Rel-13","S2","2014-06-23","2015-03-18",1,"SP-150249","-","NTT DOCOMO","Daisuke Fujishima (fujishimad@nttdocomo.co.jp)","Mar15: 0->70%¦June2015: Compl:70%->100, WID: SP-140707-> SP-150249","23.060; 23.401; 23.236",64,33,null,null,"2014-05-30","2015-06-18"]
[4607,690013,"      CT4 aspects for Dedicated Core Networks CT aspects","DECOR-CT",3,"Rel-13","C4","2015-06-25","2016-03-11",1,"CP-150423",null,null,null,"7/12/15: 70%->90. FCD -> 03/16, ES CP-150617¦7/3/16: 90%->100","29.274; 29.060; 23.003; 29.272; 29.002; 29.305; 23.008; 29.230; 29.303; 23.007",69,35,null,null,"2015-09-07","2016-03-07"]
[4610,610030,"Service Exposure and Enablement Support","SEES",1,"Rel-13","S1","2013-09-12","2014-09-17",1,"SP-130505","S1-143301","KPN","toon.norp@tno.nl","SP#62 completion 06/14=>09/14. Linked to Rel-12 Study TR 22.888 (FS_MTCe) and to Features Rel-11 SIMTC & Rel-12 MTCe and MOSAP","Stage 1",61,31,null,null,"2013-08-26","2013-11-26"]
[4613,640048,"Architecture Enhancements for Service capability Exposure","AESE",1,"Rel-13","S2,S3","2014-06-18","2016-03-11",1,"SP-140704","-","Intel","puneet.jain@intel.com","-","Stage 2",64,33,null,null,"2014-05-30","2014-12-12"]
[4618,680001,"   CT aspects of Architecture Enhancements for Service capability Exposure","AESE-CT",2,"Rel-13","C3","2015-06-15","2016-03-11",1,"CP-150576",null,"Yizhuang Wu, Huawei ","wuyizhuang@huawei.com","14/09/15: WID:CP-150402->CP-150487->CP-150576",null,68,35,null,null,"2015-06-15","2015-09-14"]
[4621,621000,"Rel-13 LTE Carrier Aggregation","LTE_CA_Rel13",1,"Rel-13","R4","2013-12-09","2018-12-14",0.95,"-","-","-","-","Acronym changed from \"LTE_CA_Rel-13\" to \"LTE_CA_Rel13\"",null,62,32,null,null,"2012-12-14","2015-01-15"]
[4622,690080,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 12","LTE_CA_B4_B4_B5_B12",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151208","-","US Cellular",null,"13/6/16: moved from Rel-14 to Rel-13 (was a mistake)",null,69,35,null,null,"2015-09-29","2016-06-13"]
[4626,690181,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 4 and Band 5","LTE_CA_B2_B4_B4_B5-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151210","-","US Cellular",null,"13/6/16: moved from Rel-14 to Rel-13 (was a mistake)",null,69,35,null,null,"2015-09-29","2016-06-13"]
[4631,620032,"   LTE Advanced 3 band Carrier Aggregation (3DL/1UL) for Band 3, Band 8 and Band 27","LTE_CA_B3_B8_B27",2,"Rel-13","R4","2013-12-09","2015-12-15",0.25,"RP-131754","-","KT","Chungwoo HWANG (cwhwang@kt.com)","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-09"]
[4634,630033,"   LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 22","LTE_CA_B7_B22",2,"Rel-13","R4","2014-03-06","2015-06-15",1,"RP-140094","-","Orange, Ericsson","erika.tejedor@ericsson.com","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[4637,640022,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 2 and Band 12","LTE_CA_B2_B2_B12",2,"Rel-13","R4","2014-06-18","2015-06-15",1,"RP-141232","-","U.S. Cellular","sebastian.thalanany@uscellular.com","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-21"]
[4640,640025,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 8","LTE_CA_B3_B3_B8",2,"Rel-13","R4","2014-06-16","2015-06-15",1,"RP-140692","-","CHTTL","Po-Han Hsieh (pohanhsieh@cht.com.tw)","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[4645,640232,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 41, Band 42 and Band 42","LTE_CA_B41_B42_B42-Perf",3,"Rel-13","R4","2014-06-18","2015-06-15",1,"RP-140974","RP-150536","Huawei","leo.liuye@huawei.com","CD:Thu 11/12/14->Sun 15/03/15¦Compl:0%->0%¦Stat Rep: RP-141084->RP-141732 1st Apr 15: Compl:0%->60% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:60%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141; 36.307",64,33,null,null,"2014-06-16","2015-06-18"]
[4649,650038,"   LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 28","LTE_CA_B2_B28",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141145","-","Huawei","alf.ahlstrom@huawei.com","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4650,650138,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 28","LTE_CA_B2_B28-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141145","RP-150536","Huawei","alf.ahlstrom@huawei.com","CD:Fri 11/12/15->Sun 15/03/15¦Compl:0%->50%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:50%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101; 36.104; New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[4653,650139,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 28","LTE_CA_B4_B28-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141146","RP-150536","Huawei","alf.ahlstrom@huawei.com","CD:Fri 11/12/15->Sun 15/03/15¦Compl:0%->35%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:35%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101; 36.104; New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[4658,650041,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 40","LTE_CA_B1_B40",2,"Rel-13","R4","2014-09-15","2015-12-15",1,"RP-141312","-","KT","ilwhan.kim@kt.com","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4661,650042,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 40","LTE_CA_B3_B40",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141674","-","KT","Chungwoo HWANG (cwhwang@kt.com)","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4664,650043,"   LTE Advanced inter-band Carrier Aggregation of Band 20 and Band 31","LTE_CA_B20_B31",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141336","-","Huawei","Liu Liehai (liuliehai@huawei.com)","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4667,650044,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 31","LTE_CA_B3_B31",2,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141337","-","Huawei","Liu Liehai (liuliehai@huawei.com)","Inter-band CA 2DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4672,650245,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 40","LTE_CA_B5_B40-Perf",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-150285","RP-150536","SK Telecom","haesung.park@sk.com","¦WID: RP-142043->RP-141888¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->80% 1st Apr 15: WID: RP-141888->RP-150285 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.141; 36.307",65,33,null,null,"2014-06-16","2015-06-18"]
[4676,650049,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 41 and Band 41","LTE_CA_B8_B41_B41",2,"Rel-13","R4","2014-09-12","2015-06-15",1,"RP-141290","-","China Mobile","PAN, Qun (panqun@chinamobile.com)","Inter-band CA 3DL/1UL","LTE",65,33,null,null,"2014-06-16","2014-09-22"]
[4677,650149,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 41 and Band 41","LTE_CA_B8_B41_B41-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141845","RP-150536","China Mobile","PAN, Qun (panqun@chinamobile.com)","¦WID: RP-142043->RP-141845¦Stat Rep: -->RP-141732 1st Apr 15: Compl:80%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101; 36.104; 36.133; New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[4680,650151,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 38, Band 40 and Band 40","LTE_CA_B38_B40_B40-Core",3,"Rel-13","R4","2014-09-15","2015-06-15",1,"RP-141655","RP-150536","Samsung","xutao.zhou@samsung.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->0%¦Stat Rep: -->RP-141732 1st Apr 15: Compl:0%->70% 1st Apr 15: Stat Rep: RP-141732->RP-150013 03/07/15: Compl:70%->100% 03/07/15: Stat Rep: RP-150013->RP-150536","36.101; 36.104; 36.133; New 36.8xx",65,33,null,null,"2014-06-16","2015-06-18"]
[4685,660072,"   LTE Carrier Aggregation Enhancement Beyond 5 Carriers","LTE_CA_enh_b5C",2,"Rel-13",null,"2014-12-15","2018-09-14",1,"RP-142286",null,"Nokia Networks","Nokia","FCD: 06/16->12/15, Rel-14?->Rel-13",null,66,34,null,null,"2015-01-12","2015-01-15"]
[4688,730074,"      UE Conformance Test Aspects - LTE Carrier Aggregation Enhancement Beyond 5 Carriers: PUCCH on Scell","LTE_CA_enh_b5C_PUCCH-UEConTest",3,"Rel-13","R5","2016-09-15","2018-09-14",1,"RP-192558",null,"Huawei",null,"¦20/12/16: Compl:0%->5%19/6/17: Compl:5%->8%¦19/9/17: Compl:8%->15%¦8/1/18: 27/3/18; 14/1/20: WID:RP-171764->RP-192558; 14/1/20: 20%->100",null,73,37,null,null,"2016-09-26","2020-01-14"]
[4690,660180,"      Core part: HSPA Dual-Band UL carrier aggregation","HSUPA_DB_MC-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151852","RP-151281","Qualcomm","Qualcomm","1st Apr 15: Compl:0%->10% 1st Apr 15: WID: RP-142237->RP-150129 1st Apr 15: Stat Rep: ->RP-150127 03/07/15: Compl:10%->40% 03/07/15: Stat Rep: RP-150127->RP-150761 29/09/15: Compl:40%->50% 29/09/15: Stat Rep: RP-150761->RP-151281¦",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4696,660182,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 41","LTE_CA_B3_B41-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151446","RP-151131","China Telecom","China Telecom","1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->65% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-142239->RP-151446 29/09/15: Stat Rep: RP-150536->RP-151131¦29/09/1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4699,660183,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 3","LTE_CA_B1_B3_B3-Core",3,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-141777","RP-151131","China Unicom","China Unicom","1st Apr 15: Compl:0%->50% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->90% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:90%->100% 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2015-09-29"]
[4703,660284,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 28","LTE_CA_B1_B19_B28-Perf",3,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-150639","RP-151131","NTT DOCOMO","NTT DOCOMO","03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: WID: RP-141791->RP-150639 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2015-09-29"]
[4704,660085,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 21, Band 42 and Band 42","LTE_CA_B21_B42_B42",2,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-141792",null,"NTT DOCOMO","NTT DOCOMO",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4707,660086,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 40 and Band 40","LTE_CA_B7_B40_B40",2,"Rel-13","R4","2014-12-15","2015-09-15",1,"RP-141802",null,"ZTE","ZTE",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4712,660287,"      Perf. part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 28","LTE_CA_B1_B8_B28-Perf",3,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-150447","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: WID: RP-141826->RP-150447 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4715,660288,"      Perf. Part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7","LTE_CA_B3_B7_B7_BWset-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-141881","RP-150536","Ericsson","Ericsson","Acronym changed from LTE_CA_B3_B7_B7-Perf 1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4717,660189,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 7 and Band 28","LTE_CA_B7_B7_B28-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-141882","RP-150536","Ericsson","Ericsson","1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4723,660191,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 40","LTE_CA_B1_B8_B40-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151259","RP-151131","KT","KT","1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: WID: RP-141947->RP-151259 29/09/15: Stat Rep: RP-1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4726,660192,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 40","LTE_CA_B3_B8_B40-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-151261","RP-151131","KT","KT","1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->60% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->95% 29/09/15: WID: RP-141949->RP-151261 29/09/15: Stat Rep: RP-1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4730,660293,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL) of Band 3, Band 7 and Band 8","LTE_CA_B3_B7_B8-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142013","RP-150536","Ericsson","Ericsson","1st Apr 15: Compl:0%->99% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4731,660094,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 28","LTE_CA_B1_B3_B28",2,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142038",null,"Nokia Networks","Nokia Networks",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4735,660195,"      Core part:LTE Advanced 3 band Carrier Aggregation (3DL/1UL) of Band 3, Band 8 and Band 28","LTE_CA_B3_B8_B28-Core",3,"Rel-13","R4","2014-12-15","2016-03-15",0.4,"RP-142193","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: CD:Tue 15/12/15->Tue 15/09/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131¦",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4739,660296,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 8, Band 42 and Band 42","LTE_CA_B8_B42_B42-Perf",3,"Rel-13","R4","2014-12-15","2016-03-15",1,"RP-142194","RP-151131","Softbank Mobile","Softbank Mobile","1st Apr 15: Compl:0%->20% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:20%->40% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131;",null,66,34,null,null,"2015-01-12","2016-03-22"]
[4742,660297,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 40 and Band 40","LTE_CA_B28_B40_B40-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150676","RP-151131","Huawei","Huawei","1st Apr 15: WID: RP-142206->RP-150233 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: CD:Mon 15/06/15->Tue 15/12/15 03/07/15: WID: RP-150233->RP-150676 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131¦",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4744,660198,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 40 and Band 40","LTE_CA_B3_B40_B40-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-151071","RP-150536","Huawei","Huawei","1st Apr 15: Compl:0%->50% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->100% 03/07/15: WID: RP-142207->RP-151071 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4750,661100,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 7","LTE_CA_B1_B3_B7-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142209","RP-151131","Huawei","Huawei","1st Apr 15: Compl:0%->30% 1st Apr 15: CD:Tue 15/12/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:30%->40% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:40%->50% 29/09/15: CD:Tue 1",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4753,661101,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 5","LTE_CA_B3_B3_B5-Core",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142238","RP-150536","Intel","Intel","1st Apr 15: Compl:0%->10% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4757,661202,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 28","LTE_CA_B3_B7_B28-Perf",3,"Rel-13","R4","2014-12-15","2015-06-15",1,"RP-142244","RP-150536","Ericsson","Ericsson","1st Apr 15: Compl:0%->99% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:99%->100% 03/07/15: Stat Rep: RP-150013->RP-150536",null,66,34,null,null,"2015-01-12","2015-06-18"]
[4758,661003,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 30","LTE_CA_B2_B2_B12_B30",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142198",null,"AT&T","AT&T",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4762,661104,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 30","LTE_CA_B2_B2_B5_B30-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150448","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: CD:Tue 15/12/15->Tue 15/09/15 1st Apr 15: WID: RP-142199->RP-150448 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: RP-150013->RP-150536 29/09",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4766,661205,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2 Band 29 and Band 30","LTE_CA_B2_B2_B29_B30-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150450","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142200->RP-150450 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4769,661206,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 12 and Band 30","LTE_CA_B2_B4_B12_B30-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150452","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142201->RP-150452 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4771,661107,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 30","LTE_CA_B2_B4_B5_B30-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150451","RP-151131","AT&T","AT&T","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-142202->RP-150451 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->95% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4777,661109,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 25, Band 41, Band 41 and Band 41","LTE_CA_B25_B41_B41_B41-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142204","RP-151131","Alcatel-Lucent","Alcatel-Lucent","1st Apr 15: Compl:0%->50% 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:50%->90% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:90%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4780,661110,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 in REL-13","LTE_CA_2UL_R13-A1-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150678","RP-151131","Huawei","Huawei","1st Apr 15: Compl:0%->40% 1st Apr 15: WID: RP-141935->RP-150411 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:40%->60% 03/07/15: WID: RP-150411->RP-150678 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:60%->80% 29/09/15: Stat Rep: RP-150",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4784,661211,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 in REL-13","LTE_CA_2UL_R13-A2-Perf",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-150408","RP-151131","Qualcomm","Qualcomm","1st Apr 15: Compl:0%->50% 1st Apr 15: WID: RP-141975->RP-150408 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4785,661012,"   LTE Advanced dual uplink inter-band Carrier Aggregation Class A3 in REL-13","LTE_CA_2UL_R13-A3",2,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142010",null,"Ericsson","Ericsson",null,null,66,34,null,null,"2015-01-12","2015-01-12"]
[4789,661113,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 4 DL","LTE_CA_NC_B41_4DL-Core",3,"Rel-13","R4","2014-12-15","2015-12-15",1,"RP-142022","RP-151131","Alcatel-Lucent","Alcatel-Lucent","1st Apr 15: Compl:0%->10% 1st Apr 15: CD:Tue 15/03/16->Tue 15/12/15 1st Apr 15: Stat Rep: ->RP-150013 03/07/15: Compl:10%->50% 03/07/15: Stat Rep: RP-150013->RP-150536 29/09/15: Compl:50%->80% 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,66,34,null,null,"2015-01-12","2016-01-01"]
[4793,670265,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 42","LTE_CA_B1_B3_B42-Perf",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150641","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150121->RP-150641 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[{"$f":"A4796+1","v":4796},670266,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 42","LTE_CA_B1_B19_B42-Perf",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150642","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150122->RP-150642 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4798,670167,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 21 and Band 42","LTE_CA_B1_B21_B42-Core",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150643","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150123->RP-150643 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4804,670169,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 21 and Band 42","LTE_CA_B19_B21_B42-Core",3,"Rel-13","R4","2015-03-16","2015-06-15",1,"RP-150645","RP-150536","NTT DOCOMO, INC.",null,"03/07/15: Compl:0%->100% 03/07/15: CD:Tue 15/09/15->Mon 15/06/15 03/07/15: WID: RP-150125->RP-150645 03/07/15: Stat Rep: ->RP-150536",null,67,34,null,null,"2015-04-01","2015-06-18"]
[4807,670170,"      Core part: Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 7","LTE_CA_B4_B4_B7_BWset-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150429","RP-151131","Rogers Communications",null,"03/07/15: CD:Tue 15/09/15->Tue 15/12/15 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4809,670071,"   Additional bandwidth combination set for LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12","LTE_CA_B4_B7_B12_BWset",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150430",null,"Rogers Communications",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4812,670072,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 7 and Band 12","LTE_CA_B2_B7_B12",2,"Rel-13","R4","2015-03-16","2016-03-15",1,"RP-150431",null,"Rogers Communications",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4816,670173,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 7","LTE_CA_B2_B4_B7-Core",3,"Rel-13","R4","2015-03-16","2016-03-15",1,"RP-150432","RP-151131","Rogers Communications",null,"03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-1511311/1/16:22/3/16: Compl:0%->100%",null,67,34,null,null,"2015-04-01","2016-03-22"]
[4820,670274,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 7, Band 20 and Band 38","LTE_CA_B7_B20_B38-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150433","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->30% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:30%->60% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4825,670176,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 12","LTE_CA_B2_B2_B4_B12-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150659","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->95% 03/07/15: WID: RP-150074->RP-150659 03/07/15: Stat Rep: ->RP-150536 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4827,670077,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 4","LTE_CA_B2_B2_B4_B4",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150075",null,"Nokia Networks",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4831,670178,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 5 and Band 40","LTE_CA_B1_B3_B5_B40-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-151216","RP-151131","SK Telecom",null,"03/07/15: Compl:0%->30% 03/07/15: WID: RP-150434->RP-150617 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:30%->60% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-150617->RP-151216 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4834,670179,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 7 and Band 8","LTE_CA_B1_B3_B7_B8-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150435","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->40% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:40%->45% 29/09/15: Stat Rep: RP-150536->RP-151131",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4836,670080,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 5 and Band 29","LTE_CA_B2_B4_B5_B29",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150436",null,"Huawei",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4839,670081,"   LTE Advanced dual uplink inter-band Carrier Aggregation FDD-TDD","LTE_CA_2UL_FDD_TDD",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150064",null,"KDDI",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4843,670182,"      Core part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A4 in REL-13","LTE_CA_2UL_R13-A4-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150616","RP-151131","Nokia Networks",null,"03/07/15: Compl:0%->25% 03/07/15: WID: RP-150410->RP-150616 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:25%->75% 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4847,670283,"      Perf. part:LTE Advanced 3DL/2UL inter-band Carrier Aggregation","LTE_CA_3DL_2UL-Perf",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-151230","RP-151131","Nokia Corporation",null,"03/07/15: Compl:0%->25% 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:25%->75% 29/09/15: CD:Tue 15/03/16->Tue 15/12/15 29/09/15: WID: RP-150479->RP-151230 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4852,670185,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 8","LTE_CA_C_B8-Core",3,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-151177","RP-151131","CMCC",null,"03/07/15: Compl:0%->60% 03/07/15: WID: RP-150437->RP-150809 03/07/15: Stat Rep: ->RP-150536 29/09/15: Compl:60%->90% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: WID: RP-150809->RP-151177 29/09/15: Stat Rep: RP-150536->RP-151131 ",null,67,34,null,null,"2015-04-01","2016-01-01"]
[4854,670086,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 42 for 4DL","LTE_CA_C_B42_4DL",2,"Rel-13","R4","2015-03-16","2015-12-15",1,"RP-150438",null,"CATT",null,null,null,67,34,null,null,"2015-04-01","2015-04-01"]
[4858,680177,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 8 and Band 11","LTE_CA_B1_B8_B11-Core",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150609","RP-151131","Softbank Mobile",null,"29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4861,680178,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 20 and Band 32","LTE_CA_B3_B20_B32-Core",3,"Rel-14","R4","2015-06-15","2016-03-15",0.9,"RP-150864","RP-151131","Ericsson",null,"29/09/15: Compl:0%->50% 29/09/15: Stat Rep: -->RP-1511311/22/3/16: Compl:50%->90%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4863,680079,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 42 and Band 42","LTE_CA_B7_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151012","-","Huawei",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4866,680080,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 20, Band 42 and Band 42","LTE_CA_B20_B42_B42",2,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-151013","-","Huawei",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4870,680181,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 38","LTE_CA_B3_B7_B38-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151014","RP-151131","Nokia Networks",null,"29/09/15: Compl:0%->60% 29/09/15: Stat Rep: -->RP-1511311/1/16: Compl:",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4874,680282,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 28, Band 41 and Band 41","LTE_CA_B28_B41_B41-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151111","RP-151131","KDDI",null,"29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4879,680185,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 4, Band 7 and Band 12","LTE_CA_B2_B4_B7_B12-Core",3,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-150628","RP-151131","Rogers Communications",null,"29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:0%->100%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4882,680186,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 19 and Band 42","LTE_CA_B1_B3_B19_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150632","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4885,680187,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 3, Band 42 and Band 42","LTE_CA_B1_B3_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150633","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4888,680188,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 42 and Band 42","LTE_CA_B1_B19_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150634","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4890,680089,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 19, Band 42 and Band 42","LTE_CA_B3_B19_B42_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150635","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4893,680090,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 19, Band 21 and Band 42","LTE_CA_B1_B19_B21_B42",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150636","-","NTT DOCOMO, INC.",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4897,680191,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 1, Band 21, Band 42 and Band 42","LTE_CA_B1_B21_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150637","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4901,680292,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 19, Band 21, Band 42 and Band 42","LTE_CA_B19_B21_B42_B42-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150638","RP-151131","NTT DOCOMO, INC.",null,"29/09/15: Compl:0%->95% 29/09/15: CD:Tue 15/09/15->Tue 15/12/15 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4906,680194,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 4 and Band 5","LTE_CA_B2_B2_B4_B5-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150731","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4909,680195,"      Core part:LTE Advanced 4-Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 12 and Band 12","LTE_CA_B2_B2_B12_B12-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-150732","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4911,680096,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 5 and Band 30","LTE_CA_B4_B4_B5_B30",2,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151015","-","AT&T",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4916,680297,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 12 and Band 30","LTE_CA_B4_B4_B12_B30-Perf",3,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151016","RP-151131","AT&T",null,"29/09/15: Stat Rep: -->RP-151131 22/3/16: Compl:50%->100%",null,68,35,null,null,"2015-07-03","2016-03-22"]
[4917,680098,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 4, Band 4, Band 29 and Band 30","LTE_CA_B4_B4_B29_B30",2,"Rel-13","R4","2015-06-15","2016-03-15",1,"RP-151017","-","AT&T",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4920,681000,"   LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 2, Band 5 and Band 12","LTE_CA_B2_B2_B5_B12",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151018","-","U.S. Cellular",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4925,681201,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 2, Band 5, Band 12 and Band 12","LTE_CA_B2_B5_B12_B12-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151019","RP-151131","U.S. Cellular",null,"29/09/15: Compl:0%->40% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4928,681202,"      Perf. part:LTE Advanced 3DL/2UL mixed intra- and inter-band Carrier Aggregation","LTE_CA_3DL_2UL_inter_intra-Perf",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP151576","RP-151131","Nokia Networks",null,"covers combinations of contiguous intra-band CA and inter-band CA or combinations of non-contiguous intra-band CA and inter-band CA for LTE¦pure intra-band CA combinations are also covered by this WI¦note: There is already a REL-13 WI LTE_CA_3DL_2UL ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4933,681104,"      Core part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4","LTE_CA_NC_B4_BWset-Core",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-151034","RP-151131","Nokia Networks",null,"LTE_CA_NC_B4 was completed in REL-12 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4936,681105,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 5","LTE_CA_NC_B5-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151036","RP-151131","Intel",null,"29/09/15: Compl:0%->20% 29/09/15: Stat Rep: -->RP-151131 ",null,68,35,null,null,"2015-07-03","2016-01-01"]
[4938,681006,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42 for 4DL","LTE_CA_NC_B42_4DL",2,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151102","-","Huawei",null,null,null,68,35,null,null,"2015-07-03","2015-07-03"]
[4943,680274,"      Perf. part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 12","LTE_CA_B2_B12_BWset-Perf",3,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150585","RP-151131","Nokia Networks",null,"LTE_CA_B2_B12 was completed as REL-12 WI 29/09/15: Compl:0%->100% 29/09/15: Stat Rep: -->RP-151131",null,68,35,null,null,"2015-07-03","2015-09-29"]
[4944,680076,"   Additional bandwidth combination set 2 for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12_BWset2",2,"Rel-13","R4","2015-06-15","2015-09-15",1,"RP-150947","-","Nokia Networks",null,"LTE_CA_B4_B12 was completed in REL-11 and LTE_CA_B4_B12_BWset was completed in REL-12",null,68,35,null,null,"2015-08-12","2015-07-03"]
[4947,680072,"   Introduction of 1447-1467MHz Band for TD-LTE in China","LTE_TDD_1447MHz_China",2,"Rel-13","R4","2015-06-15","2016-09-15",1,"RP-151037","-","Huawei",null,"Aug 15: TR numb added",null,68,35,null,null,"2015-08-12","2015-08-12"]
[4952,680184,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 41, Band 41, Band 42 and Band 42","LTE_CA_B41_B41_B42_B42-Core",3,"Rel-13","R4","2015-06-15","2015-12-15",1,"RP-151562","RP-151131","ZTE",null,"29/09/15: Compl:0%->40% 29/09/15: WID: RP-150627->RP-151562 29/09/15: Stat Rep: ->RP-151131",null,68,35,null,null,"2015-08-12","2016-01-01"]
[4956,690273,"      Perf. part:LTE Advanced inter-band Carrier Aggregation for Band 5 and Band 38","LTE_CA_B5_B38-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151367","-","Huawei",null,"¦1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4959,690274,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 11 and Band 18","LTE_CA_B1_B11_B18-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151156","-","KDDI",null,"1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4963,690076,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 41 and Band 42","LTE_CA_B3_B41_B42",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151365","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4965,690276,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 41 and Band 42","LTE_CA_B3_B41_B42-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151365","-","Huawei",null,"¦1/1/16: Compl:0%->100%",null,69,35,null,null,"2015-09-29","2016-01-01"]
[4970,690178,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 41, Band 41 and Band 41","LTE_CA_B39_B41_B41_B41-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151175","-","CMCC",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4971,690278,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 41, Band 41 and Band 41","LTE_CA_B39_B41_B41_B41-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151175","-","CMCC",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4974,690279,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL1UL) of Band 39, Band 39, Band 41 and Band 41","LTE_CA_B39_B39_B41_B41-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151176","-","CMCC",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4979,690183,"      Core part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 3, Band 28, Band 40 and Band 40","LTE_CA_B3_B28_B40_B40-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151363","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4983,690284,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) for Band 28, Band 40, Band 40 and Band 40","LTE_CA_B28_B40_B40_B40-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151364","-","Huawei",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4986,690285,"      Perf. part:LTE Advanced 4 Band Carrier Aggregation (4DL/1UL) of Band 3, Band 7, Band 7 and Band 28","LTE_CA_B3_B7_B7_B28-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151511","-","Telstra",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4990,690090,"   LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 19, Band 21, Band 42 and Band 42","LTE_CA_B1_B19_B21_B42_B42",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151160","-","NTT DOCOMO",null,null,null,69,35,null,null,"2015-09-29","NA"]
[4992,690290,"      Perf. part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 19, Band 21, Band 42 and Band 42","LTE_CA_B1_B19_B21_B42_B42-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151160","-","NTT DOCOMO",null,null,null,69,35,null,null,"2015-09-29","2016-01-01"]
[4995,690291,"      Perf. part:LTE Advanced 5 Band Carrier Aggregation (5DL/1UL) of Band 1, Band 3, Band 7, Band 7 and Band 28","LTE_CA_B1_B3_B7_B7_B28-Perf",3,"Rel-13","R4","2015-09-15","2016-03-15",1,"RP-160141","-","Telstra",null,"22/3/16: Compl:95%->100%;",null,69,35,null,null,"2015-09-29","2016-03-22"]
[5001,690293,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 41 and Band 41","LTE_CA_3DL3UL_B39_B41_B41-Perf",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151402","-","CATT",null,"TDD case",null,69,35,null,null,"2015-09-29","2016-01-01"]
[5002,690094,"   LTE Advanced 3 Band Carrier Aggregation (3DL/3UL) of Band 39, Band 39 and Band 41","LTE_CA_3DL3UL_B39_B39_B41",2,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151403","-","CATT",null,"TDD case¦5/10/15: 36.899-13 added;","36.899-13",69,35,null,null,"2015-09-29","2015-10-05"]
[5006,690195,"      Core part: Additional bandwidth combination set for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7","LTE_CA_NC_B7_BWset-Core",3,"Rel-13","R4","2015-09-15","2015-12-15",1,"RP-151462","-","Huawei",null,"LTE_CA_NC_B7 was completed in REL-12 ¦",null,69,35,null,null,"2015-09-29","2016-01-01"]
[5010,710001,"(Small) Test Technical Enhancements and Improvements for Rel-13","TEI13_Test",1,"Rel-13","SP,CP,RP,GP","2013-09-18","2015-12-21",1,"-","PCG-31","-","-","Created upon demand of RAN5","-",61,31,null,null,"2015-01-12","2016-02-24"]
[5013,0,"Release 13 IoT related Studies","-",1,"Rel-13","SP,R2","2013-09-12","2015-12-25",1,"-","-","-","-","-","-",null,null,null,null,"2013-03-04","2013-03-04"]
[5017,670036,"Study on Battery Efficient Security for very low Throughput Machine Type Communication Devices","FS_BEST_MTC_Sec",1,"Rel-13","S3","2015-03-13","2015-12-11",1,"SP-150171",null,"Barry, Aguibou, VODAFONE Group Plc","Barry, Aguibou, VODAFONE Group Plc","TR number added¦June2015: Compl:0%->10¦7/12/15: 10%->50¦11/12/15: 50%->75¦7/3/16: 75%->95¦19/9/16: 95%->100¦6/10/16: 33.163 added;","32.863; 33.163",67,34,null,null,"2015-03-13","2016-10-06"]
[5019,570034,"Study on Application specific Congestion control for Data Communication","FS_ACDC",1,"Rel-13","S1","2012-09-17","2014-09-17",1,"SP-130415","S1-143305","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#65 completed. SP#64 TR 22.806v200 for Approval. ACDC is applicable to UTRAN and E-UTRAN. Possible overlap with RAN2 TR 36.848 Study on smart congestion mitigation in E-UTRAN (prioritising MMTEL voice over other traffic during congestion)",22.806000000000001,57,29,null,null,"2012-08-31","2014-08-29"]
[5022,600046,"Study on Isolated E-UTRAN Operation for Public Safety","FS_IOPS",1,"Rel-13","S1","2013-06-25","2014-06-18",1,"SP-130596","-","General Dynamics","paul.piggin@gd-broadband.com","SP#64 completed. TR 22.897v200 for Approval. Linked to Rel-12 TR 22.803 (FS_ProSe) and FeaturES in CP-150ProSe, GCSE_LTE",22.896999999999998,60,31,null,null,"2013-05-30","2014-05-27"]
[5028,630017,"Study on RAN Sharing Enhancements on GERAN and UTRAN","FS_GUSH",1,"Rel-13","S1","2014-03-07","2014-09-17",1,"SP-140073","-","Telefónica","chris.friel@telefonica.com","SP#65 completed. Update on GERAN and UTRAN of Rel-12 TR 22.852 Study on RAN Sharing Enhancements (FS_RSE)","22.852 updates",63,32,null,null,"2014-02-05","2014-08-29"]
[5029,520035,"Study on Usage Monitoring Enhancements for Service, Application and Subscriber Group","FS_UMONC_sas",1,"Rel-13","S2","2011-06-08","2014-12-12",1,"SP-140403","-","China Telecom","Jinyan Li (lijy@ctbri.com.cn)","SP#64 revived. Added to the Title \"for Service, Application and Subscriber Group\", Changed Acronym: FS_UMONC=>FS_UMONC_sas",23.858000000000001,52,27,null,null,"2011-05-19","2014-06-19"]
[5033,500034,"Study on Security aspects of Integration of Single Sign-On (SSO) frameworks with 3GPP networks","FS_SSO_Int_Sec",1,"Rel-13","S3","2010-12-28","2015-06-12",1,"SP-150368","-","Ericsson","vesa.lehtovirta@ericsson.com","SP#65 moved to Rel-13. Updated WID SP-100734=>SP-140576. Completion 09/14=>06/15. Dec.14: 60->65%¦June2015: Compl:65%->100¦June2015: WID:SP-140576->SP-150368",33.895000000000003,50,26,null,null,"2010-11-25","2015-06-18"]
[5037,620060,"Study on Charging aspects on Roaming End-to-end scenarios with VoLTE IMS and interconnecting networks","FS_REVOLTE_IMS_CH",1,"Rel-13","S5","2013-12-17","2015-06-12",1,"SP-130609","-","Deutsche Telekom","Roland Jesske (r.jesske@telekom.de)","SP#64 moved to Rel-13. Completion 06/14=>12/14. Dec.14: 35->55, CD: 12/14->06/15. Mar 15: 55->75%¦June2015: Compl:75%->100",32.848999999999997,62,32,null,null,"2013-11-28","2015-06-15"]
[5041,590034,"Study on Downlink MIMO","FS_DOMIMO",1,"Rel-13","G1,G2","2014-08-14","2016-05-12",1,"GP-130288","-","Nokia Networks","juergen.hofmann@nokia.com","GP#62 completion 08/14=>02/15. Moved to Rel-13. GP#57 approved WID. Dec.14: 50->65%, CD: 02/15->05/15. 7/9/15: FCD: 11/15->02/16¦2/3/16: 65%->75, FCD: 02/16->05/16¦11/9/17: 75%->100","45.8xy",57,30,null,null,"2013-03-04","2017-09-11"]
[5042,640017,"Study on MIMO OTA antenna test function for LTE","FS_LTE_MIMO_OTA_ATF",1,"Rel-13","R4","2013-03-18","2014-12-15",1,"RP-141325","RP-142045","Keysight","Moray_Rumney@keysight.com","CD:Thu 11/12/14->Mon 15/12/14¦Compl:60%->100%¦Stat Rep: RP-141124->RP-142045","36.509; new 37.978",64,33,null,null,"2014-06-16","2015-01-12"]
[5048,640018,"Study on Indoor Positioning Enhancements for UTRA and LTE","FS_UTRA_LTE_iPos_enh",1,"Rel-13","R1,R4","2014-06-18","2015-09-15",1,"RP-141102","RP-151178","NextNav","Vogedes Jerome (jvogedes@NextNav.com)","CD:Thu 17/09/15->Tue 15/09/15¦Compl:0%->8%¦Stat Rep: RP-141101->RP-141818 1st Apr 15: Compl:8%->30% 1st Apr 15: Stat Rep: RP-141818->RP-150080 03/07/15: Compl:30%->75% 03/07/15: Stat Rep: RP-150080->RP-150595 29/09/15: Compl:75%->100% 29/09/15: Stat ","UTRA; LTE 37.857",64,33,null,null,"2014-06-16","2015-09-29"]
[5049,650014,"Study on Downlink enhancements for UMTS","FS_UTRA_EDL",1,"Rel-13","R2,R1","2014-09-12","2015-06-15",1,"RP-150224","RP-150681","Huawei","jun.chen@huawei.com","WID: RP-141901¦Stat Rep: -->RP-142233 1st Apr 15: Compl:40%->80% 1st Apr 15: WID: RP-141901->RP-150224 1st Apr 15: Stat Rep: RP-142233->RP-150223. 5/5/15: R4 replaced by R1 (correction mistake) 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-150223->","UTRA 25.706",65,33,null,null,"2014-09-15","2015-06-18"]
[5055,660064,"Study on Network-Assisted Interference Cancellation and Suppression for UMTS","FS_UTRA_NAICS",1,"Rel-13","R1","2014-12-15","2015-09-15",1,"RP-150174","RP-151235","Huawei","Huawei","TS number added 1st Apr 15: Compl:0%->20% 1st Apr 15: WID: RP-142250->RP-150174 1st Apr 15: Stat Rep: ->RP-150175. 5/5/15: \"R4\" replaced by \"R1\" (correction mistake) 03/07/15: Compl:20%->65% 03/07/15: Stat Rep: RP-150175->RP-150679 29/09/15: Compl:65%-",25.765999999999998,66,34,null,null,"2015-01-12","2015-09-29"]
[5056,660065,"Study on Enhanced Multiuser Transmissions and Network Assisted Interference Cancellation for LTE","FS_LTE_MUTX_NAIC",1,"Rel-13","R1","2014-12-15","2015-03-15",0,"RP-142315","RP-150213","MediaTek","MediaTek","1st Apr 15: CD:Tue 15/12/15->Sun 15/03/15 1st Apr 15: Stat Rep: ->RP-150213. 5/5/15: \"R4\" replaced by \"R1\" (correction mistake)",null,66,34,null,null,"2015-01-12","2015-05-05"]
[5060,660069,"Study on RAN sharing enhancements for UMTS","FS_RSE_UTRA_GUSH",1,"Rel-13","R3","2014-12-15","2015-06-15",1,"RP-150686","RP-150684","Huawei","Huawei","03/07/15: Compl:10%->100% 03/07/15: WID: RP-142284->RP-150686 03/07/15: Stat Rep: RP-150227->RP-150684. 7/10/15: responsible group corrected (R4->R3)",25.756,66,34,null,null,"2015-01-12","2015-10-07"]
[5064,670040,"Study on regulatory aspects for flexible duplex for E-UTRAN","FS_LTE_flex_duplex_reg",1,"Rel-13","RP","2016-06-15","2016-12-15",1,"RP-150470","RP-151307","LG Electronics Inc.",null,"TR added 03/07/15: Compl:0%->5% 03/07/15: Stat Rep: -->RP-150770 29/09/15: Compl:5%->100% 29/09/15: Stat Rep: RP-150770->RP-151307",36.881999999999998,67,34,null,null,"2015-04-01","2015-09-29"]
[5068,670093,"Study on EGPRS Access Security Enhancements with relation to cellular IoT","FS_EASE_IoT",1,"Rel-13","S3","2015-03-12","2015-12-11",1,"SP-150145",null,"Vesa Torvinen, Ericsson",null,"TR added¦June2015: Compl:0%->25¦7/12/15: 25%->70¦28/1/16: 33.420 added¦7/3/16: 70%->100","New 33.860; 33.420",67,34,null,null,"2015-04-02","2016-03-07"]
[5069,680013,"Study on SCC AS Restoration","FS_SCCAS_RES",1,"Rel-13","C4","2015-06-15","2015-06-15",1,"CP-150398",null,"Hao Zhang,, China Mobile","zhanghao@chinamobile.com","07/09/15: 5%->20¦7/12/15: 20%->100","New 29.812",68,35,null,null,"2015-06-15","2015-12-07"]
[5075,720087,"Study on multi-node testing for LAA","FS_LTE_LAA_multinode_test",1,"Rel-13","R4","2016-06-15","2017-06-15",1,"RP-162144",null,"Huawei",null,"coexistence testing for REL-13 WI LTE_LAA26/9/16: Compl:0%->10%26/9/16: WID: RP-161197->RP-161672¦20/12/16: Compl:10%->30%¦20/12/16: CD:Thu 15/12/16->Wed 15/03/17¦20/12/16: WID: RP-161672->RP-162144¦21/3/17: CD:Wed 15/03/17->Thu 15/06/17;",null,72,37,null,null,"2016-07-01","2017-06-19"]
[5076,560435,"Stopped - Study on Compliance of 3GPP SA5 specifications to the NGMN NGCOR","FS_OAM_NGMN_NGCOR",1,"Rel-13","S5","2012-06-26","2017-12-15",1,"SP-140787","-","Huawei","zoulan@huawei.com","SP#65 updated WID SP-140349=>SP-140539. Dec.14: 35->45, 12/14: 28.821 added. Mar 15: 45->50%¦June2015: Compl:50%->60. 07/09/15: FCD: 09/15->12/15¦7/12/15: FCD:12/15->03/16¦21/3/17:marked as stopped, was 60%","32.837; 28.821",56,29,80,null,"2012-05-14","2017-03-21"]
[5082,500131,"   Stage 1 for MOSAP","MOSAP-SA1",2,"Rel-12","S1","2010-12-16","2011-09-21",1,"SP-120427","-","Cisco","Vojislav Vucetic (vvucetic@cisco.com)","SP#53 completed",22.277999999999999,50,26,null,null,"2010-11-29","2012-06-09"]
[5083,520025,"   TR on Stage 2 for MOSAP","MOSAP-SA2TR",2,"Rel-12","S2","2011-06-06","2013-12-11",1,"SP-120427","-","Intel","chang.hong.shan@intel.com","SP#62 completed. TR 23.862v200 for Approval. SP#58 frozen as v100.","new 23.862",52,27,null,null,"2011-05-26","2012-11-22"]
[5087,530043,"Service and Media Reachability for Users over Restrictive Firewalls","SMURFs",1,"Rel-12","S1","2011-09-21","2012-06-20",1,"SP-110653","-","Vodafone","mona.mustapha@vodafone.com","SP#56 Stage 1 completed","Stage 1",53,27,null,null,"2011-07-19","2011-09-15"]
[5091,550025,"Integration of Single Sign-On (SSO) frameworks with 3GPP networks","SSO_Int",1,"Rel-12","S1","2012-03-08","2012-09-12",1,"SP-120184","-","InterDigital","christopher.wallace@interdigital.com","SP#57 Stage 1 completed. Triggered by Rel-12 TR 22.895. Linked to SA3 33.8xy (Study on Security aspects of SSO_Int), 33.914 (SSO application security for common IMS based on SIP Digest), 33.924 (i/w GBA and OpenID), 33.980 (i/w GBA and Liberty Alliance)","Stage 1",55,28,null,null,"2012-02-22","2012-08-07"]
[5095,570027,"IMS access via Digital Video Broadcast - Return Channel via Satellite (DVB-RCS2)","IMSSat",1,"Rel-12","S1","2012-02-02","2012-09-12",1,"SP-120543","-","KPN","toon.norp@tno.nl","SP#57 Stage 1 completed. Integrate Satcom access with IMS. Specify DVB-RCS2 as an IP Connectivity Access Network for IMS","Stage 1",57,29,null,null,"2012-08-06","2012-08-08"]
[5096,570127,"   Stage 1 for IMS access via DVB-RCS2","IMSSat-SA1",2,"Rel-12","S1","2012-02-02","2012-09-12",1,"SP-120543","-","KPN","toon.norp@tno.nl","SP#57 completed. Definition of DVB-RCS2 as a non-3GPP IP Connectivity Access Network for IMS",22.228000000000002,57,29,null,null,"2012-08-06","2012-08-08"]
[5102,590140,"   Stage 1 for Emergency Session Identification ","ESID-SA1",2,"Rel-12","S1","2013-03-04","2013-03-06",1,"SP-130126","-","Telecom Italia","carmen.catalano@telecomitalia.it","SP#59 completed (22.101 CR#0445)",22.100999999999999,59,30,null,null,"2013-02-19","2013-02-19"]
[5103,590041,"Deleted - Application and Service Access Control","ASAC",1,"Rel-12","S1","2013-03-06","2013-06-19",1,"SP-130124","-","NTT DOCOMO","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#60 stopped and Rel-13 FS_ACDC continues. Triggered by TR 22.806 Study on Application specific Congestion control for Data Communication (FS_ACDC) UID_570034","Stage 1",59,30,"SP-60","PCG-31","2013-02-19","2013-02-19"]
[5109,500128,"   TR on Stage 2 for LIPA Mobility and SIPTO at the Local Network","LIMONET-SA3",2,"Rel-12","S2","2010-10-15","2013-03-06",1,"SP-120926","-","Huawei","zhufenqin@huawei.com","SP#59 completed. TR 23.859 v100 for Information and Approval","new 23.859",50,26,null,null,"2010-11-26","2013-02-27"]
[5111,501328,"      Stage 2 for SIPTO at the Local Network","LIMONET-SIPTO-SA2",3,"Rel-12","S2","2010-10-22","2013-06-19",1,"SP-120926","-","Huawei","zhufenqin@huawei.com","SP#60 completed","23.060; 23.401",50,26,null,null,"2010-11-26","2013-06-06"]
[5114,530215,"         CT1 part of Stage 3 CN aspects of SIPTO at the Local Network","LIMONET-SIPTO-CT1",4,"Rel-12","C1","2011-09-24","2014-03-05",1,"CP-130274","-","Huawei","peter.schmitt@huawei.com","CP#63 completed","24.008; 24.301",53,27,null,null,"2011-08-27","2014-01-29"]
[5118,500228,"      Deleted - Stage 2 for stand-alone L-GW and associated Mobility for LIPA and SIPTO at the Local Network","LIMONET-LIPA-del1",3,"Rel-12","S2","2010-10-22","2012-12-12",1,"SP-120926","-","Huawei","zhufenqin@huawei.com","SP#58 updated WID SP-120256=>SP-120926 (stopped BB2 LIMONET-LIPA on Mobility)","23.060; 23.401",50,26,"SP-58","PCG-30","2010-11-26","2013-02-27"]
[5122,510049,"Operator Policies for IP Interface Selection","OPIIS",1,"Rel-12","S2,C1","2011-03-23","2013-12-06",1,"SP-120738","-","LG Electronics","taehyeon.kim@lge.com","Linked to Rel-10 IFOM IP Flow Mobility and seamless WLAN offload (non-seamless WLAN offload aspects) & Rel-11 LIMONET (support traffic offload at local network)","Stage 2/3",51,26,null,null,"2011-02-21","2013-02-27"]
[5123,510149,"   TR on Stage 2 for Operator Policies for IP Interface Selection","OPIIS",2,"Rel-12","S2","2011-03-23","2012-12-12",1,"SP-120738","-","LG Electronics","taehyeon.kim@lge.com","SP#58 completed","new 23.853",51,26,null,null,"2011-02-21","2012-12-10"]
[5129,590013,"   Stage 3 for SMS submit and delivery without MSISDN in IMS","SMSMI-CT",2,"Rel-12","C1,C4","2013-03-01","2013-12-06",1,"CP-130090","-","NSN","peter.leis@nsn.com","CP#62 completed. Address scenario IMS client to IMS client SMS (comprises SMS receive and send SMS without requiring an MSISDN associated as part of their subscription record in HSS","Stage 3",59,30,null,null,"2013-02-16","2013-11-18"]
[5132,530042,"IMS-based Telepresence","IMS_TELEP",1,"Rel-12","S1,C1,C3,C4,IETF","2010-03-22","2014-12-09",1,"SP-110588","-","Orange","bruno.tossou@orange-ftgroup.com","This feature does not introduce any changes to the IMS architecture, and no stage 2 impacts are identified","Stage 1/2/3",53,27,null,null,"2011-07-19","2012-06-08"]
[5134,580001,"   CT part for IMS Telepresence (Stage 2/3)","IMS_TELEP",2,"Rel-12","C1,C3,C4,IETF","2010-03-22","2014-12-09",1,"CP-140624","-","Huawei","Weiwei(Tommy) Yang (tommy@huawei.com)","CP#65 updated WID CP-140196=>CP-140624. 2/4/15: acronym changed to IMS_TELEP","Stage 2/3",58,30,null,null,"2012-11-19","2015-04-02"]
[5138,641002,"      (IETF) Framework for Telepresence Multi-Streams (draft-ietf-clue-framework) ","IMS_TELEP",3,"Rel-12","C1-IETF","2010-03-22","2014-12-05",1,"CP-140624","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","work in progress. 2/4/15: acronym changed to IMS_TELEP; 23/4/20: 50%->90. Was (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-framework ); 9/4/21: RFC 8845 added;","draft-ietf-clue-framework; RFC 8845",64,33,null,null,"2014-06-06","2021-04-09"]
[5141,641005,"      (IETF) An XML Schema for the CLUE data model (draft-ietf-clue-data-model-schema) ","IMS_TELEP",3,"Rel-12","C1-IETF","2010-03-22","2014-12-05",1,"CP-140624","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","work in progress. 2/4/15: acronym changed to IMS_TELEP; 23/4/20: 50%->90. Was (IETF) CT1 part of IMS Telepresence (draft-ietf-clue-data-model-schema); 9/4/21: RFC 8846 added;","draft-ietf-clue-data-model-schema; RFC 8846",64,33,null,null,"2014-06-06","2021-04-09"]
[5145,560120,"   Stage 1 for Group Communication System Enablers for LTE","GCSE_LTE",2,"Rel-12","S1","2012-06-18","2013-06-19",1,"SP-140433","-","Nokia Networks","Juergen.Merkel@nsn.com","SP#60 completed. TS 22.468 v100 for 1-step Approval","New 22.468",56,29,null,null,"2012-05-14","2014-09-07"]
[5149,610035,"   Security for Group Communication System Enablers for LTE (Stage 2)","GCSE_LTE",2,"Rel-12","S3","2013-09-13","2014-06-18",1,"SP-140433","-","Nokia Networks","anja.jerichow@nsn.com","SP#64 completed",33.246000000000002,61,31,null,null,"2013-09-03","2014-09-07"]
[5150,640010,"   CT aspects of Group Communication System Enablers for LTE","GCSE_LTE-CT",2,"Rel-12","C3,C4,C1","2014-06-13","2014-12-09",1,"CP-140559","-","Nokia Networks","thomas.belling@nsn.com","CP#65 updated WID CP-140452=>C3-143199 (added CT1 part)","Stage 3",64,33,null,null,"2014-06-10","2014-09-06"]
[5156,560022,"Machine-Type and other mobile data applications Communications enhancements","MTCe",1,"Rel-12",null,"2009-12-10","2016-05-12",0.98,"SP-130327","-","Intel","puneet.jain@intel.com","-","Stage 1/2/3",56,29,null,null,"2012-04-13","2013-11-28"]
[5159,560722,"   TR on Security aspects of Machine-Type Communications","MTCe-SA3TR",2,"Rel-12","S3","2009-12-10","2014-03-07",1,"SP-130327","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","SP#63 completed. TR 33.868v100 for 1-step Approval. Was Rel-10 UID_460023 (Security for NIMTC). Was Rel-11 UID_490028 (TR on Security aspects of MTC). SP#56 activity transferred to Rel-12 Feature MTCe","New 33.868",56,29,null,null,"2012-08-16","2014-02-27"]
[5161,560122,"   BB1: Small Data and Device Triggering Enhancements (SDDTE)","MTCe-SDDTE",2,"Rel-12","S2,C4,C3","2012-06-18","2014-09-11",1,"SP-120450","-","Intel","puneet.jain@intel.com ","-","-",56,29,null,null,"2012-04-13","2013-11-28"]
[5165,630101,"         CT4 part of Stage 3 for BB1: Small Data and Device Triggering Enhancement","MTCe-SDDTE-CT",4,"Rel-12","C4","2014-03-05","2014-09-11",1,"CP-140489","-","Huawei","peter.schmitt@huawei.com","CP#65 completed. Updated WID CP-140272=>CP-140489","29.002; 29.336; 23.008; 29.337; 29.338; 29.230",63,32,null,null,"2014-01-29","2014-07-29"]
[5168,560322,"   BB3: UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP",2,"Rel-12",null,"2012-06-18","2016-05-12",0.93,"SP-120442","-","Ericsson","peter.hedman@ericsson.com","-","-",56,29,null,null,"2012-04-13","2013-11-28"]
[5172,620107,"         CT1 part of Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP)","MTCe-UEPCOP-CT1",4,"Rel-12","C1","2013-12-06","2014-09-11",1,"CP-130714","-","Ericsson","mikael.wass@ericsson.com","CP#65 completed","24.008; 24.301",62,32,null,null,"2013-11-18","2014-07-28"]
[5177,700005,"      Testing of Support of Power Saving Mode in GERAN","MTCe-UEPCOP_GERAN3new",3,"Rel-12","G3","2015-11-11","2016-05-12",0.1,"GP-151186",null,"Ericsson","sajal.kumar.das@ericsson.com","7/12/15: created.02/3/16: acronym: MTCe-UEPCOP-GERAN_test->MTCe-UEPCOP_GERAN3new¦2/3/16: 0%->10",null,70,36,null,null,"2014-08-29","2016-03-02"]
[{"$f":"A5180+1","v":5180},620143,"      Core part: RAN enhancements for Machine-Type and other mobile data applications Communications","MTCe-RAN-Core",3,"Rel-12","R2,R3","2014-02-03","2014-09-12",1,"RP-140752","RP-141096","ZTE","sergio.parolari@zte.com.cn","RP#65 completed","25.300; 25.304; 25.413; 36.300; 36.304; 36.413; 36.423",62,32,null,null,"2013-12-07","2014-09-15"]
[5181,600012,"Low cost & enhanced coverage MTC UE for LTE","LC_MTC_LTE",1,"Rel-12","R1,R2,R4","2013-06-15","2016-12-15",1,"RP-130848","-","Vodafone","eric.bouton@vodafone.com","Triggered by Rel-11 TR 36.888 (FS_LC_MTC_UE)","LTE",60,31,null,null,"2013-06-17","2014-09-09"]
[5186,570031,"   Stage 1 for Policy and Charging Support for Fixed Mobile Convergence","P4C-FMC",2,"Rel-12","S1","2012-09-10","2012-09-12",1,"SP-120542","-","Huawei","amar.deol@huawei.com","SP#57 completed",22.277999999999999,57,29,null,null,"2012-08-06","2013-01-08"]
[5188,560724,"      TR on Stage 2 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (P4C-F)","P4C-F-SA2TR",3,"Rel-12","S2","2012-06-20","2014-12-12",1,"SP-120275","-","Huawei","marco.spini@huawei.com","SP#64 TR 23.896 was never sent for approval due to incomplete P4C BBs. SP#61 TR 23.896v100 for Information. Dec.14: 90->100%. Mar15: 23.896 for approval.","new 23.896",56,29,null,null,"2012-06-04","2015-03-13"]
[5192,620009,"         CT1 part of Stage 3 for BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks","P4C-F-CT3",4,"Rel-12","C1","2013-12-06","2014-03-05",1,"CP-130776","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","CP#63 completed",24.302,62,32,null,null,"2013-11-19","2014-01-29"]
[5195,600043,"      Traffic Detection Function (TDF) based Charging for traffic from fixed terminals and NSWO traffic from 3GPP UEs in fixed broadband access networks (Stage 2/3)","P4C-F-CH_T",3,"Rel-12","S5","2013-06-24","2014-06-18",1,"SP-130262","-","Openet Telecom","alan.mcnamee@openet.com","SP#64 completed","Stage 2 (32.240; 32.251); Stage 3 (32.298; 32.299)",60,31,null,null,"2013-06-02","2014-06-10"]
[5199,560324,"   Deleted - BB3: Policy and Charging Control for 3GPP UEs connected to fixed broadband access network via S2b and S2c reference points for EPC routed traffic (P4C-S2bc)","P4C-S2bc",2,"Rel-12","S2","2012-06-21","2012-12-12",1,"SP-120445","-","ZTE","Tricci So (tso@zteusa.com)","SP#58 stopped (at 0% completion)","23.139; 23.203; new 23.896",56,29,"SP-58","PCG-30","2012-06-04","2013-01-08"]
[5204,560325,"   Stage 1 for IMS Business Trunking for IP-PBX in Static Mode of Operation","BusTI-SA1",2,"Rel-12","S1","2011-09-28","2012-09-12",1,"SP-120862","-","Deutsche Telekom","kurt.bischinger@t-mobile.at","SP#57 completed. 22.228CR#0171 ",22.228000000000002,56,29,null,null,"2012-05-11","2012-12-10"]
[5207,610007,"   CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3)","BusTI-CT",2,"Rel-12","C1,C3","2013-09-06","2014-12-09",1,"CP-140197","-","Deutsche Telekom","michael.kreipl@telekom.de","-","Stage 3",61,31,null,null,"2013-08-10","2014-03-03"]
[5208,610107,"      CT1 part of CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3)","BusTI-CT",3,"Rel-12","C1","2013-09-06","2014-12-09",1,"CP-140197","CP-140607","Deutsche Telekom","michael.kreipl@telekom.de","CP#65 completion 09/14=>12/14. Exception in CP-140607. Dec.14: 85->100%","23.218; 24.229; 24.525 (transfer of ETSI 182 025)",61,31,null,null,"2013-08-10","2014-12-04"]
[5213,580055,"   Deleted - TR on Security Aspects of WLAN Network Selection for 3GPP Terminals","WLAN_Nsdel",2,"Rel-12","S3","2012-12-13","2014-03-07",1,"SP-120847","-","Huawei","Lydia Xu (xuyixian@huawei.com)","SP#63 stopped (84% complete)","New 33.865 ",58,30,"CP-63","PCG-32","2012-11-02","2014-03-04"]
[5215,570028,"Deleted - IMS Registration Control","IMS_RegCon",1,"Rel-12","S1,S2,C1,C4","2012-01-31","2013-12-11",1,"SP-120735","-","China Mobile","lulu@chinamobile.com","SP#62 stopped. Specify for fixed line the requirement of controlling user registration to IMS based on network information related to user location (e.g. IP address, DSLAM information)","Stage 1/2/3",57,29,"SP-62","PCG-32","2012-08-06","2013-12-10"]
[5218,600016,"   Deleted - CT aspects of IMS registration control","IMS_RegCon-CT",2,"Rel-12","C1,C4","2013-06-19","2013-12-11",1,"CP-130217","-","China Mobile","Jiang Yi (jiangyi@chinamobile.com)","SP#62 no CT/Stage 3 work is needed (stopped at 0% completion)","Stage 2/3",60,31,"SP-62","PCG-32","2013-05-28","2013-12-10"]
[5223,580259,"   TR on Stage 2 for Proximity-based Services","ProSe-SA2TR",2,"Rel-12","S2","2012-12-13","2014-03-07",1,"SP-140574","-","Qualcomm","Haris Zisimopoulos (harisz@qti.qualcomm.com)","SP#63 completed. TR 23.703v200 for Approval","New 23.703",58,30,null,null,"2012-11-16","2014-09-15"]
[5227,640039,"   Charging Aspects of Proximity-based Services","ProSe-CH",2,"Rel-12","S5","2014-06-19","2015-03-13",1,"SP-140401","SP-140543","Qualcomm","Cheng Hong (hongc@qti.qualcomm.com)","SP#65 exception in SP-140543. Mar15: 85->100%","Stage 2/3",64,33,null,null,"2014-06-06","2015-03-05"]
[5231,630106,"      CT1 part of CT aspects of Proximity-based Services","ProSe-CT",3,"Rel-12","C1","2014-03-05","2014-12-09",1,"CP-140290","CP-140615","Qualcomm","Lena Chaponniere (lguellec@qti.qualcomm.com)","CP#65 completion 09/14=>12/14. Exception in CP-140615. TS 24.333/4v200 for Approval. Dec.14: 90->100%","24.301; 23.122; New TSs (24.333; 24.334)",63,32,null,null,"2014-01-29","2014-12-04"]
[5234,630406,"      CT6 part of CT aspects of Proximity-based Services","ProSe-CT",3,"Rel-12","C6","2014-03-06","2014-12-09",1,"CP-140290","CP-140695","Qualcomm","Lena Chaponniere (lguellec@qti.qualcomm.com)","CP#65 completion 09/14=>12/14. Exception in CP-140695. Dec.14: 60->100%",31.102,63,32,null,null,"2014-01-29","2014-12-03"]
[5235,630030,"   LTE Device to Device Proximity Services","LTE_D2D_Prox",2,"Rel-12",null,"2014-03-11","2017-06-15",1,"RP-140955","-","Qualcomm","Shailesh Patil (patil@qti.qualcomm.com)","follow-up of TR 36.843 FS_LTE_D2D_Prox","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5240,580162,"   Stage 1 for Web Real Time Communication access to IMS","IMS_WebRTC",2,"Rel-12","S1","2012-12-14","2013-06-19",1,"SP-130707","-","China Mobile","lulu@chinamobile.com","SP#60 completed","22.101; 22.228",58,30,null,null,"2012-11-16","2013-09-09"]
[5242,600041,"   Stage 2 for Web Real Time Communication access to IMS","IMS_WebRTC",2,"Rel-12","S2","2013-06-19","2014-03-07",1,"SP-130707","-","China Mobile","Yu Qing (yuqing@chinamobile.com)","SP#63 completed",23.228000000000002,60,31,null,null,"2013-06-06","2014-02-04"]
[5245,620067,"   TR on Security for Web Real Time Communication access to IMS","IMS_WebRTC",2,"Rel-12","S3","2013-12-11","2014-09-17",1,"SP-130707","-","Ericsson","oscar.ohlsson@ericsson.com","SP#65 completed. TR 33.871v200 for Approval","New 33.871",62,32,null,null,"2013-12-05","2014-09-04"]
[5250,630103,"      CT1 part of CT aspects of Web Real Time Communication (WebRTC) Access to IMS","IMS_WebRTC-CT1",3,"Rel-12","C1","2014-03-05","2014-12-09",1,"CP-140192","CP-140621","China Mobile","Jiang Yi (jiangyi@chinamobile.com)","CP#65 TS 24.371v100 for Information. Completion 09/14=>12/14. Exception in CP-140621. Dec.14: 70->90%. 3/3/15: 100% cpltd.","24.229; New 24.371",63,32,null,null,"2014-01-29","2015-03-03"]
[5254,870067,"       (IETF) Third-Party Token-based Authentication and Authorization for Session Initiation Protocol (SIP) (draft-ietf-sipcore-sip-token-authnz)","IMS_WebRTC-yusef",3,"Rel-12","C1-IETF","2014-09-12","2014-12-05",1,null,null,null,null,"9/4/21: RFC 8898 added;","RFC 8898",87,44,null,null,"2014-09-02","2021-04-09"]
[5258,580163,"   Stage 2 for Usage Monitoring Control PCC enhancement","UMONC",2,"Rel-12","S2","2012-12-13","2013-03-06",1,"SP-120928","-","ZTE","bi.yifeng@zte.com.cn ","SP#59 completed. 23.203 CR#0782 (Time Based Usage Monitoring), CR#0784 (Usage Monitoring via Online Charging System)",23.202999999999999,58,30,null,null,"2012-11-18","2013-02-27"]
[5261,590139,"   Stage 2 for Application Based Charging","ABC-SA2",2,"Rel-12","S2","2013-03-07","2013-06-19",1,"SP-130328","-","Allot","Alla Goldner (agoldner@allot.com)","SP#60 completed",23.202999999999999,59,30,null,null,"2013-02-21","2013-07-25"]
[5263,600049,"   CT3 aspects of Application Based Charging (Stage 3)","ABC-CT3",2,"Rel-12","C3","2013-06-14","2013-12-06",1,"CP-130353","-","Allot","Alla Goldner (agoldner@allot.com)","CP#62 completed","29.212; 29.213; 29.214; 29.215; 29.219",60,31,null,null,"2013-05-29","2013-10-21"]
[5266,610009,"   Stage 3 for Enhanced S2a Mobility Over trusted WLAN access to EPC","eSaMOG-St3",2,"Rel-12","C1,C4","2013-09-09","2014-12-09",1,"CP-130715","-","ZTE","Joy Zhou (zhou.xingyue@zte.com.cn)","CP#62 updated WID CP-130580=>CP-130715","Stage 3",61,31,null,null,"2013-08-10","2013-11-28"]
[5269,610039,"Optimized Offloading to WLAN in 3GPP-RAT Mobility","WORM",1,"Rel-12","S2,C1","2013-09-12","2014-06-13",1,"SP-130392","-","BlackBerry","Steve Barrett (sbarrett@blackberry.com)","Linked to TR 23.890 Study on Optimized Offloading to WLAN in 3GPP-RAT mobility (FS_WORM), SAE for support for non-3GPP accesses, Multi-Access PDN Connectivity (MAPCON), IP Flow Mobility and Seamless WLAN Offload (IFOM), CS Fallback in EPS (SAES-CSFB)","Stage 2/3",61,31,null,null,"2013-07-25","2013-09-09"]
[5272,610040,"Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case","NETLOC_TWAN",1,"Rel-12","S2,C3,C1,C4","2013-09-12","2014-09-11",1,"SP-130393","-","Alcatel-Lucent","Laurent.thiebaut@alcatel-lucent.com","Rel-11 Network Provided Location Information for IMS (NWK-PL2IMS) covers the case where UE is served by a 3GPP RAN. This WI covers the case where the UE is served by a TWAN","Stage 2/3",61,31,null,null,"2013-07-25","2013-09-09"]
[5277,620308,"      CT4 part of Network-provided Location information for IMS Trusted WLAN Access Network (TWAN) case","NETLOC_TWAN-CT",3,"Rel-12","C4","2013-12-06","2014-09-11",1,"CP-130810","-","China Telecom","Xia Xu (xiaxu@ctbri.com.cn)","CP#65 completed","29.273; 29.274; 29.275; 29.328; 29.329",62,32,null,null,"2013-11-19","2014-07-28"]
[5281,630004,"   CT aspects of Core Network Overload – User Location Information reporting improvements","CNO_ULI-CT",2,"Rel-12","C3,C4","2014-03-05","2014-09-11",1,"CP-140093","-","Alcatel-Lucent","horst.brinkmann@alcatel-lucent.com","Specify Stage 3 procedures to support the ULI signalling optimizations","Stage 3",63,32,null,null,"2014-01-29","2014-01-29"]
[5285,510054,"Security aspects of Public Warning System","PWS_Sec",1,"Rel-12","S3,S1","2011-03-23","2014-09-17",1,"SP-140299","-","ST-Ericsson","john.mattsson@ericsson.com","-","-",51,26,null,null,"2012-06-02","2014-06-09"]
[5288,511354,"   Deleted - SA3 part for Security aspects of Public Warning System","PWS_Sec-del1",2,"Rel-12","S3","2011-03-30","2014-06-18",1,"SP-140299","-","ST-Ericsson","john.mattsson@ericsson.com","SP#64 stopped","New 33.269",51,26,"SP-64","PCG-33","2012-06-02","2014-06-09"]
[5290,510254,"   Deleted - Stage 2 for Security aspects of Public Warning System","PWS_Sec-del3",2,"Rel-12","S2","2011-03-23","2011-09-21",1,"SP-120434","-","ST-Ericsson","john.mattsson@ericsson.com","SP#53 work stopped as already done in previous releases",23.401,51,26,"SP-53","PCG-27","2012-06-02","2012-02-20"]
[5293,520031,"Security enhancements for usage of Generic Bootstrapping Architecture (GBA) from the browser (Stage 2)","Web_GBA",1,"Rel-12","S3","2011-06-08","2013-06-19",1,"SP-120890","-","Nokia","Silke.Holtmanns@nokia.com","SP#60 completed","33.220; 33.222; New 33.823",52,27,null,null,"2011-05-17","2013-07-01"]
[5297,580005,"   CT aspects of Extended IMS media plane security features (Stage 2/3)","eMEDIASEC-CT",2,"Rel-12","C4,C1,C3,IETF","2012-12-13","2014-12-09",1,"CP-130597","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","-","Stage 2/3",58,30,null,null,"2012-11-14","2013-11-19"]
[5299,580006,"      CT4 part of CT aspects of Extended IMS media plane security features","eMEDIASEC-CT",3,"Rel-12","C4","2012-12-19","2014-12-09",1,"CP-130597","CP-140479","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#65 completion 09/14=>12/14. Exception in CP-140479. Dec.14: 90->100. 2/4/15: acronym changed to eMEDIASEC-CT","23.334; 29.334; 29.238; 23.333; 29.333",58,30,null,null,"2012-11-14","2015-04-02"]
[5304,580008,"      CT3 part of CT aspects of Extended IMS media plane security features","eMEDIASEC-CT",3,"Rel-12","C3","2012-12-19","2014-12-09",1,"CP-130597","CP-140569","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#65 completion 06/14=>12/14. Level 100%=>80%. Exception in CP-140569. CP#64 completed. Dec.14: 80->100. 2/4/15: acronym changed to eMEDIASEC-CT",29.161999999999999,58,30,null,null,"2012-11-14","2015-04-02"]
[{"$f":"A5308+1","v":5308},600050,"   CT aspects of Tunneling of UE Services over Restrictive Access Networks (Stage 3)","TURAN-CT",2,"Rel-12","C1","2013-06-14","2014-06-13",1,"CP-130716","-","Huawei","Haitao Wei (weihaitao@huawei.com)","CP#64 completed. Stage 3 for 2 new SA3 solutions for firewall traversal: 1) UE access to PLMN IP-based services via restrictive non-3GPP Ans, 2) UE access to IMS services via restrictive ANs","24.229; 24.302; New 24.322",60,31,null,null,"2013-05-28","2014-05-26"]
[5312,470032,"   Stage 2/3 for Codec for Enhanced Voice Services","EVS_codec-SA4",2,"Rel-12","S4","2010-03-25","2014-12-12",1,"SP-140151","SP-140467","Huawei","lei.miao@huawei.com","SP#65 completion 09/14=>12/14. Exception in SP-140467. TS 26.441v200 for Approval. TSs 26.442/44/45/46/47/48/49/50/51v100 for 1-step Approval. Ongoing TS 26.443 EVS Codec ANSI C code (floating point). Dec.14: 90->95","26.114; New (26.441; 26.442; 26.443; 26.444; 26.445; 26.446; 26.447; 26.448; 26.449; 26.450; 26.451)",47,24,null,null,"2010-03-10","2015-06-26"]
[5315,650105,"      CT4 part of CT impacts of codec for Enhanced Voice Services","EVS_codec-CT",3,"Rel-12","C4","2014-09-16","2014-12-09",1,"CP-140800","CP-140478","Nokia Networks","Jan.Kall@nsn.com","CP#65 exception in CP-140478. Dec.14: 0->100¦WID: CP-140492-> CP-140800","23.334; 29.232; 29.238; 29.332; 29.333; 29.334",65,33,null,null,"2014-07-29","2014-12-09"]
[5317,650305,"      CT3 part of CT impacts of codec for Enhanced Voice Services","EVS_codec-CT",3,"Rel-12","C3","2014-09-16","2014-12-09",1,"CP-140800","CP-140560","Nokia Networks","Jan.Kall@nsn.com","CP#65 exception in CP-140560. Dec.14: 20->100¦WID: CP-140492-> CP-140800","29.163; 29.292",65,33,null,null,"2014-07-29","2014-12-09"]
[5320,560140,"   SA4 part of Coordination of Video Orientation","CVO-SA4",2,"Rel-12","S4","2012-06-07","2013-03-06",1,"SP-120228","-","Ericsson","frederic.gabin@ericsson.com","SP#59 completed. Resolve backward compatible video orientation mis-alignment in MTSI real-time video communication via interaction between MTSI video clients at call setup & during mid-call of the video orientation for correct local rendering","26.114; 26.141; 26.234; 26.346",56,29,null,null,"2012-06-07","2013-02-16"]
[5324,600306,"      CT3 part of CT aspects of Coordination of Video Orientation","CVO-CT",3,"Rel-12","C3","2013-06-14","2013-12-06",1,"CP-130393","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed","29.162; 29.163",60,31,null,null,"2013-05-28","2013-11-18"]
[5326,570133,"   TR on Evaluation of High Efficiency Video Coding for 3GPP Services","HEVC-SA4TR",2,"Rel-12","S4","2012-09-12","2014-06-19",1,"SP-130569","-","Qualcomm","Ye-Kui Wang (yekuiw@qti.qualcomm.com)","SP#64 completed. TR 26.906v200 for Approval","New 26.906",57,29,null,null,"2012-08-30","2014-04-16"]
[5331,580166,"   TR on IMS-based Streaming and Download Delivery Enhancements","IMS_SDE-SA4TR",2,"Rel-12","S4","2012-12-12","2014-03-07",1,"SP-120767","-","Intel","ozgur.oyman@intel.com","SP#63 completed. Identify use cases and requirements based on Rel-10/11 PSS and MBMS functionality to be addressed for IMS-based streaming and download enhancements","new 26.827",58,30,null,null,"2012-11-12","2014-01-29"]
[5335,580267,"   Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE - UE Delay aspects","ART_LTE-UED",2,"Rel-12","S4","2012-12-12","2014-09-17",1,"SP-120770","-","AT&T, Orange","luisa.marchetto@att.com, stephane.ragot@orange.com","SP#65 completed","26.131; 26.132",58,30,null,null,"2012-11-12","2014-08-13"]
[5339,590143,"   Enhanced MBMS Operation","MI-EMO",2,"Rel-12","S4","2013-03-06","2014-12-12",1,"SP-140212","SP-140471","Huawei","Zhiming Li (lizhiming@huawei.com)","SP#65 completion 09/14=>12/14. Exception in SP-140471. Dec.14: 85->100","26.247; 26.346",59,30,null,null,"2013-02-20","2015-03-05"]
[5340,590443,"   TR on MBMS operation on Demand","MI-MooDTR",2,"Rel-12","S4","2013-03-06","2014-12-12",1,"SP-130026","SP-140471","Qualcomm","Charles Lo (clo@qti.qualcomm.com) ","SP#65 completion 09/14=>12/14. Exception in SP-140471. SP#63 TR 26.849v100 for Information. Dec.14: 75->100","New 26.849",59,30,null,null,"2013-02-20","2015-03-05"]
[5344,600007,"   CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions","E2EMTSI-CT",2,"Rel-12","C3,C1,C4","2013-06-21","2015-09-14",1,"CP-130397","-","Ericsson","susana.fernandez@ericsson.com","Stage 2/3. 5/5/15: corrected to be Rel-12. Nothing to be done in the end (covered by Rel-13 QOSE2EMTSI-CT), so 100%","Stage 2/3",60,31,null,null,"2013-02-20","2015-05-05"]
[5347,600307,"      CT4 part of CT aspects of End-to-End Multimedia Telephony Service for IMS (MTSI) extensions","E2EMTSI-CT",3,"Rel-12","C4","2013-06-21","2014-09-12",1,"CP-130397","-","Ericsson","susana.fernandez@ericsson.com","CP#64 completion 06/14=>09/14. 5/5/15: corrected to be Rel-12. Nothing to be done in the end (covered by Rel-13 QOSE2EMTSI-CT), so 100%","23.333; 23.334; 29.238; 29.332; 29.333; 29.334",60,31,null,null,"2013-05-29","2015-05-05"]
[5353,560035,"   Compliance of 3GPP SA5 specifications to the NGMN Next Generation Converged Operations Requirements (NGCOR)","OAM-NGMN_NGCOR",2,"Rel-12","S5","2012-06-20","2014-09-17",1,"SP-140321","-","Huawei","christian.toche@huawei.com","SP#65 moved to Rel-13 OAM-PMID (Converged management Performance Management Interface Definition) UID_560235","-",56,29,null,null,"2012-05-14","2014-08-25"]
[5355,560335,"      3GPP Fault Management Solution Profile for NGMN NGCOR","OAM-FMSP",3,"Rel-12","S5","2012-06-20","2013-06-19",1,"SP-120778","-","Ericsson","thomas.tovinger@ericsson.com","SP#60 completed. TS 28.390v200 for Approval","new 28.390",56,29,null,null,"2012-05-23","2013-06-13"]
[5358,530250,"      NIM part Network Management for 3GPP Interworking WLAN","OAM-IWLAN-SA5NM",3,"Rel-12","S5","2011-09-21","2013-12-11",1,"SP-140542","-","China Mobile","Chengang@chinamobile.com, lijian@chinamobile.com","SP#65 discontinue I-WLAN specs: Move parts (e.g. IOCs) applicable for EPC and non-3GPP access interworking NRMs from 28.601/2/6 to 28.611/2/6. Withdraw 28.601/2/6 (CN and non-3GPP access i/w NRMs). SP#62 completed. TSs 28.601/2/6/11/12/16 for Approval","32.632; 32.636; 32.752; 32.756; new (28.611; 28.612; 28.616; withdrawn 28.601; 28.602; 28.606)",53,27,null,null,"2011-08-27","2014-09-10"]
[5362,580054,"   Deleted - Rel-12 Performance Management","OAM12-PM",2,"Rel-12","S5","2013-06-21","2014-09-16",1,"-","-","-","-","OAM12-PM is an umbrella BB also for PM related TEI12 type of changes that are not part of any other dedicated feature/WI","-",58,30,"SP-69",null,"2012-11-15","2014-08-19"]
[5366,570037,"Rel-12 Charging","CH12",1,"Rel-12","S5","2012-12-12","2014-06-18",1,"-","-","-","-","CH12 is an umbrella Feature for changes that are not part of any other dedicated feature/WI","-",57,29,null,null,"2012-09-19","2012-09-19"]
[5367,580051,"   Short Message Service - Service Center (SMS-SC) Offline Charging","SMS-SC-CH",2,"Rel-12","S5","2012-12-12","2014-03-07",1,"SP-140027","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","Stage 2/3. SP#63 completed. Updated WID SP-120775=>SP-140027","32.240; 32.274; 32.297; 32.298; 32.299",58,30,null,null,"2012-11-20","2014-02-27"]
[5371,530018,"IMS Emergency PSAP Callback (Stage 3)","EMC_PC",1,"Rel-12","C1,C3,IETF","2011-09-21","2014-06-13",1,"CP-130218","-","Ericsson","christer.holmberg@ericsson.com","Dep. IETF ECRIT on PSAP call back. Fulfill SA1/2 Rel-7 EMC1 reqs UID_32045 PS domain and IMS impacts for supporting IMS Emergency calls (related to BB UID_1653 Emergency Call Enhancements for IP& PS Based Calls","Stage 3",53,27,null,null,"2011-08-27","2013-11-18"]
[5374,530218,"   CT3 part of IMS Emergency PSAP Callback","EMC_PC",2,"Rel-12","C3","2011-09-24","2013-09-06",1,"CP-130218","-","Ericsson","christer.holmberg@ericsson.com","CP#61 completed. 2/4/15: acronym changed to EMC_PC","29.163; 29.165",53,27,null,null,"2011-08-27","2015-04-02"]
[5380,590021,"   Public Warning System - Reset/Failure/Restart in Warning Message Delivery in LTE","REP_WMD-RFR_PWS",2,"Rel-12","R3","2013-03-04","2014-06-13",1,"RP-130398","-","one2many, Huawei","peter.sanders@one2many.eu, Dai Mingzeng (daimingzeng@huawei.com)","-","LTE",59,30,null,null,"2013-02-26","2013-03-01"]
[5382,580012,"Single Radio Voice Call Continuity (SRVCC) before ringing (Stage 3)","bSRVCC",1,"Rel-12","C1,C3,R5","2012-12-07","2014-03-06",1,"CP-130219","-","NTT DOCOMO","keisuke.sasada.kx@nttdocomo.com","Linked to Rel-8 Feature IMS Service Continuity (IMS-Cont) UID_390056. TS 23.237 Rel-12 CR#0444 under TEI12","GERAN; UTRA; LTE",58,30,null,null,"2012-11-19","2013-06-10"]
[5385,620017,"   Test part: Single Radio Voice Call Continuity (SRVCC) before ringing","bSRVCC-UEConTest",2,"Rel-12","R5","2013-12-06","2014-03-06",1,"RP-131919","RP-140422","NTT DOCOMO","Masahiro.Tamaoki.eu@nttdocomo.com","RP#63 completed. Testing for CT1 TS 24.237 (IMS service continuity Stage 3)","34.229-1; 34.229-2; 36.523-1; 36.523-2 ",62,32,null,null,"2013-11-25","2013-12-14"]
[5389,651002,"   Deleted - (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-jesske-sipcore-sip-tree-cap-indicators)","IMSProtoc6",2,"Rel-12","C1-IETF","2014-09-12","2014-12-05",1,"CP-120905","-","christer.holmberg@ericsson.com","christer.holmberg@ericsson.com","Not completed internet-draft. 4/2/15: acronym changed to IMSProtoc6; 9/4/21: 25%->100","draft-allen-sipcore-sip-tree-cap-indicators",65,33,null,null,"2014-09-02","2021-04-09"]
[5393,580016,"SAE Protocol Development - Phase 3","SAES3",1,"Rel-12","C1","2012-12-07","2014-09-11",1,"CP-120704","-","InterDigital","behrouz.aghili@interdigital.com ","Stage 3 continuation of Rel-8 Feature SAES (3GPP System Architecture Evolution Specification - Evolved Packet System) UID_320005","Stage 2/3",58,30,null,null,"2012-11-19","2013-02-16"]
[5394,580017,"   SAE Protocol Development (Stage 3) - Phase 3","SAES3-CT1",2,"Rel-12","C1","2012-12-07","2014-09-11",1,"CP-120704","-","InterDigital","behrouz.aghili@interdigital.com ","CP#65 completed","23.122; 24.008; 24.167; 24.229; 24.301; 24.302; 24.303; 24.304; 24.305; 24.312; 29.018; 29.118",58,30,null,null,"2012-11-20","2014-05-26"]
[5398,580021,"   Stage 2 for IM-SSF Application Server Service Data Descriptions","IMS_SSFDD",2,"Rel-12","C1","2012-12-07","2013-03-01",1,"CP-120756","-","Huawei","susan.shishufeng@huawei.com","CP#59 completed",23.218,58,30,null,null,"2012-11-19","2013-02-16"]
[5401,590015,"   Stage 2 for Diameter based interface between SGSN and SMS central functions","Dia_SGSN_SMS",2,"Rel-12","C1","2013-03-07","2013-12-06",1,"CP-130437","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#62 completed",23.04,59,30,null,null,"2013-02-16","2013-11-18"]
[5407,610006,"   CT3 part of eMBMS restoration procedures","eMBMS_Rest",2,"Rel-12","C3","2013-09-04","2014-09-11",1,"CP-140271","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#65 completed",29.061,61,31,null,null,"2013-03-07","2014-08-01"]
[5409,590114,"   Stage 2 for Dual Radio VCC enhancements","eDRVCC",2,"Rel-12","S2","2012-09-19","2013-03-01",1,"CP-130091","-","Ericsson","Jan.Holm@ericsson.com","Stage 2 in Rel-12 TEI12 TS 23.237 CR#0431, CR#0440, CR#0441, CR#0453 (pre-alerting). 2/4/15: acronym changed to eDRVCC",23.236999999999998,59,30,null,null,"2013-02-16","2015-04-02"]
[5413,600009,"CT aspects of Signalling of Image Size (Stage 2/3)","SIS_CT",1,"Rel-12","C4,C1,C3","2013-06-14","2013-12-06",1,"CP-130394","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed. SA4 Rel-8 MTSI Video: Dynamic Rate Adaptation/Signalling of Image Size UID_34041 has included service aspects to support image attribute (a=imageattr) in TS 26.114 as in RFC 6236. But associated CN aspects were not included","Stage 2/3",60,31,null,null,"2013-05-28","2013-11-19"]
[5416,600309,"   CT3 part of CT Aspects of Signalling of Image Size","SIS_CT",2,"Rel-12","C3","2013-06-14","2013-12-06",1,"CP-130394","-","Ericsson","nevenka.biondic@ericsson.com","CP#62 completed","29.162; 29.163",60,31,null,null,"2013-05-28","2013-11-19"]
[5420,610104,"   TR on Proxy Call Session Control Function (P-CSCF) restoration enhancements","PCSCF_RES",2,"Rel-12","C4","2013-09-06","2014-09-11",1,"CP-140490","-","Ericsson","maria.cruz.bartolome@ericsson.com","CP#65 completed. TR 29.806v200 for Approval","New 29.806",61,31,null,null,"2013-08-10","2014-09-06"]
[5421,640999,"   Common for HSS & PCRF solutions","PCSCF_RES",2,"Rel-12","C4,C3,C1","2013-04-03","2014-12-09",1,"CP-140490","-","Ericsson","maria.cruz.bartolome@ericsson.com","-","-",64,33,null,null,"2014-07-29","2014-07-29"]
[5425,640998,"   HSS based solution","PCSCF_RES",2,"Rel-12","C4,C1","2013-04-03","2014-12-09",1,"CP-140490","-","Ericsson","maria.cruz.bartolome@ericsson.com","-","-",64,33,null,null,"2014-07-29","2014-07-29"]
[5428,640997,"   PCRF based solution","PCSCF_RES",2,"Rel-12","C3,C1","2013-04-03","2014-12-09",1,"CP-140490","-","Huawei","susan.shishufeng@huawei.com","-","-",64,33,null,null,"2014-07-29","2014-07-29"]
[5434,670033,"   (IETF) CT1 part of Updating IMS to conform to RFC 6665 (draft-ietf-sipcore-refer-clarifications)","UP6665",2,"Rel-12","C1-IETF","2015-03-13","2015-03-13",1,"CP-130717",null,"BlackBerry","Andrew Allen (aallen@blackberry.com)","Added as per CT chair indications on 12th March 2015, no WID, no end date; 9/4/21: RFC 7647 added;","draft-ietf-sipcore-refer-clarification; RFC 7647",67,34,null,null,"2015-03-13","2021-04-09"]
[{"$f":"A5436+1","v":5436},670035,"   (IETF) CT1 part of Updating IMS to conform to RFC 6665 (draft-roach-sipcore-6665-clarifications)","UP6665",2,"Rel-12","C1-IETF","2015-03-13","2015-03-13",1,"CP-130717",null,"BlackBerry","Andrew Allen (aallen@blackberry.com)","Added as per CT chair indications on 12th March 2015, no WID, no end date¦14/09/15: 50%->100","draft-roach-sipcore-6665-clarification",67,34,null,null,"2015-03-13","2015-09-14"]
[5439,620204,"   CT3 part of IMS Operator Determined Call Barring enhancements","eIODB",2,"Rel-12","C3","2013-12-09","2014-09-11",1,"CP-130711","-","Ericsson","Jorgen.Axell@ericsson.com","CP#65 completed",29.164999999999999,62,32,null,null,"2013-11-18","2014-08-01"]
[5444,630005,"Transfer of ETSI business trunking specifications","IMS_Corp2",1,"Rel-12","C1,S1","2014-03-05","2014-12-09",1,"SP-140170","-","Alcatel-Lucent","keith.drage@alcatel-lucent.com, Youssef Chadli","Rel-12 enhancements to business trunking (BusTI). ETSI E2NA(14)000019 asked 3GPP to take responsibility of business communications over IMS: TS 181 019, TS 182 023, TS 182 024, TS 182 025, TR 183 060","-",63,32,null,null,"2014-01-29","2014-03-07"]
[5447,630008,"Support of ALT-C attribute","ALTC",1,"Rel-12","C4,C1,C3","2014-03-10","2014-12-09",1,"CP-140191","-","Orange","lionel.morand@orange.com","SA2 TS 23.228 requires UEs supporting IPv4, IPv6 or both IPv4 and IPv6 IP address formats shall be supported by IMS. Specify procedures to support altc SDP attribute within IMS for terminating communications destined to an enterprise network.","-",63,32,null,null,"2014-01-29","2014-03-03"]
[5448,630108,"   CT4 part of Support of ALT-C attribute","ALTC",2,"Rel-12","C4","2014-03-10","2014-12-09",1,"CP-140191","CP-140485","Orange","lionel.morand@orange.com","CP#65 completion 09/14=>12/14. Exception in CP-140485. Dec.14: 0->100","23.334; 29.238; 29.334",63,32,null,null,"2014-01-29","2014-12-04"]
[5452,640103,"   CT4 part of Diameter Overload Control Mechanisms","DOCME",2,"Rel-12","C4","2014-06-13","2014-12-09",1,"CP-140273","CP-140486","Orange","lionel.morand@orange.com","CP#65 completion 09/14=>12/14. Exception in CP-140486. Dec.14: 70->100","29.228; 29.229; 29.272; 29.273; 29.328; 29.329; 29.336; 29.337; 29.344; 29.345",64,33,null,null,"2014-05-25","2014-12-04"]
[5455,640104,"   CT1 part of Impacts of RFC7044 for introduction of the new History-Info header field","HISTORY_CT",2,"Rel-12","C1","2014-06-13","2014-12-09",1,"CP-140285","CP-140609","Deutsche Telekom","Roland Jesske (r.jesske@telekom.de)","CP#65 completion 09/14=>12/14. Exception in CP-140609. Dec.14: 85->100","24.229; 24.259; 24.604",64,33,null,null,"2014-04-07","2014-12-04"]
[5461,640008,"Unstructured Supplementary Service Data (USSD) method selection (Stage 3)","USSD_MS",1,"Rel-12","C1","2014-06-11","2014-06-13",1,"CP-140450","-","Ericsson","ivo.sedlacek@ericsson.com","CP#64 approved WID & completed. Related to R11 USSD simulation service in IMS (delivery of UE originating USSD request using IMS, I.e. introduce 2nd method for delivery of UE originating USSD request to network (additional to USSD using CS domain)","24.173; 24.390; New 24.391",64,33,null,null,"2014-04-07","2014-06-12"]
[5463,640011,"Overload Control for PCC based Diameter applications","DOCME-PCC",1,"Rel-12","C3,IETF","2014-06-13","2014-12-09",1,"CP-140405","-","Huawei","Xia Haitao (xiahaitao@huawei.com)","Triggered by TR 29.809 Study on Diameter overload control mechanism (FS_DOCME)","-",64,33,null,null,"2014-06-10","2014-06-16"]
[5466,650004,"Network Initiated USSD Simulation Services in IMS","USSI-NET",1,"Rel-12","C1","2014-09-12","2014-12-09",1,"CP-140625","CP-140610","AT&T","Martin Dolly (md3135@att.com)","CP#65 exception in CP-140610. Dec.14: 75->100",24.39,65,33,null,null,"2014-07-28","2014-12-04"]
[5471,570002,"Downlink Multi Carrier GERAN","DMCG",1,"Rel-12","G2,G1,C1,G3new","2012-09-10","2015-03-13",0.91,"GP-140190","-","Ericsson","paul.schliwa-bertling@ericsson.com","Linked to Rel-7 Downlink Dual Carrier UID_50579 (Previous work on multiple carriers on the downlink was limited to two). Ref: TR 45.912 Feasibility study for evolved GERAN, TS 43.064 GPRS Stage 2","GERAN",55,29,null,null,"2012-09-03","2014-03-01"]
[5474,570302,"   Test part: Downlink Multi Carrier GERAN","DMCG-MStest",2,"Rel-12","G3new","2012-09-10","2015-03-13",0.8,"GP-120930","-","ST-Ericsson","hakan.e.grunditz@stericsson.com","GP#63 completion 08/14=>11/14. Dec.14: 35->80%, CD:11/14->03/15","51.010-1; 51.010-2",55,29,null,null,"2012-09-03","2014-12-03"]
[5475,590033,"Mobile Station Receive Diversity (MSRD) for Voice Services over Adaptive Multi-user channels on One Slot (VAMOS)","MSRD_VAMOS",1,"Rel-12","G1,G2,C1,G3new","2013-03-01","2014-11-21",1,"GP-130849","GP-140579","Nokia Networks, Microsoft","Khairul Hasan (Nokia Networks), Markku Tarkiainen (Nokia=>Microsoft)","GP#63 completion 08/14=>11/14. Exception in GP-140579. Linked to Rel-7 Mobile Station Receive Diversity (DARP Phase II) UID_50569, Rel-9 Voice Services over Adaptive Multiuser channels on One Slot (VAMOS) UID_420002","GERAN",57,30,null,null,"2013-03-04","2014-08-29"]
[5479,620014,"New Training Sequence Codes (TSC) for GERAN","NewToN",1,"Rel-12","G1,G2,C1","2013-11-22","2014-12-09",0.93,"GP-131139","GP-140542","Ericsson","Mårten Sundberg","GP#63 completion 08/14=>11/14. Exception in GP-140542. GP#60 approved WID. Triggered by GP-131041, GP#40 GP-081949 (WID VAMOS). Linked to Rel-9 VAMOS (Previous work where new TSCs were defined for GMSK modulation) UID_420002","GERAN",60,32,null,null,"2013-11-22","2014-05-27"]
[5484,550116,"   Perf. Part: Verification of radiated multi-antenna reception performance of UEs in LTE/UMTS","HSPA_LTE_measRP_MIMO-Perf",2,"Rel-12","R4","2012-03-05","2013-12-06",1,"RP-120368","RP-131507","Vodafone","luis.anaya@vodafone.com","RP#62 completed. Rx diversity (defined as Rel-6 HSDPA RAN4 enhanced type 1 req.) & MIMO (defined as Rel-7 HSDPA MIMO for HSPA). Rx diversity & MIMO (defined as part of Rel-8 basic LTE WI)","new 37.977",55,28,null,null,"2012-02-23","2013-08-30"]
[5487,590019,"Support for BeiDou Navigation Satellite System (BDS) for UTRA and LTE","LCS_BDS",1,"Rel-12","R2,R3,R4,R5","2013-03-04","2015-06-15",1,"RP-130416","-","CATR","Ying Du (duying1@catr.cn)","BeiDou = Chinese Navigation Satellite System. Location Services (LCS) TS 22.071 Stage 1, TS 23.271 Stage 2","UTRA; LTE",59,30,null,null,"2013-02-26","2013-03-05"]
[5490,590319,"   Core part: Support for BeiDou Navigation Satellite System (BDS) for LTE","LCS_BDS-LTE-Core",2,"Rel-12","R2","2013-03-04","2013-12-06",1,"RP-130416","RP-131525","CATR","Ying Du (duying1@catr.cn)","RP#62 completed","36.305; 36.355",59,30,null,null,"2013-02-26","2013-11-29"]
[5493,620011,"Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN","LCS_BDS_GERAN",1,"Rel-12","G2,G1,G3new","2013-11-22","2015-03-13",0.93,"GP-140211","-","ZTE","Wang Xinhui (wangxinhui@zte.com.cn)","GP#60 approved WID. Based on the same framework used in Rel-8 Support for Additional Navigation Satellite Systems (ANSS) for LCS UID_38001","GERAN",60,32,null,null,"2013-11-22","2014-03-01"]
[5498,600019,"Deleted - New Base Station specification structure","BSspec_struc",1,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-130851","-","Ericsson","johan.skold@ericsson.com","Triggered by Rel-12 TR 37.810 Study on Base Station specification structure (FS_BSspec_struc)","UTRA; LTE; MSR",60,31,"RP-62","PCG-32","2013-06-17","2013-06-17"]
[5501,600021,"L-band for Supplemental Downlink in E-UTRA and UTRA","LTE_UTRA_SDL_BandL",1,"Rel-12","R4,R2,R3","2013-06-17","2015-12-15",1,"RP-140092","-","Orange","olfa.benhaddada@orange.com","ECC(12)052 CEPT decision to harmonize 1452-1492 MHz (L-band) for mobile communications Supplemental Downlink (SDL) => standardize L-band and corresponding E-UTRA and UTRA requirements for SDL operation in Region 1","UTRA; LTE",60,31,null,null,"2013-06-17","2013-12-07"]
[5502,600121,"   Core part: L-band for Supplemental Downlink in E-UTRA and UTRA","LTE_UTRA_SDL_BandL-Core",2,"Rel-12","R4,R2,R3","2014-02-13","2014-06-13",1,"RP-140092","RP-140633","Orange","olfa.benhaddada@orange.com","RP#64 completed. RP#65 forgotten TR 37.814 v100 for 1-step Approval","25.101; 25.104; 25.113; 25.133; 25.307; 25.327; 25.461; 25.466; 34.124; 36.101; 36.104; 36.113; 36.124; 36.133; 36.307; 36.331; 37.104; 37.113; new 37.814",60,31,null,null,"2013-06-17","2014-09-15"]
[5506,610103,"   Stage 2 for LTE-HRPD (High Rate Packet Data in 3GPP2) inter-RAT SON","LTE_HRPD_SON",2,"Rel-12","S2","2013-09-11","2013-12-11",1,"-","-","Huawei","Huan Li (ivy.lihuan@huawei.com)","SP#62 completed",23.402000000000001,61,31,null,null,"2013-08-15","2013-11-28"]
[5511,620142,"   Core part: Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA","LTE_UTRA_IncMon-Core",2,"Rel-12","R4,R2","2013-12-15","2014-12-15",1,"RP-132061","RP-141787","Ericsson","christopher.callender@ericsson.com","¦CD:Thu 18/12/14->Mon 15/12/14¦WID: RP-141966->RP-142235¦Stat Rep: RP-141600->RP-141787","25.133; 25.331; 36.133",62,32,null,null,"2013-12-07","2015-01-12"]
[5514,620048,"WLAN/3GPP Radio Interworking","UTRA_LTE_WLAN_interw",1,"Rel-12","R2,S2,C1,C4","2013-12-06","2014-12-09",1,"RP-140981","-","Intel","sasha.sirotkin@intel.com","Triggered by Rel-12 TR 37.834 Study on WLAN/3GPP Radio Interworking (FS_UTRA_LTE_WLAN_interw)","UTRA; LTE",62,32,null,null,"2013-12-09","2013-12-09"]
[5517,640006,"   CT aspects of WLAN/3GPP Radio Interworking (Stage 2/3)","UTRA_LTE_WLAN_interw-CT",2,"Rel-12","C1,C4","2014-09-09","2014-12-09",1,"CP-140623","-","Alcatel-Lucent","jennifer.liu@alcatel-lucent.com","CP#65 revised WID CP-140287=>CP-140623 (added CT4 part)","Stage 2/3",64,33,null,null,"2014-04-07","2014-09-09"]
[5520,660075,"UE Conformance Test Aspects – WLAN/3GPP Radio Interworking","UTRA_LTE_WLAN_interw-UEConTest",1,"Rel-12","R5","2014-12-15","2016-03-15",1,"RP-151270","RP-151264","Intel","Intel","Rel13->Rel-12¦Moved at appropriate place 1st Apr 15: Compl:0%->5% 1st Apr 15: Stat Rep: ->RP-150098 03/07/15: Compl:5%->20% 03/07/15: Stat Rep: RP-150098->RP-150929 29/09/15: Compl:20%->60% 29/09/15: WID: RP-141879->RP-151270 29/09/15: Stat Rep: RP-15",null,66,34,null,null,"2015-01-12","2016-03-22"]
[5525,530029,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25","LTE_CA_NC_B25",2,"Rel-12","R4","2011-09-19","2013-06-14",1,"RP-130179","-","Sprint","George.Cummings@sprint.com","Intra-band NC","LTE",53,27,null,null,"2011-09-15","2013-06-07"]
[5529,550110,"      Deleted - Core part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5 with 2UL","LTE_CA_B3_B5_2UL-Core",3,"Rel-12","R4","2012-03-05","2013-03-01",1,"RP-120867","RP-130098","SK Telecom","Seungpyo Hong","RP#59 stopped (covered by new WI LTE_CA_2UL-A4)","36.101; 36.104; 36.133; 36.307; new generic 36.851",55,28,"RP-59","PCG-30","2012-02-23","2013-07-29"]
[5530,550210,"      Deleted - Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 5 with 2UL","LTE_CA_B3_B5_2UL-Perf",3,"Rel-12","R4","2012-03-12","2013-03-01",1,"RP-120867","RP-130099","SK Telecom","Seungpyo Hong","RP#59 stopped (covered by new WI LTE_CA_2UL-A4)","36.133; 36.141",55,28,"RP-59","PCG-30","2012-02-23","2013-07-29"]
[5533,550111,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 3","LTE_CA_NC_B3-Core",3,"Rel-12","R4","2012-03-05","2013-12-06",1,"RP-131359","RP-131573","SK Telecom","haesung.park@sk.com","RP#62 completed","36.101; 36.104; 36.133; new 36.833-2-03",55,28,null,null,"2012-02-23","2013-12-02"]
[5538,560016,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4","LTE_CA_NC_B4",2,"Rel-12","R4","2012-06-18","2013-09-06",1,"RP-131135","-","T-Mobile USA","nelson.ueng@t-mobile.com","Intra-band NC","LTE",56,29,null,null,"2012-06-13","2013-06-12"]
[5541,560017,"   LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4","LTE_CA_B2_B4",2,"Rel-12","R4","2012-06-18","2013-09-06",1,"RP-130175","-","T-Mobile USA","nelson.ueng@t-mobile.com","Inter-band 1 UL","LTE",56,29,null,null,"2012-06-13","2012-09-07"]
[5544,570012,"   LTE Advanced inter-band Carrier Aggregation of Band 23 and Band 29","LTE_CA_B23_B29",2,"Rel-12","R4","2012-09-12","2013-06-14",1,"RP-130170","-","DISH Network","mariam.sorond@dish.com, johny.kim@dish.com","Inter-band 1 UL","LTE",57,29,null,null,"2012-09-03","2012-09-03"]
[5547,570013,"   LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 26","LTE_CA_B3_B26",2,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-130658","-","KT","Chungwoo HWANG (cwhwang@kt.com)","Inter-band 1 UL","LTE",57,29,null,null,"2012-09-03","2013-06-07"]
[5552,570214,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 19","LTE_CA_B3_B19-Perf",3,"Rel-12","R4","2012-09-13","2013-06-14",1,"RP-130198","RP-130526","NTT DOCOMO","Kei ANDO","RP#60 completed","36.141; 36.307",57,29,null,null,"2012-09-03","2013-06-08"]
[5556,570016,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 3","LTE_CA_C_B3",2,"Rel-12","R4","2012-09-11","2013-09-06",1,"RP-131184","-","China Unicom","Fei CUI (cuifei1@chinaunicom.cn)","Intra-band NC","LTE",57,29,null,null,"2012-09-03","2013-08-29"]
[5557,570116,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 3","LTE_CA_C_B3-Core",3,"Rel-12","R4","2012-09-11","2013-09-06",1,"RP-131184","RP-131029","China Unicom","Fei CUI (cuifei1@chinaunicom.cn)","RP#61 completed. Updated WID RP-130294=>RP-131184 (impacted specs)","36.101; 36.104; 36.133; new 36.833-1-03",57,29,null,null,"2012-09-03","2013-09-04"]
[5560,570118,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 8","LTE_CA_B1_B8-Core",3,"Rel-12","R4","2012-02-02","2013-06-14",1,"RP-130181","RP-130515","Softbank Mobile","Kenichi Kihara","RP#60 completed","36.101; 36.104; new generic 36.851",57,29,null,null,"2012-09-03","2013-06-04"]
[5565,580032,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 26","LTE_CA_B1_B26",2,"Rel-12","R4","2012-12-07","2013-09-06",1,"RP-130668","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band 1UL/2DL","LTE",58,30,null,null,"2012-12-10","2012-12-10"]
[5568,580033,"   LTE Advanced inter-band Carrier Aggregation of Band 39 and Band 41","LTE_CA_B39_B41",2,"Rel-12","R4","2012-12-10","2014-03-06",1,"RP-130292","RP-140428","China Mobile","Pan Qun (panqun@chinamobile.com)","Inter-band 2DL","LTE",58,30,null,null,"2012-12-10","2014-03-05"]
[5570,580233,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 39 and Band 41","LTE_CA_B39_B41-Perf",3,"Rel-12","R4","2012-12-14","2014-03-06",1,"RP-130292","RP-140428","China Mobile","Pan Qun (panqun@chinamobile.com)","RP#63 completed","36.133; 36.141",58,30,null,null,"2012-12-10","2014-03-05"]
[5576,580235,"      Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 7","LTE_CA_NC_B7-Perf",3,"Rel-12","R4","2012-12-14","2013-12-06",1,"RP-130813","RP-131576","Ericsson","christian.bergljung@ericsson.com","RP#62 completed","36.141; 36.307",58,30,null,null,"2012-12-10","2013-12-02"]
[5579,580236,"      Perf part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 27","LTE_CA_C_B27-Perf",3,"Rel-12","R4","2012-12-14","2014-06-13",1,"RP-131679","RP-140569","NII Holdings","bill.shvodian@nii.com","RP#64 completed. TR 36.833-1-27v200 for Approval","36.101; 36.133; 36.141; 36.307; new 36.833-1-27",58,30,null,null,"2012-12-10","2014-06-12"]
[5583,590024,"   LTE Advanced inter-band Carrier Aggregation of Band 19 and Band 21","LTE_CA_B19_B21",2,"Rel-12","R4","2013-03-04","2013-06-14",1,"RP-130197","-","NTT DOCOMO","Kei ANDO","Inter-band 1 UL","LTE",59,30,null,null,"2013-02-26","2013-02-26"]
[5584,590124,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 19 and Band 21","LTE_CA_B19_B21-Core",3,"Rel-12","R4","2013-03-04","2013-06-14",1,"RP-130197","RP-130533","NTT DOCOMO","Kei ANDO","RP#60 completed","36.101; 36.104; 36.133; new generic 36.851",59,30,null,null,"2013-02-26","2013-06-08"]
[5587,590125,"      Deleted - Core part:LTE Advanced inter-band Carrier Aggregation of Band 8 and Band 26","LTE_CA_B8_B26-Core",3,"Rel-12","R4","2013-03-04","2013-12-06",1,"RP-130201","RP-131549","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#62 stopped (at 20%)","36.101; 36.104; 36.133; new generic 36.851",59,30,"RP-62","PCG-32","2013-02-26","2013-12-02"]
[5592,590028,"   LTE Advanced dual uplink inter-band Carrier Aggregation Class A2","LTE_CA_2UL-A2",2,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-130327","-","Qualcomm","Gene Fong (gfong@qti.qualcomm.com)","Inter-band CA 2UL","LTE",59,30,null,null,"2013-02-26","2014-09-09"]
[5595,590023,"   LTE Advanced dual uplink inter-band Carrier Aggregation Class A3","LTE_CA_2UL-A3",2,"Rel-12","R4","2013-03-04","2014-12-15",1,"RP-140853","-","Ericsson","christian.bergljung@ericsson.com ","Inter-band CA 2UL","LTE",59,30,null,null,"2013-02-26","2014-09-09"]
[5597,590223,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A3","LTE_CA_2UL-A3-Perf",3,"Rel-12","R4","2013-03-13","2014-12-15",1,"RP-140853","RP-141732","Ericsson","christian.bergljung@ericsson.com ","¦Stat Rep: RP-141084->RP-141732","36.141; 36.307",59,30,null,null,"2013-02-26","2015-01-12"]
[5603,590226,"      Perf. part:LTE Advanced dual uplink inter-band Carrier Aggregation Class A5","LTE_CA_2UL-A5-Perf",3,"Rel-12","R4","2013-03-13","2014-12-15",1,"RP-141195","RP-141732","NTT DOCOMO","kei.andou.ye@nttdocomo.com","¦Stat Rep: RP-141084->RP-141732","36.141; 36.307",59,30,null,null,"2013-02-26","2015-01-12"]
[5606,590227,"      Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 39","LTE_CA_C_B39-Perf",3,"Rel-12","R4","2013-03-07","2014-03-06",1,"RP-131171","RP-140428","China Mobile","Li Nan (linan@chinamobile.com)","RP#63 completed","36.141; 36.307",59,30,null,null,"2013-02-26","2014-03-05"]
[5610,600123,"      Deleted - Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 2UL","LTE_CA_NC_B41_2UL-Core",3,"Rel-12","R4","2013-06-19","2014-03-06",1,"RP-131237","RP-140428","Sprint","yang.xu@clearwire.com","RP#63 stopped (5% complete). Reason: Market conditions have eliminated the need for this feature, at least for the foreseeable future","36.101; 36.104; 36.133; new 36.833-3-41",60,31,"RP-63","PCG-32","2013-06-17","2014-03-05"]
[5611,600223,"      Deleted - Perf. part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 2UL","LTE_CA_NC_B41_2UL-Perf",3,"Rel-12","R4","2013-06-20","2014-03-06",1,"RP-131237","RP-140428","Sprint","yang.xu@clearwire.com","RP#63 stopped (0% complete). ","36.101; 36.104; 36.133; 36.141; 36.307",60,31,"RP-63","PCG-32","2013-06-17","2014-03-05"]
[5615,600025,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 23","LTE_CA_C_B23",2,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131265","-","Dish Network","mariam.sorond@dish.com, johny.kim@dish.com","Intra-band C CA","LTE",60,31,null,null,"2013-06-17","2013-06-17"]
[5619,600126,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 23","LTE_CA_NC_B23-Core",3,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131700","RP-131577","Dish Network","mariam.sorond@dish.com, johny.kim@dish.com","RP#62 completed","36.101; 36.104; 36.133; new 36.833-2-23",60,31,null,null,"2013-06-17","2013-12-19"]
[5622,600128,"      Core part:LTE Advanced inter-band Carrier Aggregation of Band 12 and Band 25","LTE_CA_B12_B25-Core",3,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131159","RP-131705","US Cellular","sebastian.thalanany@uscellular.com ","RP#62 completed","36.101; 36.104; 36.133; new generic 36.851",60,31,null,null,"2013-06-05","2013-12-02"]
[5624,600029,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 18 - Additional bandwidth combination set","LTE_CA_B1_B18_BWset",2,"Rel-12","R4","2013-06-18","2013-09-06",1,"RP-130669","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band 1UL/2DL","LTE",60,31,null,null,"2013-06-05","2013-06-17"]
[5630,600031,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 30","LTE_CA_B2_B5_B30",2,"Rel-12","R4","2013-06-18","2014-09-12",1,"RP-131696","-","AT&T","marc.grant@att.com","Inter-band 3DL","LTE",60,31,null,null,"2013-06-17","2014-09-08"]
[5633,600032,"   Deleted -LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 17 and Band 30","LTE_CA_B2_B17_B30",2,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131130","-","AT&T","marc.grant@att.com","Inter-band 3DL","LTE",60,31,"RP-62","PCG-32","2013-06-17","2014-03-05"]
[5637,600133,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 29 and Band 30","LTE_CA_B2_B29_B30-Core",3,"Rel-12","R4","2013-06-19","2014-09-12",1,"RP-141212","RP-141084","AT&T","marc.grant@att.com","RP#65 completed. Updated WID RP-131697=>RP-141212","36.101; 36.104; 36.133; 36.141; 36.307; new generic 36.853 (3 Band CA with 1UL)",60,31,null,null,"2013-06-17","2014-09-08"]
[5638,600233,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 29 and Band 30","LTE_CA_B2_B29_B30-Perf",3,"Rel-12","R4","2013-06-19","2014-09-12",1,"RP-141212","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101; 36.104; 36.133; 36.141; 36.307",60,31,null,null,"2013-06-17","2014-09-08"]
[5642,600035,"   Deleted -LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 17 and Band 30","LTE_CA_B4_B17_B30",2,"Rel-12","R4","2013-06-18","2013-12-06",1,"RP-131133","-","AT&T","marc.grant@att.com","Inter-band 3DL","LTE",60,31,"RP-62","PCG-32","2013-06-17","2013-06-17"]
[5646,600136,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 29 and Band 30","LTE_CA_B4_B29_B30-Core",3,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141215","RP-141084","AT&T","marc.grant@att.com","RP#65 completed. Updated WID RP-131699=>RP- 141215","36.101; 36.104; 36.133; 36.141; 36.307; new generic 36.853 (3 Band CA with 1UL)",60,31,null,null,"2013-06-17","2014-09-08"]
[5649,600137,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 13","LTE_CA_B2_B4_B13-Core",3,"Rel-12","R4","2013-06-14","2014-09-12",1,"RP-141434","RP-141084","Verizon","zheng.zhao@verizonwireless.com","RP#65 completed. Updated RP-131684=>RP-141434","36.101; 36.104; 36.133; new generic 36.853 (3 Band CA with 1UL)",60,31,null,null,"2013-06-17","2014-09-21"]
[5651,600038,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 13","LTE_CA_B2_B2_B13",2,"Rel-12","R4","2013-06-18","2014-09-12",1,"RP-141435","-","Verizon","zheng.zhao@verizonwireless.com","Inter-band CA 3DL","LTE",60,31,null,null,"2013-06-17","2014-09-21"]
[5657,610017,"   LTE Advanced inter-band Carrier Aggregation of Band 7 and Band 28","LTE_CA_B7_B28",2,"Rel-12","R4","2013-09-09","2013-12-06",1,"RP-131307","-","Huawei","Liehai Liu (liuliehai@huawei.com)","Inter-band 1UL/2DL","LTE",61,31,null,null,"2013-09-07","2013-12-02"]
[5660,610018,"   LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 25","LTE_CA_B5_B25",2,"Rel-12","R4","2013-09-09","2013-12-06",1,"RP-131343","-","U.S. Cellular","sebastian.thalanany@uscellular.com ","Inter-band 1UL/2DL","LTE",61,31,null,null,"2013-09-07","2013-12-02"]
[5662,610218,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 25","LTE_CA_B5_B25-Perf",3,"Rel-12","R4","2013-09-09","2013-12-06",1,"RP-131343","RP-131705","U.S. Cellular","sebastian.thalanany@uscellular.com ","RP#62 completed","36.141; 36.307",61,31,null,null,"2013-09-07","2013-12-02"]
[5665,610219,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 11","LTE_CA_B1_B11-Perf",3,"Rel-12","R4","2013-09-09","2014-06-13",1,"RP-131354","RP-140569","SoftBank Mobile","kenichi.kihara@g.softbank.co.jp","RP#64 completed","36.141; 36.307",61,31,null,null,"2013-09-07","2014-06-20"]
[5669,610021,"   LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 7","LTE_CA_B5_B7",2,"Rel-12","R4","2013-09-09","2013-12-02",1,"RP-131365","-","LG Uplus","Yeonsang KOO (yskoo@lguplus.co.kr)","Inter-band 1UL/2DL","LTE",61,31,null,null,"2013-09-07","2013-12-02"]
[5673,610122,"      Core part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 41 for 3DL","LTE_CA_C_B41_3DL-Core",3,"Rel-12","R4","2013-09-09","2014-09-12",1,"RP-140100","RP-141084","Alcatel-Lucent","man-hung.ng@alcatel-lucent.com","RP#65 completed","36.101; 36.104; 36.133; 36.307; New 36.833-5-41",61,31,null,null,"2013-09-07","2014-09-08"]
[5676,610123,"      Core part:LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 2","LTE_CA_NC_B2-Core",3,"Rel-12","R4","2013-09-09","2014-06-13",1,"RP-131366","RP-140569","Ericsson","imadur.rahman@ericsson.com","RP#64 completed. TR 36.833-2-02v100 for 1-step Approval","36.101; 36.104; 36.133; New 36.833-2-02",61,31,null,null,"2013-09-07","2014-06-12"]
[5678,620018,"   LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 3","LTE_CA_B1_B3",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-132022","-","China Unicom","Hao Chen (chenhao49@chinaunicom.cn)","Inter-band CA 2DL","LTE",62,32,null,null,"2013-12-07","2013-12-07"]
[5684,620020,"   LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4 - Additional bandwidth combination set","LTE_CA_B2_B4_BWset",2,"Rel-12","R4","2013-12-09","2014-03-06",1,"RP-131656","-","T-Mobile USA","nelson.ueng@t-mobile.com","Inter-band 2DL","LTE",62,32,null,null,"2013-12-07","2014-03-04"]
[5687,620021,"   LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 27","LTE_CA_B4_B27",2,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140142","-","NII Holdings","bill.shvodian@nii.com","Inter-band CA 2DL","LTE",62,32,null,null,"2013-12-07","2014-03-13"]
[5689,620221,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 27","LTE_CA_B4_B27-Perf",3,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140142","RP-140569","NII Holdings","bill.shvodian@nii.com","RP#64 completed","36.141; 36.307",62,32,null,null,"2013-12-07","2014-06-20"]
[{"$f":"A5692+1","v":5692},620222,"      Perf. part:LTE Advanced inter-band Carrier Aggregation of Band 3 and Band 27","LTE_CA_B3_B27-Perf",3,"Rel-12","R4","2013-12-09","2014-03-06",1,"RP-140119","RP-140428","KT","Chungwoo HWANG (cwhwang@kt.com)","RP#63 completed. Updated WID RP-131752=>RP-140119","36.101; 36.104; 36.133; 36.141",62,32,null,null,"2013-12-07","2014-03-13"]
[5696,620024,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 8","LTE_CA_B1_B3_B8",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141654","-","KT","Ilwhan Kim (ilwhan.kim@kt.com)","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-22"]
[5700,620125,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 5 and Band 7","LTE_CA_B1_B5_B7-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141462","RP-141084","LG Uplus","Yeonsang KOO (yskoo@lguplus.co.kr)","RP#65 completed. Updated WID RP-140209=>RP-141462","36.101; 36.104; 36.133; new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-22"]
[5705,620027,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 12","LTE_CA_B2_B4_B12",2,"Rel-12","R4","2013-12-09","2014-12-11",1,"RP-140189","-","U.S. Cellular","sebastian.thalanany@uscellular.com ","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-09"]
[5708,620028,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 5 and Band 12","LTE_CA_B2_B5_B12",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-140190","-","U.S. Cellular","sebastian.thalanany@uscellular.com ","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5711,620029,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 12","LTE_CA_B2_B12_B12",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-131654","-","AT&T","marc.grant@att.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5714,620030,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 30","LTE_CA_B2_B12_B30",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141211","-","AT&T","marc.grant@att.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5716,620230,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 12 and Band 30","LTE_CA_B2_B12_B30-Perf",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141211","RP-141084","AT&T","marc.grant@att.com","RP#65 completed","36.101; 36.104; 36.133; 36.141; 36.307",62,32,null,null,"2013-12-07","2014-09-08"]
[5719,620231,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 3, Band 7 and Band 20","LTE_CA_B3_B7_B20-Perf",3,"Rel-12","R4","2013-12-10","2014-09-12",1,"RP-141224","RP-141084","Vodafone","luis.anaya@vodafone.com","RP#65 completed","36.101; 36.133; 36.141; 36.307",62,32,null,null,"2013-12-07","2014-09-21"]
[5723,620034,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 12","LTE_CA_B4_B12_B12",2,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-131655","-","AT&T","marc.grant@att.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5727,620135,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 4, Band 12 and Band 30","LTE_CA_B4_B12_B30-Core",3,"Rel-12","R4","2013-12-09","2014-09-12",1,"RP-141214","RP-141084","AT&T","marc.grant@att.com","RP#65 completed. Updated WID RP-131653=>RP-141214","36.101; 36.104; 36.133; 36.141; 36.307; new generic 36.853 (3 Band CA with 1UL)",62,32,null,null,"2013-12-07","2014-09-08"]
[5732,620036,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 7 - Additional bandwidth combinations","LTE_CA_C_B7_BW",2,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-131810","-","Orange","Olfa BEN HADDADA","Intra-band contig. CA 2DL/2UL","LTE",62,32,null,null,"2013-12-07","2013-12-07"]
[5735,620038,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 3 DL","LTE_CA_NC_B41_3DL",2,"Rel-12","R4","2013-12-09","2015-03-13",1,"RP-140101","-","Sprint, Alcatel-Lucent","man-hung.ng@alcatel-lucent.com","Intra-band non-contig. CA 3DL","LTE",62,32,null,null,"2013-12-07","2014-09-08"]
[5738,620039,"   LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 42","LTE_CA_NC_B42",2,"Rel-12","R4","2013-12-09","2014-06-13",1,"RP-140671","-","Huawei","Liu Liehai (liuliehai@huawei.com)","Intra-band non-contig. CA 2DL","LTE",62,32,null,null,"2013-12-07","2014-03-13"]
[5741,620050,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 5","LTE_CA_B1_B3_B5",2,"Rel-12","R4","2013-12-06","2014-09-12",1,"RP-141454","-","SK Telecom","haesung.park@sk.com","Inter-band CA 3DL","LTE",62,32,null,null,"2013-12-09","2014-09-21"]
[5743,620250,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation(3DL/1UL) for Band 1, Band 3 and Band 5","LTE_CA_B1_B3_B5-Perf",3,"Rel-12","R4","2013-12-06","2014-09-12",1,"RP-141454","RP-141084","SK Telecom","haesung.park@sk.com","RP#65 completed. Updated WID RP-132121=>RP-141454","36.141; 36.307",62,32,null,null,"2013-12-09","2014-09-21"]
[5746,620251,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 1, Band 3 and Band 20","LTE_CA_B1_B3_B20-Perf",3,"Rel-12","R4","2013-12-10","2014-09-12",1,"RP-141222","RP-141084","Vodafone","luis.anaya@vodafone.com","RP#65 completed","36.101; 36.133; 36.141; 36.307",62,32,null,null,"2013-12-09","2014-09-21"]
[5751,620153,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 8 and Band 20","LTE_CA_B7_B8_B20-Core",3,"Rel-12","R4","2013-12-09","2014-12-15",1,"RP-132080","RP-141732","Vodafone","luis.anaya@vodafone.com","CD:Thu 11/12/14->Mon 15/12/14¦Compl:85%->100%¦Stat Rep: RP-141084->RP-141732","36.101; 36.104; 36.133; new generic 36.853 (3 Band CA with 1UL); 36.851 (2 Band CA with 1UL)",62,32,null,null,"2013-12-09","2015-01-12"]
[5754,630122,"      Core part: Additional bandwidth combinations for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29","LTE_DL_FDD700_B29_BWset-Core",3,"Rel-12","R4","2014-03-03","2014-03-06",1,"RP-140084","RP-140428","AT&T","marc.grant@att.com","RP#63 approved WI (no Perf. Part) & completed. Rel-10 and Rel-11 versions of 36.307 affected","36.101; 36.307",63,32,null,null,"2014-03-10","2014-03-12"]
[5759,630025,"   Additional bandwidth combinations for LTE Advanced inter-band Carrier Aggregation to support 3DL fallback","LTE_CA_3DL_FB_BW",2,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140454","-","Qualcomm","Fong Gene (gfong@qti.qualcomm.com)","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-03-10"]
[5762,630126,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 7 and Band 7","LTE_CA_B3_B7_B7-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141196","RP-141084","Nokia Networks","iwajlo.angelow@nsn.com","RP#65 completed. Updated WID RP-140095=>RP-141196. Mar15: acronym reverted to LTE_CA_B3_B7_B7-Core_","36.101; 36.104; 36.133; new generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2015-03-10"]
[5765,630127,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 19 and Band 21","LTE_CA_B1_B19_B21-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141193","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed. Updated WID RP-140106=>RP-141193","36.101; 36.104; 36.133; new generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2014-09-21"]
[5768,630128,"      Core part: LTE-Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 3 and Band 7","LTE_CA_B3_B3_B7-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-141126","RP-141084","TeliaSonera","Ralf.Schuh@TeliaSonera.com","RP#65 completed. Updated RP-140390=>RP-141126","36.101; 36.104; 36.133; new generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2014-09-08"]
[5770,630029,"   LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL","LTE_CA_C_B40_3DL",2,"Rel-12","R4","2014-03-06","2014-06-13",1,"RP-140948","-","China Mobile","Pan Qun (panqun@chinamobile.com)","Intra-band contig. CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-03-10"]
[5773,630035,"   Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 4 and Band 12","LTE_CA_B4_B12_BWset",2,"Rel-12","R4","2014-03-07","2014-09-12",1,"RP-141235","-","T-Mobile USA","nelson.ueng@t-mobile.com","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-09-21"]
[5778,630236,"      Perf. Part:LTE Advanced inter-band Carrier Aggregation of Band 41 and Band 42","LTE_CA_B41_B42-Perf",3,"Rel-12","R4","2014-03-07","2014-09-12",1,"RP-140450","RP-141084","Huawei","leo.liuye@huawei.com","RP#65 completed",36.140999999999998,63,32,null,null,"2014-03-10","2014-09-08"]
[5781,630237,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4, and Band 12","LTE_CA_B4_B4_B12-Perf",3,"Rel-12","R4","2014-03-07","2014-09-12",1,"RP-141709","RP-141084","T-Mobile USA","nelson.ueng@t-mobile.com","RP#65 completed","36.101; 36.104; 36.133; 36.141; 36.307",63,32,null,null,"2014-03-10","2014-09-22"]
[5786,630145,"      Core part: Additional bandwidth combinations for LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 25","LTE_CA_NC_B25_BWset-Core",3,"Rel-12","R4","2014-03-06","2014-09-12",1,"RP-140452","RP-141084","Huawei","Liu Liehai (liuliehai@huawei.com)","RP#65 completed","36.101; 36.307; 36.833-2-25",63,32,null,null,"2014-03-10","2014-09-08"]
[5789,640120,"      Core part: Additional bandwidth combination set 2 for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 4","LTE_CA_B2_B4_BWset2-Core",3,"Rel-12","R4","2014-06-15","2014-09-12",1,"RP-140599","RP-141084","T-Mobile USA","nelson.ueng@T-Mobile.com","Dec 14: Prev CD:Fri 12/09/14¦Prev %:100%, title changed. Mar 15: Acronym changed to LTE_CA_B2_B4_BWset2-Core_","36.101; 36.851",64,33,null,null,"2014-06-16","2015-03-10"]
[5791,640121,"      Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5","LTE_CA_B2_B5_Bwset-Core",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140642","RP-141732","AT&T","marc.grant@att.com","¦WID: RP-142043->RP-141803¦Stat Rep: RP-141084->RP-141732","36.101; 36.851",64,33,null,null,"2014-06-16","2015-01-12"]
[5794,640127,"      Perf. Part: E-UTRA UE demodulation/Channel State Information (CSI) performance requirements for multiple Carrier Aggregation configurations","LTE_CA_Mult-Perf",3,"Rel-12","R4","2014-06-16","2015-03-13",1,"RP-141304","RP-150188","China Mobile","Zhang Xiaoran (zhangxiaoran@chinamobile.com)","CD:Thu 12/03/15->Sun 15/03/15¦Compl:10%->90%¦Stat Rep: RP-141303->RP-141839 1st Apr 15: Compl:90%->100% 1st Apr 15: Stat Rep: RP-141839->RP-150188",36.100999999999999,64,33,null,null,"2014-06-16","2015-04-01"]
[5797,640228,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 3 and Band 19","LTE_CA_B1_B3_B19-Perf",3,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141004","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed","36.141; 36.307",64,33,null,null,"2014-06-16","2014-09-08"]
[5800,640229,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 19, Band 42 and Band 42","LTE_CA_B19_B42_B42-Perf",3,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141007","RP-141084","NTT DOCOMO","teruaki.toeda.zf@nttdocomo.com","RP#65 completed","36.141; 36.307",64,33,null,null,"2014-06-16","2014-09-08"]
[5805,640131,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 42 and Band 42","LTE_CA_B1_B42_B42-Core",3,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141006","RP-141084","NTT DOCOMO","ANDO Kei (kei.andou.ye@nttdocomo.com)","RP#65 completed","36.101; 36.104; 36.133; generic 36.853 (3 Band CA with 1UL)",64,33,null,null,"2014-06-16","2014-09-08"]
[5808,640135,"      Core part: Additional bandwidth combination set for LTE Advanced intra-band contiguous Carrier Aggregation in Band 40 for 3DL","LTE_CA_C_B40_3DL_BW-Core",3,"Rel-12","R4","2014-06-16","2014-09-12",1,"RP-141127","RP-141084","TeliaSonera","Ralf.Schuh@TeliaSonera.com","RP#65 completed. Updated WID RP-140950=>RP-141127",36.100999999999999,64,33,null,null,"2014-06-16","2014-09-08"]
[5813,630034,"   LTE Advanced inter-band Carrier Aggregation of Band 5 and Band 13","LTE_CA_B5_B13",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140169","-","Intel","xinrong.wang@intel.com ","Inter-band CA 2DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5816,630039,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 5","LTE_CA_B2_B2_B5",2,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140165","-","Intel","peiling.zhang@intel.com","Inter-band CA 3DL","LTE",63,32,null,null,"2014-03-10","2014-09-09"]
[5818,630239,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 2 and Band 5","LTE_CA_B2_B2_B5-Perf",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140165","RP-141732","Intel","peiling.zhang@intel.com","CD:Thu 12/03/15->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101; 36.133; 36.141; 36.307",63,32,null,null,"2014-03-10","2015-01-12"]
[5821,630240,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 4 and Band 5","LTE_CA_B4_B4_B5-Perf",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140166","RP-141732","Intel","peiling.zhang@intel.com","CD:Thu 12/03/15->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101; 36.133; 36.141; 36.307",63,32,null,null,"2014-03-10","2015-01-12"]
[5824,630241,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 5 and Band 13","LTE_CA_B2_B5_B13-Perf",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140167","RP-141732","Intel","xinrong.wang@intel.com ","CD:Thu 12/03/15->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101; 36.133; 36.141; 36.307",63,32,null,null,"2014-03-10","2015-01-12"]
[5827,630242,"      Perf. part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 5 and Band 13","LTE_CA_B4_B5_B13-Perf",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-140168","RP-141732","Intel","xinrong.wang@intel.com ","CD:Thu 12/03/15->Mon 15/12/14¦Compl:10%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101; 36.133; 36.141; 36.307",63,32,null,null,"2014-03-10","2015-01-12"]
[5832,630144,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 18 and Band 28","LTE_CA_B1_B18_B28-Core",3,"Rel-12","R4","2014-03-06","2014-12-15",1,"RP-141788","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","¦WID: RP-142043->RP-141788¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.101; 36.104; 36.133; generic 36.853 (3 Band CA with 1UL)",63,32,null,null,"2014-03-10","2015-01-12"]
[5836,640223,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 4, Band 7 and Band 12","LTE_CA_B4_B7_B12-Perf",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140661","RP-141732","Rogers Wireless","pavlo.nebesny@rci.rogers.com","CD:Thu 12/03/15->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.133; 36.141",64,33,null,null,"2014-06-16","2015-01-12"]
[5840,640026,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 41 and Band 41","LTE_CA_B39_B41_B41",2,"Rel-12","R4","2014-06-16","2014-12-15",1,"RP-140708","-","China Mobile","PAN Qun (panqun@chinamobile.com)","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[5843,640033,"   LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 41 and Band 41","LTE_CA_B1_B41_B41",2,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-140963","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Inter-band CA 3DL/1UL","LTE",64,33,null,null,"2014-06-16","2014-09-09"]
[5845,640233,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 1, Band 41 and Band 41","LTE_CA_B1_B41_B41-Perf",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-142297","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","Compl:100%->0%¦WID: RP-142043->RP-142297¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.141; 36.307",64,33,null,null,"2014-06-16","2015-01-12"]
[5848,640234,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 26, Band 41 and Band 41","LTE_CA_B26_B41_B41-Perf",3,"Rel-12","R4","2014-06-18","2014-12-15",1,"RP-142298","RP-141732","KDDI","Masaaki Obara (ms-obara@kddi.com)","Compl:100%->0%¦WID: RP-142043->RP-142298¦Stat Rep: RP-141084->RP-141732¦Release: Rel-13->Rel-12","36.141; 36.307",64,33,null,null,"2014-06-16","2015-01-12"]
[5851,650246,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 25, Band 41 and Band 41","LTE_CA_B25_B41_B41-Perf",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-142018","RP-141732","Alcatel-Lucent","Ng, Man Hung (man-hung.ng@alcatel-lucent.com)","¦WID: RP-142043->RP-142018¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12",36.140999999999998,65,33,null,null,"2014-06-16","2015-01-12"]
[5854,650248,"      Perf. Part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 39, Band 39 and Band 41","LTE_CA_B39_B39_B41-Perf",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-142302","RP-141732","China Mobile","PAN, Qun (panqun@chinamobile.com)","¦WID: RP-141288->RP-142302¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.141; 36.307",65,33,null,null,"2014-06-16","2015-01-12"]
[5859,650152,"      Core part:LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 2, Band 4 and Band 29","LTE_CA_B2_B4_B29-Core",3,"Rel-12","R4","2014-09-15","2014-12-15",1,"RP-141668","RP-141732","Huawei","SHAN Huiping (shanhuiping@huawei.com)","CD:Fri 11/12/15->Mon 15/12/14¦Compl:0%->100%¦Stat Rep: -->RP-141732¦Release: Rel-13->Rel-12","36.101; 36.104; 36.133; New 36.8xx",65,33,null,null,"2014-06-16","2015-01-12"]
[5863,510033,"Deleted - Carrier based HetNet ICIC for LTE","LTE_CA_HetNet_ICIC",1,"Rel-12","R3,R1,R2","2011-03-18","2013-06-14",1,"RP-121198","-","Nokia Siemens Networks","krzysztof.kordybach@nsn.com","RP#60 stopped. RP#58 on hold til June 2013","LTE",51,26,"RP-60","PCG-31","2011-03-14","2013-06-12"]
[5867,570217,"   Perf. Part: LTE in the US Wireless Communications Service (WCS) Band 30","LTE_WCS_band-Perf",2,"Rel-12","R4","2012-09-13","2013-06-14",1,"RP-130843","RP-130570","AT&T","marc.grant@att.com","RP#60 completed. Updated WID RP-121419=>RP-130843","36.101; 36.133; 36.141",57,29,null,null,"2012-09-03","2013-06-11"]
[5870,570119,"   Core part: Introduction of LTE 450 MHz band in Brazil","LTE450_Brazil-Core",2,"Rel-12","R4","2012-09-11","2013-06-14",1,"RP-121414","RP-130567","Huawei","Liehai Liu (liuliehai@huawei.com)","RP#60 completed. TR 36.840 v100 for 1-step Approval","36.101; 36.104; 36.113; 36.124; 36.133; 37.104; 37.113; 36.307; new 36.840",57,29,null,null,"2012-09-03","2013-06-05"]
[5872,600005,"   Test part: Introduction of LTE 450 MHz band in Brazil","LTE450_Brazil-UEConTest",2,"Rel-12","R5","2013-06-18","2013-12-06",1,"RP-130646","RP-131457","Huawei","Xiang Li (tricia.li@huawei.com)","RP#62 completed","36.508; 36.521-1; 36.521-2; 36.521-3",60,31,null,null,"2013-05-30","2013-11-29"]
[5875,570220,"   Perf. part: Further Downlink MIMO Enhancement for LTE Advanced","LTE_eDL_MIMO_enh-Perf",2,"Rel-12","R4","2012-09-15","2014-12-15",1,"RP-121416","RP-142042","Alcatel-Lucent","ren.da@alcatel-lucent.com","¦CD:Fri 12/06/15->Mon 15/06/15¦WID: RP-141966->RP-142235¦Stat Rep: RP-141378->RP-142042",36.100999999999999,57,29,null,null,"2012-09-03","2015-01-12"]
[5881,580127,"   Core part: Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation","LTE_TDD_eIMTA-Core",2,"Rel-12","R1,R2,R3,R4","2012-12-07","2014-06-13",1,"RP-121772","RP-140724","CATT","Zukang Shen (shenzukang@catt.cn)","RP#64 completed","36.101; 36.104; 36.133; 36.211; 36.212; 36.213; 36.214; 36.300; 36.321; 36.331; 36.413; 36.423",58,30,null,null,"2012-09-03","2014-07-06"]
[5883,690072,"   UE Conformance Test Aspects - Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation","LTE_TDD_eIMTA-UEConTest",2,"Rel-12","R5","2015-09-15","2018-03-15",1,"RP-151398",null,"CATT",null,"tested: REL-12 WI LTE_TDD_eIMTA-Core;1/1/16: Compl:0%->5%¦22/3/16: Compl:5%->15% 21/3/ 19 827/3/",null,69,35,null,null,"2015-09-29","2018-03-27"]
[5886,580030,"Further enhancements for HeNB mobility-X2-GW","EHNB_enh2_X2GW",1,"Rel-12","R3","2012-12-10","2014-06-13",1,"RP-122006","-","Alcatel-Lucent","Philippe.Godin@alcatel-lucent.com","Rel-10 H(e)NB Mobility Enhancements adds signalling via horizontal RAN interfaces (Iurh, X2) to support H(e)NB to H(e)NB mobility. Rel-11 TR37.803 triggered WI UID_560014 partly completed in Rel-11¦remaining work including solution definition is Rel-12","LTE",58,30,null,null,"2012-12-10","2012-12-10"]
[5890,600013,"LTE TDD-FDD joint operation including Carrier Aggregation","LTE_CA_TDD_FDD",1,"Rel-12","R1,R2,R4","2013-04-12","2014-12-15",1,"RP-140465","-","Nokia","lars.e.lindh@nokia.com","-","LTE",60,31,null,null,"2013-06-17","2014-03-13"]
[5894,600114,"   Core part: LTE Coverage Enhancements","Cov_Enh_LTE-Core",2,"Rel-12","R1,R2,R4","2013-03-01","2014-06-13",1,"RP-130833","RP-140683","China Telecom","Xiaoming She (shexm@ctbri.com.cn)","RP#64 completed","36.101; 36.104; 36.133; 36.211; 36.212; 36.213; 36.300; 36.321; 36.331",60,31,null,null,"2013-06-17","2014-06-12"]
[5897,610024,"Further MBMS operations support for E-UTRAN","MBMS_LTE_OS",1,"Rel-12","R2,R1,R3,R4","2013-09-15","2014-12-15",1,"RP-140282","-","Verizon","yeesin.chan@verizonwireless.com","Solutions for Minimization of Drive Tests (MDT), in order to reduce the need for manual drive testing for MBMS.","LTE",61,31,null,null,"2013-09-07","2014-09-09"]
[5899,620073,"   Perf. part: Further MBMS operations support for E-UTRAN","MBMS_LTE_OS-Perf",2,"Rel-12","R4","2013-12-15","2014-12-15",1,"RP-140282","RP-141821","Verizon","yeesin.chan@verizonwireless.com","¦CD:Wed 17/12/14->Mon 15/12/14¦WID: RP-130848->RP-140522¦Stat Rep: RP-141431->RP-141821",36.133000000000003,62,32,null,null,"2013-12-18","2015-01-12"]
[5902,620240,"   Perf. part: Dual Connectivity for LTE","LTE_SC_enh_dualC-Perf",2,"Rel-12","R4","2013-12-15","2015-06-15",1,"RP-141797","RP-150791","NTT DOCOMO","kunihiko.teshima.hg@nttdocomo.com","¦Stat Rep: RP-141264->RP-141796 1st Apr 15: Compl:15%->45% 1st Apr 15: Stat Rep: RP-141796->RP-150160 03/07/15: Compl:45%->100% 03/07/15: Stat Rep: RP-150160->RP-150791","36.101; 36.104; 36.133",62,32,null,null,"2013-12-07","2015-06-18"]
[5908,620241,"   Perf. part: E-UTRA Small cell enhancements - Physical layer aspects","LTE_SC_enh_L1-Perf",2,"Rel-12","R4","2013-12-15","2015-06-15",1,"RP-141459","RP-150690","Huawei","Elean FAN (fanxiaoan@huawei.com)","¦CD:Wed 18/03/15->Sun 15/03/15¦WID: RP-130848->RP-140522¦Stat Rep: RP-141632->RP-141899 1st Apr 15: Compl:40%->80% 1st Apr 15: CD:Sun 15/03/15->Mon 15/06/15 1st Apr 15: Stat Rep: RP-141899->RP-150173 03/07/15: Compl:80%->100% 03/07/15: Stat Rep: RP-","36.101; 36.104; 36.133; 36.141",62,32,null,null,"2013-12-09","2015-06-18"]
[5910,620047,"Inter-eNB Coordinated Multi-Point (CoMP) for LTE","COMP_LTE_IeNB",1,"Rel-12","R3,R1","2013-12-15","2014-12-12",1,"RP-140983","-","Samsung","Sung Hwan Won (sunghwan.won@samsung.com)","Stage 3. Rel-11 did not address support of a network interface for CoMP involving multiple eNBs with non-ideal backhaul (affected operators might not take advantage of performance benefit from inter-eNB CoMP operation).","LTE",62,32,null,null,"2013-12-07","2013-12-07"]
[5913,630131,"   Core part: Smart Congestion Mitigation in E-UTRAN","SCM_LTE-Core",2,"Rel-12","R2","2014-03-06","2014-09-12",1,"RP-140434","RP-141292","LG Electronics","youngdae.lee@lge.com","RP#65 completed",36.331000000000003,63,32,null,null,"2014-03-10","2014-09-21"]
[5917,630032,"Positioning Enhancements for RF Pattern Matching in E-UTRA","LCS_LTE_RFPMT",1,"Rel-12","R3,R2","2014-04-25","2014-06-13",1,"RP-140177","-","Polaris Wireless","Gordon Scot (sgordon@polariswireless.com)","follow-up of TR 36.809 FS_LCS_LTE_RFPMT","LTE",63,32,null,null,"2014-03-10","2014-03-10"]
[5921,630246,"   Perf. part: Network-Assisted Interference Cancellation and Suppression for LTE","LTE_NAICS-Perf",2,"Rel-12","R4","2014-03-11","2015-09-15",1,"RP-151297","RP-151296","MediaTek","Craig.Burnet@mediatek.com","CD:Fri 12/06/15->Mon 15/06/15¦Compl:0%->25%¦Stat Rep: RP-141621->RP-141866 1st Apr 15: Compl:25%->50% 1st Apr 15: Stat Rep: RP-141866->RP-150179 03/07/15: Compl:50%->85% 03/07/15: CD:Mon 15/06/15->Tue 15/09/15 03/07/15: Stat Rep: RP-150179->RP-150862",36.100999999999999,63,32,null,null,"2014-03-10","2015-09-29"]
[5922,690070,"   UE Conformance Test Aspects: Network-Assisted Interference Cancellation and Suppression for LTE","LTE_NAICS-UEConTest",2,"Rel-12","R5","2015-09-15","2017-03-15",1,"RP-160265",null,"Mediatek",null,"tested: LTE_NAICS was a REL-12 RAN1 WI¦1/1/16: Compl:0%->35%¦1/1/16: WID: RP-151298->RP-151945¦",null,69,35,null,null,"2015-09-29","2017-03-21"]
[5926,580028,"HSPA signalling enhancements for more efficient resource usage for LCR","LCR_TDD_HSPA_sign_enh",1,"Rel-12","R1,R2,R3,R4","2012-12-11","2013-12-20",1,"RP-121984","-","CATT","Yanping Xing (xingyanping@catt.cn)","Stage 2/3. Triggered by Rel-11 TR 25.874 Study on HSPA feedback and signalling efficiency enhancements for LCR TDD (FS_LCRTDD_HSPAenh) UID_540026","UTRA",58,30,null,null,"2012-12-10","2012-12-10"]
[5929,600017,"HNB Positioning for UTRA","UTRA_HNB_Pos",1,"Rel-12","R3","2013-06-18","2013-12-06",1,"RP-132037","-","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","RP#62 completed","UTRA",60,31,null,null,"2013-06-17","2013-12-09"]
[5935,610026,"UMTS Mobility enhancements for heterogeneous networks","UTRA_HetNet_mob",1,"Rel-12","R2,R3,R4","2013-07-23","2014-06-13",1,"RP-132039","-","Huawei","Xudong Yang (yangxudong@huawei.com)","Triggered by Rel-12 TR 25.800 Study on UMTS heterogeneous networks (FS_UTRA_hetnet) UID_570024. Stage 2/3","UTRA",61,31,null,null,"2013-09-07","2013-09-07"]
[5937,610226,"   Perf. part: UMTS Mobility enhancements for heterogeneous networks","UTRA_HetNet_mob-Perf",2,"Rel-12","R4","2013-09-09","2014-06-13",1,"RP-132039","RP-140636","Huawei","Xudong Yang (yangxudong@huawei.com)","RP#64 completed","25.101; 25.104; 25.133; 25.141",61,31,null,null,"2013-09-07","2014-06-12"]
[5940,620254,"   Perf. part: Heterogeneous Networks enhancements","UTRA_HetNet_enh-Perf",2,"Rel-12","R4","2013-12-15","2014-12-15",1,"RP-141701","RP-141898","Huawei","carmela.cozzo@huawei.com","¦Stat Rep: RP-141702->RP-141898","25.101; 25.104; 25.133; 25.141",62,32,null,null,"2013-12-09","2015-01-12"]
[5944,620049,"Further Enhanced Uplink (EUL) enhancements","EDCH_enh",1,"Rel-12","R2","2013-12-15","2015-03-13",1,"RP-140127","-","Ericsson","mark.curran@ericsson.com","Triggered by Rel-12 UTRA TR 25.700 Study on Further Enhanced Uplink (EUL) enhancements (FS_EDCH_enh)","UTRA",62,32,null,null,"2013-12-09","2014-09-15"]
[{"$f":"A5948+1","v":5948},660032,"(IETF) (Small) Technical Enhancements and Improvements for Rel-12 (draft-ietf-insipid-session-id)","TEI12_IETF",1,"Rel-12","C1-IETF","2014-06-13","2014-12-09",1,"CP-140815",null,"Alcatel-Lucent",null,"Mar15: In WGLC¦21/3/17: 50%->100; 9/4/21: RFC 7989 added;","draft-ietf-insipid-session-id; RFC 7989",66,34,null,null,"2014-12-04","2021-04-09"]
[5949,610001,"Test - (Small) Technical Enhancements and Improvements for Rel-12","TEI12_Test",1,"Rel-12","R5,G3new","2014-10-24","2015-12-11",1,"-","-","-","-","-","-",61,31,null,null,"2013-07-29","2013-07-29"]
[5953,490035,"Study on Integration of Single Sign-On (SSO) frameworks with 3GPP networks","FS_SSO_Int",1,"Rel-12","S1","2010-09-23","2012-03-07",1,"SP-100640","-","InterDigital","christopher.wallace@interdigital.com ","SP#55 completed. Linked to SA3 Study on Single Sign On (SSO) Application Security for IMS - based on SIP Digest (UID_480048), SA3 TR 33.924 Extended Identity Management (GBA-IdM) and SA3 TR 33.980 (LibSec)",22.895,49,25,null,null,"2010-08-31","2012-02-22"]
[5956,530044,"Study on Proximity-based Services","FS_ProSe",1,"Rel-12","S1","2011-09-22","2013-03-05",1,"SP-110638","-","Qualcomm","Rich Hovey (rhovey@qualcomm.com)","SP#59 completed",22.803000000000001,53,27,null,null,"2011-09-08","2013-02-19"]
[5962,490234,"   SA2 part of Study on IMS based Peer-to-Peer Content Distribution Services (Stage 2)","FS_IMS_P2P_CDS",2,"Rel-12","S2","2010-09-23","2012-06-20",1,"SP-120622","-","China Mobile","Yu Qing (yuqing@chinamobile.com)","SP#56 completed. TR 23.844v100 for Information and Approval",23.844000000000001,49,25,null,null,"2010-09-15","2012-06-14"]
[5964,490036,"Study on Core Network Overload solutions","FS_CNO",1,"Rel-12","S2","2010-09-23","2013-12-11",1,"SP-120490","-","Huawei","Mirko.Schramm@huawei.com","SP#62 completed. Linked to CT4 TR 23.857 Study on EPC Nodes Restoration (UID_490014)",23.843,49,25,null,null,"2010-08-31","2013-11-28"]
[5967,500037,"Study on System Enhancements for Energy Efficiency","FS_SEEE",1,"Rel-12","S2","2010-12-16","2012-06-20",1,"SP-100888","-","Huawei","frank.mademann@huawei.com","SP#56 completed",23.866,50,26,null,null,"2010-11-25","2012-06-19"]
[5972,410143,"   SA1 part of Study on Multi Access PDN connectivity and IP flow Mobility","FS_MAPIM",2,"Rel-12","S1","2008-08-08","2011-09-21",1,"SP-110452","-","Qualcomm","Gerardo Giaretta (gerardog@qualcomm.com)","SP#53 completed",23.861000000000001,41,21,null,null,"2008-09-15","2013-01-16"]
[5975,480043,"Study on Extended IMS Media Plane Security features","FS_eMEDIASEC",1,"Rel-12","S3","2010-06-10","2013-03-06",1,"SP-100256","-","Vodafone","Aguibou.Barry@vodafone.com","SP#59 completed. Continuation of Rel-9 Feature UID_430036 IMS Media Plane Security (MEDIASEC). Study solutions and extensions to features and functionality described in TR 33.828 and TS 33.328",33.829000000000001,48,25,null,null,"2010-05-05","2013-02-19"]
[5976,530047,"Deleted - Study on Firewall traversal (Stage 2)","FS_Fire",1,"Rel-12","S3","2011-06-17","2014-09-17",1,"SP-120849","-","Acme Packet","Prashant Kumar (PKumar@acmepacket.com)","SP#65 stopped. Linked to Rel-12 Service and Media Reachability for Users over Restrictive Firewalls (SMURFs) UID_530043",33.83,53,27,"SP-65","PCG-33","2011-07-19","2014-05-21"]
[5980,610044,"Study on HTML5 for a new presentation layer in 3GPP services","FS_HTML5",1,"Rel-12","S4","2013-09-12","2014-09-16",1,"SP-130357","-","Samsung","Imed Bouazizi (i.bouazizi@sta.samsung.com)","SP#65 completed. TR 26.907v200 for Approval. SP#64 TR 26.907v100 for Information. ",26.907,61,31,null,null,"2013-09-09","2014-09-05"]
[5983,540032,"Study on OAM aspects of Network Sharing","FS_OAM_SHARE",1,"Rel-12","S5","2011-12-07","2013-09-11",1,"SP-130044","-","Alcatel-Lucent, Huawei","Padma.Sudarsan@alcatel-lucent.com, zoulan@huawei.com","SP#61 completed. Linked to Network Sharing UID_31018, SA1 22.951 (Service aspects and requirements for network sharing), SA2 23.251 (Network Sharing¦Architecture)",32.850999999999999,54,28,null,null,"2012-06-02","2013-09-04"]
[5989,590011,"Study on XML based access of AF to the PCRF","FS_XML_AF_PCRF",1,"Rel-12","C3","2013-03-01","2013-12-04",1,"CP-130167","-","Alcatel-Lucent","horst.brinkman@alcatel-lucent.com","CP#64 completed. Investigate introducing an XML-based protocol (e.g. SOAP, Restful HTTP, etc.) between AF and PCRF for non-IMS applications",29.817,59,30,null,null,"2013-02-16","2014-06-19"]
[5991,620001,"Study on Development of conformance requirements for the IP Multimedia Services Identity Module (ISIM) application support in ME","FS_ISIM_CR",1,"Rel-12","C6","2013-12-09","2014-12-09",1,"CP-130812","-","Gemalto","ly-thanh.phan@gemalto.com","CP#65 completion 09/14=>12/14. Gathering of all ISIM-related conformance requirements and the assessment of CT6 coverage¦June2015: Compl:30%->100",31.829000000000001,62,32,null,null,"2013-11-22","2015-06-15"]
[5994,520001,"Study on Voice services over Adaptive Multi-user channels on One Slot (VAMOS) enhancements","FS_eVAMOS",1,"Rel-12","GP,G2,G1","2010-10-27","2014-05-30",1,"GP-110991","-","China Mobile, Huawei","Chao Luo (chluo@huawei.com), dengjuan@chinamobile.com","GP#62 completed. TR 43.801v100 for 1-step Approval. GP#50 approved WID. Triggered by Rel-8 TR 45.914 Study Multi-User-Reusing One Timeslot (MUROS) UID_50590 and Rel-9 VAMOS UID_420002",43.801000000000002,50,27,null,null,"2011-05-21","2014-05-30"]
[5999,570023,"Study on Scenarios and Requirements of LTE Small Cell Enhancements for E-UTRA and E-UTRAN","FS_LTE_SC_enh_req",1,"Rel-12","RP","2012-09-11","2012-12-07",1,"RP-121418","RP-121651","China Mobile","Hai TANG (tanghai@chinamobile.com)","RP#58 completed. TR 36.932 v100 for Information and Approval","LTE 36.932",57,29,null,null,"2012-09-03","2012-12-06"]
[6002,580038,"Study on LTE Device-to-Device Proximity Services - Radio Aspects","FS_LTE_D2D_Prox",1,"Rel-12","R1,R2,R3,R4","2012-12-17","2014-03-06",1,"RP-122009","RP-140416","Qualcomm","Shailesh Patil (patil@qti.qualcomm.com)","RP#63 completed. TR 36.843 for 1-step approval (90% complete). Started normative work. Linked to Rel-12 TR 22.803 Study on Proximity-based Services (FS_ProSe) and Feature ProSe","LTE 36.843",58,30,null,null,"2012-12-10","2014-03-14"]
[6003,580042,"Study on 3D-channel model for Elevation Beamforming and FD-MIMO studies for LTE","FS_LTE_3D_channel",1,"Rel-12","R1","2012-12-10","2014-09-12",1,"RP-141237","RP-141206","Nokia Networks","bishwarup.mondal@nsn.com","RP#65 completed. Updated WID RP-130811=>RP-141237. TR 36.873v210 for Approval. Enhance performance with 3D-beamforming or with FD-MIMO. Study new channel modelling in both vertical and horizontal dimensions awa user locations in the network","LTE 36.873",58,30,null,null,"2012-12-10","2014-09-21"]
[6007,590018,"Study on Network-Assisted Interference Cancellation and Suppression for LTE","FS_LTE_NAICS",1,"Rel-12","R1,R4","2013-03-08","2014-03-06",1,"RP-130404","RP-132108","MediaTek","jeff.zhuang@mediatek.com","RP#63 completed. TR 36.866 (90% complete) for Approval. Started normative work","LTE 36.866",59,30,null,null,"2013-02-26","2014-03-14"]
[{"$f":"A6012+1","v":6012},530056,"Study on RF and EMC requirements for active Antenna Array System (AAS) Base Station","FS_AAS_BS_LTE_UTRA",1,"Rel-12","R4,R1","2011-09-19","2013-03-01",1,"RP-111349","RP-130124","Huawei","Ronnie.zhang@huawei.com","RP#59 completed","UTRA; LTE 37.840",53,27,null,null,"2011-09-19","2013-02-28"]
[6015,580045,"Study on WLAN/3GPP Radio Interworking","FS_UTRA_LTE_WLAN_interw",1,"Rel-12","R2","2012-12-10","2013-12-06",1,"RP-122038","RP-131611","Intel","sasha.sirotkin@intel.com","RP#62 completed. Evaluate LTE-WLAN/UTRA-WLAN i/w procedures while improving (non-)seamless mobility. Deployed WLAN often under-utilized¦User experience suboptimal when UE connects to overloaded WLAN.","UTRA; LTE 37.834",58,30,null,null,"2012-12-10","2013-12-03"]
[6018,580049,"Study on 2GHz FDD for UTRA and LTE in Region 1 (1980-2010MHz and 2170-2200MHz Bands)","FS_UTRA_LTE_1980_2170_REG1",1,"Rel-12","R4","2012-12-11","2014-09-12",1,"RP-140505","RP-141099","DISH Network","johny.kim@dish.com, mariam.sorond@dish.com","RP#65 completed. Within EU these bands can be used for terrestrial mobile as a complement to mobile satellite services. Study adding an FDD band into UTRA/E-UTRA in applicable countries of Region 1","UTRA; LTE 37.846",58,30,null,null,"2012-12-10","2014-09-22"]
[6021,570024,"Study on UMTS heterogeneous networks","FS_UTRA_HetNet",1,"Rel-12","R1,R2,R3","2012-06-12","2013-09-06",1,"RP-121436","RP-131606","Huawei","carmela.cozzo@huawei.com","RP#62 completed","UTRA 25.800",57,29,null,null,"2012-09-03","2013-12-02"]
[6026,600018,"Study on HNB Emergency Warning Area for UTRA","FS_HNB_warn_area",1,"Rel-12","R3","2013-06-18","2014-03-06",1,"RP-131258","RP-140129","Alcatel-Lucent, Ip.access","Martin.Warner@alcatel-lucent.com, Kit.kilgour@ipaccess.com ","RP#63 completed. TR 25.703 v100 for 1-step approval","UTRA 25.703",60,31,null,null,"2013-06-17","2014-02-26"]
[6029,470051,"Advanced IP Interconnection of Services","IPXS",1,"Rel-11","S1,S2,C1,C3","2010-03-25","2012-09-12",1,"SP-100876","-","Telefónica","chris.friel@O2.com","CP#58 completed. Triggered by Rel-10 TR 22.893 UID_380083 Study on advanced requirements for IP interconnect (FS_IPXS)","-",47,24,null,null,"2002-03-05","2012-11-19"]
[6030,470052,"   Stage 1 for Advanced IP Interconnection of Services","IPXS",2,"Rel-11","S1","2010-03-25","2011-09-21",1,"SP-100876","-","Telefónica","chris.friel@O2.com","SP#53 completed","22.101; 22.228",47,24,null,null,"2002-03-05","2011-08-24"]
[6034,530204,"      CT3 part of Stage 3 for Advanced IP Interconnection of Services","IPXS",3,"Rel-11","C3","2011-09-13","2012-09-07",1,"CP-110646","-","Ericsson","christer.holmberg@ericsson.com","CP#57 completed",29.164999999999999,53,27,null,null,"2011-08-29","2012-08-13"]
[6039,520121,"      Deleted - MTC Feature Control (described in TS 22.368, clause 7.1.1 and 23.888, clause 5.7)","SIMTC-Reach",3,"Rel-11","S2","2011-06-10","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","-",52,27,"SP-54","PCG-28","2011-05-26","2012-11-12"]
[6042,520421,"      Identifiers – especially removal of MSISDN dependencies in the architecture","SIMTC-Reach",3,"Rel-11","S2","2011-06-09","2012-06-20",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#56 completed","New 23.682",52,27,null,null,"2011-05-26","2012-11-12"]
[6045,530006,"   BB1: Stage 3 (CS+PS) Reachability Aspects of SIMTC","SIMTC-ReachCSPS",2,"Rel-11","C1,C3,C4,C6","2011-09-19","2012-12-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","22/01: acronym modified","Stage 3",53,27,null,null,"2011-08-29","2015-01-22"]
[6048,530306,"      CT4 part of Stage 3 BB1: Reachability Aspects of SIMTC","SIMTC-ReachCSPS",3,"Rel-11","C4","2011-09-19","2012-12-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","22/01: acronym modified","23.003; 23.008; 29.002; 29.060; 29.230; New (29.336; 29.337)",53,27,null,null,"2011-08-29","2015-01-22"]
[6053,530305,"         CT1 part of Stage 3 CS aspects for SIMTC ","SIMTC-CS",4,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#57 completed","24.008; 24.301",53,27,null,null,"2012-06-15","2012-08-13"]
[6057,560202,"      CT4 part of Stage 2/3 for SMS in MME architecture option and related PS-only service subscription","SIMTC-PS_Only",3,"Rel-11","C4","2012-06-15","2012-12-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#58 completed. TS 29.338 v200 for Approval","23.003; 23.008; 23.012; 29.002; 29.272; 29.305; New 29.338 ",56,29,null,null,"2012-04-23","2012-11-28"]
[6060,530209,"      Stage 3 (CS+PS) Extended Access Barring for UTRAN and E-UTRAN","SIMTC-RAN_OC",3,"Rel-11","C1,C6","2011-09-16","2012-09-07",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#57 completed. Updated WID CP-120418=>CP-120617","Stage 3",53,27,null,null,"2011-08-29","2012-08-24"]
[6061,530309,"         CT1 part of Stage 3 Extended Access Barring for UTRAN and E-UTRAN","SIMTC-RAN_OC",4,"Rel-11","C1","2011-09-16","2012-06-15",1,"CP-120617","-","Ericsson","mikael.wass@ericsson.com","CP#56 completed","23.122; 24.008; 24.301",53,27,null,null,"2011-08-29","2012-06-01"]
[6066,520122,"      Deleted - Effectively maintain connectivity for a large number of MTC Devices (TS 22.368, 7.1.1)","SIMTC-Sig",3,"Rel-11","S2","2011-06-10","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","TBD",52,27,"SP-55","PCG-28","2011-05-26","2012-11-12"]
[6069,530207,"         Deleted - CT1 part of Stage 3 Signalling Optimizations of SIMTC","SIMTC-Sig",4,"Rel-11","C1","2011-09-16","2011-12-09",1,"CP-110756","-","Ericsson","mikael.wass@ericsson.com","-","23.122; 24.008; 24.301; 24.368",53,27,"CP-55","PCG-28","2011-08-29","2011-11-28"]
[6072,520123,"      Deleted - Charging Requirements (TS 22.368, 7.1.5)","SIMTC-CN_Pow",3,"Rel-11","S2","2011-06-10","2011-12-14",1,"SP-120848","-","Intel","puneet.jain@intel.com ","SP#54 work stopped","TBD",52,27,"SP-55","PCG-28","2011-05-26","2012-11-12"]
[6075,530008,"      Deleted - Stage 3 (CS+PS) CN-based requirements and Power Considerations of SIMTC","SIMTC-CN_Pow",3,"Rel-11","C1,C6","2011-09-16","2011-12-09",1,"CP-110756","-","Ericsson","mikael.wass@ericsson.com","CP#54 work stopped","Stage 3",53,27,"CP-55","PCG-28","2011-08-29","2011-12-13"]
[6080,520124,"      Deleted - Secure Connection MTC Feature (TS 22.368, 7.2.10)","SIMTC-Sec",3,"Rel-11","S3","2011-06-08","2012-09-12",1,"SP-120848","-","Samsung","Rajavelsamy R (rajvel@samsung.com)","SP#57 stopped (activity transferred to Rel-12 Feature MTCe","TBD",52,27,"CP-57","PCG-29","2011-05-26","2012-11-12"]
[6084,480031,"Unstructured Supplementary Service Data (USSD) simulation service in IMS","USSI",1,"Rel-11","S1,C1,C3","2010-06-10","2012-12-07",1,"SP-100408","-","Deutsche Telekom","kurt.bischinger@t-mobile.at","CP#58 completed","-",48,25,null,null,"2010-06-06","2012-11-19"]
[6085,480131,"   Stage 1 for USSD simulation service in IMS","USSI",2,"Rel-11","S1","2010-06-10","2010-06-10",1,"SP-100408","-","Deutsche Telekom","kurt.bischinger@t-mobile.at","SP#48 completed. Specify a CS domain USSD like service over IMS (see GSM Mobile User Initiated USSD)",22.172999999999998,48,25,null,null,"2010-06-06","2011-08-24"]
[6088,520203,"      CT3 part of Stage 3 for USSD simulation service in IMS","USSI",3,"Rel-11","C3","2011-06-07","2012-09-07",1,"CP-110534","-","Deutsche Telekom","reinhard.lauster@t-mobile.at ","CP#57 completed",29.164999999999999,52,27,null,null,"2011-05-18","2012-08-13"]
[6093,520004,"   CT3 aspects of QoS Control Based on Subscriber Spending Limits (Stage 3)","QoS_SSL-CT3",2,"Rel-11","C3","2011-06-03","2012-06-15",1,"CP-120203","-","Huawei","QiaoWeihua@huawei.com","CP#56 completed","29.212; 29.213; 29.214; 29.215; new 29.219",52,27,null,null,"2011-05-18","2012-04-20"]
[6096,490232,"   Stage 1 for Optimized Service Charging and Allocation of Resources in IMS whilst Roaming","OSCAR",2,"Rel-11","S1","2010-09-23","2011-09-21",1,"SP-110347","-","Vodafone","mona.mustapha@vodafone.com","SP#53 completed","22.115; 22.173; 22.228",49,25,null,null,"2010-08-31","2012-03-05"]
[6098,530021,"Inclusion of Media Resource Broker (Stage 2/3)","MRB",1,"Rel-11","C1,C3,IETF","2011-09-16","2013-06-14",1,"CP-120277","-","AT&T","Martin Dolly (md3135@att.com)","Stage 1 and TR on Stage 2 in Rel-11 Feature OSCAR UID_490032","Stage 2/3",53,27,null,null,"2011-08-25","2012-06-06"]
[6103,560003,"      CT3 part of Stage 3 for Inclusion of Media Resource Broker","MRB",3,"Rel-11","C3","2012-06-15","2012-09-07",1,"CP-120277","-","AT&T","Martin Dolly (md3135@att.com)","CP#57 completed",29.164999999999999,56,29,null,null,"2012-06-01","2012-08-13"]
[6107,510047,"Support for 3GPP Voice Interworking with Enterprise IP-PBX","VINE",1,"Rel-11","S1,C1","2011-03-23","2013-03-01",1,"SP-110176","-","Tatara Systems","Phillip Brown (pbrown@tatarasystems.com)","SP#53 Stage 1 completed. CP#59 completed. Triggered by Rel-11 TR 22.809 Study on Support for 3GPP Voice Interworking with Enterprise IP-PBX (FS_VINE) UID_480033","-",51,26,null,null,"2011-02-21","2013-02-16"]
[6111,520128,"   Stage 1 for Anonymous Call Rejection in the CS domain","ACR_CS",2,"Rel-11","S1","2011-06-07","2011-06-08",1,"SP-110421","-","Alcatel-Lucent","Betsy.Covell@alcatel-lucent.com","SP#52 completed under TEI11. Approved WID and CRs in SP-110376 (22.082 CR#0005, 22.085 CR#0004, 22.081 CR#0007, 22.088 CR#0003, 22.004 CR#0013)","22.004; 22.081; 22.082; 22.085; 22.088",52,27,null,null,"2011-05-19","2011-09-19"]
[6112,530011,"   Core Network aspects of Anonymous Call Rejection in the CS domain","ACR_CS-CN",2,"Rel-11","C4,C3","2011-09-14","2011-12-02",1,"CP-110587","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#54 completed","Stage 2/3",53,27,null,null,"2011-08-27","2011-08-27"]
[6115,460026,"Support for BroadBand Forum Accesses Interworking","BBAI",1,"Rel-11","S2,S1,C1,C3,C4,IETF","2009-12-10","2012-12-12",1,"SP-120539","-","Ericsson","peter.bleckert@ericsson.com","SP#57 updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#56 completed. Triggered by BBF WT 203, WT-134 (interworking btw 3GPP EPS and BBF's fixed broadband accesses)","-",46,24,null,null,"2009-12-06","2012-08-30"]
[6120,530012,"   Stage 3 BB I - Core Network impacts: BBF interworking with home routed traffic for WLAN and H(e)NB","BBAI_BBI-CT",2,"Rel-11","C1,C3,C4","2011-09-16","2012-12-07",1,"CP-120419","-","Ericsson","Zu.Qiang@Ericsson.com","CP#58 completed","Stage 3",53,27,null,null,"2011-08-29","2012-11-17"]
[6123,551002,"      Deleted - (IETF) on Stage 3 BB I for BBAI; Home (e)Node B – Security Gateway Interface","BBAI_BBI-CT",3,"Rel-11","C4-IETF","2012-03-02","2012-06-15",1,"CP-120419","-","Lionel Morand","-","Draft removed from 3GPP documentation","draft-so-ipsecme-ikev2-cpext",55,28,"CP-56","PCG-29","2012-03-05","2012-06-14"]
[6125,530312,"      CT3 part of Stage 3 BB I: BBF interworking with home routed traffic for WLAN and H(e)NB","BBAI_BBI-CT",3,"Rel-11","C3","2011-09-16","2012-09-07",1,"CP-120419","-","Ericsson","Zu.Qiang@Ericsson.com","CP#57 completed","29.212; 29.213; 29.215",53,27,null,null,"2011-08-29","2012-08-13"]
[6130,530113,"      TR on Stage 3 BB II for 3GPP System to Fixed Broadband Access Network Interworking; UE to network protocols","BBAI_BBII-CT",3,"Rel-11","C1","2011-09-16","2012-06-15",1,"CP-120420","-","Ericsson","Susana.Fernandez@ericsson.com","CP#56 completed ",24.82,53,27,null,null,"2011-08-29","2012-06-14"]
[6134,490027,"   Deleted - Stage 1 BB III: BBF convergence and network based mobility ","-",2,"Rel-11","S1","2010-09-23","2011-09-21",1,"SP-120539","-","Huawei","Amar Deol (adeol@huawei.com)","SP#57 stopped. Updated WID SP-120419=>SP-120539 (removed BB3 objectives not implemented in Stage 2). SP#53 completed",22.277999999999999,49,25,"SP-57","PCG-29","2010-09-01","2012-06-09"]
[6138,530214,"      Deleted - CT1 part of Stage 3 BB III: BBF convergence and network based mobility","-",3,"Rel-11","C1","2011-09-16","2012-03-02",1,"CP-110927","-","Huawei","qiaoweihua@huawei.com","CP#55 stopped","TBD",53,27,"CP-55","PCG-28","2011-08-29","2012-02-20"]
[6139,530314,"      Deleted - CT3 part of Stage 3 BB III: BBF convergence and network based mobility","-",3,"Rel-11","C3","2011-09-16","2012-03-02",1,"CP-110927","-","Huawei","qiaoweihua@huawei.com","CP#55 stopped","29.212; 29.213; 29.215",53,27,"CP-55","PCG-28","2011-08-29","2012-02-20"]
[6143,480235,"   Stage 2 on SRVCC for eMPS","eMPS_SRVCC",2,"Rel-11","S2","2010-06-10","2011-12-14",1,"SP-110346","-","NTT DoCoMo","Atsushi Minokuchi (minokuchi@nttdocomo.co.jp)","SP#54 completed","23.216; 23.237",48,25,null,null,"2010-06-06","2012-03-04"]
[6146,520005,"   CN aspects of Single Radio Video Call Continuity for 3G-CS","vSRVCC-CT",2,"Rel-11","C1,C3,C4","2011-06-03","2012-06-15",1,"CP-120278","-","NEC","gottfried.punz@neclab.eu","Stage 3. CP#56 completed","-",52,27,null,null,"2011-05-18","2012-06-06"]
[6150,480038,"Network-provided Location information for IMS (NETLOC)","NWK-PL2IMS",1,"Rel-11","S2,S1,S5,C3,C4,C1","2010-06-10","2013-03-01",1,"SP-110631","-","T-Mobile","michele.zarri@t-mobile.co.uk ","Covers the case where UE is served by a 3GPP RAN. Architecture making Cell/PLMN ID (UE is camped on) available to IMS nodes when the operator needs to record this information either to fulfil legal obligations or for charging.","-",48,25,null,null,"2010-06-06","2012-11-13"]
[6152,480138,"   TR on Stage 2 for Network-provided Location information for IMS","NWK-PL2IMS",2,"Rel-11","S2","2010-06-10","2011-12-14",1,"SP-110631","-","T-Mobile","michele.zarri@t-mobile.co.uk ","SP#54 completed","new 23.842",48,25,null,null,"2010-06-06","2011-12-06"]
[6158,550308,"      CT1 part of CT aspects of Network-provided Location information for IMS","NWK-PL2IMS-CT",3,"Rel-11","C1","2012-03-02","2013-03-01",1,"CP-120845","-","Huawei","Qiao Weihua (qiaoweihua@huawei.com)","CP#57 completed. 3/3: Acronym changed from \"NWK-PL2IMS_CT\"","24.229; 24.292",55,28,null,null,"2012-02-22","2015-03-03"]
[6161,500232,"   Stage 2 for Service Awareness and Privacy Policies","SAPP",2,"Rel-11","S2","2010-10-15","2011-09-21",1,"SP-100882","-","Allot","Alla Goldner (agoldner@allot.com)","SP#53 completed",23.202999999999999,50,26,null,null,"2010-11-26","2011-08-12"]
[6165,530017,"   CT aspects of VPLMN Autonomous CSG Roaming","VCSG-St3",2,"Rel-11","C4","2011-12-07","2011-12-07",1,"CP-120196","-","ZTE","Fei Lu (lu.fei1@zte.com.cn)","CP#57 completed","23.003; 23.007; 23.008; 23.012; 29.002; 29.230; 29.272",53,27,null,null,"2011-08-27","2012-08-13"]
[6166,510048,"Data Identification in Access Network Discovery and Selection Function (ANDSF)","DIDA",1,"Rel-11","S2,C1","2011-03-23","2012-12-07",1,"SP-110084","-","Qualcomm","Gerardo Giaretta (gerardo@qualcomm.com)","SP#58 completed. Linked to Rel-10 IFOM (IP Flow Mobility and seamless WLAN offload) UID_450041. Defines IP flow mobility, seamless and non seamless WLAN offload and respective ANDSF extensions","Stage 2/3",51,26,null,null,"2011-02-21","2012-11-19"]
[6170,510050,"LOcation-Based Selection of gaTEways foR WLAN","LOBSTER",1,"Rel-11","S2,C4","2011-03-23","2012-06-15",1,"SP-110752","-","ZTE","zhu.chunhui@zte.com.cn","CP#56 completed. Related to UID_350027 SAE for support for non-3GPP accesses (SAES-SA-FP_n3GPP). Enhancements to ePDG and PDN GW selection functions for S2b and S2c based on UE location","-",51,26,null,null,"2011-03-18","2012-06-01"]
[6173,540110,"      CT4 part of CT aspects of LOcation-Based Selection of gaTEways foR WLAN","LOBSTER-CT",3,"Rel-11","C4","2011-12-02","2012-06-15",1,"CP-120252","-","ZTE","zhou.xingyue@zte.com.cn","CP#56 completed",29.273,54,28,null,null,"2011-11-23","2012-09-24"]
[6177,530201,"   CT aspects for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA (Stage 3)","rSRVCC-CT",2,"Rel-11","C1,C3,C4","2011-09-16","2012-09-07",1,"CP-110726","-","Ericsson","ivo.sedlacek@ericsson.com","CP#57 completed","Stage 3",53,27,null,null,"2011-08-25","2012-08-14"]
[6179,530401,"      CT3 part for Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA","rSRVCC-CT",3,"Rel-11","C3","2011-09-19","2012-09-07",1,"CP-110726","-","Ericsson","ivo.sedlacek@ericsson.com","CP#57 completed","29.165; 29.292",53,27,null,null,"2011-08-25","2012-08-14"]
[6185,530046,"S2a Mobility based On GTP and WLAN access to EPC","SaMOG_WLAN",1,"Rel-11","S2,C4,C1,C3,IETF","2011-09-22","2014-03-05",1,"SP-110642","-","ZTE","Chunhui Zhu (zhu.chunhui@zte.com.cn)","Triggered by Rel-11 TR 23.852 FS_SaMOG UID_510061, Rel-8 UID_350027 SAE for support for non-3GPP accesses (defines PMIP-S2a)","Stage 2/3",53,27,null,null,"2011-08-12","2014-02-19"]
[6188,540111,"      CT4 part of CN aspects of Mobility based On GTP & PMIPv6 for WLAN access to EPC","SaMOG_WLAN-CN",3,"Rel-11","C4","2011-12-02","2012-09-07",1,"CP-110802","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#57 completed","23.003; 23.007; 23.008; 29.273; 29.274; 29.281; 29.303",54,28,null,null,"2011-10-26","2012-08-13"]
[6192,540029,"Roaming Architecture for Voice over IMS with Local Breakout","RAVEL",1,"Rel-11","S2,S5,C1,C3","2011-11-28","2012-12-07",1,"SP-110885","-","Deutsche Telekom","michele.zarri@telekom.com","CP#58 completed. Triggered by Rel-11 TR 23.850 Study on Roaming Architecture for Voice over IMS with Local Breakout (FS_RAVEL). GSMA CPWP LS_in S5-102806 asked 3GPP SA5 to check if CS voice charging principles also apply to voice over IMS","Stage 2/3",54,28,null,null,"2011-10-25","2012-11-20"]
[6193,540129,"   Stage 2 for Roaming Architecture for Voice over IMS with Local Breakout","RAVEL",2,"Rel-11","S2","2011-11-28","2011-12-14",1,"SP-110885","-","Deutsche Telekom","michele.zarri@telekom.com","SP#54 completed","23.002; 23.228",54,28,null,null,"2011-10-25","2011-11-28"]
[6197,550204,"      CT3 part of CT aspects of Roaming Architecture for Voice over IMS with Local Breakout","RAVEL-CT",3,"Rel-11","C3","2012-03-02","2012-12-07",1,"CP-120088","-","Deutsche Telekom","reinhard.lauster@)t-mobile.at","CP#58 completed","29.165; 29.162; 29.079",55,28,null,null,"2012-02-20","2012-11-20"]
[6201,570107,"      CT1 part of Stage 3 for IMS Overload Control","IOC",3,"Rel-11","C1","2012-09-05","2012-12-07",1,"CP-120561","-","Alcatel-Lucent","Keith Drage","CP#58 completed",24.228999999999999,57,29,null,null,"2012-08-13","2012-11-20"]
[{"$f":"A6204+1","v":6204},571002,"      (IETF) CT part of Stage 3 for IMS Overload Control (soc-overload-rate-control)","IOC",3,"Rel-11","C1-IETF,C3-IETF","2013-07-29","2014-12-09",1,"CP-120561","-","Keith Drage","Keith Drage","Submitted to IESG for publication. Dec14: 50->90%. Mar15: 100%. Impacted RFC updated (was draft-ietf-soc-overload-rate-control). Jun 15: RFC 7415 (was draft-ietf-soc-overload-rate-control)","RFC 7415",57,29,null,null,"2012-09-03","2015-03-10"]
[6206,520030,"Rel-11 Security small Enhancements","SEC11",1,"Rel-11","S3","2011-06-08","2012-09-12",1,"-","-","-","-","SEC11 is an umbrella Feature for Security related TEI11 type of changes that are not part of any other dedicated feature","-",52,27,null,null,"2011-04-19","2012-08-16"]
[6212,510053,"H(e)NB security features for UE mobility scenarios (Stage 2)","HNB_mob_Sec",1,"Rel-11","S3","2011-03-23","2012-03-07",1,"SP-110025","-","Huawei","Marcus Wong (mwong@huawei.com)","SP#55 completed. Add HeNB Security extensions to Extended H(e)NB Features (EHNBF) UID_450053",33.32,51,26,null,null,"2011-02-14","2012-02-20"]
[6215,540212,"   Stage 3 for GBA extensions for re-use of SIP Digest credentials","GBA-ext-St3",2,"Rel-11","C4,C1","2011-12-02","2012-09-07",1,"CP-110804","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#57 completed","Stage 3",54,28,null,null,"2011-11-23","2012-08-14"]
[6219,530048,"Enhancements to Multimedia: PSS, MMS, and MBMS Enhancements and Performance Improvements","EMM",1,"Rel-11","S4","2011-09-07","2013-03-06",1,"SP-120025","-","Qualcomm","Nikolai Leung (nleung@qualcomm.com)","Stage 3. SP#59 completed","26.140; 26.234; 26.247; New 26.951=>26.851",53,27,null,null,"2011-09-07","2013-02-16"]
[6220,530148,"   Enhancement to FEC for MBMS","EMM-EFEC",2,"Rel-11","S4","2011-09-21","2013-03-06",1,"SP-120182","-","Qualcomm","Thomas Stockhammer (c_tstock@qualcomm.com)","SP#59 completed","26.346; new 26.947",53,27,null,null,"2011-09-07","2013-02-16"]
[6224,510051,"Rel-11 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM11",1,"Rel-11","S5","2011-03-23","2013-03-06",1,"-","-","-","-","OAM11 is an umbrella Feature also for OAM&P related TEI11 type of changes that are not part of any other dedicated feature/WI","-",51,26,null,null,"2011-02-22","2011-02-22"]
[6228,510057,"      IMS Performance Management enhancements","OAM-ePM-IMS",3,"Rel-11","S5","2011-03-23","2012-03-07",1,"SP-110134","-","ZTE","guo.wenjie1@zte.com.cn","SP#55 completed",32.408999999999999,51,26,null,null,"2011-02-22","2012-03-05"]
[6233,510059,"      UTRAN Self-Organizing Networks (SON) management","OAM-SON-UTRAN",3,"Rel-11","S5","2011-03-23","2012-09-12",1,"SP-120552","-","Huawei","kai.zhangkai@huawei.com","SP#57 completed. Updated WID SP-110518=>SP-120552","UTRA 32.405; 32.500; 32.511; 32.521; 32.522; 32.526; 32.642; 32.646",51,26,null,null,"2011-02-22","2012-08-31"]
[6235,540031,"      Inter-RAT Energy Saving Management","OAM-IRAT-ESM",3,"Rel-11","S5","2011-12-07","2012-12-12",1,"SP-110701","-","Nokia Siemens Networks, Huawei","clemens.suerbaum@nsn.com, xiahaitao@huawei.com","SP#58 completed. Triggered by Rel-11 TR 32.834 (Study on OAM aspects of inter-RAT Energy Saving) UID_510045. Needs coordination with RAN WGs","32.405; 32.551; 32.522; 32.526; 32.642; 32.646; 32.762; 32.766",54,28,null,null,"2011-11-22","2012-11-19"]
[6239,550019,"   Unification of Charging session from SIP AS and SRVCC functions in IMS","UCHIMS_AS-SRVCC",2,"Rel-11","S5","2012-03-07","2012-12-12",1,"SP-120042","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","Stage 2/3. SP#58 completed","32.260; 32.275; 32.298; 32.299",55,28,null,null,"2012-02-22","2012-12-05"]
[6242,510229,"   Stage 2/3 SA5 part of Transit Inter Operator Identifier for IMS Interconnection Charging in multi operator environment","IOI_IMS_CH",2,"Rel-11","S5","2010-10-27","2011-12-07",1,"SP-110132","-","Deutsche Telekom","matthias.seibel@telekom.de","SP#54 completed","32.240; 32.260; 32.298; 32.299",51,26,null,null,"2011-02-22","2011-10-24"]
[6246,480111,"   TR on User Data Convergence (UDC) Data Model","UDC_DM",2,"Rel-11","C4","2010-06-04","2012-09-07",1,"CP-110384","-","Telecom Italia","mauro.ficaccio@telecomitalia.it","CP#57 completed","new 29.935",48,25,null,null,"2010-05-26","2012-09-25"]
[6247,480211,"   User Data Convergence (UDC) Data Model","UDC_DM",2,"Rel-11","C4","2010-06-04","2012-09-07",1,"CP-110384","-","Telecom Italia","mauro.ficaccio@telecomitalia.it","CP#57 completed",29.335000000000001,48,25,null,null,"2010-05-26","2012-08-13"]
[6251,520108,"   CT4 part of enhanced Nodes Restoration for EPC","eNR_EPC",2,"Rel-11","C4","2011-06-03","2012-12-07",1,"CP-120449","-","ZTE","lu.fei1@zte.com.cn","CP#58 completed","23.007; 23.008; 23.018; 29.274; 29.275",52,27,null,null,"2011-05-18","2012-11-20"]
[6255,520009,"Reference Location Information (Stage 3)","RLI",1,"Rel-11","C4,C1","2011-06-03","2011-09-16",1,"CP-110386","-","Huawei","susan.shishufeng@Huawei.com","CP#53 completed. Stage 2 clause C.1.1 of SA2 TS 23.167 CR#0182 (WI code: TEI11)","-",52,27,null,null,"2011-05-18","2011-06-01"]
[6260,591001,"   (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 5 (RFC 7315)","IMSProtoc5",2,"Rel-11","C1-IETF","2013-03-01","2014-09-12",1,"CP-110437","-","Roland Jesske","Roland Jesske","CP#65 completed","RFC 7315 (was draft-drage-sipping-rfc3455bis); draft-mohali-dispatch-originating-cdiv-parameter",59,30,null,null,"2013-02-21","2014-09-02"]
[6262,611002,"   (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 5 (RFC 7135)","IMSProtoc5",2,"Rel-11","C1-IETF","2013-09-06","2014-06-13",1,"CP-110437","-","Roland Jesske","Roland Jesske","CP#64 completed","RFC 7135 (was draft-polk-local-emergency-rph-namespace)",61,31,null,null,"2013-08-23","2014-06-06"]
[6266,560008,"   Stage 2 for Service Identification for RRC Improvements in GERAN","SIRIG",2,"Rel-11","S2","2012-06-18","2012-09-07",1,"-","-","-","-","SP#57 completed","23.060; 23.251",56,29,null,null,"2012-06-18","2012-08-31"]
[6269,550009,"      Deleted - CT3 part of CN aspects of Service Identification for RRC Improvements in GERAN","SIRIG",3,"Rel-11","C3","2012-03-02","2012-06-15",1,"CP-120033","-","China Mobile","zhanghao@chinamobile.com","CP#56 stopped (SA2 decided NO CT3 impact)",29.212,55,28,"CP-56","PCG-29","2012-02-20","2012-04-20"]
[6271,530019,"SAE Protocol Development - Phase 2","SAES2",1,"Rel-11","C1","2011-09-16","2012-09-07",1,"CP-110639","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#57 completed. Stage 3 continuation of Rel-8 Feature SAES (3GPP System Architecture Evolution Specification - Evolved Packet System) UID_320005","-",53,27,null,null,"2011-08-27","2012-08-14"]
[6274,530020,"GCSMSC and GCR Redundancy for VGCS/VBS (Stage 2/3)","RT_VGCS_Red",1,"Rel-11","C1","2011-09-19","2012-09-07",1,"CP-120279","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#57 completed. Stage 2/3 adding a CN internal functionality, not affecting Voice Group Call Service (VGCS)/VBS as perceived by service subscriber. Hence, no Stage 1 impact for VGCS/VBS (42.068, 42.069)","Stage 2/3",53,27,null,null,"2011-08-27","2012-08-14"]
[6278,540017,"Enhancements for Multimedia Priority Service (MPS) – Gateway Control Priority","eMPS_Gateway",1,"Rel-11","C4,C3","2011-12-02","2012-09-07",1,"CP-110806","-","Telcordia","Viqar Shaikh","CP#57 completed. Stage 3. Stage 1 for MPS in 22.153. Details of any MGW actions for priority needs to be further studied within the scope of this WI.","Stage 3",54,28,null,null,"2011-10-26","2012-08-13"]
[6282,560005,"AT commands for Universal Resource Identifier (URI) support","ATURI",1,"Rel-11","C1","2012-06-15","2013-03-01",1,"CP-120275","-","Intel","frank.kowalewski@intel.com","CP#59 completed. Define new AT cmd for URI addresses for IMS services (eg VoLTE). 27.007(AT cmd to control MT functions and GSM/UMTS/LTE network services from TE), 27.005(AT commands for SMS). Currently address types for AT cmd based on dialling#","27.005; 27.007",56,29,null,null,"2012-06-02","2013-02-16"]
[6287,570210,"   CT4 part of IMS Operator Determined Call Barring","IODB",2,"Rel-11","C4","2012-09-07","2013-03-12",1,"CP-120685","-","Orange","Youssef.Chadli@Orange.com","CP#58 completed","23.008 ; 23.015 ; 29.328 ; 29.329 ; 29.364",57,29,null,null,"2012-08-13","2012-11-17"]
[6289,570111,"   CT3 part of Enhanced T.38 FAX support","MMTel_T.38_FAX",2,"Rel-11","C3","2012-09-07","2012-12-07",1,"CP-120673","-","NEC","Naoaki Suzuki (n-suzuki@en.jp.nec.com)","CP#58 completed",29.163,57,29,null,null,"2012-08-13","2012-11-20"]
[6293,540116,"   Deleted - TR Study on enhancement of protocols for SMS service over SGs","PROTOC_SMS_SGs",2,"Rel-11","C4","2011-12-02","2012-06-15",1,"CP-120034","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#56 stopped (abandonned new TR 29.818)","new 29.818",54,28,"CP-56","PCG-29","2011-10-26","2012-06-19"]
[6296,510001,"Full Support of Multi-Operator Core Network by GERAN","Full_MOCN-GERAN",1,"Rel-11","G2,S2,C1","2011-03-04","2013-05-17",1,"GP-121090","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","GP#58 completed. GP#49 approved WID. Standardization of management of MOCN supporting MSs/UES in CP-150GERAN. Continuation of Rel-10 MOCN-GERAN UID_490001","GERAN",49,26,null,null,"2011-03-04","2013-05-17"]
[6298,510201,"   Stage 2 for Full Support of Multi-Operator Core Network by GERAN","Full_MOCN-GERAN",2,"Rel-11","S2","2011-06-08","2012-03-07",1,"SP-110390","-","Alcatel-Lucent","nicolas.drevon@alcatel-lucent.com","SP#55 completed","23.251; 23.272",49,26,null,null,"2011-03-04","2011-12-06"]
[6301,560004,"      CT4 part of CN Stage 3 for Full Support of Multi-Operator Core Network by GERAN","Full_MOCN-GERAN",3,"Rel-11","C4","2012-06-13","2012-09-07",1,"CP-120563","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","CP#57 completed",23.003,54,29,null,null,"2012-06-02","2012-11-19"]
[6305,540203,"   Perf. part: Medium range/local area requirements for multicarrier BTS","MRLA-Perf",2,"Rel-11","G1","2011-11-28","2012-11-23",1,"GP-111782","-","Ericsson","Eric Nordström","Test spec. GP#56 completed. GP#52 approved WID",51.021000000000001,52,28,null,null,"2011-11-25","2012-11-23"]
[6309,500220,"   Perf. part: Extending 850 MHz Upper Band (814 – 849 MHz)","e850_UB-Perf",2,"Rel-11","R4","2010-12-10","2012-03-02",1,"RP-111396","RP-120076","Sprint","John.J.Humbert@Sprint.com","RP#55 completed","25.101; 25.104; 25.113; 25.133; 25.141; 25.461; 25.466; 36.101; 36.104; 36.124; 36.133; 36.141; 36.307; 36.331; 37.104; 37.113; 37.141",50,26,null,null,"2010-12-10","2012-02-23"]
[6314,530133,"   Core part: Enhancement of Minimization of Drive Tests for E-UTRAN and UTRAN","eMDT_UMTSLTE-Core",2,"Rel-11","R2,R1,R3,R4","2011-09-19","2012-12-07",1,"RP-121204","RP-121556","MediaTek","Johan Johansson","RP#58 completed","25.133; 25.123; 25.304; 25.331; 25.413; 25.423; 36.133; 36.304; 36.306; 36.331; 36.413; 36.423; 37.320; 36.300",53,27,null,null,"2011-09-15","2012-11-27"]
[6317,530136,"   Core part: Network Energy Saving for E-UTRAN","Netw_Energy_LTE-Core",2,"Rel-11","R3","2011-09-19","2012-09-07",1,"RP-120620","RP-121016","China Mobile","yangning@chinamobile.com","RP#57 completed. Inter-RAT aspect can affect UTRA and GERAN as well","25.413; 36.300; 36.413; 36.423",53,27,null,null,"2011-09-15","2012-09-06"]
[6319,530037,"E-UTRA medium range and MSR medium range/local area BS class requirements","medBS_class_LTE_MSR",1,"Rel-11","R4,G1","2011-09-19","2012-12-07",1,"RP-111383","-","Ericsson","johan.skold@ericsson.com","Stage 3. GERAN BS RF requirements specs need aligned with RAN4 ongoing Rel-11 Feature UID_530037 E-UTRA medium range and MSR medium range/local area BS class requirements (medBS_class_LTE_MSR)","UTRA; LTE; GERAN",53,27,null,null,"2011-09-15","2011-09-15"]
[6324,550115,"   Core part: RF Requirements for Multi-Band and Multi-Standard Radio (MB-MSR) Base Station","MB_MSR_RF-Core",2,"Rel-11","R4,G1","2012-02-06","2012-12-07",1,"RP-120857","RP-121985","Huawei","Liu Ye (leo.liuye@huawei.com)","RP#58 completed","25.104; 25.105; 36.104; 37.104; new 37.812",55,28,null,null,"2012-02-23","2012-12-05"]
[6325,550215,"   Perf. part: RF Requirements for Multi-Band and Multi-Standard Radio (MB-MSR) Base Station","MB_MSR_RF-Perf",2,"Rel-11","R4,G1","2012-03-08","2014-03-06",1,"RP-120857","RP-140064","Huawei","Liu Ye (leo.liuye@huawei.com)","RP#63 completed","25.141; 25.142; 36.141; 37.141",55,28,null,null,"2012-02-23","2014-03-03"]
[6328,560014,"Further enhancements to H(e)NB mobility - Part 2","EHNB_enh2",1,"Rel-11","R3,R2","2012-06-19","2012-12-07",1,"RP-121712","-","Alcatel-Lucent","Martin.Warner@alcatel-lucent.com","Stage 2/3. Legacy UE Handling (X2-GW, 20% complete, moved to Rel-12 UID_580030). Triggered by FS_EHNB_enh (UTRA, LTE TR 37.803 under AI 12.3.2)","UTRA; LTE",56,29,null,null,"2012-06-13","2012-11-27"]
[{"$f":"A6332+1","v":6332},430211,"   Perf. part: Network-Based Positioning Support for LTE","LCS_LTE-NBPS-Perf",2,"Rel-11","R4","2009-03-24","2014-06-13",1,"RP-131259","RP-140626","TruePosition","terri.brooks@trueposition.com","RP#64 completed. TS 36.112v100 for 1-step Approval","36.111; new 36.112",43,22,null,null,"2009-03-06","2014-06-11"]
[6336,510021,"Further Enhanced Non CA-based ICIC for LTE","eICIC_enh_LTE",1,"Rel-11","R1,R2,R3,R4,R5","2011-03-22","2014-12-15",1,"RP-120860","-","China Mobile","ShenXiaodong@chinamobile.com","-","LTE",51,26,null,null,"2011-03-14","2012-12-05"]
[6341,510128,"   Core part: New Band LTE Downlink FDD 716-728 MHz (Band 29), Carrier Aggregation of Band 2 and Band 29 and of Band 4 and Band 29","LTE_DL_FDD700-Core",2,"Rel-11","R4","2011-03-22","2012-12-07",1,"RP-110710","RP-121604","AT&T","marc.grant@att.com ","RP#58 completed","36.101; 36.104; 36.141; 36.307",51,26,null,null,"2011-03-14","2012-11-26"]
[6344,510131,"   Core part: LTE RAN Enhancements for Diverse Data Applications","LTE_eDDA-Core",2,"Rel-11","R2","2011-03-18","2012-12-07",1,"RP-120256","RP-121571","BlackBerry","Gordon Young (gyoung@rim.com)","RP#58 completed","36.300; 36.321; 36.331; new 36.822",51,26,null,null,"2011-03-14","2012-11-29"]
[6346,510032,"LTE E850 - Lower Band for Region 2 (non-US), Band 27","LTE_e850_LB",1,"Rel-11","R1,R2,R4,R5","2011-03-23","2013-03-01",1,"RP-120602","-","NII Holdings","bill.shvodian@nii.com","Stage 3","LTE",51,26,null,null,"2011-03-14","2012-06-09"]
[6351,520117,"   Core part: LTE for 700 MHz Digital Dividend","LTE_APAC700-Core",2,"Rel-11","R4,R2,R3","2011-06-07","2012-06-15",1,"RP-110875","RP-120572","Ericsson","olav.queseth@ericsson.com","RP#56 completed. TR 36.820 v100 for Information and Approval","25.461; 25.466; 36.101; 36.104; 36.113; 36.124; 36.133; 36.307; 37.104; 37.113; new 36.820",52,27,null,null,"2011-06-02","2012-06-09"]
[6352,520217,"   Perf. part: LTE for 700 MHz Digital Dividend","LTE_APAC700-Perf",2,"Rel-11","R4","2011-06-09","2012-06-15",1,"RP-110875","RP-120573","Ericsson","olav.queseth@ericsson.com","RP#56 completed","36.133; 36.141; 37.141",52,27,null,null,"2011-06-02","2012-06-09"]
[6355,520119,"   Core part: Relays for LTE (part 2)","LTE_Relay2-Core",2,"Rel-11","R4","2011-06-07","2012-09-07",1,"RP-110914","RP-121008","Ericsson","christian.hoymann@ericsson.com ","RP#57 completed. TS 36.116, TR 36.826 v100 for Information & Approval. RP#52 Core part not completed in Rel-10","36.133; new RAN4 (36.116; 36.826)",52,27,null,null,"2011-06-03","2012-09-04"]
[6359,530231,"   Perf. part: Signalling and Procedure for Interference Avoidance for in-device coexistence","SPIA_IDC_LTE-Perf",2,"Rel-11","R4","2011-09-20","2012-12-07",1,"RP-111356","RP-121574","China Mobile","Zhenping HU","RP#58 completed",36.133000000000003,53,27,null,null,"2011-09-15","2012-11-27"]
[6364,530432,"   Perf. part: Coordinated Multi-Point Operation for LTE – Downlink","COMP_LTE_DL-Perf",2,"Rel-11","R4","2011-09-23","2013-12-06",1,"RP-111365","RP-131465","Samsung","xutao.zhou@samsung.com","RP#62 completed","36.101; 36.104; 36.133; 36.141; 36.307",53,27,null,null,"2011-09-15","2013-11-29"]
[6367,540125,"   Core part: Enhanced downlink control channel(s) for LTE Advanced","LTE_enh_dl_ctrl-Core",2,"Rel-11","R1,R2,R4","2011-12-09","2012-12-07",1,"RP-120871","RP-121579","Alcatel-Lucent","sigen.ye@alcatel-lucent.com","RP#58 completed","36.101; 36.211; 36.212; 36.213; 36.331",54,28,null,null,"2011-12-07","2012-11-28"]
[6371,550112,"   Core part: Public Safety Broadband High Power UE for Band 14 for Region 2","LTE_B14_PSBB_HPUE-Core",2,"Rel-11","R4","2012-03-05","2012-12-07",1,"RP-120362","RP-121581","Motorola Solutions","xiaowei.jin@motorolasolutions.com","RP#58 completed. TR 36.837 v100 for Information and Approval","36.101; new 36.837",55,28,null,null,"2012-02-23","2012-12-05"]
[6373,550013,"Improved Minimum Performance Requirements for E-UTRA: Interference Rejection","LTE_Interf_Rej",1,"Rel-11","R4,R5","2012-03-05","2014-09-12",1,"RP-120382","-","Renesas Mobile","Timo Roman","RP#58 completed. Triggered by FS_enh_perf_UE_LTE. Adds Perf. requirements for demodulation of the already specified PDSCH with the transmission modes defined in Rel-8 to Rel-10","LTE",55,28,null,null,"2012-02-23","2012-11-27"]
[6378,590007,"   Test part: Additional special subframe configuration for LTE TDD","LTE_TDD_add_subframe-UEConTest",2,"Rel-11","R5","2013-03-04","2013-06-14",1,"RP-130305","RP-130475","Huawei","Li Xiang (tricia.li@huawei.com)","RP#60 completed","36.508; 36.523-1; 36.523-2; 36.523-3",59,30,null,null,"2013-02-26","2013-06-04"]
[6379,580158,"Rel-11 LTE Carrier Aggregation","LTE_CA_Rel-11",1,"Rel-11","R1,R2,R3,R4,R5","2010-12-10","2014-12-12",1,"-","-","-","-","LTE_CA_Rel-11","LTE",58,30,null,null,"2012-11-30","2012-11-30"]
[6382,510230,"      Perf. part: LTE Carrier Aggregation Enhancements","LTE_CA_enh-Perf",3,"Rel-11","R4","2011-03-15","2014-12-12",1,"RP-121999","RP-141969","Nokia","lars.e.lindh@nokia.com","¦Stat Rep: RP-141377->RP-141969","36.101; 36.104; 36.133; 36.141",51,26,null,null,"2011-03-14","2015-01-12"]
[6387,480123,"         Core part: LTE Advanced Carrier Aggregation of Band 3 and Band 7","LTE_CA_B3_B7-Core",4,"Rel-11","R4","2010-12-10","2012-09-07",1,"RP-120830","RP-121022","TeliaSonera","Ralf.Schuh@TeliaSonera.com","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101; 36.104; 36.307; new generic 36.850",48,25,null,null,"2010-06-04","2012-09-04"]
[6391,500217,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 17","LTE_CA_B4_B17-Perf",4,"Rel-11","R4","2010-12-17","2012-12-07",1,"RP-121458","RP-121595","AT&T","marc.grant@att.com ","RP#58 completed","36.101; 36.104; 36.133; 36.307",50,26,null,null,"2010-12-10","2012-11-26"]
[6394,500218,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 13","LTE_CA_B4_B13-Perf",4,"Rel-11","R4","2010-12-21","2012-12-07",1,"RP-120905","RP-121594","Ericsson","christian.bergljung@ericsson.com ","RP#58 completed","36.101; 36.133; 36.141",50,26,null,null,"2010-12-10","2012-11-27"]
[6398,510023,"      LTE Advanced Carrier Aggregation of Band 5 and Band 12","LTE_CA_B5_B12",3,"Rel-11","R4,R2","2011-03-22","2012-12-07",1,"RP-120221","-","US Cellular","sebastian.thalanany@uscellular.com ","Stage 3. RP#58 completed","LTE",51,26,null,null,"2011-03-14","2012-11-27"]
[6400,510223,"         Perf. part: LTE Advanced Carrier Aggregation of Band 5 and Band 12","LTE_CA_B5_B12-Perf",4,"Rel-11","R4","2011-03-25","2012-12-07",1,"RP-120221","RP-121597","US Cellular","sebastian.thalanany@uscellular.com ","RP#58 completed","36.101; 36.104; 36.133; 36.307",51,26,null,null,"2011-03-14","2012-11-27"]
[6405,510125,"         Core part: LTE Advanced Carrier Aggregation of Band 2 and Band 17","LTE_CA_B2_B17-Core",4,"Rel-11","R4","2011-03-23","2012-09-07",1,"RP-110432","RP-121034","AT&T","marc.grant@att.com ","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101; 36.104; 36.133; 36.141; 36.307; new generic 36.850",51,26,null,null,"2011-03-14","2012-09-04"]
[6409,510226,"         Perf. part: LTE Advanced Carrier Aggregation of Band 4 and Band 5","LTE_CA_B4_B5-Perf",4,"Rel-11","R4","2011-03-25","2012-12-07",1,"RP-110433","RP-121589","AT&T","marc.grant@att.com ","RP#58 completed","36.101; 36.104; 36.133; 36.307",51,26,null,null,"2011-03-14","2012-11-26"]
[6410,510027,"      LTE Advanced Carrier Aggregation of Band 5 and Band 17","LTE_CA_B5_B17",3,"Rel-11","R4","2011-03-23","2012-12-07",1,"RP-110434","-","AT&T","marc.grant@att.com ","Stage 3. RP#58 completed","LTE",51,26,null,null,"2011-03-14","2012-11-26"]
[6414,530123,"         Core part: LTE Advanced Carrier Aggregation of Band 3 and Band 20","LTE_CA_B3_B20-Core",4,"Rel-11","R4","2011-09-19","2012-09-07",1,"RP-120887","RP-121046","Vodafone","tim.frost@vodafone.com","RP#57 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101; 36.104; 36.133; 36.307; new generic 36.850",53,27,null,null,"2011-09-15","2012-09-04"]
[6418,530224,"         Perf. part: LTE Advanced Carrier Aggregation of Band 8 and Band 20","LTE_CA_B8_B20-Perf",4,"Rel-11","R4","2011-09-23","2012-12-07",1,"RP-120888","RP-121601","Vodafone","Luis.Anaya@vodafone.com","RP#58 completed","36.101; 36.104; 36.133; 36.141",53,27,null,null,"2011-09-15","2012-11-27"]
[6421,530226,"         Perf. part: LTE Advanced Carrier Aggregation of Band 3 and Band 5","LTE_CA_B3_B5-Perf",4,"Rel-11","R4","2011-09-21","2012-09-07",1,"RP-120899","RP-121043","SK Telecom","Haesung Park","RP#57 completed","36.133; 36.141",53,27,null,null,"2011-09-15","2012-09-04"]
[6425,540020,"      LTE Advanced Carrier Aggregation of Band 11 and Band 18","LTE_CA_B11_B18",3,"Rel-11","R4,R2","2011-12-09","2012-12-07",1,"RP-120898","-","KDDI","Masaaki Obara (ms-obara@kddi.com)","Stage 3. RP#58 completed","LTE",54,28,null,null,"2011-12-07","2012-12-04"]
[6427,540220,"         Perf. part: LTE Advanced Carrier Aggregation of Band 11 and Band 18","LTE_CA_B11_B18-Perf",4,"Rel-11","R4","2011-12-15","2012-12-07",1,"RP-120898","RP-121603","KDDI","Masaaki Obara (ms-obara@kddi.com)","RP#58 completed",36.133000000000003,54,28,null,null,"2011-12-07","2012-12-04"]
[6432,540122,"         Core part: LTE Advanced Carrier Aggregation of Band 1 and Band 19","LTE_CA_B1_B19-Core",4,"Rel-11","R4,R2","2012-03-05","2012-09-07",1,"RP-120866","RP-120552","NTT DoCoMo","Hiromasa Umeda (umedah@nttdocomo.co.jp)","RP#56 completed. RP#59 new generic TR 36.850v100 for Information and Approval","36.101; 36.104; 36.133; 36.307; new generic 36.850",54,28,null,null,"2011-12-07","2012-06-15"]
[6436,540223,"         Perf. part: LTE Advanced Carrier Aggregation of Band 1 and Band 21","LTE_CA_B1_B21-Perf",4,"Rel-11","R4","2011-12-13","2012-12-07",1,"RP-121173","RP-121055","NTT DoCoMo","Hiromasa Umeda (umedah@nttdocomo.co.jp)","RP#57 completed","36.133; 36.141",54,28,null,null,"2011-12-07","2012-09-04"]
[6437,550018,"      LTE Advanced Carrier Aggregation of Band 3 and Band 8","LTE_CA_B3_B8",3,"Rel-11","R4","2012-03-05","2012-12-07",1,"RP-121162","-","KT","Chungwoo HWANG (cwhwang@kt.com)","Stage 3. RP#58 completed","LTE",55,28,null,null,"2012-02-23","2012-11-27"]
[6441,520015,"      LTE Advanced Carrier Aggregation in Band 38","LTE_CA_B38",3,"Rel-11","R4","2011-06-07","2012-09-07",1,"RP-110862","-","Huawei","ronnie.zhang@huawei.com","Stage 3. RP#57 completed. WI only covers intra-band contiguous and not non-contiguous aspects","LTE",52,27,null,null,"2011-06-02","2012-09-04"]
[6445,520116,"         Core part: LTE Advanced Carrier Aggregation in Band 41","LTE_CA_B41-Core",4,"Rel-11","R4","2011-06-07","2012-03-02",1,"RP-120249","RP-120126","Clearwire","michael.hart@clearwire.com","RP#55 completed. Updated WID RP-110673=>RP-120249. TR 36.827 v100 for Information + Approval","36.101; 36.104; 36.133; 36.141; 36.307; 37.104; new 36.833-1-41 [instead of 36.827]",52,27,null,null,"2011-06-02","2012-02-23"]
[6448,530128,"         Core part: LTE Advanced Carrier Aggregation in Band 7","LTE_CA_B7-Core",4,"Rel-11","R4","2011-09-19","2012-09-07",1,"RP-121193","RP-121062","China Unicom","Zhangchao Ma (mazc@chinaunicom.cn), Zhonghao Zhang (zhangzh306@chinaunicom.cn)","RP#57 completed. TR 36.831 v100 for Information & Approval","36.101; 36.104; 36.133; 36.141; 36.307; 37.104; 37.141; new 36.833-1-07 [instead of 36.831] ",53,27,null,null,"2011-09-15","2012-09-04"]
[6450,450016,"UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test","UEAnt_FSTest",1,"Rel-11","R4,R5","2009-09-18","2016-09-15",1,"RP-111381","-","CATR","Guo Lin (guolin@emcite.com)","-","UTRA",45,23,null,null,"2009-09-15","2011-09-17"]
[6456,500021,"UE demodulation performance requirements under multiple-cell scenario for 1.28Mcps TDD","LCR_TDD_UE_demod_mc",1,"Rel-11","R4,R5","2010-12-10","2012-03-02",1,"RP-111244","-","China Mobile","Li Nan (linan@chinamobile.com)","Stage 3","UTRA",50,26,null,null,"2010-12-10","2011-09-12"]
[6457,500121,"   Perf. part: UE demodulation performance requirements under multiple-cell scenario for 1.28Mcps TDD","LCR_TDD_UE_demod_mc-Perf",2,"Rel-11","R4","2010-12-10","2011-09-16",1,"RP-111244","RP-110996","China Mobile","Li Nan (linan@chinamobile.com)","RP#53 completed. TR 25.873v100 for Approval","25.102; new 25.873",50,26,null,null,"2010-12-10","2011-09-12"]
[6463,500422,"   Perf. part: Uplink Transmit Diversity for HSPA - Open Loop","HSPA_UL_TxDiv-OL-Perf",2,"Rel-11","R4","2010-12-14","2012-12-07",1,"RP-120367","RP-121545","Huawei","zongjie.wang@huawei.com","RP#58 completed","25.101; 25.133",50,26,null,null,"2010-12-10","2012-11-28"]
[6464,590008,"   Test part: Uplink Transmit Diversity for HSPA","HSPA_UL_TxDiv-UEConTest",2,"Rel-11","R5","2013-03-04","2014-06-13",1,"RP-130351","RP-140767","Qualcomm","Shubhang Vora (svora@qti.qualcomm.com)","RP#64 completed","34.121-1; 34.121-2; 34.123-1; 34.123-2; 34.123-3",59,30,null,null,"2013-01-29","2014-06-10"]
[6468,510019,"Non-contiguous 4C-HSDPA operation","NC_4C_HSDPA",1,"Rel-11","R4,R2,R3","2011-03-23","2013-03-01",1,"RP-110416","-","Ericsson","muhammad.kazmi@ericsson.com","-","UTRA",51,26,null,null,"2011-03-14","2013-02-27"]
[6472,510120,"   Core part: Further Enhancements to CELL_FACH","Cell_FACH_enh-Core",2,"Rel-11","R2,R1,R3,R4","2011-03-18","2012-12-07",1,"RP-111321","RP-121547","Qualcomm","Ravi Agarwal","RP#58 completed","25.101; 25.104; 25.133; 25.211; 25.212; 25.213; 25.214; 25.306; 25.308; 25.319; 25.321; 25.331; 25.423; 25.433",51,26,null,null,"2011-03-14","2012-11-27"]
[6475,530034,"HSDPA Multiflow Data Transmission","HSDPA_MFTX",1,"Rel-11","R2,R1,R3,R4,R5","2011-09-19","2015-03-13",1,"RP-111375","-","Nokia Siemens Networks","Alexander Sayenko","Stage 2,3","UTRA",53,27,null,null,"2011-09-15","2011-09-15"]
[6477,530234,"   Perf. part: HSDPA Multiflow Data Transmission","HSDPA_MFTX-Perf",2,"Rel-11","R4","2011-09-20","2013-09-06",1,"RP-111375","RP-130959","Nokia Siemens Networks","kamil.bechta@nsn.com","RP#61 completed","25.101; 25.104; 25.133; 25.141",53,27,null,null,"2011-09-15","2013-08-29"]
[6483,540109,"   Core part: MIMO with 64QAM for HSUPA","MIMO_64QAM_HSUPA-Core",2,"Rel-11","R1,R2,R3,R4","2011-12-09","2012-12-07",1,"RP-121794","RP-121554","Nokia Siemens Networks","Karri Ranta-aho","RP#58 completed","25.101; 25.104; 25.133; 25.211; 25.212; 25.213; 25.214; 25.215; 25.308; 25.321; 25.331; 25.423; 25.433; 26.306",54,28,null,null,"2011-12-07","2013-02-27"]
[6484,540209,"   Perf. part: MIMO with 64QAM for HSUPA","MIMO_64QAM_HSUPA-Perf",2,"Rel-11","R4","2011-12-13","2013-09-06",1,"RP-121794","RP-130960","Nokia Siemens Networks","kamil.bechta@nsn.com","RP#61 completed","25.101; 25.104; 25.133; 25.141",54,28,null,null,"2011-12-07","2013-08-29"]
[6490,560001,"Test - (Small) Technical Enhancements and Improvements for Rel-11","TEI11_Test",1,"Rel-11","R5,G3new","2012-06-15","2013-12-11",1,"-","-","-","-","-","-",56,29,null,null,"2012-06-13","2012-06-13"]
[6491,571004,"(IETF) (Small) Technical Enhancements and Improvements for Rel-11 (RFC 7077)","TEI11_IETF",1,"Rel-11","C4-IETF","2012-09-07","2013-12-06",1,"-","-","Lionel Morand","Lionel Morand","CP#62 completed","RFC 7077 (was draft-ietf-netext-update-notifications)",57,29,null,null,"2012-09-03","2013-11-28"]
[6495,480033,"Study on Support for 3GPP Voice Interworking with Enterprise IP-PBX","FS_VINE",1,"Rel-11","S1,S2","2010-09-23","2011-03-23",1,"SP-100411","-","Tatara Systems","Phillip Brown (pbrown@tatarasystems.com)","SP#51 completed. Support Interworking between 3GPP networks and Enterprise environments to provide enterprise voice services via 3GPP mobile devices",22.809000000000001,48,25,null,null,"2010-06-06","2011-06-06"]
[6499,440048,"Study on IPv6 Migration","FS_IP6M",1,"Rel-11","S2","2009-06-04","2011-06-08",1,"SP-090362","-","China Mobile","Li Lianyuan (lilianyuan@chinamobile.com), Liu Hong (liuhongyfw@chinamobile.com)","SP#52 completed",23.975000000000001,44,23,null,null,"2009-05-31","2011-05-26"]
[6503,480048,"Study on Single Sign On (SSO) Application Security for IMS - based on SIP Digest","FS_SSO_APS",1,"Rel-11","S3","2010-06-10","2012-06-20",1,"SP-100639","-","Nokia","Silke.Holtmanns@nokia.com","SP#56 completed. SP#55 TR 33.914v200 approved (converted 33.804). Study reuse of non-UICC credentials (in particular SIP Digest) to provide security for access to applications. Provide reference material for IMS based non-UICC based SSO to applications","33.914 converted to 33.804",48,25,null,null,"2010-06-07","2012-06-13"]
[6504,520036,"Study on Mobile 3D Video Coding","FS_M3DVC",1,"Rel-11","S4","2011-06-08","2012-06-20",1,"SP-110310","-","Orange","gilles.teniou@orange-ftgroup.com","SP#56 completed. Extends Rel-10 work on 3D video formats UID_480044 Improved Video Coding Support for PSS and MBMS",26.905000000000001,52,27,null,null,"2011-05-26","2012-08-20"]
[6510,480003,"Study on Signal Precoding enhancements for EGPRS2 DL","FS_SPEED",1,"Rel-11","G1,G2","2010-09-03","2012-03-02",1,"GP-111281","-","Ericsson","marten.sundberg@ericsson.com","GP#53 completed (03/12). GP#46 approved WID. ","GERAN 45.860",46,25,null,null,"2010-05-27","2012-03-02"]
[6511,470014,"Study on Coordinated Multi-Point operation for LTE","FS_CoMP_LTE",1,"Rel-11","R1,R2,R3","2010-12-10","2011-09-16",1,"RP-101425","RP-111343","Samsung","bruno.clerckx@samsung.com","RP#53 completed","LTE 36.819",47,24,null,null,"2010-03-19","2011-05-27"]
[6517,530055,"Study on Enhanced performance requirement for LTE UE","FS_enh_perf_UE_LTE",1,"Rel-11","R4,R1","2011-09-19","2012-03-02",1,"RP-111378","RP-120167","NTT DoCoMo","Yuta Sagae","RP#55 completed. TR 36.829 v100 for Information + Approval","LTE 36.829",53,27,null,null,"2011-09-19","2012-02-27"]
[6518,550022,"Study on Measurements of radio performances for LTE terminals - Total Radiated Power (TRP) and Total Radiated Sensitivity (TRS) test methodology","FS_LTE_OTA",1,"Rel-11","R4","2012-03-05","2012-09-07",1,"RP-120412","RP-121083","CATR","Xudong An (anxudong@emcite.com)","RP#57 completed","LTE 25.914; New 37.902",55,28,null,null,"2012-02-23","2012-09-03"]
[6522,500002,"Study on UE Application Layer Data Throughput Performance","FS_UE_App_Data_Perf",1,"Rel-11","R5,R4","2010-09-16","2011-09-16",1,"RP-101422","RP-111543","Spirent","ron.borsato@spirent.com","RP#54 completed","UTRA; LTE 37.901",50,26,null,null,"2010-12-08","2011-11-29"]
[6526,500014,"Study on Uplink MIMO","FS_UTRA_UL_MIMO",1,"Rel-11","R1","2010-12-10","2011-09-16",1,"RP-101432","RP-111048","Qualcomm","Sharad Sambhwani","RP#53 completed (1-step Approval)","UTRA 25.871",50,26,null,null,"2010-12-08","2011-09-02"]
[6530,510035,"Deleted - Study on Enhanced Uplink Transmission for LTE","FS_eUL_TX_LTE",1,"Rel-11","R1","2011-03-22","2012-06-15",1,"RP-120259","RP-120585","Huawei","Yongxing Zhou","RP#56 stopped. RP-120856 discussion: most content moved to Rel-11 Coordinated Multi-Point Operation for LTE – Uplink (COMP_LTE_UL) and RAN1 has no time to look at it","LTE 36.8xy",51,26,"RP-56","PCG-29","2011-03-21","2012-06-18"]
[6531,0,"--- RELEASE 10 ---","-",1,"Rel-10","CP,GP,RP,SP","2008-12-11","2011-09-21",1,"-","-","-","-","-","-",null,null,null,null,"2006-05-31","2010-02-09"]
[6537,460529,"      Stage 2 on eMPS for IMS Aspects","ePRIOR-St2",3,"Rel-10","S2","2009-12-10","2010-09-23",1,"SP-100647","-","Telcordia, NTT DoCoMo","Vijay Varma, Katsutoshi Nishida","22/01: acronym modified","23.002; 23.203; 23.221; 23.228; 23.272; 23.401",46,24,null,null,"2009-12-06","2015-01-22"]
[6538,460229,"   Deleted - TR 23.854 on Stage 2 on enhancements for Multimedia Priority Service","-",2,"Rel-10","S2","2009-12-10","2010-12-16",1,"SP-100647","-","Telcordia, NTT DoCoMo","Vijay Varma, Katsutoshi Nishida","SP#49 TR 23.854 v100 for Information. SP#50 moved to Rel-11 SRVCC aspect of enhancements for Multimedia Priority Service UID_480135 (place holder for solution alternatives and agreed functions to be reflected in affected existing TS)","new 23.854",46,24,"SP-50","PCG-27","2009-12-06","2010-11-30"]
[6544,410031,"   Stage 1 for Network Improvements for Machine-Type Communications","NIMTC",2,"Rel-10","S1","2008-09-18","2010-03-25",1,"SP-100863","-","KPN","toon.norp@tno.nl","SP#47 completed","22.011; New 22.368",41,21,null,null,"2008-09-15","2010-03-09"]
[6545,450028,"   Deleted - TR on Stage 2 for Network Improvements for Machine-Type Communications","NIMTC",2,"Rel-10","S2","2009-09-24","2010-12-16",1,"SP-100863","-","Samsung","erik.guttman@partner.samsung.com","SP#50 updated WID SP-090832=>SP-100863 (TR 23.888 not submitted for approval to conclude Rel-10 NIMTC as it will continue to serve as basis for Rel-11 SIMTC work item)","New 23.888",45,23,"SP-50","PCG-26","2009-09-21","2010-12-01"]
[6549,480005,"   CN part of Stage 3 for Network Improvements for Machine-Type Communications","NIMTC-CN",2,"Rel-10","C1,C4,C6","2010-06-04","2011-06-03",1,"CP-110442","-","Ericsson","mikael.wass@ericsson.com","CP#52 completed","Stage 3",48,25,null,null,"2010-05-26","2011-06-01"]
[6553,510005,"      CT6 part of Stage 3 for Network Improvements for Machine-Type Communications","NIMTC-CN",3,"Rel-10","C6","2011-03-18","2011-06-03",1,"-","-","Sagem-Orga","heiko.kruse@sagem-orga.com","CP#52 completed",31.102,51,26,null,null,"2011-03-10","2011-05-18"]
[6557,570004,"   UE Conformance Test Aspects - Network Improvements for Machine-Type Communications","NIMTC-UEConTest",2,"Rel-10","R5","2012-09-11","2013-06-14",1,"RP-121124","RP-130465","Ericsson","calle.hagenfeldt@ericsson.com","RP#60 completed. Testing for CT1 part of Stage 3 UID_480105, RAN mechanisms to avoid CN overload due to MTC UID_490024","34.123-1; 34.123-2; 34.123-3; 36.523-1; 36.523-2; 36.523-3 ",57,29,null,null,"2012-09-05","2013-06-03"]
[6558,430035,"Multi Access PDN Connectivity","MAPCON",1,"Rel-10","S2,C4,C1,C3","2009-03-13","2011-03-18",1,"SP-090659","-","Telecom Italia","ivano.guardini@telecomitalia.it","CP#51 completed. SP#49 Stage 2 completed. Triggered by TR 23.861 UID_410043 FS_MAPIM. Stage 1 in Rel-9 22.278 (6.2 - IP session control)","-",43,22,null,null,"2009-03-05","2011-02-08"]
[6564,440052,"IMS Service Continuity – Inter Device Transfer enhancements","IMS_SC_eIDT",1,"Rel-10","S1,S2,C1,IETF","2009-06-04","2012-12-07",1,"SP-090452","-","Huawei","Amar Deol (adeol@huawei.com)","CP#51 completed. SP#47 Stage 1 completed. Rel-9 set Inter-Device Transfer requirements UID_410033 (IMS_SCC-IDT). Adds IDT scenarios and requirements","-",44,23,null,null,"2009-05-25","2010-03-09"]
[6567,470001,"   Stage 3 - IMS Inter-UE Transfer enhancements","IMS_SC_eIDT",2,"Rel-10","C1","2010-03-19","2011-03-18",1,"CP-110285","-","Huawei","georg.mayer@huawei.com ","CP#51 completed. WID updated CP-100334=>CP-110285","24.216; 24.229; 24.237; new (24.837; 24.337)",47,24,null,null,"2010-03-17","2011-03-17"]
[6569,450030,"IP-Short-Message-Gateway enhancements for CPM-SMS Interworking ","CPM-SMS",1,"Rel-10","S1,S2,C3","2009-09-24","2010-09-17",1,"SP-090615","-","China Mobile","Qing Huang (huangqing@chinamobile.com)","CP#49 completed. SP#47 Stage 1 completed. IP-SM-GW enhancements for interworking with OMA CPM","-",45,23,null,null,"2009-09-08","2010-03-09"]
[6573,450033,"Completion of Communications on Not Logged-in","CCNL",1,"Rel-10","S1,C1,C3","2009-09-24","2011-03-18",1,"SP-090493","-","Deutsche Telekom","Kurt Bischinger","CP#51 completed. SP#45 Stage 1 completed","-",45,23,null,null,"2009-09-08","2009-09-08"]
[6576,480006,"   CT3 part of Stage 3 for Completion of Communications on Not Logged-in","CCNL",2,"Rel-10","C3","2010-06-04","2010-09-17",1,"CP-100335","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#49 completed",29.164999999999999,48,25,null,null,"2010-05-26","2010-09-01"]
[6580,450039,"   Security for Local IP Access and Selected Internet IP Traffic Offload","LIPA_SIPTO",2,"Rel-10","S3","2009-09-24","2010-09-23",1,"SP-110131","-","Huawei, Qualcomm","Marcus Wong (mwong@huawei.com), Brian Rosenberg (bmr@qualcomm.com)","SP#49 completed","33.102; 33.107; 33.108; 33.320; 33.401",45,23,null,null,"2009-09-08","2010-07-23"]
[6584,450338,"      Stage 2 for Local IP Access","LIPA",3,"Rel-10","S2","2009-09-24","2010-09-23",1,"SP-110131","-","Huawei, China Mobile","patrice.hede@huawei.com, Tao Sun (suntao@chinamobile.com)","SP#49 completed (has impacts to RAN)","23.060; 23.401",45,23,null,null,"2009-09-08","2010-09-06"]
[6585,480008,"      Stage 3 for Local IP Access","LIPA",3,"Rel-10","C4,C1","2010-06-04","2011-03-18",1,"CP-100292","-","China Mobile","Zhang Hao (zhanghao@chinamobile.com) ","CP#51 completed","-",48,25,null,null,"2010-05-26","2010-05-26"]
[6591,480107,"         CT4 part of Stage 3 for SIPTO for macro networks","SIPTO",4,"Rel-10","C4","2010-06-04","2011-03-18",1,"CP-110091","-","Huawei","Caixia Qi (qcxmay@huawei.com)","CP#51 completed. Updated WID CP-100419=>CP-110091","23.003; 23.008; 29.002; 29.272; 29.303",48,25,null,null,"2010-05-26","2011-03-08"]
[6594,450042,"   Stage 1 for IP Flow Mobility and seamless WLAN offload","IFOM",2,"Rel-10","S1","2009-09-24","2009-12-10",1,"SP-100089","-","Qualcomm","David Williams (dwilliam@qualcomm.com)","SP#46 completed",22.277999999999999,45,23,null,null,"2009-09-08","2010-10-01"]
[6596,470021,"   Charging for IP Flow Mobility and seamless WLAN offload","IFOM",2,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-100089","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#51 completed","32.240; 32.251; 32.252; 32.298; 32.299",47,24,null,null,"2010-02-12","2011-03-09"]
[6600,450044,"Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA",1,"Rel-10","S2,S4,C4,C3,C1,IETF","2009-07-15","2012-09-07",1,"SP-100467","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","CP#52 completed. Triggered by Rel-9 UID_440013 Vocoder rate adaptation for LTE","UTRA; LTE",45,23,null,null,"2009-09-08","2011-05-23"]
[6603,450046,"   Stage 2 for Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA",2,"Rel-10","S2","2009-09-24","2010-09-23",1,"SP-100467","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","SP#49 completed","23.060; 23.203; 23.228; 23.401",45,23,null,null,"2009-09-08","2010-09-14"]
[6607,531006,"      (IETF) CT3, CT4 part of CN aspects of Enabling Coder Selection and Rate Adaptation for UTRAN and E-UTRAN for Load Adaptive Applications","ECSRA_LAA-CN",3,"Rel-10","C3-IETF,C4-IETF","2009-07-15","2012-09-07",1,"CP-100702","-","Lionel Morand","-","CP#57 completed","RFC 6679 (was draft-ietf-avtcore-ecn-for-rtp)",53,27,null,null,"2011-08-31","2012-09-03"]
[6612,420034,"   IMS aspects of Architecture for Home NodeB","EHNB-IMS",2,"Rel-10","S2","2008-12-11","2010-03-25",1,"SP-080799","-","Alcatel-Lucent","Nicolas Drevon","SP#47 completed. Chosen solution has no normative impacts","New 23.832",42,22,null,null,"2008-12-09","2010-02-26"]
[6615,460128,"   Stage 2 for Optimal Media Routing","OMR",2,"Rel-10","S2","2010-03-25","2010-03-25",1,"SP-090803","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com","SP#47 completed",23.228000000000002,46,24,null,null,"2009-12-06","2010-02-26"]
[6616,480010,"   Stage 3 for Optimal Media Routing","OMR",2,"Rel-10","C3,C1,C4","2010-06-04","2011-06-03",1,"CP-110134","-","Alcatel-Lucent","jim.calme@alcatel-lucent.com","CP#51 completion 03/11=>06/11. WID updated CP-100327=>CP-110134","-",48,25,null,null,"2010-05-26","2011-03-10"]
[6621,470026,"IMS Emergency Session Enhancements","IESE",1,"Rel-10","S1,S2,C1","2010-03-25","2011-06-03",1,"SP-100170","-","Deutsche Telekom, T-Mobile","michele.zarri@t-mobile.co.uk ","CP#52 completed. SP#49 completed. Source of external requirements: ETSI TISPAN TS 181.019 (Business Communication Requirements)","-",47,24,null,null,"2010-03-10","2011-05-23"]
[6623,470028,"   Stage 2 for IMS Emergency Session Enhancements","IESE",2,"Rel-10","S2","2010-03-25","2010-09-23",1,"SP-100170","-","Deutsche Telekom, T-Mobile","michele.zarri@t-mobile.co.uk ","SP#49 completed",23.167000000000002,47,24,null,null,"2010-03-10","2010-09-06"]
[6627,490009,"   Stage 3 for S2b Mobility based on GTP","SMOG-St3",2,"Rel-10","C4,C3,C1","2010-09-17","2011-03-18",1,"CP-100644","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#51 Stage 3 completed","-",49,25,null,null,"2010-09-01","2011-03-18"]
[6630,490309,"      CT1 part of Stage 3 for S2b Mobility based on GTP","SMOG-St3",3,"Rel-10","C1","2010-09-17","2010-12-10",1,"CP-100644","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.com","CP#50 completed",24.302,49,25,null,null,"2010-09-01","2010-11-25"]
[6634,470029,"Lawful Interception in the 3GPP Rel-10","LI10",1,"Rel-10","S3","2010-03-25","2011-06-08",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#52 completed","33.106 (LI requirements); 33.107 (LI architecture and functions); 33.108 (Handover interface for LI)",47,24,null,null,"2010-02-23","2011-03-12"]
[6639,470529,"   LI for MEDIASEC (IMS Media security)","LI10",2,"Rel-10","S3","2010-03-25","2011-03-23",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#51 completed","33.106; 33.107; 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[6642,470829,"   LI for LCLS (Local Call Local Switch)","LI10",2,"Rel-10","S3","2010-03-25","2011-03-23",1,"SP-100108","-","PIDS, BT","Koen Jaspers (k.b.jaspers@minjus.nl), alex.leadbeater@bt.com","SP#51 completed","33.106; 33.107; 33.108",47,24,null,null,"2010-02-23","2011-03-12"]
[6643,470033,"Optimization of IMS based PSS and MBMS User Service","OPT_IMS_PSS_MBMS_US",1,"Rel-10","S4","2010-03-25","2011-03-23",1,"SP-100031","-","Ericsson","markus.kampmann@ericsson.com","SP#51 completed. Work to enhance UID_430046 Rel-9 IMS_PSS_MBMS_US_EXT",26.236999999999998,47,24,null,null,"2010-03-10","2011-03-02"]
[6648,480041,"Enhancements and Addition of Audio Tests to 26.131 and 26.132","EAAT",1,"Rel-10","S4","2010-06-10","2011-06-08",1,"SP-100306","-","Vodafone","ramin.afchar@vodafone.com","SP#52 completed. Reduce fragmentation in acoustic testing (3GPP SA4, ETSI STQ, GCF CAG, CTIA) & Review existing acoustic tests to determine need for new spec","26.131; 26.132",48,25,null,null,"2010-05-28","2011-05-17"]
[6650,460031,"Rel-10 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM10",1,"Rel-10","S5,C4","2009-12-10","2011-09-21",1,"-","-","-","-","OAM10 is an umbrella Feature also for OAM&P related TEI10 type of changes that are not part of any other dedicated feature/WI",30.82,46,24,null,null,"2009-12-01","2011-08-26"]
[6653,470035,"      IRP Solution Set specification organisation improvements","OAM-IRP-SS",3,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-100774","-","Nokia Siemens Networks, Huawei","Jörg Schmidt (J.Schmidt@nsn.com), Lan Zou (zlan@huawei.com) ","SP#51 completed","32.153; new (32.111-6.32.126.32.176.32.306.32.316.32.326.32.336.32.346.32.356.32.366.32.376.32.386.32.396.32.416.32.446.32.506/26/36.32.606.32.616.32.626.32.636.32.646.32.656.32.666.32.676.32.696.32.716.32.726.32.736.32.746.32.756.32.766.32.776.32.786)",47,24,null,null,"2010-02-12","2011-03-09"]
[6658,460034,"   Rel-10 Self-Organizing Networks (SON) - OAM aspects","OAM10-SON",2,"Rel-10","S5","2009-12-10","2011-06-08",1,"-","-","-","-","umbrella BB","-",46,24,null,null,"2009-12-01","2009-12-12"]
[6661,470037,"      OAM aspects of Energy Saving in Radio Networks","OAM-ES",3,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-110128","-","Nokia Siemens Networks","clemens.suerbaum@nsn.com","SP#51 completed. WID updated SP-100226=>SP-110128. Triggered by Rel-10 TR 32.826 Study on Telecommunication Management¦Energy Savings Management (FS_OAM_ESM) UID_430044","32.425; 32.522; 32.526; 32.626; 32.762; 32.766; new 32.551",47,24,null,null,"2010-02-12","2011-03-17"]
[6666,470042,"      Management of UE based network performance measurements","OAM-PM-UE",3,"Rel-10","S5,C4","2010-03-25","2011-06-08",1,"SP-100612","-","Huawei, Nokia Siemens Networks, Ericsson","Zou Lan (zlan@huawei.com), gyula.bodog@nsn.com, ulf.hubinette@ericsson.com","SP#52 completed. Stage 2/3. Linked to UID_460003 Minimization of drive tests for E-UTRAN and UTRAN (MDT_UMTSLTE)","-",47,24,null,null,"2010-02-12","2011-03-22"]
[6669,470043,"      3G HNB and LTE HeNB Subsystem performance measurements","OAM-PM-HeNS",3,"Rel-10","S5","2010-03-25","2011-03-23",1,"SP-100081","-","China Mobile","Chen Gang (chengang@chinamobile.com)","SP#51 completed","32.582; 32.592; new (32.452; 32.453)",47,24,null,null,"2010-03-08","2011-03-09"]
[6670,470044,"Rel-10 Charging Management small Enhancements","CH10",1,"Rel-10","S5","2009-06-04","2011-03-23",1,"-","-","-","-","CH10 is an umbrella Feature also for OAM&P related TEI10 type of changes that are not part of any other dedicated feature/WI",30.82,47,24,null,null,"2010-02-12","2010-02-12"]
[6675,470003,"IMS Stage 3 IETF Protocol Alignment - phase 4","IMSProtoc4",1,"Rel-10","C1","2010-03-19","2011-03-18",1,"CP-100099","-","Alcatel-Lucent","keith.drage@alcatel-lucent.com","CP#51 completed. Ensure protocol alignment between 3GPP Stage 3 IMS work and IETF. Review capabilities provided in SIP by IETF and document whether these capabilities are supported in the IM CN Subsystem or not","23.218; 24.229; 24.930",47,24,null,null,"2010-03-17","2011-02-28"]
[6677,480014,"Further improvements of II-NNI Stage 3 based on operational feedback and evolution of other specifications","II-NNI2",1,"Rel-10","C3","2010-06-04","2013-03-01",1,"CP-100326","-","Orange","beata.dobrowolska@orange-ftgroup.com","Improvements of Rel-9 Feature UID_440027 Operational description of the Inter-IMS Network to Network Interface (II-NNI)","-",48,25,null,null,"2010-05-26","2013-02-21"]
[6680,561002,"   (IETF) Further improvements of II-NNI Stage 3 (RFC 6809)","II-NNI2",2,"Rel-10","C3-IETF","2012-04-20","2012-12-07",1,"CP-100326","-","christer.holmberg@ericsson.com","Christer Holmberg","CP#58 completed","RFC 6809 (was draft-ietf-sipcore-proxy-feature)",56,29,null,null,"2012-04-20","2012-12-04"]
[6685,500007,"Introduction of Smart Card Web Server launch functionality","SCWS_L",1,"Rel-10","C6","2010-12-10","2011-03-18",1,"CP-100883","-","Telecom Italia","davide.pratone@telecomitalia.it","CP#51 completed. Define a solution which allows enabling to launch Smart Card Web Server servicES in CP-150an easy and simple manner",31.102,50,26,null,null,"2010-11-28","2011-03-03"]
[6689,500210,"   CT4 part of Stage 3 for SRVCC enhancements","eSRVCC",2,"Rel-10","C4","2010-12-10","2011-03-18",1,"CP-100881","-","China Mobile","Jiang Y (jiangyi@chinamobile.com)","CP#51 completed","23.003; 23.008; 29.002; 29.230; 29.272; 29.305; 29.328; 29.329",50,26,null,null,"2010-10-25","2011-02-28"]
[6693,570005,"   Conformance test aspects SRVCC in alerting phase","aSRVCC-UEConTest",2,"Rel-10","R5","2012-09-11","2013-03-01",1,"RP-121700","RP-130042","NTT DoCoMo","Takao.Shimizu.rp@nttdocomo.com","RP#59 completed","36.523-1; 36.523-2; 36.523-3; 34.229-1; 34.229-2; 34.229-3",57,29,null,null,"2012-09-05","2013-02-27"]
[6696,500212,"   CT3 part of PCRF failure and restoration","PCRF_FR",2,"Rel-10","C3","2010-12-10","2011-03-18",1,"CP-100703","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","CP#51 completed","Stage 3 29.212; 29.213; 29.214; 29.215",50,26,null,null,"2010-10-25","2011-03-01"]
[6698,510007,"CS and IMS Interworking for CAT service - Early Session model","CIIC_ES",1,"Rel-10","C3","2011-03-16","2011-06-03",1,"CP-110283","-","ZTE","li.shitao@zte.com.cn","CP#52 completed. Stage 1 in Rel-8 TS 22.182 Customized Alerting Tones (CAT) service. Stage 3 TS 24.182 defines 3 impl models: Gateway, Forking, Early Session. Specify missing CAT service interworking procedures btw CS & IMS networks","Stage 3 29.163; 29.235; 29.292",51,26,null,null,"2011-03-02","2011-03-10"]
[6701,510009,"Mobile Terminating Roaming Forwarding with pre-paging","MTRF",1,"Rel-10","C4","2011-03-16","2011-06-03",1,"CP-110093","-","Ericsson","philip.hodges@ericsson.com","CP#52 completed. Provides Stage 2/3 alternative solution to Mobile Terminating Roaming Retry to solve roaming events during paging, in particular to support CSFB. Hence, no new Stage 1 requirements exist","Stage 2/3: 23.012; 23.018; 23.116; 29.002",51,26,null,null,"2011-02-22","2011-03-08"]
[6704,510210,"   CT1 part of UICC access to IMS Specification","IMS-UICC-S",2,"Rel-10","C1","2011-03-16","2011-06-03",1,"CP-110279","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#52 completed",24.228999999999999,51,26,null,null,"2011-03-03","2011-05-18"]
[6707,440022,"   TR on CN aspects of Local Call Local Switch","LCLS-CN",2,"Rel-10","C4","2009-05-29","2010-09-16",1,"CP-100867","-","Vodafone","David.Hutton@vodafone.com","CP#49 completed","new 23.889",44,23,null,null,"2009-05-13","2010-12-09"]
[6712,480002,"Tightened Link Level Performance Requirements for Single Antenna MS","TIGHTER",1,"Rel-10","G1,G2,C1,G3new","2010-09-03","2013-03-01",1,"GP-101083","-","Renesas Mobile","carsten.juncker@renesasmobile.com","GP#46 approved WID","GERAN",46,25,null,null,"2010-05-27","2013-03-16"]
[{"$f":"A6716+1","v":6716},490001,"Support of Multi-Operator Core Network by GERAN","MOCN-GERAN",1,"Rel-10","G2,S2,C1","2010-05-21","2011-03-04",1,"GP-101443","-","Alcatel-Lucent","michel.robert@alcatel-lucent.com","GP#47 approved WID. 900 MHz spectrum re-farming to other RATs lead operators to reduce GSM capacity and therefore share their GSM networks. Hence the need for the most suitable (GE)RAN sharing method","GERAN",47,25,null,null,"2010-05-27","2011-03-04"]
[6720,490002,"Enhancements of Iur-g interface","eIurg",1,"Rel-10","G2,R3","2010-09-03","2011-06-03",1,"GP-101758","-","China Mobile, ZTE","Ms Juan Deng (dengjuan@chinamobile.com), Xinhui Wang (wangxinhui@zte.com.cn)","GP#47 approved WID","GERAN.UTRA",47,25,null,null,"2010-09-05","2011-05-26"]
[6723,380077,"1.28 Mcps TDD Repeater","RANimp-Repeaters1.28TDD",1,"Rel-10","R4","2007-12-04","2010-03-19",1,"RP-071003","RP-100039","RITT","qinyan@chinattl.com","RP#47 completed","UTRA 25.113; New 25.116; 25.153 (testing)",38,21,null,null,"2007-12-17","2010-03-09"]
[6725,460014,"1.28 Mcps TDD Home NodeB RF requirements","HNB_LCRTDD_RF",1,"Rel-10","R4","2009-12-04","2010-12-10",1,"RP-100607","-","TD Tech","Li Rong (lirong@td-tech.com)","RP#50 completed. Triggered by FS_RAN-HNBLCRTDD UID_410016 Study on 1.28 Mcps TDD Home NodeB (TR 25.866)","UTRA",46,24,null,null,"2009-11-30","2010-12-03"]
[6728,470012,"Multi-User Multiple-Input and Multiple-Output (MU-MIMO) for 1.28Mcps TDD","MUMIMO_LCR_TDD",1,"Rel-10","R1,R2,R3,R4","2010-03-19","2011-06-03",1,"RP-100347","-","CATT","Yanping Xing (xingyanping@datangmobile.cn)","RP#52 completed","UTRA",47,24,null,null,"2010-03-19","2010-03-23"]
[6731,450027,"AGNSS Minimum Performance for UTRAN","AGNSSPerf_UTRAN",1,"Rel-10","R4,R5","2009-09-18","2011-09-16",1,"RP-100363","-","Thales","Michel.monnerat@thalesaleniaspace.com","RP#53 completed. Triggered by Rel-7 UID_20050 (GNSS in UTRAN) and Rel-8 UID_400051 (Support for Additional NSS). Linked to GERAN Rel-9 UID_38002 (AGNSS Performances and Testing Procedures)","UTRA",45,23,null,null,"2009-09-15","2010-12-08"]
[6734,460005,"Inclusion of RF Pattern Matching Technologies as positioning method in the UTRAN","LCS_UMTS_RFPMT",1,"Rel-10","R2,R3","2009-12-04","2011-03-18",1,"RP-091427","RP-110048","Polaris Wireless","Norman Shaw (nshaw@polariswireless.com)","RP#51 completed. Triggered by Study UID_380079 Evaluation of the inclusion of Path Loss Based Technology in the UTRAN (25.907)","UTRA",46,24,null,null,"2009-11-30","2011-03-11"]
[6739,540006,"   Test part: Four carrier HSDPA","4C_HSDPA-UEConTest",2,"Rel-10","R5","2011-12-02","2013-09-06",1,"RP-111565","RP-130940","Qualcomm","Shubhang Vora (svora@qualcomm.com)","RP#61 completed","34.108; 34.121-1; 34.121-2; 34.123-1; 34.123-2; 34.123-3",54,28,null,null,"2011-11-24","2013-08-29"]
[6743,480020,"Automatic Neighbour Relation (ANR) for UTRAN","ANR_UTRAN",1,"Rel-10","R3,R2,R5","2010-06-04","2012-12-07",1,"RP-100688","-","ZTE","Zhai.hengxing@zte.com.cn","RP#52 Core completed. Automatic Neighbour Relation (ANR) function for UTRAN relieves operators from the burden of manually managing the Neighbour cell Relations (NRs)","UTRA",48,25,null,null,"2010-06-03","2013-04-15"]
[6747,480121,"   Core part: Support of New Band Combinations for Dual-Band Dual Cell HSDPA","DB_DC_HSDPA-Core",2,"Rel-10","R4,R2","2010-06-04","2011-06-03",1,"RP-100657","RP-110523","AT&T","Vince Spatafora (vs5785@att.com)","RP#52 completed. RP#62 existing TS 25.317 replaced by new TS 25.327","25.101; 25.104; 25.141; 25.317 replaced by new 25.327",48,25,null,null,"2010-06-03","2011-05-24"]
[6750,490023,"   Core part: MIMO operation with non-MIMO coexistence in HSDPA","MIMO_HSDPA-Core",2,"Rel-10","R4","2010-09-17","2011-06-03",1,"RP-100993","RP-110524","Qualcomm","Heechoon Lee","RP#52 completed",25.103999999999999,49,25,null,null,"2010-09-10","2011-05-27"]
[6752,510017,"   Test part: MIMO operation with non-MIMO coexistence in HSDPA","MIMO_HSDPA-UEConTest",2,"Rel-10","R5","2011-03-18","2012-03-02",1,"RP-110244","RP-120042","Qualcomm","Shubhang Vora (svora@qualcomm.com)","RP#55 completed","34.108; 34.121-1; 34.121-2; 34.123-1; 34.123-2; 34.123-3",51,26,null,null,"2011-03-10","2012-02-23"]
[6755,460107,"   Core part: Carrier Aggregation for LTE","LTE_CA-Core",2,"Rel-10","R1,R2,R3,R4","2009-12-04","2011-06-03",1,"RP-100661","RP-110535","Nokia","lars.e.lindh@nokia.com","RP#52 completed. RP#56 new RAN4 TR (36.807, 36.808) v200 for Approval","36.101; 36.104; 36.133; 36.211; 36.212; 36.213; 36.300; 36.302; 36.306; 36.321; 36.331; 36.413; 36.423; 37.104; new RAN4 (36.807; 36.808)",46,24,null,null,"2009-11-30","2012-06-07"]
[6759,460108,"   Core part: Enhanced Downlink Multiple Antenna Transmission for LTE","LTE_eDL_MIMO-Core",2,"Rel-10","R1,R2,R4","2009-12-04","2011-03-18",1,"RP-100196","RP-110067","NTT DoCoMo","Hidekazu Taoka (taoka@nttdocomo.com)","RP#51 completed. RP#56 new RAN4 TR 36.807 v200 for Approval","36.101; 36.104; 36.133; 36.201; 36.211; 36.212; 36.213; 36.300; 36.306; 36.321; 36.331; new RAN4 36.807",46,24,null,null,"2009-11-30","2012-06-07"]
[6761,560012,"   Test part: Enhanced Downlink Multiple Antenna Transmission for LTE","LTE_eDL_MIMO-UEConTest",2,"Rel-10","R5","2012-06-18","2013-06-14",1,"RP-120612","RP-130464","ZTE","Carolyn Taylor (carolyn.tayl@zte.com.cn)","RP#60 completed. Testing for 36.101, 36.133","36.508; 36.521-1; 36.521-2",56,29,null,null,"2012-06-06","2013-06-04"]
[6766,460013,"Relays for LTE","LTE_Relay",1,"Rel-10","R1,R2,R4,S2,S3,C4,C6","2009-12-04","2011-06-08",1,"RP-110911","-","Ericsson","christian.hoymann@ericsson.com","RP#52 completed (open RAN4 Core & Perf parts moved to new Rel-11)","LTE",46,24,null,null,"2009-11-30","2011-02-14"]
[6770,500038,"   LTE Relay Nodes Security","LTE_Relay-Sec",2,"Rel-10","S3,C6","2010-12-16","2011-03-22",1,"SP-100733","-","Qualcomm","Adrian Escott (aescott@qualcomm.com)","-","-",50,26,null,null,"2010-11-25","2011-02-14"]
[6774,510012,"   Core Network Impacts for Relay Nodes","LTE_Relay-CN",2,"Rel-10","C4","2011-03-16","2011-03-18",1,"CP-110094","-","Vodafone","David.Hutton@vodafone.com","CP#51 completed","23.003; 23.008; 29.303; 29.230; 29.272",51,26,null,null,"2011-02-28","2011-03-08"]
[6777,470207,"   Perf. part: Enhanced Inter-Cell Interference Control (ICIC) for non-Carrier Aggregation (CA) based deployments of heterogeneous networks for LTE","eICIC_LTE-Perf",2,"Rel-10","R4","2010-03-19","2012-06-15",1,"RP-100383","RP-120461","China Mobile","Xiaodong XU (xuxiaodong@chinamobile.com)","RP#56 completed","36.101; 36.133",47,24,null,null,"2010-03-19","2012-06-05"]
[6779,470008,"LTE TDD in 2600MHz for US","LTE_TDD_2600_US",1,"Rel-10","R4,R2,R3,R5","2010-03-19","2010-12-10",1,"RP-101003","-","Clearwire","michael.hart@clearwire.com","RP#50 Testing completed. RP#49 Core+Perf completed","LTE",47,24,null,null,"2010-03-19","2010-12-03"]
[6782,480019,"   UE conformance test part: LTE TDD in 2600MHz for US","LTE_TDD_2600_US-UEConTest",2,"Rel-10","R5","2010-06-04","2010-12-10",1,"RP-100615","RP-101071","Clearwire","michael.hart@clearwire.com","RP#50 completed","36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-1; 36.523-2; 36.523-3",48,25,null,null,"2010-06-01","2010-12-03"]
[6788,470110,"   Core part: Adding L-Band (Band 24) LTE for ATC of MSS in North America","L_Band_LTE_ATC_MSS-Core",2,"Rel-10","R4,R2","2009-12-11","2010-12-10",1,"RP-101284","RP-101117","LightSquared","Eric.Jacks@lightsquared.com, Maqbool.Aliani@lightsquared.com","RP#51 completed","25.101; 25.104; 25.141; 25.461; 25.466; 34.124; 36.101; 36.104; 36.113; 36.124; 36.133; 36.307; 37.104; 37.141; new RAN4 36.813",47,24,null,null,"2010-03-19","2011-03-17"]
[6790,510015,"   Test part: Adding L-Band (Band 24) LTE for ATC of MSS in North America","L_Band_LTE_ATC_MSS-UEConTest",2,"Rel-10","R5","2011-03-18","2011-09-16",1,"RP-110777","RP-110980","LightSquared","masoud.olfat@lightsquared.com","RP#53 completed","36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-2",51,26,null,null,"2011-03-10","2011-09-06"]
[6793,480027,"Further enhancements to MBMS for LTE","MBMS_LTE_enh",1,"Rel-10","R2,R3,R5","2010-06-04","2012-03-02",1,"RP-101244","-","Huawei","Ms Zhao Junhui (zhaojh@huawei.com)","RP#51 completed. SA2 decided not to support MBR>GBR in Rel-10 MBMS. For SA2, MBR=GBR in Rel-10 MBMS. Hence RAN removed “enabling statistical multiplexing gains for variable bit rate services” in Objectives","LTE",48,25,null,null,"2010-06-04","2011-03-14"]
[6797,380073,"   Core part: UMTS/LTE 3500 MHz","RInImp8-UMTSLTE3500",2,"Rel-10","R4,R2,R3","2007-11-30","2011-09-16",1,"RP-091380","RP-110987","Ericsson","johan.skold@ericsson.com","RP#53 completed. TR 37.801v200 for Approval","25.101; 25.104; 25.113; 25.133; 25.141; 25.307; 25.307; 25.331; 25.461; 25.463; 34.124; 36.101; 36.104; 36.113; 36.141; 36.331; new 37.801",38,21,null,null,"2007-12-17","2011-09-09"]
[6801,460103,"   Core part: Minimization of Drive Tests for E-UTRAN and UTRAN","MDT_UMTSLTE-Core",2,"Rel-10","R2,R4,R3","2009-12-04","2011-06-03",1,"RP-100360","RP-110528","Nokia Siemens Networks","malgorzata.tomala@nsn.com","RP#52 completed","25.133; 25.215; 25.304; 25.331; 25.423; 36.133; 36.214; 36.300; 36.304; 36.331; 36.413; 36.423; new 37.320 (Stage 2)",46,24,null,null,"2009-11-30","2011-05-24"]
[6802,530041,"   Test part: Minimization of Drive Tests for E-UTRAN","MDT_UMTSLTE-UEConTest",2,"Rel-10","R5","2011-09-19","2013-03-01",1,"RP-120598","RP-130036","Ericsson","leif.mattisson@ericsson.com","RP#59 completed. Testing for LTE only","LTE 34.108; 34.109; 34.123-1; 34.123-2; 34.123-3; 36.508; 36.509; 36.523-1; 36.523-2; 36.523-3 ",53,27,null,null,"2011-09-06","2013-02-27"]
[6806,480024,"Expanded 1900 MHz Band for UTRA and LTE","E1900",1,"Rel-10","R4,R2,R5","2010-06-04","2012-09-07",1,"RP-100676","-","Sprint","nick.j.baustert@sprint.com","Expand UTRA and E-UTRA band 2 to include frequencies between 1910 – 1915 MHz and 1990-1995 MHz (US FCC allocation)","UTRA; LTE",48,25,null,null,"2010-06-04","2012-09-04"]
[6809,520013,"   Test part: Expanded 1900 MHz Band for UTRA and LTE","E1900-UEConTest",2,"Rel-10","R5","2011-06-07","2012-09-07",1,"RP-110712","RP-120957","Sprint","nick.j.baustert@sprint.com","RP#57 completed","34.108; 34.121-1; 34.121-2; 34.123-1; 34.123-2; 34.123-3; 36.508; 36.521-1; 36.521-2; 36.521-3; 36.523-1; 36.523-2; 36.523-3",52,27,null,null,"2011-05-23","2012-09-04"]
[6815,540001,"      GERAN BS Test part: Multi-Standard Radio BS RF requirements for non-contiguous spectrum deployments","MSR_NC-GERAN",3,"Rel-10","G1","2011-09-02","2011-11-25",1,"GP-101618","-","Ericsson","mats.y.samuelsson@ericsson.com ","GP#52 completed",51.021000000000001,52,28,null,null,"2011-11-25","2011-11-25"]
[6817,521004,"(IETF) (Small) Technical Enhancements and Improvements for Rel-10 (draft-atarius-dispatch-meid-urn) --> RFC8464","TEI10_IETF",1,"Rel-10","C1-IETF","2009-06-04","2014-12-04",1,"-","-","Andrew Allen","Andrew Allen","Not completed internet-draft, waiting for draft-montemurro to complete; 26/6/19: 75%->100; 23/4/20: 100%->100","draft-atarius-dispatch-meid-urn",52,27,null,null,"2011-06-20","2020-04-23"]
[6820,350014,"Deleted - Registration in Densely-populated area (RED)","RED",1,"Rel-10","S1","2007-03-12","2009-09-24",1,"SP-070133","-","NTT DoCoMo","tanakai@nttdocomo.co.jp","SP#35 Stage 1 completed. SP#45 Stage 2 work stopped. SP#46 work stopped/abandoned","-",35,18,"SP-46","PCG-24","2007-03-29","2009-12-07"]
[6824,380162,"   Deleted - Stage 1 for N3GtoNSP","N3GtoNSP",2,"Rel-10","S1","2007-12-07","2009-09-24",1,"SP-070874","-","Telefónica O2","chris.friel@O2.com","SP#45 work stopped/abandoned",22.010999999999999,38,21,"SP-45","PCG-23","2007-12-13","2009-09-21"]
[6828,430017,"Deleted - UTRAN 2 ms TTI uplink range improvement","RANimp-2mTTI_ULimp",1,"Rel-10","R1,R2,R3,R4","2009-03-06","2010-03-19",1,"RP-090333","RP-100040","Nokia Siemens Networks","Karri Ranta-aho (karri.ranta-aho@nsn.com)","RP#47 work stopped/abandoned (no CR approved). Cell sets the TTI (Transmission Time Interval) to 2 ms ","25.133; 25.212; 25.214; 25.321; 25.331",43,22,"RP-47","PCG-24","2009-10-07","2010-03-16"]
[6829,440043,"Deleted - Enhanced Home NodeB / eNodeB continuation of Rel-9","eEHNB",1,"Rel-10","S2","2008-12-11","2010-03-25",1,"-","-","Alcatel-Lucent","Nicolas Drevon","SP#47 deleted (SA2 work moved under SA1 UID_450053). SP#44 Umbrella Feature created to host WIs moved out of Rel-9 (SA2 UID_420034 on IMS aspects of Architecture for Home NodeB)","-",44,23,"SP-47","PCG-24","2007-12-13","2009-06-01"]
[6833,460012,"Deleted - Latency reductions for LTE","LTE_LATRED",1,"Rel-10","R2,R1","2009-12-04","2010-12-10",1,"RP-091449","-","Ericsson","henrik.enbuske@ericsson.com","RP#50 work stopped (RP-101266)","LTE",46,24,"RP-50","PCG-26","2009-11-30","2010-12-08"]
[6836,470106,"   Deleted - Core part: Enhanced Interference Management for Home NodeBs","HNB_IM-Core",2,"Rel-10","R3","2010-03-19","2010-09-17",1,"RP-100392","RP-100754","Qualcomm","Andrei Radulescu (aradules@qualcomm.com)","RP#49 stopped (no further standardization needed)","25.413; 25.467; 25.469",47,24,"RP-49","PCG-25","2010-03-19","2010-09-09"]
[6842,410039,"Study on Personal Broadcast Service","FS_PBS",1,"Rel-10","S1","2008-09-18","2010-03-25",1,"SP-080504","-","ETRI","Jaihyung Cho","SP#47 completed",22.946999999999999,41,21,null,null,"2008-09-15","2010-03-09"]
[{"$f":"A6844+1","v":6844},430030,"Study on Haptic Services","FS_Haptics",1,"Rel-10","S1","2009-03-12","2010-03-25",1,"SP-090664","-","SK Telecom","jinhan.song@sktelecom.com ","SP#47 completed. Covers Mobile/Fixed/Cordless/etc terminals. Haptic (human-machine tactile communication) extend service offering & richness of user experience beyond current visual & auditory senses",22.986999999999998,43,22,null,null,"2009-02-12","2010-08-11"]
[6847,440049,"Study on Single Radio Voice Call Continuity enhancements","FS_eSRVCC",1,"Rel-10","S2","2009-06-04","2010-09-23",1,"SP-090363","-","China Mobile","Hou zhiqiang (houzhiqiang@chinamobile.com), Jiang Yi (jiangyi@chinamobile.com)","SP#49 completed (Conclusion: select the SIP anchoring based solution for normative work CR (TEI10) introducing and completing stage-2). Analyzed performance of Rel-8 SRVCC solution from E-UTRAN/HSPA to UTRAN/GERAN",23.856000000000002,44,23,null,null,"2009-05-31","2010-09-06"]
[6851,480044,"Study on Improved Video Coding Support","FS_IVCS",1,"Rel-10","S4","2010-06-10","2011-03-23",1,"SP-100304","-","Nokia, ETRI","imed.bouazizi@nokia.com, jaihyung@etri.re.kr","SP#51 completed. Extends Rel-9 Improved Video Support for PSS and MBMS (UID_430039)",26.904,48,25,null,null,"2010-05-28","2011-02-18"]
[6855,460037,"Study on Alignment of 3GPP Generic NRM IRP and TMF Shared Information Data (SID) model","FS_3GNRM_TMFSID",1,"Rel-10","S5","2009-12-10","2011-03-23",1,"SP-090759","-","Nokia Siemens Networks","olaf.pollakowski@nsn.com","SP#51 completed",32.828000000000003,46,24,null,null,"2009-12-01","2011-03-09"]
[6856,460038,"Study on Harmonization of 3GPP Alarm IRP and TMF Interface Program (TIP) Fault Management","FS_3G_TMF_FM",1,"Rel-10","S5","2009-12-10","2011-03-23",1,"SP-090760","-","Nokia Siemens Networks, Alcatel-Lucent","olaf.pollakowski@nsn.com, Padma.Sudarsan@alcatel-lucent.com ","SP#51 completed",32.829000000000001,46,24,null,null,"2009-12-01","2011-03-22"]
[6860,480016,"Study on User Data Convergence (UDC) evolution ","FS_UDCe",1,"Rel-10","C4","2010-06-04","2011-03-18",1,"CP-100296","-","Alcatel-Lucent","jean-jacques.trottin@alcatel-lucent.com","CP#51 completed. Study UDC evolution from FeaturES in CP-150Rel-9 UID_400034 and Rel-10 UID_480011 UDC Data Model",23.844999999999999,48,25,null,null,"2010-05-26","2011-02-28"]
[6863,460016,"Study on Solutions for Energy Saving within UTRA Node B","FS_Energy_UMTS",1,"Rel-10","R1,R3","2009-12-04","2010-09-17",1,"RP-091439","RP-100796","Vodafone","Prakash.bhat@vodafone.com","RP#49 completed. Based on ETSI EE TS 102 706.","UTRA 25.927",46,24,null,null,"2009-11-30","2010-09-09"]
[6869,450012,"Deleted - Study on Interworking Proxy between GTP based and PMIP based interfaces","FS_GTP-MIP-IW",1,"Rel-10","C4","2009-09-18","2010-06-04",1,"CP-090517","-","NTT DoCoMo","takaaki.matsuura.sp@s1.nttdocomo.com","CP#48 work stopped/abandoned",29.875,45,23,"CP-48","PCG-25","2009-09-08","2010-05-26"]
[6871,400035,"Enhanced Home NodeB / eNodeB","EHNB",1,"Rel-9","S1,S2,S3,S5,C1,C6,R2,R3,R4,R5,GP","2008-06-05","2011-12-09",1,"SP-090214","-","T-Mobile","michael.kurz@t-mobile.at ","RP#54 Testing completed","UTRA; LTE",40,21,null,null,"2007-12-13","2011-11-29"]
[6874,420035,"   Security aspects of Enhanced Home NodeB / eNodeB","EHNB-Sec",2,"Rel-9","S3","2008-12-11","2009-12-10",1,"SP-080879","-","Huawei","Marcus Wong (mwong@huawei.com)","SP#46 completed","New 33.320",42,22,null,null,"2008-12-09","2009-12-07"]
[6879,440066,"   3G HNB and LTE HeNB OAM&P Type 2 Interface","HNB_eHNB-OAM_Type2",2,"Rel-9","S5","2009-05-15","2010-03-25",1,"SP-090315","-","Ericsson","edwin.tse@ericsson.com","SP#47 completed","New (32.571; 32.572)",44,23,null,null,"2009-05-18","2010-03-08"]
[6882,430025,"   Home NB and Home eNB enhancements - RAN3 aspects","EHNB-RAN3",2,"Rel-9","R3","2009-03-06","2009-12-04",1,"RP-090349","RP-091050","Alcatel-Lucent","Martin Warner (mw15@alcatel-lucent.com)","RP#46 completed (based on high priority items specified in RP-090995)","25.413; 25.467; 25.467; 25.468; 25.469; 25.469; 36.401; 36.413; New 25.444",43,22,null,null,"2009-03-10","2009-11-27"]
[6883,430026,"   Home NB and Home eNB enhancements - RAN2 aspects","EHNB-RAN2",2,"Rel-9","R2","2009-03-06","2010-03-19",1,"RP-091392","RP-100037","Huawei","Yang Xudong (yangxudong@huawei.com)","RP#47 completed","25.304; 25.331; 25.367; 36.300; 36.304; 36.331",43,22,null,null,"2009-03-10","2010-03-16"]
[6887,370026,"Value-Added Services for Short Message Service","VAS4SMS",1,"Rel-9","S1,C4,C1","2007-09-10","2009-12-04",1,"SP-070572","-","China Mobile","Wu Bin (wubin@chinamobile.com)","CP#46 completed","-",37,19,null,null,"2007-10-02","2009-11-16"]
[6890,410014,"   CT1 aspects of VAS4SMS Interface and Signalling Flow","VAS4SMS",2,"Rel-9","C1","2008-09-09","2009-12-04",1,"CP-090813","-","China Mobile","Wu Bin (wubin@chinamobile.com)","CP#46 completed",23.04,41,21,null,null,"2008-09-11","2009-12-02"]
[6896,380057,"Public Warning System","PWS",1,"Rel-9","S1,C1,C4,R2,R3,R5","2007-12-06","2012-12-07",1,"SP-070876","-","T-Mobile","Mark.Younge@t-mobile.com","TSG#46 completed. Larger scope than Rel-8 Feature UID_370051 (ETWS). Triggered by TR 22.968 Study UID_320025 (FS_PWS)","LTE",38,21,null,null,"2007-12-13","2009-12-03"]
[6898,440029,"   Stage 3 for Public Warning System","PWS-St3",2,"Rel-9","C1,C4","2009-05-29","2009-12-04",1,"CP-090437","-","Qualcomm","Ramachandran Subramanian (rsubrama@qualcomm.com)","RP#46 completed","-",44,23,null,null,"2009-05-13","2009-12-03"]
[6901,440005,"   Public Warning System (PWS) – RAN aspects","PWS-RAN",2,"Rel-9","R2,R3","2009-05-30","2009-12-04",1,"RP-090649","RP-091052","AT&T","don.zelmer@att.com","RP#46 completed","LTE 36.300; 36.302; 36.331; 36.413",44,23,null,null,"2009-05-20","2009-12-03"]
[6906,430102,"   Stage 3 for Support of Personal Area Networks and Enhancements to Personal Network Management","PAN_EPNM",2,"Rel-9","C1","2009-03-09","2010-06-04",1,"CP-090435","-","Huawei","Lili Yang (kadyyang@huawei.com)","CP#48 completed",24.259,43,22,null,null,"2009-03-05","2010-05-28"]
[6909,430031,"   Multimedia Telephony (MMTel) Service and Supplementary Services - Online Charging and completion for Offline Charging (all supplementary services)","eMMTel-SS-CH",2,"Rel-9","S5","2009-03-12","2010-03-25",1,"SP-090196","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#47 completed","32.275; 32.298; 32.299",43,22,null,null,"2009-02-26","2010-03-08"]
[6910,430032,"   Support of Real-time Transfer of Tariff Information (RTTI) in IMS charging","IMSTSS-RTTI-CH",2,"Rel-9","S5","2009-03-12","2010-03-25",1,"SP-090306","-","Orange","Jean-Luc Garcia (jl.garcia@orange-ftgroup.com)","SP#47 completed. Linked to SA5 Rel-8 UID_380042 AoC support in IMS Charging (IMSTSS)","32.240; 32.280; 32.298; 32.299",43,22,null,null,"2009-02-26","2010-03-08"]
[6914,430103,"   Stage 2/3 for User Data Convergence (UDC) Technical Realization","UDC-CN",2,"Rel-9","C4","2009-03-06","2010-03-19",1,"CP-090017","-","Ericsson","emiliano.merino@ericsson.com","-","-",43,22,null,null,"2009-03-04","2010-03-09"]
[6919,440061,"      UDC – Common Baseline Information Model","UDC-MMAN-CBIM",3,"Rel-9","S5","2009-06-04","2010-03-25",1,"SP-090310","-","China Mobile, Ericsson","Lan Si Zhong, Miguel Garcia","SP#47 completed","32.172; new 32.182 ",44,23,null,null,"2009-05-18","2010-03-08"]
[6922,410134,"   Stage 2/3 for IMS Service Continuity Enhancements: Service, Policy and Interactions","IMS_SCC-SPI",2,"Rel-9","S2,C1","2008-09-18","2010-03-19",1,"SP-080561","-","Huawei","HengLiang Zhang (hl_zhang@huawei.com)","-","-",41,21,null,null,"2008-09-15","2012-07-20"]
[6925,410135,"   Stage 2/3 for IMS Centralized Services","IMS_SCC-ICS",2,"Rel-9","S2,C1","2008-09-18","2010-03-19",1,"SP-080634","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com ","-","-",41,21,null,null,"2008-09-15","2009-06-02"]
[6928,430004,"   Stage 3 - IMS Centralized Services support via I1 interface","IMS_SCC-ICS_I1",2,"Rel-9","C1","2009-03-06","2010-03-19",1,"CP-090640","-","Huawei","Lili Yang(kadyyang@huawei.com)","CP#47 completed","24.237; 24.292; new 24.294",43,22,null,null,"2009-03-05","2010-03-02"]
[6933,380064,"Support for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPS",1,"Rel-9","S1,S2,S3,C1,C3,C4,R2,R3,R5,IETF","2000-01-03","2014-06-13",1,"SP-080844","-","Alcatel-Lucent","Deborah Barclay","RP#56 completed testing. CP#47 completed. SP#48 completed","GERAN; LTE",38,21,null,null,"2007-10-02","2012-06-05"]
[6936,420022,"   Security aspects for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPS-Sec",2,"Rel-9","S3","2008-12-12","2010-06-10",1,"SP-080844","-","Alcatel-Lucent","Deborah Barclay","SP#48 completed","33.401; 33.402",42,22,null,null,"2008-12-09","2010-05-05"]
[6937,440035,"   Stage 3 for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPS",2,"Rel-9","C1,C3,C4,R5","2009-05-29","2012-06-15",1,"CP-090564","-","Alcatel-Lucent","Frank Alfano (falfano@alcatel-lucent.com)","RP#56 completed testing. CP#47 completed","GERAN; LTE",44,23,null,null,"2009-05-13","2012-06-05"]
[6941,440038,"      CT4 aspects - Stage 3 for IMS Emergency Calls over GPRS and EPS","IMS_EMER_GPRS_EPSC4",3,"Rel-9","C4","2009-05-29","2009-12-04",1,"CP-090564","-","Alcatel-Lucent","Frank Alfano (falfano@alcatel-lucent.com)","CP#46 completed","23.003; 23.008; 29.060; 29.272; 29.273; 29.274; 29.275; 29.276",44,23,null,null,"2009-05-13","2009-11-16"]
[6946,460018,"      CT aspects of SRVCC support for IMS Emergency Calls","IMS_EMER_GPRS_EPS-SRVCC",3,"Rel-9","C1,C4,C3,IETF","2009-05-29","2014-06-13",1,"CP-090882","-","China Mobile","jiangyi@chinamobile.com","CP#46 completed","-",46,24,null,null,"2009-05-13","2009-12-02"]
[6949,460019,"         CT3 aspects of SRVCC support for IMS Emergency Calls","IMS_EMER_GPRS_EPS-SRVCC",4,"Rel-9","C3","2009-12-04","2009-12-04",1,"CP-090882","-","China Mobile","jiangyi@chinamobile.com","CP#46 completed",29.163,46,24,null,null,"2009-05-13","2009-12-02"]
[6952,400038,"   LCS Control Plane Solution for EPS","LCS_EPS-CPS",2,"Rel-9","S2,C4,C1","2008-06-05","2010-03-19",1,"SP-080445","-","Polaris Wireless","Robert Gross (rgross@polariswireless.com)","Triggered by abandoned Study UID_380068 (FS_LCS_EPS). Linked to Feature UID_380064 Support for IMS Emergency Calls over GPRS and EPS","-",40,21,null,null,"2007-12-13","2008-11-22"]
[6955,440120,"      CT1 aspects of Control Plane LCS in the EPC","LCS_EPS-CPS",3,"Rel-9","C1","2009-05-29","2010-03-19",1,"CP-090811","-","Polaris Wireless","Robert Gross (rgross@polariswireless.com)","CP#47 completed",24.300999999999998,44,23,null,null,"2009-05-13","2010-03-02"]
[6960,420023,"   Security for MBMS support in EPS","MBMS_EPS",2,"Rel-9","S3","2008-12-11","2009-12-10",1,"SP-080737","-","China Mobile","Liu Hong (liuhongyfw@chinamobile.com)","SP#46 completed",33.246000000000002,42,22,null,null,"2008-12-09","2009-12-09"]
[6964,430007,"   MBMS support in LTE","MBMS_LTE",2,"Rel-9","R2,R3,R4","2009-03-06","2010-03-19",1,"RP-091457","RP-100033","Huawei","arnaud.meylan@huawei.com","RP#47 completed","25.446; 36.101; 36.104; 36.141; 36.300; 36.304; 36.321; 36.322; 36.323; 36.331; 36.440; 36.441; 36.442; 36.444; 36.445",43,22,null,null,"2009-03-10","2010-03-16"]
[6965,500024,"   Conformance Test Aspects – MBMS support in LTE","MBMS_LTE-UEConTest",2,"Rel-9","R5","2010-12-10","2011-12-09",1,"RP-101245","RP-111437","Huawei","Zhang Xin (zhangxin0208@huawei.com)","RP#54 completed","36.508; 36.521-1; 36.521-2; 36.523-1; 36.523-2; 36.523-3",50,26,null,null,"2010-12-10","2011-11-29"]
[6968,450006,"   CT1 aspects of Access Network Discovery and Selection Function enhancements","eANDSF",2,"Rel-9","C1","2009-09-18","2010-03-19",1,"CP-090742","-","Panasonic","benjamin.limck@sg.panasonic.com","CP#47 completed","24.302; 24.312",45,23,null,null,"2009-09-08","2010-03-02"]
[6973,450049,"System aspects of vocoder rate adaptation for LTE","LTEimp-Vocoder",1,"Rel-9","S2,S4,C1,C3,R2,IETF","2007-05-07","2012-09-12",1,"SP-090653","-","Qualcomm","AC Mahendran (ac@qualcomm.com)","Triggered by RAN2 UID_440013 Vocoder rate adaptation for LTE","LTE",45,23,null,null,"2009-05-28","2012-09-03"]
[6976,440013,"   Vocoder rate adaptation for LTE","LTEimp-Vocoder",2,"Rel-9","R2","2009-05-30","2009-09-18",1,"RP-090978","RP-090704","Alcatel-Lucent","Sudeep Palat (spalat@alcatel-lucent.com)","RP#45 completed","36.300 CR#0114",44,23,null,null,"2009-05-28","2009-10-24"]
[6979,33025,"Access Security Enhancements","ACCSEC2",1,"Rel-9","S3","2007-07-02","2009-06-04",1,"SP-040865","-","Ericsson","Bengt.Sahlin@ericsson.com","SP#44 completed. Stopped TR 33.801. CRs 33.102,43.020 on A5/2 removal done long time ago. A5/4 introduction CRs will be done under UID_440057 128 bit encryption for GSM and GPRS. SP#26 approved WID (improved GERAN security)","33.102; 43.020",33,17,null,null,"2005-03-24","2010-08-06"]
[6982,410029,"   SA3 work on PUCI","PUCI",2,"Rel-9","S3","2008-09-18","2009-12-10",1,"SP-080482","-","NEC","Anand R. Prasad (anand@bq.jp.nec.com)","SP#46 completed. No normative work done in Rel-9","New 33.937",41,21,null,null,"2008-09-15","2009-12-07"]
[6987,460020,"   CN aspects of IMS Media Plane Security","MEDIASEC_CORE",2,"Rel-9","C1,C4,C3","2009-09-18","2010-06-04",1,"CP-090884","-","Vodafone","peter.dawes@vodafone.com","CP#48 completed","-",45,23,null,null,"2009-02-11","2009-12-02"]
[6991,440053,"GBAPush enhancements (Generic push layer)","eGBAPush",1,"Rel-9","S3","2008-03-12","2010-03-25",1,"SP-090282","-","Ericsson","Rolf Blom","SP#43 umbrella to host 33.224, moved from Rel-8 to Rel-9. SP#47 completed","New 33.224",44,23,null,null,"2009-02-11","2009-09-21"]
[6992,420039,"   SA3 part of eGBAPush (Generic push layer)","eGBAPush",2,"Rel-9","S3","2008-03-12","2010-03-25",1,"SP-090282","-","Ericsson","Rolf Blom","SP#47 completed","New 33.224",39,21,null,null,"2008-03-22","2010-02-23"]
[6995,440156,"   SA3 part of Network Domain Security (NDS) enhancements to support backhaul security","NDS_Backhaul",2,"Rel-9","S3","2009-06-04","2010-03-25",1,"SP-090286","-","Vodafone","Peter.Howard@vodafone.com","SP#47 completed","33.102; 33.210; 33.310; 33.401; 33.402",44,23,null,null,"2009-05-18","2010-03-01"]
[7000,440357,"   CT1 part of 128 bit encryption for GSM and GPRS","A5/4-GEA4",2,"Rel-9","C1","2009-06-04","2009-09-18",1,"SP-090287","-","Ericsson","Karl Norrman","CP#45 completed","24.008.44.064",44,23,null,null,"2009-05-18","2009-09-08"]
[7003,440657,"   GERAN3new (testing) part of 128 bit encryption for GSM and GPRS","A5/4-GEA4",2,"Rel-9","G3new","2009-06-04","2009-11-20",1,"GP-091212","-","Ericsson","Karl Norrman","GP#44 completed. GP#43 WID approved",51.01,44,23,null,null,"2009-05-18","2009-11-20"]
[7005,420027,"Timed Graphics","TG",1,"Rel-9","S4","2008-12-11","2010-03-25",1,"SP-080683","-","Ericsson","clinton.priddle@ericsson.com","SP#47 completed. Provide graphics in parallel to a video stream (without requiring an umbrella scene descriptor such as 3GPP DIMS in TS 26.142)","26.114; 26.140; 26.234; 26.244; 26.245; 26.346; New 26.430",42,22,null,null,"2008-11-23","2010-02-01"]
[7011,440051,"Syndicated Feed Reception within 3GPP environments","SFR",1,"Rel-9","S4","2009-06-04","2009-12-10",1,"SP-090260","-","Ericsson","Thorsten.Lohmar@ericsson.com","SP#46 completed. TS 26.150v100 for Approval. RSS optimized for mobile use. Reuse/reference OMA's enabler DCD.","New 26.150",44,23,null,null,"2009-05-31","2009-12-07"]
[7014,420030,"   Rel-9 Network Infrastructure Management","OAM9-NIM",2,"Rel-9","S5","2008-12-11","2010-03-25",1,"-","-","-","-","SP#42 umbrella BB created to host OAM WIs","-",42,22,null,null,"2008-11-25","2008-12-01"]
[7018,420032,"   Rel-9 Performance Management","OAM9-PM",2,"Rel-9","S5","2009-03-12","2010-06-10",1,"-","-","-","-","SP#42 umbrella BB created to host OAM WIs","-",42,22,null,null,"2008-11-25","2008-12-01"]
[7019,440059,"      Enhancement of UTRAN Performance Measurements","-",3,"Rel-9","S5","2009-06-04","2009-12-10",1,"SP-090308","-","China Mobile","liangshuangchun@cmdi.chinamobile.com, lijian@chinamobile.com, Bao Haitao","SP#46 completed",32.405000000000001,44,23,null,null,"2009-05-18","2009-12-01"]
[7022,430043,"   Rel-9 Self-Organizing Networks (SON) - OAM aspects","OAM9-SON",2,"Rel-9","S5","2008-02-22","2010-06-10",1,"-","-","-","-","SP#43 umbrella BB created to host OAM WIs","-",43,22,null,null,"2009-03-09","2010-02-09"]
[7027,440068,"Rel-9 Charging Management small Enhancements","CH9",1,"Rel-9","S5","2009-06-04","2010-03-25",1,"-","-","-","-","CH9 is an umbrella Feature also for OAM&P related TEI9 type of changes that are not part of any other dedicated feature/WI",30.818999999999999,44,23,null,null,"2009-05-19","2010-03-08"]
[7030,400010,"   CT4 aspects of CS-IBCF and CS-TrGW definition in 3GPP specifications","CS-IBCF",2,"Rel-9","C4","2008-05-30","2009-12-04",1,"CP-090073","-","Telecom Italia","mauro.ficaccio@telecomitalia.it","CP#46 completed","23.231; 29.232; new 29.238",40,21,null,null,"2007-09-05","2009-11-25"]
[7032,410108,"   CT4 part of IMS – Interconnection Border Control Function (IBCF) – Transition Gateway (TrGW); Ix Interface; Stage 3","IMS_IBCF",2,"Rel-9","C4","2008-09-12","2009-12-04",1,"CP-090019","-","Alcatel-Lucent","bruno.landais@alcatel-lucent.fr","CP#46 completed","new 29.238",41,21,null,null,"2007-09-05","2009-11-16"]
[7038,440018,"   CT4 aspects of Completion of IMS Restoration Procedures","eIMS_RP",2,"Rel-9","C4","2009-05-29","2010-03-19",1,"CP-091050","-","Ericsson","Emiliano Merino (emiliano.merino@ericsson.com)","CP#47 completed","23.380; 23.820",44,23,null,null,"2009-05-13","2010-03-09"]
[7041,440039,"IMS Stage 3 IETF Protocol Alignment - phase 3","IMSProtoc3",1,"Rel-9","C1,IETF","2009-05-29","2014-12-05",1,"CP-090491","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#47 completed","-",44,23,null,null,"2009-05-13","2010-03-02"]
[7045,440070,"Operational description of the Inter-IMS Network to Network Interface (II-NNI)","II-NNI",1,"Rel-9","C3,IETF","2009-05-29","2014-12-09",1,"CP-090331","-","Orange","sebastien.daudet@orange-ftgroup.com","-","-",44,23,null,null,"2009-05-29","2013-02-28"]
[7046,440170,"   Operational description of the Inter-IMS Network to Network Interface","II-NNI",2,"Rel-9","C3","2009-05-29","2010-06-04",1,"CP-090331","-","Orange","-","CP#48 completed",29.164999999999999,44,23,null,null,"2012-04-20","2010-05-27"]
[7050,561007,"   (IETF) Operational description of the Inter-IMS Network to Network Interface","II-NNI",2,"Rel-9","C3-IETF","2012-04-20","2014-12-09",1,"CP-090331","-","Roland Jesske","Roland Jesske","In RFC Editors Queue. Mar15: 90->100%. RFC updated (was draft-ietf-cuss-sip-uui). Jun 15: RFC 7433 (was draft-ietf-cuss-sip-uui)","RFC 7433",56,29,null,null,"2012-04-20","2015-03-10"]
[7054,450005,"Definition of Ml interface for Control Plane LCS (Stage 3)","EMC2",1,"Rel-9","C1","2009-09-18","2010-03-19",1,"CP-090746","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#47 completed [Stage 3 for Rel-7 Emergency Calls (EMC1)]. Related to Rel-9 UID_400038 LCS Control Plane Solution for EPS. Stage 2 in Rel-9 UID_400038 (23.271), UID_410037 (23.167)",24.228999999999999,45,23,null,null,"2009-09-17","2010-03-02"]
[7057,470004,"In Case of Emergency (ICE) Graphics","ICE_Graphics",1,"Rel-9","C6","2010-03-17","2010-03-19",1,"CP-100178","-","Sagem-Orga","heiko.kruse@sagem-orga.com","CP#47 approved WID and completed. Added capability to store ICE graphical information (picture). Linked to CT6 Rel-8 ICE Feature UID_380059 In Case of Emergency numbers storage and easy access on UICC","31.102 CR#0433",47,24,null,null,"2010-03-09","2010-03-17"]
[7059,410017,"   LCR TDD UE OTA Performance Requirements","RInImp9-RFLCROTA",2,"Rel-9","R4","2008-09-12","2009-05-29",1,"RP-080744","RP-090389","RITT","Wu Xiang (wuxiang@chinattl.com)","RP#44 completed technical work (RAN4 internal TR abandoned)","UTRA (no 25.8xy produced)",41,21,null,null,"2008-09-11","2009-09-09"]
[7065,430010,"   Performance requirement for LCR TDD with UE speeds up to 350 km/h","RInImp9-LCRTDD350",2,"Rel-9","R4","2009-03-06","2009-12-04",1,"RP-090258","RP-091035","CATT","Yuexia Song (songyuexia@catt.cn)","RP#46 completed","UTRA 25.102; 25.105; 25.142",43,22,null,null,"2009-02-27","2009-12-02"]
[7068,440007,"   Conformance Test Aspects – UMTS/LTE in 800 MHz for Europe","RInImp-UEConTest-UMTSLTE800EU",2,"Rel-9","R5","2009-05-19","2010-09-17",1,"RP-090485","RP-100736","Ericsson","fredrik.sundstrom@ericsson.com","RP#49 completed. Testing for UID_430009 UMTS/LTE 800 MHz for Europe","UTRA; LTE 34.108; 34.121-1; 34.121-2; 36.508; 36.521-1; 36.521-2; 36.521-3",44,23,null,null,"2009-05-18","2010-09-08"]
[7072,450018,"Conformance Test Aspects – SMS over IMS in E-UTRAN","SMSoverIMS_UEConTest",1,"Rel-9","R5","2009-09-18","2010-03-19",1,"RP-090959","RP-100072","Alcatel-Lucent","Nidal Khrais (khrais@alcatel-lucent.com)","RP#47 completed","LTE 34.229-1; 34.229-2; 34.229-3",45,23,null,null,"2009-09-15","2010-03-16"]
[7073,430013,"Rel-9 RAN improvements","-",1,"Rel-9","RP","2009-03-06","2010-09-08",1,"-","-","-","-","RP#47 completed","UTRA",43,22,null,null,"2009-03-06","2010-09-08"]
[7077,430018,"   Transmit Antenna Array (TxAA) extension for non-MIMO UEs","RANimp-TxAA_nonMIMO",2,"Rel-9","R1,R2,R3,R4","2009-03-06","2009-03-06",1,"RP-090013","RP-091040","Nokia","Arto Lehti (arto.lehti@nokia.com)","RP#46 completed","25.101; 25.104; 25.211; 25.212; 25.213; 25.214; 25.215; 25.308; 25.306; 25.321; 25.331; 25.423; 25.433",43,22,null,null,"2009-03-06","2009-11-26"]
[7081,510014,"   Conformance Test Aspects – Dual-Cell HSUPA","RANimp-DC_HSUPA_UEConTest",2,"Rel-9","R5","2011-03-18","2012-12-07",1,"RP-110116","RP-121524","Ericsson","leif.mattisson@ericsson.com","RP#58 completed. Testing for Rel-9 UID_430014 Dual-Cell HSUPA","UTRA 34.108; 34.121-1; 34.121-2; 34.123-1; 34.123-2; 34.123-3",51,26,null,null,"2011-03-10","2012-11-28"]
[7084,430019,"   LTE Pico NodeB RF Requirements","LTEimp-Pico_eNB-RF",2,"Rel-9","R4","2009-03-06","2009-12-04",1,"RP-091155","RP-091045","Huawei","Liyan Yin (yinliyan@huawei.com)","RP#46 completed","36.104; 36.141; new 36.931",43,22,null,null,"2009-02-27","2010-02-08"]
[7086,490018,"   UE Conformance Test Aspects – Enhanced Dual-layer transmission for LTE TDD","LTEimp-eDL_UEConTest",2,"Rel-9","R5","2010-09-17","2011-06-03",1,"RP-100868","RP-110509","China Mobile","Shanpeng Xiao (xiaoshanpeng@chinamobile.com)","RP#52 completed. Testing for UID_430029 (Enhanced Dual-Layer transmission for LTE)","36.508; 36.521-1; 36.521-2",49,25,null,null,"2010-09-09","2011-05-18"]
[7092,420003,"   Stage 2 for Voice services over Adaptive Multi-user channels on One Slot","VAMOS",2,"Rel-9","GP,G1,G2","2008-11-21","2010-05-21",1,"GP-081964","-","Nokia Siemens Networks, China Mobile","juergen.hofmann@nsn.com, liuxiaoyu@chinamobile.com","GP#46 completed. GP#40 WID approved",45.000999999999998,40,22,null,null,"2008-11-23","2010-05-27"]
[7095,490005,"   VAMOS - MS conformance testing","VAMOS_MStest",2,"Rel-9","G3new","2010-09-03","2012-03-02",1,"GP-101604","-","BlackBerry","Raveendra Seetharam (rseetharam@rim.com)","GP#53 completed. GP#47 WID approved","51.010-1; 51.010-2",47,25,null,null,"2010-09-04","2012-03-02"]
[7097,440002,"Cell Broadcast protocol Base Station Controller – Cell Broadcast Centre (BSC-CBC)","CEBRO",1,"Rel-9","GP,C1","2009-05-15","2010-03-19",1,"GP-091022","-","Ericsson","claes-goran.persson@ericsson.com","CP#47 completed. GP#45 completed. GP#42 WID approved","-",42,23,null,null,"2009-05-18","2010-03-05"]
[{"$f":"A7100+1","v":7100},440003,"Hybrid Location","HILT",1,"Rel-9","GP","2009-05-18","2009-11-20",1,"GP-091075","-","TruePosition","Matt Ward (mward@trueposition.com)","GP#44 completed. GP#42 WID approved (Hybrid Integrated Location Technology=HILT)","43.059; 48.071",42,23,null,null,"2009-05-18","2009-09-07"]
[7104,410001,"   Deleted - Stage 1 for ServAl","-",2,"Rel-9","S1","2006-12-06","2008-09-18",1,"SP-070126","-","Telefónica O2","chris.friel@O2.com","SP#41 closed (no tangible result of this work¦no CR against TR 22.983)",22.983000000000001,33,21,"SP-41","PCG-21","2006-10-06","2010-08-05"]
[7108,380086,"Deleted - Definition of 3GPP UICC services over the new high-speed interface","UICCHS",1,"Rel-9","C6","2010-03-19","2010-03-19",1,"CP-070837","-","Gemalto","Denis.Lheriteau@gemalto.com","CP#47 work stopped/abandoned","31.xyz",38,21,"CP-47","PCG-24","2008-01-31","2009-11-25"]
[7111,390041,"   Deleted - CS over EPS ","SAES_Ph2",2,"Rel-9","S2","2008-03-12","2008-12-08",1,"-","-","-","-","SP#39 SAE functionality moved to Rel-9. BUT no agreed WID","-",39,21,"SP-39","PCG-21","2007-03-29","2009-03-24"]
[7113,390043,"      Deleted - Single Radio Aspects of SAE for Optimized Handover with WiMAX","SAES_Ph2",3,"Rel-9","S2","2007-06-25","2008-06-09",1,"-","-","-","-","SP#39 SAE functionality moved to Rel-9. BUT no agreed WID","-",39,21,"SP-39","PCG-21","2007-04-26","2009-03-24"]
[7119,320031,"Study on Service Continuity for Emergency Voice Calls","FS_VCCEm",1,"Rel-9","S2","2006-06-08","2009-03-12",1,"SP-080555","-","Nortel","Ricky Kaura (rkaura@nortel.com)","SP#43 completed",23.826000000000001,32,17,null,null,"2006-07-19","2009-02-24"]
[7122,360007,"Study on Self-Organizing Networks (SON) related OAM interfaces for Home NodeB","FS_OAM-SON-HNB",1,"Rel-9","S5","2007-06-07","2009-06-04",1,"SP-080461","-","Huawei","Zou Lan (zlan@huawei.com)","SP#44 completed. Linked to SA5 TR 32.816 Study of Management for LTE and SAE (UID_340036)",32.820999999999998,36,19,null,null,"2007-05-28","2009-05-18"]
[7124,400029,"Study on Service Oriented Architecture (SOA) for IRP","FS_OAM_SOA_IRP",1,"Rel-9","S5","2008-06-05","2009-06-04",1,"SP-080281","-","Ericsson","edwin.tse@ericsson.com","SP#44 completed. Spin-off implementation WI UID_440064 Service Oriented Architecture (SOA) for IRP",32.823999999999998,40,21,null,null,"2007-05-28","2009-06-02"]
[7127,410016,"Study on 1.28 Mcps TDD Home NodeB","FS_RAN-HNBLCRTDD",1,"Rel-9","R4","2008-02-20","2009-12-04",1,"RP-080767","RP-091081","TD Tech","Li Rong (lirong@td-tech.com)","RP#46 completed",25.866,41,21,null,null,"2007-12-17","2009-12-03"]
[7131,440015,"Study on Enhanced Interference Management Mechanisms for HNBs","FS_eInterfMgmtMchsm_HNB",1,"Rel-9","R3","2009-05-30","2009-09-18",1,"RP-090667","RP-090733","Qualcomm","Farhad Meshkati (fmeshkat@qualcomm.com)","RP#45 completed. Triggered by RAN4 UID_430027 Study on Enhanced Interference Management for HNBs",25.966999999999999,44,23,null,null,"2009-05-26","2009-09-15"]
[7135,320022,"   Requirements for evolution of the 3GPP system architecture ","AIPN-SAE",2,"Rel-8","S1","2006-06-08","2007-12-12",1,"SP-080132","-","T-Mobile","michael.kurz@t-mobile.at ","SP#38 completed","22.011; 22.246; New 22.278",32,17,null,null,"2006-06-23","2010-07-28"]
[7140,340054,"      Stage 3 SAE impact on existing capabilities","SAES",3,"Rel-8","C3","2007-02-05","2008-12-05",1,"CP-080772","-","Huawei","Wei Weihua (weiwh@huawei.com)","CP#42 completed",29.061,34,18,null,null,"2006-07-19","2010-07-28"]
[7143,340023,"      Stage 3 EPC interworking with external PDNs (SGi)","SAES-St3-intwk",3,"Rel-8","C3","2007-02-05","2009-05-29",1,"CP-080772","-","Huawei","Wei Weihua (weiwh@huawei.com)","CP#44 completed",29.061,34,18,null,null,"2006-07-19","2010-07-28"]
[7146,370017,"      Unified guidelines for Diameter usage within 3GPP","SAES-DIAM",3,"Rel-8","C3","2007-09-21","2008-12-05",1,"CP-080055","-","Huawei","Javier Gonzalez Gallego","CP#42 completed","New 29.909",37,19,null,null,"2007-09-25","2010-07-28"]
[7149,350042,"      SAES-SA-FP_LTE with GTP variant","SAES-SA-FP_LTE-GTP",3,"Rel-8","S2,C4","2007-01-02","2009-03-06",1,"SP-080132","-","Nokia Siemens Networks","balazs.bertenyi@nsn.com","CP#43 completed","-",35,18,null,null,"2007-04-26","2010-07-28"]
[7151,340055,"         CT4 Stage 3 for GTP v2 protocol","SAES-SA-FP_LTE-GTP",4,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed",29.274000000000001,34,18,null,null,"2006-07-19","2010-07-28"]
[7154,370018,"         CT4 Stage 3 for PMIP protocol within EPC","SAES-SA-FP_LTE-IETF",4,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.275; 29.282",37,19,null,null,"2006-07-19","2010-07-28"]
[7158,340053,"      Stage 3 for security aspects of LTE Access","SAES-LTE",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.008; 24.301",34,18,null,null,"2006-07-19","2010-07-28"]
[7162,370008,"      Stage 2 for Interoperation between LTE and 2G/3G","EPSto2_3G",3,"Rel-8","S2","2007-02-05","2008-09-18",1,"SP-080132","-","Motorola","Irfan.Ali@motorola.com","SP#41 completed","23.401; 23.402",37,19,null,null,"2007-09-19","2010-07-28"]
[7167,380032,"      Stage 3 for EPC to UTRAN","SAES-SA-FP_3GPP",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.274; 29.275; 29.281",38,21,null,null,"2006-07-19","2010-07-28"]
[7170,360023,"      Stage 3 for Inter-system mobility between E-UTRAN and CDMA2000","SAES-SA-FP_3GPP",3,"Rel-8","C1","2007-02-05","2009-03-06",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#43 completed","24.301; 24.302",36,19,null,null,"2007-09-12","2010-07-28"]
[7173,350044,"      Stage 2 for Host-based Mobility aspects","SAES-SA-FP_n3GPP-HBMob",3,"Rel-8","S2","2007-01-02","2008-06-05",1,"SP-080132","-","Motorola","Irfan.Ali@motorola.com","SP#40 completed",23.402000000000001,35,18,null,null,"2007-04-26","2010-07-28"]
[7176,521011,"      (IETF) Stage 3 for Mobility management based on DSMIPv6 (draft-ietf-mip6-hiopt)","SAES-SA-FP_n3GPP",3,"Rel-8","C1-IETF","2007-02-05","2012-06-15",1,"CP-080493","-","Mark Jones","-","CP#56 completed; 9/4/21: RFC 6610 added;","RFC 6610 (was draft-ietf-mip6-hiopt); RFC 6610",52,27,null,null,"2011-06-20","2021-04-09"]
[7178,390009,"      Stage 3 for Mobility management based on MIP v4","SAES-SA-FP_n3GPP",3,"Rel-8","C1","2007-02-05","2008-12-05",1,"CP-080493","-","Nokia Siemens Networks","robert.zaus@nsn.com","CP#42 completed",24.303999999999998,39,21,null,null,"2008-03-03","2010-07-28"]
[7181,390045,"      Stage 2 Security aspects for non-3GPP Access","SAES-SA-FP_n3GPP",3,"Rel-8","S3","2008-03-12","2008-12-11",1,"SP-080132","-","Nokia Siemens Networks","marc.blommaert.ext@nsn.com","SP#42 completed","33.402; 33.210; 33.310",39,21,null,null,"2008-03-19","2010-07-28"]
[7186,340057,"      Stage 3 for Interfaces EPC - non-3GPP IP access ","SAES-SA-FP_n3GPP",3,"Rel-8","C4","2007-02-05","2009-03-06",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#43 completed","29.273; 29.275",34,18,null,null,"2006-07-19","2010-07-28"]
[7189,340059,"      Stage 3 for EPC - AAA interface","SAES-SA-FP_n3GPP",3,"Rel-8","C4","2007-02-05","2008-12-05",1,"CP-090247","-","Huawei","shahab.lavasani@huawei.com","CP#42 completed",29.273,34,18,null,null,"2006-07-19","2010-07-28"]
[7194,410006,"      MME to MSC interface for SRVCC","SAES-SRVCC",3,"Rel-8","C4","2008-09-12","2009-03-06",1,"CP-080793","-","Nokia Siemens Networks","Giorgi Gulbani","CP#43 completed","23.003; 23.008; New (29.274; 29.277; 29.280)",41,21,null,null,"2008-09-01","2010-07-28"]
[7197,390036,"   CS Fallback in EPS","SAES-CSFB",2,"Rel-8","S2,C1,C4","2008-03-12","2009-03-06",1,"SP-080097","-","T-Mobile, Vodafone","sabine.demel@t-mobile.at, chris.pudney@vodafone.com","CP#43 completed","-",39,21,null,null,"2007-03-29","2010-07-28"]
[7200,400003,"      CT4 part of Stage 3 for CS Fallback in EPS","SAES-CSFB",3,"Rel-8","C4","2008-05-30","2008-12-05",1,"CP-080791","-","NEC","yannick.lair@nectech.fr","CP#42 completed","23.007; 23.008; 29.274; New 29.277",40,21,null,null,"2007-03-29","2010-07-28"]
[7203,380037,"      EPC Network Resource Model (NRM) Integration Reference Point (IRP)","EPC-OAM",3,"Rel-8","S5","2008-01-07","2009-03-12",1,"SP-070737","-","Huawei","WANG, Xuelong","SP#43 completed","New (32.751; 32.752; 32.753; 32.755)",38,21,null,null,"2005-06-17","2009-02-23"]
[7205,380038,"   EPC Charging","EPC-CH",2,"Rel-8","S5","2008-01-07","2009-03-12",1,"SP-070736","-","Nokia Siemens Networks","Gerald.Goermer@nsn.com","SP#43 completed","32.240; 32.296; 32.251; 32.252; 32.298; 32.299",38,21,null,null,"2005-06-17","2010-07-28"]
[7208,390021,"   CT6 aspects of SAE","SAES",2,"Rel-8","C6","2008-03-07","2011-06-03",1,"CP-080164","-","Nokia","Rune Lindholm","CP#44 completed core specification","-",39,21,null,null,"2008-03-12","2010-07-28"]
[7213,390019,"   Issues for CT3 TR 29.804","SAES",2,"Rel-8","C3","2007-02-05","2008-09-12",1,"CP-080068","-","Ericsson ","j.javier.pastor@ericsson.com","CP#41 completed",29.803999999999998,39,21,null,null,"2006-07-19","2010-07-28"]
[7216,350032,"   Deleted (covered by 380064): SAE aspects of Emergency Calls","SAES-SA-EmCall",2,"Rel-8","S2","2008-03-03","2008-03-03",1,"-","-","Nokia Siemens Networks","-","SP#37 stopped","-",35,18,"SP-37",null,"2007-03-29","2009-03-24"]
[7221,350021,"      Deleted - CT4 aspects of SAES","SAES",3,"Rel-8","C4","2007-09-04","2007-09-04",1,"CP-060676","-","-","-","SP#37 stopped",29.803000000000001,35,18,"SP-37",null,"2006-07-19","2009-03-24"]
[7224,340037,"   Deleted - Architecture enhancements for non-3GPP accesses","SAES-non_3GPP",2,"Rel-8","S2","2007-09-04","2007-09-04",1,"SP-060926","-","Motorola","Irfan.Ali@motorola.com","SP#34 stopped. Replaced by UID_350027 and its children",23.402000000000001,34,18,"SP-34",null,"2006-06-23","2009-03-24"]
[7226,350023,"   Deleted - SA aspects of System Architecture Evolution","SAES-SA",2,"Rel-8","S2","2006-04-12","2007-10-01",1,"-","-","-","-","SP#34 stopped","-",35,18,"SP-34",null,"2007-03-29","2009-03-24"]
[7229,380039,"   Stage 1 for ICS Requirement and Architecture","ICSRA",2,"Rel-8","S1","2007-09-03","2008-03-12",1,"SP-070924","-","AT&T","Randolph Wohlert (rwohlert@tri.sbc.com)","SP#39 completed",22.100999999999999,38,21,null,null,"2007-10-02","2008-07-23"]
[7232,400005,"      CT1 aspects - Stage 3 for ICSRA","ICSRA",3,"Rel-8","C1","2008-05-30","2009-03-06",1,"CP-091046","-","Ericsson","Sean Schneyer","CP#46 completed","24.229; new (24.292; 24.286)",40,21,null,null,"2008-03-03","2009-12-07"]
[7235,521016,"      (IETF) CT1 aspects - Stage 3 for ICSRA (RFC 7195)","ICSRA",3,"Rel-8","C1-IETF","2008-05-30","2014-06-13",1,"CP-091046","-","Andrew Allen","-","CP#64 complete","RFC 7195 (was draft-ietf-mmusic-sdp-cs)",52,27,null,null,"2011-06-20","2014-06-06"]
[7240,400105,"      Deleted - Stage 3 for ICSRA – I1 interface","ICSRA",3,"Rel-8","C1","2008-05-30","2008-09-12",1,"CP-080492","-","Huawei","xupeili@huawei.com","CP#41 work stopped",24.292999999999999,40,21,"CP-41","PCG-21","2008-03-03","2009-12-02"]
[7243,370023,"      Service and Capability for Core IMS - inclusion of TISPAN requirements","TISCAPR8",3,"Rel-8","S1","2007-09-03","2007-12-14",1,"SP-070691","-","Ericsson","Susana Sabater","SP#39 completed","22.228; 22.115; 22.101",37,19,null,null,"2007-10-02","2008-03-20"]
[7248,370024,"      Merging TISPAN MMTel [requirements] for Common IMS","TMMTEL",3,"Rel-8","S1","2007-09-10","2007-12-07",1,"SP-070569","-","Nokia Siemens Networks","-","SP#38 completed",22.172999999999998,37,19,null,null,"2007-10-02","2007-11-19"]
[7251,380007,"      CT1 part of Stage 3 CCBS_CCNR","CCBS_CCNR",3,"Rel-8","C1","2007-05-02","2009-03-06",1,"CP-080215","-","Deutsche Telekom","martin.huelsemann@telekom.de","CP#43 completed","24.642; 24.229; 24.173",38,21,null,null,"2007-11-14","2012-01-11"]
[7253,521019,"      (IETF) Stage 3 CCBS_CCNR [RFC 6910 (was draft-ietf-bliss-call-completion)]","CCBS_CCNR",3,"Rel-8","C1-IETF,C3-IETF","2007-05-02","2013-06-14",1,"CP-080215","-","Roland Jesske","-","CP#60 completed","RFC 6910 (was draft-ietf-bliss-call-completion)",52,27,null,null,"2011-06-20","2013-06-10"]
[7256,390015,"      Stage 3 FA","FA",3,"Rel-8","C1","2008-01-30","2009-03-06",1,"CP-080219","-","Nortel","milanpa@nortel.com","CP#43 completed","24.239; 24.173",39,21,null,null,"2008-03-03","2009-02-20"]
[7259,521020,"      (IETF) Stage 3 CW-IMS (salud-alert-info-urns)","CW_IMS",3,"Rel-8","C1-IETF","2007-06-22","2014-12-09",1,"CP-080214","-","Roland Jesske","Roland Jesske","In RFC Editors Queue. Dec.14: 75->90¦7/3/16: 90%->100; 9/4/21: RFC 7462 added;","draft-ietf-salud-alert-info-urns; RFC 7462",52,27,null,null,"2011-06-20","2021-04-09"]
[7262,370003,"      Add Interconnection Border Control Function (IBCF) to IMS Charging","CH8_IMS",3,"Rel-8","S5","2007-09-17","2008-03-12",1,"SP-070621","-","Alcatel-Lucent","maryse.gardella@alcatel-lucent.com","SP#39 completed","32.260; 32.298",37,19,null,null,"2007-09-15","2008-03-23"]
[7267,390052,"   Security CIMS_3GPP2","CIMS_3GPP2",2,"Rel-8","S3","2008-03-12","2008-12-11",1,"SP-080220","-","Nortel","Amar Deol (deola@nortelnetworks.com)","SP#42 completed [issues addressed under UID_370078 (IMS-Sec)]. Acronym changed from \"CIMS_3GPP2, IMS_Common\"","33.141; 33.203; 33.210",39,21,null,null,"2008-03-03","2015-03-24"]
[7271,390027,"      Stage 3 CIMS_3GPP2 (CT4)","REDOC_3GPP2",3,"Rel-8","C4","2008-03-07","2008-12-11",1,"CP-080795","-","Alcatel-Lucent","orsic@alcatel-lucent.com","CP#42 completed","29.228; 29.229; 29.328; 29.329",39,21,null,null,"2008-03-03","2009-03-26"]
[7275,350010,"      CT1 aspects of PktCbl-Deploy","PktCbl-Deploy",3,"Rel-8","C1","2007-03-26","2008-05-30",1,"CP-070122","-","Cablelabs","D.Hancock@CableLabs.com","CP#40 completed","-",35,18,null,null,"2007-03-29","2008-05-13"]
[7278,350013,"      CT1,CT3 aspects of PktCbl-Interwork","PktCbl-Intw",3,"Rel-8","C1,C3","2007-03-26","2008-03-14",1,"CP-070575","-","Cablelabs","D.Hancock@CableLabs.com","CP#39 completed",24.228999999999999,35,18,null,null,"2007-03-29","2008-03-03"]
[7280,350033,"      SA3 aspects of PktCbl-Sec","PktCbl-Sec",3,"Rel-8","S3","2006-12-06","2008-03-12",1,"SP-060933","-","Cablelabs","s.dotson@cablelabs.com","SP#39 completed","33.203; 33.210; 33.220",35,18,null,null,"2005-11-04","2008-03-23"]
[7283,350007,"      CT4 aspects of PktCbl-Sec","PktCbl-Sec",3,"Rel-8","C4","2007-03-26","2008-03-14",1,"CP-070124","-","Cablelabs","D.Hancock@CableLabs.com","CP#39 completed","29.228; 29.229; 23.008",35,18,null,null,"2007-03-29","2008-05-27"]
[7286,360014,"   SA2 aspects of IMS_Corp","IMS_Corp",2,"Rel-8","S2","2007-06-22","2008-09-18",1,"SP-080095","-","Orange","Delphin Barankanira","no Stage 2 impacts",23.228000000000002,36,19,null,null,"2007-06-22","2010-07-29"]
[7289,390023,"   CT4 aspects of IMS_Corp","IMS_Corp",2,"Rel-8","C4","2008-02-26","2008-12-05",1,"CP-080220","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#42 completed","29.228; 29.229; 23.003; 23.008; 29.433",39,21,null,null,"2008-03-07","2008-11-22"]
[7294,380044,"   Maintenance of TISPAN release 2 common IMS","IMS_Comm_Mtce8",2,"Rel-8","S2","2007-07-02","2007-12-06",1,"SP-070916","-","Telecom Italia","antonio.ascolese@telecomitalia.it","SP#38 completed","23.506; 23.507.23.517; 23.521",38,21,null,null,"2007-10-02","2010-07-29"]
[7298,400011,"   Stage 3 IMS Service Continuity","IMS-Cont",2,"Rel-8","C1","2008-05-30","2009-05-29",1,"CP-080491","-","Huawei","Lili Yang (kadyyang@huawei.com)","CP#44 completed","24.237; 24.229; 24.216",40,21,null,null,"2007-10-02","2009-05-13"]
[7302,390154,"   CT4 part of Stage 3 for IMS-Sec","IMS-Sec",2,"Rel-8","C4","2007-06-07","2009-03-06",1,"-","-","Ericsson","-","CP#43 completed","-",39,21,null,null,"2007-11-21","2009-02-20"]
[7305,34046,"IMS initiated and controlled PSS and MBMS User Service","IMS_PSS_MBMS_US",1,"Rel-8","S4,S3,IETF","2008-03-12","2011-09-21",1,"SP-080201","-","FT, Ericsson","olle.franceschi@ericsson.com","SP#39 WID approved","-",34,18,null,null,"2008-03-18","2011-06-30"]
[7307,521022,"   (IETF) IMS initiated and controlled PSS and MBMS User Service (RFC 6080)","IMS_PSS_MBMS_US",2,"Rel-8","S4-IETF","2008-03-12","2011-09-21",1,"SP-080201","-","Ericsson","-","SP#53/IETF#81 completed","RFC 6080 (was draft-ietf-sipping-config-framework)",52,27,null,null,"2011-06-20","2013-08-23"]
[7310,7014,"   Stage 3 of MW-IMS","MIW-IMS-St3C3",2,"Rel-8","C3","2005-09-23","2007-11-30",1,"CP-070096","-","Vodafone","nico.gabriele@vodafone.com","Moved from Rel-7. Feature extended in Rel-8 by including Stage 3 covering MONA UID_380021","29.863; 29.163",70,36,null,null,"2006-02-16","2008-08-05"]
[7316,521024,"   (IETF) IMS Stage 3 IETF Protocol Alignment (RFC 6544)","IMSProtoc2",2,"Rel-8","C1-IETF","2007-06-22","2012-06-15",1,"CP-080794","-","Keith Drage","-","CP#56 completed","RFC 6544 (was draft-ietf-mmusic-ice-tcp)",52,27,null,null,"2011-06-20","2012-04-20"]
[7318,380014,"Interworking between User-to-User Signalling (UUS) and SIP ","UUSIW",1,"Rel-8","C1,C3,IETF","2007-11-30","2014-12-09",1,"CP-070782","-","Huawei","Lili Yang (kadyyang@huawei.com)","CP#43 completed","-",38,21,null,null,"2007-11-13","2009-03-11"]
[7321,551001,"   (IETF) Stage 3 MGCF UUSIW (cuss-sip-uui-isdn)","UUSIW",2,"Rel-8","C1-IETF,C3-IETF","2011-03-17","2014-12-09",1,"CP-070782","-","Keith Drage","Keith Drage (drage@alcatel-lucent.com)","In RFC Editors Queue. Dec.14: 75->90. Mar15: 90->100%. RFC updated (was draft-ietf-cuss-sip-uui-isdn). June 2015: RFC 7434 (was draft-ietf-cuss-sip-uui-isdn)","RFC 7434",55,28,null,null,"2012-03-03","2015-03-10"]
[7325,380020,"   Stage 3 Overlap (CT3)","Overlap",2,"Rel-8","C3","2007-11-30","2009-03-06",1,"CP-070731","-","Deutsche Telekom","r.jesske@telekom.de","CP#43 completed",29.163,38,21,null,null,"2007-11-13","2008-11-25"]
[7329,380235,"   AS/MRFC Stage 3","MRFC_TS",2,"Rel-8","C1","2007-11-14","2008-12-05",1,"CP-070784","-","Hewlett-Packard","mark.syrett@hp.com","CP#42 completed","24.229; 24.147; 24.247",38,21,null,null,"2007-11-14","2012-01-10"]
[7332,400026,"   IMS Restoration Procedures (CT4)","IMS_RP",2,"Rel-8","C4","2008-05-30","2009-03-06",1,"CP-080447","-","Ericsson","german.blanco@ericsson.com","CP#43 completed","23.380; 29.228; 29.229; 29.230; 23.008",40,21,null,null,"2007-03-29","2010-07-30"]
[7334,410003,"IMS Application Server Service Data Descriptions for AS interoperability","IMS_ASIO",1,"Rel-8","C4","2008-09-12","2009-03-06",1,"CP-080451","-","Alcatel-Lucent","nhberry@alcatel-lucent.com","CP#43 completed. Triggered by UID_360030 (FS_IMS_ASIO)","29.328; 29.329; 29.364",41,21,null,null,"2007-09-05","2009-02-20"]
[7337,390025,"   CT1 part of Stage 3 for I-WLAN NSP","IWLANNSP",2,"Rel-8","C1","2008-03-07","2009-03-06",1,"CP-080217","-","Research In Motion","Adrian Buckley (abuckley@rim.com)","CP#43 completed",24.234000000000002,39,21,null,null,"2008-03-07","2009-03-25"]
[7343,7042,"Enhancements for Voice Group Call Service (VGCS) Applications (EVA)","EVA",1,"Rel-8","S1,C1,C4,G2","2006-03-15","2009-09-18",1,"SP-070904","-","Nortel","Amar Deol (deola@nortelnetworks.com)","CP#45 completed","-",70,36,null,null,"2006-03-21","2010-07-30"]
[7345,370019,"   VGCS/VBS and GPRS Interactions","EVA",2,"Rel-8","S1","2007-09-03","2008-03-21",1,"SP-070653","-","Huawei","Ling Liu","SP#39 completed","42.068; 42.069",37,19,null,null,"2007-10-02","2008-05-16"]
[7348,52148,"   GERAN2 aspects of EVA","EVA",2,"Rel-8","G2","2006-06-30","2008-02-22",1,"GP-071855","-","Nortel","frank.billenkamp@nortel.com","GP#37 completed","44.018; 48.008",null,null,null,null,"2006-07-05","2008-05-16"]
[7352,350041,"   Stage 3 for PNM","PNM",2,"Rel-8","C1,C4","2007-03-26","2009-03-06",1,"CP-080065","-","Vodafone","yang.lu@vodafone.com","CP#43 completed","-",null,null,null,null,"2006-02-16","2007-11-19"]
[{"$f":"A7356+1","v":7356},350049,"   Deleted - Actual Requirements of PNM","PNM",2,"Rel-8","C1","2007-03-26","2007-03-26",1,"-","-","Ericsson","-","SP#37 stopped","-",null,null,"SP-37",null,"2007-05-04","2009-03-24"]
[7357,330005,"eCall Data Transfer","EData",1,"Rel-8","S1,C1","2006-09-28","2009-03-06",1,"SP-060678","-","Airbiquity","rrobinson@airbiquity.com","SP#39 completed. Linked to SA4 Feature UID_34042 (eCall_Phase2)","-",null,null,null,null,"2006-10-06","2010-08-02"]
[7361,450001,"eCall Conformance Testing","eCall_MSTest",1,"Rel-8","G3new","2009-09-04","2010-09-03",1,"GP-091098","-","Ericsson, Qualcomm","Vikrant Jain (vikrantj@qualcomm.com)","GP#47 completed. GP#43 WID approved. Testing for Rel-8 eCall_Phase2 (UID_34042) and EData (UID_330005)","51.010-1; 51.010-2",45,23,null,null,"2009-09-07","2010-09-04"]
[7364,380061,"   Stage 1 for IPinterc","IPinterc",2,"Rel-8","S1","2007-12-06","2008-03-12",1,"SP-080565","-","Telefónica O2","chris.friel@O2.com","SP#39 completed. ","22.101; 22.228",38,21,null,null,"2007-12-13","2010-08-02"]
[7370,7006,"      Deleted (never approved) - Stage 2 of FBI for TISPAN R2 - Rel 8","FBI2-TISP2-s2",3,"Rel-8","S2","2007-11-30","2007-11-30",1,"-","-","Nokia Siemens Networks","-","SP#36 stopped","-",null,null,"SP-36",null,"2006-02-16","2009-03-24"]
[7372,410002,"   Stage 1 for SIP_Nc (covered by Feature IPinterc)","SIP_Nc",2,"Rel-8","S1","2007-12-06","2008-03-12",1,"SP-070871","-","Telefónica O2","chris.friel@O2.com","22/07/08 Created. Stage 1 for SIP_Nc (covered by SA1 Feature UID_380060 Ipinterc)","22.101; 22.228",41,21,null,null,"2007-12-13","2008-03-20"]
[7375,360028,"   Interworking between the 3GPP CS domain with SIP-I as signalling protocol and other networks","SIP_Nc-St3C3",2,"Rel-8","C3","2007-09-14","2009-03-06",1,"CP-080282","-","Nokia Siemens Networks","Thomas.Belling@nsn.com","CP#43 completed. CP#42 target 12/08=>03/09","29.235; 23.172; 23.202; 29.007; 29.163; 29.414",null,null,null,null,"2007-09-05","2009-02-19"]
[7379,400015,"   CT1 aspects of ETWS","ETWS",2,"Rel-8","C1","2008-05-30","2008-12-05",1,"CP-080951","-","NTT DoCoMo","yamashitahi@s1.nttdocomo.co.jp","CP#42 completed",23.041,40,21,null,null,"2007-12-13","2010-08-02"]
[7383,380059,"In Case of Emergency numbers storage and easy access on UICC ","ICE",1,"Rel-8","S1,C6","2007-03-13","2009-03-06",1,"SP-070944","-","Vodafone","armin.toepfer@vodafone.com","CP#43 completed (ICE Graphics not included in Rel-8)","-",38,21,null,null,"2007-12-13","2009-03-04"]
[7384,380159,"   Stage 1 for ICE","ICE",2,"Rel-8","S1","2007-03-13","2008-03-12",1,"SP-070944","-","Vodafone","armin.toepfer@vodafone.com","SP#39 Stage 1 completed","22.030; 22.101",38,21,null,null,"2007-12-13","2008-06-17"]
[7388,370028,"   Stage 1 for CAT","CAT",2,"Rel-8","S1","2006-12-06","2007-09-20",1,"SP-070122","-","China Mobile","fenglingjuan@chinamobile.com","-",22.181999999999999,37,null,null,null,"2007-10-02","2008-09-10"]
[7391,390114,"      IMS CAT SS","CAT-SS",3,"Rel-8","C1","2008-04-21","2008-12-04",1,"CP-080496","-","Nortel","milanpa@nortel.com","CP#42 completed",24.181999999999999,39,21,null,null,"2008-03-03","2008-11-21"]
[7397,350047,"   Stage 1 for MESSIW","MESSIW",2,"Rel-8","S1","2007-03-26","2007-03-26",1,"SP-070816","-","Huawei","ling.liu@huawei.com","SP#35 completed","22.105; 22.340",null,null,null,null,"2005-11-04","2008-03-22"]
[7399,400016,"   CT3 part of Stage 3 for MESSIW","MESSIW",2,"Rel-8","C3","2008-05-30","2009-03-06",1,"CP-080773","-","Huawei","xupeili@huawei.com","CP#43 completed",29.311,40,21,null,null,"2006-07-19","2009-02-19"]
[7402,320023,"   Service Requirements for PRIOR","PRIOR_EMR",2,"Rel-8","S1","2006-06-08","2007-12-06",1,"SP-060780","-","Telcordia","jgarraha@telcordia.com","SP#38 completed","New 22.153",32,null,null,null,"2003-03-28","2008-06-03"]
[7406,360010,"Open Service Access (OSA) Rel-8 ","OSA8",1,"Rel-8","S1,C5","2007-08-23","2008-05-30",1,"SP-070692","-","Orange","Song Dong","SP#40 maintenance & new OSA work moved to OMA. Rel-9 onwards 3GPP references to 22.127 changed to OMA Parlay Service Access Requirements (OMA-RD-Parlay_Service_Access-V1_0-20100427-A).","-",null,null,null,null,"2005-03-22","2010-08-30"]
[7410,370012,"      Deleted - Ensure Parlay-X composable with identity management frameworks, in particular Liberty Alliance","-",3,"Rel-8","C5","2007-10-25","2008-05-30",1,"CP-080429","-","Ericsson","catherine.mulligan@ericsson.com","CP#40: Work moved to OMA","existing 29.199-xy",37,21,"CP-40","PCG-21","2007-09-13","2009-03-24"]
[7411,370013,"      Parlay-X Content Management web service (store/manage meta-data)","OSA8-IMS",3,"Rel-8","C5","2007-10-25","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.199-21",37,null,null,null,"2007-09-13","2009-01-19"]
[7415,380047,"      Deleted - Security on User Profile Management - reuse GUP API (22.127 CR 0084 S1-071794)","-",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Telecom Italia","vincenzo.amorino@telecomitalia.it","SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA","PXWS Framework",38,21,"CP-40","PCG-21","2007-12-05","2009-03-24"]
[7418,380050,"      Deleted - Subscriber event notification (22.127 CR 0087 S1-071836)","-",3,"Rel-8","C5","2007-12-05","2008-05-30",1,"CP-080429","-","Telecom Italia","vincenzo.amorino@telecomitalia.it","SP#38 SP-070853 R8 CRs 22.127 OSA Stage 1. CP#40: Work moved to OMA","PXWS Framework",38,21,"CP-40","PCG-21","2007-12-05","2009-03-24"]
[7424,390067,"      Framework Enterprise Operator (Service Subscription function)","OSA8-IMS",3,"Rel-8","C5","2008-01-10","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.198-03",39,21,null,null,"2008-03-26","2009-01-19"]
[7426,390069,"      Connectivity Manager SCF","OSA8-IMS",3,"Rel-8","C5","2008-01-10","2008-05-30",1,"CP-080429","-","Alcatel-Lucent","unmehopa@alcatel-lucent.com","CP#40 completed","29.198-10",39,21,null,null,"2008-03-26","2009-01-19"]
[7429,370084,"   Stage 1 for PPACR","PPACR-S1",2,"Rel-8","S1","2007-06-12","2007-09-14",1,"SP-070501","-","NTT DoCoMo","Morita Takashi","SP#37 completed",22.010999999999999,37,null,null,null,"2007-10-16","2008-05-16"]
[7434,380065,"Home NodeB / eNodeB","HomeNB",1,"Rel-8","S1,C1,C4","2007-12-06","2009-03-06",1,"SP-070952","-","Vodafone","John Watson","CP#43 completed","-",38,21,null,null,"2007-12-13","2009-03-11"]
[7437,410012,"   CSG and Idle Mode Mobility for LTE Home eNodeB","HomeNB-LTE",2,"Rel-8","C1","2008-09-12","2009-03-06",1,"CP-080498","-","Huawei","zhang.peng@huawei.com","CP#43 completed","23.122; new (24.285; 24.301; 24.801)",41,21,null,null,"2008-09-03","2009-03-11"]
[7438,410013,"   CSG and Idle Mode Mobility for 3G Home NodeB","HomeNB-3G",2,"Rel-8","C1","2008-09-12","2009-03-06",1,"CP-080792","-","Qualcomm","Osok Song","CP#43 completed","23.122; 24.008; new 24.285",41,21,null,null,"2008-09-03","2009-03-11"]
[7442,390034,"   FDD Home NodeB RF requirements","HNB-RF",2,"Rel-8","R4","2008-03-07","2009-03-06",1,"RP-080971","RP-090041","Motorola","Ying Cai (yingcai@motorola.com)","RP#43 completed","25.104; 25.141; new 25.967",39,21,null,null,"2004-09-27","2009-02-27"]
[7447,390046,"Generic Bootstrapping Architecture Push Function","GBAPush",1,"Rel-8","S3,C1,C4","2008-03-12","2009-03-06",1,"SP-080133","-","Ericsson","Rolf Blom","CP#43 completed","-",39,21,null,null,"2008-03-22","2009-02-20"]
[7449,390246,"   CT1 part of GBAPush ","GBAPush",2,"Rel-8","C1","2008-03-12","2009-03-06",1,"CP-090112","-","Ericsson","Rolf Blom","CP#43 completed",24.109000000000002,39,21,null,null,"2008-03-22","2009-03-04"]
[7453,400028,"Encoding formats, transport formats and media description signalling for interworking, QoE, and other enhancements to MTSI-MHI","MTSI_eMHI",1,"Rel-8","S4,C3,C4","2007-12-06","2009-03-12",1,"SP-080443","-","Ericsson, Qualcomm","olle.franceschi@ericsson.com, nleung@qualcomm.com","TSG#43 completed","-",40,21,null,null,"2007-12-09","2009-02-21"]
[7456,400020,"   CT4 part of Enhancement of interworking between MTSI and CS networks","MTSI_eMHI",2,"Rel-8","C4","2008-05-30","2009-03-06",1,"CP-080774","-","Huawei","Tingfang Tang (tagna_online@huawei.com)","CP#43 completed",29.332000000000001,40,21,null,null,"2007-12-09","2009-02-20"]
[7461,35053,"      Advanced Alarming on Itf-N","OAM8-NIM",3,"Rel-8","S5","2007-06-07","2008-06-12",1,"SP-070492","-","Nokia Siemens Networks","SUERBAUM, Clemens","SP#40 completed","32.121; 32.122; 32.123",null,null,null,null,"2005-06-17","2008-06-04"]
[7464,400030,"      IRP SOAP Solution Sets","OAM8-NIM",3,"Rel-8","S5","2008-06-05","2009-03-12",1,"SP-090148","-","Ericsson","edwin.tse@ericsson.com","SP#43 completed","32.111-7; 32.617; 32.417; 32.367; 32.347; 32.111-1; 32.111-2; 32.111-3; 32.111-5; 32.307; 32.317; 32.341; 32.342; 32.343; 32.345; 32.361; 32.362; 32.363; 32.365; 32.411; 32.412; 32.413; 32.415; 32.611; 32.612; 32.613; 32.615; 32.625",40,21,null,null,"2007-09-15","2009-08-11"]
[7465,450052,"      Create missing specifications for IRP XML definitions","OAM8-NIM",3,"Rel-8","S5","2009-09-24","2009-12-04",1,"SP-090553","-","ZTE","Shuqiang Huang (huangsq@zte.com.cn)","SP#46 completed. Create missing XML definitions specs for IRPs (Advanced Alarm Management, Communication Surveillance, Self-Configuration of Network Elements, Software Management) needed for implementation of Rel-8 Notification Log IRP (TS 32.33x)","new (32.125; 32.355; 32.505; 32.535); 32.150; 32.153; 32.335 ",45,23,null,null,"2009-09-11","2009-12-01"]
[7469,360001,"      HSUPA performance measurements ","OAM8-PM",3,"Rel-8","S5","2007-06-07","2008-12-11",1,"SP-070835","-","China Mobile","Li Jian (lijian@chinamobile.com)","SP#42 completed",32.405000000000001,null,null,null,null,"2007-05-28","2008-11-25"]
[7474,531003,"      Deleted - (IETF) Service Level Tracing in IMS (draft-dawes-sipping-debug-event)","OAM8-Trace",3,"Rel-8","C1-IETF","2008-03-07","2011-12-09",1,"CP-080315","-","Peter Dawes","peter.dawes@vodafone.com","CP#54 Draft removed from 3GPP documentation, covered by draft-dawes-sipping-debug; 9/4/21: 100%->100","draft-dawes-sipping-debug-event",53,27,null,null,"2011-07-29","2021-04-09"]
[7477,870081,"   (IETF) A Two-Way Active Measurement Protocol (TWAMP) (draft-ietf-ippm-twamp) --> RFC 5357","OAM8",2,"Rel-8","S5-IETF","2008-03-07","2010-09-06",1,"-","-","-","-","-","-",34,null,null,null,"2007-07-13","2009-03-24"]
[7480,360003,"   SMS online charging","CH8",2,"Rel-8","S5","2007-06-07","2007-12-14",1,"SP-070293","-","Vodafone","Gavin.Wong@vodafone.com","SP#38 completed","32.240; 32.299; new 32.274",null,null,null,null,"2007-05-29","2008-03-17"]
[7483,380024,"Conferencing enhancements for Mp interface","eMp",1,"Rel-8","C4","2007-11-30","2008-12-05",1,"CP-080725","-","Huawei","Chencheng@huawei.com","CP#42 completed","-",null,21,null,null,"2007-11-19","2010-08-02"]
[7488,350046,"   External interface for eUPHBOOK","eUPHBOOK-Ext_Spec",2,"Rel-8","C6","2007-05-07","2008-03-07",1,"CP-080382","-","Gemalto","Jacques.seif@gemalto.com","CP#39 completed","new 31.220",null,null,null,null,"2006-01-24","2008-05-29"]
[7492,330018,"   LTE – Physical Layer","LTE-Phys",2,"Rel-8","R1","2006-09-25","2008-03-07",1,"RP-080747","RP-080741","NTT DoCoMo","Sadayuki Abeta","RP#39 completed","36.201; 36.211; 36.212; 36.213; 36.214; 25.215; 25.225",null,null,null,null,"2006-03-21","2009-12-18"]
[7495,330021,"   LTE – Evolved UTRA and UTRAN RF Radio Transmission/Reception, System Performance Requirements and Conformance Testing","LTE-RF",2,"Rel-8","R4","2006-09-25","2008-12-05",1,"RP-080747","RP-080741","Nokia Siemens Networks","Tuomo Saynajakangas","RP#42 completed. RP#47 abandoned draft 36.801, 36.803, 36.804","36.101; 36.104; 36.113; 36.124; 36.133; 36.141; 36.942; 25.123; 25.133",null,null,null,null,"2006-03-21","2010-03-16"]
[7496,370046,"   LTE – FDD repeaters","LTE-Repeaters",2,"Rel-8","R4","2007-09-14","2009-03-06",1,"RP-070749","RP-090037","Powerwave Technologies, Andrew Wireless","ralf.michanikl@andrew.com, Alf.Ahlstrom@pwav.com","RP#43 completed. RP#47 create Rel-9 TR 36.956 (see R4-100386, RP-100320_RAN4 Report)","36.106; 36.143; 25.113",37,null,null,null,"2007-10-01","2010-03-16"]
[7501,390003,"      Key Performance Indicators (KPIs) for E-UTRAN","E-UTRAN-OAM",3,"Rel-8","S5","2008-02-22","2009-03-12",1,"SP-080063","-","Ericsson ","ulf.hubinette@ericsson.com ","SP#43 completed","new (32.450; 32.451)",39,21,null,null,"2005-06-17","2009-02-23"]
[7504,390005,"      Self-Establishment of eNBs, including automated Software Management","LTE_SON-OAM",3,"Rel-8","S5","2008-02-22","2008-12-11",1,"SP-080849","-","Nokia Siemens Networks","SUERBAUM, Clemens","SP#42 completed","new (32.501; 32.502; 32.503; 32.531; 32.532; 32.533)",39,21,null,null,"2005-06-17","2010-03-22"]
[7507,25041,"   3G LTE – Terminal Protocol Conformance Test Specifications","LTE-UEConTest_SIG",2,"Rel-8","R5","2007-06-01","2009-12-04",1,"RP-080647","RP-091060","NEC, Motorola","david.lecompte@nectech.fr, Jacob.John@motorola.com","RP#46 completed","36.521-1; 36.521-2; 36.508; 36.509; 36.523-1; 36.523-2; 36.523-3",null,null,null,null,"2006-03-21","2009-11-27"]
[7510,350034,"   UMTS 1500 MHz","RInImp8-UMTS1500",2,"Rel-8","R4","2007-03-05","2007-09-14",1,"RP-070078","RP-070526","NTT DoCoMo","Takehiro Nakamura (nakamurata@nttdocomo.co.jp)","RP#37 completed","25.101; 25.104; 25.133; 25.141; 25.331; 25.942; 25.306; 25.307; 34.121",null,null,null,null,"2004-09-27","2009-07-09"]
[7515,370032,"   CS Voice Service over HSPA","RInImp8-CsHspa",2,"Rel-8","R2","2007-07-19","2008-03-07",1,"RP-070765","RP-080042","Nokia Siemens Networks","woonhee.hwang@nsn.com","RP#39 completed","25.323; 25.331; 25.322",37,null,null,null,"2007-10-02","2010-08-02"]
[7519,25050,"   Conformance Test Aspects – CS Voice Service over HSPA","RInImp8-CsHspa_UEConTest",2,"Rel-8","R5","2007-06-01","2008-09-12",1,"RP-080160","RP-080542","Huawei","baoyi@huawei.com","RP#41 completed","34.108; 34.123-1; 34.123-2; 34.123-3",null,null,null,null,"2008-03-11","2008-09-09"]
[7522,360013,"   Combination of 64QAM and MIMO for HSDPA (FDD)","RANimp-64QamMimoHsdpa",2,"Rel-8","R1","2007-06-04","2008-09-12",1,"RP-070500","RP-080518","Ericsson","Johan.Bergman@ericsson.com","RP#41 completed","25.308; 25.211; 25.212; 25.213; 25.306; 25.331; 25.433; 25.435; 25.423; 25.425; 25.101; 25.104; 25.141",null,null,null,null,"2007-06-21","2010-08-03"]
[7523,370036,"   Improved L2 for uplink","RANimp-UplinkL2dataRates",2,"Rel-8","R2","2007-09-14","2008-05-30",1,"RP-070717","RP-080265","Ericsson","Janne.Peisa@ericsson.com","RP#40 completed. Linked to UID_370037 Enhanced Uplink for CELL_FACH State in FDD","25.319; 25.301; 25.306; 25.321; 25.331; 25.433; 25.435; 25.423; 25.425; 25.427",37,null,null,null,"2007-10-02","2010-08-03"]
[7528,380075,"   64QAM for 1.28 Mcps TDD HSDPA","RANimp-64Qam1.28TDD",2,"Rel-8","R1","2007-12-04","2008-12-05",1,"RP-070924","RP-080806","ZTE","zfmail@zte.com.cn","RP#42 completed. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824","25.102; 25.105; 25.123; 25.142; 25.201; 25.221; 25.222; 25.223; 25.224; 25.306; 25.308; 25.321; 25.331; 25.423; 25.433",38,21,null,null,"2007-12-17","2010-08-03"]
[7531,390029,"   HSPA VoIP to WCDMA/GSM CS continuity","RANimp-HSPAVoIP",2,"Rel-8","R2","2008-03-07","2009-03-06",1,"RP-080749","RP-090050","Nokia","Simone.Provvedi@nokia.com","RP#43 completed","25.331; 25.413",39,21,null,null,"2008-03-17","2010-08-03"]
[7533,400050,"   MIMO for 1.28 Mcps TDD. Linked to Rel-8 Study on Scope of future HSPA Evolution for 1.28 Mcps TDD (UID_370041) TR 25.824","RANimp-MIMOLCR",2,"Rel-8","R1,R4","2008-01-24","2009-05-29",1,"RP-080485","RP-090313","CATT","wangke@datangmobile.cn","RP#43 completed","25.201; 25.221; 25.222; 25.223; 25.224; 25.306; 25.308; 25.321; 25.331; 25.423; 25.433; 25.102; 25.105; 25.142",40,21,null,null,"2008-03-17","2010-08-03"]
[7538,440010,"   Conformance Test Aspects – 1.28 Mcps TDD Improved L2 support for high data rates","RANimp-UEConTest_ImprovedL2LCRTDD",2,"Rel-8","R5","2009-05-29","2010-09-17",1,"RP-090491","RP-100737","CATT","Xiaozhong Chen (chenxiaozhong@datangmobile.cn)","RP#49 completed. Testing for Rel-7 UID_340039 Improved L2 support for high data rates and Rel-8 UID_370036 Improved L2 for uplink","34.108; 34.123-1; 34.123-2; 34.123-3",44,23,null,null,"2009-05-20","2010-09-09"]
[7542,430028,"   Conformance Test Aspects – Receiver Type3i","RANimp-UEConTest_ReceiverType3i",2,"Rel-8","R5","2009-03-06","2009-12-04",1,"RP-090010","RP-091066","Qualcomm","Ashok Kumar Narayanaswamy (anarayan@qualcomm.com)","RP#46 completed. Testing for Receiver Type3i in 25.101 UE radio Tx and Rx FDD","34.108; 34.121-1; 34.121-2",43,22,null,null,"2009-03-10","2010-08-03"]
[7546,450026,"   Conformance Test Aspects – HS-DSCH Serving Cell Change Enhancements","HSDSCH_UEConTest",2,"Rel-8","R5","2009-09-18","2010-03-19",1,"RP-090756","RP-100077","Qualcomm","Shubhang Vora (svora@qualcomm.com)","RP#47 completed. Testing for UID_390030","34.108; 34.121-1; 34.121-2; 34.123-1; 34.123-2; 34.123-3",45,23,null,null,"2009-09-15","2010-08-03"]
[7547,360008,"3.84 Mcps TDD MBMS over a Single Frequency Network (MBSFN) Integrated Mobile Broadcast","MBSFN-DOB",1,"Rel-8","R1","2007-06-04","2008-12-05",1,"RP-081124","RP-080218","Ericsson","Lars.Lindbom@ericsson.com","RP#42 completed. WID updated RP-070493=>RP-081124 (changed WI title \"MBSFN Downlink Optimized Broadcast (DOB) 3.84 Mcps TDD\" => \"3.84Mcps TDD MBSFN Integrated Mobile Broadcast\"). ","25.102; 25.105; 25.123; 25.201; 25.221; 25.222; 25.223; 25.224; 25.304; 25.306; 25.331; 25.346; 25.402; 25.433",null,null,null,null,"2007-06-21","2008-12-09"]
[7550,51583,"   G1 part of GERAN support for GERAN - 3G Long Term Evolution interworking","GELTE",2,"Rel-8","G1","2006-09-08","2009-02-20",1,"GP-061757","-","Nokia, Nokia Siemens Networks","sergio.parolari@nsn.com, vlora.rexhepi@nokia.com","GP#41 completed","43.055; 43.129; 43.246; 45.002; 45.008; 45.010",null,null,null,null,"2006-09-13","2010-09-09"]
[7555,50587,"GAN Enhancements","GANENH",1,"Rel-8","GP","2007-05-15","2009-09-04",1,"GP-071484","-","T-Mobile","mohammed.versi@t-mobile.com","GP#37 completed. GP#43 completed Testing","-",null,null,null,null,"2007-09-06","2009-09-28"]
[7558,50591,"AoIP (A-interface over IP)","AoIP",1,"Rel-8","GP,S4,C4,C1,C3","2000-01-03","2008-12-11",1,"GP-081361","-","China Mobile, Ericsson","wangshuaiyu@chinamobile.com, paul.schliwa-bertling@ericsson.com","GP#40/TSG#42 completed . Triggered by TR 43.903 Study on A-interface over IP (AINTIP) UID_50589. ","-",null,21,null,null,"2008-02-26","2008-12-03"]
[7560,400042,"   Media Requirements for CS over IP based User Plane","AoIP-CSoIP",2,"Rel-8","S4","2007-12-05","2008-12-11",1,"SP-080444","-","China Mobile, Ericsson","Karl.Hellwig@Ericsson.com","SP#42 completed","26.102; 26.103; 26.202",40,21,null,null,"2007-12-09","2008-11-21"]
[7565,51147,"New multicarrier BTS class ","MCBTS",1,"Rel-8","G1","2007-08-31","2008-08-29",1,"GP-071542","-","Alcatel-Lucent","thomas.bitzer@alcatel-lucent.de","GP#39 completed","45.005; 45.050; 51.021",null,null,null,null,"2007-09-06","2008-08-31"]
[7569,400051,"   RAN2 part of Support for Additional Navigation Satellite Systems (ANSS) for LCS","RANimp-ANSS",2,"Rel-8","R2","2008-05-30","2008-12-05",1,"RP-080346","RP-080813","Qualcomm","Etienne Chaponniere (echaponn@qualcomm.com)","RP#42 WI closed at 95%. Considers Rel-9 performance requirements","25.305; 25.306; 25.331; 25.413; 25.423; 25.433; 25.453",40,21,null,null,"2008-03-17","2008-12-04"]
[7573,53091,"MS conformance testing of changes introduced by WI \"Support of Packet-switched Handover for GERAN A/Gb mode\"","PSHCT-MStest",1,"Rel-8","G3new","2008-02-22","2008-11-21",1,"GP-080411","-","Rohde & Schwarz","Franz.Segerer@ROHDE-SCHWARZ.COM","GP#40 completed",51.01,null,21,null,null,"2008-02-26","2008-11-22"]
[7574,320001,"(Small) Technical Enhancements and Improvements for Rel-8","TEI8",1,"Rel-8","SP,CP,RP,GP","2007-01-01","2008-12-11",1,"-","-","-","-","SP#42 completed","-",null,null,null,null,"2005-11-04","2009-02-20"]
[7578,31068,"   Deleted - Stage 1","AIPN",2,"Rel-8","S1","2004-06-28","2006-03-15",1,"SP-050181","-","NTT DoCoMo","c.masyu@nttdocomo.co.jp","22.258 withdrawn, superseded by 22.278 (UID 320022). SP#38 stopped",22.257999999999999,null,null,"SP-38",null,"2004-08-30","2009-03-24"]
[7581,330007,"Deleted -Enhancements to BS30 Bearer service for Videotelephony","BS30",1,"Rel-8","S1","2007-03-15","2007-03-15",1,"SP-060484","-",3,"andre.jarvis@three.co.uk","SP#38 stopped (no support)","22.002; 22.004; 22.101; 22.105; 24.008",null,null,"SP-38",null,"2006-10-06","2009-03-24"]
[7585,400223,"   Deleted - Contact Manager API for Java™ Card test specification ","eUPHBOOK-Test",2,"Rel-8","C6","2008-06-02","2010-03-19",1,"CP-080430","-","Gemalto","jacques.seif@gemalto.com","CP#47 work stopped/abandoned","31.321 (internal interface (API))",40,21,"CP-47","PCG-24","2008-11-24","2010-03-09"]
[7587,0,"Release 8 Studies","-",1,"Rel-8","CP,GP,RP,SP","2005-10-07","2005-10-07",1,"-","-","-","-","-","-",null,null,null,null,"2004-09-08","2010-02-09"]
[7593,330016,"Study on Paging Permission with Access Control","FS_PPAC",1,"Rel-8","S1","2006-09-28","2007-09-20",1,"SP-060785","-","NTT DoCoMo","Katsuhiro NOGUCHI (noguchi@nttdocomo.co.jp)","SP#37 completed. Spin-off new Feature UID_370084 (PPACR)",22.908000000000001,null,null,null,null,"2006-10-06","2010-08-31"]
[7596,340035,"Study on Service continuity between mobile and WLAN networks","FS_SMLSWLAN",1,"Rel-8","S1","2006-12-06","2007-12-06",1,"SP-060936","-","NEC","joerg.swetina@neclab.eu","SP#38 completed",22.937000000000001,34,null,null,null,"2006-10-06","2010-08-31"]
[7600,32087,"   Stage 2 study on 3GPP architectural development","FS_SAE",2,"Rel-8","S2","2006-01-09","2008-09-18",1,"SP-070163","-","Vodafone","chris.pudney@vodafone.com","SP#41 completed",23.882000000000001,null,null,null,null,"2005-01-31","2008-09-14"]
[7601,7024,"   Security study for Inter-access mobility between non-3GPP and 3GPP system","FS_SAE",2,"Rel-8","S3","2007-09-03","2009-03-12",1,"SP-070163","-","Nokia","dajiang.zhang@nokia.com","SP#43 completed","33.821; 33.822",null,null,null,null,"2006-02-21","2009-02-20"]
[7605,380034,"Study on centralized IMS service control","FS_ICS",1,"Rel-8","S2,S1","2006-10-23","2008-03-12",1,"SP-070494","-","Ericsson","peter.bleckert@ericsson.com","SP#39 completed","-",38,21,null,null,"2007-10-31","2008-03-20"]
[7608,380078,"Study on Architecture of IMS based Customized Alerting Tone (CAT)","FS_CAT-St2",1,"Rel-8","S2","2007-12-04","2008-09-18",1,"SP-070905","-","China Mobile","WANG, Jing (wangjing@chinamobilecom)","SP#41 completed as Rel-8",23.872,38,21,null,null,"2007-12-20","2008-09-23"]
[{"$f":"A7612+1","v":7612},35074,"Study on SA5 MTOSI XML Harmonization","OAM8-NIM-XML",1,"Rel-8","S5","2006-05-10","2007-09-12",1,"SP-070305","-","Nortel","jduguay@nortel.com","SP#37 completed. WID updated SP-050295=>SP-070305",32.817999999999998,null,null,null,null,"2005-11-24","2009-10-15"]
[7614,340036,"Study on Management for LTE and SAE","FS_OAM_LTE_SAE",1,"Rel-8","S5","2006-12-07","2008-12-11",1,"SP-060753","-","Ericsson","robert.petersen@ericsson.com ","SP#42 completed",32.816000000000003,34,null,null,null,"2006-12-15","2008-11-25"]
[7620,380023,"Study on InterWorking Function between MAP based and Diameter based interfaces","FS_MAP2Diam",1,"Rel-8","C4","2007-11-30","2008-12-05",1,"CP-070760","-","Huawei","liming49985@huawei.com","CP#42 completed. Spin-off implementation Building Block UID_410007 (MAP2Diam) under the SAES Feature UID_320005",29.805,38,21,null,null,"2007-11-19","2008-11-22"]
[7623,360016,"Study on Improved network controlled mobility between LTE and 3GPP2/mobile WiMAX radio technologies","FS_RAN-LTEmob",1,"Rel-8","R4","2007-06-04","2007-12-03",1,"RP-070511","RP-070827","Motorola","hao.bi@Motorola.com","RP#38 completed",36.938000000000002,null,null,null,null,"2007-06-21","2008-06-26"]
[7627,51148,"Study on Optimized Transmit Pulse Shape for Downlink EGPRS2-B ","WIDER",1,"Rel-8","G1","2007-11-16","2010-05-21",1,"GP-072026","-","Research In Motion, Nokia Siemens Networks","jdwyer@RIM.COM and eddie.riddington@nsn.com","GP#46 completed",45.912999999999997,null,null,null,null,"2008-02-26","2010-05-27"]
[7628,350017,"Deleted - Study on Mobility between 3GPP-WLAN Interworking and 3GPP Systems","FS_SM3GWLAN",1,"Rel-8","S2","2007-03-20","2008-09-18",1,"SP-070106","-","Orange","-","SP#41 stopped. Draft TR 23.827 content implemented in TS 23.327.","withdrawn 23.827",null,null,"SP-41","PCG-21","2007-03-29","2008-09-17"]
[7632,390032,"Deleted - Study on Dual-Cell HSDPA operation","FS_RAN-DCHS",1,"Rel-8","R1","2007-08-15","2009-03-06",1,"RP-080228","RP-090066","Qualcomm","Josef Blanz","RP#43 stopped (draft TR 25.825 v100 withdrawn). Conclusions in RP-090318 (RAN1 findings of the UTRA Multi-Carrier Evolution study). RP#42 New WI approved on Dual-Cell HSDPA operation on adjacent carriers (UID_400052)","withdrawn 25.825 v100",39,21,"RP-43","PCG-22","2007-12-17","2009-03-17"]
[7635,32106,"   TR on ServID","ServID",2,"Rel-7","S2","2005-05-02","2006-03-21",1,"SP-060293","-","Ericsson","stephen.terrill@ericsson.com","-",23.815999999999999,null,null,null,null,"2005-07-01","2008-07-01"]
[7639,32116,"Supporting Globally Routable User Agent URIs in IMS","GRUU",1,"Rel-7","S2,S1,C1","2005-11-14","2007-06-15",1,"SP-050633","-","Research In Motion","Adrian Buckley (abuckley@rim.com)","SP#29 approved WID","-",null,null,null,null,"2003-03-28","2008-07-01"]
[7641,7010,"   Stage 1,2 of GRUU","GRUU",2,"Rel-7","S1,S2","2006-07-03","2006-09-29",1,"SP-050633","-","Research In Motion","Adrian Buckley (abuckley@rim.com)","SP#29 approved WID","22.228; 23.228; 23.218; 24.229",null,null,null,null,"2006-02-16","2008-07-01"]
[7647,690069,"   UE Conformance Test Aspects - Multimedia Telephony Services for IMS (MTSI) over fixed access","MTSI_FIXED_ACCESS-UEConTest",2,"Rel-7","R5","2015-09-15","2017-03-15",1,"RP-151257",null,"Telecom Italia",null,"tested: REL-7 SA/CT WI MTSI;1/1/16: Compl:0%->5%¦22/3/16: Compl:5%->15%1/7/16: Compl:15%->30% ¦21/",null,69,35,null,null,"2015-09-29","2017-03-21"]
[7650,350147,"Multimedia Telephony Service for IMS (MTSI) - UE Conformance Testing","MTSI-UEConTest",1,"Rel-7","R5","2007-09-19","2009-03-12",1,"RP-080605","RP-090056","Ericsson, Motorola","Leif.Mattisson@ericsson.com, Jacob.John@motorola.com","RP#43 completed. Linked UID_7038 (MTSI)","34.123-1; 34.123-2; 34.123-3; 34.229-1; 34.229-2",null,null,null,null,"2006-03-21","2009-02-24"]
[7654,387003,"   SA2 aspects of MCIMSTR1","MCIMSTR1-S2",2,"Rel-7","S2","2007-09-18","2007-12-06",1,"SP-070915","-","Ericsson","Raymond Forbes","-","23.406; 23.417; 23.508.23.509; 23.511",38,21,null,null,"2008-01-10","2008-07-21"]
[7655,380072,"   SA1,SA2 part of Maintenance of TISPAN release 1 common IMS","IMS_Comm_Mtce7",2,"Rel-7","S2,S1","2007-07-02","2007-12-06",1,"SP-080501","-","BT, Ericsson","Dick Knight, Raymond Forbes","SP#38 completed","22.173; 22.273; 22.401; 23.406; 23.417; 23.508; 23.509; 23.511",38,21,null,null,"2007-10-02","2010-07-29"]
[7659,32046,"   Study on Stage 2 for IMS-level solution","EMC1",2,"Rel-7","S2","2003-02-26","2005-09-16",1,"SP-050604","-","Siemens","Rainer Liebhart","-",23.867000000000001,null,null,null,null,"2003-03-27","2005-12-22"]
[7663,1653,"   Emergency Call Enhancements for IP& PS Based Calls – stage 3","EMC1",2,"Rel-7","C1,C4,IETF","2006-01-09","2011-12-09",1,"CP-050529","-","Ericsson","alf.heidermark@ericsson.com","-","-",null,null,null,null,"2000-08-08","2005-12-22"]
[7668,1646,"      CT1 PS domain aspects to support IMS Emergency sessions","EMC1",3,"Rel-7","C1","2006-01-09","2007-06-15",1,"CP-050529","-","Ericsson","alf.heidermark@ericsson.com","-","24.008; 24.234",null,null,null,null,"2000-08-08","2007-09-12"]
[7670,11065,"IMS Support of Conferencing","IMSconf",1,"Rel-7","C1","2005-11-04","2007-03-15",1,"CP-070120","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","CP#35 revised WID","24.147; 24.229",null,null,null,null,"2005-12-22","2008-07-01"]
[7674,32096,"   Stage 2 on Session Continuity: covered by SAE","WLAN2",2,"Rel-7","S2","2005-06-07","2005-06-07",1,"-","-","-","-","Acronym changed from \"WLAN2, WLAN-SC\"","-",null,null,null,null,"2005-06-07","2015-03-24"]
[7677,11059,"   WLAN-PNA - Stage 3","WLANPNA-st3",2,"Rel-7","C1,C3,C4","2006-02-01","2006-09-26",1,"CP-060256","-","NEC","-","Approved at CP#29","-",null,null,null,null,"2005-03-22","2006-06-23"]
[7681,32092,"Enhancements to support QoS provisioning over 3GPP/WLAN Interworking","WLANQOS",1,"Rel-7","S2,C4,C1","2005-03-14","2007-03-09",1,"SP-050682","-","Samsung","-","Moved from FS section Feb 06. SP-30 updated WID","-",null,null,null,null,"2005-06-07","2008-07-18"]
[7682,7015,"   Deleted - TR on support of QoS on WLAN","WLANQOS",2,"Rel-7","S2","2005-03-14","2006-01-31",1,"SP-050682","-","Samsung","-","SP#32 stopped",23.835999999999999,null,null,"SP-32",null,"2006-02-16","2008-07-18"]
[7686,32079,"Location Services enhancements","LCS3",1,"Rel-7","S1,S2,GP,C4,R2","2004-06-28","2007-12-17",1,"SP-040682","-","-","-","-","-",null,null,null,null,"2002-06-21","2008-07-02"]
[7690,20042,"   UE positioning - Velocity","LCS3-UEPos-Velocity",2,"Rel-7","R2","2005-03-15","2006-09-15",1,"RP-050300","RP-060459","SiRF","BRodilitz@SiRF.com","-","25.305; 25.331; 25.410; 25.413; 25.453",null,null,null,null,"2005-06-20","2008-07-02"]
[7695,340007,"      Stage 2 for LCS architecture for I-WLAN","LCS3-IWLAN",3,"Rel-7","S2","2006-10-23","2007-03-02",1,"SP-060818","-","LG Electronics","dhshim@lge.com ; phede@lge.com","-","23.234; 23.271; 23.167",34,null,null,null,"2006-02-16","2011-08-15"]
[7697,31084,"MBMS Enhancements","MBMSE",1,"Rel-7","S1,R1,C3","2005-07-11","2007-11-30",1,"SP-050389","-","China Mobile","liuhongyfw@chinamobile.com","-","-",null,null,null,null,"2005-06-20","2008-06-25"]
[7701,350022,"   MBMS Low Chip Rate TDD Physical Layer Enhancement","MBMSE-RANPhysLCRTDD",2,"Rel-7","R1","2007-03-16","2007-09-10",1,"RP-070253","RP-070292","RITT","Lin Hui","-","25.346; 25.221; 25.222; 25.223; 25.224; 25.306; 25.331; 25.402; 25.433; 25.102; 25.105; 25.123",null,null,null,null,"2007-04-02","2008-06-25"]
[7704,25049,"   Conformance Test Aspects – MBMS TDD Physical layer Enhancements – MBSFN for HCR and VHCR TDD","MBMSE-RANPhysTDD_UEConTest",2,"Rel-7","R5","2007-06-01","2008-09-12",1,"RP-080155","RP-080541","IPWireless","tspeight@ipwireless.com","RP#41 completed","34.108; 34.122; 34.123-1/2/3",null,null,null,null,"2008-03-11","2008-09-09"]
[7708,31051,"Advanced Global Navigation Satellite System (AGNSS) concept","LCS3-AGNSS",1,"Rel-7","S1,S2,GP,R2","2004-06-28","2007-08-31",1,"SP-040681","-","Alcatel","Michel.monnerat@thalesaleniaspace.com","-","-",null,null,null,null,"2004-08-30","2008-06-25"]
[7709,50551,"   Stage 1/2 for Towards AGNSS Concept","AGNSS",2,"Rel-7","S1,S2","2007-02-16","2007-02-16",1,"SP-040681","-","Alcatel","richard.couty@space.alcatel.fr","-","22.071; 23.271",null,null,null,null,"2012-05-21","2012-05-21"]
[7713,31048,"Unstructured Supplementary Service Data (USSD) message delivery and transfer to USIM","USSD-USIM",1,"Rel-7","S1,C6","2004-03-05","2005-08-12",1,"SP-040104","-","Axalto","Christophe Dubois (cdubois@axalto.com)","-","-",null,null,null,null,"2004-06-08","2008-09-10"]
[7717,31064,"   Stage 1 for CSICS","CSICS",2,"Rel-7","S1","2005-01-17","2005-06-09",1,"SP-050228","-","TeliaSonera","Robert.Frank@teliasonera.com","-",22.279,null,null,null,null,"2005-02-28","2008-07-02"]
[7722,31066,"   Stage 1 for CAMEL Trunk Triggers","TTCAMEL",2,"Rel-7","S1","2004-12-17","2005-12-05",1,"SP-040743","-","Nortel","Amar Deol (deola@nortelnetworks.com)","-",22.077999999999999,null,null,null,null,"2004-12-17","2008-07-18"]
[7724,31088,"IMS Service Brokering enhancements","ISB",1,"Rel-7","S1","2005-12-07","2006-03-13",1,"SP-050830","-","Telcordia","jbakker@telcordia.com","No CR submitted in rel-8 (according to CR database). ",22.228000000000002,null,null,null,null,"2005-11-04","2008-03-25"]
[7728,11056,"   Architecture and protocol aspects ","EVGCS",2,"Rel-7","C1,C4","2004-08-27","2007-06-15",1,"CP-050528","-","Siemens","robert.zaus@nsn.com","-","43.068; 44.068",null,null,null,null,"2005-09-14","2006-03-09"]
[7731,752076,"   GERAN2 aspects of EVGCS","EVGCS",2,"Rel-7","G2","2004-08-27","2007-02-16",1,"GP-071855","-","Siemens","kenneth.isaacs@roke.co.uk","-","-",75,38,null,null,"2004-10-15","2007-03-08"]
[7733,31070,"   Service Requirements for VGCS improvements","IVGCS",2,"Rel-7","S1","2005-03-15","2005-06-08",1,"SP-070167","-","T-Mobile","kurt.bischinger@t-mobile.at","-",42.067999999999998,null,null,null,null,"2005-03-22","2007-03-29"]
[7736,11063,"      CT1 aspects of IVGCS","IVGCS",3,"Rel-7","C1","2005-12-01","2007-03-15",1,"CP-070118","-","T-Mobile","-","-","43.068; 44.068",null,null,null,null,"2005-09-14","2007-09-12"]
[{"$f":"A7740+1","v":7740},31072,"      Service Requirements for OSA Service Broker","OSA7",3,"Rel-7","S1","2005-03-15","2005-06-08",1,"SP-050183","-","AePONA","eamonn.murray@aepona.com","-",22.126999999999999,null,null,null,null,"2005-03-22","2006-02-16"]
[7744,7018,"      Parlay X Message Broadcast Web Service","OSA7",3,"Rel-7","C5","2006-04-28","2006-12-01",1,"CP-070200","-","ETRI","-","-","29.199-15; 23.198",null,null,null,null,"2006-03-01","2012-07-26"]
[7749,340003,"      Parlay-X Multimedia Multicast Control Web Service","OSA7",3,"Rel-7","C5","2006-10-26","2007-03-09",1,"CP-070200","-","ETRI","-","-","29.199-20; 23.198",34,null,null,null,"2006-10-26","2012-07-26"]
[7751,31053,"Selective Disabling of UE Capabilities","SDoUE",1,"Rel-7","S1,S2,C1","2005-01-24","2007-06-15",1,"SP-050182","-","Motorola","-","Moved from FS section Feb 06","-",null,null,null,null,"2004-08-30","2008-07-17"]
[7754,7036,"   Stage 3 of SDoUE","SDoUE",2,"Rel-7","C1","2006-03-10","2007-06-15",1,"CP-070121","-","Ericsson","christian.herrero@ericsson.com","-",24.305,null,null,null,null,"2006-03-22","2008-07-17"]
[7759,32064,"Access Class Barring and Overload Protection","ACBOP",1,"Rel-7","S2,C1","2004-03-15","2006-09-08",1,"SP-040338","-","Vodafone","chris.pudney@vodafone.com","-",23.898,null,null,null,null,"2004-04-14","2008-07-15"]
[7760,32065,"   TR on Stage 2","ACBOP",2,"Rel-7","S2","2004-03-15","2005-03-31",1,"SP-040338","-","NTT DoCoMo","Jean-Jacques Davidian (davidian@docomo.fr)","-",23.898,null,null,null,null,"2004-04-14","2008-07-15"]
[7763,20009,"   Deleted - Extra ACBOP information in RAN","ACBOP",2,"Rel-7","RP","2004-03-15","2004-03-15",1,"-","-","-","-","-",25.331,null,null,"RP-25",null,"2004-04-14","2004-10-13"]
[7767,32075,"      Stage 2 of FBI for TISPAN R1","-",3,"Rel-7","S2","2004-10-14","2006-03-08",1,"-","-","-","-","-","-",null,null,null,null,"2006-02-16","2006-05-31"]
[7771,13025,"         CT3 aspects of FBI for TISPAN R1","-",4,"Rel-7","C3","2003-11-05","2006-12-08",1,"NP-040618","-","Siemens","peter.leis@nsn.com","-","29.163; 29.209",null,null,null,null,"2004-09-03","2006-10-12"]
[7776,7004,"      Protocol impact of FBI for PacketCable","-",3,"Rel-7","C1","2006-05-01","2007-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2006-02-16","2007-03-08"]
[7779,32094,"   FS on SMSIP","-",2,"Rel-7","S2","2004-10-14","2005-06-13",1,"SP-060658","-","Huawei","zhangwenlin@huawei.com","SP#33 updated WID",23.803999999999998,null,null,null,null,"2005-06-07","2008-07-15"]
[7781,310001,"   Stage 3 for SMSIP","SMSIP-St3",2,"Rel-7","C4,C1","2005-06-08","2007-06-14",1,"CP-060697","-","Nokia","jari.jansson@nokia.com","CP#34 updated WID","-",null,null,null,null,"2006-04-13","2008-07-15"]
[7786,32103,"   Stage 2 for PCC","-",2,"Rel-7","S2","2005-07-04","2006-09-15",1,"SP-060217","-","Nokia","balazs.bertenyi@nsn.com","SP-29 approved WID. SP-31 updated WID. 23.125 will be discontinued from Rel-7.",23.202999999999999,null,null,null,null,"2005-07-01","2008-07-18"]
[7787,32109,"   Evolution of policy control and flow based bearer level charging","-",2,"Rel-7","S2","2006-08-01","2006-12-29",1,"SP-060217","-","Nokia","balazs.bertenyi@nsn.com","SP-29 approved WID. SP-31 updated WID. 23.125 will be discontinued from Rel-7.","23.207; 23.002; 23.228",null,null,null,null,"2005-07-01","2008-07-18"]
[7790,13030,"   Rx reference point for PCC CT3 aspects","PCC-Rx",2,"Rel-7","C3,C1","2005-12-02","2007-11-30",1,"CP-060435","-","Ericsson","j.javier.pastor@ericsson.com","WID approved at CP#30, Revised at CP#31, Revised at CP#33","-",null,null,null,null,"2005-12-13","2008-07-18"]
[7794,32104,"   TR for Voice Call Continuity between CS and IMS (incl. I-WLAN)","-",2,"Rel-7","S2","2004-12-31","2005-12-08",1,"SP-060292","-","Alcatel-Lucent","andy.bennett@alcatel-lucent.com ","-",23.806000000000001,null,null,null,null,"2005-07-01","2008-07-21"]
[7799,11066,"      CT1 aspects of Stage 3 for Voice Call Continuity between CS and IMS (incl. I-WLAN)","-",3,"Rel-7","C1","2006-02-01","2007-06-15",1,"CP-070186","-","Alcatel-Lucent","Keith Drage (drage@alcatel-lucent.com)","-","24.206; 24.216",null,null,null,null,"2005-10-04","2008-07-21"]
[7802,7046,"One Tunnel solution for optimization of Packet Data Traffic","OPTUNEL",1,"Rel-7","S2","2006-03-27","2007-10-31",1,"SP-060819","-","Nokia","antti.j.pasanen@nokia.com","-","-",null,null,null,null,"2006-03-22","2008-07-15"]
[7806,320029,"CSI Terminating Session handling","CSItermS",1,"Rel-7","S2,C1","2006-06-08","2007-06-15",1,"SP-060437","-","Samsung","Osok Song","Triggered by the abandoned Study UID_32117 ","-",null,null,null,null,"2006-07-19","2008-07-17"]
[7808,340015,"   Stage 3 of CStermS","-",2,"Rel-7","C1","2006-12-14","2007-06-15",1,"CP-070239","-","Samsung","chenho.chin@samsung.com","CP-34 approved WID. CP-35 updated WID ","24.229; 24.279",34,null,null,null,"2007-01-05","2008-07-17"]
[7813,33026,"Lawful Interception in the 3GPP Rel-7 architecture","LI-7A",1,"Rel-7","S3","2005-06-28","2005-12-08",1,"SP-050237","-","BMWI","berthold.wilhelm@regtp.de","-","33.106; 33.107; 33.108",null,null,null,null,"2005-06-20","2008-07-16"]
[7814,33028,"Key establishment between a UICC and a terminal","KeyEstUTerm",1,"Rel-7","S3","2005-12-07","2006-09-28",1,"SP-050780","-","Gemalto","mireille.pauliac@gemplus.com","-",33.11,null,null,null,null,"2005-12-12","2008-01-10"]
[7817,732031,"   HTTPS connection between a UICC and a NAF","SEC7-HSUN",2,"Rel-7","S3,C1","2005-09-12","2005-09-12",1,"SP-050573","-","Gemalto","JSeif@axalto.com, mireille.pauliac@gemplus.com","-","33.918; 33.222; 24.109",null,null,null,null,"2005-11-04","2008-07-16"]
[7821,310004,"      SA3 aspects of SEC7-NDS-TCAPsec","SEC7-NDS-TCAPsec-SA3",3,"Rel-7","S3","2005-09-12","2006-03-10",1,"SP-050579","-","Siemens","marc.blommaert.ext@nsn.com","-",33.204000000000001,null,null,null,null,"2005-11-04","2008-07-16"]
[7826,7045,"   CT4 aspects of VGCSFlex","VGCSFlex-c4",2,"Rel-7","C4","2006-03-22","2007-03-09",1,"CP-060102","-","Siemens","robert.zaus@nsn.com","-",29.001999999999999,null,null,null,null,"2006-03-22","2008-07-21"]
[7829,13033,"Interworking between the 3GPP CS domain with BICC or ISUP as signalling protocol and external SIP-I networks","ExtSIPI",1,"Rel-7","C3","2006-09-22","2008-07-22",1,"CP-070101","-","Siemens","Thomas.Belling@nsn.com","-",29.164000000000001,null,null,null,null,"2006-10-06","2008-04-17"]
[7833,13026,"   Deleted - CT3 aspects of Mp","-",2,"Rel-7","C3","2006-09-22","2006-09-22",1,"-","-","Ericsson","philip.hodges@ericsson.com","CP#34: CT3 not involved in Mp interface definition",29.161999999999999,null,null,"CP-33",null,"2003-01-13","2008-07-15"]
[7835,14021,"   Stage 3 for Mp (MRFC - MRFP) interface","Mp-St3c4",2,"Rel-7","C4","2006-02-13","2007-06-08",1,"CP-070246","-","Ericsson","philip.hodges@ericsson.com","-",29.332999999999998,null,null,null,null,"2003-01-13","2008-07-15"]
[7840,330001,"High speed interface between the UICC and the ME","HSI",1,"Rel-7","C6","2006-09-22","2007-11-30",1,"CP-070259","-","Gemalto","jacques.seif@GEMALTO.COM","Following ETSI publication of TS 102 600, expected to be completed at CT6 meeting 45",31.100999999999999,null,null,null,null,"2006-09-21","2008-01-11"]
[7844,34035,"Optimizations for Multimedia Telephony over IMS","OMTIMS",1,"Rel-7","S4","2005-09-28","2005-09-29",1,"SP-060226","-","Ericsson","olle.franceschi@ericsson.com","Aug2015: 99%->100","26.235; 26.236",null,null,null,null,"2005-10-04","2015-08-12"]
[7845,34037,"   Deleted - Characterisation of Adaptive Jitter Management Performance for VoIP Services","OMTIMS-CAJMP",2,"Rel-7","S4","2005-09-28","2005-09-29",1,"SP-050432","-","Lucent","dhuo@lucent.com","SP-35 stopped","-",null,null,"SP-35",null,"2005-10-04","2007-03-29"]
[7849,35042,"   Rel-7 Network Infrastructure Management","OAM7-NIM",2,"Rel-7","S5","2005-09-02","2007-06-14",1,"-","-","-","-","-","-",null,null,null,null,"2005-06-17","2007-03-29"]
[7853,35048,"      Delta synchronization between IRP Manager and IRP Agent (Study + Implementation)","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050306","-","Siemens","-","-","32.391/2/3/5 ",null,null,null,null,"2005-06-17","2007-06-22"]
[7856,35052,"      Partial suspension of Itf-N during maintenance/testing (Study + Implementation)","-",3,"Rel-7","S5","2005-09-02","2007-06-14",1,"SP-050310","-","Siemens","-","-","32.381/2/3/5",null,null,null,null,"2005-06-17","2007-06-22"]
[7860,35071,"      Repeater Network Resource Model (NRM) definition","-",3,"Rel-7","S5","2006-02-13","2006-12-07",1,"SP-050731","-","China Mobile","-","-","32.721/2/3/5",null,null,null,null,"2005-11-24","2007-03-29"]
[7862,340009,"      Notification XML Schema","-",3,"Rel-7","S5","2006-12-07","2007-03-15",1,"SP-060754","-","Huawei","Christian.Toche@huawei.com","12/2006 SP#34 WID approved","New 32.325/345/365/415; CR to 32.335/615/665",null,null,null,null,"2006-12-15","2007-03-29"]
[7867,35060,"      ATM bearer network Performance measurements","-",3,"Rel-7","S5","2005-09-02","2007-03-15",1,"SP-050318","-","ZTE","-","-","No impact on 32.404; 32.405; 32.406; 32.407 ",null,null,null,null,"2005-06-17","2007-03-29"]
[7871,35040,"      End-to-end Service Level tracing for IMS","-",3,"Rel-7","S5","2005-11-11","2007-03-15",1,"SP-050627","-","Vodafone","-","07/2005: OMA (Stage 1), Stage 2/3 SA5, CT1/3/4","32.101; 32.421; 32.422; 32.423",null,null,"SP-31",null,"2005-03-02","2007-03-29"]
[7872,35062,"      Trace record content for UTRAN TDD","-",3,"Rel-7","S5","2005-09-02","2006-12-07",1,"SP-050628","-","Nokia","-","-","32.421; 32.422; 32.423",null,null,null,null,"2005-03-02","2007-03-29"]
[7876,320007,"Rel-7 Charging Management small Enhancements","CH7",1,"Rel-7","S5","2006-05-22","2007-06-14",1,"-","-","Orange","alain.bibas@orange-ft.com","CH7 is an umbrella Feature also for OAM&P related TEI7 type of changes that are not part of any other dedicated feature/WI",30.817,null,null,null,null,"2006-05-22","2009-03-09"]
[7880,21006,"   MIMO - Physical layer","MIMO-Phys",2,"Rel-7","R1","2003-09-12","2007-03-15",1,"RP-030192","RP-070037","Alcatel-Lucent","hchuang@Alcatel-Lucent.com","Completed Sep 2007¦SR in RP-070037","25.211; 25.212; 25.213; 25.214; 25.215; 25.221",null,null,null,null,"2003-03-27","2008-06-24"]
[7883,24008,"   MIMO - RF Radio Transmission/Reception, System Performance Requirements and Conformance Testing","MIMO-RF",2,"Rel-7","R4","2003-12-12","2007-09-17",1,"RP-030192","RP-070531","Alcatel-Lucent","ngm@Alcatel-Lucent.com","Completed Sep 2007¦SR in RP-070531","-",null,null,null,null,"2003-03-27","2008-06-24"]
[7885,25037,"      Conformance Test Aspects – Multiple Input Multiple Output Antennas (MIMO) for FDD","MIMO-UEConTest_FDD",3,"Rel-7","R5","2007-03-09","2008-03-07",1,"-","-","Qualcomm","svora@qualcomm.com","-","34.108; 34.109; 34.121-1; 34.121-2; 34.123-1; 34.123-2; 34.123-3",null,null,null,null,"2006-09-20","2010-06-16"]
[7891,20027,"   UMTS 900 MHz","RInImp-UMTS900",2,"Rel-7","R4","2004-12-15","2005-12-14",1,"RP-040541","RP-050662","Nortel","Yannick Li (yli@nortelnetworks.com)","RP#30 completed","25.101; 25.104; 25.113; 25.133; 25.141; 25.331; 25.942; 25.306; 25.307; 34.121",null,null,null,null,"2005-01-04","2010-07-27"]
[7892,20043,"   UMTS 1700 MHz","RInImp-UMTS1700",2,"Rel-7","R4","2005-03-15","2005-12-14",1,"RP-050385","RP-050824","NTT DoCoMo","Takehiro Nakamura (nakamurata@nttdocomo.co.jp)","RP#30 completed","25.101; 25.104; 25.113; 25.133; 25.141; 25.306; 25.307; 25.331; 34.121",null,null,null,null,"2005-06-20","2010-07-27"]
[7898,7029,"      Additional minimum UE performance requirement for downlink physical channels in support of E-DCH operation based on type 1 enhanced receiver (Rx-Diversity)","RInImp-RxDiv-EDCH",3,"Rel-7","R4","2006-03-15","2006-12-15",1,"RP-060184","RP-060679","Qualcomm","Serge Willenegger (sergew@qualcomm.com)","RP#34 completed",25.100999999999999,null,null,null,null,"2006-03-21","2010-07-27"]
[7899,20049,"   Deleted Improved support of gaming over HSDPA/EDCH","RInImp-Gaming",2,"Rel-7","R2","2005-12-15","2006-12-15",1,"-","RP-060680","Cingular","Don Zelmer (dz1069@att.com)","RP#34 stopped. SR in RP-060680","-",null,null,"RP-34",null,"2005-12-15","2010-07-27"]
[7903,25008,"   UE Conformance Test for UMTS 900 MHz (band VIII)","RInImp-UMTS900_Test",2,"Rel-7","R5","2005-11-11","2006-06-02",1,"-","-","Qualcomm","hanye@qualcomm.com","RP#32 completed","34.108; 34.121",null,null,null,null,"2002-02-28","2006-03-21"]
[7907,25028,"   Conformance Test Aspects – Extended UMTS 1.7/2.1 GHz","RInImp-UEConTest_UMTS1721Ext",2,"Rel-7","R5","2006-12-01","2007-06-01",1,"RP-060676","RP-070312","Motorola","carolyn.taylor@motorola.com","RP#36 completed","34.108; 34.121-1; 34.121-2",null,null,null,null,"2006-09-20","2007-06-11"]
[7910,20029,"Rel-7 RAN improvements","-",1,"Rel-7","RP,S5","2004-12-15","2007-06-15",1,"-","-","-","-","Generic feature","-",null,null,null,null,"2005-01-04","2008-06-25"]
[7912,20031,"   Delay optimization for procedures applicable to CS and PS Connections","RANimp-DelayOpt",2,"Rel-7","R2","2005-03-15","2006-09-15",1,"RP-050386","RP-060453","Nokia","juho.pirskanen@nokia.com","RP#33 completed","25.815; 25.321; 25.322; 25.331",null,null,null,null,"2005-03-15","2010-07-27"]
[7918,330009,"   Enhanced CELL_FACH State in FDD","RANimp-EnhState",2,"Rel-7","R2","2006-09-25","2007-06-04",1,"RP-070245","RP-070286","Nokia","juho.pirskanen@nokia.com","RP#36 completed","25.308; 25.304; 25.306; 25.321; 25.331; 25.433; 25.435; 25.423; 25.425.",null,null,null,null,"2006-10-06","2010-07-27"]
[7919,340038,"   64QAM for HSDPA (FDD)","RANimp-64QamDownlink",2,"Rel-7","R1","2006-12-15","2007-06-04",1,"RP-070223","RP-070287","Ericsson","Johan.Bergman@ericsson.com","RP#36 completed","25.308; 25.211; 25.212; 25.213; 25.306; 25.331; 25.433; 25.435; 25.423; 25.425; 25.101; 25.104; 25.141",null,null,null,null,"2006-10-06","2010-07-27"]
[7925,25026,"Rel-7 RAN improvements - UE Conformance Testing","-",1,"Rel-7","R5","2006-09-20","2009-09-18",1,"-","-","-","-","Linked to Feature UID_20029 (RANimp) ","-",null,null,null,null,"2006-09-22","2010-07-27"]
[7926,25021,"   Conformance Test Aspects - 3.84 Mcps and 7.68 Mcps TDD Enhanced Uplink","RANimp-UEConTest_EDCHTDH",2,"Rel-7","R5","2006-09-20","2008-09-12",1,"RP-060484","RP-080536","IPWireless","tspeight@ipwireless.com","RP#41 completed","34.108; 34.122; 34.123-1; 34.123-2; 34.123-3",null,null,null,null,"2006-09-21","2010-07-27"]
[7930,25034,"   Conformance Test Aspects – Continuous connectivity for packet data users","RANimp-UEConTest_CPC",2,"Rel-7","R5","2007-03-09","2008-05-30",1,"RP-070023","RP-080282","Nokia","jarkko.hellsten@nokia.com","RP#40 completed","34.108; 34.121-1; 34.121-2; 34.123-1; 34.123-2; 34.123-3",null,null,null,null,"2006-09-21","2010-07-27"]
[7934,20016,"   VHCRTDD: Physical Layer","VHCRTDD-Phys",2,"Rel-7","R1","2004-09-15","2006-03-15",1,"RP-060119","RP-060684","IPwireless","Martin Beale (mbeale@ipwireless.com)","RP#31 completed","25.221; 25.222; 25.223; 25.224.25.225",null,null,null,null,"2004-09-27","2010-07-27"]
[7937,20019,"   VHCRTDD: RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing","VHCRTDD-RF",2,"Rel-7","R4","2004-09-15","2006-06-15",1,"RP-060119","RP-060684","IPwireless","Shin Horng Wong (shwong@ipwireless.com)","RP#32 completed","25.102; 25.105; 25.123; 25.133; 25.142",null,null,null,null,"2004-09-27","2010-07-27"]
[7939,20035,"3.84 Mcps TDD Enhanced Uplink","EDCHTDD",1,"Rel-7","RP","2005-03-15","2006-09-15",1,"RP-050100","RP-060462","IPwireless","nanderson@ipwireless.com","RP#33 completed","-",null,null,null,null,"2005-03-15","2010-07-27"]
[7945,20055,"1.28 Mcps TDD Enhanced Uplink","LCRTDD-EDCH",1,"Rel-7","R1,R2,R3,R4,R5","2006-03-15","2008-09-12",1,"RP-060202","RP-070296","CATT","Haijing Hu","RP#35 completed","-",null,null,null,null,"2006-03-21","2010-07-27"]
[7946,20056,"   1.28 Mcps TDD Enhanced Uplink: Physical Layer","LCRTDD-EDCH-Phys",2,"Rel-7","R1","2006-03-15","2007-03-15",1,"-","RP-070038","CATT","Ke Wang ","RP#35 completed","25.201; 25.221; 25.222; 25.223; 25.224; 25.225",null,null,null,null,"2006-03-21","2010-07-27"]
[7952,50118,"MS Antenna Performance Evaluation Method and Requirements","APEMR",1,"Rel-7","GP","2005-01-28","2007-11-16",1,"GP-050284","-","TeliaSonera","Ulf.Tegth@teliasonera.com","GP#36 completed for R7","25.914; 25.144; 45.005",null,null,null,null,"2007-09-05","2008-05-19"]
[7953,50119,"Lower 700 MHz Inclusion in the GERAN Specifications","GSM710",1,"Rel-7","GP","2005-01-03","2006-06-30",1,"GP-050543","-","UTC","dcotton@mtview.union-tel.com","-","-",null,null,null,null,"2005-02-01","2006-09-19"]
[7957,55094,"      G3 aspects of GSM710","-",3,"Rel-7","G3new","2005-08-31","2006-06-30",1,"-","-","-","-","-",51.01,null,null,null,null,"2005-12-20","2006-07-17"]
[7961,52144,"   Support of Conversational Services in A/Gb mode via the PS domain – RLC Non-Persistent mode","SCSAGB-RLCNP",2,"Rel-7","G2","2006-06-30","2006-11-17",1,"GP-061503","-","Ericsson","gunnar.hedby@ericsson.com","-","43.955; 43.064; 44.060; 45.001; 45.002; 45.003; 45.005; 45.010; 51.010; 51.021",null,null,null,null,"2006-07-05","2008-01-10"]
[7965,50566,"   Changes to core specification","TGSM810-Core",2,"Rel-7","GP","2005-04-08","2005-09-02",1,"GP-050946","-","Huawei","chende@huawei.com","-","45.005; 45.050; 24.008; 45.008; 45.001; 43.022; 43.030; 44.018; 44.060",null,null,null,null,"2005-04-21","2005-09-15"]
[7966,55092,"   Changes to MS testing specification","TGSM810-MStest",2,"Rel-7","G3new","2005-04-08","2007-08-31",1,"GP-050947","-","Huawei","chende@huawei.com","-","51010-1",null,null,null,null,"2005-04-21","2007-09-12"]
[7972,50569,"Mobile Station Receive Diversity (DARP Phase II)","MSRD2",1,"Rel-7","GP","2005-11-11","2007-11-16",1,"GP-061491","-","Nokia","kent.pedersen@nokia.com","GP#36 completed","-",null,null,null,null,"2005-11-21","2008-05-19"]
[7975,50573,"   Test Scenarios for Mobile Station Receive Diversity, DARP Phase II ","MSRD2-TestSc",2,"Rel-7","GP","2005-11-11","2007-02-16",1,"GP-060117","-","Nokia","kent.pedersen@nokia.com","GP#33 completed",45.005000000000003,null,null,null,null,"2005-11-21","2007-03-08"]
[7977,50579,"Downlink Dual Carrier","GDCDL",1,"Rel-7","GP","2006-01-20","2009-09-04",1,"GP-061331","-","Nokia Siemens Networks","leonardo.provvedi@roke.co.uk","GP#35 completed","-",null,null,null,null,"2006-01-24","2009-04-01"]
[7980,53086,"   Downlink Dual Carrier – MS Conformance Test ","GDCDL-MStest",2,"Rel-7","G3new","2006-01-20","2009-09-04",1,"GP-060486","-","Nokia Siemens Networks","leonardo.provvedi@roke.co.uk","GP#43 completed",51.01,null,null,null,null,"2006-01-24","2009-09-07"]
[7984,52146,"   Reduced TTI","LATRED-REDTTI",2,"Rel-7","G2","2006-06-30","2007-08-31",1,"GP-061521","-","Ericsson","Hakan.Persson@Ericsson.com","GP#35 completed","45.001; 45.002; 45.003; 45.005; 45.010; 43.055; 43.064; 44.060; 51.010-1; 51.021",null,null,null,null,"2006-07-05","2008-12-15"]
[7988,51141,"   Layer 1 Support for HUGE","HUGE-Layer1",2,"Rel-7","G1","2006-09-08","2008-02-22",1,"GP-061903","-","Nokia Siemens Networks, Ericsson","eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com","GP#37 completed","45.001; 45.002; 45.003; 45.004; 45.008",null,null,null,null,"2006-09-13","2008-12-15"]
[7992,53087,"   MS Conformance Test for HUGE","HUGE-Mstest",2,"Rel-7","G3new","2006-09-08","2011-05-20",1,"GP-061906","-","Nokia Siemens Networks, Ericsson","eddie.riddington@nokia.com, stefan.g.eriksson@ericsson.com","GP#50 completed",51.01,null,null,null,null,"2006-09-13","2011-05-21"]
[7993,50121,"REduced symbol Duration, Higher Order modulation and Turbo coding (RED HOT) for downlink","REDHOT",1,"Rel-7","GP","2006-11-17","2011-05-20",1,"GP-071080","-","Ericsson, Nokia Siemens Networks, Marvell","stefan.g.eriksson@ericsson.com","GP#38 completed","-",null,null,null,null,"2006-11-20","2008-12-15"]
[7999,25030,"Test - (Small) Technical Enhancements and Improvements for Rel-7","TEI7_Test",1,"Rel-7","R5","2006-06-02","2007-11-28",1,"-","-","-","-","-","-",null,null,null,null,"2010-05-26","2010-05-26"]
[8002,32115,"   Deleted - PS domain aspects to support IMS Emergency sessions","-",2,"Rel-7","S2","2006-06-23","2006-06-23",1,"SP-050604","-","Nokia","curt.c.wong@nokia.com","Approved at SP#29","23.867; 23.abc; 23.060; 23.002; 23.271",null,null,"SP-30",null,"2005-03-22","2005-12-22"]
[8004,32019,"   Deleted - Stage 2","-",2,"Rel-7","S2","2006-01-06","2006-01-06",1,"-","-","-","-","DAB - Not yet required in SA2 as it exists in previous releases","-",null,null,"SP-26",null,"2002-03-25","2004-12-06"]
[8007,701216,"Deleted - Improvements of Radio Interface","-",1,"Rel-7","RP","2004-09-15","2004-09-15",1,"-","-","-","-","Stage 2 description of Interim conclusion","-",70,36,"SP-24",null,"2000-03-31","2004-07-08"]
[8011,31082,"Study on Multimedia Telephony Capabilities for IMS","MITE",1,"Rel-7","S1","2005-07-11","2006-07-31",1,"SP-050387","-","Ericsson","peter.bleckert@ericsson.com","Spin-off Feature UID_7038 (MTSI)",22.972999999999999,null,null,null,null,"2005-04-21","2008-07-01"]
[8015,31075,"Study on Videotelephony teleservice","VidTel",1,"Rel-7","S1","2005-03-01","2006-01-17",1,"SP-050506","-","T-Mobile","michael.kurz@t-mobile.at ","-",22.902999999999999,null,null,null,null,"2005-03-22","2008-06-27"]
[8020,35066,"Study on SOAP/HTTP IRP Solution Sets","OAM7-NIM-XML",1,"Rel-7","S5","2005-09-02","2006-12-07",1,"SP-050610","-","Nortel","Suzèle Lariven (lariven@nortel.com)","SP#34 completed",32.808999999999997,null,null,null,null,"2005-09-16","2010-07-27"]
[8023,7034,"Study on Bandwidth Saving at Nb Interface with IP transport","BSNbIP",1,"Rel-7","C3","2006-03-10","2007-03-09",1,"CP-060438","-","Siemens","Thomas.Belling@siemens.com","Moved to FS at CT32 (in line with slides)",29.814,null,null,null,null,"2006-03-20","2010-07-27"]
[8026,7050,"Study on using M2PA in 3GPP network ","FS-M2PA",1,"Rel-7","C4","2006-03-22","2007-06-08",1,"CP-060698","-","China Mobile","zhaoyuyi@chinamobile.com","-",29.800999999999998,null,null,null,null,"2006-03-22","2008-07-01"]
[8029,330003,"   CT3 aspects of NcSIP","-",2,"Rel-7","C3","2006-05-15","2007-09-14",1,"CP-070034","-","Ericsson","ragnar.huslende@ericsson.com","-",29.802,null,null,null,null,"2006-09-21","2008-07-01"]
[8031,20034,"Study on Performance Evaluation of the UE behaviour in high speed trains with speeds up to 350 kmph","RANFS-HSTrains",1,"Rel-7","R4","2005-03-15","2006-06-15",1,"RP-050146","RP-060412","Vodafone","Mike.vogel@vodafone.com,tim.frost@vodafone.com","RP#32 (Jun 2006) completed. SR in RP-060412","none",null,null,null,null,"2005-03-15","2008-06-23"]
[8035,20052,"Deleted - Study on Performance Improvements in Small Cells using HSDPA/EDCH","SMALLCELLS",1,"Rel-7","R1,R4","2005-12-15","2006-06-15",1,"RP-050782","RP-060263","Cingular","Marc Grant","RP#32 (Jun 2006) stopped at 0% completion","none",null,null,"SP-69",null,"2005-12-15","2008-06-23"]
[8038,330013,"Study on Dynamically reconfiguring a FDD UE receiver to reduce power consumption when desired Quality of Service is met","FSUEPow",1,"Rel-7","R4","2007-06-22","2007-06-22",1,"RP-060641","RP-070534","Nokia","Chris.callender@nokia.com, tiina.s.koskinen@nokia.com","RP#37 (Sep 2007) completed. SR in RP-070534",25.905999999999999,null,null,null,null,"2006-10-06","2008-06-23"]
[8042,31077,"Deleted - Covered by SI - Personal Network (PN) and Personal Area Network (PAN)","PNPAN",1,"Rel-7","S1","2005-12-08","2005-12-08",1,"SP-050386","-","Vodafone","armin.toepfer@vodafone.com","-","-",null,null,"SP-30",null,"2005-04-21","2005-12-22"]
[8047,50095,"   Deleted - GERAN review of the TR","-",2,"Rel-7","GP","2005-06-30","2005-06-30",1,"-","-","-","-","-","-",null,null,"SP-26",null,"2003-07-23","2004-12-06"]
[8050,32098,"   Deleted - Study on enhancement of radio performance for VoIMS","-",2,"Rel-7","S2","2006-07-21","2006-07-21",1,"SP-050351","-","Nortel","Laurence Lautier (lautierl@nortel.com)","WID approved SP#28. SA2#52 stopped",23.806999999999999,null,null,"SP-32",null,"2005-06-22","2006-05-31"]
[8053,34040,"Deleted eCALLIBMS - Study on Transferring of emergency call data – in-band modem solution (moved to Rel-8) ","-",1,"Rel-7","S4","2007-06-22","2007-06-22",1,"SP-060935","-","Airbiquity","lhong@airbiquity.com","SP-38 stopped",26.966999999999999,null,null,"SP-38",null,"2006-12-10","2007-06-22"]
[8056,50552,"Deleted - Study on enhanced support of Video Telephony","VIDGER",1,"Rel-7","GP","2006-06-30","2006-06-30",1,"GP-042221","-","Ericsson","stefan.g.eriksson@ericsson.com","FS CLOSED at G#28 (no input)","-",null,null,"SP-32",null,"2004-10-15","2006-03-09"]
[8058,1216,"Rel-6 Improvements of Radio Interface","-",1,"Rel-6","R2,R4,R5","2000-08-14","2006-12-01",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2004-07-08"]
[8061,24004,"   Base station classification for FDD","RInImp-BSClass-FDD",2,"Rel-6","R4","2000-08-14","2002-12-04",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-16","2004-07-08"]
[8066,25010,"   Conformance Test Aspects – UMTS 1.7/2.1 GHz Band","RInImp-UMTS1721_Test",2,"Rel-6","R5","2006-03-10","2006-12-01",1,"-","-","Motorola","carolyn.taylor@motorola.com","-","TS34.121, TS34.108",null,null,null,null,"2006-03-21","2010-06-16"]
[8069,25001,"      Testing of Improved Minimum Performance for HSDPA","RInImp-HSPerf-10Code_Test",3,"Rel-6","R5","2003-09-19","2006-03-16",1,"-","-","Motorola","carolyn.taylor@motorola.com","-","34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2004-09-27","2010-06-16"]
[8074,1506,"   FS on Radio link performance enhancements","RInImp-Rlperf",2,"Rel-6","R1","2000-08-14","2004-09-14",1,"-","-","Nokia","antti.toskala@nokia.com","Study finished at RP#25",25.899000000000001,null,null,null,null,"2003-10-02","2004-10-13"]
[8077,21004,"   FS on Uplink Enhancements for Dedicated Transport Channels","RInImp-FSUpDTrCh",2,"Rel-6","R1","2002-09-06","2004-03-12",1,"-","-","Nokia","Karri.Ranta-aho@nsn.com","-",25.896000000000001,null,null,null,null,"2003-10-02","2004-07-08"]
[8078,21005,"   FS on Analysis on Higher Chip Rates for UTRA TDD evolutions","RInImp-FSVHCRTDD",2,"Rel-6","R1","2002-09-06","2004-09-14",1,"-","-","IPWireless","mbeale@ipwireless.com","Study finished at RP#25",25.895,null,null,null,null,"2003-10-02","2004-10-13"]
[8083,20003,"FDD Enhanced Uplink","EDCH",1,"Rel-6","R2,R1,R3,R4,R5","2004-03-15","2007-09-14",1,"-","-","Ericsson","Joakim Bergström ","-","-",null,null,null,null,"2004-03-18","2004-07-08"]
[8085,20005,"   FDD Enhanced Uplink - Physical Layer","EDCH-Phys",2,"Rel-6","R1","2004-03-15","2005-03-14",1,"-","-","Nokia","Karri.Ranta-aho@nsn.com","-","25.211, 25.212, 25.213, 25.214, 25.215",null,null,null,null,"2004-03-18","2005-03-25"]
[8088,20008,"   FDD Enhanced Uplink - RF Radio Transmission/ Reception, System Performance Requirements and Conformance Testing","EDCH-RF",2,"Rel-6","R4","2004-03-15","2004-06-24",1,"-","-","Ericsson","thomas.unshelm@ericsson.com","-","25.101, 25.104, 25.133, 25.141",null,null,null,null,"2004-03-18","2006-01-13"]
[8093,21009,"      optimization of channelisation code utilisation for 3.84 Mcps TDD","RANimp-RABSE-CodOptTDD",3,"Rel-6","R1","2004-03-15","2005-03-14",1,"-","-","IPWireless","Nicholas Anderson","WIDS modified in RP#26, RP-040551","-",null,null,null,null,"2004-03-18","2006-01-13"]
[8096,23005,"      Deleted - Improvement of RRM across RNS and RNS/BSS","RANimp-RRM1",3,"Rel-6","R3","2003-12-05","2003-12-05",1,"-","-","Nokia","antti.toskala@nokia.com","abandoned RP-23","-",null,null,"RP-23",null,"2004-10-19","2004-10-21"]
[8101,23015,"      Tilting Antenna - RAN aspects","-",3,"Rel-6","R3","2003-03-14","2004-09-14",1,"-","-","Vodafone","Andreas.Hauser@vodafone.com","Finished at RP#25","25.460, 25.461, 25.462, 25.463",null,null,null,null,"2003-03-27","2004-10-13"]
[8104,32023,"Location Services enhancements 2","LCS2",1,"Rel-6","S2,S5,N4,R2,R4,R5,OMA","2001-01-15","2004-12-16",1,"SP-030127","-","Nokia","Jan Kåll","-","-",null,null,null,null,"2002-06-21","2012-06-02"]
[8106,32051,"      Stage 2 for Improvement on Le interface","-",3,"Rel-6","S2","2002-06-17","2003-09-22",1,"SP-030127","-","Nokia","Jan Kåll","-","23.002,23.271",null,null,null,null,"2003-03-27","2012-05-21"]
[8109,32047,"      Stage 2 for Enhanced support for anonymity and user privacy","-",3,"Rel-6","S2","2002-07-08","2003-06-27",1,"SP-030127","-","Nokia","Jan Kåll","-","23.002,23.271",null,null,null,null,"2003-03-27","2012-05-21"]
[8112,32048,"      Stage 2 for Enhanced inter-GMLC interface","-",3,"Rel-6","S2","2002-06-24","2003-09-05",1,"SP-030127","-","Nokia","Jan Kåll","-","23.002,23.271",null,null,null,null,"2003-03-27","2012-05-21"]
[8115,32049,"      Stage 2 for Location Services support for IMS public identities","-",3,"Rel-6","S2","2003-02-24","2004-01-23",1,"SP-030127","-","Nokia","Jan Kåll","-","23.002,23.271",null,null,null,null,"2003-03-27","2012-05-21"]
[8120,32057,"      Stage 3 for New area event for location service triggering reports - impacts MLP, RLP and PCP","-",3,"Rel-6","OMA","2004-01-01","2004-12-15",1,"SP-040232","-","OMA","OMA-LIAISON@mail.openmobilealliance.org","-","-",null,null,null,null,"2003-07-23","2012-05-21"]
[8123,24012,"      A-GPS minimum performance specification","LCS-UEPos-AGPSPerf",3,"Rel-6","R4,R5","2003-06-06","2004-09-14",1,"-","-","AT&T Wireless","donglin.shen@attws.com","RP#25 completed (FDD)","new 25.171, 34.171 (testing)",null,null,null,null,"2003-07-04","2012-05-21"]
[8128,2026,"   Enhanced HE control of security (including positive authentication reporting)","-",2,"Rel-6","S3","2001-01-03","2003-09-25",1,"SP-000421","-","Vodafone","Peter.Howard@vodafone.com","SP#9 approved WID S3-000490 (Enhanced home control of security by HE)",33.101999999999997,null,null,null,null,"2000-09-22","2011-08-08"]
[8131,33007,"         Rel-6 IP network layer security (NDS/IP)","SEC1-NDS-IP",4,"Rel-6","S3","2002-06-17","2003-09-25",1,"SP-000420","-","-","-","SP#9 approved WID S3-000626 (Access security for IP-based services)",33.21,null,null,null,null,"2002-11-08","2011-08-08"]
[8133,33019,"   Key Management of group keys for Voice Group Call Services","SECGKYV",2,"Rel-6","S3","2003-09-26","2004-11-26",1,"SP-030491","-","Vodafone","benno.tietz@vodafone.com","-","42.068, 43.068, 44.068, 42.069, 43.069, 44.069, 31.102, 24.008, 48.008, 42.009, 43.020, New TSs (55.236, 55.205) MILENAGE algorithms ",null,null,null,null,"2003-10-14","2005-01-13"]
[8136,14014,"   Enhancements to the Cx and Sh interfaces","IMS2-CCR",2,"Rel-6","N4","2003-06-06","2004-08-31",1,"NP-030229","-","-","-","Shared public user identities need to be solved. If email approval CR is accepted. Work 100% done.","-",null,null,null,null,"2003-06-09","2005-03-25"]
[8139,31026,"      Stage 1 - TS on IMS group management","-",3,"Rel-6","S1","2002-03-14","2002-12-09",1,"-","-","Nokia","juha.kalliokulju@nokia.com","-","-",null,null,null,null,"2002-03-21","2003-12-07"]
[8142,11037,"   IMS Conferencing","-",2,"Rel-6","N1","2002-11-04","2004-12-08",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-13","2003-01-13"]
[8147,31034,"      Stage 1 22.340","IMSM-TS",3,"Rel-6","S1","2002-11-11","2002-12-11",1,"SP-020065","-","Nokia","juha.kalliokulju@nokia.com","-",22.34,null,null,null,null,"2003-01-13","2010-09-07"]
[8151,60001,"      SIP/SIMPLE Instant messaging","-",3,"Rel-6","OMA","2004-01-01","2005-12-30",1,"-","-","-","OMA-LIAISON@mail.openmobilealliance.org","Updated according to SP-040232","-",null,null,null,null,"2004-06-08","2005-03-25"]
[8155,11052,"      Procedured associated with IMS-ALG","-",3,"Rel-6","N1","2004-09-06","2005-06-17",1,"-","-","-","-","-","-",null,null,null,null,"2005-04-20","2005-06-02"]
[8158,13004,"      Interworking for 3GPP_SIP and IETF_SIP","-",3,"Rel-6","N3","2000-08-28","2003-06-13",1,"-","-","Siemens","Thomas.Belling@nsn.com","[DAB - 20.08.03] - CN Part of TR Complete @ CN#20","New 29.962",null,null,null,null,"2002-02-28","2003-09-15"]
[8160,11044,"      Interworking for IPv6 to IPv4 (SIP / SDP aspects)","-",3,"Rel-6","N1","2004-05-11","2004-09-08",1,"-","-","-","-","-","-",null,null,null,null,"2004-03-01","2004-09-08"]
[8163,14001,"   Mn interface (IM-MGW to MGCF) enhancements (CN4 Part)","IMS-CCR-Mn",2,"Rel-6","N4","2001-08-07","2004-09-01",1,"-","-","-","-","TISPAN issue is open","-",null,null,null,null,"2001-10-08","2005-03-09"]
[8166,31042,"   IMS Subscription and access scenarios","-",2,"Rel-6","S1","2002-12-16","2003-06-13",1,"-","-","TeliaSonera","FRANK, Robert","-",22.8,null,null,null,null,"2003-03-28","2010-08-31"]
[8169,32027,"   Deleted - Stage 2 of IMS Phase 2","-",2,"Rel-6","S2","2003-09-19","2003-09-19",1,"SP-020544","-","-","-","-","-",null,null,"SP-21",null,"2004-10-19","2004-10-21"]
[8174,35036,"   PoC charging","PoC-CH",2,"Rel-6","S5","2004-09-27","2005-06-09",1,"SP-050032","-","Siemens","Gerald.Goermer@nsn.com","SP#28 06/2005 completed",32.271999999999998,null,null,null,null,"2004-10-29","2006-01-13"]
[8178,32061,"   Stage 2 for commonality","-",2,"Rel-6","S2","2002-09-16","2003-09-19",1,"SP-020543","-","Nokia","balazs.bertenyi@nsn.com","-",23.864000000000001,null,null,null,null,"2003-09-15","2004-07-08"]
[8182,32701,"   TR 23.976 on Push Architecture","-",2,"Rel-6","S2","2002-11-11","2004-02-27",1,"SP-030126","-","Research In Motion","Nick Alfano","-",23.975999999999999,null,null,null,null,"2002-09-26","2004-07-08"]
[8185,31031,"      Definition of service requirements charging","-",3,"Rel-6","S1","2002-11-15","2003-12-19",1,"-","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-",22.14,null,null,null,null,"2003-01-13","2004-03-12"]
[8187,42012,"   OMA dependencies","-",2,"Rel-6","OMA","2003-08-15","2005-04-29",1,"-","-","-","-","-","OMA specs",null,null,null,null,"2002-09-26","2005-03-25"]
[8190,35034,"   MMS charging","MMS6-CH",2,"Rel-6","S5","2003-03-21","2004-09-16",1,"SP-040778","-","-","-","SP#25 09/2004 completed",32.270000000000003,null,null,null,null,"2004-10-29","2006-01-13"]
[8196,2499,"Presence Capability","PRESNC",1,"Rel-6","S1,S2,S3,S4,N1,N3,N4,OMA","2001-03-19","2005-12-07",1,"SP-010064","-","Motorola","Mark Cataldo","merged \"Presence Service Enhancements\" (UID31028, PRES1) to this feature as no answer was provided on why Presence and Presence Encmts had same target completion date","-",null,null,null,null,"2001-03-30","2004-09-08"]
[8198,2502,"   Stage 2 for Presence Capability","-",2,"Rel-6","S2","2001-09-12","2002-09-20",1,"SP-010517","-","Nokia","balazs.bertenyi@nsn.com","-","23.002, 24.229, New 23.141",null,null,null,null,"2001-03-30","2011-08-09"]
[8201,34025,"   Media Codecs and Formats for IMS Messaging and Presence","PRESNC-COFIMP",2,"Rel-6","S4","2003-06-12","2005-12-07",1,"SP-030212","-","Nokia","harri.honko@nokia.com","-","26.141, 26.936",null,null,null,null,"2003-07-04","2006-01-13"]
[8205,50057,"   Feasibility study on A/Gb enhancements","AGbEnFS-FS",2,"Rel-6","G2","2002-08-30","2002-11-08",1,"GP-022565","-","Vodafone","jose-luis.carrizo@vodafone.co.uk","-","None",null,null,null,null,"2002-05-23","2009-11-18"]
[8209,50081,"      Impact on 3GPP architecture and requirement to co-ordinatge with other TSGs (CN, SA)","-",3,"Rel-6","GP","2002-08-30","2002-11-08",1,"-","-","-","-","-","None",null,null,null,null,"2002-09-26","2009-11-18"]
[8212,50063,"Flexible Layer One for GERAN","FLOGER",1,"Rel-6","GP,S3","2000-01-03","2004-06-25",1,"GP-021018","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2003-09-16"]
[8214,50065,"      Technical Report on Realisation of a Flexible Layer One","-",3,"Rel-6","GP","2002-04-19","2004-02-06",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-03-12"]
[8217,51004,"      Channel Coding in 45.003 for Realisation of a Flexible Layer One","-",3,"Rel-6","G1","2002-04-19","2004-04-23",1,"GP-021019","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-03-12"]
[8223,52074,"      Modifications to RRC in 44.118 and 44.018","-",3,"Rel-6","G2","2002-04-19","2004-06-25",1,"GP-021020","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,null,null,"2002-05-23","2004-07-08"]
[8225,52076,"      Ciphering in 44.060, 44.160, 44.018, 44.118","-",3,"Rel-6","S3,G2","2002-04-19","2003-08-29",1,"GP-021021","-","Nokia","benoist.sebire@nokia.com","-","44.060, 44.160, 44.018, 44.118",null,null,null,null,"2002-05-23","2003-09-16"]
[8228,55079,"   Deleted - GERAN BTS Conformance test for the Flexible Layer One - DELETE","FLOGER-BTSconf",2,"Rel-6","G3new","2004-02-06","2004-02-06",1,"GP-021023","-","Nokia","benoist.sebire@nokia.com","-","-",null,null,"GP-27",null,"2002-05-23","2005-03-09"]
[8232,2545,"   Stage 1 for Multimedia Broadcast and Multicast Service","-",2,"Rel-6","S1","2001-05-11","2002-04-01",1,"-","-","-","-","-","22.146, 22.101",null,null,null,null,"2001-03-30","2012-07-26"]
[8236,11030,"   Support of the MBMS in CN protocols","-",2,"Rel-6","N1","2002-06-18","2004-12-08",1,"NP-040493","-","-","-","-","-",null,null,null,null,"2002-06-21","2012-07-26"]
[8237,13015,"   Gmb interface for MBMS (CN3 part)","-",2,"Rel-6","N3","2003-08-29","2004-12-08",1,"-","-","-","-","-",29.061,null,null,null,null,"2003-10-13","2012-07-26"]
[8241,31044,"      Stage 1 for MBMS User Services","-",3,"Rel-6","S1","2003-05-13","2004-04-01",1,"-","-","-","-","-",22.245999999999999,null,null,null,null,"2001-03-30","2012-07-26"]
[8244,20022,"      Introduction of MBMS in RAN (physical & upper layers, access network interfaces)","-",3,"Rel-6","R2","2002-01-01","2004-12-14",1,"-","-","Nokia","juho.pirskanen@nokia.com","-","25.346, 25.304, 25.321, 25.322, 25.323",null,null,null,null,"2004-09-27","2012-07-26"]
[8250,25011,"      Conformance Test Aspects – MBMS","MBMS_Test",3,"Rel-6","R5,T1","2006-03-10","2007-09-14",1,"-","-","Qualcomm","Shubhang Vora (svora@qualcomm.com)","-","34.108, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-03-21","2012-07-26"]
[{"$f":"A8252+1","v":8252},50085,"   Support of MBMS in GERAN","MBMS-GERAN",2,"Rel-6","GP,G2,G3new","2001-08-30","2005-01-28",1,"GP-022566","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[8255,50098,"      Simultaneous support of MBMS services","-",3,"Rel-6","GP","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2012-07-26"]
[8259,50088,"      MBMS channel allocations procedures to multiple MSs","-",3,"Rel-6","GP","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[8263,50092,"      MBMS Security aspects","-",3,"Rel-6","GP","2002-08-30","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-09-26","2012-07-26"]
[8264,53081,"      MBMS-GERAN - MS conformance tests","-",3,"Rel-6","G3new","2002-01-25","2005-01-28",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2012-07-26"]
[8268,32999,"   TR on Architectural impacts","-",2,"Rel-6","S2","2003-05-12","2004-03-02",1,"-","-","-","-","-",23.876999999999999,null,null,null,null,"2001-11-29","2004-07-08"]
[8271,11021,"   Deleted - SES codec negotiation at Session Description Protocol (SDP)","-",2,"Rel-6","N1","2003-06-04","2003-06-04",1,"-","-","-","-","Abandoned NP-23","-",null,null,"NP-23",null,"2004-10-20","2004-10-21"]
[8277,33009,"   Security aspects of GUP","-",2,"Rel-6","S3","2002-07-16","2003-09-18",1,"SP-030109","-","Lucent","Bradley Owen (bvowen@lucent.com)","SP#19 approved WID","33.102, 33.203, 33.210",null,null,null,null,"2002-11-08","2011-08-08"]
[8279,31011,"   Requirements for Digital Rights Management","-",2,"Rel-6","S1","2001-10-08","2002-06-13",1,"-","-","Openwave","nicholas.wood@openwave.com","-","-",null,null,null,null,"2001-10-11","2003-07-04"]
[8282,33001,"   Security for Digital Rights Management","-",2,"Rel-6","OMA","2002-06-17","2003-03-03",1,"-","-","-","-","SA3 acknowledge role in WI at SA3#20. Active contribution S3#24, S3#25. S3 WID approved SP#17","-",null,null,null,null,"2001-10-11","2005-03-25"]
[8287,32018,"   Architecture Definition for scenarii 2 and 3","-",2,"Rel-6","S2","2002-03-25","2004-05-31",1,"SP-020542","-","-","-","-",23.234000000000002,null,null,null,null,"2002-03-25","2004-07-08"]
[8290,13019,"   Stage 3 - CN3 aspects (Wi Interface for Scenario 3)","-",2,"Rel-6","N3","2003-05-23","2004-09-30",1,"-","-","-","-","-",29.161000000000001,null,null,null,null,"2004-06-08","2005-03-09"]
[8291,11042,"   Stage 3 for scenario 2","-",2,"Rel-6","N1","2003-05-23","2004-09-08",1,"NP-030490","-","-","-","-","-",null,null,null,null,"2003-06-09","2005-03-09"]
[8295,31015,"Priority Service","PRIOR1",1,"Rel-6","S1","2002-05-30","2003-09-26",1,"SP-010523","-","Telcordia","James Garrahan (jgarraha@telcordia.com)","-","-",null,null,null,null,"2002-02-27","2010-08-31"]
[8298,31043,"   Priority service implementation guide","-",2,"Rel-6","S1","2003-03-28","2003-09-26",1,"SP-010523","-","Telcordia","James Garrahan (jgarraha@telcordia.com)","-",22.952000000000002,null,null,null,null,"2003-07-04","2010-08-31"]
[8304,22004,"   Enhancement of the support of network sharing in the UTRAN","NTShar-UTRANEnh",2,"Rel-6","R2","2003-09-19","2003-09-19",1,"-","-","TeliaSonera","Anders.Dahlen@TeliaSonera.com","-","25.401, 25.413, 25.331, 25.304",null,null,null,null,"2003-10-02","2005-01-13"]
[8306,32016,"QoS Improvements","QoS1",1,"Rel-6","S2,N3","2002-07-15","2004-12-08",1,"SP-010719","-","Nokia","-","-","23.107, 23.207, 23.221",null,null,null,null,"2002-01-24","2002-01-24"]
[8309,13016,"   Gq interface specification for Dynamic Policy control enhancements – Stage 3","-",2,"Rel-6","N3","2003-08-29","2004-12-08",1,"NP-030198","-","Nokia","Anna.Sillanpaai@nokia.com","[DAB - 25.05.04] - Delayed to Sept - possibly Dec 2004","29.207, 29.208, 29.209",null,null,null,null,"2003-10-13","2005-03-09"]
[8314,11049,"   Stage 3 Ua & Ub interfaces","-",2,"Rel-6","N1","2003-11-03","2004-12-08",1,"-","-","Nokia","-","-",24.109000000000002,null,null,null,null,"2004-03-01","2009-11-10"]
[8317,31040,"   Scope of the Open Service Access Release 6","-",2,"Rel-6","S1","2003-03-28","2003-06-27",1,"SP-030038","-","-","-","-","-",null,null,null,null,"2003-03-28","2004-03-12"]
[8318,15038,"   OSA Stage 2","-",2,"Rel-6","N5","2004-08-13","2005-03-10",1,"-","-","-","-","Inherited by CN5 from SA2 at TSG#25 Sep 2004. SA2's 23.127 (OSA/VHE Stage 2) replaced from Rel-6 onwards by a new CN5 TS 23.198 (Stage 2 OSA-only).","23.198 OSA Stage 2-ONLY replaces 23.127 (OSA/VHE) from Rel-6 onwards",null,null,null,null,"2004-09-03","2005-03-25"]
[8322,15032,"   OSA interfaces at different levels of abstractions (Parlay X, Web services)","-",2,"Rel-6","N5","2003-07-14","2004-09-10",1,"-","-","-","-","-",29.199000000000002,null,null,null,null,"2003-03-27","2005-01-13"]
[8327,50401,"Addition of frequency bands to GSM (TAPS)","TAPS",1,"Rel-6","GP","2002-06-28","2005-01-28",1,"GP-022072","-","Nokia","Torben Themsen","-","-",null,null,null,null,"2002-07-31","2005-03-09"]
[8330,54102,"   Deleted - Addition of frequency bands to GSM – Changes for conformance tests","TAPS-Conf",2,"Rel-6","G4","2002-06-28","2005-01-28",1,"GP-022074","-","Nokia","Torben Themsen","-","-",null,null,"GP-23",null,"2002-07-31","2005-03-09"]
[8333,51131,"   Identification of requirements for streaming","-",2,"Rel-6","G1","2003-06-27","2003-08-29",1,"GP-022564","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2002-09-26","2003-09-16"]
[8336,51134,"      Performance of NACC","-",3,"Rel-6","G1","2000-01-03","2003-08-29",1,"-","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2003-02-13","2003-09-16"]
[8341,52134,"      Inter-system NACC","-",3,"Rel-6","G2","2003-06-27","2003-11-21",1,"-","-","Vodafone","José Luis Carrizo Martínez","-","-",null,null,null,null,"2003-02-13","2003-09-16"]
[8344,54131,"   Deleted - MS conformance testing for Seamless support of streaming services in A/Gb mode","-",2,"Rel-6","G3new","2003-12-19","2004-01-30",1,"GP-023424","-","Vodafone","José Luis Carrizo Martínez","Marked as stopped 10/2009","-",null,null,"GP-27",null,"2002-09-26","2009-10-13"]
[8345,54132,"      Deleted - MS conformance tests for Seamless support of streaming services in A/Gb mode","-",3,"Rel-6","G4,G5","2003-12-19","2004-01-30",1,"GP-023424","-","Vodafone","José Luis Carrizo Martínez","Marked as stopped 10/2009","-",null,null,"GP-27",null,"2003-02-13","2009-10-13"]
[8349,35010,"Rel-6 Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM6",1,"Rel-6","S5","2002-09-12","2005-03-11",1,"SP-040766","-","-","-","SP#26: Updated WID SP-040766 was SP-020445. Completion delayed 12/04->03/05 due to OAM-Trace in CN1/4.","-",null,null,null,null,"2002-11-08","2005-01-13"]
[8354,35022,"      Subscriber and UE trace management","-",3,"Rel-6","S5","2002-09-20","2004-12-16",1,"-","-","Nokia","kari.t.ronka@nokia.com","SP#26 12/2004 completed","32.421, 32.422, 32.423, 52.008",null,null,null,null,"2003-10-03","2006-01-13"]
[8357,35016,"Rel-6 Charging Management","CH",1,"Rel-6","S5,S2,N3","2002-11-21","2005-06-09",1,"SP-040773","-","T-Mobile","karl-heinz.nenner@t-mobile.de","SP#28 Target 09/2005 for WLAN Charging 32.252","-",null,null,null,null,"2003-01-13","2006-01-13"]
[8360,35025,"   CDR parameter description","-",2,"Rel-6","S5","2003-03-21","2005-06-09",1,"-","-","-","-","SP#28 06/2005 completed",32.298000000000002,null,null,null,null,"2004-10-29","2006-01-13"]
[8363,35028,"   OCS: Applications and interfaces","-",2,"Rel-6","S5","2003-03-21","2004-12-16",1,"-","-","-","-","SP#26 12/2004 completed",32.295999999999999,null,null,null,null,"2004-10-29","2006-01-13"]
[8368,35019,"   Charging Management for the Service domain","-",2,"Rel-6","S5","2003-03-21","2005-06-09",1,"SP-040778","-","Siemens","Gerald.Goermer@nsn.com","SP#26: Updated WID SP-040778 was SP-030050. Target completion 06/2005. Consisting of MMS-CH, LCS-CH, WLAN-CH, POC-CH, MBMS-CH","32.252, 32.270, 32.271, 32.272",null,null,null,null,"2003-01-13","2006-01-13"]
[8372,13020,"      Gx interface for flow based charging","-",3,"Rel-6","N3","2004-02-02","2004-12-08",1,"NP-040245","-","Nokia","juha.a.rasanen@nokia.com","-",29.21,null,null,null,null,"2004-05-20","2005-03-09"]
[8373,13021,"      Rx interface for flow based charging","-",3,"Rel-6","N3","2004-02-02","2005-03-11",1,"NP-040339","-","Nortel","Javier Gonzalez Gallego","-",29.209,null,null,null,null,"2004-05-20","2005-03-25"]
[8376,43001,"      Rel-6 Java API Test specification","-",3,"Rel-6","T3","2002-03-20","2002-06-10",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","-","-",null,null,null,null,"2002-05-30","2010-02-09"]
[8381,502031,"      C SIM API","-",3,"Rel-6","T3","2000-09-25","2002-09-27",1,"TP-000155","-","Aspects Software","Neil Livingston","-","31.101, 31.102, 31.103, 31.111, 31.113, new 31.115, 31.116",null,null,null,null,"2000-09-27","2010-02-09"]
[8384,43009,"      USIM application toolkit Conformance Test Specification for Mobile Equipments ","-",3,"Rel-6","T3","2003-12-05","2005-03-04",1,"TP-030259","-","Gemplus","Eric.laffont@gemplus.com","-",31.123999999999999,null,null,null,null,"2004-12-06","2005-06-02"]
[8387,34024,"   Stage 3 for Packet Switched Streaming Services Rel-6","PSSrel6-Stage3",2,"Rel-6","S4","2002-12-13","2005-12-07",1,"SP-020685","-","Ericsson","olle.franceschi@ericsson.com","TR tbc by Sept. 05","26.233, 26.234, 26.244, 26.245, 26.246, 26.401, 26.402, 26.403, 26.404, 26.405, 26.406, 26.410, 26.411, 26.412, 26.273, 26.290, 26.304, 26.412, 26.274, 26.936",null,null,null,null,"2003-03-27","2009-11-13"]
[8390,34028,"3G-324M Improvements","3G-324MI",1,"Rel-6","S4","2004-03-16","2004-12-16",1,"SP-040067","-","Ericsson","bo.burman@ericsson.com","-","26.111, 26.911",null,null,null,null,"2004-03-02","2004-12-06"]
[8395,50600,"Multiple TBF in A/Gb mode","MULTBF",1,"Rel-6","GP,G2","2002-04-05","2005-01-28",1,"GP-021263","-","Ericsson","gunnar.mildh@era.ericsson.se","GP#17 Nov 2003 Moved from Rel-5 UID_50058 MULTBF (Only Multiple TBF Concept paper produced in Rel-5)","-",null,null,null,null,"2003-07-31","2006-01-13"]
[8399,50604,"      Multiple TBF Stage 3 (44.060) CRs","-",3,"Rel-6","GP,G2","2002-04-05","2003-08-29",1,"-","-","-","-","-","-",null,null,null,null,"2003-07-31","2004-12-06"]
[8400,50605,"   Deleted - Multiple TBF in A/Gb mode – MS testing","MULTBF-Testing",2,"Rel-6","G3new","2005-01-28","2005-01-28",1,"GP-022098","-","Ericsson","gunnar.mildh@era.ericsson.se","-","-",null,null,"GP-27",null,"2003-07-31","2005-03-09"]
[8403,50444,"Addition of U-TDOA in the CS domain ","UTDOACS",1,"Rel-6","GP","2003-11-21","2004-04-23",1,"GP-032773","-","TruePosition","Bob Gross, Rhys Robinson (rlgross@trueposition.com)","Completed, except for potential LMU performance specs","-",null,null,null,null,"2003-12-01","2004-03-12"]
[8408,50104,"      Performance requirements in 45.005 for DARP for GMSK modulated voice services","DARP-GMSK-Perf",3,"Rel-6","GP","2004-02-06","2004-11-12",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2004-12-06"]
[8411,50107,"      Performance requirements in 45.005 for DARP for GPRS and EGPRS MCS1-MCS4","DARP-GPRSE-Perf",3,"Rel-6","GP","2004-02-06","2004-11-12",1,"-","-","-","-","-","-",null,null,null,null,"2003-12-01","2004-12-06"]
[8413,50115,"   DARP Capability signalling","DARP-CAPSIG",2,"Rel-6","GP","2003-11-21","2004-11-12",1,"GP-041970","-","Nokia","tommy.bysted@nokia.com","-","-",null,null,null,null,"2003-12-01","2004-12-06"]
[8419,50113,"   Deleted - MS Conformance testing - Reduction of PS service interruption in DTM","PSintDTM-ConfMS",2,"Rel-6","G3new","2004-06-25","2005-06-24",1,"-","-","-","-","-","-",null,null,"GP-25",null,"2003-12-01","2008-12-12"]
[8422,31046,"Circuit Switched Video and Voice Service Improvements","CS_VSS",1,"Rel-6","S2,N1","2004-01-12","2005-09-02",1,"SP-040331","-","Vodafone","John Watson","-","-",null,null,null,null,"2003-03-14","2004-07-08"]
[8426,11053,"   Switching between voice and video call - Redial solution","-",2,"Rel-6","N1","2005-01-03","2005-06-17",1,"SP-040331","-","Vodafone","-","-","23.009, 24.008",null,null,null,null,"2005-04-20","2005-06-02"]
[8427,52137,"   Deleted - CS_VSS - GERAN2 Part","-",2,"Rel-6","G2","2005-09-02","2005-09-02",1,"SP-040331","-","Vodafone","-","-","-",null,null,"GP-26",null,"2004-01-28","2005-04-21"]
[8430,50553,"Generic Access to A/Gb Interface (GAAI)","GAAI",1,"Rel-6","GP","2004-06-25","2006-01-20",1,"GP-042247","-","Motorola","-","-","-",null,null,null,null,"2004-10-15","2006-01-13"]
[8435,50559,"Support of PS Handover for GERAN A/Gb mode","SPSHAGB",1,"Rel-6","GP,G2","2003-11-03","2005-08-24",1,"GP-051160","-","Ericsson","gunnar.hedby@ericsson.com","Replaces SCSAGB- Originally Started Nov 2003 as GP-030443","-",null,null,null,null,"2005-04-20","2006-01-13"]
[8438,50562,"   Definition of radio resource management functionality for Support of PS Handover for GERAN A/Gb mode","SPSHAGB-RRM",2,"Rel-6","GP,G2","2003-11-03","2005-08-24",1,"GP-051163","-","Ericsson","gunnar.hedby@ericsson.com","Replaces SCSAGB-RRM","-",null,null,null,null,"2005-04-20","2006-01-13"]
[8440,33021,"Study on Security for early IMS","SEC-IMS",1,"Rel-6","S3","2004-10-01","2005-03-28",1,"SP-040691","-","Vodafone","Peter.Howard@vodafone.com","SP#24 approved WID. SP#46 withdrawn TR 33.978 from Rel-8 onwards",33.978000000000002,null,null,null,null,"2003-07-25","2011-08-09"]
[8446,50501,"   Deleted - Creation of a TR","SCSAGB-TR",2,"Rel-6","GP","2003-11-21","2003-11-21",1,"GP-030444","-","Ericsson","David Bladsjö (david.bladsjo@ericsson.com)","-","-",null,null,"GP-17",null,"2003-02-13","2010-03-02"]
[8449,50504,"   Deleted SCSAGB-RRM - Definition of radio resource management functionality","-",2,"Rel-6","GP","2003-11-21","2003-11-21",1,"GP-030447","-","Ericsson","David Bladsjö (david.bladsjo@ericsson.com)","Not started","-",null,null,"GP-17",null,"2003-02-13","2010-03-02"]
[8453,0,"--- RELEASE 5 ---","-",1,"Rel-5","NP,GP,RP,SP,TP","2000-01-03","2001-03-29",1,"-","-","-","-","-","-",null,null,null,null,"2008-07-11","2010-02-09"]
[8454,625,"IP transport in the UTRAN","ETRAN-IPtrans",1,"Rel-5","R3","2000-07-17","2002-03-29",1,"-","-","Alcatel","Nicolas Drevon","-","-",null,null,null,null,"2000-03-31","2001-12-12"]
[8458,2478,"   Layer 2 and 3 aspects","HSDPA-L23",2,"Rel-5","R2","2001-04-05","2002-03-29",1,"-","-","Motorola","Ravi Kuchibhotla","-","-",null,null,null,null,"2001-03-20","2002-02-28"]
[8462,25012,"   Conformance Testing of HCR TDD HSDPA","HSDPA_HCRTDD_Test",2,"Rel-5","R5","2006-03-10","2007-03-09",1,"-","-","IPWireless","drichards@ipwireless.com","-","34.108, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2006-03-21","2010-06-16"]
[8465,1477,"      TDD Base station classification","RInImp-BSClass-TDD",3,"Rel-5","R4","2000-08-14","2002-03-08",1,"-","-","Nokia","antti.toskala@nokia.com","-","-",null,null,null,null,"2000-07-26","2002-06-21"]
[8467,2469,"   Enhancement on the DSCH hard split mode","RInImp-DSCHhsp",2,"Rel-5","R1","2001-03-16","2002-03-29",1,"-","-","Samsung","Jaeyoel KIM","-","-",null,null,null,null,"2001-03-20","2002-03-25"]
[8473,1839,"   Deleted - Conformance Test Spec. improvements in Radio Interface","-",2,"Rel-5","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-09-14","2001-10-11"]
[8476,500009,"Rel-5 RAN improvements","-",1,"Rel-5","RP","2001-03-16","2007-03-09",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2002-06-21"]
[8480,23002,"      FS Introduction of direct transport bearers between SRNC and Node-B","RAN-imp-RRMopt-DTB",3,"Rel-5","R3","2001-06-15","2002-06-04",1,"-","-","Ericsson","Risto Sepponen","FS was closed and introduction of WI not agreed at RAN #16 ","-",null,null,null,null,"2001-09-19","2002-11-08"]
[8481,2488,"   RL Timing Adjustment","RANimp-RLTA",2,"Rel-5","R3","2001-03-16","2002-03-29",1,"-","-","Ericsson","Elena Voltolina","-","-",null,null,null,null,"2001-03-20","2002-03-01"]
[8485,2491,"   Re-arrangements of Iub transport bearers","RANimp-TTPS",2,"Rel-5","R3","2001-03-16","2002-03-29",1,"-","-","Nokia","antti.toskala@nokia.com","-","-",null,null,null,null,"2001-03-20","2002-03-01"]
[8489,21002,"   Support of Site Selection Diversity Transmission in UTRAN","RANimp-SSDT",2,"Rel-5","R1","2001-12-14","2002-06-04",1,"-","-","NEC","-","RP-020356","-",null,null,null,null,"2002-02-28","2002-06-21"]
[8492,2222,"      Deleted - Testing Radio access bearer support enhancements","-",3,"Rel-5","T1","2002-01-01","2002-09-02",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2001-12-10"]
[8494,23004,"UTRAN Sharing in Connected Mode","NETSHARE",1,"Rel-5","R3","2001-12-03","2002-09-03",1,"-","-","Ericsson ","Martin Israelsson","Formerly 'Shared Network support in connected mode', renamed at RAN #16.","-",null,null,null,null,"2002-03-21","2002-11-08"]
[8500,2233,"      SIP Call Control protocol for the IMS","-",3,"Rel-5","N1","2000-10-02","2002-03-22",1,"NP-010643","-","Lucent","Keith Drage (drage@alcatel-lucent.com)","TSGN_10 approved the change:CN1 - SA2 SIP joint meeting spotted one more place for improvement: work tasks with ID 1998 and 1278 are actually subtasks under of single CN1 WT. One WI has been approved for the CN1 WT with title \"SIP Call Control protocol","24.228, 24.229, 23.218",null,null,null,null,"2000-12-11","2002-01-24"]
[8503,2255,"         IMS Session Handling; stage 2","-",4,"Rel-5","N1","2000-10-02","2002-03-22",1,"-","-","-","-",23.218,23.218,null,null,null,null,"2001-02-08","2002-02-28"]
[8505,10004,"      Main IETF dependencies","-",3,"Rel-5","NP","2000-01-03","2002-06-14",1,"-","-","Lucent","-","-","-",null,null,null,null,"2002-01-25","2003-03-28"]
[{"$f":"A8508+1","v":8508},2522,"         IETF: RFC 3312 (Without COMET)(Integration of resource management and SIP)","-",4,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-05-06","2003-03-14"]
[8512,11001,"         IETF: RFC editor Queue (refer method)","-",4,"Rel-5","N1","2000-11-24","2002-06-07",1,"-","-","Lucent","-","-","-",null,null,null,null,"2001-10-08","2003-03-14"]
[8516,11022,"         IETF: RFC 3311 (The Update method)","-",4,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","Lucent","-","-","-",null,null,null,null,"2002-06-21","2003-03-14"]
[8519,1290,"         Addressing","-",4,"Rel-5","S2","2000-10-09","2002-03-22",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2000-04-01"]
[8521,1292,"            Impact on HSS ","-",5,"Rel-5","N4","2000-11-15","2002-03-22",1,"-","-","-","-","Covered by 29.228 & 29228","-",null,null,null,null,"2000-04-19","2002-05-30"]
[8527,2574,"   Security Aspects of Requirement for Network Configuration Independence","SEC1-NCI",2,"Rel-5","S3","2001-07-02","2001-12-28",1,"SP-010324","-","AT&T Wireless","hugh.shieh@attws.com","Consider security aspects in SA2 TS 23.228 clause 4.4 & annex C",33.203000000000003,null,null,null,null,"2001-06-09","2011-08-08"]
[8530,2036,"   Multimedia codecs and protocols for conversational PS services","IMS-CODEC",2,"Rel-5","S4","2000-07-26","2002-09-27",1,"SP-000398","-","Toshiba, Nokia","B. Aronson (Toshiba), pasi.s.ojala@nokia.com","-","26.235, 26.236",null,null,null,null,"2000-09-27","2003-03-27"]
[8532,34020,"      Transport protocols","-",3,"Rel-5","S4","2002-03-12","2002-03-12",1,"-","-","Nokia","P. Ojala","-",26.236000000000001,null,null,null,null,"2002-03-25","2002-03-25"]
[8535,11026,"      IETF: RFC 3329 (Security mechanism agreement for SIP connections)","-",3,"Rel-5","N1","2000-11-24","2002-05-13",1,"-","-","-","-","-","-",null,null,null,null,"2002-06-21","2003-03-14"]
[8539,10001,"   Stage 3 description of IMS interfaces","-",2,"Rel-5","NP","2001-03-14","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-08","2002-01-24"]
[8543,11018,"      Mr interface (CSCF to MRF)","-",3,"Rel-5","N1","2001-03-14","2002-03-29",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-08","2002-02-28"]
[8548,14998,"      Si interface (HSS to IM-SSF)","-",3,"Rel-5","N4","2002-01-16","2002-08-30",1,"-","-","-","-","SA16: Part of Rel5 only if completed in September 02. Marked as closed 12/2008 (was marked 72% complete)","-",null,null,null,null,"2002-03-25","2002-05-30"]
[8551,11028,"      Mj interface (BGCF to MGCF)","-",3,"Rel-5","N1","2001-03-14","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-11","2003-03-14"]
[8554,12000,"   CAMEL control of IMS services","IMS-CAMEL",2,"Rel-5","N2","2001-04-16","2002-09-06",1,"NP-020305","-","Lucent","Angelica Remoquillo","-","-",null,null,null,null,"2000-04-19","2002-06-21"]
[8557,12003,"      Stage2 work 'Si interface'","-",3,"Rel-5","N2","2002-01-07","2002-09-06",1,"-","-","-","-","DAB 12.12.01 split into cn4 and cn2 parts","-",null,null,null,null,"2002-01-24","2003-01-13"]
[8559,14004,"      Deleted - SDM issues for CAMEL control of IMS","-",3,"Rel-5","N4","2002-02-14","2002-06-07",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"NP-17",null,"2001-10-08","2008-12-12"]
[8562,32006,"      Charging Implications of IMS architecture","-",3,"Rel-5","S2","2001-08-06","2001-11-16",1,"SP-010519","-","-","-","-","-",null,null,null,null,"2001-10-08","2002-02-28"]
[8566,11011,"      IETF: draft-ietf-aaa-diameter - should be CN4","-",3,"Rel-5","NP","2000-11-24","2002-06-07",1,"-","-","-","-","Marked as closed 12/2008 (was marked 90% complete)","-",null,null,null,null,"2001-10-08","2008-12-12"]
[8570,41005,"   Testing of support for IMS - TTCN","-",2,"Rel-5","T1","2002-09-18","2004-03-03",1,"TP-030052","-","Anritsu","dan.fox@eu.anritsu.com","Marked as stopped 12/2008","34.108, 34.123",null,null,null,null,"2002-09-26","2008-12-12"]
[8575,34003,"   Stage 2 (version Rel-5 of TS 26.234)","-",2,"Rel-5","S4","2002-01-03","2002-03-14",1,"SP-010392","-","-","-","2nd resp SA2",26.234000000000002,null,null,null,null,"2001-06-28","2002-03-25"]
[8578,32010,"   General Stage 2 for Rel-5","-",2,"Rel-5","S2","2001-09-11","2002-06-07",1,"-","-","-","-","Marked as closed 12/2008 (was marked 47% complete)","-",null,null,null,null,"2000-11-21","2008-12-12"]
[8581,15002,"      Stages 2 and 3 for Multimedia Call Control","-",3,"Rel-5","N5","2001-09-11","2002-06-07",1,"-","-","-","-","-","29.198-04",null,null,null,null,"2002-02-28","2002-06-21"]
[8584,15007,"   Call Control Service Mapping; Multiparty Call Control SIP - Stage 3","-",2,"Rel-5","N5","2001-09-11","2002-06-07",1,"-","-","-","-","-","29.998-04-4",null,null,null,null,"2002-02-28","2002-06-21"]
[8586,1419,"   OSA Security","OSA1-SEC",2,"Rel-5","S3","2000-07-11","2002-12-20",1,"SP-000302","-","Ericsson","colin.blanchard@bt.com","SP#8 approved WID",33.101999999999997,null,null,null,null,"2000-04-19","2011-08-08"]
[8589,1422,"      security related SCF(s) definition","-",3,"Rel-5","N5","2001-09-21","2002-06-07",1,"NP-010692","-","Ericsson","Ard.Jan.Moerdijk@eln.ericsson.se","-","29.198, 29.998",null,null,null,null,"2000-04-19","2002-06-21"]
[8594,1529,"      Stages 2 and 3 for Interactions OSA - e-commerce","-",3,"Rel-5","N5","2001-09-21","2002-06-07",1,"NP-010692","-","Ericsson","Ard.Jan.Moerdijk@eln.ericsson.se","-","29.198, 29.998",null,null,null,null,"2000-07-28","2002-06-21"]
[8597,1786,"   LCS - OSA interfaces","OSA1-LCSI",2,"Rel-5","S1","2000-09-11","2002-06-07",1,"-","-","Siemens","joerg.swetina@neclab.eu","az: CN#13 - changed to Rel5","-",null,null,null,null,"2000-04-19","2001-10-08"]
[8602,1433,"   Retrieval of Terminal capabilities","OSA2-TC",2,"Rel-5","S2","2000-07-11","2002-12-13",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2003-07-25"]
[8605,2122,"      Provisioning of the terminal capabilities","-",3,"Rel-5","T2","2001-04-02","2002-12-13",1,"-","-","-","-","According to T2 SWG1 M. Cataldo this is automatically supported by the MExE support of UAProf therefore 100% complete",23.056999999999999,null,null,null,null,"2000-11-22","2003-07-25"]
[8608,2012,"   Call Party Handling","CAMEL4-CPH",2,"Rel-5","N2","2000-07-10","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-15","2002-05-30"]
[8611,2015,"   Inclusion of flexible tone injection ","CAMEL4-IFTI",2,"Rel-5","N2","2000-07-17","2002-03-08",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2002-02-28"]
[8613,2460,"   Notification of GPRS mobility management to CSE","CAMEL4-NMM",2,"Rel-5","N2","2001-03-02","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-13","2002-05-30"]
[8616,2515,"   Location information during an ongoing call (Handover DP)","CAMEL4-HODP",2,"Rel-5","N2","2001-05-14","2002-06-07",1,"-","-","-","-","-","-",null,null,null,null,"2001-05-29","2002-05-30"]
[8621,2466,"   MExE Rel-5 Improvements and Investigations","MEXE5-ENHANC",2,"Rel-5","T2","2001-03-26","2002-03-08",1,"TP-010071","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2002-03-21"]
[8624,31005,"      Stage 1 for Wideband Telephony Service - AMR","-",3,"Rel-5","S1","2001-10-01","2002-03-22",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-05","2002-03-01"]
[8629,1656,"      N1 Aspects for Wideband Telephony Service - AMR","-",3,"Rel-5","N1","2001-09-21","2001-12-21",1,"-","-","-","-","Some of N1 tasks: Indication of supported codecs by the MS, Bearer cap negociation, codec indication to MS","-",null,null,null,null,"2000-08-08","2002-09-26"]
[8632,1627,"         Codec qualification","-",4,"Rel-5","S4","2000-02-02","2000-05-31",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-08","2002-02-28"]
[8634,891,"         Codec selection","-",4,"Rel-5","S4","2000-10-23","2000-10-27",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-05","2002-02-28"]
[8637,34008,"         AMR-WB and narrrowband interworking","AMRWB-IWG",4,"Rel-5","S4","2001-09-27","2002-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-09","2002-02-28"]
[8640,34011,"         Deleted - WB Conferencing and WB Voice Group calls","-",4,"Rel-5","S1","2000-01-03","2000-01-03",1,"-","-","-","-","-","-",null,null,"SP-07",null,"2001-10-09","2003-07-25"]
[8643,1628,"            Definition for Terminal Acoustic Characteristics","-",5,"Rel-5","S4","2000-01-01","2000-01-31",1,"-","-","-","-","-",26.131,null,null,null,null,"2000-08-08","2002-02-28"]
[8648,2266,"      Signalling for the A interface","-",3,"Rel-5","GP","2000-01-03","2001-06-29",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8651,50000,"      Link Adaptation in 45.009","-",3,"Rel-5","GP","2001-03-26","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-10-09","2002-07-31"]
[8656,2573,"   Terminal local model enhancements","TLM5",2,"Rel-5","T2","2001-05-14","2002-03-20",1,"TP-010224","-","-","-","-",23.227,null,null,null,null,"2000-09-14","2003-03-27"]
[8659,2474,"      UE positioning enhancements for 1.28 Mcps TDD","LCS-128Pos",3,"Rel-5","R2","2001-04-09","2002-03-29",1,"RP-010215","-","CATT","Xiaohua Mei","-","25.123, 25.224, 25.225, 25.302, 25.303, 25.304, 25.305, 25.331, 25.420, 25.423, 25.430, 25.433, New 25.859",null,null,null,null,"2001-03-20","2002-02-28"]
[8661,1171,"   Event Based and Periodic LCS","LCS1-EBP",2,"Rel-5","S1,S2,N4","2000-05-22","2002-06-07",1,"-","-","Pacific Bell Wireless","Randolph Wohlert (rwohlert@tri.sbc.com)","-","-",null,null,null,null,"2000-04-19","2012-05-21"]
[8664,1179,"      Impact on MAP","-",3,"Rel-5","N4","2002-03-15","2002-06-07",1,"-","-","-","-","Possible impact on UTRAN of LCS quality level request","-",null,null,null,null,"2000-04-19","2002-05-30"]
[8667,2438,"      Gb interface support for LCS","-",3,"Rel-5","GP","2000-04-03","2001-08-31",1,"GP-011925","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2012-05-21"]
[8670,2442,"   Location Services for GERAN in Iu Mode","-",2,"Rel-5","S2,G1,G2,R2,R3","2000-04-03","2002-06-28",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8675,2447,"      RRC protocol support for LCS","-",3,"Rel-5","G1,G2,R2,R3","2001-08-20","2001-11-30",1,"GP-011926","-","Nokia","Margaret Livingston","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8679,55069,"      LCS MS test case work plan (Release 98/99/4)","-",3,"Rel-5","G4,G5","2002-06-03","2003-06-27",1,"GP-000458","-","-","-","Marked as closed 12/2008 (was marked 60% complete)","-",null,null,null,null,"2002-05-23","2012-05-21"]
[8683,55072,"      Deleted - LCS BTS test cases","-",3,"Rel-5","G4,G5","2002-06-03","2003-06-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-15",null,"2002-05-23","2008-12-12"]
[8686,2435,"      Co-ordinated development of GSM LCS Phase 2 and UMTS LCS, S2 and GERAN","-",3,"Rel-5","GP,S2,S5,R2,R3,G2,G1","2000-08-28","2002-06-28",1,"GP-000456","-","-","-","-","-",null,null,null,null,"2001-02-01","2012-05-21"]
[8688,35008,"   Charging and OAM&P for LCS enhancements","LCS1-OAM",2,"Rel-5","S5","2001-09-21","2002-06-28",1,"SP-010461","-","-","-","-","32.200-series",null,null,null,null,"2000-04-19","2012-05-21"]
[8691,32022,"   Deleted - CHECK STATUS - Inter-GMLC interface","-",2,"Rel-5","S2","2002-05-30","2002-12-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"SP-10",null,"2002-05-30","2008-12-12"]
[8694,2576,"      Rel-5 IP network layer security (NDS/IP) (SEC1-NDS-IP)","-",3,"Rel-5","S3","2000-06-15","2002-03-15",1,"SP-010326","-","Telenor","Geir-myrdahl.koien@telenor.com","SP#12 WID updated SP-000420 (S3-000606) =>SP-010326 (S3-010286)","New 33.210",null,null,null,null,"2001-06-09","2011-08-08"]
[8697,1579,"         Deleted - Integration of GTP signalling security architecture - for User plane protection in core network (e.g., provided by IPsec)","-",4,"Rel-5","N4","2001-09-14","2002-06-07",1,"-","-","-","-","Waiting for input from SA3!. Marked as stopped 12/2008","-",null,null,"NP-16",null,"2000-04-09","2008-12-12"]
[8702,2244,"   Overall System Architecture for Intra Domain Connection of RAN Nodes to Multiple CN Nodes","-",2,"Rel-5","S2","2001-01-03","2001-09-21",1,"-","-","-","-","-","-",null,null,null,null,"2000-12-13","2001-09-19"]
[8706,50067,"   GERAN work for Intra Domain Connection of RAN Nodes to Multiple CN Nodes","IDCRAN-GERAN",2,"Rel-5","GP","2002-02-08","2002-06-28",1,"GP-020492","-","Ericsson","ingemar.backlund@era.ericsson.se","Accept changes Gb over IP","-",null,null,null,null,"2002-05-23","2002-09-26"]
[8710,52077,"      48.016 Use of Gb interface concepts when a network applies IDNNS","-",3,"Rel-5","G2","2002-02-08","2002-06-28",1,"-","-","-","-","Closed, accept changes for Gb over IP","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8713,2321,"   Deleted - Evolution of the transport for A","GEIMP3-EtA",2,"Rel-5","GP","2001-04-06","2002-12-20",1,"GP-010910","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8715,2323,"      Deleted - Adaptation of the Layer 3 BSSMAP procedures as required","-",3,"Rel-5","GP","2001-04-06","2002-12-20",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8718,35003,"   Rel-5 Performance Management","-",2,"Rel-5","S5","2001-09-17","2002-09-12",1,"SP-010631","-","Nortel","-","-","32.4xy, 52.402",null,null,null,null,"2000-04-26","2002-11-08"]
[8724,2396,"GERAN enhancements for streaming services 2 (usage of ECSD)","-",1,"Rel-5","GP","2000-11-06","2002-06-28",1,"GP-010430","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Motorola, Vodafone","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8725,2398,"   Usage of ECSD Concept","-",2,"Rel-5","GP","2000-11-06","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8729,2402,"   MAC header","-",2,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8733,2415,"      Update of Evolution of Iu ps specifications ","-",3,"Rel-5","GP,R3","2001-12-03","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8737,2419,"      Update of Evolution of Iu cs specifications ","-",3,"Rel-5","GP,R3","2000-09-01","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-02","2002-07-31"]
[8740,2558,"   E2E QoS interworking","E2EQoS-IW",2,"Rel-5","N3","2000-08-28","2002-06-07",1,"NP-010528","-","Lucent","Daisuke Yokota (yokota@lucent.com)","[DAB - 30/07/02] - % complete to 95% (if we exclude Diffserv). Marked as closed 12/2008 (was marked 95% complete)","29.208, 29.207, 27.060, 29.061, 24.008, 24.228, , 24.229, 29.060, 29.163",null,null,null,null,"2001-06-08","2008-12-12"]
[8742,2569,"Rel-5 Messaging enhancements","MESS5",1,"Rel-5","T2","2001-06-15","2003-03-31",1,"-","-","-","-","support of UAProf, so this in my opinion is 100% complete","-",null,null,null,null,"2000-09-14","2001-03-13"]
[8745,42000,"      Technical realization of MESS5-MMS","-",3,"Rel-5","T2","2001-06-15","2002-06-07",1,"-","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","stage 3 MM7 is missing",23.14,null,null,null,null,"2001-07-04","2003-03-27"]
[8751,50001,"GERAN Inter BSC NACC improvements over the Gb Interface","GERNACC",1,"Rel-5","GP","2001-09-03","2002-06-28",1,"GP-012313","-","-","-","-","-",null,null,null,null,"2001-09-19","2002-07-31"]
[8753,32502,"      Stage 2 - Concept","-",3,"Rel-5","N4,S2","2001-09-03","2001-10-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-09-19","2002-07-31"]
[8756,50002,"   Modification of Gb protocols for GERAN Inter BSC NACC over Gb Interface","GERNACC-Gbmod",2,"Rel-5","GP","2001-11-30","2002-06-28",1,"GP-012314","-","-","-","-","-",null,null,null,null,"2001-09-19","2002-07-31"]
[8760,50035,"   Deleted - GERAN MS Conformance test for Enhanced Power Control","-",2,"Rel-5","GP","2001-12-10","2003-12-19",1,"GP-012750","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-12-10","2003-02-13"]
[{"$f":"A8764+1","v":8764},50061,"      Concept","-",3,"Rel-5","GP","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8765,52004,"      Changes to 44.018","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8769,51028,"      Changes to 45.005","-",3,"Rel-5","G1","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8770,52005,"      Changes to 24.008","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8771,52006,"      Changes to 48.058","-",3,"Rel-5","G2","2001-12-10","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8772,50039,"   Deleted - GERAN MS Conformance test for 8PSK HR","-",2,"Rel-5","GP","2001-12-10","2003-12-19",1,"GP-012754","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-12-10","2008-12-12"]
[8773,50040,"   GERAN BTS Conformance test for 8PSK HR","-",2,"Rel-5","GP","2001-12-10","2002-12-20",1,"GP-012755","-","-","-","-","-",null,null,null,null,"2001-12-10","2003-01-13"]
[8774,13000,"Service Change and UDI Fallback","SCUDIF",1,"Rel-5","N3","2001-10-08","2002-06-07",1,"NP-020164","-","Ericsson","Rune.Werner.Wiik@ericsson.no","-","29.007, 27.001, 24.008",null,null,null,null,"2001-09-19","2003-07-25"]
[8775,501800,"Rel-5 USIM toolkit enhancements","USAT5",1,"Rel-5","T3,S1","2000-06-05","2003-09-26",1,"-","-","G & D","Michael Meyer","Acronym changed from USAT1, USAT1-Interpr, USAT1LocLnk","22.038, 31.111 (USAT1), 22.038, 03.19, 03.48 (USAT1LocLnk), 23.048 (USAT1SM), 43.019 (USAT1APIJAVA)",null,null,null,null,"2000-09-14","2015-03-24"]
[8776,43002,"   Deleted - Test specification for USIM toolkit security mechanisms","-",2,"Rel-5","T3","2002-05-28","2003-09-26",1,"TP-020028","-","Gemplus","Sophie Viallet","Marked as stopped 12/2008","-",null,null,"TP-21",null,"2002-05-30","2003-01-13"]
[8777,1801,"   Protocol Standardisation of a SIM Toolkit Interpreter","-",2,"Rel-5","T3,T2","2000-06-05","2003-01-22",1,"TP-000116","-","G & D","Michael Meyer","28/5/2001: T3-19 proposed that since the stage 2 and 3 will not be presented to TP-12 for approval as expected, the WI will be moved to rel-5, with completion expected at TP-13.","T2 27.103",null,null,null,null,"2000-09-14","2001-05-28"]
[8778,2497,"      Stage 1 for Protocol Standardisation of a SIM Toolkit Interpreter","-",3,"Rel-5","T3","2000-06-05","2001-03-16",1,"-","-","-","-","5/10/2001: Stage one comepeted at TP-12.","31.112, 31.113, 31.114",null,null,null,null,"2001-03-30","2001-10-05"]
[8779,2496,"      Stage 2 and 3","-",3,"Rel-5","T3","2001-01-03","2002-03-08",1,"-","-","-","-","5/10/2001: TS 31.112 and 31.113 approved at TP-13. TS 31.114 to be presented to TP-14.","31.112, 31.113, 31.114",null,null,null,null,"2001-03-30","2002-06-04"]
[8780,2518,"      Test specification for Protocol Standardisation of a SIM Toolkit Interpreter","-",3,"Rel-5","T3","2001-09-03","2003-01-22",1,"TP-010111","-","Gemplus","Gérald MAUNIER","5/10/2001: Work started on test specification. Marked as closed 12/2008 (was marked 12% complete)","-",null,null,null,null,"2001-03-30","2008-12-12"]
[8781,501802,"   (U)SIM API","USAT5-API",2,"Rel-5","T3","2002-03-20","2002-09-20",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","8/3/2001: test spec is based on R99 core spec, so deleted from Workplan. Acronym changed from USAT1-API, TEI4","-",null,null,null,null,"2000-09-14","2015-03-24"]
[8782,504301,"      Rel-5 Java API Test specification","-",3,"Rel-5","T3","2002-03-20","2002-09-20",1,"TP-020029","-","Microelectrónica Española","Mario Pérez ","-",51.012999999999998,null,null,null,null,"2002-05-30","2002-09-26"]
[8783,30001,"(Small) Technical Enhancements and Improvements for Rel-5","TEI5",1,"Rel-5","SP,CP,RP,GP","2000-01-03","2000-01-03",1,"-","-","-","-","\"Joker\" WI, to be used for a Rel 5 CR not related to any feature and with very limited impact on the system","-",null,null,null,null,"2000-09-26","2000-04-01"]
[8784,25018,"Test - (Small) Technical Enhancements and Improvements for Rel-5","TEI5_Test",1,"Rel-5","R5,T1","2000-01-03","2008-12-31",1,"-","-","-","-","\"Joker\" WI, to be used for small modifications applicable to Rel 5 conformance testing. Moved in from Stoyan/testing WP.","34.108, 34.109, 34.121-1, 34.121-2, 34.122, 34.123-1, 34.123-2, 34.123-3, 34.171, 34.229-1, 34.229-2, 34.229-3",null,null,null,null,"2006-03-21","2008-05-06"]
[8785,31013,"Technical Report on UE Functionality Split","UESPLIT",1,"Rel-5","S1","2000-01-03","2000-05-01",1,"SP-010484","-","Motorola","jian.j.wu@motorola.com","-","New 22.944 ",null,null,null,null,"2001-10-11","2010-09-14"]
[8786,2520,"User Equipment Management","UEM",1,"Rel-5","S5","2001-06-21","2002-06-28",1,"SP-010286","-","Vodafone","john.mudge@vf.vodafone.co.uk","-",32.802,null,null,null,null,"2001-06-06","2002-06-21"]
[8787,35000,"   FS on User Equipment (UE) Management ","OAM-UEM",2,"Rel-5","S5","2001-06-21","2002-06-28",1,"SP-010286","-","Vodafone","john.mudge@vf.vodafone.co.uk","-",32.802,null,null,null,null,"2001-07-03","2002-06-21"]
[8788,50201,"Flow control supporting an MS with multiple data flows with different QoS over the Gb interface","FlowCon",1,"Rel-5","GP","2002-06-24","2002-08-30",1,"GP-021767","-","Ericsson","ingemar.backlund@era.ericsson.se","50101 -> 50201","-",null,null,null,null,"2002-07-31","2008-05-06"]
[8789,50202,"   Update of stage 2 specifications","-",2,"Rel-5","GP","2002-06-24","2002-08-30",1,"-","-","-","-","50102 -> 50202","-",null,null,null,null,"2002-07-31","2008-05-06"]
[8790,32097,"      Concept document 23.060 (changes to)","-",3,"Rel-5","S2","2002-06-28","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-07-31","2002-09-26"]
[8791,50203,"      Flow Control","-",3,"Rel-5","GP","2002-06-24","2002-06-28",1,"-","-","-","-","50103 -> 50203","-",null,null,null,null,"2002-07-31","2008-05-06"]
[8792,50204,"   Modification of BSSGP protocol","-",2,"Rel-5","GP","2002-06-24","2002-06-28",1,"GP-021508","-","Ericsson","ingemar.backlund@era.ericsson.se","50104 -> 50204","-",null,null,null,null,"2002-07-31","2012-10-26"]
[8793,52095,"      Stage 3 (changes to 48.018)","-",3,"Rel-5","G2","2002-06-24","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-07-31","2002-09-26"]
[8794,50058,"Deleted - Multiple TBF in A/Gb mode - Phase 1 (MULTBF)","-",1,"Rel-5","GP","2002-04-19","2003-11-28",1,"GP-021263","-","Ericsson","gunnar.mildh@era.ericsson.se","GP#17 Nov 2003 Moved to Rel-6 as UID_50600 MULTBF (Only Multiple TBF Concept paper produced in Rel-5)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8795,50059,"   Deleted - Multiple TBF in A/Gb mode - Core (MULTBF-Agbmode)","-",2,"Rel-5","GP","2002-04-19","2003-08-22",1,"GP-021263","-","-","-","Marked as closed 12/2008 (was marked 26% complete)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8796,50060,"      Deleted - Multiple TBF Concept paper","-",3,"Rel-5","GP","2002-04-19","2003-08-22",1,"-","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","-",null,null,"GP-17",null,"2002-05-23","2009-11-12"]
[8797,51001,"      Deleted - Multiple TBF Stage 2 (43.064) CRs","-",3,"Rel-5","G1","2002-04-19","2002-11-22",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2002-05-23","2009-11-12"]
[8798,50062,"      Deleted - Multiple TBF Stage 3 (44.060) CRs","-",3,"Rel-5","G2","2002-04-19","2002-11-22",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2002-05-23","2009-11-12"]
[8799,50206,"   Deleted - Multiple TBF in A/Gb mode - Phase 1 – MS testing","-",2,"Rel-5","GP","2002-06-24","2003-11-28",1,"GP-022098","-","Ericsson","ingemar.backlund@era.ericsson.se","08/08: duplicate UID_50106=-> 50206. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2002-07-31","2009-11-12"]
[8800,54101,"      Deleted - MS conformance tests for Multiple TBF in A/Gb mode ","-",3,"Rel-5","G4","2002-06-24","2003-11-28",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2002-07-31","2009-11-12"]
[8801,2345,"Alignment of 3G functional split and Iu","GER3GAL",1,"Rel-5","GP","2000-06-08","2003-12-19",1,"GP-021256","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2002-09-26"]
[8802,2346,"   GERAN user / control plane","GER3GAL-GUCOPL",2,"Rel-5","GP","2000-08-07","2002-08-30",1,"GP-021255","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8803,2347,"      Alignment with UMTS bearer concept","-",3,"Rel-5","GP","2000-08-07","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8804,50300,"         Enhanced power control - for Alignment with UMTS bearer concept","-",4,"Rel-5","GP","2001-08-31","2001-08-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-09-19","2001-09-12"]
[8805,2423,"         Stage 2 - for Alignment with UMTS bearer concept","-",4,"Rel-5","GP","2000-08-07","2001-06-29",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8806,2348,"         Adoption of the UTRAN PDCP","-",4,"Rel-5","GP","2000-11-06","2001-12-21",1,"-","-","-","-","Responsible is GERAN¦RAN WG2 help may be needed.","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8807,50043,"         Development of RLC / MAC","-",4,"Rel-5","GP","2001-08-31","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2003-01-13"]
[8808,50044,"         Development of GERAN RRC","-",4,"Rel-5","GP","2001-06-22","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-07-31"]
[8809,50045,"         Ciphering and integrity protection concept paper","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8810,50046,"         Multiple TBF or equivalent Concept paper","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8811,50047,"         Paging concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8812,50048,"         Dedicated Physical subchannels, includes traffic and control channels","-",4,"Rel-5","GP","2001-08-31","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8813,50049,"         Iu support and broadcast concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8814,50050,"         Impact of using RLC instead of LAPDm concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8815,50051,"         Contention resolution, mobile station identity, and access concept","-",4,"Rel-5","GP","2001-08-31","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8816,50052,"         PDCP concept","-",4,"Rel-5","GP","2001-08-31","2002-04-19",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8817,50053,"         Downlink delayed TBF release","-",4,"Rel-5","GP","2001-08-31","2002-08-30",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-09-26"]
[8818,50054,"         Add transparent RLC Concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8819,50055,"         Handover concept","-",4,"Rel-5","GP","2001-08-31","2002-02-08",1,"-","-","-","-","-","-",null,null,null,null,"2002-05-23","2002-05-21"]
[8820,2424,"      Physical layer alignment with UMTS bearer concept","-",3,"Rel-5","GP","2000-11-06","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8821,2356,"         PDTCH/TCH in 45.003","-",4,"Rel-5","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8822,2357,"         Control channels in 45.003","-",4,"Rel-5","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8823,2358,"         Receiver performance in 45.005 for PDTCH/TCH and control channels","-",4,"Rel-5","GP","2000-11-06","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8824,2359,"   Iu rg interface","GER3GAL-Iurg",2,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"GP-010428","-","Ericsson","Frank Muller","AWS, Nokia, Ericsson, Nortel, Siemens, Vodafone","-",null,null,null,null,"2001-02-01","2003-02-13"]
[8825,2425,"      Inter BSS interface","-",3,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8826,2360,"         Identification of requirements for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8827,2361,"         Stage 2 for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[{"$f":"A8828+1","v":8828},2362,"         Adoption of relevant parts from Iur - for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8829,2363,"         Complementation with GERAN specifics - for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8830,2364,"         Stage 3 for Inter BSS interface","-",4,"Rel-5","GP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8831,2426,"      Inter BSS-RNS interface","-",3,"Rel-5","GP,RP","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8832,2365,"         Identification of requirements for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8833,2366,"         Stage 2 for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8834,2367,"         Adoption of relevant parts from Iur - for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8835,2368,"         Complementation with GERAN specifics - for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2002-01-30","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8836,2369,"         Stage 3 for Inter BSS-RNS interface","-",4,"Rel-5","GP,R3","2002-01-30","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8837,2370,"   Voice over GERAN PS and CS concept","-",2,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"GP-011252","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8838,2371,"      Architecture for A, Iu cs and Iu ps","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8839,2372,"      Transcoder position/operation","-",3,"Rel-5","GP","2000-11-06","2001-04-13",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8840,2373,"      Handover for Voice over GERAN PS and CS","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8841,2374,"      RTP payload","-",3,"Rel-5","GP,R3","2000-11-06","2002-06-28",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-11-08"]
[8842,2375,"      Codec renegotiation concept","-",3,"Rel-5","GP,R3","2000-11-06","2002-03-29",1,"-","-","-","-","-","-",null,null,null,null,"2002-11-08","2002-11-08"]
[8843,2376,"      LA","-",3,"Rel-5","GP","2000-11-06","2001-04-13",1,"-","-","-","-","-","-",null,null,null,null,"2002-11-08","2002-11-08"]
[8844,2388,"   Deleted - GERAN MS Conformance test for GERAN interface evolution","-",2,"Rel-5","GP","2001-06-11","2003-12-19",1,"GP-021253","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[8845,2389,"      Deleted - MS test for GERAN interface evolution","-",3,"Rel-5","GP","2001-06-11","2003-12-19",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[8846,2390,"   GERAN BSS Conformance test for GERAN interface evolution","-",2,"Rel-5","GP","2000-06-08","2003-12-19",1,"GP-021254","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,null,null,"2001-02-01","2008-12-12"]
[8847,2391,"      Deleted - BSS test","-",3,"Rel-5","GP","2000-06-08","2003-12-19",1,"-","-","-","-","Not started. Marked as stopped 12/2008","-",null,null,"GP-17",null,"2001-02-01","2008-12-12"]
[8848,2330,"GERAN support for IMS","GERIMS",1,"Rel-5","GP","2000-05-01","2002-12-20",1,"GP-010420","-","Nokia","Shkumbin Hamiti","AWS, Nokia, Ericsson, Nortel, Siemens, Motorola","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8849,2331,"   GERAN Header adaptation","GERIMS-HEADAPT",2,"Rel-5","GP,S2,RP","2000-05-01","2002-12-20",1,"GP-010421","-","Nokia","Shkumbin Hamiti","AWS, Nokia, Ericsson, Nortel, Siemens, Motorola","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8850,2332,"      Definition of compression and removal modes for PDCP protocol","-",3,"Rel-5","GP,S2,RP","2000-07-24","2000-09-01",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8851,2333,"      Conceptual description in stage 2","-",3,"Rel-5","GP,S2,RP","2000-05-01","2001-10-31",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8852,2334,"      Necessary changes on stage 3 regarding header removal","-",3,"Rel-5","GP,S2,RP","2000-11-06","2002-12-20",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8853,2335,"   Deleted - GERAN Radio access bearer design for IMS","GERIMS-RABDES",2,"Rel-5","GP,S2,RP","2000-11-06","2002-06-28",1,"GP-010422","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-10",null,"2001-02-01","2008-12-12"]
[8854,2422,"      Deleted - MuM control signalling for conversational multimedia services","-",3,"Rel-5","GP,S2,RP","2000-11-06","2002-06-28",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-10",null,"2001-02-01","2008-12-12"]
[8855,2431,"         Deleted - Identification of requirements for MuM control signalling for conversational multimedia services","-",4,"Rel-5","GP,S2,RP","2000-11-06","2002-02-08",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED","-",null,null,"GP-08",null,"2001-02-13","2003-01-13"]
[8856,2337,"         Deleted - Necessary modifications due to SIP","-",4,"Rel-5","GP,S2,RP","2002-05-06","2002-06-28",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED","-",null,null,"GP-10",null,"2001-02-01","2003-01-13"]
[8857,2341,"   Deleted - GERAN MS Conformance test for support of IMS","GERIMS-MSconf",2,"Rel-5","GP","2001-06-11","2002-12-20",1,"GP-010424","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8858,2342,"      Deleted - MS test for support of IMS","-",3,"Rel-5","G4","2001-06-11","2002-12-20",1,"-","-","-","-","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8859,2343,"   Deleted - GERAN BTS Conformance test for support of IMS","GERIMS-BTSconf",2,"Rel-5","GP","2001-06-11","2002-12-20",1,"GP-010425","-","Nokia","Shkumbin Hamiti","TERMINATED - NOT STANDARDIZED. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-02-01","2008-12-12"]
[8860,54001,"MS Conformance Testing of Dual Transfer Mode","MSCTDTM",1,"Rel-5","G4,G5","2002-11-11","2003-02-07",1,"GP-023236","-","Vodafone","Dave Fox","Needed to complete DTM (R99)","-",null,null,null,null,"2003-01-13","2003-02-13"]
[8861,32033,"Handling of early Ues","LATE_UE",1,"Rel-5","S2","2000-01-03","2003-06-27",1,"SP-030125","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-01-15"]
[8862,32031,"   Feasibility Study on Handling of early Ues","-",2,"Rel-5","S2","2002-10-07","2002-12-13",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-01-15"]
[8863,32032,"   Stage 2 for Handling of early Ues","-",2,"Rel-5","S2","2003-01-06","2003-06-27",1,"-","-","-","-","-","-",null,null,null,null,"2003-01-15","2003-07-23"]
[8864,22001,"   FS for the Early Mobile Handling in UTRAN","FSEarlyUE",2,"Rel-5","R2","2002-09-09","2003-06-06",1,"-","-","Vodafone","alan.law@vodafone.com ","-","-",null,null,null,null,"2002-09-16","2003-07-04"]
[8865,96,"   Note: Stage 3 RAN part not shown","-",2,"Rel-5","RP","2000-01-03","2000-01-03",1,"-","-","-","-","-","-",null,null,null,null,"2000-10-09","2001-10-11"]
[8866,0,"--- RELEASE 4 ---","-",1,"Rel-4","NP,GP,RP,SP,TP","2000-01-03","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2008-07-11","2010-02-09"]
[8867,1861,"Miscellaneous UE Conformance Testing Activities","MISTST1",1,"Rel-4","T1","2001-04-02","2004-12-01",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2003-01-13"]
[8868,1862,"   Optimization of Test Time, RF Aspects (FDD)","MISTST1-OpFDD",2,"Rel-4","T1","2001-09-24","2003-09-03",1,"TP-030052","-","-","-","It is believed that the current R99 test spec. can be optimised for faster overall test times. Marked as stopped 12/2008 (was 70% complete)",34.121000000000002,null,null,null,null,"2000-09-14","2008-12-12"]
[8869,1863,"   Optimization of Test Time, RF Aspects (TDD)","MISTST1-OpTDD",2,"Rel-4","T1","2001-09-24","2003-09-03",1,"TP-030052","-","-","-","It is believed that the current R99 test spec. can be optimised for faster overall test times",34.122,null,null,null,null,"2000-09-14","2008-12-12"]
[8870,1907,"   Extensions to R99 Test cases","MISTST1-Ext",2,"Rel-4","T1","2001-04-02","2003-12-02",1,"TP-030052","-","-","-","Further test coverage of the R99 specification to cover supplementry services. Marked as stopped 12/2008 (was 70% complete)","34.123 p 1,2",null,null,null,null,"2000-08-24","2008-12-12"]
[8871,2564,"   Extension to R99 Test cases - TTCN","-",2,"Rel-4","T1","2002-06-28","2004-03-03",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","-",null,null,null,null,"2001-06-01","2008-12-12"]
[8872,2565,"   Creation of R99 TCs for TDD - prose","MISTST1-TDD",2,"Rel-4","T1","2001-10-01","2004-07-01",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 50% complete)","34.123-1",null,null,null,null,"2001-06-01","2008-12-12"]
[8873,2566,"   Deleted - Creation of R99 TCs for TDD - TTCN","-",2,"Rel-4","T1","2002-09-03","2004-12-01",1,"TP-030052","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-26",null,"2001-06-01","2008-12-12"]
[8874,1908,"   Deleted - Review all other work items for impact on new or exiting 34 series specs.","-",2,"Rel-4","T1","2002-07-02","2002-12-27",1,"-","-","-","-","Marked as stopped 12/2008","34.121,122,123,125",null,null,"TP-18",null,"2000-09-06","2008-12-12"]
[8875,1340,"Real Time Facsimile","FAX-RT",1,"Rel-4","S1","2000-02-22","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8876,1341,"   Real Time Fax ","-",2,"Rel-4","S2","2000-02-22","2000-06-23",1,"SP-000169","-","-","-","postponed from R99 to R00, SP-000169","-",null,null,null,null,"2000-04-09","2000-11-15"]
[8877,1808,"      Terminal capabilities, AT commands","-",3,"Rel-4","T2","2000-02-22","2000-06-23",1,"-","-","-","-","-","21.904, 27.007",null,null,null,null,"2000-09-14","2000-04-01"]
[8878,1343,"      Signalling aspects (e.g. ICM)","-",3,"Rel-4","N1","2000-02-22","2000-06-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-11-15"]
[8879,1648,"      Service provision","-",3,"Rel-4","N3","2000-02-22","2000-06-23",1,"-","-","-","-","-",23.146000000000001,null,null,null,null,"2000-08-08","2000-11-15"]
[8880,1345,"      Review whether service/stage 1 aspects need to be aligned","-",3,"Rel-4","S1","2000-04-14","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8881,1346,"      Review whether architecture/stage 2 aspects need to be aligned","-",3,"Rel-4","S2","2000-04-14","2000-06-23",1,"SP-000169","-","-","-","-","-",null,null,null,null,"2000-04-09","2000-04-01"]
[8882,1539,"Transparent End-to-End PS mobile streaming application","PSTREAM",1,"Rel-4","S4","2000-04-03","2001-03-21",1,"SP-000345","-","-","-","-","26.233, 26.234",null,null,null,null,"2000-07-28","2001-03-20"]
[8883,1818,"Multimedia Messaging","MMS4",1,"Rel-4","T2,S1","2000-02-22","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","Acronym changed from \"MMS, Rel-4\"","22.140, 23.140",null,null,null,null,"2000-09-14","2015-03-24"]
[8884,136,"   Definition of service requirements for Multimedia Messaging","-",2,"Rel-4","S1","2000-02-22","2000-05-31",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8885,1819,"   Review of definition of service requirements","-",2,"Rel-4","T2","2000-06-01","2001-03-14",1,"TP-000078","-","Siemens","-","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8886,1820,"   Technical Realisation ","-",2,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8887,1821,"      Review of definition of reference Achitecture model","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8888,1822,"      Fulfill Requirements of Stage 1","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","e.g. minimum set of media formats, media format conversion, personalization of MMS. ","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8889,1823,"      Definition of MMS primitives in Stage 2","-",3,"Rel-4","T2","2000-04-10","2001-03-14",1,"TP-000078","-","Siemens","Josef.Laumen@SAL.SIEMENS.DE","-","22.140, 23.140",null,null,null,null,"2000-09-14","2009-07-08"]
[8890,1541,"Transcoder-Free Operation","TrFO",1,"Rel-4","N4,S2,N1","2000-01-03","2001-03-30",1,"-","-","-","-","Lead given to CN4 from CN","-",null,null,null,null,"2000-07-28","2002-03-25"]
[8891,112,"   Out-of-Band Transcoder Control solution","TrFO-OoBTC",2,"Rel-4","N4","2000-01-03","2001-03-30",1,"N4-000531","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","-","-",null,null,null,null,"2000-04-06","2009-07-08"]
[{"$f":"A8892+1","v":8892},1512,"      implementation in UTRAN","TrFO-OoBTC-UTRAN",3,"Rel-4","R3","2000-09-11","2001-03-30",1,"-","-","Siemens","Alexander Vesely","moved according to NP-000575","25.401, 25.410, 25.413, 25.415, 23.153",null,null,null,null,"2000-07-26","2001-03-20"]
[8893,896,"      Impact on architecture, Principles and Terminology","-",3,"Rel-4","S2","2000-01-03","2000-10-20",1,"-","-","-","-","e.g. study cascading TrFO/TFO/TrFO","-",null,null,null,null,"2000-04-06","2000-12-13"]
[8894,1657,"      Codec Negotiation between UE and MSC","-",3,"Rel-4","N1","2000-08-14","2001-02-02",1,"-","-","Motorola","Andrew Howell","the link to NP-000085has been deleted because refering to a R99 status sheet","24.008, 23.009, 23.108, (29.002)",null,null,null,null,"2000-08-08","2000-12-04"]
[8895,115,"      Codec Negotiation inter MSC","-",3,"Rel-4","N4","2000-07-03","2000-12-22",1,"-","-","-","-","Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex + list of open issues","-",null,null,null,null,"2000-04-06","2001-03-12"]
[8896,894,"      Bearer establishment inter MSC","-",3,"Rel-4","N4","2000-07-03","2000-12-22",1,"NP-000127","-","-","-","Bearer establishment inter MSC. TS 23.153 R99 part complete. capabilities moved to annex.",23.152999999999999,null,null,null,null,"2000-04-06","2001-03-12"]
[8897,905,"   Speech Transcoder: Location and Control at the UMTS Core Network Border","TrFO-STLC",2,"Rel-4","S2","2000-04-10","2000-09-29",1,"-","-","-","-","WI description and Tdoc S2-99352","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8898,124,"      Transcoder at Edge ","-",3,"Rel-4","NP","2000-04-10","2000-09-29",1,"-","-","-","-","WI description and Tdoc S2-99352","-",null,null,null,null,"2000-04-06","2001-03-12"]
[8899,2310,"GERAN improvements 1 (Gb over IP)","GEIMP1",1,"Rel-4","GP","2000-05-09","2001-03-19",1,"GP-000433","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8900,2311,"   Gb over IP (Ip-fication of Gb)","GbIP",2,"Rel-4","GP","2000-05-09","2001-03-19",1,"GP-000434","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8901,2312,"      Concept of Gb over IP (Ip-fication of Gb)","-",3,"Rel-4","GP","2000-05-09","2000-11-10",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8902,2313,"      Changes to 08.16, 08.18","-",3,"Rel-4","GP","2000-05-09","2001-03-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8903,2314,"GERAN improvements 2 (NACC)","GEIMP2",1,"Rel-4","GP","2000-11-06","2003-06-10",1,"GP-012812","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8904,2315,"   Gb enhancements","Gben",2,"Rel-4","GP","2000-11-06","2001-06-08",1,"GP-000436","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8905,2316,"      Intra BSC NACC (Network Assisted Cell Change)","-",3,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8906,2420,"         Concept","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8907,2317,"         Changes in 03.64","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8908,2318,"         Changes in 04.60","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8909,2319,"         Changes in 44.008","-",4,"Rel-4","GP","2000-11-06","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-09-12"]
[8910,50030,"   MS conformance test for Intra BSC NACC","GEIMP2-Msconf",2,"Rel-4","GP","2001-11-30","2003-06-10",1,"GP-012811","-","-","-","-","-",null,null,null,null,"2001-12-10","2003-02-13"]
[8911,50299,"      Changes in 51.010","-",3,"Rel-4","G5,G4","2001-11-30","2003-06-10",1,"-","-","-","-","az 05/08: duplicated UID_50099 => 50299. Marked as closed 12/2008 (was marked 50% complete)","-",null,null,null,null,"2002-05-23","2008-05-06"]
[8912,2324,"GERAN improvements 4 (Delayed TBF)","GEIMP4",1,"Rel-4","GP","2001-01-15","2001-06-08",1,"GP-010363","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8913,2325,"   Gb enhancements 2","GEIMP4-Gben2",2,"Rel-4","GP","2001-01-15","2001-06-08",1,"GP-010363","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-05-21"]
[8914,2429,"      Stage 2 for Gb enhancements 2","-",3,"Rel-4","GP","2001-01-15","2001-06-08",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-13","2002-03-01"]
[8915,2421,"      Stage 3 (changes in 44.060)","-",3,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8916,2327,"         Definition of enhanced countdown procedure","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8917,2328,"         Definition of enhanced TBF release procedure","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8918,2329,"         Definition of USF=FREE type polling mechanism on PDCH","-",4,"Rel-4","G2","2001-01-15","2001-04-06",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-03-01"]
[8919,1222,"Low Chip Rate TDD option","LCRTDD",1,"Rel-4","R1","2000-07-19","2003-12-02",1,"-","-","CWTS","G. Yang","-","-",null,null,null,null,"2000-04-26","2003-01-13"]
[8920,1223,"   Physical layer for Low Chip Rate TDD option","LCRTDD-Phys",2,"Rel-4","R1","2000-07-19","2001-03-30",1,"-","-","CWTS","G. Yang","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8921,1224,"   Layer 2 and layer 3 protocol aspects","LCRTDD-L23",2,"Rel-4","R2","2000-07-19","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8922,1225,"   RF radio transmission/reception, system performance requirements and conformance testing","LCRTDD-RF",2,"Rel-4","R4","2000-08-14","2001-03-30",1,"-","-","CWTS","D. Zhang","-","-",null,null,null,null,"2000-04-26","2001-03-30"]
[8923,1227,"   UE radio access capability","LCRTDD-UErac",2,"Rel-4","R2","2000-08-14","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[8924,1228,"   Iub/Iur protocol aspects - for Low Chip Rate TDD option","LCRTDD-IubIur",2,"Rel-4","R3","2000-08-14","2001-03-30",1,"-","-","CWTS","Y. Liu","-","-",null,null,null,null,"2000-04-26","2001-03-20"]
[8925,2262,"   Low chiprate TDD interworking with GERAN","-",2,"Rel-4","GP","2000-09-01","2001-01-19",1,"GP-000432","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8926,2263,"      Handover and Cell Selection / Reselection to UTRA 1.28 Mcps TDD","-",3,"Rel-4","GP","2000-09-01","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8927,2103,"   Conformance Test Aspects - Low Chip Rate TDD","-",2,"Rel-4","T1","2001-09-17","2003-12-02",1,"-","-","-","-","-","-",null,null,null,null,"2000-11-01","2000-04-01"]
[8928,2217,"      Testing Layer 2 and layer 3 protocol aspects","-",3,"Rel-4","T1","2001-09-17","2003-07-02",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 60% complete)","34.123-1, 34.123-2",null,null,null,null,"2000-11-16","2003-03-14"]
[8929,2562,"      Deleted - Testing Layer 2 and layer 3 protocol aspects - TTCN","-",3,"Rel-4","T1","2002-12-03","2003-12-02",1,"TP-030052","-","-","-","Marked as stopped 12/2008","34.123-3",null,null,"TP-22",null,"2001-05-31","2003-03-14"]
[8930,2218,"      Testing RF Radio Transmission and Reception","-",3,"Rel-4","T1","2001-09-17","2002-06-28",1,"TP-030052","-","-","-","duration set to 6 months (was 0), finish date set","-",null,null,null,null,"2000-11-16","2003-01-13"]
[8931,1322,"Enable bearer independent CS architecture","CSSPLIT",1,"Rel-4","S2,N3,N4","2000-01-03","2002-03-01",1,"SP-000288","-","Siemens","Alexander Milinski","-","-",null,null,null,null,"2000-04-09","2011-08-06"]
[8932,1323,"   Enable bearer-independent call control","-",2,"Rel-4","N4","2000-01-03","2001-08-16",1,"N4-000512","-","Ericsson","Heinz-Peter.Keutmann@eed.ericsson.se ","DAB 12.12.01 should be 100% hence closed","-",null,null,null,null,"2000-04-09","2002-01-24"]
[8933,1516,"      Architecture and Stage 2 description","-",3,"Rel-4","S2","2000-01-03","2000-09-08",1,"-","-","-","-","R00 stage 2 at least 80 % complete in TSGS #8 21.-23.6.2000",23.001999999999999,null,null,null,null,"2000-07-28","2000-04-01"]
[8934,1325,"      Standardisation of protocols (control & user planes) over Nb interface","-",3,"Rel-4","N3","2001-01-02","2001-03-30",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-05-30"]
[8935,1326,"      Standardisation of protocols over reference points between MSC server and Gateway MSC server","-",3,"Rel-4","N4","2000-09-25","2001-03-23",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8936,1616,"      Standardisation of detailed stage 2 description","-",3,"Rel-4","N4","2000-07-17","2001-03-23",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-08-08","2001-03-12"]
[8937,1327,"      Bearer control between MSC server and MGW","-",3,"Rel-4","N4","2000-09-01","2001-08-16",1,"N4-000512","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8938,1328,"         stage 3 - protocol issues","-",4,"Rel-4","N4","2000-09-01","2001-08-16",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-03-12"]
[8939,1329,"         stage 3 - parameter value issues","-",4,"Rel-4","N3","2001-01-02","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-05-30"]
[8940,2052,"   Deleted - Conformance Test Aspects - Enable bearer independent CS architecture","CSSPLIT-TEST",2,"Rel-4","T1","2001-03-05","2002-03-01",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-15",null,"2000-10-09","2000-04-01"]
[8941,1445,"MExE enhancements Rel-4","MEXE",1,"Rel-4","T2,S3","2000-01-03","2001-12-14",1,"TP-030052","-","-","-","-","-",null,null,null,null,"2000-04-09","2001-09-14"]
[8942,1447,"   MExE Security Analysis Activity","MEXE-SEC",2,"Rel-4","S3,T2","2000-02-22","2001-12-14",1,"SP-010327","-","BT","Andrew.Myers@bt.com","SP#12 updated WID","-",null,null,null,null,"2000-04-18","2011-08-06"]
[8943,2045,"      Stage 3 for MExE Security","-",3,"Rel-4","S3","2000-07-17","2001-12-14",1,"SP-010327","-","BT","Andrew.Myers@bt.com","-","21.133, 33.102",null,null,null,null,"2000-10-09","2011-08-06"]
[8944,1448,"      Terminal aspects for MExE Security","-",3,"Rel-4","T2","2000-02-22","2000-12-15",1,"SP-010327","-","BT","Andrew.Myers@bt.com","-",23.056999999999999,null,null,null,null,"2000-04-09","2001-03-13"]
[8945,1810,"   MExE Rel-4 Improvements and Investigations","MEXE-ENHANC",2,"Rel-4","T2","2000-01-03","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8946,1812,"      3rd MExE classmark","-",3,"Rel-4","T2","2000-01-03","2000-12-15",1,"-","-","Motorola","Mark Cataldo","Additional features for MExE R2000","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8947,1814,"      FS on Secure download mechanism and capabilities to support SDR concepts","-",3,"Rel-4","T2","2000-02-07","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8948,1815,"      FS on Support of MP3/MPEG4 content","-",3,"Rel-4","T2","2000-02-07","2000-12-15",1,"-","-","Motorola","Mark Cataldo","-","22.057, 23.057",null,null,null,null,"2000-09-14","2001-03-13"]
[8949,1631,"Tandem Free aspects for 3G and between 2G and 3G systems ","TFO",1,"Rel-4","S4","2000-02-22","2001-06-15",1,"-","-","-","-","RAN and CN to verify no problems for GSM terminals roaming in 3G R99","-",null,null,null,null,"2000-08-08","2001-03-30"]
[8950,1632,"   Tandem Free AMR","TFO-AMR",2,"Rel-4","S4","2000-02-22","2001-06-15",1,"-","-","-","-","RAN and CN to verify UMTS_AMR_2 support","-",null,null,null,null,"2000-08-08","2001-03-30"]
[8951,130,"      Specification of Tandem Free AMR","-",3,"Rel-4","S4","2000-02-22","2001-03-23",1,"-","-","-","-","-",28.062000000000001,null,null,null,null,"2000-04-06","2001-03-20"]
[8952,907,"      Impact of Tandem Free AMR on:","-",3,"Rel-4","NP","2001-01-08","2001-06-15",1,"-","-","-","-","\"Implementation\" changed to \"Impact on:\" by A. Sultan (for better wording)","-",null,null,null,null,"2000-04-06","2000-04-01"]
[8953,131,"         CN","-",4,"Rel-4","NP","2001-03-26","2001-06-15",1,"-","-","-","-","RAN and CN to verify UMTS_AMR_2 support","-",null,null,null,null,"2000-04-06","2001-03-30"]
[8954,132,"         GERAN","-",4,"Rel-4","GP","2001-01-08","2001-04-06",1,"-","-","-","-","End date Modified from June to March to have it in Rel4","-",null,null,null,null,"2000-04-06","2002-02-28"]
[8955,2230,"Advanced Speech Call Items enhancements_Rel-4","ASCI4",1,"Rel-4","N1","2000-12-03","2002-03-14",1,"NP-000730","-","Nortel","sonia.garapaty@nortelnetworks.com","Approved at CN#10. Acronym changed from ASCI, Rel-4","-",null,null,null,null,"2000-12-11","2015-03-24"]
[{"$f":"A8956+1","v":8956},2232,"   Stage 2 for Advanced Speech Call Items enhancements_Rel-4 (ASCI)","-",2,"Rel-4","N4","2000-12-03","2002-03-14",1,"-","-","Sagem","Vivien Perlic","CN4#11 30/11/02: no inputs received in CN4","23.067, 24.067",null,null,null,null,"2000-12-11","2001-12-12"]
[8957,2231,"   Stages 2 and 3 on A interface","-",2,"Rel-4","N1","2000-12-03","2001-03-23",1,"-","-","Nortel","sonia.garapaty@nortelnetworks.com","-","44.068, 44.069, 24.008",null,null,null,null,"2000-12-11","2001-05-30"]
[8958,2403,"700 MHz spectrum support","700SS",1,"Rel-4","GP","2000-01-03","2002-12-20",1,"GP-000449","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8959,2404,"   GERAN support for the 700 MHz band","-",2,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8960,2405,"      Signalling support","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8961,2406,"      Physical layer definitions - for GERAN support for the 700 MHz band","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8962,2407,"      Receiver performance and RF budget","-",3,"Rel-4","GP","2000-01-03","2001-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-02-13"]
[8963,2408,"   GERAN MS Conformance test for 700 MHz band","-",2,"Rel-4","GP","2001-04-02","2001-11-30",1,"GP-000451","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-07-31"]
[8964,2410,"   GERAN BTS Conformance test for 700 MHz band","-",2,"Rel-4","GP","2001-04-02","2002-12-20",1,"GP-000452","-","-","-","-","-",null,null,null,null,"2001-02-01","2003-01-13"]
[8965,2463,"Operator Determined Barring for Packet Oriented Services","ODB",1,"Rel-4","NP","2000-06-01","2001-03-19",1,"NP-010089","-","NEC","Toshiyuki Tamura (tamurato@aj.jp.nec.com)","Completed WI missing from the P-plan Added for tracking","-",null,null,null,null,"2001-03-20","2001-03-20"]
[8966,2546,"UMTS QoS Architecture for PS Domain","QoSPS",1,"Rel-4","S2,S5,R3,GP","2000-01-03","2002-11-27",1,"SP-010342","-","Ericsson","Ina.widegren@era.ericsson.se","-","-",null,null,null,null,"2001-06-08","2002-01-24"]
[8967,2548,"   Architecture","-",2,"Rel-4","S2","2000-06-05","2001-01-03",1,"-","-","-","-","-",23.106999999999999,null,null,null,null,"2001-06-08","2002-01-24"]
[8968,2550,"   Charging and OAM&P for QoS Management","QoSPS-OAM",2,"Rel-4","S5","2001-09-21","2002-06-28",1,"SP-010461","-","-","-","-","32-series",null,null,null,null,"2001-06-08","2002-06-21"]
[8969,1681,"   RAB Quality of Service (re)Negotiation over Iu","QoSPS-MAPEND-RABQoS",2,"Rel-4","R3","2000-08-21","2001-03-23",1,"-","-","Ericsson","anders.molander@ericsson.com ","-",25.413,null,null,null,null,"2000-07-26","2001-02-16"]
[8970,1991,"      RAB Quality of Service Negotiation over Iu","QoSPS-MAPEND-RABQoS-Negot",3,"Rel-4","R3","2000-08-21","2001-03-23",1,"-","-","Ericsson","anders.molander@ericsson.com ","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[8971,2456,"      RAB Quality of Service Negotiation over Iu during relocation","QoSPS-MAPEND-RABQoS-NegotReloc",3,"Rel-4","R3","2001-03-02","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-09","2001-03-12"]
[8972,1992,"      RAB Quality of Service Re-Negotiation over Iu","QoSPS-MAPEND-RABQoS-ReNegot",3,"Rel-4","R3","2000-09-25","2001-03-23",1,"-","-","Motorola","S. Irwin","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[8973,1553,"   GERAN QoS Aspects - Handovers: maintenance of real-time QoS while moving between cells in the PLMN including inter-SGSN and SRNS relocation or possibly other mechanisms","GERQoS",2,"Rel-4","GP","2000-01-03","2001-11-30",1,"GP-010431","-","-","-","-","-",null,null,null,null,"2000-04-26","2003-01-13"]
[8974,2306,"      Handover Concept for the PS domain","-",3,"Rel-4","GP","2000-01-03","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8975,2309,"         Stable RT handover report 25.936 including header removal","-",4,"Rel-4","GP","2000-01-03","2000-01-19",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-08","2002-01-24"]
[8976,2307,"         Update of stage 2","-",4,"Rel-4","GP","2000-01-03","2001-02-13",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2002-01-24"]
[8977,2308,"         Update of relevant stage 3 specs -> RRC","-",4,"Rel-4","G2","2000-01-03","2001-11-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-01","2001-12-10"]
[8978,50010,"   Deleted - GERAN MS Conformance test for inter-system and intra-system Packet data real-time Handover","GERQoS-Mstest",2,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"GP-012287","-","-","-","Still exist? To be clarified by GERAN4/5. Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8979,50011,"      Deleted - Handover for the PS domain","-",3,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8980,50012,"         Deleted - Stable RT handover report 25.936 including header removal","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8981,50013,"         Deleted - Update of stage 2","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8982,50014,"         Deleted - Update of relevant stage 3 specs","-",4,"Rel-4","G4,R3","2001-08-31","2002-11-27",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"GP-12",null,"2001-09-19","2008-12-12"]
[8983,1685,"   PS-domain handover for real-time services","QoSPS-PSdoRTS",2,"Rel-4","R3","2000-08-28","2001-03-30",1,"-","-","Nokia","atte.lansisalmi@nokia.com ","-","-",null,null,null,null,"2000-04-19","2001-03-12"]
[8984,2554,"   Deleted - RAB QoS Renegotiation at Relocation","-",2,"Rel-4","R3","2001-01-03","2001-03-23",1,"-","-","-","-","Marked as stopped 12/2008","25.851, 25.946",null,null,"RP-11",null,"2001-06-08","2008-12-12"]
[8985,1993,"(Small) Technical Enhancements and Improvements for Rel-4","TEI4",1,"Rel-4","SP,CP,RP,GP","2000-01-03","2000-01-03",1,"-","-","-","-","\"Joker\" WI, to be used for a Rel 4 CR not related to any feature and with very limited impact on the system","-",null,null,null,null,"2000-09-26","2000-04-01"]
[8986,25017,"Test - (Small) Technical Enhancements and Improvements for Rel-4","TEI4_Test",1,"Rel-4","R5,T1","2000-01-03","2001-03-30",1,"-","-","-","-","\"Joker\" WI, to be used for small modifications applicable to Rel 4 conformance testing. Moved in from the Stoyan/Testing WP","-",null,null,null,null,"2006-03-21","2008-05-06"]
[8987,400002,"Rel-4 Evolutions of the transport in the UTRAN","ETRAN",1,"Rel-4","RP","2000-08-21","2002-08-23",1,"-","-","Alcatel","Francois Courau","-","-",null,null,null,null,"2000-03-31","2000-11-17"]
[8988,12,"   QoS optimization for AAL2 connections over Iub and Iur interfaces","ETRAN-QoSAAL2",2,"Rel-4","R3","2000-08-21","2001-03-30",1,"-","-","Japan Telecom","T. Yoshimura","-","-",null,null,null,null,"2000-03-31","2001-03-20"]
[8989,1995,"   Transport bearer modification procedure on Iub, Iur, and Iu","ETRAN-MigrMod",2,"Rel-4","R3","2000-10-02","2001-03-30",1,"-","-","Japan Telecom","T. Yoshimura","-","-",null,null,null,null,"2000-09-26","2001-03-20"]
[8990,401834,"   Deleted - Conformance Test Aspects of Rel-4 evolutions of the transport in UTRAN","-",2,"Rel-4","T1","2002-02-25","2002-08-23",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-09-14","2009-10-13"]
[8991,2208,"      Deleted - Testing RAB support enhancements","CT-RABS?",3,"Rel-4","T1","2002-02-25","2002-08-23",1,"-","-","-","-","Marked as stopped 12/2008","34.108, 34. 121, 34.122, 34.123 p 1,2, 34.123 pt 3",null,null,"TP-17",null,"2000-11-16","2009-10-13"]
[8992,400004,"Rel-4 Evolutions of the transport in the CN","CNTRSP",1,"Rel-4","N4,N1,N2,S2","2000-05-29","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2001-03-20"]
[8993,859,"   IP Transport of CN protocols (e.g. CAP, MAP)","SS7IP",2,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-26","2001-03-20"]
[8994,1679,"      Stage 3 for IP Transport of CN protocols (e.g. CAP, MAP)","-",3,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-25","2001-03-13"]
[8995,2018,"         CAP","-",4,"Rel-4","N2","2000-12-07","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-25","2001-03-13"]
[8996,2019,"         MAP","-",4,"Rel-4","N4","2000-12-07","2001-03-23",1,"-","-","-","-","-",29.202000000000002,null,null,null,null,"2000-08-25","2001-03-12"]
[8997,2253,"         BSSAP+","SS7IP-BSSAP+",4,"Rel-4","N1","2001-01-15","2001-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2001-02-08","2001-03-12"]
[8998,1513,"   FS on Transport and control separation in the PS CN domain","-",2,"Rel-4","S2","2000-05-29","2001-03-23",1,"SP-000293","-","Ericsson","Juan-Antonio.Ibanez@eed.ericsson.se","-","-",null,null,null,null,"2000-07-28","2001-09-19"]
[8999,1615,"      Architectural impacts","-",3,"Rel-4","S2","2000-05-29","2001-03-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-08-08","2001-02-08"]
[9000,401216,"Rel-4 Improvements of Radio Interface","-",1,"Rel-4","RP","2000-07-10","2003-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2001-10-11"]
[9001,1509,"   UTRA repeater specification (master)","RInImp-REP",2,"Rel-4","R4","2000-07-10","2001-03-21",1,"-","-","Mikom, Allgon","T. Kummetz, Mikom; Alf Ahlström, Allgon","-","-",null,null,null,null,"2000-07-26","2001-03-30"]
[9002,1994,"   DSCH power control improvement in soft handover","RInImp-DSCHsho",2,"Rel-4","R1","2000-09-11","2001-03-23",1,"-","-","Nokia","antti.toskala@nokia.com","-","-",null,null,null,null,"2000-09-26","2001-03-12"]
[9003,1996,"   UMTS 1800","RInImp-UMTS18",2,"Rel-4","R4","2000-09-25","2001-12-14",1,"-","-","Motorola","Howard Benn","-","-",null,null,null,null,"2000-09-26","2001-11-29"]
[9004,2467,"   UMTS 1900","RInImp-UMTS19",2,"Rel-4","R4","2001-03-19","2001-12-14",1,"-","-","Motorola","Howard Benn","-",25.100999999999999,null,null,null,null,"2001-03-19","2009-07-09"]
[9005,1219,"   FS on High Speed downlink packet access","RInImp-HSDPA",2,"Rel-4","R2","2000-08-21","2001-03-23",1,"-","-","Motorola","Amitabha Ghosh (qa0047@email.mot.com)","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[9006,1510,"   Deleted - FS on improved common DL channel for Cell-FACH state","RInImp-DLCFACH",2,"Rel-4","R2","2000-09-11","2001-12-28",1,"-","-","GBT","J. Kwak","Stopped at RP#14","-",null,null,"RP-14",null,"2000-04-26","2009-10-13"]
[9007,401839,"   Conformance Test Spec. Rel-4 improvements in Radio Interface","-",2,"Rel-4","T1","2001-10-08","2003-03-14",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2001-10-11"]
[9008,2212,"      Deleted - Testing Improved usage of downlink resource in FDD for CCTrCHs of dedicated type","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2001-12-10"]
[9009,2213,"      Deleted - Testing Terminal Power saving features","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2001-12-10"]
[9010,2214,"      Deleted - Testing DSCH power control improvement in soft handover","-",3,"Rel-4","T1","2002-02-18","2002-08-30",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-02-28"]
[9011,2215,"      Testing UMTS 1800","-",3,"Rel-4","T1","2001-10-08","2002-06-14",1,"TP-030052","-","-","-","-","34.108, 34,121, 34.122, 34.123-1",null,null,null,null,"2000-11-16","2003-01-13"]
[9012,41000,"      Testing UMTS 1900","-",3,"Rel-4","T1","2001-10-08","2002-06-14",1,"TP-030052","-","-","-","-","34.108, 34,121, 34.122, 34.123-1",null,null,null,null,"2000-11-16","2003-01-13"]
[9013,2561,"      Testing UMTS 1800 - TTCN","-",3,"Rel-4","T1","2002-06-17","2003-03-14",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[9014,41001,"      Testing UMTS 1900 - TTCN","-",3,"Rel-4","T1","2002-06-17","2003-03-14",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[9015,400009,"Rel-4 RAN improvements","-",1,"Rel-4","RP","2000-08-14","2004-03-17",1,"-","-","-","-","-","-",null,null,null,null,"2000-03-31","2000-11-17"]
[9016,655,"   Node B synchronization for TDD","RANimp-NBsync",2,"Rel-4","R1","2000-08-14","2001-03-23",1,"-","-","Siemens","S. Oestreich","-","-",null,null,null,null,"2000-04-26","2001-03-12"]
[9017,2206,"   RAB support enhancement for Rel-4","RANimp-RABSE",2,"Rel-4","R2","2000-08-21","2001-03-23",1,"-","-","Ericsson","M. Israelsson, A. Krishnarajah","29 Nov 2000: split into ROHC and non-ROHC part¦5 Mar 2001: splitting off of ROHC for Rel-4 agreed by R2","-",null,null,null,null,"2000-12-04","2002-02-28"]
[9018,402102,"   Deleted - Conformance Test Aspects - Rel-4 RAN Improvements","-",2,"Rel-4","T1","2002-01-01","2004-03-17",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-23",null,"2000-11-01","2000-04-01"]
[9019,402222,"      Deleted - Testing Radio access bearer support enhancments","-",3,"Rel-4","T1","2002-01-01","2002-09-02",1,"-","-","-","-","Marked as stopped 12/2008","-",null,null,"TP-17",null,"2000-11-16","2002-04-09"]
[{"$f":"A9020+1","v":9020},402461,"      Deleted - Testing RAB support enhancements-Robust Header Compression","RABimp-RoCH",3,"Rel-4","T1","2002-05-28","2003-09-03",1,"TP-030052","-","-","-","UID changed. Marked as stopped 12/2008","34.123-1, -2",null,null,"TP-21",null,"2001-03-20","2003-03-14"]
[9021,41006,"      Deleted - Testing RAB support enhancements-Robust Header Compression - TTCN","-",3,"Rel-4","T1","2002-05-28","2004-03-17",1,"TP-030052","-","-","-","UID changed. Marked as stopped 12/2008","34.123-3",null,null,"TP-23",null,"2002-09-26","2003-03-14"]
[9022,41007,"      Testing of Extended Robut Header Compression","Ext-RoHC",3,"Rel-4","T1","2002-09-18","2003-09-30",1,"TP-030052","-","-","-","Marked as closed 12/2008 (was marked 15% complete)","34.123-1, -2",null,null,null,null,"2002-09-26","2003-03-14"]
[9023,41008,"      Deleted - Testing of Extended Robut Header Compression - TTCN","-",3,"Rel-4","T1","2002-09-18","2003-12-16",1,"TP-030052","-","-","-","Marked as stopped 12/2008","34.123-3",null,null,"TP-22",null,"2002-09-26","2003-03-14"]
[9024,41009,"      Deleted - General changes to TS34.121 corresponding to release 4","RANimp-test,TEI4",3,"Rel-4","T1","2003-03-03","2004-03-03",1,"-","-","-","-","Marked as stopped 12/2008","34.108, 34.121",null,null,"TP-23",null,"2003-03-14","2003-03-14"]
[9025,401652,"Rel-4 Emergency call enhancements","EMC1-CS",1,"Rel-4","N1,S1,T1","2000-01-03","2002-05-28",1,"-","-","Ericsson","-","Acronym changed from EMC1, EMC1-CS","-",null,null,null,null,"2000-08-08","2015-03-24"]
[9026,1654,"   For CS based calls","EMC1-CS",2,"Rel-4","N1","2000-01-03","2002-05-28",1,"NP-010136","-","Ericsson","-","WI approved in TSG_10","-",null,null,null,null,"2000-08-08","2001-05-30"]
[9027,1320,"      Distinction in CS domain of emergency call types to different emergency services","-",3,"Rel-4","S1","2000-05-01","2000-06-23",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2008-07-21"]
[9028,1999,"      Distinction in CS domain of emergency calls to different emergency types","-",3,"Rel-4","N1","2000-08-24","2000-09-22",1,"NP-010136","-","-","-","Calls to different emergency services such as ambulance, fire brigade, police, etc. can be routed to respective different emergency centres.",24.007999999999999,null,null,null,null,"2000-09-23","2008-07-21"]
[9029,402224,"      Deleted - Conformance Test Aspects - Emergency call enhancements","-",3,"Rel-4","T1","2000-01-03","2000-07-28",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"TP-08",null,"2000-11-16","2008-12-12"]
[9030,2226,"      Testing CS based emergency calls","-",3,"Rel-4","T1","2002-02-25","2002-05-28",1,"TP-030052","-","-","-","-","34.123-1",null,null,null,null,"2000-11-28","2003-01-13"]
[9031,2563,"      Testing CS based emergency calls - TTCN","-",3,"Rel-4","T1","2001-11-22","2002-05-28",1,"TP-030052","-","-","-","-","34.123-3",null,null,null,null,"2001-05-31","2003-01-13"]
[9032,401826,"Rel-4 Terminal interfaces","TI",1,"Rel-4","T2","2000-01-03","2001-03-15",1,"-","-","-","-","-","-",null,null,null,null,"2000-09-14","2001-03-13"]
[9033,1827,"   AT commands enhancements","TI-ATC",2,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","-",27.007000000000001,null,null,null,null,"2000-09-14","2001-03-13"]
[9034,1828,"      Specification of AT commands for new services","-",3,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","goal not completely achieved because of missing input",27.007000000000001,null,null,null,null,"2000-09-14","2001-03-20"]
[9035,1829,"   Wide Area Data Synchronization","TI-WADS",2,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","AS: Rel5 changed to Rel4 according to SP#10 decision, milestone on testing added","-",null,null,null,null,"2000-09-14","2000-12-19"]
[9036,1830,"      Continues evolution of Synchronization protocol","TI-SYNC-EVOL",3,"Rel-4","T2","2000-01-03","2001-03-14",1,"-","-","-","-","-","27.903, 27.103",null,null,null,null,"2000-09-14","2001-03-20"]
[9037,1832,"   Terminal local model","TLM",2,"Rel-4","T2","2000-05-16","2001-03-15",1,"TP-000080","-","Ericsson","Olga.Tome@ECS.ERICSSON.SE","-",23.227,null,null,null,null,"2000-09-14","2001-09-14"]
[9038,401536,"Rel-4 Location Services enhancements","LCS4",1,"Rel-4","S2,S1,T2,N1,N4,R3,R2","2000-04-03","2001-12-28",1,"SP-010518","-","Nokia","Jan Kall","Acronym changed form LCS1","-",null,null,null,null,"2000-07-28","2015-03-24"]
[9039,2229,"   CBS interactions","LCS4-CBS",2,"Rel-4","T2","2000-04-03","2001-12-28",1,"-","-","-","-","-",23.041,null,null,null,null,"2000-09-14","2015-03-24"]
[9040,523,"   LCS support in the CS domain","LCS4-CS",2,"Rel-4","S2","2000-05-15","2001-01-19",1,"-","-","-","-","Only MAP impact foreseen so far. To be further split if needed.","-",null,null,null,null,"2000-04-19","2015-03-24"]
[9041,525,"   LCS support in the PS domain","LCS4-PS",2,"Rel-4","S2,S1,N1,N4","2000-05-01","2001-12-28",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2015-03-24"]
[9042,1642,"      Stage 1 for LCS support in the PS domain","-",3,"Rel-4","S1","2000-07-03","2000-08-25",1,"-","-","Pacific Bell Wireless","Randolph Wohlert (rwohlert@tri.sbc.com)","To be also considered: External LCS client identity, and Privacy options when PDP-context and when no PDP-context is established",22.071000000000002,null,null,null,null,"2000-08-08","2000-04-01"]
[9043,1181,"      Stage 2 for LCS support in the PS domain","-",3,"Rel-4","S2,R2,G1","2000-05-01","2001-01-19",1,"-","-","-","-","SP#10 completed","25.305 (UTRAN part), new 23.271 (CN part by S2, 43.059 (GERAN part)",null,null,null,null,"2000-04-19","2000-12-13"]
[9044,1180,"      Stage 3 for LCS support in the PS domain","-",3,"Rel-4","N1,N4","2000-08-21","2001-12-28",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2001-10-10"]
[9045,526,"         Layer 3 LCS signalling UE (MS) -SGSN (UMTS PS and and GSM-GPRS)","-",4,"Rel-4","N1","2000-08-21","2001-12-28",1,"-","-","Nokia","Janne Muhonen","-","-",null,null,null,null,"2000-04-19","2002-03-25"]
[9046,2462,"         MAP impacts of LCS","-",4,"Rel-4","N4","2000-08-21","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2001-03-20","2001-03-20"]
[9047,527,"         GTP signalling for LCS","-",4,"Rel-4","N4","2000-08-21","2001-03-30",1,"-","-","-","-","-","-",null,null,null,null,"2000-04-19","2001-03-12"]
[9048,401600,"   UE positioning Rel-4","LCS1-UEpos",2,"Rel-4","R3,R2","2000-04-03","2001-03-30",1,"RP-000509","RP-010045","-","-","-","-",null,null,null,null,"2000-07-26","2002-04-09"]
[9049,1601,"      Iub/Iur interfaces for methods Rel 99","LCS1-UEpos-IubIur",3,"Rel-4","R3","2000-04-03","2001-03-30",1,"RP-000509","RP-010045","Ericsson","Yun-Chao Hu","-","25.401, 25.420, 25.423, 25.430, 25.433, new 25.850",null,null,null,null,"2000-07-26","2001-03-20"]
[9050,1602,"      UE positioning enhancements - IPDL for TDD","LCS1-UEpos-enh",3,"Rel-4","R2","2000-08-28","2001-03-23",1,"RP-000509","RP-010045","Siemens","Armin Sitte ","5 Mar 2001: split of IPDL for TDD agreed by R2","new 25.847",null,null,null,null,"2000-07-26","2012-05-22"]
[9051,401560,"Rel-4 UICC/(U)SIM enhancements and interworking","UICC1",1,"Rel-4","T3","2000-07-24","2001-03-23",1,"-","-","-","-","Acronym changed from UICC1, Rel-4","-",null,null,null,null,"2000-04-09","2015-03-24"]
[9052,1799,"   Common PCN Handset Specification (CPHS)","UICC1-CPHS",2,"Rel-4","T3","2000-07-24","2001-03-23",1,"TP-000116","-","One2One","-","28/5/2001: CRs approved at TP-11. WI complete.",27.103000000000002,null,null,null,null,"2000-09-14","2001-05-28"]
[9053,401800,"Rel-4 (U)SIM toolkit enhancements","USAT4",1,"Rel-4","T3,S1","2000-06-05","2001-03-23",1,"-","-","Gemplus","Jean-Francois Rubon","Acronym changed from USAT1, USAT1-LocLnk, USAT1APIJAVA, USAT1SM","23.048 (USAT1SM), 43.019 (USAT1APIJAVA)",null,null,null,null,"2000-09-14","2015-03-24"]
[9054,2034,"   USAT local link","USAT1-LocLnk",2,"Rel-4","T3,S1","2000-06-05","2001-03-23",1,"TP-000116","-","Gemplus","Jean-Francois Rubon","25/5/2001:CR was approved at TP-11. WI is complete","22.038, 31.111",null,null,null,null,"2000-09-27","2001-05-28"]
[9055,401571,"Rel-4 Security enhancements","SEC4",1,"Rel-4","S3,N4,N1","2000-01-03","2002-03-15",1,"SP-000421","-","Vodafone","Peter.Howard@vodafone.com","acronym changed from SEC1","-",null,null,null,null,"2000-04-09","2015-03-24"]
[9056,1331,"   Rel-4 Lawful Interception","SEC4-LI",2,"Rel-4","S3","2000-08-21","2001-03-23",1,"-","-","-","-","Requirements capture: S3#14 (Aug 00), Feature specification: S3#15 (Sep 00), Definition of architecture. Should be included in general LI work mentioned above.. Acronym changed from SEC1-LI",33.106999999999999,null,null,null,null,"2000-04-09","2015-03-24"]
[9057,1587,"   Evolution of GSM CS algorithms (e.g. A5/3 development and deployment)","SEC1-CSALGO1",2,"Rel-4","S3","2000-01-03","2001-01-15",1,"SP-000306","-","DTI, BIS","cbrookson@iee.org","SP#8 approved WID","33.102, 33.103, 33.105",null,null,null,null,"2000-04-09","2009-11-17"]
[9058,1588,"   Evolution of GSM PS algorithms (e.g. GEA 2 deployment)","SEC1-PSALGO1",2,"Rel-4","S3,N4,N1","2000-02-22","2000-12-22",1,"SP-000307","-","DTI, BIS","cbrookson@iee.org","SP#8 approved WID","33.102, 33.103, 33.105",null,null,null,null,"2000-04-09","2009-11-17"]
[9059,1589,"      Deleted - Main aspects of Evolution of GSM PS algorithms (e.g. GEA 2 deployment)","-",3,"Rel-4","S3","2000-02-22","2000-11-24",1,"-","-","DTI, BIS","cbrookson@iee.org","Complete TSG#09 (09/2000). S3#17: Proposed for deletion. TO BE DELETED","-",null,null,"SP-69",null,"2000-04-09","2011-08-06"]
[9060,1618,"      Impact on GTP","-",3,"Rel-4","N4","2000-03-20","2000-12-22",1,"-","-","DTI, BIS","cbrookson@iee.org","-","-",null,null,null,null,"2000-08-08","2000-12-13"]
[9061,1661,"      GEA capability indication in MS CM","SEC1-PSALGO1-GEACAP",3,"Rel-4","N1","2000-06-19","2000-12-22",1,"-","-","Vodafone Airtouch","Duncan Mills","-","-",null,null,null,null,"2000-08-08","2000-11-15"]
[9062,401583,"   Deleted - MAP application layer security","SEC1-MAPAL",2,"Rel-4","S3","2000-01-03","2002-03-15",1,"-","-","-","-","REPLACED BY NDS-MAP and NDS-IP. Completed Auto Key Management -> Rel-6. Marked as stopped 12/2008","-",null,null,"SP-15",null,"2000-04-09","2009-11-17"]
[9063,401584,"      Deleted - Main aspects of MAP application layer security","-",3,"Rel-4","S3","2000-02-21","2001-03-29",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"SP-11",null,"2000-04-09","2002-04-09"]
[9064,402025,"      Deleted - Other stage 3 aspects","-",3,"Rel-4","N4","2000-02-22","2000-11-24",1,"-","-","-","-","UID changed. Marked as stopped 12/2008","-",null,null,"CP-10",null,"2000-04-09","2002-04-09"]
[9065,401594,"      Deleted - Visibility and Configurability of security","SEC1-VCS",3,"Rel-4","S3","2000-01-03","2002-03-15",1,"SP-000305","-","France Telecom","Sebastien.nguyenngoc@rd.francetelecom.com","CR approved at SA3#21 awaiting comments from CN1. Marked as stopped 12/2008","-",null,null,"SP-15",null,"2000-04-09","2009-11-17"]
[9066,401142,"Rel-4 Charging and OAM&P","OAM4",1,"Rel-4","S5","2000-12-01","2001-10-05",1,"SP-010461","-","-","-","SP#13 approved WID","-",null,null,null,null,"2000-04-26","2002-01-24"]
[9067,2089,"   Rel-4 Principles, high level Requirements and Architecture","-",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-010461","-","Motorola, Telia","Michael.Truss@motorola.com, Tommy.R.Berggren@TELIA.SE","-","32.101, 32.102",null,null,null,null,"2000-04-26","2003-01-13"]
[9068,2088,"   Rel-4 Performance Management","-",2,"Rel-4","S5","2000-12-01","2001-09-28",1,"SP-010238","-","T-Mobile","karl-heinz.nenner@t-mobile.de","-","32.4xy, 52.402",null,null,null,null,"2000-04-26","2003-01-13"]
[9069,2081,"   Fault Management","-",2,"Rel-4","S5","2000-12-01","2001-10-05",1,"SP-000524","-","Lucent","-","-","32.111-1/4",null,null,null,null,"2000-04-26","2003-01-13"]
[9070,2082,"   Configuration Management","-",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-000524","-","Ericsson","thomas.tovinger@ericsson.com","-","32.106-1/8",null,null,null,null,"2000-04-26","2003-01-13"]
[9071,2083,"   Rel-4 Charging Management","-",2,"Rel-4","S5","2000-12-01","2001-09-28",1,"SP-000524","-","T-Mobile","karl-heinz.nenner@t-mobile.de","-","32.200, 32.205, 32.215, 32.235",null,null,null,null,"2000-04-26","2009-07-07"]
[9072,2071,"   UTRAN Operations and Maintenance procedures","UOAM",2,"Rel-4","S5","2000-12-01","2001-06-21",1,"SP-000524","-","Mannesmann Mobilfunk","bert.boden@d2mannesmann.de","-",32.799999999999997,null,null,null,null,"2000-10-09","2003-01-13"]
[9073,1517,"Global Text Telephony","GTT",1,"Rel-4","S1,S2,S4,T1,R5","2000-01-03","2001-03-19",1,"SP-010340","-","Ericsson ","gunnar.hellstrom@omnitor.se","SP#12 updated WID SP-000162=>SP-010340","-",null,null,null,null,"2000-07-28","2009-10-14"]
[9074,1634,"   Stage 1 for Global Text Telephony","-",2,"Rel-4","S1","2000-04-05","2000-12-22",1,"SP-010340","-","-","-","-",22.225999999999999,null,null,null,null,"2000-08-08","2012-05-09"]
[9075,1519,"   Stage 2 for Global Text Telephony","-",2,"Rel-4","S2","2000-01-03","2000-10-13",1,"SP-010340","-","-","-","-",23.225999999999999,null,null,null,null,"2000-07-28","2002-01-24"]
[9076,2234,"   Specification of Cellular Text telephone Modem","GTT-CTM",2,"Rel-4","S4","2000-09-11","2001-03-19",1,"SP-010340","-","-","-","-","-",null,null,null,null,"2000-12-13","2002-02-28"]
[9077,2238,"      General description and C-code","-",3,"Rel-4","S4","2000-09-11","2000-12-11",1,"-","-","-","-","-","26.226, 26.230",null,null,null,null,"2000-12-13","2002-02-28"]
[9078,2237,"      Minimum Performance requirements","-",3,"Rel-4","S4","2000-09-11","2001-03-19",1,"-","-","-","-","-",26.231000000000002,null,null,null,null,"2000-12-13","2002-02-28"]
[9079,1852,"   Deleted - Conformance Test Aspects - Global Text Telephony","GTT_Test",2,"Rel-4","R5,T1","2000-09-21","2000-09-21",1,"-","-","-","-","RP#45 work item abandoned/closed (it was never really started)","-",null,null,"RP-45","PCG-23","2000-09-14","2009-09-15"]
[9080,0,"--- RELEASE 99 ---","-",1,"R99","NP,SP,TP,SMG","2000-01-03","2000-12-29",1,"-","-","-","-","-","-",null,null,null,null,"2006-05-31","2010-02-09"]
[9081,60150,"UMTS Features","-",1,"R99","S1,S2,S4,SMG,N3,N4,RP","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-08-11"]
[9082,60102,"   UMTS_SERVICES","UMTS_SERVICES",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[9083,60103,"   UMTS phase 1","UMTS1",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.1,null,null,null,null,"2009-07-06","2009-07-06"]
[{"$f":"A9084+1","v":9084},60119,"   UMTS Capabilities","UMTS_Capabil",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Requirement for high quality speech in UMTS Phase 1 but not in R99",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[9085,60164,"   Architecture of the GSM-UMTS platform","-",2,"R99","S2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","wid “Architecture overview of the GSM-UMTS System”, “Architecture the GSM-UMTS Platform” and “New Access Network to Core Network (BSS-NSS) interface”","23.002, 23.008, 23.060, 23.101, 23.110",null,null,null,null,"2009-07-16","2009-07-21"]
[9086,60165,"   UMTS Terrestrial Radio Access Network","UTRAN",2,"R99","RP","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.011, 22.038, 22.060, 22.078, 22.100, 22.101, 22.105, 22.115, 22.129, 23.002, 23.060, 24.007, 24.008, 25.101, 25.102, 25.104, 25.105, 25.113, 25.123, 25.133, 25.141, 25.142, 25.201, 25.211, 25.212, 25.213, 25.214, 25.215, 25.221, 25.222, 25.223, 25.224,",null,null,null,null,"2009-07-16","2009-07-21"]
[9087,60083,"   UMTS 1800, UMTS 1900","Rlnlmp19,Rlnlmp18",2,"R99","R2","1999-01-01","1999-12-31",1,"-","-","-","-","-","25.307 CR#0002, 0003 Inclusion of release independent RF related information",null,null,null,null,"2009-07-30","2010-02-09"]
[9088,60149,"   Mandatory speech codec for narrowband telephony service","Mandatory_Speech_Codec,AMR-NB,AMR",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","Define the default speech codec for UMTS (both for FDD and TDD). Definition limited to selection of one codec among several existing ones/proposed codecs: GSM AMR, IS127 EVRC, ITU G.729 and MPEG-4 speech codec.","04.08, 05.01, 05.02, 05.03, 05.05, 05.08, 05.09, 05.09, 05.50, 08.60, 08.61, 11.21, 26.071, 26.073, 26.074, 26.090, 26.091, 26.092, 26.093, 26.094, 26.101, 26.102, 26.103, 26.104, 26.975",null,null,null,null,"2009-07-16","2009-08-11"]
[9089,60055,"   Codec for low bitrate multimedia telephony service","Low_bit_rate_codec_for_MM_Tel.,H.324M",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","-","26.104, 26.110, 26.111, 26.911, 26.912, 26.915",null,null,null,null,"2009-07-16","2009-08-11"]
[9090,60109,"   3G Audio-Visual Terminal characteristics","WI5TAC,3G-AVT,Terminal_Acoustic_Characteristics",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99129","-","-","-","-","26.131, 26.132",null,null,null,null,"2009-07-16","2009-08-11"]
[9091,60104,"   Updates_for_UMTS","Updates_for_UMTS",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","24.022, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[9092,60124,"   UMTS","UMTS",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.060, 29.061",null,null,null,null,"2009-07-08","2009-07-06"]
[9093,60151,"UMTS and GSM Features","-",1,"R99","S1,S2,SMG,T2,N1,N2,N3,N4,R2,R3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[9094,60147,"   Multimedia Messaging Service","MMS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","MMS allows users to send/receive messages e.g. almost unlimited text length, images, audio and video clips and new content types. R99 only includes the concept. MMS stage 3 is not included in 23.140. Rel-4 adds detailed architecture and protocols.","22.140, 23.040, 23.140",null,null,null,null,"2009-07-16","2009-07-21"]
[9095,60121,"   Location Services","LCS",2,"R99","S1,S2,S3,SMG1,SMG2,SMG12,N1,N2,N4,R2,R3","1999-01-01","1999-12-31",1,"SP-99327","-","-","-","LCS provide ability to localize a terminal","02.07, 03.71, 04.31, 04.35, 04.71, 05.05, 08.08, 08.31, 08.71, 09.31, 22.071, 23.002, 23.003, 23.007, 23.008, 23.016, 23.018, 23.032, 23.171, 24.007, 24.008, 24.030, 24.080, 25.305, 25.306, 25.331, 25.413, 25.423, 29.002, 29.010",null,null,null,null,"2009-07-16","2011-08-06"]
[9096,60118,"   Customised Application for Mobile network Enhanced Logic Phase 3","CAMEL3",2,"R99","S1,S2,N2,N4","1999-01-01","1999-12-31",1,"SP-99368","-","-","-","CAMEL is a network feature providing mechanisms to support services of operators which are not covered by standardised services, even when roaming outside the HPLMN.","22.101, 23.008, 23.012, 23.016, 23.018, 23.060, 23.072, 23.078, 23.079, 23.082, 23.093, 29.002, 29.078",null,null,null,null,"2009-07-16","2009-07-21"]
[9097,60218,"      Global view","-",3,"R99","S1,S2,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.078, 23.078, 29.078",null,null,null,null,"2009-07-16","2009-07-21"]
[9098,60318,"      Multiple Subscriber Profile (MSP) based on CAMEL phase 3","-",3,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","MSP is an optional service enabling mobile subscribers to have several profiles associated with a single IMSI, with each profile being a subscription option. Each profile may be used for mobile originated and mobile terminated calls.","22.097 (Advanced Addressing)",null,null,null,null,"2009-07-16","2009-07-21"]
[9099,60038,"   Short Message Service enhancements / Enhanced Messaging Service (EMS)","EMS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","SMS for 3G terminals compatible with GSM SMS. Added Enhanced Messaging Service (EMS) allowing small pictures, sounds, animations to be transferred via SMS.","23.038, 23.039, 23.040, 23.042",null,null,null,null,"2009-07-16","2009-07-21"]
[9100,60122,"   Mobile Station Execution Environment","MExE",2,"R99","S1,SMG1,T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","MExE provides a standardized MS execution environment and ability to negotiate its supported capabilities with a MExE SP. R99 enhances SIM MExE certificate management, security clarifications, QoS and defines two MExE classmarks WAP/Personal-Java based.","02.57, 22.057, 22.101, 23.057",null,null,null,null,"2009-07-16","2009-07-21"]
[9101,60123,"   MS_Classmark","MS_Classmark",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","MExE classmark identifies a category of MExE UE supporting MExE functionality with a minimum level of processing, memory, display, and interactive capabilities. Several MExE classmarks may be defined. ",24.007999999999999,null,null,null,null,"2009-07-08","2009-07-07"]
[9102,60057,"   MultiCall","Multicall",2,"R99","S1,N1,N2,N4","1999-01-01","1999-12-31",1,"NP-000348","-","-","-","Multicall allows several simultaneous CS calls with dedicated bearers of independent traffic and performance characteristics. R99 Multicall was defined as a supplementary service limited to one CS bearer to be used for speech at any time.","22.030, 22.083, 22.087, 23.008, 23.009, 23.016, 23.018, 23.108, 23.135, 24.008, 24.080, 24.135, 29.002, 29.010",null,null,null,null,"2009-07-16","2009-07-21"]
[9103,60058,"      Stage 1 for Multicall","-",3,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.030, 22.083, 22.087",null,null,null,null,"2009-07-30","2010-02-09"]
[9104,60105,"   Virtual Home Environment","VHE",2,"R99","S1,SMG1,S2","1999-01-01","1999-12-31",1,"-","-","-","-","Information exists in SP#5-8 reports & in SP-99416,SP-000095,SP 000155. OSA allows service development by operators and 3rd parties by making use of network functionality through open, standardised, secure, extensible and scalable interfaces. ","02.01, 22.105, 22.121,23.127",null,null,null,null,"2009-07-06","2009-07-06"]
[9105,60067,"   Open Service Access","OSA",2,"R99","S1,S2,N5","1999-01-01","1999-12-31",1,"-","-","-","-","Open Service Architecture became in later Releases Open Service Access. Produced by Parlay, ETSI SPAN (TISPAN), 3GPP SA1 (Stage 1), SA2 (Stage 2) and CN5 (Stage 3), resulting in a single set of standard OSA APIs for the whole development community.","22.121, 23.127, 29.198, 29.998",null,null,null,null,"2009-07-06","2009-07-06"]
[9106,60091,"   Super Charger mechanism for signalling traffic associated with mobility","Super_Charger",2,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","Super Charger reduces mobility management cost by reducing the volume of location update signalling. It changes subscriber data management associated with inter-VLR and SGSN location updates. It also applies to packet services (SGSN replaces VLR and ","21.905, 23.007, 23.008, 23.012, 23.016, 23.018, 23.040, 23.060, 23.116, 23.912, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[9107,60039,"   Follow_Me service","Follow_Me",2,"R99","S1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","Follow Me enables a mobile subscriber A to manipulate the Follow Me data of a party B in such a way that - under certain conditions - subsequent calls directed to party B will be forwarded to subscriber A. It is PLMN-specific and control based on USSD","21.905, 22.004, 22.030, 22.082, 22.090, 22.094, 23.090, 24.090, 22.094, 23.011, 23.015, 23.082, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[9108,60093,"   Wide area network Synchronization and object exchange","SYNC",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Allows data stored in ME/USIM to be synchronized with the outside world. TS 27.103 defines protocols based upon IrMC level 4 and will evaluate new technologies (XML) for inclusion. From Rel-4 IrMC was replaced by SyncML in 27.103. ","27.103, 27.903",null,null,null,null,"2009-07-16","2009-07-06"]
[9109,60145,"   R99 Terminal Interfaces","-",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-20"]
[9110,60166,"      AT commands for 3GPP","-",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","AT commands to control a 3G ME via an external Terminal Equipment (TE), fully compatible with GSM AT commands. R99 adds new AT commands e.g. to control Advanced Speech Call Items (ASCI) services.","27.005, 27.007",null,null,null,null,"2009-07-16","2009-07-20"]
[9111,60167,"      Physical interfaces","-",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Conclusion: 3GPP should not produce any technical specification for terminal interfaces other than radio interface and USIM interface. SDOs could develop own optional physical connector specification based on market requirements",27.901,null,null,null,null,"2009-07-16","2009-07-20"]
[9112,60168,"      Multiplexer","MUXMS-TE",3,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Multiplexing protocol allowing a number of simultaneous sessions between a MS and a terminal¦used to send any data (voice, SMS, USSD, fax etc.). 27.010 describes the protocol, but not the commands or data transported with it.",27.01,null,null,null,null,"2009-07-16","2009-07-20"]
[9113,60169,"   Bearer Services","-",2,"R99","S1,T2,N1,N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-20"]
[9114,60012,"      Circuit Switched Bearer Services","Circuit_switched_Bearer_Services",3,"R99","S1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported","22.002, 23.910, 27.001, 29.007",null,null,null,null,"2009-07-16","2009-07-20"]
[9115,60021,"         Stage 1 for Circuit Switched Bearer Services","CS_Bearerss_in_UMTS",4,"R99","S1","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","CS and real-time data services provided for interworking with PSTN/ISDN so that user is unaware of access network used (UMTS, GSM or handover between ANs). Transparent(constant delay) & non-transparent(zero error with flow control) services are supported",22.001999999999999,null,null,null,null,"2009-07-16","2009-07-20"]
[9116,60019,"         CS_Bearers","CS_Bearers",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.007000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[9117,60020,"         CS_Bearerss","CS_Bearerss",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.21, 23.910, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[9118,60022,"         CS_Data","CS_Data",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.001, 27.002, 27.003, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[9119,60023,"         CS_Data_Bearers","CS_Data_Bearers",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.910, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[9120,60024,"         Deleted - CN3 poart of Circuit Switched Bearer Services","CSBS",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","23.910, 27.001, 29.007",null,null,"NP-06",null,"2009-07-30","2010-02-09"]
[9121,60040,"      Frame Tunnelling Mode","FTM",3,"R99","T2,N1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","FTM is a type of async non-transparent CS bearer service (22.002). Generic term for HDLC and HDLC-related transmission protocols. Converts async non-transp data stream towards mobile side & sync data stream using X.31 flag stuffing on fixed network side.","22.002, 27.001, 27.007, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[9122,60171,"      Access to ISPs and Intranets – Wireless/Remote access to LANs","InterworkingwithPDN(DHCP)",3,"R99","N3","1999-01-01","1999-12-31",1,"N3-99069","-","-","-","Access to an Intranet or ISP by running DHCP between the TE and a server in the Intranet/ISP domain. ",29.061,null,null,null,null,"2009-07-16","2009-07-06"]
[9123,60070,"      PHS Internet Access Forum Specification","PIAFS",3,"R99","S1,N3","1999-01-01","1999-12-31",1,"NP-99285","-","-","-","PIAFS is one type of CS bearer data service (22.002). It refers to async CS tx protocol over ISDN 64 kbit/s unrestricted digital line. Facilitates interworking between PHS-MS and UMTS-UE & UMTS-UE and existing PIAFS TA (Terminal Adapter).","22.002, 27.001, 27.007, 29.007",null,null,null,null,"2009-07-16","2009-07-06"]
[9124,60170,"         Personal Handyphone System Internet Access Forum Standard (PIAFS)","-",4,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","PIAFS was originally standardised by the PHS Internet Access Forum in Japan. More information can be found at: http://www.infopro.or.jp/piaf",22.001999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[9125,60092,"         Support_of_PIAFS_in_UMTS","Support_of_PIAFS_in_UMTS",4,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.001, 27.007, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[9126,60172,"   Universal Integrated Circuit Card (UICC) and Universal Subscriber Identity Module (USIM)","UICC,USIM",2,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","For 3G, GSM 11.11 was divided into two parts: a platform comprised of basic physical, electrical and logical specification (31.101) and an application specification (31.102)","-",null,null,null,null,"2009-07-16","2009-07-21"]
[9127,60173,"      UICC / Terminal interface; Physical and logical characteristics","UICC",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","Defines a generic Terminal/Integrated Circuit Card (ICC) interface. Is independent of 3G USIM application => platform for any IC card application. Ensures interoperability between ICC and terminal independently of manufacturer, card issuer or operator.","31.101 (Since 10/2000, ETSI EP SCP is responsible for the generic Terminal/Integrated Circuit Card (ICC) interface 102 221)",null,null,null,null,"2009-07-16","2009-07-21"]
[9128,60142,"      UICC/(U)SIM enhancements and interworking","UICC99",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Acronym changed from UICC1","31.102, 31.900",null,null,null,null,"2009-07-08","2015-03-24"]
[9129,60174,"      Characteristics of the USIM application","USIM",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","Defines Universal Subscriber Identity Module (USIM) application for 3G telecom network operation & resides on UICC, an IC card specified in 31.101. UICC can be used as a multi-application card: several USIMs and/or other applications can co-exist",31.102,null,null,null,null,"2009-07-16","2009-07-21"]
[9130,60114,"      UICC Application Identifiers","AID,Application_Identifiers",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Defines and administers Application IDentifiers (AID) for UICC. AID is used to address an application in the card. Consists of Registered application provider ID (RID) & Proprietary application ID exception (PIX - according to ISO/IEC 7816-5).","21.111, 31.110",null,null,null,null,"2009-07-16","2009-07-21"]
[9131,60139,"      SIM Application Toolkit","SAT",3,"R99","S1,T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","11.14, 22.030, 22.100, 22.101",null,null,null,null,"2009-07-08","2009-07-06"]
[9132,60141,"      USIM Application Toolkit","USAT",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Defines UICC - ME interface, and mandatory ME procedures for USAT. Based on GSM 11.14 (SIM Application Toolkit). Commands and procedures defined in USIM and 3G Terminal for using USAT. Service and security requirements defined in 22.100 and 22.101.",31.111000000000001,null,null,null,null,"2009-07-16","2009-07-21"]
[9133,60175,"      Bearer Independent Protocol for SAT applications to exchange data over the GSM network","BIP",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines at SIM-ME interface a basic protocol allowing SIM Toolkit applications to determine available bearers and to exchange data by selecting using the most appropriate bearer available (CS data, GPRS, SMS, Unstructured Supplementary Service Data (USSD)","03.48, 11.10, 11.14",null,null,null,null,"2009-07-16","2009-07-21"]
[9134,60176,"      Administrative commands and functions for IC cards","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines function and syntax of administrative commands for telecommunication IC Card used during installation, activation and de-activation of applications. Compliant to ISO/IEC 7816 series. Handed over to ETSI Project Smart Card Platform (SCP) in 2000.","ETSI 102 222",null,null,null,null,"2009-07-16","2009-07-21"]
[9135,60177,"      USIM and UICC requirements","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99084","-","-","-","High level requirements for 3GPP IC card and its interface to 3GPP terminal (USIM&UICC reqs). Service&security reqs in 322.01,22.00. USIM is a 3GPP application on an IC card. Inter-operates with 3GPP terminals and provides access to 3GPP services",21.111000000000001,null,null,null,null,"2009-07-16","2009-07-21"]
[9136,60140,"      SIM_API","SIM_API",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","-",3.19,null,null,null,null,"2009-07-08","2009-07-06"]
[9137,60086,"      SIM_toolkit_API","SIM_toolkit",3,"R99","SMG9,T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.48, 11.11, 11.14",null,null,null,null,"2009-07-06","2009-07-06"]
[9138,60087,"      Deleted - 1.8 Volt SIM ME interface","SMIME_1.8V",3,"R99","SMG9","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI",11.18,null,null,"TP-06",null,"2009-07-30","2010-02-09"]
[9139,60178,"   USIM/UICC Testing","-",2,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[9140,60179,"      Terminal tests for the UICC Interface","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Test spec for the interface between UICC and terminal (originally based GSM 11.10-1 clause 27). Ensures UICC - terminal interoperability independently of manufacturer, card issuer or operator. Tests for applications residing on UICC are in 31.121",31.12,null,null,null,null,"2009-07-16","2009-07-21"]
[9141,60180,"      USIM application test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"TP-99184","-","-","-","Application test spec originally based on GSM 11.17. Aspects related to UICC administrative management phase are not defined. Any internal technical realisation of either UICC or terminal is only specified where these are reflected over the interface.",31.120999999999999,null,null,null,null,"2009-07-16","2009-07-21"]
[9142,60181,"      USIM conformance test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","Conformance Test specification for UICC defined in 31.101 with USIM defined in 31.102.",31.122,null,null,null,null,"2009-07-16","2009-07-21"]
[9143,60182,"      SIM toolkit test specification","-",3,"R99","T3","1999-01-01","1999-12-31",1,"-","-","-","-","SIM Application Toolkit (SAT) has major impact on ME design and enhances SIM/ME interface. Contains tests for SIM/ME interface optional features (no network related signalling issues involved). Doesn't form basis for any type approval or regulatory tests.","11.10-4",null,null,null,null,"2009-07-16","2009-07-21"]
[9144,60137,"   Security for UMTS and GSM Features","Security",2,"R99","S3,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.09, 03.20, 21.133, 22.022, 23.003, 23.007, 23.008, 23.012, 23.018, 24.007, 24.008, 24.010, 24.011, 29.002, 29.060, New (33.102, 33.103, 33.105, 33.107, 35.201)",null,null,null,null,"2009-07-16","2009-07-21"]
[9145,60183,"      Fraud Information Gathering Service (for connection-orientated services)","FIGS",3,"R99","S3","1999-01-01","1999-12-31",1,"-","-","-","-","HPLMN can monitor its subscribers in VPLMN, which collects info on a defined set of monitored subscribers activities & sends it to HPLMN, which can perform service limitation control eg Operator Determined Barring (ODB) and IST to limit financial exposure","New 22.031, 23.031",null,null,null,null,"2009-07-16","2009-07-21"]
[9146,60085,"      Immediate Service Termination / SECurity Immediate Service Termination","IST,SECIST",3,"R99","S3,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","HPLMN can terminate all activities of its subscriber in VPLMN, if decides (based on info via eg FIGS) that a roaming subscriber is behaving in fraudulent/suspicious way. HPLMN can terminate all subscriber activities including calls in progress.","03.35, 22.032, 23.008, 23.016, 23.035, 29.002",null,null,null,null,"2009-07-08","2009-07-21"]
[9147,60018,"      Core_Network_Security","Core_Network_Security",3,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.001999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[{"$f":"A9148+1","v":9148},60152,"GSM Features","-",1,"R99","S1,S2,SMG,T2,N1,N2,N3,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2009-07-21"]
[9149,60184,"   Dual Transfer Mode within GSM and GPRS","DTM",2,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","2-99-1780 (2-99-H80 from SMG2#32) WID on “BSS co-ordination of Radio Resource allocation for class A GPRS services - GSM Radio Access (R99)”","03.55, 03.64, 04.18, 04.60, 05.01, 05.02, 05.08, 08.08, 23.060, 24.007, 24.008",null,null,null,null,"2009-07-16","2009-07-21"]
[9150,60013,"      Class A Dual Transfer Mode","Class_A_Dual_Transfer_Mode_(DTM)",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.0999999999999996,null,null,null,null,"2009-07-06","2009-07-06"]
[9151,60027,"      Dual Transfer Mode","-",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.55, 03.64, 04.18, 05.01, 05.02, 05.08, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[9152,60185,"   General Packet Radio Service enahancements","GPRSenhancements",2,"R99","S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2","1999-01-01","1999-12-31",1,"-","-","-","-","GPRS was introduced in Release 97. Release 99 brings a number of essential corrections e.g. on Downlink Power Control, Timing Advance procedure, Cell reselection delay time, PBCCH scheduling, PTCCH mapping, etc. ","05.02, 05.05, 05.08, 05.10, 05.50, 11.21, 23.064, 24.008, 24.060",null,null,null,null,"2009-07-16","2010-02-09"]
[9153,60132,"      General Packet Radio Service","GPRS",3,"R99","S1,S2,SMG1,SMG2,SMG7,N1,N2,N3,N4,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.60, 03.22, 03.64, 04.18, 04.60, 04.64, 04.65, 05.01, 05.02, 05.05, 05.08, 05.10, 08.08, 08.18, 11.10-1, 11.21, 22.041, 22.060, 23.003, 23.007, 23.060, 23.107, 23.122, 24.007, 24.008, 27.007, 27.060, 29.002, 29.016, 29.018, 29.060, 29.061",null,null,null,null,"2009-07-07","2009-07-06"]
[9154,60133,"      GPRS2","GPRS2",3,"R99","SMG1,N2","1999-01-01","1999-12-31",1,"-","-","-","-","Introduction of EGPRS (S1) + Introduction of Reserved Service Labels in the APN (N2)","02.60, 23.003",null,null,null,null,"2009-07-09","2009-07-06"]
[9155,60134,"      GPRS Tunnelling Protocol enhancement","GTP_enhancement",3,"R99","N4,N2","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.003, 23.008, 29.060",null,null,null,null,"2009-07-07","2009-07-06"]
[9156,60186,"   Enhanced Data rates for GSM Evolution - Phase 1","EDGE-Phase1",2,"R99","SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2","1999-01-01","1999-12-31",1,"-","-","-","-","EDGE is independent of the frequency bands, so it can be deployed e.g. in 900 and 1900 MHz bands. The new physical layer based on 8-PSK modulation is introduced and EGPRS and ECSD facilitate the new modulation in single and multi slot constellation.","10.59, 02.34, 02.60, 03.30, 05.10, 05.50, 11.26",null,null,null,null,"2009-07-16","2010-02-09"]
[9157,60030,"      Enhanced Data rates for GSM Evolution","EDGE",3,"R99","SMG2,SMG1,SMG3,SMG4,SMG7,SMG9,SMG10,N1,N3,T2","1999-01-01","1999-12-31",1,"-","-","-","-","WID in SMG2 331/97, SMG 1147/97, SMG 1148/97","02.34, 03.10, 03.20, 03.64, 04.03, 04.04, 04.06, 04.08, 04.18, 04.21, 04.22, 04.60, 04.64, 05.01, 05.02, 05.03, 05.04, 05.05, 05.08, 05.10, 05.50, 07.01, 07.02, 07.03, 08.08, 08.20, 08.58, 08.60, 09.07, 09.18, 11.10-1, 11.11, 11.21, 11.26, 23.034, 24.008,",null,null,null,null,"2009-07-06","2009-07-06"]
[9158,60034,"      EDGE-Layer1","EDGE-Layer1",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","WID in SMG2 331/97, SMG 1147/97, SMG 1148/97","05.05, 05.10, 05.50",null,null,null,null,"2009-07-06","2009-07-06"]
[9159,60135,"      High Speed Circuit Switched Data","HSCSD",3,"R99","SMG1,SMG2,SMG7","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","02.34, 04.18, 11.10-1",null,null,null,null,"2009-07-08","2009-07-06"]
[9160,60029,"      Enhanced Circuit Switched Data - Phase 1","ECSD",3,"R99","S1,SMG","1999-01-01","1999-12-31",1,"-","-","-","-","ECSD supports both transparent and non-transparent services, up to 64 kbit/s and 57.6 kbit/s respectively. See Tdoc SMG2 670/99 “ECSD Concept Evaluation” for more info","05.02, 08.58, 22.034",null,null,null,null,"2009-07-06","2009-07-06"]
[9161,60032,"      EDGE-Enhanced Circuit Switched Data","EDGE-ECSD",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.03,null,null,null,null,"2009-07-06","2009-07-06"]
[9162,60035,"      Enhanced GPRS - Phase 1","EGPRS",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.07, 03.64, 04.14, 04.18, 04.60, 05.05, 05.08, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[9163,60033,"      EDGE-EGPRS","EDGE-EGPRS",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","05.03, 05.05, 05.08",null,null,null,null,"2009-07-06","2009-07-06"]
[9164,60069,"      Packet Flow Context (PFC) ","PFC",3,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",4.18,null,null,null,null,"2009-07-06","2009-07-06"]
[9165,60031,"      Support for EGPRS in ANSI-136 networks and EDGE COMPACT","EDGE-Compact",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","Support for EGPRS in ANSI-136 networks” and “EDGE Compact” (for ANSI-136 networks only). COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","03.22, 03.30, 03.64, 05.01, 05.02, 05.03, 05.05, 05.08, 05.10",null,null,null,null,"2009-07-06","2009-07-06"]
[9166,60036,"      EGPRS COMPACT","EGPRS-Compact",3,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","04.18, 05.02",null,null,null,null,"2009-07-06","2009-07-06"]
[9167,60136,"      COMPACT","COMPACT",3,"R99","SMG,N1","1999-01-01","1999-12-31",1,"-","-","-","-","COMPACT = Deployment of servicES in CP-150spectrum below 1 MHz","03.22, 04.18, 04.60, 05.08, 23.122, 24.008",null,null,null,null,"2009-07-08","2009-07-06"]
[9168,60047,"   GSM_400","GSM_400",2,"R99","SMG2,SMG7,T2","1999-01-01","1999-12-31",1,"-","-","-","-","GSM in the 400 MHz bands allows to deploy GSM within frequency bands in the range 450 to 500 MHz, previously used for analogue cellular systems. See Tdoc SMG2 190/99 and 595/99 for further info.","02.17, 03.22, 03.30, 04.04, 04.18, 04.60, 05.01, 05.02, 05.05, 05.08, 05.10, 05.50, 08.18, 08.58, 11.21, 24.008, 27.007",null,null,null,null,"2009-07-06","2009-07-06"]
[9169,60048,"   GSM_450","GSM_450",2,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.22, 03.30, 05.01, 05.05, 05.08",null,null,null,null,"2009-07-06","2009-07-06"]
[9170,60131,"   GSM_700","GSM_700",2,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",5.05,null,null,null,null,"2009-07-06","2009-07-06"]
[9171,60041,"   Deleted - GERAN","GERAN",2,"R99","SMG2,S2","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","G2: 04.18 CR#A248 , 04.60 CR#B090 ",null,null,"SP-06",null,"2009-07-30","2010-02-09"]
[9172,60153,"GSM Features transposed to UMTS","-",1,"R99","S1,S3,T2,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-02-09"]
[9173,60187,"   Cell Broadcast Service","CBS",2,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure. Applicability of the Cell Broadcast Service (as defined for GSM network) to 3G networks",23.041,null,null,null,null,"2009-07-16","2010-02-09"]
[9174,60188,"   GSM mobile number portability euro MNP / North American MNP","MNP",2,"R99","S1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","R98 MNP: mobile subscriber ability to change PLMN operator within the same country whilst retaining its original MS ISDN number (MSISDN). IMSI is changed, only MSISDN is kept. R99 adds requirements for North American Service Provider Number Portability.",22.065999999999999,null,null,null,null,"2009-07-16","2010-02-09"]
[9175,60144,"      Mobile Number Portability","-",3,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.018, 23.066, 29.002",null,null,null,null,"2009-07-08","2009-07-06"]
[9176,60189,"   Automatic establishment of roaming relations","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","Telecom Italia","enrico.scarrone@telecomitalia.it","framework for commercial and technical interworking between UMTS Home Environments and Serving Networks who have no direct prior commercial agreements with each other.","22.101, 22.971",null,null,null,null,"2009-07-16","2010-08-31"]
[9177,60190,"   Advanced addressing","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.101, 22.75U, 22.975",null,null,null,null,"2009-07-16","2010-02-09"]
[9178,60191,"   UMTS numbering, addressing and identities","-",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Also new requirements for Single and Multiple Numbering scheme was added (CR#20 and 21). Deleted the term International Mobile User Identifier (IMUI) and changed IMSI (International Mobile Station Identifier=>International Mobile Subscriber Identity.",22.100999999999999,null,null,null,null,"2009-07-16","2010-02-09"]
[9179,60192,"   Lawful Interception for GSM Features transposed to UMTS","LI",2,"R99","S3","1999-01-01","1999-12-31",1,"-","-","-","-","Defines an interception system in UMTS that supports a number of regional interception regulations. Regional interception requirements shall be met in using specific (regional) mediation functions allowing only required information to be transported.","New 33.106, 33.107",null,null,null,null,"2009-07-16","2009-07-06"]
[9180,60154,"Charging","-",1,"R99","S1,S5","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-02-09"]
[9181,60011,"   R99 Charging","Charging",2,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.115, 23.121",null,null,null,null,"2009-07-06","2009-07-06"]
[9182,60215,"   R99 OAM Charging Management","OAMCH,CH",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99271","-","-","-","-","32.005, 32.015",null,null,null,null,"2009-07-06","2009-08-11"]
[9183,60155,"Operations, Administration, Maintenance and Provisioning (OAM&P)","OAM1999",1,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-","-",null,null,null,null,"2009-07-06","2010-02-09"]
[9184,60073,"   OAM Principles and High-level Requirements","PR,Princs_&_Reqs_(PR)",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-",32.100999999999999,null,null,null,null,"2009-07-06","2009-08-11"]
[9185,60062,"   OAM Architecture","OAMAR,AR,Telecom_Management_Arch_(AR)",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99581","-","-","-","-","32.101, 32.102",null,null,null,null,"2009-07-06","2009-08-11"]
[9186,60014,"   OAM Configuration Management","OAMCM,CM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99273","-","-","-","-","32.106, 32.106-1, 32.106-2, 32.106-3, 32.106-4, 32.106-5, 32.106-6, 32.106-7, 32.106-8",null,null,null,null,"2009-07-06","2009-08-11"]
[9187,60063,"   OAM Fault Management","OAMFM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99272","-","-","-","-","32.111, 32.111-1, 32.111-2, 32.111-3, 32.111-4",null,null,null,null,"2009-07-06","2009-08-11"]
[9188,60064,"   OAM Performance Management","OAMPM,PM",2,"R99","S5","1999-01-01","1999-12-31",1,"SP-99274","-","-","-","-","12.04, 32.104",null,null,null,null,"2009-07-06","2009-08-11"]
[9189,60106,"Vocabulary","Vocabulary",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",21.905000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[9190,60037,"Emergency","Emergency",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[9191,60049,"GSM General Bearer Services (GBS) and interworking scenarios support in UMTS","GSM_to_UMTS_Evol",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","UMTS shall support GSM General Bearer Services (GBS) and interworking scenarios as specified in 02.02",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[9192,60043,"GPRS_Mobile_IP_interworking","GPRS_Mobile_IP_interworking",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[9193,60046,"GSM/UMTS interworking","2G3Ginterworking",1,"R99","N1,N2,N4,R3,S1,SMG","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.22, 04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 08.18, 08.58, 09.08, 22.011, 23.003, 23.009, 23.014, 23.034, 23.122, 24.007, 24.008, 24.011, 24.080, 29.108",null,null,null,null,"2009-07-06","2009-07-06"]
[9194,60050,"Handover","Handover",1,"R99","S1,SMG2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.18, 08.08, 08.58, 22.129, 23.009, 29.002, 29.010",null,null,null,null,"2009-07-06","2009-07-06"]
[9195,60120,"2G3Ghandover","2G3Ghandover",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-","04.18, 04.60, 05.02, 05.08, 05.10, 08.08, 29.010",null,null,null,null,"2009-07-06","2009-07-06"]
[9196,60088,"Service Provider Name Indication","SPANME",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Service Provider Name Indication included in R98 (02.07) was not carried into R99 (22.101), but is in the SIM/USIM specification for R99",22.100999999999999,null,null,null,null,"2009-07-06","2009-07-06"]
[9197,60026,"Data & Data_CleanUp","Data,Data_CleanUp",1,"R99","SMG1","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.01, 02.02, 02.04, 02.34",null,null,null,null,"2009-07-06","2009-07-06"]
[9198,60125,"Unstructured Supplementary Service Data (USSD)","USSD",1,"R99","SMG1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","02.04, 02.90, 23.090, 29.002",null,null,null,null,"2009-07-07","2009-07-07"]
[9199,60126,"Man-Machine Interface (MMI) of the User Equipment (UE)","MMI",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Data services streamlining + Support for Anonymous Call Rejection",22.03,null,null,null,null,"2009-07-08","2009-07-07"]
[9200,60127,"Network Identity and Timezone (NITZ)","NITZ",1,"R99","SMG1,SMG3","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.42, 04.08",null,null,null,null,"2009-07-08","2009-07-07"]
[9201,60128,"Deleted - Operator Determined Barring for Packet Oriented Services","ODB_Enh.",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Remove ODB for Packet Oriented Services from R99",22.041,null,null,"SP-69",null,"2009-07-09","2009-07-07"]
[9202,60068,"Packet Flow Management","Packet_Flow_Management",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",8.18,null,null,null,null,"2009-07-06","2009-07-06"]
[9203,60044,"GPRS_Point-To-Multipoint Group call ","GPRS_PTMG",1,"R99","SMG1","1999-01-01","1999-12-31",1,"-","-","-","-","-",2.6,null,null,null,null,"2009-07-06","2009-07-06"]
[9204,60156,"Call Forwarding","-",1,"R99","SMG1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-22","2010-02-09"]
[9205,60010,"   Call Forwarding enhancements","CF_enhancements",2,"R99","N4,N2","1999-01-01","1999-12-31",1,"-","-","-","-","No additional features for R99.","23.078, 23.079, 23.082, 29.002, 29.078",null,null,null,null,"2009-07-06","2009-07-06"]
[9206,60116,"   Call_Forwarding","Call_Forwarding",2,"R99","SMG1,N2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.82, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[9207,60117,"   Call_Forwarding_Enhancements","Call_Forwarding_Enhancements",2,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",23.082000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[9208,60157,"Quality of Service ","-",1,"R99","S2,T2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","WID SMG 98-0781 End To End UMTS QoS Management","-",null,null,null,null,"2009-07-16","2010-02-09"]
[9209,60076,"   End-to-end UMTS Quality of Service management","QoS",2,"R99","S2,T2,N1,N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","WID SMG 98-0781 End To End UMTS QoS Management","23.107, 23.907, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[9210,60130,"   End-to-end QoS for PS Domain including IMS","E2EQoS99",2,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","Acronym changed from E2EQos","23.060, 23.170",null,null,null,null,"2009-07-08","2015-03-24"]
[9211,60045,"   GPRS-enhanced_QoS","GPRS-enhanced_QoS",2,"R99","T2","1999-01-01","1999-12-31",1,"-","-","-","-","AT-commands for Enhanced QoS Support management",27.007000000000001,null,null,null,null,"2009-07-06","2009-07-06"]
[{"$f":"A9212+1","v":9212},60077,"   QoS_enhancements","QoS_enhancements",2,"R99","N2,N1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.008, 23.016, 24.008, 29.002, 29.060",null,null,null,null,"2009-07-06","2009-07-06"]
[9213,60129,"Support of Localised Service Area","SoLSA",1,"R99","SMG2,SMG3,SMG7,N2","1999-01-01","1999-12-31",1,"-","-","-","-","Mechanism which can be used as a platform for providing special tariffs and/or special set of service features for certain subscribers within a regionally restricted area or areas. No additional features for R99.","04.08, 04.18, 08.08, 11.10-1, 29.002",null,null,null,null,"2009-07-07","2009-07-06"]
[9214,60100,"Transcoder_location","Transcoder_location",1,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","UE location identification: background information and associated primitives 2. Transcoder location at the core network and source depending coding belonging to the non-access stratum.",23.11,null,null,null,null,"2009-07-06","2009-07-06"]
[9215,60113,"Antenna_test_methods","Antenna_test_methods",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",3.3,null,null,null,null,"2009-07-06","2009-07-06"]
[9216,60107,"WBAMR / high quality speech in UMTS Phase 1 but not in R99","WBAMR",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","Add requirement for high quality speech in UMTS Phase 1 but not in R99",22.105,null,null,null,null,"2009-07-06","2009-07-06"]
[9217,60138,"Codec","-",1,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-08-11"]
[9218,60015,"   Codecs for Multimedia Telephony Service","Codec_for_Multimedia_Telephony",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-08-11"]
[9219,60415,"      Codecs for Multimedia Telephony Service","Multimedia_Codec",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9220,60515,"      Codecs for Multimedia Telephony Service","CSM",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9221,60615,"      Codecs for Multimedia Telephony Service","WI2MMC",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9222,60715,"      Codecs for Multimedia Telephony Service","Codec(s)_for_CS_MM_Tel._Serv",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9223,60815,"      Codecs for Multimedia Telephony Service","Codec(s)_for_MM_Tel_Service",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9224,60915,"      Codecs for Multimedia Telephony Service","-",3,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","-","26.911, 26.104, 26.111",null,null,null,null,"2009-07-06","2009-08-11"]
[9225,60078,"   QoS for Speech and Multimedia Codec","QoS_for_Speech_&_MM_Codecs_/_AMR",2,"R99","S4","1999-01-01","1999-12-31",1,"SP-99060","-","-","-","-","26.102, 26.912",null,null,null,null,"2009-07-06","2009-08-11"]
[9226,60099,"   Tandem Free Operation - Adaptive Multi-Rate codec types","TFOAMR",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","UMTS_AMR2 is default Codec Type in R99 dual_mode terminals",26.103000000000002,null,null,null,null,"2009-07-06","2009-08-11"]
[9227,60112,"   Noise Suppression for AMR","AMRNS",2,"R99","S4","1999-01-01","1999-12-31",1,"-","-","-","-","Combination of the AMR speech codec and the Noise Suppression function. TS 06.77 and TR 06.78 only apply to GSM. They apply to UMTS from Rel-4 onwards, when they were converted to TS 26.077 and TR 26.078.","06.77, 06.78",null,null,null,null,"2009-07-06","2009-08-11"]
[9228,60065,"   Out-of-Band Transcoder","OoBT",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","Transcoder handling in the CN at inter-system handover and relocation + Introduction of UMTS AMR","23.009, 24.008",null,null,null,null,"2009-07-06","2009-07-06"]
[9229,60066,"   Out-of-Band Transcoder Control ","OoBTC",2,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","24.008 CR#0572 in NP-020220 was approved under this WI","24.008 CR#0572 in NP-020220",null,null,null,null,"2009-07-30","2010-02-09"]
[9230,60143,"Advanced Speech Call Items enhancements","ASCI",1,"R99","SMG1,SMG2,SMG3,SMG7,SMG9,N1,N4,S1,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","02.30, 02.68, 03.68, 03.69, 04.18, 08.08, 11.10-1, 11.11, 23.067, 23.094, 24.008, 24.067, 27.007, 29.002",null,null,null,null,"2009-07-07","2009-07-06"]
[9231,60009,"Call Control improvements","CC_Related_items",1,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","Minor improvements to 24.007 and 24.008 to increase the number of simultaneous calls/sessions from the present 7: the TI value is increased (NP-99441).","24.007, 24.008",null,null,null,null,"2009-07-06","2009-07-23"]
[9232,60059,"Multimedia","Multimedia",1,"R99","N1,N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","24.008, 27.001, 29.007",null,null,null,null,"2009-07-06","2009-07-06"]
[9233,60089,"Sub-System Number allocation for RANAP, RNSAP","SSN_allocation",1,"R99","N2","1999-01-01","1999-12-31",1,"-","-","-","-","Sub-System Number allocation for Radio Access Network Application Part, Radio Network Subsystem Application Part",23.003,null,null,null,null,"2009-07-06","2009-07-06"]
[9234,60053,"Intranet / ISP access with DHCP end-to-end","ISPaccess",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Access to an Intranet/ISP with DHCP end to end",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[9235,60072,"Point_to_Multipoint_Services","Point_to_Multipoint_Services",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Support for the IP-Multicast protocol",29.061,null,null,null,null,"2009-07-06","2009-07-06"]
[9236,60146,"Facsimile","FAX",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.003, 22.100",null,null,null,null,"2009-07-08","2009-07-06"]
[9237,60081,"Realtime_NT_FAX_in_UMTS","Realtime_NT_FAX_in_UMTS",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","Asynchronous Interface for real-time NT Fax + Introduction of Asynchronous interface for Real-time non-transparent FAX","27.001, 27.003",null,null,null,null,"2009-07-06","2009-07-06"]
[9238,60042,"Gateway Location Register (GLR) - Mobile Application Part (MAP) specification","GLR",1,"R99","N4","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.12,null,null,null,null,"2009-07-06","2009-07-06"]
[9239,60056,"Multiple Subscriber Profile phase 2","MSP2",1,"R99","S1,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","22.097, 23.072, 23.083, 23.084, 23.091, 23.093, 23.097",null,null,null,null,"2009-07-06","2009-07-06"]
[9240,60074,"Prepaging","Prepaging",1,"R99","N2,N4","1999-01-01","1999-12-31",1,"-","-","-","-","-","23.018, 23.082, 29.002",null,null,null,null,"2009-07-06","2009-07-06"]
[9241,60148,"Re-definition of channel quality measure used for AMR link adaptation for Downlink Advanced Receiver Performance (DARP) MS","-",1,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","Re-definition of channel quality measure used for AMR link adaptation for DARP MS",5.09,null,null,null,null,"2009-07-08","2009-07-06"]
[9242,60051,"Harmonized Standard","HS",1,"R99","SMG2","1999-01-01","1999-12-31",1,"-","-","-","-","-",13.21,null,null,null,null,"2009-07-06","2009-07-06"]
[9243,60090,"Streamlining of specifications","Streamlining",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","27.060, 29.061",null,null,null,null,"2009-07-06","2009-07-06"]
[9244,60079,"R99_Service_Clean_up","R99_Service_Clean_up",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","03.10, 27.001, 27.002, 27.003, 27.060, 29.007, 29.061",null,null,null,null,"2009-07-06","2009-07-06"]
[9245,60094,"(Small) Technical Enhancements and Improvements for R99","TEI",1,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[9246,60095,"   TEI_[CS_Data]","TEI_[CS_Data]",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[9247,60096,"   TEI_[GPRS]","TEI_[GPRS]",2,"R99","N3","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-06","2009-07-06"]
[9248,25016,"R99 UE Conformance Testing","TEI_Test",1,"R99","R5,T1","1999-01-01","1999-12-31",1,"-","-","-","-","Specifies Conformance Tests for a 3G UE to be recognised as “3GPP-standard compliant”. A 3GPP-external body, GCF (Global Certification Forum), delivers certificates to prove that a UE has correctly passed tests and is then conform to the 3GPP standard.","34.108, 34.121, 34.122, 34.123-1, 34.123-2, 34.123-3",null,null,null,null,"2009-07-06","2009-07-06"]
[9249,60084,"   Deleted - RTEI","RTEI",2,"R99","T1","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","34.123-1 CR#0650, 0651, 34.123-3 CR#0148, 0149, 0150",null,null,"TP-06",null,"2009-07-30","2010-02-09"]
[9250,60193,"   Common test environments for User Equipment (UE); Conformance testing","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","-",34.107999999999997,null,null,null,null,"2009-07-22","2009-07-22"]
[9251,60194,"   Terminal conformance specification, Radio transmission and reception (FDD)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in FDD mode.",34.121000000000002,null,null,null,null,"2009-07-22","2009-07-22"]
[9252,60195,"   Terminal conformance specification, Radio transmission and reception (TDD)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","measurement procedures for the conformance test of the UE that contain transmitting characteristics, receiving characteristics and performance requirements in addition to requirements for support of RRM (Radio Resource Management) in TDD mode.",34.122,null,null,null,null,"2009-07-22","2009-07-22"]
[9253,60196,"   UE conformance specification; Part 1: Protocol conformance specification","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","TS 34.123, composed of three parts, actually specifies the protocol conformance testing for the 3G UE. Part 1 describes the overall test structure.","34.123-1",null,null,null,null,"2009-07-22","2009-07-22"]
[9254,60197,"   UE conformance specification; Part 2: Implementation Conformance Statement (ICS) specification","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","Part 2 contains the applicability of each test case defined as the “Implementation Conformance Statement (ICS) proforma”, in compliance with the relevant requirements, and in accordance with the relevant guidance given in ISO/IEC 9646-7 and ETS 300 406. ","34.123-2",null,null,null,null,"2009-07-22","2009-07-22"]
[9255,60198,"   UE conformance specification; Part 3: Abstract test suites (ATSs)","-",2,"R99","R5,T1","1999-01-01","1999-01-01",1,"-","-","-","-","Part 3 specifies the protocol conformance testing in TTCN for the 3G UE at the Uu interface. It defines the TTCN test specification and design considerations in Abstract Test Suites based on the test cases specified in prose in part 1. ","34.123-3",null,null,null,null,"2009-07-22","2009-07-22"]
[9256,60028,"Deleted - Dual Tone Multi-Frequency signalling : Support in the whole 3GPP system","DTMF",1,"R99","N1","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","23.014 CR#0004",null,null,"NP-06",null,"2009-07-30","2010-02-09"]
[9257,60052,"Deleted - Intersystem_Change","Intersystem_Change",1,"R99","SMG","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","04.18 CR#A243",null,null,"SMG",null,"2009-07-30","2010-02-09"]
[9258,60054,"Deleted - Long_Forwardedto_Numbers","Long_Forwardedto_Numbers",1,"R99","N2","1999-01-01","1999-12-31",1,"-","-","-","-","-",29.001999999999999,null,null,"NP-06",null,"2009-07-06","2009-07-06"]
[9259,60080,"Deleted - RANimp-FSEarlyUE","RANimp-FSEarlyUE",1,"R99","R3","1999-01-01","1999-12-31",1,"-","-","-","-","No CR or new TS/TR approved under this WI","25.413 CR#0520, 0538, 0565, 0563, 0541, 0540, 0539, 0547",null,null,"RP-06",null,"2009-07-30","2010-02-09"]
[9260,0,"Release 1999 Studies","-",1,"R99","S1,T2","1999-01-01","1999-12-31",1,"-","-","-","-","-","-",null,null,null,null,"2009-07-16","2010-06-14"]
[9261,60061,"Advanced Addressing/Numbering","Numbering",1,"R99","S1","1999-01-01","1999-12-31",1,"-","-","Vodafone","mona.mustapha@vodafone.com ","Study on requirements for numbering and addressing for UMTS",22.975000000000001,null,null,null,null,"2009-07-06","2010-08-31"]
[9262,60161,"Combined GSM and Mobile IP mobility handling in UMTS IP CN","-",1,"R99","S2","1999-01-01","1999-12-31",1,"-","-","-","-","-",23.922999999999998,null,null,null,null,"2009-07-23","2010-02-09"]
[9263,60101,"UE Capabilities Requirements","UCR",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure",21.904,null,null,null,null,"2009-07-06","2009-07-06"]
[9264,60158,"Electrical safety requirements and regulations","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to RAN4 at TSG-T closure. TR summarizes differences between international and national standards relevant to IEC60950 and refers to regulations for conformity assessment due to different regulatory environments in different countries / regions.",34.906999999999996,null,null,null,null,"2009-07-16","2009-07-06"]
[9265,60159,"Specific Absorbtion Rate (SAR) requirements and regulations in different regions","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to RAN4 at TSG-T closure.",34.924999999999997,null,null,null,null,"2009-07-16","2009-07-06"]
[9266,60160,"Multi-mode UE issues","-",1,"R99","T2","1999-01-01","1999-12-31",1,"TP-000022","-","-","-","Moved to CT1 at TSG-T closure. Consequences on roaming capabilities and service availability (e.g. handover) of multi-mode UEs while roaming in various regions with various network configurations. Case studies for each of the possible scenarios in specs","21.810, 21.910",null,null,null,null,"2009-07-16","2009-07-06"]
[9267,60162,"Provision of fax service in GSM and UMTS","-",1,"R99","T2","1999-01-01","1999-12-31",1,"-","-","Ericsson","peter.bleckert@ericsson.com","CP#27: Moved to C1 on closure of T2¦see TP-050062. CP#28: C1->C3",22.945,null,null,null,null,"2009-07-23","2010-02-09"]
[9268,60163,"Separating Radio Resources and Mobility Management specific parts of the MS Classmark","-",1,"R99","T2","1999-01-01","1999-12-31",1,"-","-","-","-","CP#27: change of WG as a result of closure of CN and T.",23.814,null,null,null,null,"2009-07-23","2010-02-09"]