## Tdoc cover sheet
3GPP TSG CT WG1 Meeting #157 Sophia-Antipolis, France 13-17 October 2025 |  | C1-256238
Source: | CATT
Title: | Work plan for the CT1 part of 5G_ProSe_Ph3
Agenda item: | 19.36
Document for: | Information

## Contributions plan
Contribution Plan
Spec | Topic | Related LS or other WG tdoc(s) # | CT1 meeting # | tdoc(s) # | Comments | Open issues
24.554
| Adding a reference to the type 6 container |  | CT1#151 | C1-245252
| Introducing the overview of the 5G ProSe multi-hop procedures and the skeleton of the new clauses |  | CT1#151 | C1-245480
| Adding description about policies for 5G ProSe multi-hop Relays |  | CT1#151 | C1-245894
| Adding the Multi-hop path info information element |  | CT1#151 | C1-245898
| Adding an informative annex for the spec rapporteurs |  | CT1#151 | C1-245899
| Multi-hop UE-to-network relay discovery over PC5 interface with model A |  | CT1#151 | C1-245927
| 5G ProSe multi-hop UE-to-network relay additional parameters |  | CT1#151 | C1-245928
| Definition on 5G ProSe intermediate parent and child UE-to-network relay |  | CT1#151 | C1-245935
| Introducing the terms, definitions and scope for 5G ProSe multi-hop communications |  | CT1#151 | C1-245944
| Updating the UE-requested ProSeP policy provisioning procedure for multi-hop communications |  | CT1#151 | C1-245945
| Authorization and provisioning for 5G ProSe multi-hop relays |  | CT1#151 | C1-245953
| Authorization and provisioning for 5G ProSe multi-hop relays |  | CT1#152 | C1-246583
| Multi-hop UE-to-network relay discovery over PC5 interface with model A |  | CT1#152 | C1-247004
| 5G ProSe multi-hop UE-to-network relay additional parameters |  | CT1#152 | C1-247005
| Introducing the 5G ProSe direct link establishment procedure for multi-hop UE-to-network relay (based on Model A discovery) |  | CT1#152 | C1-247045
| Introducing the 5G ProSe direct link establishment procedure for multi-hop UE-to-network relay (based on Model B discovery) |  | CT1#152 | C1-247046
| Updates on the direct link modification procedure for multi-hop UE-to-network relay |  | CT1#152 | C1-247047
| Adding the information element to deliver the Remote UE parameters through the Direct Link Modification procedure |  | CT1#152 | C1-247048
| Multi-hop UE-to-network relay selection procedure |  | CT1#152 | C1-247049
| Message content type extensions |  | CT1#152 | C1-247058
| The remote UE report procedure for the 5G ProSe layer-3 multi-hop UE-to-network relay UE in TS 24.554 |  | CT1#152 | C1-247062
| Introducing the QoS mapping information in the configuration parameters for 5G ProSe multi-hop UE-to-network relay |  | CT1#153 | C1-250148
| Defining missing policy provisioning timers for multi-hop relay and other miscellaneous corrections |  | CT1#153 | C1-250152
| Correcting wrong timers usage |  | CT1#153 | C1-250154
| Correcting missing clauses numbers for multi-hop UE-to-network relay procedures |  | CT1#153 | C1-250644
| Correction on Multi-hop UE-to-network relay discovery over PC5 interface with model A |  | CT1#153 | C1-250992
| Specifying the procedure of the multi-hop UE-to-network relay discovery over PC5 interface with model B - the procedural part |  | CT1#153 | C1-250993
| Specifying the procedure of the multi-hop UE-to-network relay discovery over PC5 interface with model B - the messages part |  | CT1#153 | C1-250994
| 5G ProSe direct link establishment and direct link modification procedures for multi-hop UE-to-network relay based on model A discovery |  | CT1#153 | C1-250995
| QoS handling for 5G ProSe multi-hop UE-to-network relay |  | CT1#153 | C1-250996
| Clarification on 5G ProSe configuration information |  | CT1#153 | C1-250997
| Corrections for the "Hop Limit" |  | CT1#153 | C1-250998
| To update multihop U2N relay discovery with model A |  | CT1#153 | C1-250999
| 5G ProSe multi-hop U2N relay based on Model A discovery: adding hop count |  | CT1#153 | C1-251000
| 5G ProSe multi-hop UE-to-UE relay: IP based |  | CT1#153 | C1-251001
| 5G ProSe multi-hop L3 U2U relay discovery for IP data unit type with model B |  | CT1#153 | C1-251023
| IP address allocation for 5G ProSe end UE in multi-hop L3 U2U relay |  | CT1#153 | C1-251024
| 5G ProSe multi-hop L3 U2U relay discovery for Ethernet and unstructured data unit type with model B |  | CT1#153 | C1-251026
| IP address allocation in 5G ProSe layer-3 multi-hop U2N relay |  | CT1#153 | C1-251049
| Assigning IEI values |  | CT1#153 | C1-251050
| DNS-based discovery of target 5G ProSe end UE in 5G ProSe multi-hop L3 U2U relay procedure |  | CT1#153 | C1-251060
| Multi-hop UE-to-UE Relay Discovery Messages for IP Data Unit Type |  | CT1#153 | C1-251069
| 5G ProSe multi-hop L3 U2U relay discovery for Ethernet and unstructured data unit type with model A |  | CT1#153 | C1-251070
| Correcting Table formats |  | CT1#153 | C1-251079
| Fixing table formats, terms, abbreviations and an editorial |  | CT1#153 | C1-251080
| Multi-hop Layer-3 UE-to-UE Relay Discovery Procedures over PC5 Interface for IP Data Unit type with Model A |  | CT1#153 | C1-251183
| Clarification on changes of 5G ProSe multi-hop U2N relay UE's PDU session address |  | CT1#154 | C1-251601
| Direct link establishment procedure update for MH U2U relay based on IP |  | CT1#154 | C1-251626
| Adding the timers used for the procedure of multi-hop UE-to-network relay discovery over PC5 interface with model B |  | CT1#154 | C1-251642
| Assigning values for the content types of PC5 discovery messages for multi-hop UE-to-UE relay |  | CT1#154 | C1-251643
| Aligning the terms used for multi-hop relay |  | CT1#154 | C1-251646
| Adding the impact of the security related parameters in the UE-requested ProSeP policy provisioning procedure for multi-hop relay |  | CT1#154 | C1-251647
| Multi-hop Layer-3 UE-to-UE Relay Discovery Procedures over PC5 Interface for IP Data Unit type with Model A |  | CT1#154 | C1-251702
| Editorial corrections for 5G ProSe multi-hop UE-to-network relay |  | CT1#154 | C1-251829
| Configuration security parameters for 5G ProSe multi-hop U2U relay |  | CT1#154 | C1-252014
| Hop count and Hop limit for MH U2N relay discovery model B |  | CT1#154 | C1-252415
| Removing the hop limit from PROSE PC5 DISCOVERY message for multi-hop UE-to-network relay discovery response |  | CT1#154 | C1-252416
| Configuration security parameters for 5G ProSe multi-hop U2N relay |  | CT1#154 | C1-252417
| Add security procedures over PC8 interface for multi-hop U2N |  | CT1#154 | C1-252419
| Support PWS via Multi-hop U2N relay |  | CT1#154 | C1-252420
| QoS handling for 5G ProSe multi-hop UE-to-network relay initiated by the 5G ProSe multi-hop remote UE |  | CT1#154 | C1-252422
| Introducing the timers for the 5G ProSe additional parameters announcement procedure for multi-hop UE-to-network relay |  | CT1#154 | C1-252424
| Correction for the announcement message for multi-hop U2N relay |  | CT1#154 | C1-252426
| Add security procedures over PC8 interface for multi-hop U2U |  | CT1#154 | C1-252429
| Hop count and Hop limit for MANET discovery info |  | CT1#154 | C1-252430
| QoS Handling for Layer-3 UE-to-UE relay for Ethernet and Unstructured Data Unit Type |  | CT1#154 | C1-252431
| Update of Direct link ID update procedure for MH U2U relay based on IP |  | CT1#154 | C1-252432
| Clarification on MH U2U relay discovery model B |  | CT1#154 | C1-252433
| Adding missing clause |  | CT1#154 | C1-252434
| Hop count and Hop limit for MH U2N relay discovery model A |  | CT1#154 | C1-252451
| Add multi-hop U2N relay reselection procedure |  | CT1#154 | C1-252453
| Update multi-hop U2N relay selection procedure |  | CT1#154 | C1-252458
| Editorial correction for ProSe multi-hop U2N relay |  | CT1#155 | C1-253086
| Introducing the configuration parameters of the 5G ProSe multi-hop layer-2 UE-to-network relay UE – the procedural part |  | CT1#155 | C1-253103
| Adding the PC5 QoS flow in the List of multi-hop remote UE parameters |  | CT1#155 | C1-253105
| Corrections for the identifiers used in 5G ProSe multi-hop UE-to-UE relay discovery for IP data unit type with model B |  | CT1#155 | C1-253108
| Routing information for 5G ProSe multi-hop end UE |  | CT1#155 | C1-253115
| Specifying security procedures over PC3a interface for multi-hop UE-to-UE relay |  | CT1#155 | C1-253117
| Hop count and Hop limit for MH U2N relay discovery model A |  | CT1#155 | C1-253216
| Correction to PROSE PC5 DISCOVERY message for multi-hop U2U relay discovery response |  | CT1#155 | C1-253344
| Clarification on multi-hop L3 U2U relay discovery for IP data unit type with model A |  | CT1#155 | C1-253345
| Complete the defnition on List of multi-hop UE-to-UE relay paths IE |  | CT1#155 | C1-253349
| Introducing the 5G ProSe additional parameters announcement procedure for multi-hop UE-to-network relay |  | CT1#155 | C1-253971
| Corrections related to the Root relay info in the PC5 discovery procedures |  | CT1#155 | C1-253973
| Specifying security procedures over PC3a interface for multi-hop UE-to-network relay |  | CT1#155 | C1-253974
| Clarification on IP Address allocation in 5G ProSe multi-hop UE to Network relay procedure |  | CT1#155 | C1-253975
| Resolving the ENs related to the List of multi-hop remote UE parameters |  | CT1#155 | C1-253977
| Support PWS via Multi-hop U2N relay |  | CT1#155 | C1-253978
| Update multi-hop U2N relay selection procedure |  | CT1#155 | C1-253979
| Adding the Hop limit in the PC5 signalling messages for multi-hop UE-to-UE relay communication |  | CT1#155 | C1-253982
| Resolve EN on signal strength measurement and related timer in multi-hop U2U relay discovery |  | CT1#155 | C1-253985
| Resolve EN on updating the parameters in the procedure of multi-hop L3 U2U relay discovery for non-IP with model A |  | CT1#155 | C1-253987
| Adding the path information in the direct link establishment request/Accept messages for the multi-hop UE-to-UE relay for Ethernet and Unstructured data unit type |  | CT1#155 | C1-254005
| Adding the path information in the direct link modification request/Accept messages for the multi-hop UE-to-UE relay for Ethernet and Unstructured data unit type |  | CT1#155 | C1-254006
| Add multi-hop U2N relay reselection procedure |  | CT1#155 | C1-254025
| Resolve EN on PROSE PC5 DISCOVERY message for multi-hop L3 U2U relay discovery |  | CT1#155 | C1-254027
| Definition on ROSE PC5 DISCOVERY messages for multi-hop U2U relay discovery for non-IP |  | CT1#155 | C1-254030
| Differentiating security materials used for PC5 direct discovery for multi-hop UE-to-network relay for inter-PLMN scenarios (Model B discovery) |  | CT1#156 | C1-254561
| Specifying the security handling for 5G ProSe multi-hop UE-to-network relay discovery over PC5 interface -- Model A discovery |  | CT1#156 | C1-254562
| Specifying the security handling for 5G ProSe multi-hop UE-to-network relay discovery over PC5 interface -- Model B discovery |  | CT1#156 | C1-254563
| Corrections for 5G ProSe multi-hop UE-to-UE relay discovery security procedures over PC8 and PC3a interfaces |  | CT1#156 | C1-254564
| Correction for 5G ProSe UE-to-UE relay discovery security parameters request procedure over PC8 interface |  | CT1#156 | C1-254565
| Clarifications for multi-hop UE-to-network relay discovery procedures over PC5 |  | CT1#156 | C1-254566
| Resolving the ENs related to the terms and configurations of "5G ProSe multi-hop layer-2 UE-to-network relay" |  | CT1#156 | C1-254567
| Completing the handling for 5G ProSe direct link establishment procedure for multi-hop UE-to-network relay based on model B discovery |  | CT1#156 | C1-254569
| Adding the descriptions of the parameters used for the multi-hop PC5 discovery messages |  | CT1#156 | C1-254570
| Corrections to multi-hop U2U relay discovery messages |  | CT1#156 | C1-254696
| Resolve EN on DHCPv6 for multi-hop U2U relay case |  | CT1#156 | C1-254697
| The Security Aspect of the Multi-hop Layer-3 UE-to-UE Relay Discovery Procedures over PC5 Interface for IP Data Unit type with Model A |  | CT1#156 | C1-254786
| MAC address uniqueness for Ethernet traffic via 5G ProSe layer-3 multi-hop UE-to-UE relay |  | CT1#156 | C1-254835
| Resolution of EN for PWS support over MH U2N relay |  | CT1#156 | C1-254855
| EN resolution for PWS over layer-2 MH U2N relay |  | CT1#156 | C1-254856
| Clarification on hop limit included in multi-hop U2U discovery solicitation message |  | CT1#156 | C1-254860
| Resolve ENs on discoveree end UE procedure for multi-hop U2U relay |  | CT1#156 | C1-254862
| Update QoS parameters for multi-hop U2N based on model B |  | CT1#156 | C1-255107
| Resolve the EN related to accumulated QoS |  | CT1#156 | C1-255108
| Differentiating security materials used for PC5 direct discovery for multi-hop UE-to-network relay for inter-PLMN scenarios (Model A discovery) |  | CT1#156 | C1-255518
| Adding missing references |  | CT1#156 | C1-255519
| Further Updates to Multi-hop U2N Relay Selection Procedure |  | CT1#156 | C1-255521
| Update of the figure for the 5G ProSe additional parameters announcement procedure |  | CT1#156 | C1-255522
| Security aspects for multi-hop U2U discovery of non-IP type model A |  | CT1#156 | C1-255523
| Add multi-hop U2U relay unicast direct communication procedure for non-IP type |  | CT1#156 | C1-255524
| Support for Ethernet traffic via 5G ProSe layer-3 multi-hop UE-to-UE relay |  | CT1#156 | C1-255525
| Correction on MH U2U relay discovery model B for IP |  | CT1#156 | C1-255526
| Resolve EN on discoverer relay UE procedure for multi-hop U2U relay |  | CT1#156 | C1-255527
| Resolve EN on IP address allocation for multi-hop L3 end UE |  | CT1#156 | C1-255528
| Timers for multi-hop U2U relay discovery with model B |  | CT1#156 | C1-255529
| Correction regarding 5G ProSe U2U relay terminologies |  | CT1#156 | C1-255530
| Minor Proofreading Corrections |  | CT1#156 | C1-255563
| Resolve the ENs related to multi-hop direct link and message type |  | CT1#156 | C1-255576
24.555
| The skeleton and overview for 5G ProSe multi-hop relays |  | CT1#151 | C1-245890
| Terms for 5G ProSe multi-hop and single-hop communications |  | CT1#151 | C1-245891
| Encoding of UE policies for 5G ProSe intermediate U2N relay UE |  | CT1#152 | C1-247077
| Encoding of UE policies for 5G ProSe multi-hop U2N remote UE |  | CT1#152 | C1-247078
| Encoding of UE policies for 5G ProSe multi-hop UE-to-network relay UE |  | CT1#152 | C1-247079
| The encoding of the QoS mapping information in the configuration parameters for 5G ProSe multi-hop UE-to-network relay |  | CT1#153 | C1-250149
| Corrections in the encoding of multiple fields |  | CT1#153 | C1-250153
| Correction on ProSeP info type |  | CT1#153 | C1-250346
| Encoding of UE policies for 5G ProSe multi-hop UE-to-UE relay UE |  | CT1#153 | C1-251036
| Encoding of UE policies for 5G ProSe multi-hop UE-to-UE end UE |  | CT1#153 | C1-251037
| Encoding security parameters for multi-hop U2U relay |  | CT1#154 | C1-252016
| Encoding security parameters for multi-hop U2N relay |  | CT1#154 | C1-252418
| Reference to obsoleted IETF RFC4122 |  | CT1#154 | C1-252439
| Policy/Parameter provisioning to support PWS for 5G ProSe multi-hop U2N Relay |  | CT1#154 | C1-252471
| Correction for the encoding of the configuration parameters of 5G ProSe intermediate U2N relay UE related to the indication of PDU session parameters |  | CT1#155 | C1-253114
| Introducing the configuration parameters of the 5G ProSe multi-hop layer-2 UE-to-network relay UE – the encoding part |  | CT1#155 | C1-253976
| Policy/Parameter provisioning to support PWS for 5G ProSe multi-hop U2N Relay |  | CT1#155 | C1-253988
| Adding missing parameters in the encodings of the configuration parameters of multi-hop UEs |  | CT1#156 | C1-254571
24.501
| Enhancement of 5G ProSe capability for multi-hop relays |  | CT1#151 | C1-245912
| Update 5GMM capability for 5G ProSe multi-hop relays |  | CT1#153 | C1-251164
| PDU session establishment procedure for 5G ProSe multi-hop layer-3 UE-to-network relay |  | CT1#154 | C1-251831
| Update 5GMM capability for IM relay |  | CT1#155 | C1-253981
| Correcting wrong capability bit related to 5G ProSe layer-2 intermediate UE-to-network relay UE |  | CT1#156 | C1-254559
24.587
| Updating the Requested UE policies information element for multi-hop communications |  | CT1#151 | C1-245946
| Updating the Requested UE policies information element for different 5G ProSe multi-hop Layer-2 communications |  | CT1#153 | C1-251048
| Correction for the setting of UE policies for 5G ProSe Multi-Hop relay indicator |  | CT1#154 | C1-251637

## Expected contributions
Expected Contributions for future meetings
Spec | Topic | Related LS or other WG tdoc(s) # or TS # | Volunteered company/delegate | Contribution(s) | Comments/Open issues
24.554
Editor's notes for multi-hop U2N
| Editor’s note [5G_ProSe_Ph3, CR#0680]: It is FFS whether the Layer-2 IDs are included in the Multi-hop path info IE, together with the list of the User info IDs (or as a separate IE), due to the following statement from clause 6.3.2.5.3 in 3GPP TS 23.304: "A 5G ProSe Intermediate UE-to-Network Relay sends a Solicitation message, it additionally includes its own User Info ID in the message. i.e. the message contains the path information which is an (ordered) list of User Info ID and Layer-2 ID of Relays in the path that has relayed the Solicitation message". Editor’s note [5G_ProSe_Ph3, CR#0680]: It is FFS whether the Layer-2 IDs are included in the Multi-hop path info IE, together with the list of the User info IDs (or as a separate IE), due to the following statement from clause 6.3.2.5.3 in 3GPP TS 23.304: "the Relay Discovery Response message is forwarded along the path, where each 5G ProSe Intermediate UE-to-Network Relay determines the next hop information (e.g. User Info ID and Layer-2 ID) to forward the Relay Discovery Response message". | S2-2508102(Reply LS) U2N dicovery procedure for model B, in clause 8b.2.1.3.2 and clause 8b.2.1.3.3 | CATT
| Editor's note (CR#0682, 5G_ProSe_Ph3): The information element for remote UE context in the PROSE DIRECT LINK MODIFICATION REQUEST message is FFS. | modification procedure, in clause 8b.2.2.3 | Nokia
| Editor's note (CR 0670, 5G_ProSe_Ph3): The details of that step including any potential changes in the PROSE DIRECT LINK MODIFICATION REQUEST message to deliver the PC5 QoS Info and PC5 QoS rule(s) are FFS. Editor's note (CR 0670, 5G_ProSe_Ph3): The details of the split PC5 QoS hop-by-hop and any corresponding updates in the PROSE DIRECT LINK MODIFICATION REQUEST message are FFS. | PC5 QoS in modification procedure, in clause 8b.2.2.3 | Nokia
| Editor's Note (CR0757, 5G_ProSe_Ph3): whether the cause value #15 can be resued for the ProSe direct link establishment procedure for 5G ProSe multi-hop UE-to-network relay is FFS. Editor's Note (CR0757, 5G_ProSe_Ph3): 5G ProSe direct link modification procedure to handle multi-hop UE-to-network relay regarding the relay reselection indication is FFS. The cause (e.g. the link failure or link quality degradation of the PC5 link) for reselection indication is FFS | reselection procedure, in clause 8b.2.3.2
| Editor's Note (CR0778, 5G_ProSe_Ph3): It is FFS whether additional parameters are needed for PROSE ADDITIONAL PARAMETER ANNOUNCEMENT REQUEST message. | S2-2507872(reply LS) CR 0555 (LG Electronics, Qualcomm Incorporated) 5G ProSe additional parameters announcement procedure, clause 8b.2.8.2 | Qualcomm Incorporated
Editor's notes for multi-hop U2U
| Editor's note [5G_ProSe_Ph3, CR#0701]: The indicated security procedure for 5G ProSe multi-hop layer-3 UE-to-UE relay for the relay service code is FFS and depends on SA3 outcome. | clauses 8c.2.1.2.3.2.2
| Editor's note [5G_ProSe_Ph3, CR#0701]: The security with the associated encrypted bitmask for the relay service code is FFS and depends on SA3 outcome. | clauses 8c.2.1.2.3.2.2
| Editor’s Note [5G_ProSe_Ph3, CR#0701]: Handling of PROSE PC5 DISCOVERY message using the security materials received from 5G DDNMF or 5G PKMF is FFS. | clauses 8c.2.1.2.3.4.2
| Editor’s Note [5G_ProSe_Ph3, CR#0701]: How to apply the DUIK, DUSK, or DUCK with the associated encrypted bitmask for the relay service code for 5G ProSe multi-hop UE-to-UE relay discovery is FFS and depends on SA3 output. | clauses 8c.2.1.2.3.4.2
| Editor's Note (5G_ProSe_Ph3, CR0687): It is FFS whether to describe how to evenlop the MANET message in the IP PDU over the 5G ProSe direct link. | 5G ProSe direct link management procedure for IP, in clause 8c.2.2.2
| Editor's Note (CR0687, 5G_ProSe_Ph2): IANA registration is required for <msg-type> field. Editor's Note (CR0687, 5G_ProSe_Ph3): The value of TLV type needs to be determined by IANA registration. After that the table will be updated. | clause 10.8.2.1 and clause 11.8.1
| Editor's Note (CR0687, 5G_ProSe_Ph2): Min and Max size of Multi-hop UE-to-UE discovery info is FFS Editor's Note (CR0687, 5G_ProSe_Ph3): Minimum and maximum length of the multi-hop UE-to-UE discovery info parameter are FFS. | clause 10.8.2.1 and clause 11.8.1
| Editor's note (5G_ProSe_Ph3, CR#0704): Whether the path info field also includes source layer-2 ID of discoverer Prose end UE (specified in 5.8.6.3 but not specified in 6.3.2.6.3.1 of TS 23.304) is FFS. | S2-2508102(Reply LS) CR 0558 (Huawei, HiSilicon, KPN N.V., Qualcomm Incorporated, ZTE, Samsung) clause 11.2.24 | CATT
24.555
24.501

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments
S2-2508102 | Reply LS on the path information in 5G ProSe multi-hop discovery procedures |  | S2-2506119/ C1-253724
S2-2507872 | Reply LS on parameters for ProSe additional parameters announcement request message |  | C1-254010/S2-2506121