## Slide 1
3GPP Work Plan
Review at Plenary #110
Source: MCC / Work Plan Manager (A. Sultan)
Agenda item: Review of the Work Plan
Document for: Information
Review based on the latest available version of the Work Plan, available at: https://ftp.3gpp.org/Information/WORK_PLAN
Includes: - the progress on all WIDs, as indicated in the WG Chairs’ reports (CT & SA) and in the Status Report (RAN), - the new WIDs proposed by SA/CT WGs to this TSG (will be removed if not TSG-approved)
Does not include: - the company-proposed WIDs proposed/approved at this TSG, the revised WID/SID during this TSG
Warnings :
- This review is a high-level view of the 3GPP progress. It is based on the 3GPP Work Plan, a continuously updated document.
Some misalignments might temporarily appear on some individual items.
- Some WG cannot progress because of reasons beyond their control (e.g. dependencies with other groups).
These slides shall not be used to judge the “efficiency” of whatever WG.
© 3GPP 2025
RP-252985_SP-251599 (was CP-253011) - 3GPP TSG#110, 8 -12 December 2025, Baltimore, USA
Green highlight: good news
Yellow highlight: to be clarified
Cyan highlight: other highlight

## Slide 2: Content of this Work Plan review
Snapshot of all ongoing/future Releases
Ongoing Releases
  Rel-19 Timeline and Progress
  Rel-20 Timeline and Progress
  Rel-21 Timeline and Progress
Background information

## Slide 3
Releases 19 to 21 timelines
#108
Release 19
Note: All starting dates are indicative
#110
#112
#114
#116
#118
#120
#122
#124
#126
2025
2026
2028
*: +3 months for RAN4
**: - 3 months for RAN1 & + 3 months for RAN4 perf
#111
#113
#115
#119
#121
#123
#125
2027
2029
5GA Stage 1
RAN Completion**
Stage 3 (CT & SA)
ASN.1
&
Open
APIs
Stage 2
#117
#109
2024
#104
#106
#107
#105
Mar.
#103
TSGs
Mar.
Mar.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Jun.
Jun.
Jun.
Sep.
Sep.
Sep.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
Dec.
Dec.
Dec.
Now
SA1 St.1, Content Definition (RAN & SA St.2): completed Dec. 2023
Release 20 5GA
Release 20 FS_6G
5GA Stage 2
5GA RAN Completion**
5GA Stage 3
Chart showing Normative dates
(timeline for 5GA studies not shown)
Chart showing Studies dates
(no 6G normative work in Rel-20)
FS_6G Stage 1
FS_6G RAN P
FS_6G Stage 2
or
FS_6G RAN WG**
FS_6G Stage 3
TBD
Release 21 6G
Rel-21 timeline to be decided no later than June 2026
ITU deadlines for 6G: March 2029 for technology proposal, mid-2030 for specifications
ASN.1

## Slide 4: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 5
Release 19 timeline
#101
Note: All starting dates are indicative
#102
#103
#104
#105
#106
#107
#108
#109
#110
#111
#112
#99
RAN4
content def.
RAN Content def.
2024
2025
Sep.
Mar.
Mar.
Mar.
Jun.
Jun.
Jun.
Sep.
Sep.
Mar.
Dec.
Dec.
Dec.
2026
RAN4_Perf
Stage 3 (CT & SA)
RAN1
Stage 2 (SA2, SA6,…) Normative
RAN Completion (RAN2/3/4core)
ASN.1 & Open APIs
St.2 Content approval
#100
Jun.
2023
Now
100%
SA1 Stage 1 80%
TSGs
RAN Rel-19 workshop
SA Rel-19
Workshop

## Slide 6: Release 19 progress overview (1/2) – SA&CT
SA1 (Stage 1): completed and stable (14 Studies, 25 Normative items)
SA2, SA6 (Stage 2): completed (24 Studies, 72 Normative items) :
  3 exceptions completed over the last 3 months (AIML_CNNG_RTC_Ph2) and AmbientIoT-ARC)
SA3/4/5 (Stages 2 and 3): completed (51 studies, 73 normative items)
    Reminder: these WGs also handle Stage 3 for certain topics
    Exceptions that were completed over the last 3 months:
CT WGs(mostly Stage 3): completed (5 studies, 137 normative items)
    Reminder: some of these WGs might also handle Stage 2 for certain topics
    Exceptions that have been completed over the last 3 months:
    Note: one item not 100% complete: CT3 aspects of MPS for IMS Messaging and SMS services MPS4msg (96%). This is lead by CT4, impacting CT1, CT3 and CT4. It will be completed by CRs later on (remaining in Rel-19).
AmbientIoT-SEC | S3
ATIAS_Ph2 | S4
IVAS_Codec_Ph2 | S4
VOPS | S4
AMD_PRO-MED | S4
SCAS_5G_UDR | S3
MCXSec4 | S3
AIML_App | C1
AmbientIoT-CT | C1
XRM_Ph2_App | C1
MINT_Ph2 | C1
MINT_Ph2 | C4
MINT_Ph2 | C6
MMTel_App | C3
IMS_RES-CT | C1
IMS_RES-CT | C3
IMS_RES-CT | C4
LoSePLMN-CT | C1
TestHarmon_CrossRAT | C6

## Slide 7: Release 19 progress overview (2/2) - RAN
  All RAN1, RAN2 & RAN 3: all items completed (27 items)
  RAN4 (Perf): 54 completed items. Not completed:
Unique_ID | Name | Acronym | %
1022095 | Perf. part: Enhancements of Network energy savings for NR | Netw_Energy_NR_enh-Perf | 80%
1022094 | Perf. part: Low-power wake-up signal and receiver for NR (LP-WUS/WUR) | NR_LPWUS-Perf | 90%
1022093 | Perf. part: Artificial Intelligence (AI)/Machine Learning (ML) for NR air interface | NR_AIML_air-Perf | 60%
1062084 | Perf. part: Solutions for Ambient IoT (Internet of Things) in NR | Ambient_IoT_Solutions-Perf | 70%
1052123 | Perf. part: Introduction of IoT-NTN TDD mode | IoT_NTN_TDD-Perf | 67%
1022097 | Perf. part: Non-Terrestrial Networks (NTN) for NR Phase 3 | NR_NTN_Ph3-Perf | 80%
1032087 | Perf. part: Non-Terrestrial Networks (NTN) for Internet of Things (IoT) Phase 3 | IoT_NTN_Ph3-Perf | 85%
1032086 | Perf. Part: Enhanced requirements and conductive test methodology for NR NTN and IoT NTN | NR_IoT_NTN_req_test_enh-Perf | 90%
1042135 | Perf. part: Introduction of Ku bands for NR NTN | NR_NTN_Ku_bands-Perf | 75%
1022098 | Perf. part: XR (eXtended Reality) for NR Phase 3 | NR_XR_Ph3-Perf | 10%
1060083 | 7MHz Channel Bandwidth for n26 and n5 | NR_FR1_7MHz_BW | 99%
1040121 | Additional NR bands for NR features in Rel-19 | NR_bands_xFeature_R19 | 87%
1040120 | Rel-19 NR CA/DC for x bands DL with y bands UL (x<7, y<3) and SUL/CA band combinations with a single SUL or two SUL cells | NR_CADC_SUL_R19 | 99%
1062082 | Perf. part: Low band carrier aggregation via switching | NR_LBCA_Sw-Perf | 50%
1022089 | Perf. part: NR MIMO Phase 5 | NR_MIMO_Ph5-Perf | 80%
1022090 | Perf. part: Evolution of NR duplex operation: Sub-band full duplex (SBFD) | NR_duplex_evo-Perf | 70%
1022091 | Perf. part: NR mobility enhancements Phase 4 | NR_Mob_Ph4-Perf | 60%
1032078 | Perf. part: NR base station (BS) RF requirement evolution for FR1/FR2 and testing | NR_BS_RF_req_evo-Perf | 90%
1032079 | Perf. part: NR Radio Resource Management (RRM) Phase 5 | NR_RRM_Ph5-Perf | 80%
1032083 | Perf. part: Enhancements for Air-to-ground network for NR | NR_ATG_enh-Perf | 85%
1032077 | Perf. part: UE RF enhancements for NR FR1/FR2 and EN-DC, Phase 4 | NR_ENDC_RF_Ph4-Perf | 90%
1032082 | Perf. part: Support of intra-band non-collocated EN-DC/NR-CA deployment Phase2: new receiver type(s) | NonCol_intraB_ENDC_NR_CA_Ph2-Perf | 60%
1032085 | Perf. Part: FR1 TRP (Total Radiated Power), TRS (Total Radiated Sensitivity) and MIMO OTA (Over the Air) testing enhancement Phase 3 | TRP_TRS_MIMO_OTA_Ph3-Perf | 95%
1070064 | New LTE band for 5G broadcast for region 3 utilizing a geosynchronous satellite | LTE_band_5G_bcast_GSO | 87%
1072064 | Perf. part: New LTE band for 5G broadcast for region 3 utilizing a geosynchronous satellite | LTE_band_5G_bcast_GSO-Perf | 80%

## Slide 8: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 9: Release 20: introduction
Rel-20 has 2 components: “Rel-20_5GA” and “Rel-20_6G” (or “Rel-20_FS_6G”)
  Rel-20_5GA covers 5GA studies and normative
  Rel-20_6G covers 6G studies only (6G normative in Rel-21)
  Up to each TSG/WG how to split their time on each component (e.g. in SA1, it was initially at 50%-50%)

## Slide 10
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
Now
TSGs
SA1 5GA WID definition
100%
SA1 5GA Studies + Norm 80%
100%
St. 2 (SA2, SA6, …) 5GA St.+Norm 80%
Stage 3 5GA St + Norm
#113
Sep.
#114
Dec.
#115
Mar.
Jun
RAN1
RAN Completion (RAN2/3/4core)
#116
RAN4 C.def.
RAN4 Perf
RP Content def.
2025
2026
2027
5GA ASN.1 & Open APIs
Release 20 5GA timeline
Note: All starting dates are indicative
Workshops
5GA RAN & SA
RAN WG SID def.
St.2 WID def.
St.3 WID def.

## Slide 11: Release 20 5GA progress overview (1/2)
Stage 1: Frozen in June 2025
Stage 2 in SA2 and SA6: Significant progress on studies and Normative work. 14 (normative) new WIDs proposed this time.
  Studies: 22 studies, OCI = 66 % (against 21 studies, OCI was 36% at previous TSG)
  Normative: 22 items so far, OCI = 46 % (against 8 items, OCI was 18% at previous TSG)
RAN: Mostly working on the Studies, also identifying the normative work.
  RAN WG SIDs/WIDs approved at RAN#108 (RAN1,2,3 ) & RAN#109 (RAN4)
  RAN Content Definition is TSG##10
  Studies: 6 studies, OCI = 44 % (against 4 studies, OCI was 10% at previous TSG)
  Normative: 45 items so far, OCI=9% (against 19 items, work not started at previous TSG)

## Slide 12: Release 20 5GA progress overview (2/2)
Rel-20 5GA SA3/4/5 activities: Significant progress on studies and normative, doubling the normative WIDs
  Studies: 48 studies, OCI = 31 % (against 15 studies, OCI was 14% at previous TSG)
  Normative: 18 items so far, OCI = 33 % (against 9 items, OCI was 18% at previous TSG)
Rel-20 5GA in CT (from CP-252253/2252):
  not started, to be started in Q1 2026
  Rel-20 timeline to be used about 50%-50% between 5GA topics and FS_6G topics

## Slide 13
#111
Mar.
#107
Mar.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#106
Dec.
#110
Dec.
Now
Workshop 6G TSGs
CT & St. 3 6G SID def.
#113
Sep.
#114
Dec.
#115
Mar.
Jun
#116
SA1 6G Study
RP 6G Study
RAN1 6G Study
SA2 6G Study
Stage 3 6G Study(ies)
2025
2026
2027
RAN2/3/4 6G Study(ies)
Release 20 (FS) 6G timeline
TBD
Note: All starting dates are indicative
TBD
SA3 6G Study
SA5-CH 6G Study
Workshop SA1 on IMT-2030 use cases: May 2024
SA1 6G SID Def: May June-Sep 2024
2024
#119
Mar.
#117
Jun.
#118
Dec.
TSGs
SA4 6G Study
RP ITU Study
SA5-OAM 6G Study
SA6 6G Study

## Slide 14: Release 20 FS_6G progress overview (1/2)
Reminder: no normative work on 6G in Rel-20 (only studies)
Several groups have now started working on 6G:
Two most advanced ones are:
  SA1’s TR 22.870 on FS_6G_REQ, now at 80% (was 77%), targeted for 03/2026
  RP’s TR 38.914 on Study on 6G Radio, now 40% complete (was 10%), targeted for 06/2026
Cross-TSG topics already identified on 6G Requirements (RAN and SA1); 6G Migration (RAN and SA2); 6G Security (RAN2 and SA3)
Note: “Hyperlink” field = the WID as per the beginning of TSG#110 (final version of the WID not reflected here)

## Slide 15: Release 20 FS_6G progress overview (1/2)
Reminder: no normative work on 6G in Rel-20 (only studies)
Several groups have now started working on 6G:
Two most advanced ones are:
  SA1’s TR 22.870 on FS_6G_REQ, now at 80% (was 77%), targeted for 03/2026
  RP’s TR 38.914 on Study on 6G Radio, now 40% complete (was 10%), targeted for 06/2026
Cross-TSG topics already identified on 6G Requirements (RAN and SA1); 6G Migration (RAN and SA2); 6G Security (RAN2 and SA3)
UID | Rel-20 6G Studies |  |  | Start | End | % | WID
1050110 | Study on 6G Use Cases and Service Requirements | FS_6G_REQ | S1 | 04/09/2024 | 03/03/2026 | 80% | SP-241391
1080057 | Study on Architecture for 6G System | FS_6G_ARC | S2 | 05/06/2025 | 06/06/2026 | 20% | SP-250806
1060079 | Study on 6G Scenarios and Requirements | FS_6G_RAN_Scen_Req | RP | 08/12/2024 | 05/06/2026 | 40% | RP-251395
1080064 | Study on Modernization of Specification Format and Procedures for 6G | FS_6GSpecs | SP | 27/06/2025 | 03/03/2026 | 0% | SP-250802
1080072 | Study on 6G Radio | FS_6G_Radio | R1 | 06/06/2025 | 03/03/2027 | 12% | RP-252912
1090013 | Study on Charging Aspects of 6G Syste | FS_6G_CH | S5 | 09/09/2025 | 03/03/2027 | 15% | SP-251218
1090044 | Study on Security for the 6G System | FS_6G_SEC | S3 | 29/09/2025 | 06/06/2027 | 4% | SP-251233
1100019 | Study on 6G Application Enablement | FS_6G_APP | S6 | 03/12/2025 | 03/03/2027 | 0% | SP-251455
1100011 | Study on Lawful Interception for 6G | FS_6G_LI | S3LI | 03/12/2025 | 12/12/2027 | 0% | SP-251311
1100014 | Study on 6G Management and Orchestration | FS_6G_OAM | S5 | 03/12/2025 | 06/06/2027 | 0% | SP-251365
1100010 | Study on Media Aspects for 6G System | FS_6G_MED | S4 | 03/12/2025 | 03/03/2027 | 0% | SP-251620

## Slide 16: Release 20 FS_6G progress overview (2/2)
Stage 2 (SA2/SA6) activities:
  SA2: SID now at 20% - target clarified at TSG#110 to be Mar 27
  SA6: SID presented to TSG#110, target assumed to be March 27 as shown on SID
SA3/SA3LI/SA4/SA5 activities:
  SIDs approved at TSG#109 (SA5_CH, SA3) and TSG#110 (SA3_LI, SA4, SA5_OAM, SA6)
  Target is March 27 (SA4, SA5_CH, SA6) or June 27 (SA3, SA5_OAM) (and Dec 27 for LI)
CT activities (from CP-252253/2252):
  not started, to be started in Q4 2025
  Rel-20 timeline to be used about 50%-50% between 5GA topics and FS_6G topics

## Slide 17: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 18: Release 21
Release 21 is the release for submission to IMT-2030*, aka 6G
This implies that 3GPP (normative) work will be submitted to ITU-R before 2030
  ASN.1/OpenAPI freeze date is no earlier than March 2029
Release 21 Freezing dates and other milestones TBD:
  Previous decision: “Rel-21 timeline is to be decided no later than June 2026”
  But some groups (SA1, RAN Plenary) would have already finished their Rel-20 work by that time
  Quite urgent to define the timeline for them
SA#110: First Rel-21 SID proposed (SA1)
Note that, as usual in 3GPP, previous Generations will in parallel continue to be maintained & enhanced in Rel-21 and after
* source: TSG#103-endorsed CT-240307/SP-240458/RP-240823

## Slide 19
Discussion on Rel-21 timeline
TSG#117
TSG#118
TSG#123
TSG#109
TSG#110
TSG#111
TSG#112
TSG#113
TSG#114
TSG#115
TSG#116
2025
2026
Dec
Mar.
Mar.
Jun.
Jun.
Sep.
Sep.
Sep.
Dec.
Dec.
2027
Release 21
(incl. 6G Norm.)
Now
Rel-21 Stage 1
TBD
Mar
FS_6G RAN WG
FS_6G RAN Plenary
FS_6G Stage 1
FS_6G Stage 2
or
FS_6G Stage 3
Reminder:
Release 20
FS_6G
TBD
2028
TSG#121
TSG#122
TSG#120
Dec
Mar.
Jun.
Sep.
2029
TSG#119
?
Note: All starting dates are indicative
Other Stages?
SA1 WID def.

## Slide 20: Content of this Work Plan review
Snapshot of all ongoing Releases
Rel-19 Timeline and Progress
Rel-20 Timeline and Progress
Rel-21 Timeline and Progress
Background information

## Slide 21: Background information (1/2): overall
Dedicated e-mail list for Work Plan aspects
Open to everyone interested (rapporteus, chairs, delegates, etc.) by sending the message “Subscribe 3GPP_WORKPLAN” to the address LISTSERV@LIST.ETSI.ORG
For comments/update to the Work Plan, please use the 3GPP_WORKPLAN list
Editorial comments can be sent directly to: alain.sultan@etsi.org
3GPP Work Plan
http://www.3gpp.org/ftp/Information/WORK_PLAN
Contains Release 1999 to Release 20; Master version in MS Project; Working versions in Excel
Tutorials on content, maintenance and other info on the Work Plan in subfolder /info
3GPP Releases Descriptions – R99 to Rel-18
http://www.3gpp.org/ftp/Information/WORK_PLAN/Description_Releases/
“Releases Descriptions” for Releases 8 to 13: limited to copy-paste of the WIDs.
“Releases Descriptions” for Releases 14 to 18: TR 21.9xx: “Release xx Description; Summary of Rel-xx Work Items”, written in collaboration with all the Rel-xx Features Rapporteurs
3GPP Releases Descriptions – Rel-19
Starting, as of December 2025.
CONTRIBUTIONS FROM RAPPORTEURS STARTED TO BE PROVIDED AT TSG#110, TO BE INCLUDED IN NEXT VERSION SHORTLY AFTER THE MEETING

## Slide 22: Background information (2/2): Relationship between WGs, Stages and deadlines
Most 3GPP Working Groups handle only one Stage:
  SA1  Stage 1
  SA2  Stage 2; SA6  Stage 2
  CT WGs  Stage 3 (also Stage 2 for some specific items)
SA3, SA4 and SA5 handle several Stages for some or all their WIDs:
  SA3: handles Stages 2 and 3 for all its WIDs. Stage 2 at SA3 is one quarter after SA2/SA6’s deadline, but this date is an SA3-internal date since there is no dependency (i.e. SA3 is not expecting work from any other WGs)
  SA4: handles Stage 2 for some WIDs (for which SA4 might rely on CT WGs for Stage 3), and Stage 3 for a majority of its WIDs. Stage 2 WIDs in SA4 are clearly identified as such and have the same deadline as SA2/SA6’s date.
  SA5: handles Stages 1, 2 and 3 for all its WIDs. Stage 1 for SA5 is 4 quarters after SA1’s date. Stage 2 for SA5 is 2 quarters after SA2/SA6’s date. Stage 3 for SA5 is same date as CT WGs’ date.
  For SA3, SA4 and SA5, the completion date for all WIDs dealing with Stage 3 (fully or partially) is the same as for CT WGs.
  In this Work Plan review slides, SA3, SA4 and SA5 are reported in the “Stage 3” slides since their overall completion date is aligned with (CT’s) Stage 3. Except for SA4’s Stage 2-only WIDs but this cannot be handled by the present tools.
RAN has a slightly different process. RAN defines two dates:
  The “RAN Content Definition”, which is the same date as SA Stage 1 and SA content definition
  The “RAN Completion”, which is the same date as SA/CT’s Stage 3
  Note that there is no specific RAN-equivalent date for SA/CT’s Stage 2