## Cover sheet
3GPP TSG-RAN WG5 Meeting #110 | [7 empty] | R5-YYXXXX
Gothenburg, Sweden, 9th Feb 2026 - 13th Feb 2026
Agenda Item: | 7.5.2
Source: | CMCC, Huawei
Title: | WP Conformance - Solutions for Ambient IoT (Internet of Things) in NR plus CT1 and SA3 aspects
Work item code: | Ambient_IoT_Solutions_plus_CT1_SA3-ConTest
Release: | Rel-19
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
At the RAN#110 meeting in December 2025 the Rel-19 RAN5 work item for Conformance of Solutions for Ambient IoT (Internet of Things) in NR plus CT1 and SA3 aspects was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item to introduce the Rel-19 A-IoT into RAN5 test specifications. The work plan is updated after each RAN5 meeting to give the status of the work item. Section 2 gives an overview of the work item status. The work sheet 'WP' shows the status for each impacted/newly introduced test cases.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 5% | 0 | 20
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
AmbientIoT (FR1) |  | 5% | 0 | 20
FR1 |  | 5% | 0 | 20
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | AmbientIoT
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
Ambient IoT
AIoT Common
Common test environment | 38.591-1 | 0% |  |  | 0%
Common ICS | 38.591-4 | 0% |  |  | 0%
AIoT RF/RRM
RF common parts | 38.591-2 | 0% |  |  | 0%
RF Tx test cases | 38.591-2 Tx | 0% | 0 | 3 | 0% | 0 | 3
RF Rx test cases | 38.591-2 Rx | 0% | 0 | 3 | 0% | 0 | 3
OTA test characteristcs | 38.591-2 OTA | 0% |  |  | 0%
RRM test cases | 38.591-2 RRM | 0% | 0 | 1 | 0% | 0 | 1
Applicability RF. Demod/QSI and RRM test cases | 38.591-4 | 0% |  |  | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.9xx
Test Point analysis receiver and transmitter test cases | 38.9xx
AIoT Reader and CN protocols
Protocol test cases | 38.591-3 | 0% | 0 | 13 | 0% | 0 | 13
Applicability Protocol test cases | 38.591-4 | 0% |  |  | 0%
Test suites (TTCN) | 38.591-5
5 References
[1] RP-253381 | New WID on Conformance - Solutions for Ambient IoT (Internet of Things) in NR plus CT1 and SA3 aspects
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | Conformance - Solutions for Ambient IoT (Internet of Things) in NR plus CT1 and SA3 aspects | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | Ambient_IoT_Solutions_plus_CT1_SA3-ConTest
WP Scope: |  | This work plan covers the tasks needed to include core & performance requirements for R19 A-IoT Devices
WP Resp: |  | Danni Song (CMCC); Yaping Zhang (Huawei) | [8 empty] | WP item completion |  |  | AmbientIoT
TS Resp: |  | Danni Song (CMCC); Yaping Zhang (Huawei); Chunying Gu(Huawei); Luyang Zhao(CMCC); Olivier Genoud(TF160); Yu Shi (China Unicom)
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | AmbientIoT |  | FR1
5%
113
84
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
Ambient IoT
AIoT Common
TS 38.591-1: Common test environment- Common parts (general clauses)
|  | 38.591-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.591-1 |  | Foreword | Add Foreword for TS 38.591-1 | Huawei | RAN5#110 (Feb-26) |  | Yaping Zhang <zhangyaping13@huawei.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 1 | Scope | Add Scope for TS 38.591-1 | Huawei | RAN5#110 (Feb-26) |  | Yaping Zhang <zhangyaping13@huawei.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 2 | References | Add References for TS 38.591-1 | Huawei | RAN5#110 (Feb-26) |  | Yaping Zhang <zhangyaping13@huawei.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 3 | Definitions, symbols and abbreviations | Add Definitions, symbols and abbreviations for TS 38.591-1 | Huawei | RAN5#110 (Feb-26) |  | Yaping Zhang <zhangyaping13@huawei.com> | 0.5 | 0% | 0% |  | 0%
TS 38.591-1: Common test environment- Common parts (general clauses)
|  | 38.591-1 | 4 | Common test environments | New clause header |  |  |  |  | TBD
TBD |  | 38.591-1 | 4.1 | Environmental conditions | Add environmental conditions for A-IoT devices |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 4.2 | Common requirements of test equipment | Add generic requirements of the test equipment for RF, RRM and signalling conformance testing |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.591-1 | 4.3 | Reference test conditions | New clause header |  |  |  |  | TBD
TBD |  | 38.591-1 | 4.3.1 | Test frequencies | Add test frequencies for operationg bands |  | RAN5#112 (Aug-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 4.3.2 | Radio conditions | Add radio conditions |  | RAN5#112 (Aug-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 4.3.3 | Physical channel allocations | Add physical channel allocations |  | RAN5#112 (Aug-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 4.3.4 | Signal levels | Add signal levels for testing |  | RAN5#112 (Aug-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 4.4 | Reference system configurations | Definition of reference system configurations for testing |  | RAN5#112 (Aug-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 4.5 | Test states | Definition of test state, for example inventory, command, etc. |  | RAN5#112 (Aug-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 4.6 | Generic procedures | Definition of generic procedures for testing |  | RAN5#112 (Aug-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 4.7 | Default message and information elements contents | Definition of default message and information elements contents for testing | Huawei | RAN5#112 (Aug-26) |  | Yaping Zhang <zhangyaping13@huawei.com> | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 4.8 | Default NAS message and information elements contents | Definition of default NAS message and information elements contents for testing | Huawei | RAN5#112 (Aug-26) |  | Yaping Zhang <zhangyaping13@huawei.com> | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 4.9 | Reference configurations | Definition of reference configurations for testing, such as device identification, long-term key, etc. |  | RAN5#112 (Aug-26) |  |  | 1 | 0% | 0% |  | 0%
TS 38.591-1: Common test environment - Test environments for RF test
|  | 38.591-1 | 5 | Test environments for RF test | New clause header |  |  |  |  | TBD
TBD |  | 38.591-1 | 5.1 | Requirements of test equipment | Add test environment requirements for RF testing |  | RAN5#112 (Aug-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 5.2 | Reference test conditions | Add test conditions for RF testing |  | RAN5#112 (Aug-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 5.3 | Default message and information elements contents | Add default message and information elements contents for RF testing | Huawei | RAN5#112 (Aug-26) |  | Yaping Zhang <zhangyaping13@huawei.com> | 1 | 0% | 0% |  | 0%
TS 38.591-1: Common test environment - Test environments for Signalling test
|  | 38.591-1 | 6 | Test environment for Signalling test | New clause header |  |  |  |  | TBD
TBD |  | 38.591-1 | 6.1 | Requirements of test equipment | Add test environment requirements for signalling test cases |  | RAN5#112 (Aug-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 6.2 | Reference test conditions | Add test conditions for signalling test cases |  | RAN5#112 (Aug-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 6.3 | Reference system configurations | Add reference system configurations for signalling test cases |  | RAN5#112 (Aug-26) |  |  | 1 | 0% | 0% |  | 0%
TS 38.591-1: Common test environment - Test environments for RRM test
|  | 38.591-1 | 7 | Test environment for RRM test | New clause header |  |  |  |  | TBD
TBD |  | 38.591-1 | 7.1 | Requirements of test equipment | Add test environment requirements for RRM testing |  | RAN5#112 (Aug-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 7.2 | Reference test conditions | Add test conditions for RRM testing |  | RAN5#112 (Aug-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | 7.3 | Default message and information elements contents | Add default message and information elements contents for RRM testing | Huawei | RAN5#112 (Aug-26) |  | Yaping Zhang <zhangyaping13@huawei.com> | 1 | 0% | 0% |  | 0%
TS 38.591-1: Common test environment - Common parts (Annexes)
TBD |  | 38.591-1 | Annex A (informative) | Connection Diagrams | Add connection diagrams |  | RAN5#112 (Aug-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-1 | Annex B (informative) | Calculation of test frequencies | Add calculation of test frequencies |  | RAN5#112 (Aug-26) |  |  | 1 | 0% | 0% |  | 0%
AIoT RF/RRM
TS 38.591-2: RF and RRM conformance test cases - Common parts (general clauses)
|  | 38.591-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.591-2 |  | Foreword | Add Foreword for TS 38.591-2 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-2 | 1 | Scope | Add Scope for TS 38.591-2 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-2 | 2 | References | Add References for TS 38.591-2 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-2 | 3 | Definitions, symbols and abbreviations | Add Definitions, symbols and abbreviations for TS 38.591-2 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
|  | 38.591-2 | 4 | General | New clause header |  |  |  |  | TBD
TBD |  | 38.591-2 | 4.1 | Relationship between minimum requirements and test requirements | Add Relationship between minimum requirements and test requirements for TS 38.591-2 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-2 | 4.2 | Applicability of minimum requirements | Add Applicability of minimum requirements for TS 38.591-2 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
|  | 38.591-2 | 5 | Operating bands and channel arrangement | New clause header |  |  |  |  | TBD
TBD |  | 38.591-2 | 5.1 | General |  | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-2 | 5.2 | Operating bands | Add Operating bands for TS 38.591-2 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-2 | 5.3 | Channel bandwidth | Add Channel bandwidth for TS 38.591-2 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
|  | 38.591-2 | 5.3 | Channel bandwidth | New clause header |  |  |  |  | TBD
|  | 38.591-2 | 5.3.1 | R2D Channel bandwidth | New clause header |  |  |  |  | TBD
TBD |  | 38.591-2 | 5.3.1.1 | General |  | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-2 | 5.3.1.2 | R2D Transmission bandwidth | Add R2D Transmission bandwidth for TS 38.591-2 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-2 | 5.3.1.3 | Minimum guardband and R2D transmission bandwidth configuration | Add Minimum guardband and R2D transmission bandwidth configuration for TS 38.591-2 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-2 | 5.3.1.4 | RB alignment | Add RB alignment for TS 38.591-2 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-2 | 5.3.1.5 | R2D channel bandwidth per operating band | Add BS channel bandwidth per operating band for TS 38.591-2 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
|  | 38.591-2 | 5.3.2 | D2R Channel bandwidth | New clause header |  |  |  |  | TBD
TBD |  | 38.591-2 | 5.3.2.1 | General |  | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-2 | 5.3.2.2 | D2R Transmission bandwidth | Add D2R Transmission bandwidth for TS 38.591-2 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-2 | 5.3.2.3 | D2R channel bandwidth per operating band | Add D2R channel bandwidth per operating band for TS 38.591-2 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
|  | 38.591-2 | 5.4 | Channel arrangement | New clause header |  |  |  |  | TBD
|  | 38.591-2 | 5.4.1 | R2D Channel raster | New clause header |  |  |  |  | TBD
TBD |  | 38.591-2 | 5.4.1.1 | AIoT-ARFCN and channel raster | Add AIoT-ARFCN and channel raster for TS 38.591-2 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-2 | 5.4.1.2 | Channel raster to resource element mapping | Add Channel raster to resource element mapping for TS 38.591-2 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-2 | 5.4.1.3 | Channel raster entries for each operating band | Add Channel raster entries for each operating band for TS 38.591-2 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TS 38.591-2: RF and RRM conformance test cases - Tx
|  | 38.591-2 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.591-2 Tx | 6 | Transmitter characteristics | New clause header |  |  |  |  | TBD
TBD |  | 38.591-2 Tx | 6.0 | General |  | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
|  | 38.591-2 Tx | 6.1 | Backscatter power | New clause header |  |  |  |  | TBD
TBD | Y | 38.591-2 Tx | 6.1.1 | Device backscatter power | Add test case for Device backscatter power |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
|  | 38.591-2 Tx | 6.2 | Output RF spectrum emissions | New clause header |  |  |  |  | TBD
|  | 38.591-2 Tx | 6.2.1 | Out of band emissions | New clause header |  |  |  |  | TBD
TBD |  | 38.591-2 Tx | 6.2.1.1 | General |  | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD | Y | 38.591-2 Tx | 6.2.1.2 | Spectrum emission mask | Add test case for Spectrum emission mask |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 38.591-2 Tx | 6.2.2 | Spurious emissions | Add test case for Spurious emissions |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
TS 38.591-2: RF and RRM conformance test cases - Rx
|  | 38.591-2 Rx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.591-2 Rx | 7 | Receiver characteristics | New clause header |  |  |  |  | TBD
TBD |  | 38.591-2 Rx | 7.1 | General |  | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
|  | 38.591-2 Rx | 7.2 | Reference sensitivity power level | New clause header |  |  |  |  | TBD
TBD |  | 38.591-2 Rx | 7.2.1 | General |  | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD | Y | 38.591-2 Rx | 7.2.2 | Reference sensitivity power level | Add test case for Reference sensitivity power level |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 38.591-2 Rx | 7.2.3 | EIS partial sphere coverage | Add test case for EIS partial sphere coverage |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 38.591-2 Rx | 7.3 | Maximum input level | Add test case for Maximum input level |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
TS 38.591-2: RF and RRM conformance test cases - OTA test characteristics
|  | 38.591-2 OTA | 8 | OTA test characteristics | New clause header |  |  |  |  | TBD
|  | 38.591-2 OTA | 8.1 | General | New clause header |  |  |  |  | TBD
TBD |  | 38.591-2 OTA | 8.1.1 | Testing bands | Add descriptions for Testing bands | CMCC | RAN5#111 (May-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 0% | 0% |  | 0%
|  | 38.591-2 OTA | 8.2 | Performance metrics | New clause header |  |  |  |  | TBD
TBD |  | 38.591-2 OTA | 8.2.1 | Performance metric of Tx requirements | Add descriptions for Performance metric of Tx requirements | CMCC | RAN5#111 (May-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-2 OTA | 8.2.2 | Performance metric of Rx requirements | Add descriptions for Performance metric of Rx requirements | CMCC | RAN5#111 (May-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 0% | 0% |  | 0%
|  | 38.591-2 OTA | 8.3 | Device positioning guidelines | New clause header |  |  |  |  | TBD
TBD |  | 38.591-2 OTA | 8.3.1 | Free space | Add descriptions for Free space | CMCC | RAN5#111 (May-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 0% | 0% |  | 0%
|  | 38.591-2 OTA | 8.4 | Anechoic Chamber method | New clause header |  |  |  |  | TBD
TBD |  | 38.591-2 OTA | 8.4.1 | General |  | CMCC | RAN5#111 (May-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-2 OTA | 8.4.2 | Backscattering measurement procedure | Add descriptions for Backscattering measurement procedure | CMCC | RAN5#111 (May-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-2 OTA | 8.4.3 | Sensitivity measurement procedure | Add descriptions for Sensitivity measurement procedure | CMCC | RAN5#111 (May-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-2 OTA | 8.4.4 | Unwanted emission measurement procedure | Add descriptions for Unwanted emission measurement procedure | CMCC | RAN5#111 (May-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 0% | 0% |  | 0%
TS 38.591-2: RF and RRM conformance test cases - RRM
|  | 38.591-2 RRM |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
|  | 38.591-2 RRM | 9 | RRM | New clause header |  |  |  |  | TBD
TBD |  | 38.591-2 RRM | 9.1 | Introduction |  | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD | Y | 38.591-2 RRM | 9.2 | Test case for Ambient IoT device | Introducing the test case corresponding to 9A.2 of TS 38.191 | CMCC | RAN5#110 (Feb-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 0% | 0% |  | 0%
TR 38.9xx: MU/TT and TP analysis for Tx/Rx test cases
|  | 38.9xx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.9xx | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.9xx | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
Reader and CN protocol
TS 38.591-3: Protocol test cases
|  | 38.591-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.591-3 |  | Foreword |  |  | RAN5#111 (May-26) |  |  | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-3 | 1 | Scope |  |  | RAN5#111 (May-26) |  |  | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-3 | 2 | References |  |  | RAN5#111 (May-26) |  |  | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-3 | 3 | Definitions, symbols and abbreviations |  |  | RAN5#111 (May-26) |  |  | 0.5 | 0% | 0% |  | 0%
|  | 38.591-3 | 4 | Overview | New clause header |  |  |  |  | TBD
TBD |  | 38.591-3 | 4.1 | Test methodology |  |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-3 | 4.2 | Implicit testing |  |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-3 | 4.3 | Repetition of tests |  |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-3 | 5 | Reference conditions, generic and test procedures, test parameters |  |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
MAC
TBD |  | 38.591-3 | 6 | Layer 2 | New sub-clause header |  |  |  |  | TBD
TBD |  | 38.591-3 | 6.1 | MAC | New sub-clause header |  |  |  |  | TBD
TBD |  | 38.591-3 | 6.1.1 | Inventory | New sub-clause header |  |  |  |  | TBD
TBD | Y | 38.591-3 | 6.1.1.1 | A-IoT paging CBRA/successful/Failure/Contention resolution failure | TP1 with { Device receives paging message indicating indicates CBRA with new Transaction ID, and Paging ID field is included} ensure that { when { Paging ID is not matched} then { The device doesn't transmit the Access Random ID message} } TP2 with { Device receives paging message with new Transaction ID, and the Paging ID Presence Indication field indicates Paging ID field is included} ensure that { when { Paging ID is matched} then { The device transmits the Access Random ID message} } TP3 with { Device has transmitted the Access Random ID messag, and it doesn't receive the Random ID Response message ensure that { when { Device receives paging message indicating indicates CBRA with the same Transaction ID, and Paging ID field is matched } then { The device transmits the Access Random ID message} } TP4 with { Device has transmited the Access Random ID message, and it receives the Random ID Response message} ensure that { when { The Random ID included in the Random ID Response message doesn't match } then { The device doesn't transmit the D2R Upper Layer Data Transfer message} } TP5 with { Device has transmited the Access Random ID message, and it receives the Random ID Response message} ensure that { when { The Random ID included in the Random ID Response message matches } then { The device transmits the D2R Upper Layer Data Transfer message} } TP6 with { Device receives the Random ID Response message} ensure that { when { The AS-ID matches } then { The device transmits the D2R Upper Layer Data Transfer message} } TP7 with { Device receives paging message indicating indicates CBRA with the same Transaction ID} ensure that { when { The Paging ID field is matched } then { The device doesn't transmit the Access Random ID message} } | Huawei | RAN5#111 (May-26) |  | Chunying Gu <guchunying@huawei.com> | 1 | 0% | 0% |  | 0%
TBD | Y | 38.591-3 | 6.1.1.2 | A-IoT paging CBRA/Failure/NACK message | TP1 with { Device receives paging message indicating indicates CBRA with new Transaction ID, and group Paging ID field inclcuding PLMN ID is included} ensure that { when { The PLMN ID is matched} then { The device transmits the Access Random ID message} } TP2 with { Device has transmited the Access Random ID message, and it receives the Random ID Response message} ensure that { when { The Random ID included in the Random ID Response message matches } then { The device transmits the D2R Upper Layer Data Transfer message} } TP3 with { Device receives the NAC Feedback message, and the AS-ID matches} ensure that { when { Device receives paging message indicating indicates CBRA with the same Transaction ID, and Paging ID field is matched } then { The device transmits the Access Random ID message}} | Huawei | RAN5#111 (May-26) |  | Chunying Gu <guchunying@huawei.com> | 1 | 0% | 0% |  | 0%
TBD | Y | 38.591-3 | 6.1.1.3 | A-IoT paging CFA | TP1 with { Device receives paging message indicating indicates CFA with new Transaction ID} ensure that { when { The Paging ID is not matched} then { The device doesn't transmit the D2R Upper Layer Data Transfer message} } TP2 with { Device receives paging message indicating indicates CFA with new Transaction ID} ensure that { when { The Paging ID is matched} then { The device transmits the D2R Upper Layer Data Transfer message} } | Huawei | RAN5#111 (May-26) |  | Chunying Gu <guchunying@huawei.com> | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-3 | 6.1.2 | Command | New sub-clause header |  |  |  |  | TBD
TBD | Y | 38.591-3 | 6.1.2.1 | A-IoT Command Reading | TP1 with { Device finished CBRA access procedure, and it receives R2D Upper Layer Data Transfer message} ensure that { when { The AS-ID is not matched} then { The device doesn't transmit the D2R Upper Layer Data Transfer message} } TP2 with { Device finished CBRA access procedure, and it receives R2D Upper Layer Data Transfre message} ensure that { when { The AS-ID is matched} then { The device transmits the D2R Upper Layer Data Transfer message} } TP3 with { Device recieves the R2D Upper Layer Data Transfer message} ensure that { when { The Received Data Size field is set to 0} then { The device retransmits the D2R Upper Layer Data Transfer message} } |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 38.591-3 | 6.1.2.2 | A-IoT Command Writing | TP1 with { Device finished CFA access procedure } ensure that { when { Device receives R2D Upper Layer Data Transfer message} then { The device transmits the D2R Upper Layer Data Transfer message} } |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 38.591-3 | 6.1.2.3 | A-IoT Command Permanent Disabling | TP1 with { Device finished CFA access procedure } ensure that { when { Device receives R2D Upper Layer Data Transfer message} then { The device transmits the D2R Upper Layer Data Transfer message} } TP2 with { Device receives paging message indicating indicates CBRA with new Transaction ID, and Paging ID field is included} ensure that { when { Paging ID is matched} then { The device doesn't transmit the Access Random ID message} } |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-3 | 6.1.3 | Transport size selection | New sub-clause header |  | TBD |  |  | TBD
TBD | Y | 38.591-3 | 6.1.3.1 | D2R transport size selection | with { Device finished CFA access procedure } ensure that { when { Device receives R2D Upper Layer Data Transfer message with D2R Scheduling Info } then { Device transmits D2R Upper Layer Data transfer message with requested TB size} } | Huawei | RAN5#111 (May-26) |  | Chunying Gu <guchunying@huawei.com> | 1 | 0% | 0% |  | 0%
TBD | Y | 38.591-3 | 6.1.3.2 | R2D transport size selection | with { Device finished CFA access procedure } ensure that { when { Device receives R2D Upper Layer Data Transfer message indicating R2D TBS } then { Device decodes the R2D Upper layer Data Transfer message} } | Huawei | RAN5#111 (May-26) |  | Chunying Gu <guchunying@huawei.com> | 1 | 0% | 0% |  | 0%
NAS
TBD |  | 38.591-3 | 7 | NAS | New sub-clause header |  |  |  |  | TBD
TBD |  | 38.591-3 | 7.1 | Inventory | New sub-clause header |  |  |  |  | TBD
TBD | Y | 38.591-3 | 7.1.1 | Inventory with filtering information | with { Device receives paging message, and teh AIoT identification information includes filtering information} ensure that { when { The filtering element is PLMN ID matches the PLMN ID field in the AIoT device permanent identifier} then { The device responds to the AIoT paging} } |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
TBD |  | 38.591-3 | 7.2 | STATUS report | New sub-clause header |  |  |  |  | TBD
TBD | Y | 38.591-3 | 7.2.1 | STATUS report/Command type specific parameters invalid | with { Device has finished inventory procedure} ensure that { when { The device receives write command message, and the offset where to write the application data exceeds the device's memory} then { Device transmits D2R Upper Layer Data Transfer carring STATUS message with cause #1 "Command type specific paramete rs invalid"} } |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 38.591-3 | 7.2.2 | STATUS report/Low energy | with { Device has finished inventory procedure} ensure that { when { The device receives write command message, and the device can't execute the write command procedure the energy will be run out} then { Device transmits D2R Upper Layer Data Transfer carring STATUS message with cause #3 "Low energy"} } |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 38.591-3 | 7.2.3 | STATUS report/Invalid mandatory information | with { Device has finished inventory procedure} ensure that { when { The device receives command message with missing IE} then { Device transmits D2R Upper Layer Data Transfer carring STATUS message with cause #96 "Invalid mandatory information"} } |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
TBD | Y | 38.591-3 | 7.2.4 | STATUS report/message type non-existent or not implemented | with { Device has finished inventory procedure} ensure that { when { The device receives command message with matching AS-ID, and the device doesn't support the message type} then { Device transmits D2R Upper Layer Data Transfer carring STATUS message with cause #97 "message type non-existent or not implemented" } } |  | RAN5#111 (May-26) |  |  | 1 | 0% | 0% |  | 0%
TS 38.591-5: Protocol test suites (TTCN)
|  | 38.591-5 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.591-5 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
Applicability
TS 38.591-4: Applicability of Tx, Rx, RRM, Protocol test cases and Common Implementation Conformance Statement (ICS) proforma
|  | 38.591-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.591-4 |  | Foreword | Add Foreword for 38.591-4 | CMCC | RAN5#111 (May-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | 1 | Scope | Add Scope for 38.591-4 | CMCC | RAN5#111 (May-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | 2 | References | Add References for 38.591-4 | CMCC | RAN5#111 (May-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | 3 | Definitions, symbols and abbreviations | Add Definitions, symbols and abbreviations for 38.591-4 | CMCC | RAN5#111 (May-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
|  | 38.591-4 | 4 | Recommended test case applicability | New sub-clause header |  | TBD |  |  | TBD
TBD |  | 38.591-4 | 4.0 | Introduction | Add introduction of the rules for identifying individual test case applicability | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | 4.1 | Test case conditions and selection criteria | Add the conditions and selection criteria for the specific test cases | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | 4.2 | RF conformance test cases | Add the applicability for the specific RF test cases | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | 4.3 | RRM conformance test cases | Add the applicability for the specific RRM test cases | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | 4.4 | Protocol conformance test cases | Add the applicability for the specific SIG test cases | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
|  | 38.591-4 | Annex A (informative) | ICS proforma for NR/5GS Generation User Equipment | New sub-clause header |  | TBD |  |  | TBD
|  | 38.591-4 | A.1 | Guidance for completing the ICS proforma | New sub-clause header |  | TBD |  |  | TBD
TBD |  | 38.591-4 | A.1.1 | Purposes and structure | Add the purposes and structure description of the ICS proforma | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | A.1.2 | Abbreviations and conventions | Add abbreviations and conventions of the ICS proforma | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | A.1.3 | Instructions for completing the ICS proforma | Add instructions for completing the ICS proforma | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | A.2 | Identification of the User Equipment | Add the detailed identification of the User Equipment | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | A.3 | Identification of the protocol | Add the identification of the protocol | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
|  | 38.591-4 | A.4 | ICS proforma tables | New sub-clause header |  | TBD |  |  | TBD
TBD |  | 38.591-4 | A.4.1 | UE Implementation Types | Add ICS proforma tables for UE Implementation Types | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | A.4.2 | UE Service Capabilities | Add ICS proforma tables for UE Service Capabilities | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | A.4.3 | Baseline Implementation Capabilities | Add ICS proforma tables for Baseline Implementation Capabilities | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | A.4.3.1 | RF Baseline Implementation Capabilities | Add ICS proforma tables for RF Baseline Implementation Capabilities | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | A.4.3.2 | Physical Layer Baseline Implementation Capabilities | Add ICS proforma tables for Physical Layer Baseline Implementation Capabilities | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | A.4.3.3 | MAC Implementation Capabilities | Add ICS proforma tables for MAC Implementation Capabilities | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | A.4.3.4 | Measurement Capabilities | Add ICS proforma tables for Measurement Capabilities | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | A.4.3.5 | General Capabilities | Add ICS proforma tables for General Capabilities | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | A.4.3.6 | Mobility Capabilities | Add ICS proforma tables for Mobility Capabilities | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | A.4.3.7 | Additional capabilities for UE declared capability | Add ICS proforma tables for Additional capabilities for UE declared capability | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
TBD |  | 38.591-4 | A.4.4 | Additional information | Add ICS proforma tables for Additional information | CMCC | RAN5#112 (Aug-26) |  | Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.