## PerMeeting
|  | Maintenance | 5GA | 6G Study | Buffer
Aug'25 | 3GPPSA3#123 | 12 | 4 |  | 5
Oct'25 | 3GPPSA3#124 | 6 | 11 | 3 | 1
Nov.25 | 3GPPSA3#125 | 6 | 11 | 3 | 1 | Last meeting for 5GA SIDs Agreement
Feb'26 | 3GPPSA3#126 | 6 | 7 | 7 | 1 | Last meeting for 6G SIDs Agreement
April'26 | 3GPPSA3#127 | 6 | 7 | 7 | 1
May'26 | 3GPPSA3#128 | 6 | 8 | 6 | 1
Aug'26 | 3GPPSA3#129 | 6 | 8 | 6 | 1 | Sep'26 Stage 2 Freeze
Oct'26 | 3GPPSA3#130 | 6 | 7 | 7 | 1
Nov'26 | 3GPPSA3#131 | 6 | 8 | 6 | 1
Feb'27 | 3GPPSA3#132 | 6 | 8 | 6 | 1 | March'27 Stage 3 Freeze
April'27 | 3GPPSA3#133 | 6 |  | 14 | 1
May'27 | 3GPPSA3#134 | 6 |  | 14 | 1 | June'27 Rel-20 Completion
|  | 78 | 79 | 79 | 16
#Early closure for Social evening on Wednesday

## OverallAllocation
ID | Tech | SID/WID Title | Acronym | # 5GA TUs | # 6G TUs
1 | 5GA | Mission critical security for Rel-20 | MCX20-SEC | 1
2 | 5GA+6G | Study on Transitioning to Post Quantum Cryptography in 3GPP | FS_CryptoPQC | 3 | 3
3 | 5GA | Security Assurance Specification for 5G-Advanced | SCAS_5GA | 4
4 | 5GA | Security related Events Handling | SECHAND | 4
5 | 5GA | Study on AIMLE Service Security | FS_AIMLE_SEC | 3
6 | 5GA | New SID on Security Aspects for IMS resiliency | FS_IMSRE_SEC | 3
7 | 5GA | New SID on Security Aspect for NR Femto Phase 2 | FS_NR_Femto_SEC_Ph2 | 3
8 | 5GA | New SID on Security aspects of WAB nodes for NR | FS_5G_WAB_SEC | 3
9 | 5GA | New SID on security for PLMN hosting a NPN phase 2 | FS_PLMNNPN_Ph2 | 3
10 | 5GA | Study on providing PSK for MPQUIC/TLS | FS_PSK_MQC_TLS | 1.5
11 | 5GA | New SID on Security of AIML_Ph2 | FS_AIML_CN_Ph2_SEC | 3.5
12 | 5GA | New SID on security aspects of Integrated Sensing and Communication | FS_Sensing_SEC | 6
13 | 5GA | New SID on 5G Security Assurance Specification (SCAS) for the Container-based Products | FS_SCAS_CP | 3
14 | 5GA | New SID on Security Aspects of 5G Satellite Access Phase 4 | FS_5GSAT_Ph4_SEC | 3
15 | 6G | Study on supporting AEAD algorithms | FS_AEAD |  | 5
16 | 5GA | Study on Security aspects of CAPIF Phase 4 | FS_CAPIF_Ph4_SEC | 3
17 | 5GA | New WID on PRINS Refinement | RefinePRINS | 1
18 | 5GA | SID Study on best security practice for SBA | FS_BSP4SBA | 2 | 1
19 | 5GA | Study on Security Aspect of Ambient IoT Services in 5G phase 2 | FS_AIoT_SEC_Ph2 | 12
20 | 5GA | New WID on SCAS for NR Femto | SCAS_NR_Femto | 1.5
21 | 5GA | New WID on SCAS for NR Femto SeGW | SCAS_Femto_SeGW | 1
22 | 6G | Study on Security for the 6G System | FS_6G_SEC |  | 50
23 | 5GA | New WID on Security Assurance Specification (SCAS) for the CAPIF Core Function | SCAS_5GA_CAPIF | 2
24 | 5GA | New Study on enhanced security management service for security configuration provisioning | FS_SCP | 4
|  |  | TUs Allocated: | 70.5 | 59
|  |  | Max acceptable TUs | 70 | 70 | Though total TU Budget is 79 each
|  |  | TUs remaining: | -0.5 | 11
Note on E20: Rajvel: Allocated 7.5 only Action on it needed, either to allocate 12 TUs or reduce the scope to 7.5 TUs

## Tracking
S.NO | Tech | Tdoc | Acronym | SID/WID Title | S.TUs | N. TUs | Total | TUs consumed in SA3#123 | TUs consumed in SA3#124 | TUs consumed in SA3#125 | Allocated TUs for SA3#126 | Balance TUs | TR number | Rapporteur | Information | Approval
1 | 5GA | SP-250876 | SECHAND | Security related Events Handling |  | 4 | 4 | 1 | 1 | 1 | 0.5 | 0.5 | 33.502 | susana.sabater@vodafone.com, qiminpeng@chinamobile.com | SA#109 (Sep 25) | SA#110 (Dec 25) SA#111 (Mar 26)
2 | 5GA | SP-251237 | FS_IMSRE_SEC | Study on Security Aspects of IMS resiliency | 2.5 | 0.5 | 3 |  | 0.25 | 0 | 0 | 2.75 | 33.768 | Rohini Rajendran (Samsung, r.rohini@samsung.com) | SA#110 (Dec 25) | SA#111 (Mar 26)
3 | 5GA | SP-251238 | FS_AIMLE_SEC | Study on AIMLE Service Security | 2 | 1 | 3 |  | 0.25 | 0.5 | 0.5 | 1.75 | 33.786 | Sheeba Backia Mary Baskaran (Lenovo, smary@lenovo.com) | SA#110 (Dec 25) | SA#111 (Mar 26)
4 | 5GA | SP-251240 | FS_PSK_MQC_TLS | Study on providing PSK for MPQUIC/TLS | 1 | 0.5 | 1.5 |  | 0.5 | 0.5 | 0.25 | 0.25 | 33.778 | Li He, (Huawei, lihe2@huawei.com) | SA#110 (Dec 25) | SA#111 (Mar 26)
5 | 5GA | SP-251241 | FS_AIML_CN_Ph2_SEC | Study on Security for Core Network Enhanced Support for Artificial Intelligence (AI) / Machine Learning (ML)_Ph2 | 3 | 0.5 | 3.5 |  | 0.5 | 0.5 | 0.5 | 2 | 33.785 | Primary: Samir (InterDigital, samir.ferdi@interdigital.com) Secondary: Xie Zhenhua (vivo, zhenhua.xie@vivo.com) | SA#110 (Dec 25) | SA#111 (Mar 26)
6 | 5GA | SP-251248 | FS_BSP4SBA | Best security practice for SBA | 3 |  | 3 |  | 0.5 | 0.5 | 0.5 | 1.5 | 33.755 | Imran Saleem (Huawei, imran.saleem1@huawei.com) | SA#111 (Mar 26) | SA#111 (Mar 26)
7 | 5GA | SP-251251 | RefinePRINS | PRINS Refinement |  | 1 | 1 |  | 0.25 | 0.25 | 0 | 0.5 | CRs | Tao Wan (CableLabs, t.wan@cablelabs.com) |  | SA#111 (Mar 26)
8 | 5GA | SP-251239 | FS_PLMNNPN_Ph2 | Study on security for PLMN hosting a NPN phase2 | 2 | 1 | 3 |  | 0.5 | 0 | 0.5 | 2 | 33.758 | Primary: Jun Shen (China Telecom, shenjun6@chinatelecom.cn) Secondary: Yuze Liu (ZTE, liu.yuze@zte.com.cn) | SA#111 (Mar 26) | SA#112 (June 26)
9 | 5GA | SP-251242 | FS_Sensing_SEC | Study on Security and Privacy Aspects of Integrated Sensing and Communication | 4.5 | 1.5 | 6 |  | 1 | 1 | 1 | 3 | 33.777 | Primary: Henry Leung (Xiaomi, lianghaoran@xiaomi.com), Secondary: Leyi Zhang (ZTE, leyi.zhang@zte.com.cn) | SA#111 (Mar 26) | SA#112 (June 26)
10 | 5GA | SP-251244 | FS_5GSAT_Ph4_SEC | Study on Security Aspects of Satellite Access in 5G Phase 4 | 2 | 1 | 3 |  | 0.5 | 0.5 | 0.5 | 1.5 | 33.700-30 | Primary: Hongil Kim (Qualcomm, hongilk@qti.qualcomm.com) Secondary: Wei Zhou (CATT, zhouwei@catt.cn) | SA#111 (Mar 26) | SA#112 (June 26)
11 | 5GA | SP-251246 | FS_AIoT_SEC_Ph2 | Study on security aspect of Ambient IoT services-phase 2 | 7.5 | 4.5 | 12 |  | 0.5 | 1 | 1 | 9.5 | 33.714 | Primary: Lihui Xiong (OPPO, xionglihui@oppo.com) Secondary: Guo Longhua (Huawei, guolonghua@huawei.com) | SA#111 (Mar 26) | SA#112 (June 26)
12 | 5GA | SP-251249 | FS_NR_Femto_SEC_Ph2 | Study on security aspect for NR Femto phase2 | 2 | 1 | 3 |  | 0.5 | 0.25 | 0.5 | 1.75 | 33.746 | Peilin Liu (ZTE, liu.peilin@zte.com.cn) | SA#112 (June 26) | SA#112 (June 26)
13 | 5GA | SP-251250 | FS_5G_WAB_SEC | Study on security aspects of WAB nodes for NR | 2 | 1 | 3 |  | 0.5 | 0.5 | 0.5 | 1.5 | 33.724 | Weihan Gao (China Telecom), gaowh@chinatelecom.cn | SA#112 (June 26) | SA#112 (June 26)
14 | 5GA | SP-251252 | SCAS_NR_Femto | Security Assurance Specification (SCAS) for NR Femto |  | 1.5 | 1.5 |  | 0.25 | 0.5 | 0 | 0.75 | 33.546 | Zhonghuai Xie (China Unicom, xiezh55@chinaunicom.cn) | SA#111 (Mar 26) | SA#112 (June 26)
15 | 5GA | SP-251253 | SCAS_Femto_SeGW | Security Assurance Specification for NR Femto security gateway(SeGW) |  | 1 | 1 |  | 0.25 | 0.25 | 0 | 0.5 | 33.547 | Shihan Bao (CATT, baoshihan@cictmobile.com) | SA#111 (Mar 26) | SA#112 (June 26)
16 | 5GA | SP-250653 | MCX20-SEC | Mission Critical security for Release 20 |  | 1 | 1 | 0.25 | 0 | 0.25 | 0 | 0.5 | CRs | tim.woodward@motorolasolutions.com |  | SA#112 (June 26)
17 | 5GA+6G | SP-250858 | FS_CryptoPQC | Study on transitioning to Post Quantum Cryptography (PQC) in 3GPP | 6 |  | 6 | 1 | 1.25 | 1 | 1 | 1.75 | 33.703 | Primary: lei.zhongding@huawei.com, Secondary: virendra@qti.qualcomm.com | SA#111 (Mar 26) | SA#112 (June 26)
18 | 5GA | SP-251243 | FS_SCAS_CP | Study on Security Assurance Specification (SCAS) for Container-based Product | 2 | 1 | 3 |  | 0.5 | 0.25 | 0.25 | 2 | 33.73 | Markus Hanhisalo (Ericsson, markus.hanhisalo@ericsson.com) | SA#113 (Sep 26) | SA#113 (Sep 26)
19 | 5GA | SP-251245 | FS_CAPIF_Ph4_SEC | Study on security aspects of CAPIF Phase 4 | 2 | 1 | 3 |  | 0.5 | 0.5 | 0.5 | 1.5 | 33.700-23 | Weiyin Zhang(China Telecom, zhangwy12@chinatelecom.cn) | SA#112 (June 26) | SA#113 (Sep 26)
20 | 6G | SP-251247 | FS_AEAD | Study on supporting AEAD algorithms | 5 |  | 5 |  | 0.5 | 1 | 1 | 2.5 | 33.771 | Primary: Yuto Nakano (KDDI, yt-nakano@kddi.com) Secondary: Hu Li (vivo, huli@vivo.com) | SA#112 (June 26) | SA#113 (Sep 26)
21 | 5GA | SP-250877 | SCAS_5GA | Security Assurance Specification for 5G-Advanced |  | 4 | 4 | 1 | 0.25 | 0.5 | 0.5 | 1.75 | CRs | raina.wu@huawei.com |  | SA#113 (Sep 26)
22 | 6G | SP-251233 | FS_6G_SEC | Study on Security for the 6G System | 50 |  | 50 |  | 2 | 2 | 3 | 43 | 33.801-01 | Primary: Todor Gamishev (Orange, todor.gamishev@orange.com) Secondary: Suresh Nair (Nokia, suresh.p.nair@nokia.com) | SA#114 (Dec 26) | SA#116 (Jun 27)
23 | 5GA | SP-251672 | SCAS_5GA_CAPIF | Security Assurance Specification (SCAS) for the CAPIF Core Function |  | 2 | 2 |  |  |  | 0.25 | 1.75 | 33.531 | Primary Rapporteur: Lisanne Gebhardt, BSI (DE) (lisanne.gebhardt@bsi.bund.de ) Secondary Rapporteur: Raghavendran Ramiya, Rakuten Mobile (raghavendran.ramiya@rakuten.com ) | SA#111 (Mar 26) | SA#112 (June 26)
24 | 5GA | SP-251658 | FS_SCP | Study on enhanced security management service for security configuration provisioning | 4 |  | 4 |  |  |  | 0.25 | 3.75 | 33.704 | Minpeng Qi, CMCC (qiminpeng@chinamobile.com) | SA#113 (Sep 26) | SA#114 (Dec 26)
[7 empty] | 71.5 |  |  |  |  | 43.75 | 27.75
[7 empty] | 58 |  |  |  |  | 45.5 | 12.5