## Slide 1: Executive Report of SA5#165 SWG Charging Charging Management (CH)
Gerald Görmer, SA5 Charging SWG Chair, MATRIXX Software

## Slide 2: General information
SA5 SWG CH work status:
  Focus at this meeting on progress on Rel-20 5GA and Rel-20 6G charging work
  No CH rapporteur call planned because of upcoming two SA5 meetings
SA5 SWG CH statistics:
  Registration at this meeting
  52 delegates face-to-face
  23 delegates online
  Participation to this meeting
  21 delegates attended
  Documents at this meeting
  97 total input and 77 output contributions
  3 contributions from the CH plenary
  1 LSin and 1 LSout
  no new Rel-20 WID or SID
  1 CR for Rel-20 WID
  60 pCRs for Rel-20 and 1 TR for Information
  5 TR email approvals
  6 agreed CRs for Maintenance

## Slide 3: Incoming LSs
Tdoc | Title | Source | Decision | Reply In
S5-260028 | LS on Energy Related Information to CHF (S2-2511033; to: SA5 | SA2 | replied | S5-260520

## Slide 4: Outgoing LSs
Tdoc | Title | To | Cc | Reply To
S5-260520 | Reply LS on Energy Related Information to CHF | SA2 | , | S5-260028

## Slide 5: Charging (CH) WIs/SIs

## Slide 6
New or Revised Charging WIDs/SIDs
Number | Title | Source

## Slide 7
Charging TSs & TRs to be sent to SA#111
Number | Title | For
S5-260558 | Presentation of TR 32.872 for information | Information

## Slide 8
Charging Exception requests
Number | Title

## Slide 9: SA5 Charging progress – Summary
UID | Name | Acronym | Target (dd/mm/yyyy) | Old % | WID | New % | Change or comment
 | Rel-20 5GA Work Items | ------ | ----- | ------ | ---- | ---- | 
1090012 | Charging Aspects on XRM | XRM_Ph2-CH | 12/06/2026 | 10 % | SP-251214 | 20 % | 
1100017 | Charging aspects of next generation real time communication services phase 2 | Ph2_NG_RTC_Ph2-CH | 12/12/2026 | 0 % | SP-251695 | 0 % | No contribution
 | Rel-20 5GA Studies | ------ | ----- | ------ | ----- | ---- | 
1080014 | Study on Charging Aspects of CAPIF phase 3 | FS_CAPIF_Ph3_CH | 12/06/2026 | 30 % | SP-250869 | 50 % | 
1090010 | Study on 5GA roaming charging reliability enhancement | FS_RoamRe_CH | 12/03/2026 | 45 % | SP-251203 | 70 % | Completion is guaranteed for SA#112
1100013 | Study on 5GA Charging aspects of integrated sensing and communications | FS_Sensing_CH | 12/09/2026 | 0 % | SP-251665 | 20 % | 
1100012 | Study on Charging Aspects of satellite access phase 4 | FS_5GSAT_Ph4_CH | 12/09/2026 | 0 % | SP-251664 | 15 % | 
 | Rel-20 6G Studies | ------ | ----- | ------ | ----- | ----- | 
1090013 | Study on Charging Aspects of 6G System | FS_6G_CH | 12/03/2027 | 15 % | SP-251218 | 25 % | 
For more information, see the full Work Plan at: ftp://ftp.3gpp.org/information/WorkPlan

## Slide 10: Rel-20 WID on Charging Aspects on XRM
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1090012 | Charging Aspects on XRM | XRM_Ph2-CH | 12/06/2026 | 10 % | SP-251214 | 20 % | 
 | WT-1 |  |  | 70 % |  | 70 % | 
 | WT-2 |  |  | 0 % |  | 0 % | 
 | WT-3 |  |  | 0 % |  | 0 % | 
 | WT-4 |  |  | 0 % |  | 60 % | 
Summary of the progress at this meeting
  WT-1:
  - No progress
  WT-2:
  - No progress
  WT-3:
- No progress
  WT-4:
  - Add information elements to address charging impacts from enhanced QoS handling in XRM
RAN/SA/CT impacts and dependencies:
  No dependencies
Updates/Next steps:
  Stage2 of PDU set handling and Multiplexed media service

## Slide 11: Rel-20 WID on Charging aspects of next generation real time communication services phase 3
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1100017 | Charging aspects of next generation real time communication services phase 3 | Ph2_NG_RTC_Ph2-CH | 12/12/2026 | 0 % | SP-251695 | 0 % | 
 | WT-1 |  |  | 0 % |  | 0 % | 
 | WT-2 |  |  | 0 % |  | 0 % | 
Summary of the progress at this meeting
  WT-1:
  - no progress
  WT-2:
  - no progress
RAN/SA/CT impacts and dependencies:
  Not Identified yet
Updates/Next steps:
  Start the work

## Slide 12: Rel-20 Study on Charging Aspects of CAPIF phase 3
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1080014 | SID on Charging Aspects of CAPIF phase 3 | FS_CAPIF_Ph3-CH | 12/06/2026 | 30 % | SP-250869 | 50 % | 
 | WT-1 |  |  | 20 % |  | 30 % | 
 | WT-2 |  |  | 10 % |  | 20 % | 
Summary of the progress at this meeting
  General
    Total of 12 pCRs
  WT-1:
    6 pCRs approved in TR 28.891
    CAPIF Inter-connection Use cases, key issues and solutions to the UCs (1/2), and evaluation
  WT-2:
    6 pCRs approved in TR 28.891
    Authorization Authentication Use Case (1), key Issues, Charging Requirements , first solutions and evaluation for
  Draft TR 28.891-030 (Email Approval S5-260515)
RAN/SA/CT impacts and dependencies:
  None Identified
Updates/Next steps:
  WT-1, WT-2 Solutions, Evaluations for Topic #1, #2 and #3, and Conclusion to be disucssed

## Slide 13: Rel-20 Study on 5GA roaming charging reliability enhancement
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1090010 | 5GA roaming charging reliability enhancement | FS_RoamRe_CH | 12/03/2026 | 45 % | SP-251203 | 70 % | Completion is guaranteed for SA#112
 | WT-1 |  |  | 80 % |  | 90 % | 
 | WT-2 |  |  | 40 % |  | 60 % | 
Summary of the progress at this meeting
  WT-1:
    Use Case and key issue for CDR Generation after CHF-SMF Connection Loss
    key issue of the trigger conditions in V-CHF
  WT-2:
    - Update solution #1.2, Handling of charging information stored in V-CHF, Solutions of the trigger conditions in V-CHF
    - Handling of V-CTF when V-CTF detected both V-CHF and H-CHF failure at the same time
    - Solution topic 1 KI#1/ KI#2, topic 2 KI#1, topic 3 KI#1/ KI#2 using SBA
    - Partial solution evaluation for Key issue #1.1/ Key issue #1.2/ Key issue #1.3/ Key issue #2.1/ Key issue #3.1/ Key issue #3.2
  Presentation of TR 32.872 for information
  Draft TR 32.872 (email approval S5-260516)
RAN/SA/CT impacts and dependencies:
  None identified
Updates/Next steps:
  Continue to complete solutions, evaluations and conclusions

## Slide 14: Rel-20 Study on 5GA Charging aspects of integrated sensing and communications
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1100013 | Study on 5GA Charging aspects of integrated sensing and communications | FS_Sensing_CH | 12/06/2026 | 0 % | SP-251665 | 20 % | 
 | WT-1 |  |  | 0 % |  | 20 % | 
 | WT-2 |  |  | 0 % |  | 20 % | 
 | WT-3 |  |  | 0 % |  | 0 % | 
Summary of the progress at this meeting
  General of 3 pCRs on
    - add skeleton, scope and background
  WT-1 with 4 pCRs on:
  - business models and use cases for supporting ISAC
  WT-2 with 1 pCR on:
  - charging scenarios and potential charging requirements for supporting ISAC
  Initial skeleton of TR 28.893
  Draft TR 28.893-010 (Email Approval S5-260517)
RAN/SA/CT impacts and dependencies:
  None identified
Updates/Next steps:
  Continue to complete use cases and solutions

## Slide 15: Rel-20 Study on Charging Aspects of satellite access phase 4
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1100012 | Study on Charging Aspects of satellite access phase 4 | FS_5GSAT_Ph4_CH | 12/09/2026 | 0 % | SP-251664 | 15 % | 
 | WT-1 |  |  | 0 % |  | 15 % | 
 | WT-2 |  |  | 0 % |  | 15 % | 
Summary of the progress at this meeting
  General of 4 pCRs on
  - Add skeleton, scope and background
  WT-1 with 2 pCRs on:
  - Use case, charging requirements and KIs for IMS voice call over GEO
  WT-2 with 2 pCRs on: :
  -Use case, charging requirements and KIs for UE-satellite-UE communication
RAN/SA/CT impacts and dependencies:
  None identified
Updates/Next steps:
  Use cases and Solutions for topics

## Slide 16: Rel-20 Study on Charging Aspects of 6G System
UID | Name | Acronym | Target | Old % | WID | New % | Change or comment
1090013 | Charging Aspects of 6G System | FS_6G_CH | 12/03/2027 | 15 % | SP-251218 | 25 % | 
 | WT-1 |  |  | 12 % |  | 25 % | 
 | WT-2 |  |  | 15 % |  | 25 % | 
 | WT-3 |  |  | 0 % |  | 0 % | 
Summary of the progress at this meeting
  General: Update backgoud information and business models in 6G
  WT-1 with 6 pCRs on:
  - Add a new UC/Req/KI of 6G Charging Architecture
  - Add a new UC/Req/KI of Refund
  - Add new solution of Distributed Charging Architecture
  WT-2 with 6 pCRs on :
  - Add a new UC/Req/KI of Charging for Multi-dimensional Resources
  - Add a new UC/Req/KI of Charging Information Collection and Reporting, Optimazation of Charging Sessions and Charging Requests
  - Add a new UC/Req/KI of Failure Handling
  - Add a new UC/Req/KI of Charging for Service with Burst Traffic
    - Add new solutions of Structuring for OpenAPI and ASN.1
  WT-3: Not yet started
  Draft TR 32.801-02 v0.3.0 (Email Approval S5-260519)
RAN/SA/CT impacts and dependencies:
  WT-3 has a dependency on SA2 6G Study
Updates/Next steps:
  Use cases, Potential charging requirements, Key issues, Solutions

## Slide 17: Charging contributions
Maintenance
5GS_Ph1-SBI_CH, TEI18
Rel-20 5GA Work
XRM_PH2-CH

## Slide 18: Thank you!