## Tdoc cover sheet
3GPP TSG-CT WG1 Meeting #157 Sophia-Antipolis, France, 13-17 October 2025 |  | C1-256217
Source: | Samsung Electronics
Title: | Work plan for the CT1 part of Metaverse_App
Agenda item: | 19.42
Document for: | Discussion

## Contributions Plan
Contribution Plan
Spec | Topic | Responsible Company | Related LS or other WG tdoc(s) # | CT1 meeting #; tdoc(s) # | Comments | Open issues
24.550 | Metaverse App Service
| Spatial Anchor Management and Discovery | Samsung, InterDigital | S6-243669 | C1-247060, C1-251064, C1-250988, C1-252393, C1-252394, C1-252395, C1-255577
| Spatial Anchor Subscription | InterDigital, Samsung | S6-243670 | C1-252390, C1-252391, C1-252392
| New text for clause 9 Spatial Map (SM) management | Samsung, InterDigital | S6-243703 | C1-247059, C1-251061, C1-251062, C1-250989, C1-255537
| Spatial anchor update | Samsung, InterDigital | S6-244564 | C1-251063
| Pseudo-CR on enhancements to spatial anchor subscription procedure | InterDigital | S6-244687 | C1-252390, C1-253997, C1-253998, C1-253999
| Pseudo-CR on enhancements to spatial map subscription procedures | Samsung | S6-244689 | C1-255510, C1-255511, C1-255512
| Pseudo-CR on Support for spatial mapping data sources | Samsung | S6-244690 | C1-253993, C1-253994, C1-253995, C1-253993
| Pseudo-CR on localization service |  | S6-244711
| Spatial map procedure updates and Information Flows | Samsung | S6-244712 | C1-250989, C1-247059, C1-251061, C1-251062
| Pseudo-CR on implicit subscription for spatial map ready event | Samsung, Qualcomm Incorporated | S6-245700 | C1-247059, C1-250990
| Pseudo-CR on APIs for Spatial anchors and Spatial map services | Samsung | S6-245506 | C1-255509, C1-255513
DA | Digital Avatar Discovery | Nokia | S6-244579 | C1-252396
DA | Digital assets management | Nokia | S6-244691 | C1-253989, C1-253992, C1-254028, C1-254029, C1-255572
DA | Digital asset discovery APIs | Nokia | S6-245531 | C1-252396
| Removing EN on Get operation | Samsung | S6-250401 | C1-255577
| Enhancements to SM data source services | Samsung | S6-250405 | C1-253993, C1-253996
DA | Proposal for clause 8 digital asset media management |  | S6-250416
| Support for metaverse services requiring multiple devices | Samsung | S6-250419 | C1-255508
| Spatial anchor usage reporting |  | S6-250548

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments

## Outgoing LSs
Outgoing liaision statements (LS)
Tdoc # | Topic | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments