## Tdoc cover sheet
3GPP TSG CT WG3 Meeting #143 Sophia-Antipolis, FR, 13th – 17th October, 2025 |  | C3-254137
Source: | Huawei
Title: | Updated AmbientIoT-CT WI CT3 Work Plan
Agenda item: | 19.70
Document for: | Agreement

## CT3
CT3 Work Plan - CT3#143 - 2025-10 - AmbientIoT-CT WI (CP-252196)
# | Impact Description |  | Specification | Contributing company(ies) | Agreed Tdoc Numbers | Targeted CT3 meeting | Status
1. Support AIoT services exposure
1 | New Naiotf_AIoT Service API to support AIoT services exposure | Service and service operations description clauses | 29.569 (new TS) | Huawei, Lenovo, Nokia, Ericsson | C3-251634, C3-252391, C3-252392, C3-252393, C3-253310, C3-253473, C3-253664, C3-253663 | CT3#140 --> CT3#142 | Completed
2 |  | API general clauses (i.e. Introduction, Usage of HTTP, Error Handling, Feature negotiation, Security) | 29.569 (new TS) | Huawei, Lenovo, Nokia, Ericsson | C3-251057, C3-251577, C3-251058, C3-251640, C3-252390, C3-252057, C3-252394 | CT3#140 --> CT3#142 | Completed
3 |  | API resources and custom operations clauses | 29.569 (new TS) | Huawei, Lenovo, Nokia, Ericsson | C3-251635, C3-252391, C3-252392, C3-252393, C3-253473, C3-253664, C3-253663 | CT3#140 --> CT3#142 | Completed
4 |  | API notifications clauses | 29.569 (new TS) | Huawei, Lenovo, Nokia, Ericsson | C3-251635, C3-252391, C3-252392, C3-252393 | CT3#140 --> CT3#142 | Completed
5 |  | API data model clauses | 29.569 (new TS) | Huawei, Lenovo, Nokia, Ericsson | C3-251635, C3-252391, C3-252392, C3-252393, C3-252398, C3-253473, C3-253664, C3-253663 | CT3#140 --> CT3#143 | Completed
6 |  | OpenAPI description | 29.569 (new TS) | Huawei, Lenovo, Nokia, Ericsson | C3-251579, C3-252391, C3-252392, C3-252393, C3-253473, C3-253664, C3-253663 | CT3#140 --> CT3#143 | Completed
7 |  | Error handling, corrections, general clean-up and resolving ENs | 29.569 (new TS) | Huawei, Lenovo, Nokia, Ericsson | C3-252058, C3-253140, C3-253500 | CT3#141 --> CT3#143 | Ongoing
8 | New Nnef_AIoT Service API to support AIoT services exposure | Service and service operations description clauses | 29.522 | Huawei, Lenovo, Nokia, Ericsson | C3-252395, C3-253497, C3-253665, C3-253498 | CT3#140 --> CT3#142 | Completed
9 |  | API general clauses (i.e. Introduction, Usage of HTTP, Error Handling, Feature negotiation, Security) | 29.522 | Huawei, Lenovo, Nokia, Ericsson | C3-252395, C3-253138, C3-253314 | CT3#140 --> CT3#142 | Completed
10 |  | API resources and custom operations clauses | 29.522 | Huawei, Lenovo, Nokia, Ericsson | C3-252396, C3-253497, C3-253665, C3-253498 | CT3#140 --> CT3#142 | Completed
11 |  | API notifications clauses | 29.522 | Huawei, Lenovo, Nokia, Ericsson | C3-252396 | CT3#140 --> CT3#142 | Completed
12 |  | API data model clauses | 29.522 | Huawei, Lenovo, Nokia, Ericsson | C3-252396, C3-253499 | CT3#140 --> CT3#142 | Completed
13 |  | OpenAPI description | 29.522 | Huawei, Lenovo, Nokia, Ericsson | C3-252397, C3-253497, C3-253665, C3-253498 | CT3#140 --> CT3#142 | Completed
14 |  | Error handling, corrections, general clean-up and resolving ENs | 29.522 | Huawei, Lenovo, Nokia, Ericsson |  | CT3#142 --> CT3#143 | Ongoing