## Tdoc cover sheet
3GPP TSG CT WG3 Meeting #144 Dallas, US, 17-21, November 2025 |  | C3-255075
Source: | Nokia
Title: | Work Plan for XRM_Ph2
Agenda item: | 19.48
Document for: | Discussion

## CT3 WG
Contribution Plan
Meeting | Related stage 2 topic | Related stage 2 agreed CR # other WG tdoc(s) # | stage 2 TDoc source | Impacted stage-3 TSs | Volunteered company | Addressed Tdoc(s) in CT WGs | Plan | Comments
KI#1: Support of PDU set based QoS handling enhancement
SA2#166AH | 23.503 CR1441R5 (Rel-19, 'B'): PDU Set support in QoS Notification Control and Alternative QoS | S2-2501101 | Nokia, vivo, Huawei, HiSilicon, Xiaomi | 29.522, 29.122, 29.514, 29.512 | Huawei, Nokia | C3-250632, C3-250559, C3-250662, C3-250633, | 2025-02-01
SA2#167 | 23.503 CR1457R1 (Rel-19, 'B'): Support of providing MMSID from 5GC to NG-RAN through NGAP | S2-2502464 | China Mobile, ZTE | 29.512 | Ericsson, Huawei, Nokia | C3-251499 | 2025-04-01
SA2#167 | Support Alternative QoS profile with PDU Set QoS and Notification Control | S2-2502678 | CATT, Nokia, Tencent, vivo, Samsung, Xiaomi, Huawei, HiSilicon | 29.522, 29.122, 29.514, 29.512 | Huawei | C3-251295, C3-251496, C3-251297 | 2025-04-01
SA2#168 | 23.503 CR1548 (Rel-19, 'F'): Clarifications for QoS Notification Control with direction information | S2-2504420 | Huawei, HiSilicon, Nokia | 29.512 | CATT, Nokia | C3-252437 | 2025-05-01
SA2#168 | 23.501 CR6233 (Rel-19, 'F'): QoS Notification Control of PDU Set QoS with only one direction | S2-2504419 | Huawei, China Mobile, Nokia | 29.512, 29.514, 29.122 | CATT,Nokia | C3-252436, C3-252437 | 2025-05-01
SA2#169 | 23.501 CR6233R5 (Rel-19, 'F'): QoS Notification Control of PDU Set QoS with only one direction | S2-2505976 | CATT, Huawei, Nokia, Vivo | 29.512, 29.514, 29.122 | CATT,Nokia | C3-252436, C3-252437 | 2025-05-01
KI#2: Support PDU Set information identification for end-to-end encrypted XRM traffic
SA2#165 | 23.501 CR5728 (Rel-19, 'B'): PDU Set Information Identification for end-to-end encrypted traffic using connect-UDP - architecture part | S2-2411185 | Ericsson, InterDigital, Apple, Nokia, Lenovo, Google, Meta | 29.561 | Ericsson, Nokia, Lenovo | C3-251655, C3-250670, C3-250625, C3-252525, C3-254594 | Feb-2025, May-2025, Aug-2025, Oct-2025
SA2#165 | 23.501 CR5632 (Rel-19, 'B'): Support PDU Set information identification based on MoQ for encrypted XRM traffic | S2-2411255 | China Mobile, Huawei, Hisilicon, Interdigital, Sony | 29.561 | Ericsson, China Mobile, Huawei, Nokia, Lenovo | C3-243571 | 2025-08-01
SA2#165 | 23.501 CR5746 (Rel-19, 'B'): Usage of UDP-Option carrying XRM metadata over UDP tunnel for end-to-end encrypted XRM flows | S2-2411187 | Google, Futurewei, InterDigital Inc. | 29.561 | Lenovo, Nokia | C3-250669, C3-252435 | Feb-2025, May-2025, Nov-2025 | Editor's note for IANA exists
SA2#166 | 23.501 CR5711R5 (Rel-19, 'B'): General description of relaying media related information over N6 using an encapsulation protocol | S2-2412897 | Lenovo, Ericsson, Nokia, Google, Meta | 29.561 | Lenovo, Ericsson, Nokia, Huawei | C3-246582, C3-252525, C3-253572 | Nov-2024, May-2025, Aug-2025 | Updated revision of S2-2411182.
SA2#166 | 23.501 CR5632R5 (Rel-19, 'B'): Support PDU Set information identification based on MoQ for encrypted XRM traffic | S2-2412898 | China Mobile, Huawei, Hisilicon, Interdigital, Sony, Nokia | 29.561, 29.522, 29.122, 29.514, 29.512 | China Mobile, Huawei, Lenovo | C3-243571 | Aug-2025
SA2#166 | 23.501 CR5728R5 (Rel-19, 'B'): PDU Set Information Identification for end-to-end encrypted traffic using connect-UDP - architecture part | S2-2412899 | Ericsson, Nokia, InterDigital, Apple, Lenovo, Google, Meta | 29.561, 29.522, 29.122, 29.514, 29.512 | Nokia, Ericsson, Lenovo | C3-250670, C3-250625, C3-251505, C3-251506, C3-252527, C3-253668 | Feb-2025, May-2025, Aug-2025
SA2#166 | 23.501 CR5746R5 (Rel-19, 'B'): Usage of UDP-Option carrying XRM metadata over UDP tunnel for end-to-end encrypted XRM flows | S2-2412947 | Google, Futurewei, InterDigital Inc., Nokia | 29.561 | Lenovo, Ericsson, Nokia | C3-250669, C3-252435 | Feb-2025
SA2#167 | 23.502 CR5081R6 (Rel-19, 'B'): Procedures for handling end-to-end encrypted XRM flows | S2-2502461 | Google, Futurewei, InterDigital Inc., China Mobile, Huawei, HiSilicon, Ericsson, Nokia, Apple | 29.522, 29.122, 29.514, 29.512, 29.561 | Nokia, Ericsson, Huawei, Lenovo | C3-250670, C3-250625, C3-251505, C3-251506, C3-252617 | Feb-2025, May-2025
SA2#167 | 23.503 CR1394R6 (Rel-19, 'B'): PDU Set Information Identification for end-to-end encrypted traffic using connect-UDP - PCC part | S2-2502683 | Ericsson , InterDigital, Nokia, Google, Huawei, HiSilicon | 29.522, 29.122, 29.514, 29.512 | Ericsson , Huawei, Nokia | C3-250626, C3-250558, C3-250627, C3-251503, C3-251504, C3-251505, C3-251506, | Feb-2025,Apr-2025 | On path N6-signaling information addition, protocol description for MoQ
SA3#122 | Providing security details for forwarding mode in XRM | S3-252307 | Ericsson | 29.561 | Ericsson, Nokia | C3-254461 | Aug-2025, Oct 2025, Nov-2025 | Editor's note for IANA exists
SA2#171 | Clarifications and corrections on usage of MoQ for encrypted media flows | S2-2509337 | China Mobile | 29.561 | Nokia |  | Nov-2025
Key Issue #3: Leverage PDU Set QoS information for DSCP marking over N3/N9 in the transport network
SA2#167 | 23.503 CR1388R8 (Rel-19, 'B'): Traffic detection and QoS handling of multiplexed data flows | S2-2502674 | OPPO, China Mobile, Lenovo, Xiaomi, Ericsson, Huawei, HiSilicon, Samsung, Nokia, NTT DOCOMO, Google, vivo | 29.514, 29.512 | Ericsson, Nokia, Huawei, China Mobile, Interdigital Communications | C3-240663, C3-251649, C3-252442, C3-252524, C3-252278, C3-253697, C3-253720, C3-253581, C3-253582 | Feb-2025, Apr-2025, May-2025, Aug-2025
SA2#167 | 23.502 CR4927R6 (Rel-19, 'B'): Support multiplexing media traffic with additional Packet Filter | S2-2502210 | CATT, Nokia, OPPO, Lenovo, Samsung, Xiaomi | 29.522, 29.122, | Ericsson, Nokia, Huawei, China Mobile, Interdigital Communications | C3-253720, C3-253681, C3-253682 | 2025-08-01
KI#4 Traffic detection/mapping for multiplexed data flows
SA2#165 | 23.501 CR5783 (Rel-19, 'B'): Support differentiated QoS handling for multiplexed media flows | S2-2411184 | Nokia, NTT DOCOMO | 29.522, 29.122, 29.514, 29.512 | Ericsson, Nokia, Huawei, China Mobile, Interdigital Communications | C3-246430, C3-246388, C3-246389, C3-246431, C3-253697, C3-253720 | Nov-2024, Aug-2025
SA2#166 | 23.501 CR5783R5 (Rel-19, 'B'): Update for Support differentiated QoS handling for multiplexed media flows | S2-2412948 | Lenovo, China Telecom, InterDigital, Xiaomi, Tencent, Tencent Cloud, Nokia, Samsung, Ericsson, NTT DOCOMO, vivo, Meta USA, Apple, Huawei, HiSilicon, CATT, OPPO, Google | 29.522, 29.122, 29.514, 29.512 | Ericsson, Nokia, Huawei, China Mobile, Interdigital Communications | C3-240663, C3-251649, C3-252442, C3-252524, , C3-253720 | Feb-2025, Apr-2025, May-2025, Aug-2025
SA2#166AH | 23.501 CR5958R1 (Rel-19, 'F'): KI#4: Correct the RTCP MID for IP packet filter set | S2-2501108 | China Mobile, Lenovo | 29.514 | Ericsson, Nokia, Huawei, China Mobile, Interdigital Communications | C3-252442, C3-253720 | May-2025, Aug-2025
KI#5: QoS Handling when Traffic Characteristics Change Dynamically
SA2#165 | 23.501 CR5784 (Rel-19, 'B'): Support of Data Burst Size provisioning to NG-RAN | S2-2411254 | Nokia, Xiaomi, Huawei, HiSilicon, Samsung | 29.522, 29.122, 29.514, 29.512 | Ericsson, Huawei, ZTE, Nokia | C3-246169, C3-246387, C3-250312 | Nov-2024, Feb-2025
SA2#165 | 23.502 CR4964R3 (Rel-19, 'B'): KI5_Provision of the DL traffic characteristics information changed dynamically | S2-2411006 | Xiaomi, Samsung, OPPO, Huawei, HiSilicon, Vivo, Tencent, Nokia, Ericsson | 29.522, 29.122, 29.514, 29.512 | Ericsson, Huawei, Nokia | C3-246169, C3-246387, C3-246226, C3-253579, C3-253660, C3-253609 | Nov-2024, Aug-2025
SA2#166 | 23.501 CR5783R5 (Rel-19, 'B'): Support of Time to Next Burst provisionsing to NG-RAN | S2-2412943 | Nokia | 29.522, 29.122, 29.514, 29.512 | Nokia | C3-250530, C3-250531, C3-251495, C3-253576 | Feb-2025, Aug-2025
SA2#166 | 23.502 CR5052R1 (Rel-19, 'B'): KI5_Provision of the Time to Next Burst | S2-2412715 | Xiaomi, Lenovo, Nokia | 29.522, 29.122, 29.514, 29.512 | Nokia, Ericsson | C3-250530, C3-250531, C3-251495, C3-253576 | Feb-2025, Aug-2025
SA2#166 | 23.503 CR1324R7 (Rel-19, 'B'): KI#5, Support of Data Burst related | S2-2412952 | Vivo, Xiaomi, Samsung, Nokia, InterDigital Inc, Lenovo | 29.522, 29.122, 29.514, 29.512 | Huawei, Ericsson, Nokia | C3-246409 | 2024-11-01 | Update of S2-2411004.
SA2#167 | 23.501 CR5651R7 (Rel-19, 'B'): 23.501 Data boosting triggered by AS/AF | S2-2502472 | Lenovo, Tencent, Tencent Cloud, CATT, China Telecom, Meta USA, CMCC, Xiaomi, Samsung, Huawei, HiSilicon, Ericsson, Nokia, Apple | 29.522, 29.122, 29.514, 29.512 | Ericsson | C3-251501, C3-251502, | 2025-04-01 | Update of S2-2501353
SA2#166AH | 23.502 CR5015R5 (Rel-19, 'B'): 23.502 Data boosting triggered by AS | S2-2501352 | Lenovo, Tencent, Tencent Cloud,CATT, China Telecom, Meta USA | 29.522, 29.122, 29.514, 29.512 | Ericsson | C3-251501, C3-251502, | 2025-04-01
SA2#167 | 23.503 CR1448R4 (Rel-19, 'B'): Enhancements for AF/AS triggered expedite data transfer | S2-2502473 | Lenovo, Tencent, Tencent Cloud, CATT, Huawei, HiSilicon, Nokia, Ericsson, InterDigital Inc Nokia, Tencent, Tencent Cloud, InterDigital Inc. | 29.514, 29.512 | Ericsson | C3-251501, C3-251502, C3-252438, C3-252443, C3-253578 | Apr-2025, Aug-2025 | Update of S2-2501111
SA2#171 | Indication of Rate-Adaptable QoS Flows to NG-RAN | S2-2509579 | Ericsson, LG Electronics, CATT, Xiaomi, Lenovo | 29.522, 29.122, 29.514, 29.512 | Nokia |  | 2025-11-01
SA2#170 | 23.502 Support of uplink rate control for QoS flows at RAN | S2-2508117 | Lenovo, ZTE, China Telecom, Xiaomi, Tencent, InterDigital | 29.522, 29.122, 29.514, 29.512 | Nokia |  | 2025-11-01
SA2#171 | 23.503 Support of uplink rate control for QoS flows at RAN | S2-2509332 | Lenovo, ZTE, China Telecom, Xiaomi, Tencent, InterDigital, CATT, Ericsson, vivo | 29.522, 29.122, 29.514, 29.512 | Nokia |  | 2025-11-01
KI#6: L4S for non-3GPP access networks and intermediate 5GS nodes
SA2#165 | 23.503 CR1360R1 (Rel-19, 'B'): XRM_Ph2 KI#6 L4S support in non-3GPP access | S2-2411259 | Charter Communications, CableLabs, Tencent, Tencent Cloud, Nokia, Samsung | 29.512 | Nokia | C3-250116 | 2025-02-01
KI#7: Support for PDU Set in non-3GPP access.
SA2#165 | 23.503 CR1364R1 (Rel-19, 'B'): PDU Set handling in non-3GPP accesses | S2-2410647 | CableLabs, Charter Communications, Tencent, Tencent Cloud, Interdigital Inc., Lenovo, Nokia | 29.512 | Nokia | C3-250532 | 2025-02-01
KI#8 – Enhancements for tethered devices
KI#9: Enhancement for XR related network information exposure
SA2#167 | 23.503 CR1381R5 (Rel-19, 'B'): KI#9, Support of Rate limitation | S2-2502677 | vivo, Meta USA, Tencent, Nokia | 29.514, 29.512, 29.523, 29.122 29.522 | Ericsson, Nokia | C3-250628, C3-250629, C3-250630, C3-250631, C3-251500 | 2025-02-01 | Update of S2-2501112
SA2#167 | 23.501 CR5867R8 (Rel-19, 'B'): KI#9, Support of Rate limitation | S2-2502475 | Tencent, Tencent Cloud, vivo, Lenovo, CMCC, Nokia, Meta, Ericsson | 29.514, 29.512, 29.523, 29.122,29.522 | Ericsson, Nokia | C3-250628, C3-250629, , C3-250630,, C3-250631, C3-253577, C3-253396 | Feb-2025, Aug-2025 | Update of S2-2501113
SA2#167 | 23.502 CR5309R1 (Rel-19, 'B'): KI#9, Support of Available Data Rate | S2-2502676 | Nokia | 29.522, 29.122, 29.514, 29.512 | Huawei | C3-251660, C3-251661, C3-251662, C3-251663 | 2025-04-01
SA2#167 | 23.503 CR1419R3 (Rel-19, 'B'): Support of available data rate exposure | S2-2502471 | Huawei, HiSilicon | 29.522, 29.122, 29.514, 29.512 | Huawei | C3-251660, C3-251661, C3-251662, C3-251663 | 2025-04-01
SA2#168 | 23.501 CR6255 (Rel-19, 'F'): Available Bitrate Reporting when the Serving RAN Node Changes | S2-2504417 | InterDigital Inc. | 29.514, 29.512, 29.122 | Nokia, Huawei, ZTE, Ericsson | C3-252528, C3-252529, C3-252618, C3-253574, , C3-253575, C3-253678, C3-253679, C3-254462, C3-254463, C3-254464, C3-254465, C3-254470 | May-2025, Aug-2025, Oct-2025
SA2#168 | 23.503 CR1545 (Rel-19, 'F'): Clarifications for available bitrate exposure | S2-2503935 | Huawei, HiSilicon | 29.514, 29.512 | Huawei, Ericsson, Nokia | C3-252440, , C3-252281, C3-252282, C3-252473, C3-253575, C3-253573, C3-253584, C3-253600, C3-253474 | May-2025, Aug-2025
SA2#168 | 23.501 CR6227 (Rel-19, 'F'): Clarifications for rate limitation exposure | S2-2504418 | Huawei, HiSilicon | 29.522, 29.122 | Huawei, Ericsson, Nokia | C3-252440, | 2025-05-01
SA2#168 | 23.503 CR1547 (Rel-19, 'F'): Clarifications for rate limitation exposure | S2-2504481 | Huawei, HiSilicon | 29.514, 29.512 | Huawei, Ericsson, Nokia | C3-252440, , C3-252281, C3-252282, C3-252473 | 2025-05-01

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT meeting #; tdoc(s) # | Open issues | Comments

## Outcoming LSs
Outcoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT meeting #; tdoc(s) # | Open issues | Comments