## Cover sheet
3GPP TSG RAN WG5#108 | [10 empty] | R5-254401
<Bengaluru, India, 25th August 2025 - 29th August 2025>
Agenda Item: | 7.4.2
Source: | China Unicom
Title: | WP on UE Conformance - Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s)
Work item code: | HPUE_DC_LTE_NR_R19 -UEConTest
Release: | Rel-19
Document for: | Information
RAN5 WP template v2.0
1. Introduction
3GPP TSG RAN WG4 has introduced a Rel-19 basket WI to specify the requirements of High power ENDC combos for requested band combinations from operators. Therefore, it is proposed to create an associated 3GPP TSG RAN WG5 work item to introduce the relevant conformance test aspect based on operator’s interest.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed configurations (Note 1) | Number of new configurations | Comments
Overall completion |  | 6% (+1%) | 0 | 274 (+264)
Completion Compensation |  | -
| Note 1: | Only test cases / configurations completed for all applicable WP areas and sub-areas are counted. For completed test cases / configurations per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed configurations | Number of new configurations | Comments
NSA Option 3 (EN-DC) |  | 5.9% (+0.9%) | 0 | 274 (+264)
FR1 |  | 5.9% (+0.9%) | 0 | 274 (+264)
FR1 + FR2
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | NSA Option 3 (EN-DC)
TS:Area Scope | TS/Area | Completion | Number of new completed PC2 configurations | Number of new PC2 configurations | FR1 |  |  | FR1 + FR2
[5 empty] | Completion | Number of new completed test cases / configurations | Number of new test cases / configurations | Completion | Number of new completed test cases / configurations | Number of new test cases / configurations
NR HPUE (PC1.5 or 2) configurations
NR HPUE (PC1.5 or 2) configurations
NR HPUE (PC1.5 or 2) configurations | 2Tx PC2 EN-DC BC | 1% (+1%) | 0 | 268 (+268) | 1% (+1%) | 0 | 268 (+268)
NR HPUE (PC1.5 or 2) configurations | 3Tx PC2 EN-DC BC | 0% | 0 | 6 (+6) | 0% | 0 | 6 (+6)
5 References
[1]RP-251512 | New WID on UE Conformance - Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s)
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP on UE Conformance - Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s) | [12 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | Relative weight of effort vs TS contribution | [8 empty] | End of workplan columns. Note! Do not remove this column.
WI code |  | HPUE_DC_LTE_NR_R19 -UEConTest | [15 empty] | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 5 | 5
WP Scope: |  | The purpose of present document is to provide a workplan for the RAN5 work item UE Conformance - Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s) comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID). | [14 empty] | vs Area | 38.508-1: Test frequencies | 38.508-2: UE capabilities | 38.521-3: Common Clause | 38.521-3: Tx test cases | 38.521-3: Rx test cases | 38.522: Test case applicability | 38.533: RRM test cases / 38:.522 Test case applicability | 38.903: MU and TT | 38.905: Test point analysis
WP Resp: |  | Yu Shi, China Unicom / Chunying Gu, Huawei |  |  | shiyu19@chinaunicom.cn; guchunying@huawei.com | [7 empty] | WP item completion |  |  | NSA Option 3 (EN-DC)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new configuration or test case? | TS/Area | Configuration / Test case clause | UL configuration(s) / Test case title | Type of change | Interested Operator | Company | Status | Target | TDOC(s) | Comments | Weight | Overall | NSA Option 3 (EN-DC) |  | FR1 | FR1 + FR2
5.9% (+0.9%)
[16 empty] | 275 (+261) | 0
[16 empty] | 274 (+261) | 0
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row. | [15 empty] | CALCULATED CELLS |  | TS STATUS INPUT
2Tx PC2 EN-DC BC
1 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-18A_n77A | DC_1A_n77A DC_3A_n77A DC_18A_n77A | PC2 | KDDI | KDDI | Ongoing |  | 38.508-2： R5-254222 38.521-3： R5-254225 | RAN4 status: Completed | 1 | 66.7% (+66.7%) | 66.7% (+66.7%) |  | 66.67% |  | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0%
2 | Y | 2Tx PC2 EN-DC BC | DC_3A-11A_n79A | DC_3A_n79A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
3 | Y | 2Tx PC2 EN-DC BC | DC_8A-42A_n79A | DC_8A_n79A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
4 | Y | 2Tx PC2 EN-DC BC | DC_3A-41C_n77A | DC_3A_n77A | PC2 | KDDI | KDDI | Ongoing |  | 38.508-2： R5-254222 38.521-3： R5-254225 | RAN4 status: Completed | 1 | 66.7% (+66.7%) | 66.7% (+66.7%) |  | 66.67% |  | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0%
5 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-41C_n77A | DC_1A_n77A, DC_3A_n77A | PC2 | KDDI | KDDI | Ongoing |  | 38.508-2： R5-254222 38.521-3： R5-254225 | RAN4 status: Completed | 1 | 66.7% (+66.7%) | 66.7% (+66.7%) |  | 66.67% |  | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0%
6 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-41C_n77(2A) | DC_1A_n77A, DC_3A_n77A | PC2 | KDDI | KDDI | Ongoing |  | 38.508-2： R5-254222 38.521-3： R5-254225 | RAN4 status: Completed | 1 | 66.7% (+66.7%) | 66.7% (+66.7%) |  | 66.67% |  | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 0%
7 | Y | 2Tx PC2 EN-DC BC | DC_3A_n41A-n77A | DC_3A_n41A DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
8 | Y | 2Tx PC2 EN-DC BC | DC_3A-8B_n78A | DC_8B_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
9 | Y | 2Tx PC2 EN-DC BC | DC_3A-3A-8B_n78A | DC_8B_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
10 | Y | 2Tx PC2 EN-DC BC | DC_7A-8B_n78A | DC_8B_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
11 | Y | 2Tx PC2 EN-DC BC | DC_7A-7A-8B_n78A | DC_8B_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
12 | Y | 2Tx PC2 EN-DC BC | DC_3A-7A-8B_n78A | DC_8B_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
13 | Y | 2Tx PC2 EN-DC BC | DC_3A-3A-7A-8B_n78A | DC_8B_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
14 | Y | 2Tx PC2 EN-DC BC | DC_3A-7A-7A-8B_n78A | DC_8B_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
15 | Y | 2Tx PC2 EN-DC BC | DC_3A-3A-7A-7A-8B_n78A | DC_8B_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
16 | Y | 2Tx PC2 EN-DC BC | DC_1A-18A-42A_n77A | DC_1A_n77A DC_18A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
17 | Y | 2Tx PC2 EN-DC BC | DC_(n)40AA | DC_(n)40AA | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
18 | Y | 2Tx PC2 EN-DC BC | DC_40A_n40A | DC_40A_n40A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
19 | Y | 2Tx PC2 EN-DC BC | DC_4A_n41A | DC_4A_n41A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
20 | Y | 2Tx PC2 EN-DC BC | DC_8A_n41A | DC_8A_n41A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
21 | Y | 2Tx PC2 EN-DC BC | DC_20A_n41A | DC_20A_n41A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
22 | Y | 2Tx PC2 EN-DC BC | DC_4A_n78A | DC_4A_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
23 | Y | 2Tx PC2 EN-DC BC | DC_7C_n78A | DC_7C_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
24 | Y | 2Tx PC2 EN-DC BC | DC_20A_n78A | DC_20A_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
25 | Y | 2Tx PC2 EN-DC BC | DC_38A_n78A | DC_38A_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
26 | Y | 2Tx PC2 EN-DC BC | DC_40A_n78A | DC_40A_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
27 | Y | 2Tx PC2 EN-DC BC | DC_41A_n78A | DC_41A_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
28 | Y | 2Tx PC2 EN-DC BC | DC_40C_n78A | DC_40C_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
29 | Y | 2Tx PC2 EN-DC BC | DC_41C_n78A | DC_41C_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
30 | Y | 2Tx PC2 EN-DC BC | DC_5A_n41A | DC_5A_n41A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
31 | Y | 2Tx PC2 EN-DC BC | DC_11A_n41A | DC_11A_n41A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
32 | Y | 2Tx PC2 EN-DC BC | DC_12A_n41A | DC_12A_n41A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
33 | Y | 2Tx PC2 EN-DC BC | DC_14A_n41A | DC_14A_n41A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
34 | Y | 2Tx PC2 EN-DC BC | DC_25A_n41A | DC_25A_n41A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
35 | Y | 2Tx PC2 EN-DC BC | DC_26A_n41A | DC_26A_n41A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
36 | Y | 2Tx PC2 EN-DC BC | DC_40A_n41A | DC_40A_n41A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
37 | Y | 2Tx PC2 EN-DC BC | DC_71A_n41A | DC_71A_n41A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
38 | Y | 2Tx PC2 EN-DC BC | DC_11A_n78A | DC_11A_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
39 | Y | 2Tx PC2 EN-DC BC | DC_12A_n78A | DC_12A_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
40 | Y | 2Tx PC2 EN-DC BC | DC_18A_n78A | DC_18A_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
41 | Y | 2Tx PC2 EN-DC BC | DC_25A_n78A | DC_25A_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
42 | Y | 2Tx PC2 EN-DC BC | DC_26A_n78A | DC_26A_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
43 | Y | 2Tx PC2 EN-DC BC | DC_39A_n78A | DC_39A_n78A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
44 | Y | 2Tx PC2 EN-DC BC | DC_1A_n3A-n28A-n77A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
45 | Y | 2Tx PC2 EN-DC BC | DC_1A_n3A-n77(2A) | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
46 | Y | 2Tx PC2 EN-DC BC | DC_1A_n3A-n77A-n79A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
47 | Y | 2Tx PC2 EN-DC BC | DC_1A_n3A-n77A-n79A | DC_1A_n79A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
48 | Y | 2Tx PC2 EN-DC BC | DC_1A_n28A-n77(2A) | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
49 | Y | 2Tx PC2 EN-DC BC | DC_1A_n28A-n77A-n79A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
50 | Y | 2Tx PC2 EN-DC BC | DC_1A_n28A-n77A-n79A | DC_1A_n79A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
51 | Y | 2Tx PC2 EN-DC BC | DC_1A_n77(2A)-n79A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
52 | Y | 2Tx PC2 EN-DC BC | DC_1A_n77(2A)-n79A | DC_1A_n79A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
53 | Y | 2Tx PC2 EN-DC BC | DC_1A_n77(3A) | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
54 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n3A-n77A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
55 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n3A-n77A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
56 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n3A-n77A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
57 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n3A-n77A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
58 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n28A-n77A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
59 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n28A-n77A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
60 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n77(2A) | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
61 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n77(2A) | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
62 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n77A-n79A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
63 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n77A-n79A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
64 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n77A-n79A | DC_1A_n79A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
65 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n77A-n79A | DC_8A_n79A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
66 | Y | 2Tx PC2 EN-DC BC | DC_3A_n1A-n77A-n79A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
67 | Y | 2Tx PC2 EN-DC BC | DC_3A_n1A-n77A-n79A | DC_3A_n79A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
68 | Y | 2Tx PC2 EN-DC BC | DC_3A_n28A-n77(2A) | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
69 | Y | 2Tx PC2 EN-DC BC | DC_3A_n28A-n77A-n79A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
70 | Y | 2Tx PC2 EN-DC BC | DC_3A_n28A-n77A-n79A | DC_3A_n79A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
71 | Y | 2Tx PC2 EN-DC BC | DC_3A_n77(3A) | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
72 | Y | 2Tx PC2 EN-DC BC | DC_3A-8A_n28A-n77A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
73 | Y | 2Tx PC2 EN-DC BC | DC_3A-8A_n28A-n77A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
74 | Y | 2Tx PC2 EN-DC BC | DC_3A-8A_n77A-n79A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
75 | Y | 2Tx PC2 EN-DC BC | DC_3A-8A_n77A-n79A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
76 | Y | 2Tx PC2 EN-DC BC | DC_8A_n1A-n3A-n77A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
77 | Y | 2Tx PC2 EN-DC BC | DC_8A_n1A-n77(2A) | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
78 | Y | 2Tx PC2 EN-DC BC | DC_8A_n3A-n28A-n77A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
79 | Y | 2Tx PC2 EN-DC BC | DC_8A_n3A-n77(2A) | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
80 | Y | 2Tx PC2 EN-DC BC | DC_8A_n3A-n77A-n79A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
81 | Y | 2Tx PC2 EN-DC BC | DC_8A_n3A-n77A-n79A | DC_8A_n79A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
82 | Y | 2Tx PC2 EN-DC BC | DC_8A_n28A-n77(2A) | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
83 | Y | 2Tx PC2 EN-DC BC | DC_8A_n28A-n77A-n79A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
84 | Y | 2Tx PC2 EN-DC BC | DC_8A_n28A-n77A-n79A | DC_8A_n79A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
85 | Y | 2Tx PC2 EN-DC BC | DC_8A_n77(2A)-n79A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
86 | Y | 2Tx PC2 EN-DC BC | DC_8A_n77(2A)-n79A | DC_8A_n79A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
87 | Y | 2Tx PC2 EN-DC BC | DC_8A_n77(3A) | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
88 | Y | 2Tx PC2 EN-DC BC | DC_1A_n3A-n28A-n77(2A) | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
89 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n28A-n77(2A) | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
90 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n77(3A) | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
91 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-8A_n28A-n77A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
92 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-8A_n28A-n77A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
93 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-8A_n28A-n77A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
94 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n3A-n28A-n77A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
95 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n3A-n28A-n77A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
96 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n3A-n77(2A) | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
97 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n3A-n77(2A) | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
98 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n28A-n77(2A) | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
99 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n28A-n77(2A) | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
100 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n77(3A) | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
101 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n77(3A) | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
102 | Y | 2Tx PC2 EN-DC BC | DC_3A-8A_n28A-n77(2A) | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
103 | Y | 2Tx PC2 EN-DC BC | DC_3A-8A_n28A-n77(2A) | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
104 | Y | 2Tx PC2 EN-DC BC | DC_3A-8A_n77(3A) | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
105 | Y | 2Tx PC2 EN-DC BC | DC_3A-8A_n77(3A) | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
106 | Y | 2Tx PC2 EN-DC BC | DC_8A_n3A-n28A-n77(2A) | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
107 | Y | 2Tx PC2 EN-DC BC | DC_8A-41C_n77A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
108 | Y | 2Tx PC2 EN-DC BC | DC_8A-41A_n77A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
109 | Y | 2Tx PC2 EN-DC BC | DC_3A_n3A-n77A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
110 | Y | 2Tx PC2 EN-DC BC | DC_8A_n77A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
111 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n28A-n77A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
112 | Y | 2Tx PC2 EN-DC BC | DC_2A-13A-66A_n77A | DC_2A_n77A, DC_13A_n77A, DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
113 | Y | 2Tx PC2 EN-DC BC | DC_48D-66A_n77A | DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
114 | Y | 2Tx PC2 EN-DC BC | DC_2A-66A_n5A-n77A | DC_66A_n77A DC_5A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
115 | Y | 2Tx PC2 EN-DC BC | DC_2A-2A_n5A-n77A | DC_2A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
116 | Y | 2Tx PC2 EN-DC BC | DC_13A-66A-66A_n2A-n77A | DC_13A_n77A DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
117 | Y | 2Tx PC2 EN-DC BC | DC_2A-66A-66A_n5A-n77A | DC_2A_n77A DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
118 | Y | 2Tx PC2 EN-DC BC | DC_2A-2A-66A_n5A-n77A | DC_2A_n77A DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
119 | Y | 2Tx PC2 EN-DC BC | DC_2A_n77C | DC_2A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
120 | Y | 2Tx PC2 EN-DC BC | DC_5A_n77C | DC_2A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
121 | Y | 2Tx PC2 EN-DC BC | DC_13A_n77C | DC_2A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
122 | Y | 2Tx PC2 EN-DC BC | DC_66A_n77C | DC_2A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
123 | Y | 2Tx PC2 EN-DC BC | DC_13A-66A_n77C | DC_13A_n77A DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
124 | Y | 2Tx PC2 EN-DC BC | DC_2A-66A_n77C | DC_2A_n77A DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
125 | Y | 2Tx PC2 EN-DC BC | DC_2A-13A_n77C | DC_2A_n77A DC_13A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
126 | Y | 2Tx PC2 EN-DC BC | DC_66A-66A_n77C | DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
127 | Y | 2Tx PC2 EN-DC BC | DC_2A-5A_n77C | DC_2A_n77A DC_5A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
128 | Y | 2Tx PC2 EN-DC BC | DC_2A-48A_n77C | DC_2A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
129 | Y | 2Tx PC2 EN-DC BC | DC_48A-66A_n77C | DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
130 | Y | 2Tx PC2 EN-DC BC | DC_2A-2A_n77C | DC_2A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
131 | Y | 2Tx PC2 EN-DC BC | DC_2A-13A-66A_n77C | DC_2A_n77A DC_13A_n77A DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
132 | Y | 2Tx PC2 EN-DC BC | DC_13A-66A-66A_n77C | DC_13A_n77A DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
133 | Y | 2Tx PC2 EN-DC BC | DC_2A-5A-66A_n77C | DC_2A_n77A DC_5A_n77A DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
134 | Y | 2Tx PC2 EN-DC BC | DC_2A-66A-66A_n77C | DC_2A_n77A DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
135 | Y | 2Tx PC2 EN-DC BC | DC_5A-66A-66A_n77C | DC_5A_n77A DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
136 | Y | 2Tx PC2 EN-DC BC | DC_2A-2A-13A_n77C | DC_2A_n77A DC_13A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
137 | Y | 2Tx PC2 EN-DC BC | DC_2A-2A-66A_n77C | DC_2A_n77A DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
138 | Y | 2Tx PC2 EN-DC BC | DC_2A-2A-5A_n77C | DC_2A_n77A DC_5A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
139 | Y | 2Tx PC2 EN-DC BC | DC_66A-66A-66A_n77C | DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
140 | Y | 2Tx PC2 EN-DC BC | DC_2A-48C_n77C | DC_2A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
141 | Y | 2Tx PC2 EN-DC BC | DC_48C-66A_n77C | DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
142 | Y | 2Tx PC2 EN-DC BC | DC_2A-13A-66A-66A_n77C | DC_2A_n77A DC_13A_n77A DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
143 | Y | 2Tx PC2 EN-DC BC | DC_2A-5A-66A-66A_n77C | DC_2A_n77A DC_5A_n77A DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
144 | Y | 2Tx PC2 EN-DC BC | DC_2A-2A-13A-66A_n77C | DC_2A_n77A DC_13A_n77A DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
145 | Y | 2Tx PC2 EN-DC BC | DC_2A-2A-5A-66A_n77C | DC_2A_n77A DC_5A_n77A DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
146 | Y | 2Tx PC2 EN-DC BC | DC_2A-2A-66A-66A_n77C | DC_2A_n77A DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
147 | Y | 2Tx PC2 EN-DC BC | DC_2A-48D_n77C | DC_2A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
148 | Y | 2Tx PC2 EN-DC BC | DC_48D-66A_n77C | DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
149 | Y | 2Tx PC2 EN-DC BC | DC_13A_n2A-n77C | DC_13A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
150 | Y | 2Tx PC2 EN-DC BC | DC_13A_n66A-n77C | DC_13A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
151 | Y | 2Tx PC2 EN-DC BC | DC_2A_n2A-n77C | DC_2A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
152 | Y | 2Tx PC2 EN-DC BC | DC_5A_n2A-n77C | DC_5A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
153 | Y | 2Tx PC2 EN-DC BC | DC_66A_n2A-n77C | DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
154 | Y | 2Tx PC2 EN-DC BC | DC_2A_n5A-n77C | DC_2A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
155 | Y | 2Tx PC2 EN-DC BC | DC_5A_n5A-n77C | DC_5A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
156 | Y | 2Tx PC2 EN-DC BC | DC_13A_n5A-n77C | DC_13A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
157 | Y | 2Tx PC2 EN-DC BC | DC_66A_n5A-n77C | DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
158 | Y | 2Tx PC2 EN-DC BC | DC_2A_n66A-n77C | DC_2A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
159 | Y | 2Tx PC2 EN-DC BC | DC_5A_n66A-n77C | DC_5A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
160 | Y | 2Tx PC2 EN-DC BC | DC_13A_n66A-n77C | DC_13A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
161 | Y | 2Tx PC2 EN-DC BC | DC_66A_n66A-n77C | DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
162 | Y | 2Tx PC2 EN-DC BC | DC_13A-66A_n2A-n77C | DC_13A_n77A DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
163 | Y | 2Tx PC2 EN-DC BC | DC_66A-66A_n2A-n77C | DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
164 | Y | 2Tx PC2 EN-DC BC | DC_2A-66A_n5A-n77C | DC_66A_n77A DC_2A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
165 | Y | 2Tx PC2 EN-DC BC | DC_66A-66A_n5A-n77C | DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
166 | Y | 2Tx PC2 EN-DC BC | DC_2A-2A_n5A-n77C | DC_2A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
167 | Y | 2Tx PC2 EN-DC BC | DC_2A-2A_n66A-n77C | DC_2A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
168 | Y | 2Tx PC2 EN-DC BC | DC_n78A-n258A/B/C/D/E/F/G/H/I/J/K/L/M | DC_n78A-n258A/G/H/I | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
169 | Y | 2Tx PC2 EN-DC BC | DC_13A-48A_n77A | DC_13A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
170 | Y | 2Tx PC2 EN-DC BC | DC_2A-48A_n77A | DC_2A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
171 | Y | 2Tx PC2 EN-DC BC | DC_48A-66A_n77A | DC_66A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
172 | Y | 2Tx PC2 EN-DC BC | DC_3A_n77A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
173 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n77A | DC_1A_n77A DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
174 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-41A_n28A-n77A | DC_1A_n77A DC_3A_n77A DC_41A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
175 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-41A_n41A | DC_1A_n41A DC_3A_n41A DC_41A_n41A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
176 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-41A_n77(2A) | DC_1A_n77A DC_3A_n77A DC_41A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
177 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-41A_n77A | DC_1A_n77A DC_3A_n77A DC_41A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
178 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n28A-n77A | DC_1A_n77A DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
179 | Y | 2Tx PC2 EN-DC BC | DC_1A-41A_n28A-n77A | DC_1A_n77A DC_41A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
180 | Y | 2Tx PC2 EN-DC BC | DC_1A-41A_n41A | DC_1A_n41A DC_41A_n41A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
181 | Y | 2Tx PC2 EN-DC BC | DC_3A-41A_n41A | DC_3A_n41A DC_41A_n41A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
182 | Y | 2Tx PC2 EN-DC BC | DC_48A_n77A | n77 | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
183 | Y | 2Tx PC2 EN-DC BC | DC_7A-7A_n78A | DC_7A_n78A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
184 | Y | 2Tx PC2 EN-DC BC | DC_1A-18A_n28A-n77A | DC_1A_n77A DC_18A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
185 | Y | 2Tx PC2 EN-DC BC | DC_3A-18A_n28A-n77A | DC_3A_n77A DC_18A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
186 | Y | 2Tx PC2 EN-DC BC | DC_3A-18A_n41A-n77A | DC_3A_n41A DC_18A_n41A DC_3A_n77A DC_18A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
187 | Y | 2Tx PC2 EN-DC BC | DC_1A-28A_n41A-n77A | DC_1A_n41A DC_28A_n41A DC_1A_n77A DC_28A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
188 | Y | 2Tx PC2 EN-DC BC | DC_3A-28A_n41A-n77A | DC_3A_n41A DC_28A_n41A DC_3A_n77A DC_28A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
189 | Y | 2Tx PC2 EN-DC BC | DC_8A_n78A | DC_8A_n78A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
190 | Y | 2Tx PC2 EN-DC BC | DC_1A_n78(2A) | DC_1A_n78A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
191 | Y | 2Tx PC2 EN-DC BC | DC_3A_n78(2A) | DC_3A_n78A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
192 | Y | 2Tx PC2 EN-DC BC | DC_3A-8A_n78A | DC_3A_n78A DC_8A_n78A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
193 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n78(2A) | DC_1A_n78A DC_3A_n78A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
194 | Y | 2Tx PC2 EN-DC BC | DC_1A-41C_n28A-n77A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
195 | Y | 2Tx PC2 EN-DC BC | DC_3A-41C_n28A-n77A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
196 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-41C_n28A-n77A | DC_1A_n77A, DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
197 | Y | 2Tx PC2 EN-DC BC | DC_28A_n41A-n77A | DC_28A_n41A DC_28A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
198 | Y | 2Tx PC2 EN-DC BC | DC_1A-41A-42A_n77A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
199 | Y | 2Tx PC2 EN-DC BC | DC_1A-41C-42A_n77A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
200 | Y | 2Tx PC2 EN-DC BC | DC_3A-41A-42A_n77A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
201 | Y | 2Tx PC2 EN-DC BC | DC_3A-41C-42A_n77A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
202 | Y | 2Tx PC2 EN-DC BC | DC_3A-18A-42A_n77A | DC_3A_n77A DC_18A_n77A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
203 | Y | 2Tx PC2 EN-DC BC | DC_8B_n1A-n78A | DC_8A_n78A DC_8B_n78A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
204 | Y | 2Tx PC2 EN-DC BC | DC_3A-8B_n1A-n78A | DC_3A_n78A DC_8A_n78A DC_8B_n78A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
205 | Y | 2Tx PC2 EN-DC BC | DC_3A-3A-8B_n1A-n78A | DC_3A_n78A DC_8A_n78A DC_8B_n78A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
206 | Y | 2Tx PC2 EN-DC BC | DC_7A-8B_n1A-n78A | DC_7A_n78A DC_8A_n78A DC_8B_n78A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
207 | Y | 2Tx PC2 EN-DC BC | DC_7A-7A-8B_n1A-n78A | DC_7A_n78A DC_8A_n78A DC_8B_n78A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
208 | Y | 2Tx PC2 EN-DC BC | DC_3A-7A-8B_n1A-n78A | DC_3A_n78A DC_7A_n78A DC_8A_n78A DC_8B_n78A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
209 | Y | 2Tx PC2 EN-DC BC | DC_3A-3A-7A-8B_n1A-n78A | DC_3A_n78A DC_7A_n78A DC_8A_n78A DC_8B_n78A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
210 | Y | 2Tx PC2 EN-DC BC | DC_3A-7A-7A-8B_n1A-n78A | DC_3A_n78A DC_7A_n78A DC_8A_n78A DC_8B_n78A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
211 | Y | 2Tx PC2 EN-DC BC | DC_3A-3A-7A-7A-8B_n1A-n78A | DC_3A_n78A DC_7A_n78A DC_8A_n78A DC_8B_n78A | PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
212 | Y | 2Tx PC2 EN-DC BC | DC_1A_n3A-n28A-n79A | DC_1A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
213 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n28A-n79A | DC_1A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
214 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n28A-n79A | DC_3A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
215 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-8A_n79A | DC_1A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
216 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-8A_n79A | DC_3A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
217 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-8A_n79A | DC_8A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
218 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n28A-n79A | DC_1A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
219 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n28A-n79A | DC_8A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
220 | Y | 2Tx PC2 EN-DC BC | DC_1A_n3A-n28A-n77A-n79A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
221 | Y | 2Tx PC2 EN-DC BC | DC_1A_n3A-n28A-n77A-n79A | DC_1A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
222 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n28A-n77A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
223 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n28A-n77A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
224 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n28A-n77A-n79A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
225 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n28A-n77A-n79A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
226 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n28A-n77A-n79A | DC_1A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
227 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n28A-n77A-n79A | DC_3A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
228 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n77(3A) | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
229 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-8A_n28A-n77A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
230 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-8A_n28A-n77A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
231 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-8A_n28A-n77A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
232 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-8A_n77A-n79A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
233 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-8A_n77A-n79A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
234 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-8A_n77A-n79A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
235 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-8A_n77A-n79A | DC_1A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
236 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-8A_n77A-n79A | DC_3A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
237 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-8A_n77A-n79A | DC_8A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
238 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n77(2A)-n79A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
239 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n77(2A)-n79A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
240 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n77(2A)-n79A | DC_1A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
241 | Y | 2Tx PC2 EN-DC BC | DC_1A-8A_n77(2A)-n79A | DC_8A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
242 | Y | 2Tx PC2 EN-DC BC | DC_8A_n3A-n28A-n79A | DC_8A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
243 | Y | 2Tx PC2 EN-DC BC | DC_8A_n3A-n28A-n77A-n79A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
244 | Y | 2Tx PC2 EN-DC BC | DC_8A_n3A-n28A-n77A-n79A | DC_8A_n79A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
245 | Y | 2Tx PC2 EN-DC BC | DC_1A-41C_n3A-n77A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
246 | Y | 2Tx PC2 EN-DC BC | DC_1A-41A_n3A-n77A | DC_1A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
247 | Y | 2Tx PC2 EN-DC BC | DC_3A-41C_n3A-n77A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
248 | Y | 2Tx PC2 EN-DC BC | DC_3A-41A_n3A-n77A | DC_3A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
249 | Y | 2Tx PC2 EN-DC BC | DC_8A-41C_n1A-n77A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
250 | Y | 2Tx PC2 EN-DC BC | DC_8A-41A_n1A-n77A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
251 | Y | 2Tx PC2 EN-DC BC | DC_8A-41C_n3A-n77A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
252 | Y | 2Tx PC2 EN-DC BC | DC_8A-41A_n3A-n77A | DC_8A_n77A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
253 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-3A_n78A | DC_1A_n78A DC_3A_n78A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
254 | Y | 2Tx PC2 EN-DC BC | DC_1A-7A_n78A | DC_1A_n78A DC_7A_n78A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
255 | Y | 2Tx PC2 EN-DC BC | DC_1A-7A-7A_n78A | DC_1A_n78A DC_7A_n78A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
256 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-7A_n78A | DC_1A_n78A DC_3A_n78A DC_7A_n78A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
257 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-3A-7A_n78A | DC_1A_n78A DC_3A_n78A DC_7A_n78A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
258 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-7A-7A_n78A | DC_1A_n78A DC_3A_n78A DC_7A_n78A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
259 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-3A-7A-7A_n78A | DC_1A_n78A DC_3A_n78A DC_7A_n78A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
260 | Y | 2Tx PC2 EN-DC BC | DC_1A_n8A-n78A | DC_1A_n78A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
261 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A_n8A-n78A | DC_1A_n78A DC_3A_n78A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
262 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-3A_n8A-n78A | DC_1A_n78A DC_3A_n78A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
263 | Y | 2Tx PC2 EN-DC BC | DC_1A-7A_n8A-n78A | DC_1A_n78A DC_7A_n78A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
264 | Y | 2Tx PC2 EN-DC BC | DC_1A-7A-7A_n8A-n78A | DC_1A_n78A DC_7A_n78A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
265 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-7A_n8A-n78A | DC_1A_n78A DC_3A_n78A DC_7A_n78A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
266 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-3A-7A_n8A-n78A | DC_1A_n78A DC_3A_n78A DC_7A_n78A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
267 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-7A-7A_n8A-n78A | DC_1A_n78A DC_3A_n78A DC_7A_n78A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
268 | Y | 2Tx PC2 EN-DC BC | DC_1A-3A-3A-7A-7A_n8A-n78A | DC_1A_n78A DC_3A_n78A DC_7A_n78A | PC2 | [5 empty] | RAN4 status: New | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
3Tx PC2 EN-DC BC
1 | Y | 3Tx PC2 EN-DC BC | DC_1A-n78A | DC_1A-n78A | PC3 1Tx+PC3 2Tx / PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
2 | Y | 3Tx PC2 EN-DC BC | DC_3A-n78A | DC_3A-n78A | PC3 1Tx+PC3 2Tx / PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
3 | Y | 3Tx PC2 EN-DC BC | DC_5A-n78A | DC_5A-n78A | PC3 1Tx+PC3 2Tx / PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
4 | Y | 3Tx PC2 EN-DC BC | DC_1A-n78A | DC_1A-n78A | PC3 1Tx+PC2 2Tx / PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
5 | Y | 3Tx PC2 EN-DC BC | DC_3A-n78A | DC_3A-n78A | PC3 1Tx+PC2 2Tx / PC2 | [5 empty] | RAN4 status: Onging | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
6 | Y | 3Tx PC2 EN-DC BC | DC_5A-n78A | DC_5A-n78A | PC3 1Tx+PC2 2Tx / PC2 | [5 empty] | RAN4 status: Completed | 1 | 0% | 0% |  | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% |  |  | 0%
Note on T1: The TS's weight number is used to set the reletive weights between TS contributions used in the overall calculation of completeness of teh WP item. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new configuration or a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on M6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.
Note on Q12: Rapporteur guideline to assign applicable sub-areas for a WP item (columns S to X) To Set applicable sub-area(s) for a WP item do: - Copy the formula/cell content from one of the other non-empty cells under the "WP item status vs Area" section (columns S to X). To Clear applicable sub-area(s) for a WP item do: - Select the cell for teh WP item for the sub-area and press <Delete>-botton (clear content of the cell).