3GPP TSG-RAN WG4 Meeting #116-bis	R4-2513924

Prague, October 13th – August 17th, 2025

Source:	Nokia

Title:	Work Plan for SCM aspects in Rel-20 Demodulation

Agenda item:	6.6.2.3

Document for:	Discussion

Introduction

During RAN#109 the work item on demodulation performance phase 6 was agreed [1], whereby the WI starts during RAN4#116bis, within this contribution we present some views on the work plan of the Work Item as well as details of what Nokia believes should be included in TR 38.753.

Discussion

Work Plan (Specifically on SCM aspects)

In order to complete the work to develop spatial channel model requirements the following work plan is proposed, focussed on SCM aspects

| Meeting No. | Date | Details |
| --- | --- | --- |
| RAN4#116-bis | October 25 | Discuss possible updateds to TR 38.753 Discussion on Test Scope, Parameters and Assumptions |
| RAN4#117 | November 25 | Possible CRs for TR 38.753 Agreement on test scope for SU-PDSCH Continue discussion on test scope to SU-PMI |
| RAN #110 (December 25) |  |  |
| RAN4#118 | February 26 | Agreement on test scope for SU-PMI Initially discussion on applicability rules Simulation Alignment |
| RAN #111 (March 26) |  |  |
| RAN4#118-bis | April 26 | Update of simulation alignment Agreement on applicability |
| RAN4#119 | May 26 | Initial draft CRs submitted MU-MIMO Study Item Starts |
| RAN #112 (June 26) |  |  |
| RAN4#120 | August 26 | Refinement of draftCRs MU-MIMO Study continues |
| RAN #113 (September 26) |  |  |
| RAN4#120bis | October 26 | MU-MIMO Study continues |
| RAN4#121 | November 26 | Finalisation of CRs MU-MIMO Study continues |
| RAN #114 (December 26) |  |  |
| RAN4#122 | February 27 | MU-MIMO Study completes |
| RAN #115 (March 27) |  |  |

The work plan as indicated in this document shall be endorsed for the Spatial Channel Model aspects of the Rel-20 Demodulation work package

Conclusion

The paper presents a work plan for Rel-20 Demodulation aspects relating to Sparial Channel Modelling

The following Proposals is made:

Proposal 1: The work plan as indicated in this document shall be endorsed for the Spatial Channel Model aspects of the Rel-20 Demodulation work package

- References

- RP-252957; “NR demodulation performance Phase 6”, China Telecom, RAN#109, Beijing, September 2024.

- TR 38.753 v1.0.0

- RP-241610, “Study on spatial channel model for demodulation performance requirements for NR”, Nokia, BT Plc, RAN#107, Incheon, Korea, March 2025.