## R5#108
3GPP TSG RAN WG5 (RAN5) Meeting #108 | [9 empty] | R5-253714
Bengaluru, India 25 - 29 August 2025
WI Progress and Target Completion Date Review
Source: RAN5 Chair
To: RAN5
Purpose: For Endorsement
UIC | WI Name | Rel | Tdoc# | Pre TCD | pre % | post % | post TCD | change (mths) | Rapporteur | other comments
830083 | UE Conformance Test Aspects - Rel-16 NR CA and DC; and NR and LTE DC Configurations | Rel-16 | R5-253890 | 2025-12-01 | 64% | 64% | 2025-12-01 |  | CMCC
900056 | UE Conformance - Rel-17 NR CA and DC; and NR and LTE DC Configurations | Rel-17 | R5-254810 | 2025-12-01 | 11% | 11% | 2025-12-01 |  | Huawei
950062 | UE Conformance - Introduction of FR2 FWA (Fixed Wireless Access) UE with maximum TRP (Total Radiated Power) of 23dBm for band n257 and n258 | Rel-17 | R5-254574 | 2025-12-01 | 73% | 73% | 2025-12-01 |  | Huawei
960074 | UE Conformance - Solutions for NR to support non-terrestrial networks (NTN) | Rel-17 | R5-254870 | 2025-12-01 | 93% | 97% | 2025-12-01 |  | Qualcomm
960080 | UE Conformance - NR support for high speed train scenario in frequency range 2 | Rel-17 | R5-254662 | 2025-12-01 | 70% | 72% | 2025-12-01 |  | Samsung
960083 | UE Conformance - NR Sidelink Relay | Rel-17 | R5-254586 | 2025-09-01 | 90% | 95% | 2025-12-01 | +3 | CATT
960084 | UE Conformance - NR Sidelink enhancement | Rel-17 | R5-254583 | 2025-09-01 | 50% | 100% | 2025-09-01 |  | CATT
960089 | UE Conformance Test Aspects - NR RRM enhancement | Rel-16 | R5-254429 | 2025-09-01 | 90% | 93% | 2025-12-01 | +3 | Apple
1000051 | UE Conformance - High power UE (power class 2) for NR FR1 FDD single band | Rel-18 | R5-254405 | 2025-09-01 | 34% | 100% | 2025-09-01 |  | China Unicom
1000054 | UE Conformance - Rel-18 High Power UE for NR CA and DC; and NR and LTE DC Configurations | Rel-18 | R5-253965 | 2025-12-01 | 90% | 95% | 2025-12-01 |  | China Telecom
1000056 | UE Conformance - UE Conformance - Rel-17 Power Class 2 UE for NR inter-band CA/DC with or without SUL configurations with x (6>=x>2) bands DL and y (y=1, 2) bands UL | Rel-17 | R5-254808 | 2025-12-01 | 21% | 31% | 2025-12-01 |  | Huawei
1000057 | UE Conformance - Rel-18 NR CA and DC; and NR and LTE DC Configurations | Rel-18 | R5-254812 | 2025-12-01 | 76% | 76% | 2025-12-01 |  | Huawei
1020087 | UE Conformance - Air-to-ground network for NR | Rel-18 | R5-253874 | 2025-12-01 | 64% | 80% | 2025-12-01 |  | CMCC
1030060 | UE Conformance - NR support for dedicated spectrum less than 5MHz for FR1 | Rel-18 | R5-254371 | 2025-12-01 | 78% | 95% | 2025-12-01 |  | Nokia
1030062 | UE Conformance - Enhanced support of reduced capability NR devices plus CT1 | Rel-18 | R5-254224 | 2025-12-01 | 70% | 83% | 2025-12-01 |  | China Unicom
1030063 | UE Conformance - XR (eXtended Reality) enhancements for NR plus CT1 aspects | Rel-18 | R5-253788 | 2025-12-01 | 80% | 84% | 2025-12-01 |  | Nokia
1030064 | UE Conformance - Introduction of 900 MHz LTE band in the US | Rel-18 | R5-253867 | 2025-09-01 | 96% | 100% | 2025-09-01 |  | Nokia
1030065 | UE Conformance - NR RF requirements enhancement for frequency range 2 (FR2), Phase 3 | Rel-18 | R5-254857 | 2025-12-01 | 65% | 80% | 2025-12-01 |  | Apple
1030066 | UE Conformance - Further RF requirements enhancement for NR and EN-DC in frequency range 1 | Rel-18 | R5-254576 | 2025-12-01 | 54% | 59% | 2025-12-01 |  | Huawei
1030067 | UE Conformance - Network energy savings for NR | Rel-18 | R5-254458 | 2025-12-01 | 90% | 97% | 2025-12-01 |  | Huawei
1030069 | UE Conformance - Further NR coverage enhancements | Rel-18 | R5-254168 | 2025-12-01 | 76% | 76% | 2025-12-01 |  | China Telecom
1030070 | UE Conformance - Multi-carrier enhancements for NR | Rel-18 | R5-254526 | 2025-12-01 | 95% | 97% | 2025-12-01 |  | China Telecom
1030071 | UE Conformance - Enhanced NR support for high speed train scenario in frequency range 2 (FR2) | Rel-18 | R5-254658 | 2025-12-01 | 38% | 38% | 2025-12-01 |  | Samsung
1030072 | UE Conformance - NR MIMO evolution for downlink and uplink | Rel-18 | R5-254660 | 2025-12-01 | 59% | 60% | 2025-12-01 |  | Samsung
1030073 | UE Conformance - IoT (Internet of Things) NTN (non-terrestrial network) enhancements plus CT1 aspects | Rel-18 | R5-253871 | 2025-12-01 | 80% | 87% | 2025-12-01 |  | CMCC
1040103 | UE Conformance - Mobile Terminated-Small Data Transmission (MT-SDT) for NR | Rel-18 | R5-254185 | 2025-12-01 | 90% | 95% | 2025-12-01 |  | Qualcomm
1040104 | UE Conformance - In-Device Co-existence (IDC) enhancements for NR and MR-DC | Rel-18 | R5-253917 | 2026-06-01 | 55% | 60% | 2026-06-01 |  | CMCC
1040105 | UE Conformance - NR demodulation performance evolution | Rel-18 | R5-254440 | 2025-12-01 | 77% | 80% | 2025-12-01 |  | China Telecom
1040106 | UE Conformance - Non-Public Networks Phase 2: NG-RAN aspects plus CT1 aspects | Rel-18 | R5-253967 | 2025-12-01 | 32% | 50% | 2025-12-01 |  | China Telecom
1040107 | UE Conformance - Expanded and improved NR positioning | Rel-18 | R5-253864 | 2026-06-01 | 9% | 16% | 2026-06-01 |  | CATT
1040108 | UE Conformance - Further NR mobility enhancements | Rel-18 | R5-253744 | 2025-12-01 | 70% | 80% | 2025-12-01 |  | MediaTek
1040113 | UE Conformance - Requirement for NR frequency range 2 (FR2) multi-Rx chain DL reception | Rel-18 | R5-254876 | 2025-12-01 | 30% | 45% | 2025-12-01 |  | Qualcomm
1050128 | UE Conformance - Protocol enhancements for Mission Critical Services (MCPTT, MCVideo, MCData) for Rel-17 | Rel-17 | R5-254288 | 2025-12-01 | 47% | 66% | 2025-12-01 |  | Ericsson
1050130 | UE Conformance - NR NTN (non-Terrestrial Networks) enhancements plus CT aspects | Rel-18 | R5-254872 | 2025-12-01 | 15% | 20% | 2025-12-01 |  | Qualcomm
1050131 | UE Conformance - New bands and bandwidth allocation for LTE based 5G terrestrial broadcast | Rel-18 | R5-254874 | 2025-12-01 | 15% | 20% | 2025-12-01 |  | Qualcomm
1050132 | UE Conformance - Further enhancements on NR and MR-DC measurement gaps and measurements without gaps | Rel-18 | R5-253746 | 2025-12-01 | 55% | 70% | 2025-12-01 |  | MediaTek
1050133 | UE Conformance - IMS Data Channel for NG RTC (Real Time Communication) | Rel-18 | R5-254124 | 2025-12-01 | 71% | 99% | 2025-12-01 |  | Huawei
1060075 | UE Conformance - Alignment of eCall over IMS with CEN | Rel-19 | R5-254187 | 2025-12-01 | 90% | 94% | 2026-03-01 |  | Qualcomm
1060077 | UE Conformance - Enhancements of NR Multicast and Broadcast Services including CT aspects | Rel-18 | R5-254588 | 2025-12-01 | 5% | 10% | 2025-12-01 |  | CATT
1070060 | UE Conformance - NR Support for UAV (Uncrewed Aerial Vehicles) plus CT1 aspects | Rel-18 | R5-254231 | 2026-03-01 | 28% | 42% | 2026-03-01 |  | China Unicom
1070061 | UE Conformance - Access Traffic Steering, Switch and Splitting support in the 5G system architecture; Phase 3 | Rel-18 | R5-253722 | 2026-03-01 | 5% | 59% | 2026-03-01 |  | China Telecom
1070062 | UE Conformance - Introduction of Power Class 2 and UE 40MHz Channel Bandwidth in NR band n28 | Rel-19 | R5-253901 | 2026-03-01 | 54% | 92% | 2026-03-01 |  | CMCC
1070063 | UE Conformance - Rel-19 NR CA and DC; and NR and LTE DC Configurations | Rel-19 | R5-254814 | 2026-12-01 | 5% | 5% | 2026-12-01 |  | Huawei
1080075 | UE Conformance - MPS when access to EPC/5GC is WLAN | Rel-18 | R5-253724 | 2026-03-01 |  | 5% | 2026-03-01 |  | China Telecom
1080076 | UE Conformance - Rel-19 High power UE (power class 1.5 and 2) for NR FR1 TDD/FDD single band for handheld/FWA UEs, and high power UE operation (power class 2, 1.5 and 1) for FWVM (fixed-wireless/vehicle-mounted) use cases in a single NR band | Rel-19 | R5-253908 | 2026-06-01 |  | 56% | 2026-06-01 |  | CMCC
1080077 | UE Conformance - NR channel BW less than 5MHz for FR1 Phase 2 | Rel-19 | R5-254170 | 2026-12-01 |  | 5% | 2026-12-01 |  | China Telecom
1080078 | UE Conformance - NR power class 2 RedCap (Reduced Capability) UE in FR1 | Rel-19 | R5-254646 | 2026-12-01 |  | 5% | 2026-12-01 |  | China Telecom
1080079 | UE Conformance - Rel-18 LTE CA Configurations | Rel-18 | R5-253969 | 2026-09-01 |  | 5% | 2026-09-01 |  | China Telecom
1080080 | UE Conformance - New Rel-19 NR licensed bands and extension of existing NR bands | Rel-19 | R5-254456 | 2027-06-01 |  | 10% | 2027-06-01 |  | Huawei
1080081 | UE Conformance - Rel-19 High power UE (power class 1.5 or 2) for Dual Connectivity (DC) combinations of LTE band(s) and NR band(s) | Rel-19 | R5-254402 | 2026-12-01 |  | 6% | 2026-12-01 |  | China Unicom
1080082 | UE Conformance - mmWave in NR UE spurious emissions and EESS (Earth Exploration Satellite Service) protection | Rel-19 | R5-254399 | 2026-06-01 |  | 22% | 2026-06-01 |  | China Unicom