## Slide 1: MCC TF160 Status Report (pre-RAN5#108)
Olivier Genoud
Task Force 160 Leader, 3GPP MCC

## Slide 2
TTCN workflow Simplified view
Note: Each step above has a feedback loop to any previous step(s) (e.g. prose/TTCN bug report).
Who:
RAN5_SIG
TF160 +
SS Vendors
TF160
SS Vendor(s) +
UE Vendor(s) +
TF160
Where:
RAN5 meeting
TTCN Workshop
ETSI
SS/UE Vendor
lab
scope of this report
Notes: ASP: Abstract Service Primitive
SS: System Simulator
TTCN: Testing and Test Control Notation (version 3)
UE: User Equipment

## Slide 3
Test Models – 5G:
  Rel-17:
    NR MBS: endorsed updates to NR_CLOSE_UE_TEST_LOOP type definition for Test Loop Mode C.
  Rel-18:
    NR cov. enh. Ph2: endorsed ASP updates to add new MAC CE(s) for PHR with assumed PUSCH.
    NR XR enh.: endorsed ASP updates to add new MAC CE for Delay Status Report (DSR).
    NR ATG: endorsed initial test model & ASP updates to enable NR ATG test cases implementation.
  Prose CR to TS 38.523-3 submitted at RAN5#108 for the above.
Test Models – POS:
  Rel-18 NR POS enh.: endorsed initial test model & ASP updates to enable NR POS enh. test cases implementation.
  Prose CR to TS 37.571-4 submitted at RAN5#108 for the above.
Test models & system interface design Progress at TTCN Workshop #70 (3rd Jul’25)
Notes: ASP: Abstract Service Primitive

## Slide 4
Test Models – LTE:
  Rel-18 band 106: endorsed test model updates to increase test coverage support.
Test Models – NB-IoT:
  Rel-16: endorsed further ASP updates to support Preconfigured UL Resource (PUR).
Prose CR to TS 36.523-3 submitted at RAN5#108 for the above.
RAN5 TTCN Workshop #70 material:
  https://portal.3gpp.org/Home.aspx#/meeting?MtgId=82438
Test models & system interface design Progress at TTCN Workshop #70 (3rd Jul’25)
Notes: ASP: Abstract Service Primitive

## Slide 5: TTCN development Progress for period: May to Aug’25
Completed:
  5G:
    Rel-17 NR MIMO further enhancements
  5G-Advanced Rel-18:
    eRedCap UE
    NR multi-carrier enh. (DCI x_3)
    NR MUSIM dual Tx/Rx
    NR MT small data Tx (SDT)
  NB-IoT Rel-17:
    IoT NTN early data Tx (EDT)
Started:
  5G-Advanced Rel-18:
    5G non-public networks (NPN) - Phase 2
  IMS Rel-15:
    Real-time text (RTT)
  NB-IoT Rel-18:
    IoT NTN flexible Tx-Rx separation
  LTE Rel-18:
    LTE Band 106 (3MHz BW)
Progressed:
  Mission Critical Rel-17:
    MCPTT over NR/5GC
    MCVideo over NR/5GC
    MCData over NR/5GC
Progressed:
  5G:
    Rel-16 V2X with NR sidelink
    Rel-17 NR MBS - Broadcast
  5G-Advanced Rel-18:
    NR NTN enhancements
    NR NW energy savings
    NR coverage further enh.
    NR mobility further enh.
  NB-IoT Rel-18:
    IoT NTN enhancements
  Positioning Rel-18:
    Expanded/improved NR POS
  IMS:
    Rel-18 IMS data channel
    Rel-19 eCall over IMS - CEN alignment
Notes: Completed: The TTCN of all test cases is ready for verification.
Progressed: TTCN development ongoing, not yet completed.
Started: TTCN development has started since last report.
Suspended: TTCN development on hold due to external blocker.

## Slide 6: TTCN verification Progress for period: 16th May --> 19th Aug’25
Completed:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
P-CSCF restoration (38.523) | Rel-15 | WI-504 | 2 / 2 | +2 | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 7: TTCN verification Progress for period: 16th May --> 19th Aug’25
Progressed – 5G (EN-DC, NR/5GC):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
EN-DC access stratum | Rel-15 | 503 | 98 / 104 | = | 
NR/5GC access stratum | Rel-15 | 503 | 155 / 164 | = | 
NR/5GC NR-DC | Rel-15 | 503 | 14 / 24 | = | 
NR/5GC NR CA | Rel-15 | 510 | 31 / 33 | = | 
EN-DC NR CA | Rel-15 | 512 | 14 / 18 | = | 
5G private network - SNPN | Rel-16 | 518 | 7 / 9 | = | 
NR mobility enhancements | Rel-16 | 522 | 10 / 16 | = | 
NR UE power saving | Rel-16 | 533 | 5 / 9 | = | 
IMS eCall over NR/5GC (38.523) | Rel-16 | 537 | 4 / 15 | = | +1 under verification
MR-DC & NR CA enhancements | Rel-16 | 544 | 9 / 28 | = | 
MPS Priority Indication | Rel-16 | none | 3 / 4 | = | 
NR reduced capability (RedCap) | Rel-17 | 530 | 7 / 10 | = | 
5G NW slicing enhancements - Phase 2 | Rel-17 | 549 | 7 / 8 | = | 
NR UE power saving enhancements | Rel-17 | 540 | 1 / 5 | = | +3 under verification
NR RAN slicing enhancement | Rel-17 | none | 4 / 8 | = | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 8: TTCN verification Progress for period: 16th May --> 19th Aug’25
Progressed – IMS, Positioning, MCX:
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
LTE positioning | Rel-9+ | 166, RTF-115 | 17 / 27 | = | 
MCPTT over LTE (IPCAN test model) | Rel-14 | 288, RFT-153 | 38 / 51 | = | 
MCPTT over LTE (E-UTRA test model) | Rel-14 | 288, RFT-153 | 2 / 51 | = | 
IMS eCall over LTE (34.229) | Rel-14 | 298 | 5 / 12 | = | 
MCData over LTE (IPCAN test model) | Rel-14 | 329, RFT-153 | 4 / 28 | = | 
MCPTT enhancements over LTE (IPCAN test model) | Rel-15 | 330, RFT-153 | 5 / 22 | = | 
IMS over NR/5GC | Rel-15 | 505 | 93 / 95 | = | 
NR Positioning | Rel-16 | none | 10 / 36 | = | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 9: TTCN verification Progress for period: 16th May --> 19th Aug’25
Progressed – 4G (LTE, eMTC, NB-IoT):
Feature | 3GPP Release | Priority (GCF/PTCRB) | Verified TC # | Progress | Comments
CA intra-band contiguous | Rel-11 | 162 | 20 / 21 | = | Left: TC 7.1.2.11.1(multiple TA)
LTE ACB per PLMN | Rel-12 | 226 | 12 / 14 | +6 | 
SCE-PHY | Rel-12 | 245 | 6 / 9 | = | 
eDRX | Rel-13 | 253 | 4 / 5 | = | Left: TC 9.2.4.1.3(emergency call)
eMTC (CAT-M1) | Rel-13 | 254-A | 14 / 15 | = | Left: TC 7.1.4.3a(Lch prioritization)
eMTC (CIoT) | Rel-13 | 254-C | 2 / 5 | = | 
NB-IoT (CAT-NB1) | Rel-13 | 257 | 72 / 73 | = | Left: TCs 22.1.1.M2
LAA | Rel-13 | 272 | 1 / 2 | = | Left: TC 8.3.1.32(RSSI measurement)
eNB-IoT | Rel-14 | 295 | 11 / 14 | = | Left: SC-PTM (in iWD-003), IRAT with E-UTRA
IMS eCall over LTE (36.523) | Rel-14 | 298 | 4 / 9 | = | 
Notes: Progressed: Evolution of TTCN test case verification compared to the last report. Not completed yet.

## Slide 10: TTCN verification Progress for period: 16th May --> 19th Aug’25
Started:
Starting:
Feature | 3GPP Release | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
NR NTN (GSO) | Rel-17 | none | 9 / 22 | +9 | +2 under verification
IMS eCall over LTE - CEN alignment (34.229) | Rel-19 | 344 | 5 / 13 | +5 | 
Feature | 3GPP Release | Priority (GCF / PTCRB) | Verified TC # | Progress | Comments
NB-IoT NTN (NGSO) | Rel-17 | 333_NB | 0 / 8 |  | +1 under verification
MCPTT over NR/5GC (NR5GC test model) | Rel-17 | none | 0 / 51 |  | +1 under verification
Notes: Started: lists the features for which at least one (first) test case has been submitted and agreed since the last report.
Starting: lists the feature for which no test case has yet been verified, but at least one submission has been made, which is under review (consultation period still running).

## Slide 11
2024 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC# | TTCN Develpmt | 2025 WkLoad | TTCN Development Status (as of Aug’25) / Comments
5G V2X with NR sidelink | Rel-16 | N,L | Q2’25 | 65 | Q4’20-Q4’25 | 1.5 | 78% (@iwd-25wk24)
LTE multi-USIM UE (MUSIM) | Rel-17 | L | Q3’23 | 7 | Q4’24-Q4’25 | 1 | Not started
NR multi/broadcast services (MBS) | Rel-17 | N | Q4’23 | 46 | Q4’22-Q1’26 | 2.5 | 20% (@iwd-25wk24)
NR sidelink enhancements | Rel-17 | N | Q3’25 | 2 | Q4’22-Q4’25 | 0.5 | Not started ; no prose
NR sidelink relay | Rel-17 | N | Q3’25 | 39 | Q4’22-Q1’26 | 2.5 | Not started
NR coverage enhancements | Rel-17 | N | Q1’24 | 17 | Q1’23-Q1’25 | 0.5 | 100% (@iwd-25wk11)
NR for non-terrestrial networks (NTN) | Rel-17 | N | Q4’25 | 22 | Q1’23-Q1’25 | 0.2 | 100% (@iwd-25wk11)
NR MIMO further enhancements | Rel-17 | N | Q2’24 | 9 | Q1’23-Q2’25 | 0.5 | 100% (@iwd-25wk24)
5G ATSSS – Phases 1 & 2 | R16to17 | N,W | Q3’24 | 15 | Q2’24-Q1’26 | 1 | Not started
Dual Tx/Rx MUSIM for NR | Rel-18 | N | Q2’25 | 4 | Q3’24-Q2’25 | 0.5 | 100% (@iwd-25wk24)
IoT NTN with enhancements | Rel-18 | L | Q4’25 | 9 | Q3’24-Q4’25 | 0.5 | 89% (@iwd-25wk24)
Enhanced RedCap NR UE | Rel-18 | N | Q4’25 | 13 | Q3’24-Q4’25 | 1.5 | 100% (@iwd-25wk24)
NR multi-carrier enhancements | Rel-18 | N | Q4’25 | 24 | Q3’24-Q4’25 | 2 | 100% (@iwd-25wk24)
NR coverage further enhancements | Rel-18 | N | Q4’25 | 14 | Q3’24-Q4’25 | 1.5 | 55% (@iwd-25wk24)
NR network energy savings | Rel-18 | N | Q4’25 | 8 | Q3’24-Q4’25 | 0.5 | 62% (@iwd-25wk24)
XR enhancements for NR | Rel-18 | N | Q4’25 | 21 | Q3’24-Q1’26 | 2.3 | 40% (@iwd-25wk11)
NR mobility further enhancements | Rel-18 | N | Q4’25 | 17 | Q4’24-Q1’26 | 1.5 | 20% (@iwd-25wk24)
5G non-public networks (NPN) – Phase 2 | Rel-18 | N | Q4’25 | 9 | Q4’24-Q4’25 | 1 | 44% (@iwd-25wk24)
Expanded & improved NR positioning | Rel-18 | N | Q2’26 | 21 | Q4’24-Q4’26 | 1 | 38% (@iwd-25wk24)
New/extended bands & band combination | R16to19 | L,N | Q4’26 | n/a | Q1’21-Q4’26 | 0.5 | 58% (@iwd-25wk24)
TTCN maintenance & deliveries |  |  |  |  | Q1–Q4 | 45 | 
Release & configuration management |  |  |  |  | Q1–Q4 | 6 | 
Total: |  |  |  | 362 |  | 74 | person-months
TTCN workplan 2025
Status of 2024 tasks carried over and maintenance tasks
Notes: Note: TTCN of some features initially started in 2024 will only be completed in 2025 due to availability of prose late in CY2024, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 12
2025 Tasks | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2025 WkLoad | TTCN Development Status (as of Aug’25) / Comments
MCX Client – Rel-17 enhancements | Rel-17 | L,N | Q4’25 | 197 | Q1’25-Q4’25 | 4 | 85% (@iwd-25wk24)
LTE Band 106 (3MHz BW) | Rel-18 | L | Q3’25 | n/a | Q1’25-Q4’25 | 2 | 25% (@iwd-25wk24)
NR FR1 less than 5MHz BW (3MHz BW) | Rel-18 | N | Q4’25 | n/a | Q1’25-Q1’26 | 2 | 30% (@iwd-25wk11)
NR MT SDT | Rel-18 | N | Q4’25 | 5 | Q1’25-Q4’25 | 1 | 100% (@iwd-25wk24)
NR/MR-DC IDC enhancements | Rel-18 | N,W | Q2’26 | 5 | Q1’25-Q2’26 | 1 | 40% (@iwd-25wk11)
NR NTN enhancements | Rel-18 | N | Q4’25 | 15 | Q1’25-Q1’26 | 2.5 | 13% (@iwd-25wk24)
IMS data channel | Rel-18 | N,L | Q4’25 | 22 | Q1’25-Q4’25 | 2 | 13% (@iwd-25wk24)
LTE based 5G terrestrial broadcast | Rel-18 | L | Q4’25 | ~20 | Q3’25-Q1’26 | 1.5 | Not started ; no prose
NR air-to-ground network | Rel-18 | N | Q4’25 | 6 | Q1’25-Q4’25 | 0.5 | Not started
NR MBS enhancements | Rel-18 | N | Q4’25 | 2 | Q1’25-Q1’26 | 0.5 | Not started ; no prose
5G ATSSS – Phase 3 | Rel-18 | N,W | Q1’26 | 8 | Q3’25-Q3’26 | 1 | Not started ; no prose
NR MIMO evolution for DL & UL | Rel-18 | N | Q4’25 | ~2 | Q1’25-Q1’26 | 0.5 | Not started ; no prose
Enhanced NR high-speed train scenario in FR2 | Rel-18 | N | Q4’25 | ~2 | Q1’25-Q1’26 | 0.5 | Not started ; no prose
NR support for UAV | Rel-18 | N | Q1’26 | 20 | Q3’25-Q3’26 | 1 | Not started ; no prose
eCall over IMS alignment with CEN | Rel-19 | N,L | Q1’26 | 26 | Q1’25-Q1’26 | 3 | 85% (@iwd-25wk24)
TEIx_Test (misc. test coverage enhancement) | Rel-8+ | All | n/a | 30 | Q1’25-Q4’25 | 3 | 2025 total after RAN5#107: 18 new tests
Total: |  |  |  | 360 |  | 26 | person-months
TTCN workplan 2025
Status of new 2025 tasks
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 13
2025 workload is estimated at 100 person-months (pm), see previous slides.
PCG#53/OP#52 approved the 3GPP funding of 58 pm for 2025 TTCN tasks.
GCF and CTIA/PTCRB have agreed to continue TF160 financial support in 2025.
Current commitments for 2025 are as follows:
3GPP companies / 3GPP MRPs committed to provide 19 pm as voluntary contributions for 2025 TTCN development.
Total resources of 97 pm  estimated funding gap of 3 pm.
TTCN funding 2025
Status
Funding |  | 
Entity | Person-months | Comments
3GPP | 58 | PCG#53/OP#52 approved
GCF | 12 | NR_feMIMO, ATSSS, NR_cov_enh(2), NwEnergySav, NR_XR_enh, NR_MT_SDT, NR-eNTN
CTIA/PTCRB | 6 | NR-(f)eCoverage, NR-(f)eMIMO, NR-feMobility, NwEnergySav
Qualcomm | 2 | eCallCEN, NR-eNTN, NR_Mob_enh2
Total: | 78 | 
TTCN experts free-of-charge |  | 
Entity | Person-months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 
Adare | 3 | 
Keysight | 1 | 
Rohde&Schwarz | 1 | 
Total: | 19 | 
Notes: MRPs: Market Representation Partners

## Slide 14
Course of action to secure funding for TF160 work in 2026:
  Prior to RAN5#108 meeting (August), a request to identify the potential TTCN development tasks in 2026 has been made to 3GPP members.
  At RAN5#108, a provisional ‘TTCN Tasks List’ shall be endorsed by RAN5.
  The TTCN Tasks List will be presented at RAN#109 (Sept) for TSG RAN initial endorsement.
  The RAN Chair will then present the List to 3GPP PCG/OP (Nov) in order to support TF160 request for the TTCN funding in 2026.
  The finalized TTCN Tasks List will be reviewed & endorsed at RAN5#109 (Nov) for TSG RAN approval at RAN#110 (Dec).
Based on feedback from several RAN5 member companies and 3GPP MRPs, the list of TTCN tasks presented in the next slides has been produced by the TF160 Leader.
Preparing for 2026 TTCN Work
Overview

## Slide 15
2025 Tasks (carried over) | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2026 WkLoad | 3GPP related Work Item
5G ATSSS – Phases 1, 2 & 3 | R16to18 | N,W | Q1’26 | 23 | Q2’24-Q3’26 | 2 | ATSSS-UEConTest, ATSSS_Ph2-UEConTest, ATSSS_Ph3-UEConTest
NR multi/broadcast services (MBS) | Rel-17 | N | Q4’23 | 46 | Q4’22-Q1’26 | 2 | NR_MBS_5MBS_5MBUSA-UEConTest
NR sidelink relay | Rel-17 | N | Q3’25 | 39 | Q4’22-Q1’26 | 2 | NR_SL_Relay-UEConTest
XR enhancements for NR | Rel-18 | N | Q4’25 | 21 | Q3’24-Q1’26 | 0.5 | NR_XR_enh_plus_CT1-UEConTest
NR mobility further enhancements | Rel-18 | N | Q4’25 | 17 | Q4’24-Q1’26 | 0.5 | NR_Mob_enh2-UEConTest
Expanded & improved NR positioning | Rel-18 | N | Q2’26 | 21 | Q4’24-Q4’26 | 0.5 | NR_pos_enh2-UEConTest
NR FR1 less than 5MHz BW (3MHz BW) | Rel-18 | N | Q4’25 | n/a | Q1’25-Q1’26 | 0.25 | NR_FR1_lessthan_5MHz_BW-UEConTest
NR/MR-DC IDC enhancements | Rel-18 | N,W | Q2’26 | 5 | Q1’25-Q2’26 | 0.25 | NR_IDC_enh-UEConTest
NR NTN enhancements | Rel-18 | N | Q4’25 | 15 | Q1’25-Q1’26 | 0.5 | NR_NTN_enh_plus_CT-UEConTest
LTE based 5G terrestrial broadcast | Rel-18 | L | Q4’25 | ~20 | Q3’25-Q1’26 | 1 | LTE_terr_bcast_bands
NR MBS enhancements | Rel-18 | N | Q4’25 | 2 | Q1’25-Q1’26 | 0.5 | NR_MBS_enh_5MBS_Ph2-UEConTest
NR MIMO evolution for DL & UL | Rel-18 | N | Q4’25 | ~2 | Q1’25-Q1’26 | 0.25 | NR_MIMO_evo_DL_UL-UEConTest
Enhanced NR high-speed train scenario in FR2 | Rel-18 | N | Q4’25 | ~2 | Q1’25-Q1’26 | 0.25 | NR_HST_FR2_enh-UEConTest
NR support for UAV | Rel-18 | N | Q1’26 | 20 | Q3’25-Q3’26 | 1 | NR_UAV_plus_CT1-UEConTest
eCall over IMS alignment with CEN | Rel-19 | N,L | Q1’26 | 26 | Q1’25-Q1’26 | 0.5 | eCallCEN-UEConTest
New/extended bands & band combination | Rel-19 | L,N | Q2’27 | n/a | Q1’25-Q2’27 | 0.5 | NR_lic_bands_BW_R19-UEConTest, NR_CADC_NR_LTE_DC_R19-UEConTest, IoT_NTN_FDD_S_band-UEConTest / new
TEIx_Test (new TC coverage) | Rel-15+ | All | n/a | 30 | Q1’26-Q4’26 | 3 | TEIx_Test
TTCN maintenance & deliveries |  |  |  |  | Q1’26-Q4’26 | 45 | 
Release & configuration management |  |  |  |  | Q1’26-Q4’26 | 6 | 
Total: |  |  |  | 289 |  | 66.5 | person-months
Preparing for 2026 TTCN Work – Tasks List
2025 tasks completion and maintenance
Notes: Note: TTCN of some features initially started in 2025 will only be completed in 2026 due to availability of prose late in CY2025, especially those which impacts the Test Models.
Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 16
2026 Tasks | Rel- | RAT | Prose Target | SIG TC # | TTCN Develpmt | 2026 WkLoad | 3GPP related Work Item
MPS when access to EPC/5GC is WLAN | Rel-18 | N,L,W | Q1’26 | 4 | Q1’26-Q3’26 | 0.5 | MPS_WLAN-UEConTest
Low-power wake-up signal & receiver for NR | Rel-18 | N | Q4’26 | TBD | Q1’26-Q4’26 | 1.5 | NR_LPWUS-UEConTest / new
NR multi-carrier enhancements – Phase 2 | Rel-19 | N | Q2’26 | 2 | Q1’26-Q3’26 | 0.5 | NR_MC_enh2-UEConTest / new
IoT NTN - TDD mode | Rel-19 | L | Q3’26 | TBD | Q1’26-Q4’26 | 2 | IoT_NTN_TDD-UEConTest / new
Ambient IoT | Rel-19 | N | Q4’26 | ~20 | Q1’26-Q4’26 | 6 | Ambient_IoT_Solutions-ConTest / new
NR duplex evolution: sub-band full duplex | Rel-19 | N | Q3’27 | TBD | Q1’26-Q4’27 | 2 | NR_duplex_evo-UEConTest / new
MCX Client – Rel-18 enhancements | Rel-18 | N,L | 2026 | ~30 | 2026 – 2027 | 3 | enh4MCPTT, MCOver5MBS, MCGWUE, MC_AHGC / no Test Work Item yet
NR sidelink evolution | Rel-18 | N | 2026 | TBD | 2026 – 2027 | 1 | NR_SL_enh2 / no test Work Item yet
IoT NTN – Phase 3 | Rel-19 | L | 2026 | TBD | 2026 – 2027 | 2 | IoT_NTN_Ph3 / no test Work Item yet
NR NTN – Phase 3 | Rel-19 | N | 2026 | TBD | 2026 – 2027 | 2 | NR_NTN_Ph3 / no test Work Item yet
NR XR – Phase 3 | Rel-19 | N | 2026 | TBD | 2026 – 2027 | 2 | NR_XR_Ph3 / no test Work Item yet
NR network energy savings – Phase 2 | Rel-19 | N | 2026 | TBD | 2026 – 2027 | 2 | Netw_Energy_NR_enh / no test Work Item yet
NR mobility enhancements – Phase 4 | Rel-19 | N | 2026 | TBD | 2026 – 2027 | 2 | NR_Mob_Ph4 / no test Work Item yet
NR MIMO – Phase 5 | Rel-19 | N | 2026 | TBD | 2026 – 2027 | 1 | NR_MIMO_Ph5 / no test Work Item yet
AI/ML for NR air interface | Rel-19 | N | 2026 | TBD | 2026 – 2027 | 3 | NR_AIML_air / no test Work Item yet
Inter-RAT mobility from E-UTRA TN to NR NTN | Rel-19 | N,L | 2026 | TBD | 2026 – 2027 | 2 | LTE_TN_NR_NTN_mob / no test Work Item yet
MCX Server | Rel-16 | L | 2026 | TBD | 2026 – 2027 | TBD | TBD / no test Work Item yet
Total: |  |  |  | TBD |  | 32.5 | person-months
Preparing for 2026 TTCN Work – Tasks List
New 2026 tasks
Notes: Legend:
Blue: changes from last MCC TF160 report.
Red: Important information.
Italics: Estimation based on limited information available.

## Slide 17
2026 Funding: 2026 workload is estimated at 99 person-months (pm), see previous slides.
  Funding will be requested to 3GPP PCG/OP.
    Typically, only part of necessary funding provided by PCG/OP
      example: 58 person-months in 2025
  Funding shall also be obtained through voluntary contributions from 3GPP companies and/or MRPs.
    Commitments received to date:
   RAN / RAN5 member companies and 3GPP MRPs are respectfully asked to consider providing funding support for the TTCN tasks in 2026.
Funding |  | 
Entity | Person-months | Comments
3GPP | TBD | 
TBD | TBD | 
Total: | TBD | 
TTCN experts free-of-charge |  | 
Entity | Person-months | Comments
TDIA (CAICT, CATT, HiSilicon, Starpoint) | 14 | 
TBD | TBD | 
Total: | 14 | 
Preparing for 2026 TTCN Work

## Slide 18: Annexes

## Slide 19: TTCN deliveries and baseline 2025 schedule
One TTCN-2 full delivery (FDD) and four TTCN-3 full deliveries.
Type definitions baseline upgrade to 3GPP Release 18 required in 2025:
  Rel-18 Phase2: partial upgrade to Rel-18 Dec'24 baseline for NR+E-UTRA+LPP due to new/updated ASN.1 IEs required by Rel-18 NR, NB-IoT & POS test cases.
Week number | iWD delivery date | TTCN CR cut-off date | TTCN agreement status report | Type of delivery | Comment
 wk03 |  |  | 17-Jan |  | GCF CAG#81 (21-22 Jan)
 wk09 |  |  | 28-Feb |  | PTCRB PVG#108 (4-6 Mar)
 wk11 | 14-Mar | 10-Mar | 14-Mar | TTCN-3 Rel-18 phase2 baseline upgrade | Partial upgrade to Rel-18 Dec'24 baseline for NR+E-UTRA+LPP
 wk17 |  |  | 25-Apr |  | GCF CAG#82 (29-30 Apr)
 wk19 |  |  | 09-May |  | PTCRB PVG#109 (13-15 May)
 wk24 | 13-Jun | 09-Jun | 13-Jun | TTCN-3 | 
 wk29 |  |  | 18-Jul |  | GCF CAG#83 (22-23 Jul)
 wk32 |  |  | 08-Aug |  | PTCRB PVG#110 (12-14 Aug)
wk38 | 19-Sep | 15-Sep | 19-Sep | TTCN-3 | 
wk41 |  |  | 10-Oct |  | GCF CAG#84 (14-15 Oct)
wk44 |  |  | 31-Oct |  | PTCRB PVG#111 (4-6 Nov)
wk49 | 05-Dec | 01-Dec |  | TTCN2 (FDD) | 
wk50 | 12-Dec | 08-Dec | 12-Dec | TTCN-3 |