## Cover sheet
RAN5 meeting #108 R5-254188
Bengaluru, India, 25th Aug 2025 - 29th Aug 2025
Agenda Item: | 7.4.2
Source: | Qualcomm Incorporated
Title: | New WID on UE Conformance - Alignment of eCall over IMS with CEN
Work item code: | eCallCEN-UEConTest
Release: | Rel-19
Document for: | Information
RAN5 WP template v2.0
1. Introduction
The objective of this work plan is to define the UE conformance test aspects corresponding to WID on Rel-19 eCallCEN-UEConTest.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 94% (+4%) | 29 (+6) | 36 (+8)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 95.2% (+95.2%)
FR1 |  | 95.2% (+95.2%)
FR2
N/A
LTE |  | 99.9% (+99.9%) | 16 (+16) | 16 (+16)
FR1 |  | 99.9% (+99.9%) | 16 (+16) | 16 (+16)
N/A
N/A
N/A
N/A
N/A
N/A
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR) | [5 empty] | LTE
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2 |  |  | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 0% |  |  | 0% | 0 (+1) | 1 (+1) |  |  |  |  | 0 (+1) | 1 (+1)
Applicability Protocol test cases | 38.523-2 | 0% |  |  | 0%
Test suites (TTCN) | 38.523-3
LTE
Protocol test cases | 36.523-1 | 100% (+100%) | 1 (+1) | 1 (+1) | [6 empty] | 100% (+100%) | 1 (+1) | 1 (+1)
Applicability Protocol test cases | 36.523-2 | 100% (+100%) | [8 empty] | 100% (+100%)
Test suites (TTCN) | 36.523-3
IMS
IMS over LTE protocol test cases | 34.229-1 | 90% (+5%) | 14 (+4) | 16 (+3) | [6 empty] | 90% (+5%) | 13 (+3) | 16 (+3)
IMS over 5GS protocol test cases | 34.229-5 | 90% (+5%) | 12 (+2) | 16 (+3) | 95% (+95%) | 12 (+2) | 16 (+3)
Applicability and ICS IMS test cases | 34.229-2 | 95% (+5%) | [8 empty] | 95% (+5%)
IMS Test suite (TTCN) | 34.229-3
5 References
RP-242495 - New WID on UE Conformance - Alignment of eCall over IMS with CEN
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | New WID on UE Conformance - Alignment of eCall capable with CEN | [11 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  |  | End of workplan columns. Note! Do not remove this column.
WI code |  | eCallCEN-UEConTest
WP Scope: |  | The objective of this work plan is to define the UE conformance test aspects corresponding to WID on Rel-19 eCallCEN-UEConTest. | [13 empty] | vs Area
WP Resp: |  | Yogesh Tugnawat |  |  | yogesht@qti.qualcomm.com | [5 empty] | WP item completion |  |  |  | SA Option 2 (SA NR) |  | LTE
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | LTE |  | FR1 | FR2 | FR1
[15 empty] | 95.2% (+95.2%) |  | 99.9% (+99.9%)
[15 empty] | 15 (+15) | 0 | 21 (+21)
[15 empty] | 0.1 (+0.1) | 0 | 16.5 (+16.5)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
7 |  | 38.508-1 | 4 | Placeholder for generic procedures | [5 empty] | TBD
TS 38.508-2: Common ICS
8 |  | 38.508-2 | A.4 | Introduce/update PICS parameters for eCall capable for NR test cases | [5 empty] | TBD
RAN and CN protocol
TS 38.523-1: Protocol test cases
General tests
9 |  | 38.523-1 | 11.5 | eCall capable | New sub-clause header |  |  |  |  | 0
49 | Y | 38.523-1 | 11.5.15 | eCall Only mode / 5GS supports IMS voice over PS session / 5GS supports emergency service / eCall over IMS is not supported / emergency call over IMS | [5 empty] | 1
TS 38.523-2: Applicability for Protocol test cases
11 |  | 38.523-2 | 4.1, 4.2 | Add/update PICS and test case applicability statements for the test cases in 38.523-1 | Add/update PICS and test case applicability statements for the test cases in 38.523-1 |  |  | R5-250385 |  | 0.1 | 95% (+95%) | 95% (+95%) |  |  | 95%
TS 38.523-3: Protocol test suites (TTCN)
12 |  | 38.523-3 | [7 empty] | TBD
LTE
LTE Common
TS 36.508: Common test environment
1 |  | 36.508 | 4 | Placeholder for generic procedures | [5 empty] | 0.5
RAN and CN protocol
TS 36.523-1: Protocol test cases
General tests
2 |  | 36.523-1 | 11.3 | Placeholder | [5 empty] | 0
45 | Y | 36.523-1 | 11.3.9 | eCall Only mode / EPS supports IMS voice over PS session / EPS supports emergency service / eCall over IMS is not supported / emergency call over IMS | (1) with { UE in eCall Only mode is in the state EMM-DEREGISTERED.eCALL-INACTIVE } ensure that { when { when EPS supports IMS voice over PS, emergency service and does not support eCall over IMS and UE is requested to make a manual eCall } then { UE sends RRC Connection Request message with establishmentCause set to ‘emergency’ and establishes the normal emergency call } } | Qualcomm | RAN5#108 (Aug-25) | R5-254969 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
TS 36.523-2: Applicability for Protocol test cases
5 |  | 36.523-2 | 4.1, 4.2 | Placeholder | [5 empty] | 0.1
46 |  | 36.523-2 | 4.1, 4.2 | Applicability updates to test cases in TS 36.523-1 |  | Qualcomm | RAN5#110 (Feb-26) | R5-254970 |  | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
TS 36.523-3: Protocol test suites (TTCN)
6 |  | 36.523-3 |  | Introduction of Signaling Test Environment for eCall capable for NR | [5 empty] | TBD
IMS
TS 34.229-1: IMS over LTE protocol test cases
13 |  | 34.229-1 | 21 | eCall capable | [5 empty] | 0
47 |  | 34.229-1 | 21 | General | Updates to General clause 21.0 |  | RAN5#108 (Aug-25) | R5-254971 |  | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
14 | Y | 34.229-1 | 21.19 | eCall only mode / Manual initiation / Emergency registration / Abnormal case / IM CN sends a 486 (Busy Here) with positive ACK / Successful MSD | Test to verify that on reception of reject cause 486 Busy here with positive acknowledgement for a manually initiated INVITE for eCall capable, UE considers MSD transmission as successful. | Qualcomm | RAN5#106 (Feb-25) | R5-251340 R5-253120 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
15 | Y | 34.229-1 | 21.2 | eCall only mode / Automatic initiation / Emergency registration / Abnormal case / IM CN sends a 600 (Busy Everywhere) with positive ACK / Successful MSD | Test to verify that on reception of reject cause 600 Busy Everywhere with positive acknowledgement for automatically initiated INVITE for eCall capable, UE considers MSD transmission as successful. | Qualcomm | RAN5#106 (Feb-25) | R5-251341 R5-253120 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
16 | Y | 34.229-1 | 21.21 | eCall only mode / Manual initiation / Emergency registration / Abnormal case / IM CN sends a 603 (Decline) with positive ACK / Successful MSD | Test to verify that on reception of reject cause 603 Decline with positive acknowledgement for a manually initiated INVITE for eCall capable, UE considers MSD transmission as successful. | Qualcomm | RAN5#106 (Feb-25) | R5-251342 R5-253120 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
17 | Y | 34.229-1 | 21.22 | eCall capable / Manual initiation / Emergency registration / 200 OK with NACK | Test to verify that the UE can correctly perform eCall capable when initiated manually and continues with call establishment after 200 OK with NACK is received from SS. The process consists of emergency registration and MSD included in INVITE during call setup. | Qualcomm | RAN5#106 (Feb-25) | R5-251343 R5-253120 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
34 | Y | 34.229-1 | 21.23 | eCall capable / Automatic initiation / Emergency registration / 200 OK with NACK | Test to verify that the UE can correctly perform eCall capable when initiated automatically and continues with call establishment after 200 OK with NACK is received. The process consists of emergency registration and MSD included in INVITE during call setup. | Qualcomm | RAN5#106 (Feb-25) | R5-251344 R5-253120 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
19 | Y | 34.229-1 | 21.24 | eCall capable / eCall to URI for test service / 200 OK with NACK | Test to verify that the UE can correctly perform test eCall capable when initiated and continues with call establishment after 200 OK with NACK is received. The process consists of normal registration and MSD included in INVITE during call setup. | Qualcomm | RAN5#106 (Feb-25) | R5-251345 R5-253120 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
32 | Y | 34.229-1 | 21.25 | eCall only mode / Automatic initiation / MSD transfer and 200 OK with ACK / SIP INFO request for MSD Update / PSAP Callback / Success | Test to verify that the UE sends correctly composed SIP INFO for MSD transfer during automatically initiated eCall capable and PSAP callback after successful completion of eCall capable in ecall only mode. | Qualcomm | RAN5#106 (Feb-25) | R5-251274 R5-253120 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
33 | Y | 34.229-1 | 21.26 | eCall only mode / eCall to URI for test service / MSD transfer and 200 OK with ACK / SIP INFO request for MSD Update / PSAP Callback / Success | Test to verify that the UE sends correctly composed SIP INFO for MSD transfer during test ecall and during PSAP callback after successful completion of test eCall capable in ecall only mode. | Qualcomm | RAN5#106 (Feb-25) | R5-251275 R5-253120 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
35 | Y | 34.229-1 | 21.27 | eCall capable / Automatic initiation / Emergency registration / Abnormal case / IM CN sends a 486 (Busy Here) with positive ACK / PSAP Callback / Success | Test to verify that on reception of reject cause 486 Busy here with positive acknowledgement for automatically initiated INVITE for eCall over IMS, UE considers MSD transmission as successful and wait for PSAP callback. The process consists of normal registration, emergency registration and MSD included in INVITE during call setup. | Qualcomm | RAN5#107 (May-25) | R5-253122 R5-253120 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
36 | Y | 34.229-1 | 21.28 | eCall capable / Manual initiation / Emergency registration / Abnormal case / IM CN sends a 600 (Busy Everywhere) with positive ACK / PSAP Callback / Success | Test to verify that on reception of reject cause 600 Busy Everywhere with positive acknowledgement for manually initiated INVITE for eCall over IMS, UE considers MSD transmission as successful and wait for PSAP callback. The process consists of normal registration, emergency registration and MSD included in INVITE during call setup. | Qualcomm | RAN5#107 (May-25) | R5-253123 R5-253120 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
37 | Y | 34.229-1 | 21.29 | eCall capable / Automatic initiation / Emergency registration / Abnormal case / IM CN sends a 603 (Decline) with positive ACK / PSAP Callback / Success | Test to verify that on reception of reject cause 603 Decline with positive acknowledgement for automatically initiated eCall over IMS, UE considers MSD transmission as successful and waits for PSAP callback. The process consists of normal registration, emergency registration and MSD included in INVITE during call setup. | Qualcomm | RAN5#108 (Aug-25) | R5-254408 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
39 | Y | 34.229-1 | 21.3 | eCall capable / Automatic initiation / Emergency registration / 200 OK with ACK / PSAP Callback / SIP INFO request for MSD Update / Success | Test to verify that the ecall capable UE sends correctly composed SIP INVITE and SIP INFO for MSD transfer during automatically initiated eCall over IMS and PSAP callback respectively. This process is described in 3GPP TS 24.229 [10]. | Qualcomm | RAN5#107 (May-25) | R5-253124 R5-253120 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
38 | Y | 34.229-1 | 21.31 | eCall capable / eCall to URI for test service / 200 OK with ACK / PSAP Callback / SIP INFO request for MSD Update / Success | Test to verify that the ecall capable UE sends correctly composed SIP INFO for MSD transfer during test ecall and during PSAP callback after successful completion of test eCall over IMS. This process is described in 3GPP TS 24.229 [10]. | Qualcomm | RAN5#108 (Aug-25) | R5-254496 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
48 | Y | 34.229-1 | 21.32 | eCall capable / Manual initiation / Emergency registration / 200 OK without ACK/NACK / PSAP Callback / Success | Test to verify that the UE can correctly perform eCall over IMS when initiated manually, continues with call establishment after 200 OK without ACK or NACK is received from SS and handles PSAP callback after completion of eCall over IMS. This process is described in 3GPP TS 24.229 [10]. | Qualcomm | RAN5#108 (Aug-25) | R5-254522 |  | 1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
50 | Y | 34.229-1 | 21.33 | eCall capable / eCall to URI for test service / 200 OK without ACK/NACK / PSAP Callback / Success |  | Qualcomm | RAN5#109 (Nov-25) |  |  | 1 | 0% |  | 0% |  |  |  | 0%
51 | Y | 34.229-1 | 21.34 | eCall only mode / Automatic initiation / Emergency registration / 200 OK without ACK/NACK / PSAP Callback / Success |  | Qualcomm | RAN5#109 (Nov-25) |  |  | 1 | 0% |  | 0% |  |  |  | 0%
52 | Y | 34.229-1 | 21.35 | eCall only mode / eCall to URI for test service / 200 OK without ACK/NACK / PSAP Callback / Success |  | Qualcomm | RAN5#110 (Feb-26) |  |  | 1 | 0% |  | 0% |  |  |  | 0%
20 |  | 34.229-1 | A | Annexes
21 |  | 34.229-1 | A | Updates to Annexes - default messages | A.2.9, A.3.1, A.2.19, A.2.20 updates | Qualcomm | RAN5#108 (Aug-25) | R5-251338, R5-251339, R5-251276 R5-252213 R5-252216 R5-253120 R5-254500 |  | 0.1 | 90% (+90%) |  | 95% (+95%) |  |  |  | 95%
TS 34.229-5: IMS over 5GS protocol test cases
22 |  | 34.229-5 | Annex | [6 empty] | 1
23 |  | 34.229-5 | 11 | General | Updates to General clause 11.0 |  | RAN5#108 (Aug-25) | R5-254978 |  |  | 100% (+100%) | 100% (+100%) |  |  | 100%
24 | Y | 34.229-5 | 11.7 | eCall capable UE / Manual initiation / Emergency registration / 200 OK with NACK | Test to verify that on reception of reject cause 486 Busy here with positive acknowledgement for a manually initiated INVITE for eCall capable, UE considers MSD transmission as successful. | Qualcomm | RAN5#106 (Feb-25) | R5-251398 R5-253128 |  |  | 100% (+100%) | 100% (+100%) |  |  | 100%
25 | Y | 34.229-5 | 11.8 | eCall capable UE / Automatic initiation / Emergency registration / 200 OK with NACK | Test to verify that on reception of reject cause 600 Busy Everywhere with positive acknowledgement for automatically initiated INVITE for eCall capable, UE considers MSD transmission as successful. | Qualcomm | RAN5#106 (Feb-25) | R5-251399 R5-253128 |  |  | 100% (+100%) | 100% (+100%) |  |  | 100%
26 | Y | 34.229-5 | 11.9 | eCall capable UE / eCall to URI for test service / 200 OK with NACK | Test to verify that on reception of reject cause 603 Decline with positive acknowledgement for a manually initiated INVITE for eCall capable, UE considers MSD transmission as successful. | Qualcomm | RAN5#106 (Feb-25) | R5-251400 R5-253128 |  |  | 100% (+100%) | 100% (+100%) |  |  | 100%
27 | Y | 34.229-5 | 11.1 | eCall only mode / Manual initiation / Emergency registration / Abnormal case / IM CN sends a 486 (Busy Here) with positive ACK / Successful MSD | Test to verify that the UE can correctly perform eCall capable when initiated manually and continues with call establishment after 200 OK with NACK is received from SS. The process consists of emergency registration and MSD included in INVITE during call setup. | Qualcomm | RAN5#106 (Feb-25) | R5-251401 R5-253128 R5-254979 |  |  | 100% (+100%) | 100% (+100%) |  |  | 100%
28 | Y | 34.229-5 | 11.11 | eCall only mode / Automatic initiation / Emergency registration / Abnormal case / IM CN sends a 600 (Busy Everywhere) with positive ACK / Successful MSD | Test to verify that the UE can correctly perform eCall capable when initiated automatically and continues with call establishment after 200 OK with NACK is received. The process consists of emergency registration and MSD included in INVITE during call setup. | Qualcomm | RAN5#106 (Feb-25) | R5-251402 R5-253128 R5-254979 |  |  | 100% (+100%) | 100% (+100%) |  |  | 100%
29 | Y | 34.229-5 | 11.12 | 11.12 eCall only mode / Manual initiation / Emergency registration / Abnormal case / IM CN sends a 603 (Decline) with positive ACK / Successful MSD | Test to verify that the UE can correctly perform test eCall capable when initiated and continues with call establishment after 200 OK with NACK is received. The process consists of normal registration and MSD included in INVITE during call setup. | Qualcomm | RAN5#106 (Feb-25) | R5-251403 R5-253128 R5-254979 |  |  | 100% (+100%) | 100% (+100%) |  |  | 100%
30 | Y | 34.229-5 | 11.13 | 11.13 eCall only mode / Automatic initiation / MSD transfer and 200 OK with ACK / SIP INFO request for MSD Update / PSAP Callback / Success | (1) with { UE subjected to national regulations in CEN EN 17184 having previously established eCall type of emergency service } ensure that { when { UE receives INVITE for an incoming IMS call } then { UE checks the header fields in incoming IMS call for PSAP callback and responds with 200 OK } } (2) with { UE subjected to national regulations in CEN EN 17184 having previously established eCall type of emergency service } ensure that { when { SS requests for tranfer of MSD during an incoming IMS call } then { The UE sends 200 OK and performs MSD transfer } } | Qualcomm | RAN5#106 (Feb-25) | R5-251404 R5-253128 R5-255087 |  |  | 100% (+100%) | 100% (+100%) |  |  | 100%
31 | Y | 34.229-5 | 11.14 | 11.14 eCall only mode / eCall to URI for test service / MSD transfer and 200 OK with ACK / SIP INFO request for MSD Update / PSAP Callback / Success | (1) with { UE subjected to national regulations in CEN EN 17184 UE has an ongoing ecall to uri for test services } ensure that { when { SS sends SIP INFO message for MSD } then { the UE sends SIP INFO message including MSD } } (2) with { UE subjected to national regulations in CEN EN 17184 having previously established eCall to URI for test services } ensure that { when { UE receives INVITE for an incoming IMS call } then { UE checks the header fields in incoming IMS call for PSAP callback and responds with 200 OK } } (3) with { UE subjected to national regulations in CEN EN 17184 having previously established eCall to URI for test services } ensure that { when { SS requests for tranfer of MSD during an incoming IMS call } then { The UE sends 200 OK and performs MSD transfer } } | Qualcomm | RAN5#106 (Feb-25) | R5-251398 R5-253128 R5-253979 |  |  | 100% (+100%) | 100% (+100%) |  |  | 100%
40 | Y | 34.229-5 | 11.15 | eCall capable / Automatic initiation / Emergency registration / Abnormal case / IM CN sends a 486 (Busy Here) with positive ACK / PSAP Callback / Success | (1) with { UE is requested to make a automatic eCall over IMS } ensure that { when { UE receives 486(Busy Here) with positive ACK } then { UE considers MSD transmission successful } } (2) with { UE subjected to national regulations in CEN EN 17184 having previously considering that UE MSD transmission was successful } ensure that { when { UE receives INVITE for an incoming IMS call for PSAP callback } then { UE responds with 200 OK including correctly composed header fields } } (3) with { UE subjected to national regulations in CEN EN 17184 having previously considering that UE MSD transmission was successful } ensure that { when { SS requests for tranfer of MSD during an incoming IMS call } then { UE responds with 200 OK and performs MSD transfer } } | Qualcomm | RAN5#107 (May-25) | R5-253125 R5-254975 |  |  | 100% (+100%) | 100% (+100%) |  |  | 100%
41 | Y | 34.229-5 | 11.16 | eCall capable / Manual initiation / Emergency registration / Abnormal case / IM CN sends a 600 (Busy Everywhere) with positive ACK / Successful MSD | (1) with { UE is requested to make a manual eCall over IMS } ensure that { when { UE receives 600 (Busy Everywhere) with positive ACK } then { UE considers MSD transmission successful } } (2) with { UE subjected to national regulations in CEN EN 17184 having previously receives 600 (Busy Everywhere) with positive ACK } ensure that { when { UE receives INVITE for an incoming IMS call for PSAP callback } then { UE responds with 200 OK including correctly composed header fields } } (3) with { UE subjected to national regulations in CEN EN 17184 having previously 600 (Busy Everywhere) with positive ACK } ensure that { when { SS requests for tranfer of MSD during an incoming IMS call } then { UE responds with 200 OK and performs MSD transfer } } | Qualcomm | RAN5#107 (May-25) | R5-253126 R5-253128 R5-254976 |  |  | 100% (+100%) | 100% (+100%) |  |  | 100%
42 | Y | 34.229-5 | 11.17 | eCall capable / Automatic initiation / Emergency registration / Abnormal case / IM CN sends a 603 (Decline) with positive ACK / PSAP Callback / Success | (1) with { UE is requested to make a automatic eCall over IMS } ensure that { when { UE receives 603 (Decline) with positive ACK } then { UE considers MSD transmission successful } } (2) with { UE subjected to national regulations in CEN EN 17184 having previously received 603(Decline) with positive ACK } ensure that { when { UE receives INVITE for an incoming IMS call for PSAP callback } then { UE responds with 200 OK including correctly composed header fields } } (3) with { UE subjected to national regulations in CEN EN 17184 having previously received 603 (Decline) with positive ACK } ensure that { when { SS requests for transfer of MSD during an incoming IMS call } then { UE responds with 200 OK and performs MSD transfer } } | Qualcomm | RAN5#108 (Aug-25) | R5-254972 |  |  | 100% (+100%) | 100% (+100%) |  |  | 100%
43 | Y | 34.229-5 | 11.18 | eCall capable / Automatic initiation / Emergency registration / 200 OK with ACK / PSAP Callback / SIP INFO request for MSD Update / Success | (1) with { UE subjected to national regulations in CEN EN 17184 having previously established eCall type of emergency service } ensure that { when { UE receives INVITE for an incoming IMS call for PSAP callback } then { UE responds with 200 OK including correctly composed header fields } } (2) with { UE subjected to national regulations in CEN EN 17184 having previously established eCall type of emergency service } ensure that { when { SS requests for tranfer of MSD during an incoming IMS call } then { UE responds with 200 OK and performs MSD transfer } } | Qualcomm | RAN5#107 (May-25) | R5-253127 R5-255088 |  |  | 100% (+100%) | 100% (+100%) |  |  | 100%
44 | Y | 34.229-5 | 11.19 | eCall capable / eCall to URI for test service / Normal registration / 200 OK with ACK / PSAP Callback / SIP INFO request for MSD Update / Success | (1) with { UE subjected to national regulations in CEN EN 17184 having previously established eCall to URI for test services } ensure that { when { UE receives INVITE for an incoming IMS call for PSAP callback } then { UE responds with 200 OK including correctly composed header fields } } (2) with { UE subjected to national regulations in CEN EN 17184 having previously established eCall to URI for test services } ensure that { when { SS requests for transfer of MSD during an incoming IMS call } then { UE responds with 200 OK and performs MSD transfer } } | Qualcomm | RAN5#108 (Aug-25) | R5-254973 |  |  | 100% (+100%) | 100% (+100%) |  |  | 100%
53 | Y | 34.229-5 | 11.2 | eCall capable / Manual initiation / Emergency registration / 200 OK without ACK/NACK / PSAP Callback / Success | Test to verify that the UE can correctly perform eCall over IMS when initiated manually, continues with call establishment after 200 OK without ACK or NACK is received from SS and handles PSAP callback after completion of eCall over IMS. This process is described in 3GPP TS 24.229 [10]. | Qualcomm | RAN5#109 (Nov-25) |  |  |  | 0% | 0% |  |  | 0%
54 | Y | 34.229-5 | 11.21 | eCall capable / eCall to URI for test service / 200 OK without ACK/NACK / PSAP Callback / Success |  | Qualcomm | RAN5#110 (Feb-26) |  |  |  | 0% | 0% |  |  | 0%
55 | Y | 34.229-5 | 11.22 | eCall only mode / Automatic initiation / Emergency registration / 200 OK without ACK/NACK / PSAP Callback / Success |  | Qualcomm | RAN5#110 (Feb-26) |  |  |  | 0% | 0% |  |  | 0%
56 | Y | 34.229-5 | 11.23 | eCall only mode / eCall to URI for test service / 200 OK without ACK/NACK / PSAP Callback / Success |  | Qualcomm | RAN5#109 (Nov-25) |  |  |  | 0% | 0% |  |  | 0%
TS 34.229-2: Applicability and ICS for IMS protocol test cases
24 |  | 34.229-2 | 2, A.4.5 | PICS for CEN support |  | Qualcomm | RAN5#108 (Aug-25) | R5-250472 R5-252219 |  | 0.1 | 100% (+100%) |  | 100% (+100%) |  |  |  | 100%
25 |  | 34.229-2 | 4.1, 4.2 | Applicability updates to test cases in TS 34.229-1/5 |  | Qualcomm | RAN5#108 (Aug-25) | R5-251346 R5-251406 R5-251940 R5-252646 R5-253129 R5-252219 R5-254980 R5-254503 R5-254524 |  | 0.1 | 90% (+90%) |  | 90% (+90%) |  |  |  | 90%
TS 34.229-3: IMS test suite (TTCN)
26 |  | 34.229-3 | [7 empty] | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.