## Cover sheet
<3GPP TSG RAN WG5#108> | [7 empty] | R5-254398
<Bengaluru , India, 25th Aug 2025 - 29th Aug 2025>
Agenda Item: | 7.5.2
Source: | China Unicom
Title: | UE Conformance - mmWave in NR UE spurious emissions and EESS (Earth Exploration Satellite Service) protection
Work item code: | 1050126
Release: | Rel-19
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
The objective of the UE Conformance – mmWave in NR UE spurious emissions and EESS (Earth Exploration Satellite Service) protection work item is to define the UE conformance requirements corresponding to WID on NR_mmWave_protect-UEConTest, analyse the test case impact, applicability, test environment, and update the relevant conformance specifications for the mmWave UE protection work item in Rel-19. At the RAN#108 meeting the Rel-19 RAN5 work item for UE Conformance – mmWave in NR UE spurious emissions and EESS (Earth Exploration Satellite Service) protection was approved , the WID is in [1]. The purpose of present document is to provide a work plan for the RAN5 work item. The work plan is updated after each RAN5 meeting to give the status of the work item.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 22% (+22%)
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR2) |  | 22.4% (+22.4%)
FR2 |  | 22.4% (+22.4%)
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1
Common ICS | 38.508-2
NR RF/RRM
FR2 RF common parts | 38.521-2 | 100% (+100%) |  |  | 100% (+100%)
FR2 RF Tx test cases | 38.521-2 Tx | 13.6% (+13.6%) |  |  | 13.6% (+13.6%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 25% (+25%) |  |  | 25% (+25%)
5 References
[1] RP-251514 | New WID: UE Conformance - mmWave in NR UE spurious emissions and EESS (Earth Exploration Satellite Service) protection
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | UE Conformance - mmWave in NR UE spurious emissions and EESS (Earth Exploration Satellite Service) protection | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | 1050126
WP Scope: |  | The purpose of present document is to provide a workplan for the RAN5 work item UE Conformance - mmWave in NR UE spurious emissions and EESS (Earth Exploration Satellite Service) protection comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID
WP Resp: |  | Huifang Sun(China Unicom), Runsen Tang(Samsung) |  |  | sunhf50@chinaunicom.cn, runsen.tang@samsung.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | N/A |  |  | N/A
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR2
22.4% (+22.4%)
15 (+15)
15 (+15)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  |  | No changes needed | TBD
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). |  |  |  |  | No changes needed | TBD
NR RF/RRM
TS 38.521-2: FR2 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
1 |  | 38.521-2 | 3.2 | Symbols | Add new symbols | China Unicom | RAN5#109 (Nov-25) | R5-255231 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
TS 38.521-2: FR2 RF test cases - Tx
|  | 38.521-2 Tx |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
2 |  | 38.521-2 Tx | 6.2.3 | UE maximum output power with additional requirements | Update A-MPR test case for NS_202 | Ericsson | RAN5#109 (Nov-25) |  | From PC1 to PC7 | 1 | 0% | 0% |  | 0%
2 |  | 38.521-2 Tx | 6.2.3 | UE maximum output power with additional requirements | Add new A-MPR test case for NS_205 | China Unicom | RAN5#109 (Nov-25) | R5-255231 |  | 1 | 100% (+100%) | 100% (+100%) |  | 100%
4 |  | 38.521-2 Tx | 6.2A.3 | UE maximum output power with additional requirements for CA | Update A-MPR test case for CA_NS_202 | Ericsson | RAN5#109 (Nov-25) |  | Currently only PC1~5 Adding intra-band contigous CA with non-contiguous allocation Non-contiguous CA will be skipped since no ongoing band combination | 1 | 0% | 0% |  | 0%
4 |  | 38.521-2 Tx | 6.2A.3 | UE maximum output power with additional requirements for CA | Add new A-MPR test case for CA_NS_205 | China Unicom | RAN5#109 (Nov-25) |  | Currently only PC1~5 Adding intra-band contigous CA with contiguous allocation and non-contiguous allocation Non-contiguous CA will be skipped since no ongoing band combination | 1 | 0% | 0% |  | 0%
4 |  | 38.521-2 Tx | 6.2D.3 | UE maximum output power with additional requirements for UL MIMO | Update A-MPR for UL-MIMO test case for NS_202 | Apple | RAN5#109 (Nov-25) |  | Currently only PC1~4 | 1 | 0% | 0% |  | 0%
4 |  | 38.521-2 Tx | 6.2D.3 | UE maximum output power with additional requirements for UL MIMO | Add new A-MPR test case for UL-MIMO for NS_205 | Apple | RAN5#109 (Nov-25) |  | Currently only PC1~4 | 1 | 0% | 0% |  | 0%
5 |  | 38.521-2 Tx | 6.5.3.3 | Additional spurious emissions | Update additional spurious emission for NS_202 | Apple | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0%
5 |  | 38.521-2 Tx | 6.5.3.3 | Additional spurious emissions | Update additional spurious emission for new NS_205 | Apple | RAN5#109 (Nov-25) | R5-254866 |  | 1 | 50% (+50%) | 50% (+50%) |  | 50%
6 |  | 38.521-2 Tx | 6.5A.3.3 | Additional spurious emissions for CA | Update additional spurious emission for CA_NS_202 | Ericsson | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0%
6 |  | 38.521-2 Tx | 6.5A.3.3 | Additional spurious emissions for CA | Update additional spurious emission for new CA_NS_205 | Ericsson | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0%
7 |  | 38.521-2 Tx | Annex P | Modified MPR behaviour | Update the Annex | all | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
8 |  | 38.903 | B.2.2.27 | Influence of noise | Check if the influence of noise for NS_202 need to be updated for the new requirement of -5dBm/200MHz Adding influence of noise for NS_205. | all | RAN5#109 (Nov-25) |  | The MU for additional spurious emission of -5dBm/200MHz might need to be revisited, therefore better to assign an item here. | 1 | 0% | 0% |  | 0%
9 |  | 38.903 | B.18 | Spurious emissions | Check if the MU value for NS_202 need to be updated for the new requirement of -5dBm/200MHz Adding MU value for NS_205. | all | RAN5#109 (Nov-25) |  | The MU for additional spurious emission of -5dBm/200MHz might need to be revisited, therefore better to assign an item here. | 1 | 0% | 0% |  | 0%
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.905 | 4.1.2.1 | A-MPR, A-SEM and A-SE FR2 test cases | Add test point analysis for NS_202, NS_205 and CA_NS_202, CA_NS_205 | all | RAN5#109 (Nov-25) | R5-255230 |  | 1 | 25% (+25%) | 25% (+25%) |  | 25%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.