## Cover sheet
3GPP TSG-RAN WG5 Meeting #108 | [8 empty] | R5-254585
Bengaluru, India, 25th August 2025 – 29th August 2025
Agenda Item: | 7.5.2
Source: | CATT, China Telecom
Title: | WP UE Conformance - NR Sidelink Relay
Work item code: | NR_SL_relay-UEConTest
Release: | Rel-17
Document for: | Information
RAN5 WP template v2.0-8
1. Introduction
The objective of this work item is to specify solutions to UE conformance testing corresponding to the features described in WID of NR Sidelink Relay, including protocol test cases and associated test environment, test applicability, etc.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 95%
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 95%
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
5GS
5GS Common
Common test environment | 38.508-1 | 100%
Common ICS | 38.508-2 | 100%
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
Applicability RF, Demod/QSI and RRM test cases | 38.522 | 0%
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0%
Test Point analysis receiver and transmitter test cases | 38.905
Radio Resource Management (RRM) | 38.533 | 100%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 100%
Applicability Protocol test cases | 38.523-2 | 100%
Test suites (TTCN) | 38.523-3
5 References
[1] RP-221447 | New WID on UE Conformance - NR sidelink enhancementNew WID on UE Conformance - NR Sidelink Relay
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - NR Sidelink Relay | [10 empty] | WP item status
WI code |  | NR_SL_relay-UEConTest
WP Scope: |  | The objective of this work item is to specify solutions to UE conformance testing corresponding to the features described in WID of NR Sidelink relay, including protocol, RF and RRM test cases and associated test environment, test applicability, etc.
WP Resp: |  | Xiaozhong CHEN | [8 empty] | WP item completion |  | PC5
TS Resp: |  | <TS responsible if a new TS is involved>
WP Item ID | Is new test case? |  | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) | FR1
95%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
TBD |  | 38.508-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.508-1 | 4 | Default NG-RAN RRC message and information elements contents | Adding default PC5 RRC messages | CATT | RAN5#108 (Aug-25) | R5-233423 R5-233424 R5-233425 R5-233426 R5-232743 R5-232746 R5-235369 R5-235370 R5-235371 R5-235372 R5-235373 R5-235391 R5-241597 R5-241598 R5-241599 R5-240480 R5-240482 R5-240483 R5-240484 R5-243547 R5-242802 R5-242803 R5-243548 R5-242805 R5-242806 R5-243549 R5-243550 R5-243551 R5-242810 R5-242811 R5-245580 R5-247581 R5-245581 R5-245582 R5-244976 R5-246894 R5-247580 R5-247199 R5-247582 R5-247583 R5-247202 R5-250970 R5-251307 R5-250979 R5-252522 R5-252523 R5-252524 R5-253102 R5-252526 R5-253103 R5-252528 R5-252529 R5-252530 R5-253104 R5-254604 R5-254605 |  |  | 100% | 100% | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
TBD |  | 38.508-2 | A.4 | <Title> | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | RAN5#101 (Dec-23) | R5-235374 R5-241600 |  | TBD | 100% | 100% | 100%
NR RF/RRM
TS 38.522: Applicability for RF, Demod/QSI reporting and RRM test cases
TBD |  | 38.522 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.522 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. |  | RAN5#109 (Nov-25) |  |  | 0.1
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.533 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD | Y | 38.533 | 9.1.6.3 | NR SA FR1 Interruptions at NR sidelink discovery configuration | Test Purpose(s): <Describe test purpose(s)> |  | RAN5#108 (Aug-25) | R5-255320 |  | TBD | 100% | 100% | 100%
TBD | Y | 38.533 | 9.1.7.1 | Selection / Reselection of relay UE | Test Purpose(s): <Describe test purpose(s)> |  | RAN5#108 (Aug-25) | R5-255321 |  | 1 | 100% | 100% | 100%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | RAN5#109 (Nov-25) |  |  | 0
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | RAN5#109 (Nov-25) |  |  | TBD
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected).
Remote UE
TBD |  | 38.523-1 | 12.3 | Sidelink Relay | New sub-clause header |  | RAN5#105 (Dec-24)
TBD |  | 38.523-1 | 12.3.1 | L2 UE-to-Network Relay | New sub-clause header |  | RAN5#105 (Dec-24)
TBD |  | 38.523-1 | 12.3.1.1 | Remote UE | New sub-clause header |  | RAN5#105 (Dec-24)
TBD | Y | 38.523-1 | 12.3.1.1.1 | Sidelink Relay / L2 U2N / Remote UE / Sidelink Synchronization / Synchonization Reference Source (Re-) Selection | Test Purpose(s): <Describe test purpose(s)> | China Telecom | RAN5#106 (Feb-25) | R5-251229 | TS 38.331 5.8.2 & 5.8.3 & 5.8.5; Reference to TC 12.1.2.1 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.2 | Sidelink Relay / L2 U2N / Remote UE / 5G ProSe Direct Discovery / Monitoring | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#106 (Feb-25) | R5-244978 R5-250986 | (Model A), TS 23.304 6.3.1.2 & 6.3.2.3 ; TS 24.554 6.2.4 & 6.2.5 & 8.2.1.2.3 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.3 | Sidelink Relay / L2 U2N / Remote UE / 5G ProSe Direct Discovery / Discoverer | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#106 (Feb-25) | R5-245583 R5-250987 | Model B, as a Discoverer UE TP1+TP2, TS 23.304 6.3.1.2 & 6.3.2.3 ; TS 24.554 6.2.7 & 8.2.1.3.1 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.4 | Sidelink Relay / L2 U2N / Remote UE / 5G ProSe Direct Discovery / Direct Discovery Update | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#105 (Dec-24) | R5-246898 | TS 24.554 6.2.11 & 6.2.12；TS 23.304 6.3.1.7 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.5 | Sidelink Relay / L2 U2N / Remote UE / 5G ProSe Direct Discovery / Announcing Alert | Test Purpose(s): <Describe test purpose(s)> | China Telecom | RAN5#107 (May-25) | R5-253099 | TS 24.554 6.2.13；TS 23.304 6.3.1.6 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.6 | Sidelink Relay / L2 U2N / Remote UE / 5G ProSe Direct Discovery / Match Report | Test Purpose(s): <Describe test purpose(s)> | China Telecom | RAN5#107 (May-25) | R5-253100 | (Match Reject) TS 24.554 6.2.8 & 6.2.9 & 6.2.10 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.7 | Sidelink Relay / L2 U2N / Remote UE / Direct link establishment, reject and release | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#104 (Aug-24) | R5-244987 |  | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.8 | Sidelink Relay / L2 U2N / Remote UE / Paging | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#104 (Aug-24) | R5-244980 | Remote UE in RRC_IDLE or RRC_INACTIVE TS38.331 5.3.2 5.8.9.9 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.9 | Sidelink Relay / L2 U2N / Remote UE / RRC reconfiguration / L2 U2N Remote UE configuration | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#106 (Feb-25) | R5-251308 R5-252539 | TS38.331 5.3.5.16 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.10 | Sidelink Relay / L2 U2N / Remote UE / SRAP | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#107 (May-25) | R5-253096 |  | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.11 | Sidelink Relay / L2 U2N / Remote UE / Radio link failure related actions | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#105 (Dec-24) | R5-251309 | TS38.331 5.3.10 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.12 | Sidelink Relay / L2 U2N / Remote UE / Measurement configuration control and reporting / Event X1 | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#104 (Aug-24) | R5-245584 |  | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.13 | Sidelink Relay / L2 U2N / Remote UE / Measurement configuration control and reporting / Event X2 | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#104 (Aug-24) | R5-245585 |  | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.14 | Sidelink Relay / L2 U2N / Remote UE / Measurement configuration control and reporting / Event Y1 | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#104 (Aug-24) | R5-245586 |  | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.15 | Sidelink Relay / L2 U2N / Remote UE / Measurement configuration control and reporting / Event Y2 | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#104 (Aug-24) | R5-245587 |  | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.16 | Sidelink Relay / L2 U2N / Remote UE / Measurement configuration control and reporting / Periodical reporting | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#104 (Aug-24) | R5-245589 R5-252564 |  | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.17 | Sidelink Relay / L2 U2N / Remote UE / Sidelink RRC reconfiguration | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#108 (Aug-25) | R5-247586 R5-254601 | TS38.331 5.8.9.1 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.18 | Sidelink Relay / L2 U2N / Remote UE / Sidelink radio link failure related actions | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#106 (Feb-25) | R5-251310 | TS38.331 5.8.9.3 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.19 | Sidelink Relay / L2 U2N / Remote UE / Selection of NR Sidelink U2N Relay UE | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#106 (Feb-25) | R5-247584 R5-250988 | TS38.331 5.8.14 5.8.15 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.20 | Sidelink Relay / L2 U2N / Remote UE / Reselection of NR Sidelink U2N Relay UE | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#106 (Feb-25) | R5-250985 | TS38.331 5.8.14 5.8.15 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.21 | Sidelink Relay / L2 U2N / Remote UE / Switching from indirect to direct path | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#107 (May-25) | R5-253097 |  | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.1.22 | Sidelink Relay / L2 U2N / Remote UE / Switching from direct to indirect path | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#107 (May-25) | R5-253098 |  | 1 | 100% | 100% | 100%
Relay UE
TBD |  | 38.523-1 | 12.3.1.2 | Relay UE | New sub-clause header |  | RAN5#105 (Dec-24)
TBD | Y | 38.523-1 | 12.3.1.2.1 | Sidelink Relay / L2 U2N / Relay UE / Sidelink Synchronization / SLSS Transmission | Test Purpose(s): <Describe test purpose(s)> | China Telecom | RAN5#106 (Feb-25) | R5-250761 | TS 38.331 5.8.2 & 5.8.3 & 5.8.5;Reference to TC 12.1.2.2 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.2.2 | Sidelink Relay / L2 U2N / Relay UE / 5G ProSe U2N Relay Discovery / Announcing | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#106 (Feb-25) | R5-245588 R5-250989 | (Model A), TS 23.304 6.3.1.2 & 6.3.2.3 ; TS 24.554 6.2.2 & 6.2.3 & 8.2.1.2.2 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.2.3 | Sidelink Relay / L2 U2N / Relay UE / 5G ProSe U2N Relay Discovery / Discoveree | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#105 (Dec-24) | R5-246900 | Model B, as a Discoveree UE TP1+TP2, TS 23.304 6.3.1.2 & 6.3.2.3 ; TS 24.554 6.2.6 & 8.2.1.3.2 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.2.4 | Sidelink Relay / L2 U2N / Relay UE / Direct link establishment, reject and release | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#104 (Aug-24) | R5-245590 |  | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.2.5 | Sidelink Relay / L2 U2N / Relay UE / System information acquisition | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#107 (May-25) | R5-252568 | TS38.331 5.2.2 5.8.9.8.3 SIB12 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.2.6 | Sidelink Relay / L2 U2N / Relay UE / Paging transimission | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#104 (Aug-24) | R5-244986 R5-246901 | Relay UE in RRC_IDLE, RRC_INACTIVE and RRC_CONNECTED TS38.331 5.3.2 5.8.9.9 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.2.7 | Sidelink Relay / L2 U2N / Relay UE / RRC connection establishment triggered by Remote UE | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#105 (Dec-24) | R5-246902 | TS38.331 5.3.3 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.2.8 | Sidelink Relay / L2 U2N / Relay UE / RRC connection establishment triggered by Remote UE / Emergency | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#105 (Dec-24) | R5-246907 | TS38.331 5.3.3 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.2.9 | Sidelink Relay / L2 U2N / Relay UE / RRC connection establishment triggered by Remote UE / Rejected / T300 expired | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#105 (Dec-24) | R5-246908 | TS38.331 5.3.3 5.8.9.10 5.3.15 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.2.10 | Sidelink Relay / L2 U2N / Relay UE / RRC connection resume trggered by Remote UE | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#105 (Dec-24) | R5-247585 | TS38.331 5.3.13 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.2.11 | Sidelink Relay / L2 U2N / Relay UE / RRC reconfiguration / Uu Relay RLC channel configuration | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#108 (Aug-25) | R5-250980 R5-254601 | TS38.331 5.3.5.5.12 5.3.5.5.13 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.2.12 | Sidelink Relay / L2 U2N / Relay UE / RRC reconfiguration / PC5 Relay RLC channel configuration | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#105 (Dec-24) | R5-250981 | TS38.331 5.3.5.5.12 5.3.5.5.13 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.2.13 | Sidelink Relay / L2 U2N / Relay UE / RRC reconfiguration / L2 U2N Relay UE configuration | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#106 (Feb-25) | R5-250975 R5-252541 | TS38.331 5.3.5.15 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.2.14 | Sidelink Relay / L2 U2N / Relay UE / Radio link failure related actions | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#106 (Feb-25) | R5-251311 | TS38.331 5.3.10 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.2.15 | Sidelink Relay / L2 U2N / Relay UE / Sidelink RRC reconfiguration | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#108 (Aub-25) | R5-247587 R5-250982 R5-254603 | TS38.331 5.8.9.1 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.2.16 | Sidelink Relay / L2 U2N / Relay UE / Sidelink radio link failure related actions | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#106 (Feb-25) | R5-251312 | TS38.331 5.8.9.3 | 1 | 100% | 100% | 100%
TBD | Y | 38.523-1 | 12.3.1.2.17 | Sidelink Relay / L2 U2N / Relay UE / SRAP | Test Purpose(s): <Describe test purpose(s)> | TDIA | RAN5#107 (May-25) | R5-253105 |  | 1 | 100% | 100% | 100%
TS 38.523-2: Applicabilities of Protocol test cases
TBD |  | 38.523-2 | 4.1 | Applicabilities of sidelink relay testcases | Add new ICS statements. | CATT | RAN5#107 (May-25) | R5-244990 R5-247588 R5-250762 R5-250978 R5-253101 R5-252571 |  | 0.1 | 100% | 100% | 100%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.