## Cover sheet
3GPP TSG-RAN WG5 Meeting #108 | [10 empty] | R5-254587
Bengaluru, India, 25th August 2025 – 29th August 2025
Agenda Item: | 7.5.2
Source: | CATT
Title: | WP UE Conformance - Enhancements of NR Multicast and Broadcast Services
Work item code: | NR_MBS_enh_5MBS_Ph2-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
<Description of work item and its scope>
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 10% (+5%) | 0 | 0%
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) |  | 10% (+5%) | 0 | 0
FR1 |  | 10% (+5%) | 0 | 0
FR2 |  | 10% (+5%) | 0 | 0
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
N/A
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1 |  |  | FR2
[5 empty] | Completion | Number of new completed test cases | Number of new test cases | Completion | Number of new completed test cases | Number of new test cases
5GS RAN and CN protocols
Common test environment | 38.508-1 | 50%
Common ICS | 38.508-2 | 0%
Protocol test cases | 38.523-1 | 0%
Applicability Protocol test cases | 38.523-2 | 0%
Test suites (TTCN) | 38.523-3 | 0%
5 References
[1] RP-243116 | New WID on UE Conformance - Enhancements of NR Multicast and Broadcast Services including CT aspects
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - Enhancements of NR Multicast and Broadcast Services including CT aspects | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status |  | End of workplan columns. Note! Do not remove this column.
WI code |  | WI_codeNR_MBS_enh_5MBS_Ph2-UEConTest
WP Scope: |  | The objective of this work item is to specify solutions to UE conformance testing corresponding to the features described in WID of Enhancements of NR Multicast and Broadcast Services including CT aspects, including protocol test cases and associated test environment, test applicability, etc. | [12 empty] | vs Area
WP Resp: |  | Xiaozhong CHEN |  |  | chenxiaozhong@catt.cn | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | <TS responsible if a new TS is involved> |  |  | <Email to TS responsible>
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1 | FR2
[14 empty] | 10% (+5%) | 10% (+5%)
[14 empty] | 2 (+2) | 2 (+2)
[14 empty] | 2 (+2) | 2 (+2)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 | [7 empty] | TBD
TBD |  | 38.508-1 | 4.6.1 |  | Update RRC messages for eMBS |  | RAN5#109 (Nov-25) |  |  | 0 | 50% | 50% |  | 50% | 50%
TBD |  | 38.508-1 | 4.6.2 |  | Configuration of SIB24 |  | RAN5#109 (Nov-25) |  |  | TBD | 0% | 0% |  | 0% | 0%
TS 38.508-2: Common ICS
|  | 38.508-2 | [7 empty] | TBD
TBD |  | 38.508-2 | A.4.3.14 |  | Add ICS as needed for the test case applicability statements for the new test cases introduced in RF, RRM and protocol test cases. |  | RAN5#109 (Nov-25) |  |  | TBD | 0% | 0% |  | 0% | 0%
TS 38.509: UE specific testing functions
|  | 38.509 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.509 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.509 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
RAN and CN protocol
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
MBS Broadcast
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of modified existing test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | TBD
TBD | Y | 38.523-1 | 14.1.4 | MBS Broadcast/ Inactive | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 1 | 0% | 0% |  | 0% | 0%
MBS Multicast
TBD |  | 38.523-1 | 14.1.4 | MBS Broadcast / MBS Interest Indication | New sub-clause header |  | TBD |  |  | 0
TBD | Y | 38.523-1 | 14.1.4.1 | MBS Broadcast / MBS Interest Indication / nonServingCellMII | Test Purpose(s): <Describe test purpose(s)> |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 14.1.4.2 | MBS Broadcast / MBS Interest Indication / RRCReconfiguration | Test Purpose(s): <Describe test purpose(s)> |  | RAN5#109 (Nov-25) |  |  | TBD | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 14.1.4.3 | MBS Broadcast / MBS Interest Indication / RRCReestablishment | Test Purpose(s): <Describe test purpose(s)> |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD |  | 38.523-1 | 14.2.6 | MBS multicast reception in RRC INACTIVE | New sub-clause header |  | TBD |  |  | 0
TBD | Y | 38.523-1 | 14.2.6.1 | MBS multicast reception in RRC INACTIVE / MCCH information acquisition / Multicast MCCH information change notification | Test Purpose(s): <Describe test purpose(s)> |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 14.2.6.2 | MBS multicast reception in RRC INACTIVE / MCCH information acquisition / Cell change | Test Purpose(s): <Describe test purpose(s)> |  | RAN5#109 (Nov-25) |  |  | TBD | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 14.2.6.3 | MBS multicast reception in RRC INACTIVE / MCCH information acquisition / Paging for group notification | Test Purpose(s): <Describe test purpose(s)> |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 14.2.6.4 | MBS multicast reception in RRC INACTIVE / MCCH information acquisition / RRCRelease | Test Purpose(s): <Describe test purpose(s)> |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 14.2.6.5 | MBS multicast reception in RRC INACTIVE / Service continuity / Cell reselection | Test Purpose(s): <Describe test purpose(s)> |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 14.2.6.6 | MBS multicast reception in RRC INACTIVE / MCCH information acquisition / UE initiated RRCResume | Test Purpose(s): <Describe test purpose(s)> |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TBD | Y | 38.523-1 | 14.2.6.7 | MBS multicast reception in RRC INACTIVE / MCCH information acquisition / Network initiated RRCResume | Test Purpose(s): <Describe test purpose(s)> |  | RAN5#109 (Nov-25) |  |  | 1 | 0% | 0% |  | 0% | 0%
TS 38.523-2: Applicability for Protocol test cases
TBD |  | 38.523-2 | <Clause> | <Title> | Add new ICS statements. |  | TBD |  |  | 0.1
TBD |  | 38.523-2 | <Clause> | <Title> | Add test case applicability statements for the new test cases introduced in 38.523-1 |  | TBD |  |  | 0.1
TS 38.523-3: Protocol test suites (TTCN)
|  | 38.523-3 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.523-3 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | TBD
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.