## Cover sheet
3GPP TSG-RAN WG5 Meeting #109 | [7 empty] | R5-256047
Dallas, Texas, USA, November 17th – November 21st, 2025
Agenda Item: | 7.5.2
Source: | CMCC
Title: | WP UE Conformance - Air-to-ground network for NR
Work item code: | NR_ATG-UEConTest
Release: | Rel-18
Document for: | Information
RAN5 WP template v3.0.0
1. Introduction
At the RAN#102 meeting in December 2023 the Rel-18 RAN5 work item for UE Conformance of Air-to-ground network for NR was approved [1]. The purpose of present document is to provide a work plan for the RAN5 work item to introduce the Rel-18 Air-to-ground network for NR into RAN5 test specifications. The work plan is updated after each RAN5 meeting to give the status of the work item. Section 2 gives an overview of the work item status. The work sheet 'WP' shows the status for each impacted/newly introduced test cases.
2. Work item status
Estimation of WI overall completion:
Area |  | Completion | Number of new completed test cases (Note 1) | Number of new test cases | Comments
Overall completion |  | 85% (+5%) | 38 (+21) | 107
Completion Compensation |  | -
| Note 1: | Only test cases completed for all applicable WP areas and sub-areas are counted. For completed test cases per WP areas and WP sub-areas see below.
Estimation WI completion per area and sub-area:
|  | Completion | Number of new completed test cases | Number of new test cases | Comments
SA Option 2 (SA NR) (FR1) |  | 85.2% (+5.3%) | 38 (+21) | 107
FR1 |  | 85.2% (+5.3%) | 57 (+21) | 107
Estimation of completion per TS (area):
|  | TS/TR overall completion |  |  | SA Option 2 (SA NR)
TS/TR Scope | TS/TR | Completion | Number of new completed test cases | Number of new test cases | FR1
[5 empty] | Completion | Number of new completed test cases | Number of new test cases
LTE
LTE Common
Common test environment | 36.508
UE specific test functions | 36.509
LTE RF/RRM
RF common parts | 36.521-1
RF Rx test cases | 36.521-1 Rx
RF Tx test cases | 36.521-1 Tx
RF Demod test cases | 36.521-1 Demod
Applicability RF. Demod/QSI and RRM test cases | 36.521-2
RRM test cases | 36.521-3
Test Tolerances analysis RRM test cases | 36.903
Test Tolerances analysis receiver test cases | 36.904
Test Point analysis receiver and transmitter test cases | 36.905
LTE RAN and CN protocols
Protocol test cases | 36.523-1
Applicability Protocol test cases | 36.523-2
Test suites (TTCN) | 36.523-3
5GS
5GS Common
Common test environment | 38.508-1 | 100% |  |  | 100%
Common ICS | 38.508-2 | 100% |  |  | 100%
UE specific test functions | 38.509
NR RF/RRM
FR1 RF common parts | 38.521-1 | 97.5% (+10.5%) | 31 (+21) | 34 | 97.5% (+10.5%) | 31 (+21) | 34
FR1 RF Tx test cases | 38.521-1 Tx
FR1 RF Rx test cases | 38.521-1 Rx
FR2 RF common parts | 38.521-2
FR2 RF Tx test cases | 38.521-2 Tx
FR2 RF Rx test cases | 38.521-2 Rx
FR1 and FR2 Interworking operation with other radios RF common parts | 38.521-3
FR1 and FR2 Interworking operation with other radios RF Tx test cases | 38.521-3 Tx
FR1 and FR2 Interworking operation with other radios RF Rx test cases | 38.521-3 Rx
RF Demod/QSI test cases | 38.521-4 | 29.4% (-0%) |  |  | 29.4% (-0%)
RRM test cases | 38.533 | 83.3% (+4.9%) | 2 | 68 | 83.3% (+4.9%) | 21 | 68
Applicability RF. Demod/QSI and RRM test cases | 38.522 | 70% (-0%) |  |  | 70% (-0%)
Test Tolerances analysis RRM and RF Rx test cases | 38.903 | 0% |  |  | 0%
Test Point analysis receiver and transmitter test cases | 38.905 | 70% |  |  | 70%
5GS RAN and CN protocols
Protocol test cases | 38.523-1 | 76.9% (+0%) | 5 | 5 | 76.9% (+0%) | 5 | 5
Applicability Protocol test cases | 38.523-2
Test suites (TTCN) | 38.523-3
UE Positioning
UE Positioning Min. Performance test cases | 37.571-1
UE Positioning Protocol test cases | 37.571-2
Applicability and ICS UE Positioning test cases | 37.571-3
UE Positioning Test sutes (TTCN) | 37.571-4
UE Positioning test scenarios and assistance data | 37.571-5
IMS
IMS over LTE protocol test cases | 34.229-1
IMS over 5GS protocol test cases | 34.229-5
Applicability and ICS IMS test cases | 34.229-2
IMS Test suite (TTCN) | 34.229-3
Mission Critical Services
MC Common test environment | 36.579-1
MCPTT UE test cases | 36.579-2
MC Server Application test cases | 36.579-3
Applicability and ICS MC test cases | 36.579-4
MC Test suite (TTCN) | 36.579-5
MC Video UE test cases | 36.579-6
MC Data UE test cases | 36.579-7
5 References
[1] RP-233412 | New WID on UE Conformance - Air-to-ground network for NR
Note on B21: Overall completion of the work item reported at an earlier meeting will not be decreased if additional tasks are added or if corrections are made to the work plan. Instead the earlier reported completion status will be kept until necessary progress have been achieved such that completion exceeds the earlier reported completion level. The value of the Completion Compensation value represents the difference in the decrease caused by late additions or corrections to the work plan and the current estimated overall completion. '-' indicates that no compensation is applied.

## WP
WP Title: |  | WP UE Conformance - Air-to-ground network for NR | [10 empty] | Start of workplan status columns. Note! Do not remove this column. | WP item status | End of workplan columns. Note! Do not remove this column.
WI code |  | NR_ATG-UEConTest
WP Scope: |  | The purpose of this present document is to provide a work plan for the RAN5 work item UE Conformance Test Aspects for Air-to-ground network for NR comprising the necessary updates to existing clauses/test cases and new clauses/test cases as appropriate, with the aim of provision of conformance testing to reflect the relevant core and performance requirement (relevant core spec WIs indicated in the WID).
WP Resp: |  | Dan Song, CMCC |  |  | songdan@chinamobile.com | [5 empty] | WP item completion |  |  | SA Option 2 (SA NR)
TS Resp: |  | n/a |  |  | n/a
WP Item ID | Is new test case? | TS/area | Clause | Title | Test purpose / Task | Company | Target | TDOC(s) | Comments | Weight | Overall | SA Option 2 (SA NR) |  | FR1
85.2% (+5.3%)
186 (+1)
168.7 (+1)
5%
Start of work plan items. Note! Do not remove this row. Introduce new work plan rows/items below this row.
5GS
5GS Common
TS 38.508-1: Common test environment
|  | 38.508-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
170 |  | 38.508-1 | 3.1 | Definitions | Update of Definitions for "ATG" | CMCC | RAN5#107 (May-25) | R5-252077 | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
1 |  | 38.508-1 | 3.3 | Abbreviations | Introduction of Abbreviations for "ATG" into cl 3.3 | CMCC | RAN5#107 (May-25) | R5-241926 | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
2 |  | 38.508-1 | 4 | Common test environments | Introduction of General Test Environment for Rel-18 NR ATG UE | CMCC | RAN5#107 (May-25) | R5-244488,R5-253134 | CMCC Dan Song <songdan@chinamobile.com> Common test environment for ATG is pending since R18 ASN.1 has not been frozen until Jun 2024. Thus, this part will be updated in RAN5#104 meeting in Aug 2024 | 1 | 100% | 100% |  | 100%
3 |  | 38.508-1 | 5 | Test environments for RF test | Introduction of RF Test Environment for Rel-18 NR ATG UE | CMCC | RAN5#107 (May-25) | R5-241919,R5-244485,R5-256053 | CMCC Dan Song <songdan@chinamobile.com> IE name in SIB22 for ATG has been added with bracket since R18 ASN.1 has not been frozen until Jun 2024. Thus, this part will be updated in RAN5#104 meeting in Aug 2024 | 1 | 100% | 100% |  | 100%
4 |  | 38.508-1 | 7 | Test environments for RRM tests | Introduction of RRM Test Environment for Rel-18 NR ATG UE | CMCC | RAN5#107 (May-25) | R5-241920,R5-244486,R5-256053 | CMCC Dan Song <songdan@chinamobile.com> IE name in SIB22 for ATG has been added with bracket since R18 ASN.1 has not been frozen until Jun 2024. Thus, this part will be updated in RAN5#104 meeting in Aug 2024 | 1 | 100% | 100% |  | 100%
TS 38.508-2: Common ICS
|  | 38.508-2 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
5 |  | 38.508-2 | A.4.1 | UE Implementation Types | Introduction of common Implementation Conformance Statements for ATG UE into Table A.4.1-1 | CMCC | RAN5#107 (May-25) | R5-241715 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% | 100% |  | 100%
171 |  | 38.508-2 | A.4.3.2 | Physical Layer Baseline Implementation Capabilities | Update Physical Layer Baseline Implementation Capabilities for ATG UE | ZTE | RAN5#107 (May-25) | R5-252200 | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> | 1 | 100% | 100% |  | 100%
172 |  | 38.508-2 | A.4.3.6 | UE Implementation Types | Update UE Measurement Capabilities for ATG UE | Huawei, HiSilicon | RAN5#107 (May-25) | R5-252688 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
173 |  | 38.508-2 | A.4.3.8 | Mobility Capabilities | Update Mobility Capabilities for ATG UE | ZTE | RAN5#107 (May-25) | R5-252201 | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> | 1 | 100% | 100% |  | 100%
174 |  | 38.508-2 | A.4.3.9 | Additional capabilities for UE declared capability | Add Table for ATG Antenna Vendor Declaration | Keysight | RAN5#108 (Aug-25) | R5-254068 | Keysight Adan<adan_toril@keysight.com> | 1 | 100% | 100% |  | 100%
NR RF/RRM
TS 38.521-1: FR1 RF test cases - Common parts (general clauses, Annexes)
|  | 38.521-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
6 |  | 38.521-1 | 2 | References | Add "TS 38.104" into the "Reference" Section as per R4-2321919. | CMCC | RAN5#107 (May-25) | R5-240049 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
|  | 38.521-1 | 3 | Definitions, symbols and abbreviations | [5 empty] | 0
7 |  | 38.521-1 | 3.1 | Definitions | Add "ATG UE" into "Definitions" as per R4-2321919 | CMCC | RAN5#107 (May-25) | R5-240049 R5-243906 R5-244477 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
8 |  | 38.521-1 | 3.2 | Symbols | Add "PMaxOutputPower" into "Definitions" as per R4-2321919 | CMCC | RAN5#107 (May-25) | R5-240049 R5-243906 R5-244477 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
9 |  | 38.521-1 | 3.3 | Abbreviations | Add "ATG" and "TAB" into "Abbreviations" as per R4-2321919 | CMCC | RAN5#107 (May-25) | R5-240049 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
10 |  | 38.521-1 | 4.3 | Specification suffix information | Update cl."Specification suffix information" for ATG as per R4-2321919 | CMCC | RAN5#107 (May-25) | R5-240049 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
11 |  | 38.521-1 | 5.2J | Operating band for ATG | Introduce Operating band for ATG UE | CMCC | RAN5#107 (May-25) | R5-240049 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
TS 38.521-1: FR1 RF test cases - Tx
12 |  | 38.521-1 | 6.1J | General | Introduce general description for ATG UE Tx test cases | CMCC | RAN5#107 (May-25) | R5-242030 R5-244478 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
|  | 38.521-1 | 6.2J | Transmitter power for ATG | [5 empty] | 0
13 | Y | 38.521-1 | 6.2J.1 | UE maximum output power for ATG | Introduce UE maximum output power test case for ATG UE | CMCC | RAN5#109 (Nov-25) | R5-241751,R5-241764,R5-243037,R5-246055,R5-246061,R5-247941,R5-252078,R5-256122 | CMCC Dan Song <songdan@chinamobile.com> MU/TT are pending for antenna/TAB connectors more than 2. Applicability is incomplete | 1 | 100% (+10%) | 100% (+10%) |  | 100%
14 | Y | 38.521-1 | 6.2J.2 | Configured transmitted power for ATG | Introduce Configured transmitted power test case for ATG UE | CMCC | RAN5#109 (Nov-25) | R5-241752,R5-241764,R5-243037,R5-246056,R5-246061,R5-247941,R5-250113,R5-252078,R5-256122 | CMCC Dan Song <songdan@chinamobile.com> MU/TT are pending for antenna/TAB connectors more than 2. Applicability is incomplete | 1 | 100% (+10%) | 100% (+10%) |  | 100%
|  | 38.521-1 | 6.3J | Output power dynamics for ATG | [5 empty] | 0
15 | Y | 38.521-1 | 6.3J.1 | Minimum output power for ATG | Introduce Minimum output power test case for ATG UE | CAICT | RAN5#109 (Nov-25) | R5-241756,R5-246058,R5-246062,R5-247941,R5-250113,R5-252137,R5-256122 | CAICT Yufeng Zhang zhangyufeng@caict.ac.cn MU/TT are pending for antenna/TAB connectors more than 2. Applicability is incomplete | 1 | 100% (+10%) | 100% (+10%) |  | 100%
16 | Y | 38.521-1 | 6.3J.2 | Transmit OFF power for ATG | Introduce Transmit OFF power test case for ATG UE | CAICT | RAN5#109 (Nov-25) | R5-241755,R5-246058,R5-246062,R5-247939,R5-247941,R5-252078,R5-252137,R5-252139,R5-252136(disc) | CAICT Yufeng Zhang zhangyufeng@caict.ac.cn MU/TT are pending Applicability is incomplete | 1 | 90% | 90% |  | 90%
|  | 38.521-1 | 6.3J.3 | Transmit ON/OFF time mask for ATG | [5 empty] | 0
58 |  | 38.521-1 | 6.3J.3.0 | General | Introduce General description of Transmit ON/OFF time mask for ATG UE | CMCC | RAN5#105 (Nov-24) | R5-247735 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% | 100% |  | 100%
17 | Y | 38.521-1 | 6.3J.3.1 | General ON/OFF time mask for ATG | Introduce General ON/OFF time mask test case for ATG UE | CMCC | RAN5#109 (Nov-25) | R5-255240,R5-255254(MU),R5-255341(38.522),R5-253876(38.905),R5-256122 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> Editor’s Note: This test is incomplete. The following aspects are not yet determined: - MU/TT are FFS for ATG UEs with more than 2 transmit antenna connectors/ transceiver array boundary (TAB) connectors. - MU/TT already defined are based on preliminary analysis of single TE vendor. Values will be revisited once more detailed analysis, including analysis from other TE vendors, is available. | 1 | 100% (+15%) | 100% (+15%) |  | 100%
52 | Y | 38.521-1 | 6.3J.3.2 | Transmit power time mask for slot and short or subslot boundaries for ATG | Introduce Transmit power time mask for slot and short or subslot boundaries test case for ATG UE | CMCC | RAN5#105 (Nov-24) | R5-247736 | No test case details are specified. CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% | 100% |  | 100%
53 | Y | 38.521-1 | 6.3J.3.3 | PRACH time mask for ATG | Introduce PRACH time mask test case for ATG UE | Ericsson | RAN5#109 (Nov-25) | R5-247718,R5-247720,R5-247717,R5-247816,R5-256940,R5-256822(MU/TT) | Ericsson Håkan Grunditz <hakan.grunditz@ericsson.com> | 1 | 100% (+10%) | 100% (+10%) |  | 100%
54 | Y | 38.521-1 | 6.3J.3.4 | SRS time mask for ATG | Introduce SRS time mask test case for ATG UE | Ericsson | RAN5#109 (Nov-25) | R5-247719,R5-247720,R5-247717,R5-247816,R5-253876(38.905),R5-256940,R5-256822(MU/TT) | Ericsson Håkan Grunditz <hakan.grunditz@ericsson.com> | 1 | 100% (+5%) | 100% (+5%) |  | 100%
55 | Y | 38.521-1 | 6.3J.3.5 | PUSCH-PUCCH and PUSCH-SRS time masks for ATG | Introduce PUSCH-PUCCH and PUSCH-SRS time masks test case for ATG UE | CMCC | RAN5#109 (Nov-25) | R5-253880 | No test case details are specified. CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% | 100% |  | 100%
56 | Y | 38.521-1 | 6.3J.3.6 | Transmit power time mask for consecutive slot or long subslot transmission and short subslot transmission boundaries for ATG | Introduce Transmit power time mask for consecutive slot or long subslot transmission and short subslot transmission boundaries test case for ATG UE | CMCC | RAN5#105 (Nov-24) | R5-247736 | No test case details are specified. CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% | 100% |  | 100%
57 | Y | 38.521-1 | 6.3J.3.7 | Transmit power time mask for consecutive short subslot transmissions boundaries for ATG | Introduce Transmit power time mask for consecutive short subslot transmissions boundaries test case for ATG UE | CMCC | RAN5#105 (Nov-24) | R5-247736 | No test case details are specified. CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% | 100% |  | 100%
|  | 38.521-1 | 6.3J.4 | Power control for ATG | [5 empty] | 0
18 | Y | 38.521-1 | 6.3J.4.1 | Absolute power tolerance for ATG | Introduce Absolute power tolerance test case for ATG UE | CMCC | RAN5#109 (Nov-25) | R5-247737,R5-247740,R5-247838, R5-251703,R5-256122 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> -MU is FFS | 1 | 100% (+10%) | 100% (+10%) |  | 100%
50 | Y | 38.521-1 | 6.3J.4.2 | Relative power tolerance for ATG | Introduce Relative power tolerance test case for ATG UE | CMCC | RAN5#109 (Nov-25) | R5-247738,R5-247740,R5-247838, R5-251703,R5-256122 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> -MU is FFS | 1 | 100% (+10%) | 100% (+10%) |  | 100%
51 | Y | 38.521-1 | 6.3J.4.3 | Aggregate power tolerance for ATG | Introduce Aggregate power tolerance test case for ATG UE | CMCC | RAN5#109 (Nov-25) | R5-247739,R5-247740,R5-247838, R5-251703,R5-256122 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> -MU is FFS | 1 | 100% (+10%) | 100% (+10%) |  | 100%
|  | 38.521-1 | 6.4J | Transmit signal quality for ATG | [5 empty] | 0
19 | Y | 38.521-1 | 6.4J.1 | Frequency error for ATG | Introduce Frequency error test case for ATG UE | Ericsson | RAN5#109 (Nov-25) | R5-251514,R5-252078,R5-252576,R5-253425,R5-255243,R5-254070(MU/TT),R5-254067(disc),R5-255341(38.522) | Ericsson Hakan Grunditz <hakan.grunditz@ericsson.com> MU and TT are FFS Test procedure and Test requirements are FFS | 1 | 100% | 100% |  | 100%
|  | 38.521-1 | 6.4J.2 | Transmit modulation quality for ATG | [5 empty] | 0
20 |  | 38.521-1 | 6.4J.2.0 | General | Introduce General description of Transmit modulation quality for ATG UE | CMCC | RAN5#109 (Nov-25) | R5-253877 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% | 100% |  | 100%
21 | Y | 38.521-1 | 6.4J.2.1 | Error Vector Magnitude for ATG | Introduce Error Vector Magnitude test case for ATG UE | Ericsson | RAN5#109 (Nov-25) | R5-251681,R5-252137,R5-252139,R5-252136(disc),R5-255243,R5-255341(38.522) | Ericsson Håkan Grunditz<hakan.grunditz@ericsson.com> - MU/TT are FFS for ATG UEs with more than 2 transmit antenna connectors/ transceiver array boundary (TAB) connectors. - Test procedure and even minimum requirements are FFS in case of devices with more than one antenna/TAB connector. | 1 | 100% | 100% |  | 100%
22 | Y | 38.521-1 | 6.4J.2.1a | Error Vector Magnitude including symbols with transient period for ATG | Introduce Error Vector Magnitude including symbols with transient period test case for ATG UE | Ericsson | RAN5#109 (Nov-25) | R5-252167,R5-252316,R5-255243,R5-254070(MU/TT),R5-254067(disc),R5-255341(38.522) | Ericsson Håkan Grunditz <hakan.grunditz@ericsson.com> | 1 | 100% | 100% |  | 100%
23 | Y | 38.521-1 | 6.4J.2.2 | Carrier leakage for ATG | Introduce Carrier leakage test case for ATG UE | CMCC | RAN5#109 (Nov-25) | R5-254070(MU/TT),R5-254067(disc),R5-256049 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% (+70%) | 100% (+70%) |  | 100%
24 | Y | 38.521-1 | 6.4J.2.3 | In-band emissions for ATG | Introduce In-band emissions test case for ATG UE | CMCC | RAN5#109 (Nov-25) | R5-254070(MU/TT),R5-254067(disc),R5-256050 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% (+70%) | 100% (+70%) |  | 100%
25 | Y | 38.521-1 | 6.4J.2.4 | EVM equalizer spectrum flatness for ATG | Introduce EVM equalizer spectrum flatness test case for ATG UE | Ericsson | RAN5#109 (Nov-25) | R5-252170,R5-252316,R5-255243,R5-254070(MU/TT),R5-254067(disc),R5-255341(38.522) | Ericsson Håkan Grunditz <hakan.grunditz@ericsson.com> | 1 | 100% | 100% |  | 100%
26 | Y | 38.521-1 | 6.4J.2.5 | EVM equalizer spectrum flatness for Pi/2 BPSK for ATG | Introduce EVM equalizer spectrum flatness for Pi/2 BPSK test case for ATG UE | Ericsson | RAN5#109 (Nov-25) | R5-252241,R5-252316,R5-255243,R5-254070(MU/TT),R5-254067(disc),R5-255341(38.522) | Ericsson Håkan Grunditz <hakan.grunditz@ericsson.com> | 1 | 100% | 100% |  | 100%
|  | 38.521-1 | 6.5J | Output RF spectrum emissions for ATG | [5 empty] | 0
27 |  | 38.521-1 | 6.5J.0 | General | Introduce general description of Occupied bandwidth for ATG UE | CMCC | RAN5#103 (May-24) | R5-240053 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% | 100% |  | 100%
28 | Y | 38.521-1 | 6.5J.1 | Occupied bandwidth for ATG | Introduce Occupied bandwidth test case for ATG UE | CMCC | RAN5#109 (Nov-25) | R5-241753 R5-241764 R5-246057 R5-246061 R5-247939 R5-247941, R5-250113 | CMCC Dan Song <songdan@chinamobile.com> MU/TT are pending for antenna/TAB connectors more than 2 or MOP over than 31dBm. Applicability is incomplete | 1 | 90% | 90% |  | 90%
|  | 38.521-1 | 6.5J.2 | Out of band emission for ATG | [5 empty] | 0
29 |  | 38.521-1 | 6.5J.2.1 | General | Introduce General description of Out of band emission for ATG UE | CMCC | RAN5#105 (Nov-24) | R5-240055 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
30 | Y | 38.521-1 | 6.5J.2.2 | Spectrum emission mask for ATG | Introduce Spectrum emission mask test case for ATG UE | Ericsson | RAN5#109 (Nov-25) | R5-250189,R5-252078,R5-252562,R5-253426,R5-255748,R5-255749(MU/TT) | Ericsson Håkan Grunditz <hakan.grunditz@ericsson.com> - Test Requirements and Test procedure are FFS - MU and TT are FFS | 1 | 100% (+50%) | 100% (+50%) |  | 100%
31 | Y | 38.521-1 | 6.5J.2.3 | Adjacent channel leakage ratio for ATG | Introduce Adjacent channel leakage ratio test case for ATG UE | CMCC | RAN5#109 (Nov-25) | R5-256809,R5-256821(MU/TT) | CMCC Dan Song <songdan@chinamobile.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
|  | 38.521-1 | 6.5J.3 | Spurious emissions for ATG | [5 empty] | 0
32 |  | 38.521-1 | 6.5J.3.0 | General | Introduce General description of Spurious emissions for ATG UE | CMCC | RAN5#103 (May-24) | R5-240056 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
33 | Y | 38.521-1 | 6.5J.3.1 | General spurious emissions for ATG | Introduce General Spurious emissions test case for ATG UE | CMCC | RAN5#109 (Nov-25) | R5-241754, R5-241764, R5-246057,R5-246061, R5-250113,R5-252139,R5-252136(disc),R5-256122 | CMCC Dan Song <songdan@chinamobile.com> MU/TT are pending. - MU/TT are FFS for ATG UEs with more than 2 transmit antenna connectors/ transceiver array boundary (TAB) connectors. Applicability is incomplete | 1 | 100% (+10%) | 100% (+10%) |  | 100%
TS 38.521-1: FR1 RF test cases - Rx
34 |  | 38.521-1 | 7.1J | General | Introduce general description for ATG UE Rx test cases | CMCC | RAN5#103 (May-24) | R5-240058 R5-243038 R5-244482 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
35 |  | 38.521-1 | 7.2J | Diversity characteristics for ATG | Introduce Diversity characteristics description for ATG UE | CMCC | RAN5#103 (May-24) | R5-240059 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
|  | 38.521-1 | 7.3J | Reference sensitivity for ATG | [5 empty] | 0
36 |  | 38.521-1 | 7.3J.1 | General | Introduce General description of Reference sensitivity test case for ATG UE | CMCC | RAN5#103 (May-24) | R5-240060,R5-252079 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
37 | Y | 38.521-1 | 7.3J.2 | Reference sensitivity power level for ATG | Introduce Reference sensitivity power level test case for ATG UE | Ericsson | RAN5#109 (Nov-25) | R5-246618,R5-252079,R5-256820 | Ericsson Håkan Grunditz<hakan.grunditz@ericsson.com> | 1 | 100% (+10%) | 100% (+10%) |  | 100%
38 | Y | 38.521-1 | 7.4J | Maximum input level for ATG | Introduce Maximum input level test case for ATG UE | CAICT | RAN5#109 (Nov-25) | R5-241760,R5-246060,R5-246062,R5-247941,R5-256820 | CAICT Yufeng Zhang zhangyufeng@caict.ac.cn MU/TT are pending for antenna/TAB connectors more than 2. Applicability is incomplete | 1 | 100% (+10%) | 100% (+10%) |  | 100%
39 | Y | 38.521-1 | 7.5J | Adjacent channel selectivity for ATG | Introduce Adjacent channel selectivity test case for ATG UE | CAICT | RAN5#109 (Nov-25) | R5-241761,R5-243038,R5-246060,R5-246062,R5-247941,R5-256820 | CAICT Yufeng Zhang zhangyufeng@caict.ac.cn MU/TT are pending for antenna/TAB connectors more than 2. Applicability is incomplete | 1 | 100% (+10%) | 100% (+10%) |  | 100%
|  | 38.521-1 | 7.6J | Blocking characteristics for ATG | [5 empty] | 0
40 |  | 38.521-1 | 7.6J.1 | General | Introduce Blocking characteristics for ATG UE | CMCC | RAN5#103 (May-24) | R5-240061 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com | 0.5 | 100% | 100% |  | 100%
41 | Y | 38.521-1 | 7.6J.2 | In-band blocking for ATG | Introduce In-band blocking test case for ATG UE | CAICT | RAN5#109 (Nov-25) | R5-241762,R5-246060,R5-246062,R5-247940,R5-247941,R5-256820 | CAICT Yufeng Zhang zhangyufeng@caict.ac.cn MU/TT are pending for antenna/TAB connectors more than 2. Applicability is incomplete | 1 | 100% (+10%) | 100% (+10%) |  | 100%
42 | Y | 38.521-1 | 7.6J.3 | Out-of-band blocking for ATG | Introduce Out-of-band blocking test case for ATG UE | CAICT | RAN5#109 (Nov-25) | R5-241763,R5-246060,R5-246062,R5-247940,R5-247941, R5-251704,R5-252138,R5-252139,R5-252136(disc),R5-256820 | CAICT Yufeng Zhang zhangyufeng@caict.ac.cn MU/TT are pending - MU are FFS for ATG UEs with more than 2 transmit antenna connectors/ transceiver array boundary (TAB) connectors. Applicability is incomplete | 1 | 100% (+10%) | 100% (+10%) |  | 100%
43 | Y | 38.521-1 | 7.7J | Spurious response for ATG | Introduce Spurious response test case for ATG UE | CMCC | RAN5#109 (Nov-25) | R5-241757,R5-241764,R5-246059,R5-246061,R5-247940,R5-247941,R5-256820 | CMCC Dan Song <songdan@chinamobile.com> MU/TT are pending. Applicability is incomplete | 1 | 100% (+10%) | 100% (+10%) |  | 100%
|  | 38.521-1 | 7.8J | Intermodulation characteristics for ATG | [5 empty] | 0
44 |  | 38.521-1 | 7.8J.1 | General | Introduce Intermodulation characteristics for ATG UE | CMCC | RAN5#103 (May-24) | R5-240063 | CMCC Dan Song <songdan@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
45 | Y | 38.521-1 | 7.8J.2 | Wide band intermodulation for ATG | Introduce Wide band intermodulation test case for ATG UE | CMCC | RAN5#109 (Nov-25) | R5-241758,R5-241764,R5-246059,R5-246061,R5-247941,R5-256820 | CMCC Dan Song <songdan@chinamobile.com> MU is pending for antenna/TAB connectors more than 2. Applicability is incomplete | 1 | 100% (+10%) | 100% (+10%) |  | 100%
46 | Y | 38.521-1 | 7.9J | Spurious emissions for ATG | Introduce Spurious emissions test case for ATG UE | CMCC | RAN5#109 (Nov-25) | R5-241759, R5-241764,R5-246059,R5-246061,R5-252138,R5-252139,R5-252136(disc) | CMCC Dan Song <songdan@chinamobile.com> MU is are pending for MOP over than 31dBm. Applicability is incomplete | 1 | 100% | 100% |  | 100%
169 | Y | 38.521-1 | Annex F | Measurement uncertainties and Test Tolerances | Introduce MU/TT for ATG UE | CMCC | RAN5#109 (Nov-25) | R5-251536, R5-251537, R5-251705 | CMCC Dan Song <songdan@chinamobile.com> | 1 | 10% | 10% |  | 10%
TS 38.521-4: Demod/CSI reporting test cases
|  | 38.521-4 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
59 |  | 38.521-4 | 3.3 | Abbreviations | Add "ATG" into "Abbreviations" | CMCC | RAN5#109 (Nov-25) | R5-253884 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
|  | 38.521-4 | 5 | Demodulation performance requirements (Conducted requirements) | [5 empty] | 0
|  | 38.521-4 | 5.1 | General | [5 empty] | 0
|  | 38.521-4 | 5.1.1 | Applicability of requirements | [5 empty] | 0
60 |  | 38.521-4 | 5.1.1.1 | General | To update "5.1.1.1 General" for ATG | CMCC | RAN5#109 (Nov-25) | R5-253885 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com | 1 | 100% | 100% |  | 100%
61 |  | 38.521-4 | 5.1.1.12 | Applicability of requirements for ATG | To add applicability of requirements for ATG | CMCC | RAN5#109 (Nov-25) | R5-253885 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com | 1 | 100% | 100% |  | 100%
|  | 38.521-4 | 5.2 | PDSCH demodulation requirements | [5 empty] | 0
|  | 38.521-4 | 5.2.1 | 1RX requirements | [5 empty] | 0
|  | 38.521-4 | 5.2.2 | 2RX requirements | [5 empty] | 0
|  | 38.521-4 | 5.2.2.1 | FDD | [5 empty] | 0
62 |  | 38.521-4 | 5.2.2.1.22 | Minimum requirements for ATG | To add minimum requirements for 2RX FDD ATG UE PDSCH performance basing on Clause 5.2.2.1.22 of TS 38.101-4 | CMCC | RAN5#109 (Nov-25) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com | 1 | 0% | 0% |  | 0%
|  | 38.521-4 | 5.2.2.2 | TDD | [5 empty] | 0
63 |  | 38.521-4 | 5.2.2.2.23 | Minimum requirements for ATG | To add minimum requirements for 2RX TDD ATG UE PDSCH performance basing on Clause 5.2.2.2.23 of TS 38.101-4 | CMCC | RAN5#109 (Nov-25) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com | 1 | 0% | 0% |  | 0%
|  | 38.521-4 | 5.2.3 | 4RX requirements | [5 empty] | 0
|  | 38.521-4 | 5.2.3.1 | FDD | [5 empty] | 0
64 |  | 38.521-4 | 5.2.3.1.21 | Minimum requirements for ATG | To add minimum requirements for 4RX FDD ATG UE PDSCH performance basing on Clause 5.2.3.1.21 of TS 38.101-4 | CMCC | RAN5#109 (Nov-25) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com | 1 | 0% | 0% |  | 0%
|  | 38.521-4 | 5.2.3.2 | TDD | [5 empty] | 0
65 |  | 38.521-4 | 5.2.3.2.22 | Minimum requirements for ATG | To add minimum requirements for 4RX TDD ATG UE PDSCH performance basing on Clause 5.2.3.2.22 of TS 38.101-4 | CMCC | RAN5#109 (Nov-25) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com | 1 | 0% | 0% |  | 0%
|  | 38.521-4 | A.1 | General | [5 empty] | 0
|  | 38.521-4 | A.1.1 | Throughput definition | [5 empty] | 0
66 |  | 38.521-4 | A.1.2 | TDD UL-DL configurations for FR1 | To add new Table A.1.2-2c, Table A.3.2.2.2-31, Table A.3.2.2.2-32 and Table A.3.2.2.2-33 as per A.1.2 of TS 38.101-4; To update Table A.3.2.1.1-3 amd Table A.3.2.2.2-3 as per A.1.2 of TS 38.101-4 | CMCC | RAN5#109 (Nov-25) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com | 1 | 0% | 0% |  | 0%
|  | 38.521-4 | A.3 | DL reference measurement channels | [5 empty] | 0
|  | 38.521-4 | A.3.1 | General | [5 empty] | 0
|  | 38.521-4 | A.3.2 | Reference measurement channels for PDSCH performance requirements | [5 empty] | 0
|  | 38.521-4 | A.3.2.1 | FDD | [5 empty] | 0
|  | 38.521-4 | A.3.2.2 | TDD | [5 empty] | 0
67 |  | 38.521-4 | A.3.2.2.2 | Reference measurement channels for SCS 30 kHz FR1 | To add new Table A.3.2.2.2-40, Table A.3.2.2.2-41 and Table A.3.2.2.2-42 as per A.3.2.2.2 of TS 38.101-4; | CMCC | RAN5#109 (Nov-25) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com | 1 | 0% | 0% |  | 0%
TBD |  | 38.521-4 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | 0 | 0% | 0% |  | 0%
TBD | Y | 38.521-4 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 0 | 0% | 0% |  | 0%
TBD |  | 38.521-4 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.521-4 | <Clause> | <Title of modified existing test case> | <Describe required change of the existing test case> |  | TBD |  |  | 0 | 0% | 0% |  | 0%
TBD | Y | 38.521-4 | <Clause> | <Title of new test case> | Test Purpose(s): <Describe test purpose(s)> |  | TBD |  |  | 0 | 0% | 0% |  | 0%
TS 38.522: Applicability for RF, Demod/CSI reporting and RRM test cases
47 |  | 38.522 | 4 | Test case conditions and selection criteria | Add new ICS statements. | CMCC | RAN5#109 (Nov-25) | R5-241842,R5-253584 | CMCC Dan Song <songdan@chinamobile.com> | 0.1 | 70% | 70% |  | 70%
48 |  | 38.522 | 4.1.1 | FR1 standalone conformance test cases | Add test case applicability statements for the new test cases introduced for 38.521-x and 38.533. | CMCC | RAN5#109 (Nov-25) | R5-241842, R5-251666,R5-253584 | CMCC Dan Song <songdan@chinamobile.com> | 0.1 | 70% | 70% |  | 70%
TS 38.533: RRM test cases
|  | 38.533 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
68 |  | 38.533 | 3.3 | Abbreviations | Add "ATG" into "Abbreviations" | CMCC | RAN5#109 (Nov-25) | R5-253886 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
|  | 38.533 | 19 | NR standalone tests for ATG | [5 empty] | 0
|  | 38.533 | 19.0 | General | [5 empty] | 0
179 |  | 38.533 | 19.0.1 | Initial test environment conditions for ATG RRM tests | To add Initial test environment conditions for ATG RRM tests | CMCC | RAN5#109 (Nov-25) | R5-256956 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% | 100% |  | 100%
|  | 38.533 | 19.1 | RRC_IDLE state mobility for ATG | [5 empty] | 0
69 |  | 38.533 | 19.1.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 4.2D.2.3 and Clause 4.2D.2.4 of TS 38.133 | CMCC | RAN5#109 (Nov-25) | R5-253888 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 100% | 100% |  | 100%
70 | Y | 38.533 | 19.1.1 | NR SA FR1 Cell reselection for ATG | This test is to verify the requirement for the intra frequency NR cell reselection requirements for ATG specified in clause 4.2D.2.3 of TS 38.133. | CMCC | RAN5#109 (Nov-25) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 0% | 0% |  | 0%
71 | Y | 38.533 | 19.1.2 | NR SA FR1-FR1 Cell reselection for ATG | This test is to verify the requirement for the inter frequency NR cell reselection requirements for ATG specified in clause 4.2D.2.4 of TS 38.133. | CMCC | RAN5#109 (Nov-25) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 0% | 0% |  | 0%
72 | Y | 38.533 | 19.1.3 | NR SA FR1-FR1 Cell reselection for UE configured with hs-ATG-cellReselectionSet-r18 | This test is to verify the requirement for the inter frequency NR cell reselection requirements for ATG UE configured with hs-ATG-cellReselectionSet-r18 and for ATG UE supporting the feature for enhanced RRM requirements (Enhanced RRM requirements for measurements in IDLE and INACTIVE modes for ATG) specified in clause 4.2D.2.4 of TS 38.133. | CMCC | RAN5#109 (Nov-25) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 1 | 0% | 0% |  | 0%
|  | 38.533 | 19.2 | RRC_CONNECTED state mobility for ATG | [5 empty] | 0
|  | 38.533 | 19.2.1 | Handover for ATG | [5 empty] | 0
73 |  | 38.533 | 19.2.1.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 6.1E.1.2 of TS 38.133 | Sporton | RAN5#107 (May-25) | R5-251587 | Sporton Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> | 1 | 100% | 100% |  | 100%
74 | Y | 38.533 | 19.2.1.1 | NR SA FR1 handover with known target cell for ATG | This test is to verify the requirement for the NR FR1-NR FR1 intra frequency handover requirements for ATG specified in clause 6.1E.1.2 of TS 38.133 | Sporton | RAN5#109 (Nov-25) | R5-251587,R5-253554(MU/TT),R5-253537，R5-251870(38.903) | Sporton Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procedures for providing network assistance on ATG cells reference locations are FFS. | 1 | 70% | 70% |  | 70%
75 | Y | 38.533 | 19.2.1.2 | NR SA FR1-FR1 handover with unknown target cell for ATG | This test is to verify the requirement for the NR FR1-NR FR1 inter frequency handover requirements for ATG specified in clause 6.1E.1.2 of TS 38.133 | Sporton | RAN5#109 (Nov-25) | R5-251588,R5-253554(MU/TT)，R5-253538,R5-251872(38.903) | Sporton Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procedures for providing network assistance on ATG cells reference locations are FFS. | 1 | 70% | 70% |  | 70%
|  | 38.533 | 19.2.2 | Conditional Handover for ATG | [5 empty] | 0
76 |  | 38.533 | 19.2.2.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 6.1E.2 of TS 38.133 | Sporton | RAN5#109 (Nov-25) | R5-251589 | Sporton Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> | 1 | 100% | 100% |  | 100%
77 | Y | 38.533 | 19.2.2.1 | NR SA FR1 distance-based conditional Handover for ATG | This test is to verify the requirement for intra-frequency distance-based conditional handover from FR1 to FR1 for ATG specified in clause 6.1E.2 of TS 38.133. | Sporton | RAN5#109 (Nov-25) | R5-251589,R5-253492,R5-253825,R5-253833,R5-253826(38.903),R5-256879 | Sporton Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> | 1 | 100% | 100% |  | 100%
78 | Y | 38.533 | 19.2.2.2 | NR SA FR1-FR1 distance-based conditional Handover for ATG | This test is to verify the requirement for inter-frequency distance-based conditional handover from FR1 to FR1 for ATG specified in clause 6.1E.2 of TS 38.133. | Sporton | RAN5#109 (Nov-25) | R5-251590,R5-253492,R5-253827,R5-253833,R5-253828(38.903) | Sporton Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> | 1 | 100% | 100% |  | 100%
|  | 38.533 | 19.2.3 | RRC Connection Mobility Control for ATG | [5 empty] | 0
|  | 38.533 | 19.2.3.1 | SA: RRC Re-establishment for ATG | [5 empty] | 0
79 |  | 38.533 | 19.2.3.1.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 6.2D.1 of TS 38.133 | Sporton | RAN5#109 (Nov-25) | R5-253598 | Sporton Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> | 1 | 100% | 100% |  | 100%
80 | Y | 38.533 | 19.2.3.1.1 | NR SA FR1 RRC Re-establishment for ATG | The purpose is to verify that the NR intra-frequency RRC re-establishment delay in FR1 with known target cell is within the specified limits for ATG. These tests will verify the requirements in clause 6.2D.1 of TS 38.133. | Sporton | RAN5#109 (Nov-25) | R5-253598,R5-253829,R5-253833,R5-253830(38.903) | Sporton Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> - TT analysis is missing. - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procedures for providing network assistance on ATG cells reference locations are FFS. | 1 | 80% | 80% |  | 80%
81 | Y | 38.533 | 19.2.3.1.2 | NR SA FR1-FR1 RRC Re-establishment with unknown target cell without serving cell timing for ATG | The purpose is to verify that the NR inter-frequency RRC re-establishment delay in FR1 with unknown target cell and without serving cell timing are within the specified limits. These tests will verify the requirements in clause 6.2D.1 of TS 38.133. | Sporton | RAN5#109 (Nov-25) | R5-253599,R5-253831,R5-253833,R5-255325(38.903) | Sporton Ivan Cheng (鄭宜樺)<IvanCheng@sporton.com.tw> - TT analysis is missing. - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procedures for providing network assistance on ATG cells reference locations are FFS. | 1 | 80% | 80% |  | 80%
|  | 38.533 | 19.2.3.2 | Random Access for ATG | [5 empty] | 0
82 |  | 38.533 | 19.2.3.2.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 6.2D.2.2, Clause 6.2D.2.3 and Clause 7.1D.2 of TS 38.133 | ZTE | RAN5#109 (Nov-25) | R5-254053 | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> | 1 | 100% | 100% |  | 100%
83 | Y | 38.533 | 19.2.3.2.1 | NR SA FR1 4-step RA type contention based random access test for ATG | The purpose of this test is to verify that the behavior of the random access procedure is according to the requirements and that the PRACH power settings and timing are within specified limits. This test will verify the requirements in Clause 6.2D.2.2 and Clause 7.1D.2 of TS 38.133 in an AWGN with constant residual doppler model. | ZTE | RAN5#109 (Nov-25) | R5-255341(38.522),R5-254053,R5-254059,R5-255644,R5-256901(38.903) | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> Editor's Note: This test case is incomplete in following aspects: - TT analysis is missing. - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procedures for providing network assistance on ATG cells reference locations are FFS. | 1 | 85% (+5%) | 85% (+5%) |  | 85%
84 | Y | 38.533 | 19.2.3.2.2 | NR SA FR1 4-step RA type non-contention based random access test for ATG | The purpose of this test is to verify that the behavior of the random access procedure is according to the requirements and that the PRACH power settings and timing are within specified limits. This test will verify the requirements in Clause 6.2D.2.2 and Clause 7.1D.2 of TS 38.133 in an AWGN with constant residual doppler model. | ZTE | RAN5#109 (Nov-25) | R5-255341(38.522),R5-254054,R5-254059,R5-255645,R5-256901(38.903) | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> Editor's Note: This test case is incomplete in following aspects: - TT analysis is missing. - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procedures for providing network assistance on ATG cells reference locations are FFS. | 1 | 85% (+5%) | 85% (+5%) |  | 85%
85 | Y | 38.533 | 19.2.3.2.3 | NR SA FR1 2-step RA type contention based random access test for ATG | The purpose of this test is to verify that the behavior of the 2-step RA type random access procedure is according to the requirements and that the MsgA PRACH, MsgA PUSCH power settings and timing are within specified limits. This test will verify the requirements in Clause 6.2D.2.3 and Clause 7.1D.2 of TS 38.133 in an AWGN with constant residual doppler model. | ZTE | RAN5#109 (Nov-25) | R5-255341(38.522),R5-254055,R5-254059 | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> Editor's Note: This test case is incomplete in following aspects: - TT analysis is missing. - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procedures for providing network assistance on ATG cells reference locations are FFS. | 1 | 80% | 80% |  | 80%
86 | Y | 38.533 | 19.2.3.2.4 | NR SA FR1 2-step RA type non-contention based random access test for ATG | The purpose of this test is to verify that the behavior of the random access procedure is according to the requirements and that the MsgA PRACH, MsgA PUSCH power settings and timing are within specified limits. This test will verify the requirements in Clause 6.2D.2.3 and Clause 7.1D.2 of TS 38.133 in an AWGN with constant residual doppler model. | ZTE | RAN5#109 (Nov-25) | R5-255341(38.522),R5-254056,R5-254059 | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> Editor's Note: This test case is incomplete in following aspects: - TT analysis is missing. - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procedures for providing network assistance on ATG cells reference locations are FFS. | 1 | 80% | 80% |  | 80%
|  | 38.533 | 19.2.3.3 | SA: RRC Connection Release with Redirection for ATG | [5 empty] | 0
87 |  | 38.533 | 19.2.3.3.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 6.2D.3.2.1 of TS 38.133 | CAICT | RAN5#109 (Nov-25) | R5-253597 | CAICT Yufeng Zhang zhangyufeng@caict.ac.cn | 1 | 100% | 100% |  | 100%
88 | Y | 38.533 | 19.2.3.3.1 | NR SA FR1-FR1 RRC connection release with Redirection for ATG | This test is to verify RRC connection release with redirection from NR to NR requirements specified in clause 6.2D.3.2.1 of TS 38.133. | CAICT | RAN5#109 (Nov-25) | R5-253597,R5-255326,R5-255324 | CAICT Yufeng Zhang zhangyufeng@caict.ac.cn | 1 | 80% | 80% |  | 80%
|  | 38.533 | 19.3 | Timing for ATG | [5 empty] | 0
|  | 38.533 | 19.3.1 | UE transmit timing | [5 empty] | 0
89 |  | 38.533 | 19.3.1.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 7.1D.2 of TS 38.133 | ZTE | RAN5#109 (Nov-25) | R5-255312 | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> | 1 | 100% | 100% |  | 100%
90 | Y | 38.533 | 19.3.1.1 | NR SA FR1 UE Transmit Timing Test for ATG | The purpose of this test is to verify that the UE can follow frame timing change of the connected gNodeb and that the UE initial transmit timing accuracy, maximum amount of timing change in one adjustment, minimum and maximum adjustment rate are within the specified limits. This test will verify the requirements in clause 7.1D.2 of TS 38.133. | ZTE | RAN5#109 (Nov-25) | R5-255341(38.522),R5-255312,R5-254059 | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> Editor's Note: This test case is incomplete in following aspects: - TT analysis is missing. - T_GNSS_margin need to be subtracted for the final test requirement. - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procedures for providing network assistance on ATG cells reference locations are FFS. | 1 | 80% (+80%) | 80% (+80%) |  | 80%
|  | 38.533 | 19.3.2 | UE timer accuracy for ATG | [5 empty] | 0
|  | 38.533 | 19.3.3 | Timing advance for ATG | [5 empty] | 0
91 |  | 38.533 | 19.3.3.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 7.3D of TS 38.133 | ZTE | RAN5#109 (Nov-25) | R5-255313 | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> | 1 | 100% | 100% |  | 100%
92 | Y | 38.533 | 19.3.3.1 | NR SA FR1 timing advance adjustment accuracy for ATG | The purpose of the test is to verify UE Timing Advance adjustment delay and accuracy requirement defined in clause 7.3D of TS 38.133. | ZTE | RAN5#109 (Nov-25) | R5-255341(38.522),R5-255313,R5-254059 | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> Editor's Note: This test case is incomplete in following aspects: - TT analysis is missing. - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procedures for providing network assistance on ATG cells reference locations are FFS. | 1 | 80% | 80% |  | 80%
|  | 38.533 | 19.4 | Signalling characteristics for ATG | [5 empty] | 0
93 |  | 38.533 | 19.4.1 | Radio link Monitoring for ATG | To capture the general description for "A.19.4.1 Radio link Monitoring" of TS 38.133 | CMCC | RAN5#107 (May-25) | R5-251591 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
94 |  | 38.533 | 19.4.1.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 8.1D of TS 38.133 | Ericsson | RAN5#107 (May-25) | R5-251591 | Ericsson Kuba Kolodziej<kuba.kolodziej@ericsson.com> | 1 | 100% | 100% |  | 100%
95 | Y | 38.533 | 19.4.1.1 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for PCell configured with SSB-based RLM RS in non-DRX mode for ATG | The purpose of this test is to verify that the UE properly detects the out of sync and in sync for the purpose of monitoring downlink radio link quality of the PCell. This test will partly verify the FR1 radio link monitoring requirements in clause 8.1D of TS 38.133. | Ericsson | RAN5#109 (Nov-25) | R5-251591,R5-253497,R5-256432,R5-256438(MU/TT),R5-256906(38.903) | Ericsson Kuba Kolodziej<kuba.kolodziej@ericsson.com> -TT analysis is missing. -Message contents are FFS -Test procedure is missing | 1 | 85% (+15%) | 85% (+15%) |  | 85%
96 | Y | 38.533 | 19.4.1.2 | NR SA FR1 Radio Link Monitoring In-sync Test for PCell configured with SSB-based RLM RS in non-DRX mode for ATG | The purpose of this test is to verify that the UE properly detects the out of sync and in sync for the purpose of monitoring downlink radio link quality of the PCell. This test will partly verify the FR1 radio link monitoring requirements in clause 8.1D of TS 38.133. | Ericsson | RAN5#109 (Nov-25) | R5-251592,R5-253497,R5-256433,R5-256438(MU/TT),R5-256907(38.903) | Ericsson Kuba Kolodziej<kuba.kolodziej@ericsson.com> -TT analysis is missing. -Message contents are FFS -Test procedure is missing | 1 | 85% (+15%) | 85% (+15%) |  | 85%
97 | Y | 38.533 | 19.4.1.3 | NR SA FR1 Radio Link Monitoring Out-of-sync Test for PCell configured with CSI-RS-based RLM in non-DRX mode for ATG | The purpose of this test is to verify that the UE properly detects the out of sync for the purpose of monitoring downlink CSI-RS based radio link quality of the PCell when no DRX is used. This test will partly verify the FR1 PCell CSI-RS Out-of-sync radio link monitoring requirements in clause 8.1D of TS 38.133. | Ericsson | RAN5#109 (Nov-25) | R5-251593,R5-253497,R5-256434,R5-256438(MU/TT),R5-256906(38.903) | Ericsson Kuba Kolodziej<kuba.kolodziej@ericsson.com> -TT analysis is missing. -Message contents are FFS -Test procedure is missing | 1 | 85% (+15%) | 85% (+15%) |  | 85%
98 | Y | 38.533 | 19.4.1.4 | NR SA FR1 Radio Link Monitoring In-sync Test for PCell configured with CSI-RS-based RLM in non-DRX mode for ATG | The purpose of this test is to verify that the UE properly detects the in sync for the purpose of monitoring downlink CSI-RS based radio link quality of the PCell when no DRX is used. This test will partly verify the FR1 PCell CSI-RS In-sync radio link monitoring requirements in clause 8.1D of TS 38.133. | Ericsson | RAN5#109 (Nov-25) | R5-251594,R5-253497,R5-256435,R5-256438(MU/TT),R5-256907(38.903) | Ericsson Kuba Kolodziej<kuba.kolodziej@ericsson.com> -TT analysis is missing. -Message contents are FFS -Test procedure is missing | 1 | 85% (+15%) | 85% (+15%) |  | 85%
|  | 38.533 | 19.4.2 | Beam Failure Detection and Link recovery procedures for ATG | [5 empty] | 0
99 |  | 38.533 | 19.4.2.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 8.5D of TS 38.133 | ZTE | RAN5#109 (Nov-25) |  | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> | 1 | 0% | 0% |  | 0%
100 | Y | 38.533 | 19.4.2.1 | NR SA FR1 Beam Failure Detection and Link Recovery Test for PCell configured with SSB-based BFD and LR in non-DRX mode for ATG | The purpose of this test is to verify that the UE properly detects SSB-based beam failure in the set q0 configured for a serving cell and that the UE performs correct SSB-based link recovery based on beam candidate set q1. The purpose is to test the downlink monitoring for beam failure detection within the UEs active DL BWP, during the evaluation period, and link recovery, when no DRX is used. This test will partly verify the SSB based beam failure detection and link recovery for an FR1 serving cell requirements in clause 8.5D of TS 38.133. | ZTE | RAN5#109 (Nov-25) | R5-255627 | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> | 1 | 70% | 70% |  | 70%
101 | Y | 38.533 | 19.4.2.2 | NR SA FR1 Beam Failure Detection and Link Recovery Test for PCell configured with CSI-RS-based BFD and LR in non-DRX mode for ATG | The purpose of this test is to verify that the UE properly detects CSI-RS-based beam failure in the set q0 configured for a serving cell and that the UE performs correct CSI-RS-based link recovery based on beam candicate set q1. The purpose is to test the downlink monitoring for beam failure detection within the UEs active DL BWP, during the evaluation period, and link recovery, when no DRX is used. This test will partly verify the CSI-RS based beam failure detection and link recovery for an FR1 serving cell requirements in clause 8.5D of TS 38.133. | ZTE | RAN5#109 (Nov-25) | R5-255629 | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> | 1 | 70% | 70% |  | 70%
|  | 38.533 | 19.4.3 | Active BWP switch for ATG | [5 empty] | 0
|  | 38.533 | 19.4.3.1 | DCI-based and Timer-based Active BWP Switch for ATG | [5 empty] | 0
102 |  | 38.533 | 19.4.3.1.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 8.6D of TS 38.133 | Qualcomm | RAN5#109 (Nov-25) | R5-254823 | Vijay Balasubramanian (QCT) <vijayb@qti.qualcomm.com> | 1 | 100% | 100% |  | 100%
103 | Y | 38.533 | 19.4.3.1.1 | NR SA FR1 DCI-based DL active BWP switch in non-DRX for ATG | The purpose of this test is to verify the DL BWP switch delay requirement defined in clause 8.6D of TS 38.133. | Qualcomm | RAN5#109 (Nov-25) | R5-255341(38.522),R5-254823,R5-254827,R5-256494,R5-256498(MU/TT),R5-256489(38.903) | Vijay Balasubramanian (QCT) <vijayb@qti.qualcomm.com> | 1 | 70% (+20%) | 70% (+20%) |  | 70%
|  | 38.533 | 19.4.3.2 | RRC-based Active BWP Switch for ATG | [5 empty] | 0
104 |  | 38.533 | 19.4.3.2.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 8.6D of TS 38.133 | Qualcomm | RAN5#109 (Nov-25) | R5-254824 | Vijay Balasubramanian (QCT) <vijayb@qti.qualcomm.com> | 1 | 100% | 100% |  | 100%
105 | Y | 38.533 | 19.4.3.2.1 | NR SA FR1 RRC-based DL active BWP switch in non-DRX for ATG | The purpose of this test is to verify the DL BWP switch delay requirement for RRC-based BWP switch defined in clause 8.6D of TS 38.133. | Qualcomm | RAN5#109 (Nov-25) | R5-255341(38.522),R5-254824,R5-254827,R5-256495,R5-256498(MU/TT),R5-256490(38.903) | Vijay Balasubramanian (QCT) <vijayb@qti.qualcomm.com> | 1 | 70% (+20%) | 70% (+20%) |  | 70%
|  | 38.533 | 19.4.4 | UE specific CBW change for ATG | [5 empty] | 0
106 |  | 38.533 | 19.4.4.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 8.13D of TS 38.133 | Qualcomm | RAN5#109 (Nov-25) | R5-254825 | Vijay Balasubramanian (QCT) <vijayb@qti.qualcomm.com> | 1 | 100% | 100% |  | 100%
107 | Y | 38.533 | 19.4.4.1 | NR SA FR1 UE specific CBW change on PCell in non-DRX for ATG | The purpose of this test is to verify the UE specific CBW change delay requirement defined in clause 8.13D of TS 38.133. | Qualcomm | RAN5#109 (Nov-25) | R5-255341(38.522),R5-254825,R5-254827,R5-256496,R5-256498(MU/TT),R5-256491(38.903) | Vijay Balasubramanian (QCT) <vijayb@qti.qualcomm.com> | 1 | 70% (+20%) | 70% (+20%) |  | 70%
|  | 38.533 | 19.4.5 | Pathloss reference signal switching delay for ATG | [5 empty] | 0
108 |  | 38.533 | 19.4.5.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 8.14D of TS 38.133 | Qualcomm | RAN5#109 (Nov-25) | R5-254826 | Vijay Balasubramanian (QCT) <vijayb@qti.qualcomm.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
109 | Y | 38.533 | 19.4.5.1 | NR SA FR1 MAC-CE based pathloss reference signal switch delay for ATG | The purpose of this test is to verify the MAC-CE based pathloss reference signal switch delay requirement defined in clause 8.14D of TS 38.133. | Qualcomm | RAN5#109 (Nov-25) | R5-255341(38.522),R5-254826,R5-254827,R5-256497,R5-256498(MU/TT),R5-256492(38.903) | Vijay Balasubramanian (QCT) <vijayb@qti.qualcomm.com> | 1 | 70% (+20%) | 70% (+20%) |  | 70%
|  | 38.533 | 19.5 | Measurement procedure for ATG | [5 empty] | 0
|  | 38.533 | 19.5.1 | Intra-frequency Measurements for ATG | [5 empty] | 0
110 |  | 38.533 | 19.5.1.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 9.2D.5.1, Clause 9.2D.5.2,Clause 9.2D.6.2 and Clause 9.2D.6.3 of TS 38.133 | Ericsson | RAN5#109 (Nov-25) | R5-255310 | Ericsson Kuba Kolodziej<kuba.kolodziej@ericsson.com> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
111 | Y | 38.533 | 19.5.1.1 | NR SA FR1 event triggered reporting tests without gap under non-DRX for ATG | The purpose of this test is to verify that the UE makes correct reporting of an event. This test will partly verify the intra-frequency cell search requirements in clauses 9.2D.5.1 and 9.2D.5.2 of TS 38.133. | Ericsson | RAN5#109 (Nov-25) | R5-253496,R5-255310,R5-256439 | Ericsson Kuba Kolodziej<kuba.kolodziej@ericsson.com> | 1 | 70% (+20%) | 70% (+20%) |  | 70%
112 | Y | 38.533 | 19.5.1.2 | NR SA FR1 event triggered reporting tests with per-UE gaps under non-DRX for ATG | The purpose of this test is to verify that the UE makes correct reporting of an event. This test will partly verify the intra-frequency cell search requirements in clause 9.2D.6.2 and 9.2D.6.3 of TS 38.133. | Ericsson | RAN5#109 (Nov-25) | R5-255310,R5-256440 | Ericsson Kuba Kolodziej<kuba.kolodziej@ericsson.com> | 1 | 70% (+20%) | 70% (+20%) |  | 70%
113 | Y | 38.533 | 19.5.1.3 | NR SA FR1 event triggered reporting tests without gap under non-DRX with SSB index reading for ATG | The purpose of this test is to verify that the UE makes correct reporting of an event. This test will partly verify the FDD intra-frequency cell search requirements in clause 9.2D.5.1 and 9.2D.5.2 of TS 38.133. | Ericsson | RAN5#109 (Nov-25) | R5-255310,R5-256441 | Ericsson Kuba Kolodziej<kuba.kolodziej@ericsson.com> | 1 | 70% (+20%) | 70% (+20%) |  | 70%
114 | Y | 38.533 | 19.5.1.4 | NR SA FR1 event triggered reporting tests with per-UE gaps under non-DRX with SSB index reading for ATG | The purpose of this test is to verify that the UE makes correct reporting of an event. This test will partly verify the intra-frequency cell search requirements in clause 9.2D.6.2 and 9.2D.6.3 of TS 38.133. | Ericsson | RAN5#109 (Nov-25) | R5-255310,R5-256442 | Ericsson Kuba Kolodziej<kuba.kolodziej@ericsson.com> | 1 | 70% (+20%) | 70% (+20%) |  | 70%
|  | 38.533 | 19.5.2 | Inter-frequency Measurements for ATG | [5 empty] | 0
115 |  | 38.533 | 19.5.2.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 9.3D.4, Clause 9.3D.5 and Clause 9.3D.9 of TS 38.133 | Ericsson | RAN5#109 (Nov-25) | R5-255311 | Ericsson Kuba Kolodziej<kuba.kolodziej@ericsson.com> | 1 | 100% | 100% |  | 100%
116 | Y | 38.533 | 19.5.2.1 | NR SA FR1-FR1 event triggered reporting tests under DRX for ATG | The purpose of this test is to verify that the UE makes correct reporting of an event. This test will partly verify the SA inter-frequency NR cell search requirements in clause 9.3D.4 of TS 38.133. | Ericsson | RAN5#109 (Nov-25) | R5-255311 | Ericsson Kuba Kolodziej<kuba.kolodziej@ericsson.com> | 1 | 50% (+50%) | 50% (+50%) |  | 50%
117 | Y | 38.533 | 19.5.2.2 | NR SA FR1-FR1 event triggered reporting tests with SSB time index detection under non-DRX for ATG | The purpose of this test is to verify that the UE makes correct reporting of an event. This test will partly verify the SA inter-frequency NR cell search requirements in clause 9.3D.4 and 9.3D.5 of TS 38.133. | Ericsson | RAN5#109 (Nov-25) | R5-255311,R5-256444 | Ericsson Kuba Kolodziej<kuba.kolodziej@ericsson.com> | 1 | 50% (+50%) | 50% (+50%) |  | 50%
118 | Y | 38.533 | 19.5.2.3 | NR SA FR1-FR1 event triggered reporting tests without gap under non-DRX for ATG | The purpose of this test is to verify that the UE makes correct reporting of an event. This test will partly verify the SA inter-frequency NR cell search requirements in clause 9.3D.9 of TS 38.133. | Ericsson | RAN5#109 (Nov-25) | R5-255311,R5-256445 | Ericsson Kuba Kolodziej<kuba.kolodziej@ericsson.com> | 1 | 50% (+50%) | 50% (+50%) |  | 50%
|  | 38.533 | 19.5.3 | L1-RSRP measurement for beam reporting for ATG | [5 empty] | 0
119 |  | 38.533 | 19.5.3.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 9.5D.4.1 and Clause 9.5D.4.2 of TS 38.133 | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-254549 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
120 | Y | 38.533 | 19.5.3.1 | NR SA FR1 SSB based L1-RSRP measurement in non-DRX for ATG | The purpose of this test is to verify that the UE makes correct reporting of L1-RSRP measurement. This test will partly verify the L1-RSRP measurement requirements in clause 9.5D.4.1, with the testing configurations for NR ATG cells in Table A.19.5.3.1.1-1 of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-255341(38.522),R5-254549,R5-254550,R5-256134,R5-256900(MU/TT),R5-256902(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> Editor’s Note: This test case is incomplete in following aspects. - TT analysis is missing - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procrdures for providing network assistance on ATG cells reference locations are FFS. | 1 | 85% (+5%) | 85% (+5%) |  | 85%
121 | Y | 38.533 | 19.5.3.2 | NR SA FR1 CSI-RS based L1-RSRP measurement in non-DRX for ATG | The purpose of this test is to verify that the UE makes correct reporting of L1-RSRP measurement. This test will partly verify the L1-RSRP measurement requirements in clause 9.5D.4.2, with the testing configurations for NR ATG cells in Table A.19.5.3.2.1-1 of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-255341(38.522),R5-254549,R5-254550,R5-256134,R5-256900(MU/TT),R5-256902(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> Editor’s Note: This test case is incomplete in following aspects. - TT analysis is missing - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procrdures for providing network assistance on ATG cells reference locations are FFS. | 1 | 85% (+5%) | 85% (+5%) |  | 85%
|  | 38.533 | 19.5.4 | L1-SINR measurement for beam reporting for ATG | [5 empty] | 0
122 |  | 38.533 | 19.5.4.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 9.8D.4.1, Clause 9.8D.4.2 and Clause 9.8D.4.3 of TS 38.133 | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-254549 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
123 | Y | 38.533 | 19.5.4.1 | NR SA FR1 L1-SINR measurement with CSI-RS based CMR and no dedicated IMR configured in non-DRX for ATG | The purpose of this test is to verify that the UE makes correct reporting of L1-SINR measurement. This test will partly verify the L1-SINR measurement requirements in clause 9.8D.4.1, with the testing configurations for NR ATG cells in Table A.19.5.4.1.1-1 of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-255341(38.522),R5-254549,R5-254550,R5-256135,R5-256900(MU/TT),R5-256142(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> Editor’s Note: This test case is incomplete in following aspects. - TT analysis is missing - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procrdures for providing network assistance on ATG cells reference locations are FFS. | 1 | 85% (+5%) | 85% (+5%) |  | 85%
124 | Y | 38.533 | 19.5.4.2 | NR SA FR1 L1-SINR measurement with SSB based CMR and dedicated IMR in non-DRX for ATG | The purpose of this test is to verify that the UE makes correct reporting of L1-SINR measurement. This test will partly verify the L1-SINR measurement requirements in clause 9.8D.4.2, with the testing configurations for NR ATG cells in Table A.19.5.4.2.1-1 of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-255341(38.522),R5-254549,R5-254550,R5-256135,R5-256900(MU/TT),R5-256142(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> Editor’s Note: This test case is incomplete in following aspects. - TT analysis is missing - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procrdures for providing network assistance on ATG cells reference locations are FFS. | 1 | 85% (+5%) | 85% (+5%) |  | 85%
125 | Y | 38.533 | 19.5.4.3 | NR SA FR1 L1-SINR measurement with CSI-RS based CMR and dedicated IMR in non-DRX for ATG | The purpose of this test is to verify that the UE makes correct reporting of L1-SINR measurement. This test will partly verify the L1-SINR measurement requirements with CSI-RS based CMR and dedicated IMR configured in clause 9.8D.4.3, with the testing configurations for NR ATG cells in Table A.19.5.4.3.1-1 of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-255341(38.522),R5-254549,R5-254550,R5-256135,R5-256900(MU/TT),R5-256142(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> Editor’s Note: This test case is incomplete in following aspects. - TT analysis is missing - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procrdures for providing network assistance on ATG cells reference locations are FFS. | 1 | 85% (+5%) | 85% (+5%) |  | 85%
|  | 38.533 | 19.5.5 | NR measurements with autonomous gaps for ATG | [5 empty] | 0
126 |  | 38.533 | 19.5.5.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 9.11D of TS 38.133 | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-254549 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% (+100%) | 100% (+100%) |  | 100%
127 | Y | 38.533 | 19.5.5.1 | NR SA FR1 CGI identification of NR neighbor cell for ATG | The purpose of this test is to verify that the UE makes correct reporting of intra-frequency CGI identification of an NR neighbour ATG cell in FR1 with autonomous gaps. This test shall partly verify the measurement requirements in Clause 9.11D, with the testing configurations for NR ATG cells in Table A.19.5.5.1.1-1 of TS 38.133 | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-255341(38.522),R5-254549,R5-254550,R5-256136,R5-256900(MU/TT),R5-256143(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> Editor’s Note: This test case is incomplete in following aspects. - TT analysis is missing - Message contents are missing - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procrdures for providing network assistance on ATG cells reference locations are FFS. | 1 | 85% (+5%) | 85% (+5%) |  | 85%
|  | 38.533 | 19.6 | Measurement Performance requirements for ATG | [5 empty] | 0
|  | 38.533 | 19.6.0 | General | [5 empty] | 0
128 |  | 38.533 | 19.6.0.1 | Principles of testing for ATG UE | To capture the general description for "A.19.6 Measurement Performance requirements" of TS 38.133 | CMCC | RAN5#109 (Nov-25) | R5-255350 | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 100% | 100% |  | 100%
|  | 38.533 | 19.6.1 | SS-RSRP for ATG | [5 empty] | 0
129 |  | 38.533 | 19.6.1.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 10.1.2.1.1, Clause 10.1.2.1.2, Clause 10.1.4.1.1 and Clause 10.1.4.1.2 of TS 38.133 | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-251585 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
|  | 38.533 | 19.6.1.1 | Intra-frequency measurements for ATG | [5 empty] | 0
130 | Y | 38.533 | 19.6.1.1.1 | NR SA FR1 SS-RSRP absolute measurement accuracy for ATG | The purpose of this test is to verify that the SS-RSRP absolute measurement accuracy is within the specified limits. This test will verify the requirements in clauses 10.1.2.1.1 and 10.1.2.1.2 for intra-frequency measurements of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-251585,R5-252693，R5-252698(MU/TT),R5-253555(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
131 | Y | 38.533 | 19.6.1.1.2 | NR SA FR1 SS-RSRP relative measurement accuracy for ATG | The purpose of this test is to verify that the SS-RSRP relative measurement accuracy is within the specified limits. This test will verify the requirements in clauses 10.1.2.1.1 and 10.1.2.1.2 for intra-frequency measurements of TS 38.133. | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-250687，R5-252693，R5-252698(MU/TT),R5-253555(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
|  | 38.533 | 19.6.1.2 | Inter-frequency measurements for ATG | [5 empty] | 0
132 | Y | 38.533 | 19.6.1.2.1 | NR SA FR1-FR1 SS-RSRP absolute measurement accuracy for ATG | The purpose of this test is to verify that the SS-RSRP absolute measurement accuracy is within the specified limits. This test will verify the requirements in clauses 10.1.4.1.1 and 10.1.4.1.2 for inter-frequency measurements with the testing configurations for NR cells in Table A.19.6.1.2.1-1 of TS 38.133. | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-250688，R5-252693，R5-252698(MU/TT),R5-253555(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
133 | Y | 38.533 | 19.6.1.2.2 | NR SA FR1-FR1 SS-RSRP relative measurement accuracy for ATG | The purpose of this test is to verify that the SS-RSRP relative measurement accuracy is within the specified limits. This test will verify the requirements in clauses 10.1.4.1.1 and 10.1.4.1.2 for inter-frequency measurements with the testing configurations for NR cells in Table A.19.6.1.2.1-1 of TS 38.133. | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-250689，R5-252693，R5-252698(MU/TT),R5-253555(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
|  | 38.533 | 19.6.2 | SS-RSRQ for ATG | [5 empty] | 0
134 |  | 38.533 | 19.6.2.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 10.1.7.1.1, Clause 10.1.9.1.1 and Clause 10.1.9.1.2 of TS 38.133 | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-250690 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
135 | Y | 38.533 | 19.6.2.1 | NR SA FR1 SS-RSRQ absolute measurement accuracy for ATG | The purpose of this test is to verify that the SS-RSRQ absolute measurement accuracy is within the specified limits. This test will verify the requirements in Clause 10.1.7.1.1 of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-250690,R5-252694,R5-252698(MU/TT),R5-253556(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
|  | 38.533 | 19.6.2.2 | Inter-frequency measurements for ATG | [5 empty] | 0
136 | Y | 38.533 | 19.6.2.2.1 | NR SA FR1-FR1 SS-RSRQ absolute measurement accuracy for ATG | The purpose of this test is to verify that the SS-RSRQ absolute measurement accuracy is within the specified limits. This test will verify the requirements in Clause 10.1.9.1.1 and 10.1.9.1.2 of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-250691,R5-252694,R5-252698(MU/TT),R5-253556(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
137 | Y | 38.533 | 19.6.2.2.2 | NR SA FR1-FR1 SS-RSRQ relative measurement accuracy for ATG | The purpose of this test is to verify that the SS-RSRQ relative measurement accuracy is within the specified limits. This test will verify the requirements in Clause 10.1.9.1.1 and 10.1.9.1.2 of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-250692,R5-252694,R5-252698(MU/TT),R5-253556(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
|  | 38.533 | 19.6.3 | SS-SINR for ATG | [5 empty] | 0
138 |  | 38.533 | 19.6.3.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 10.1.12.1.1, Clause 10.1.14.1.1 and Clause 10.1.14.1.2 of TS 38.133 | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-250693 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
139 | Y | 38.533 | 19.6.3.1 | NR SA FR1 SS-SINR absolute measurement accuracy for ATG | The purpose of this test is to verify that the SS-SINR absolute measurement accuracy is within the specified limits. This test will verify the requirements in clause 10.1.12.1.1 of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-250693,R5-252695,R5-252698(MU/TT),R5-253557(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
|  | 38.533 | 19.6.3.2 | Inter-frequency measurements for ATG | [5 empty] | 0
140 | Y | 38.533 | 19.6.3.2.1 | NR SA FR1-FR1 SS-SINR absolute measurement accuracy for ATG | The purpose of this test is to verify that the SS-SINR absolute measurement accuracy is within the specified limits. This test will verify the requirements in clauses 10.1.14.1.1 and 10.1.14.1.2 of TS 38.133. | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-250694,R5-252695,R5-252698(MU/TT),R5-253557(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
141 | Y | 38.533 | 19.6.3.2.2 | NR SA FR1-FR1 SS-SINR relative measurement accuracy for ATG | The purpose of this test is to verify that the SS-SINR relative measurement accuracy is within the specified limits. This test will verify the requirements in clauses 10.1.14.1.1 and 10.1.14.1.2 of TS 38.133. | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-250695,R5-252695,R5-252698(MU/TT),R5-253557(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
|  | 38.533 | 19.6.4 | L1-RSRP measurement for beam reporting for ATG | [5 empty] | 0
142 |  | 38.533 | 19.6.4.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 9.5D.2, Clause 10.1.19.1 and Clause 10.1.19.2 of TS 38.133 | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-250696 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
|  | 38.533 | 19.6.4.1 | SSB based L1-RSRP measurements for ATG | [5 empty] | 0
143 | Y | 38.533 | 19.6.4.1.1 | NR SA FR1 SSB based L1-RSRP absolute measurement accuracy for ATG | The purpose of this test is to verify that the L1-RSRP absolute measurement accuracy is within the specified limits. This test will verify the requirements in clause 9.5D.2 and clause 10.1.19.1 of TS 38.133 for L1-RSRP measurements based on SSB with the testing configurations for NR cells in Table A.19.6.4.1.1-1 of TS 38.133. | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-250696,R5-255341(38.522),R5-255327(38.903),R5-254552 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
144 | Y | 38.533 | 19.6.4.1.2 | NR SA FR1 SSB based L1-RSRP relative measurement accuracy for ATG | The purpose of this test is to verify that the L1-RSRP relative measurement accuracy is within the specified limits. This test will verify the requirements in clause 9.5D.2 and clause 10.1.19.1 of TS 38.133 for L1-RSRP measurements based on SSB with the testing configurations for NR cells in Table A.19.6.4.1.1-1 of TS 38.133. | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-250697,R5-255341(38.522),R5-255327(38.903),R5-254552 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
|  | 38.533 | 19.6.4.2 | CSI-RS based L1-RSRP measurements for ATG | [5 empty] | 0
145 | Y | 38.533 | 19.6.4.2.1 | NR SA FR1 CSI-RS based L1-RSRP absolute measurement accuracy for ATG | The purpose of this test is to verify that the L1-RSRP absolute measurement accuracy is within the specified limits. This test will verify the requirements in clause 9.5D.3 and clause 10.1.19.2 of TS 38.133 for L1-RSRP measurements based on CSI-RS with the testing configurations for NR cells in Table A.19.6.4.2.1-1 of TS 38.133. | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-250698,R5-255341(38.522),R5-255327(38.903),R5-254552 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
146 | Y | 38.533 | 19.6.4.2.2 | NR SA FR1 CSI-RS based L1-RSRP relative measurement accuracy for ATG | The purpose of this test is to verify that the L1-RSRP relative measurement accuracy is within the specified limits. This test will verify the requirements in clause 9.5D.3 and clause 10.1.19.2 of TS 38.133 for L1-RSRP measurements based on CSI-RS with the testing configurations for NR cells in Table A.19.6.4.2.1-1 of TS 38.133. | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-250699,R5-255341(38.522),R5-255327(38.903),R5-254552 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
|  | 38.533 | 19.6.5 | L1-SINR measurement for beam reporting for ATG | [5 empty] | 0
147 |  | 38.533 | 19.6.5.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 9.8D.4.1, Clause 9.8D.4.2, Clause 9.8D.4.3, Clause 10.1.27.1, Clause 10.1.27.2 and Clause 10.1.27.3 of TS 38.133 | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-250700 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
|  | 38.533 | 19.6.5.1 | L1-SINR measurement with CSI-RS based CMR and no dedicated IMR for ATG | [5 empty] | 0
148 | Y | 38.533 | 19.6.5.1.1 | NR SA FR1 L1-SINR absolute measurement accuracy with CSI-RS based CMR and no dedicated IMR for ATG | The purpose of this test is to verify that the L1-SINR absolute measurement accuracy is within the specified limits. This test will verify the requirements in clause 9.8D.4.1 and clause 10.1.27.1 of TS 38.133 for L1-SINR measurements based on CSI-RS with the testing configurations for NR cells in Table A.19.6.5.1.1-1. | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-250700,R5-255341(38.522),R5-255328(38.903),R5-254553 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
149 | Y | 38.533 | 19.6.5.1.2 | NR SA FR1 L1-SINR relative measurement accuracy with CSI-RS based CMR and no dedicated IMR for ATG | The purpose of this test is to verify that the L1-SINR relative measurement accuracy is within the specified limits. This test will verify the requirements in clause 9.8D.4.1 and clause 10.1.27.1 of TS 38.133 for L1-SINR measurements based on CSI-RS with the testing configurations for NR cells in Table A.19.6.5.1.1-1. | Huawei, HiSilicon | RAN5#109 (Nov-25) | R5-250701,R5-255341(38.522),R5-255328(38.903),R5-254553 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
150 | Y | 38.533 | 19.6.5.2 | NR SA FR1 L1-SINR absolute measurement accuracy with SSB based CMR and dedicated IMR for ATG | The purpose of this test is to verify that the L1-SINR absolute measurement accuracy is within the specified limits. This test will verify the requirements in clause 9.8D.4.2 and clause 10.1.27.2 of TS 38.133 for L1-SINR measurements with SSB based CMR and dedicated CSI-RS based IMR, with the testing configurations for NR cells in Table A.19.6.5.2.1-1. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-250702,R5-255341(38.522),R5-255328(38.903),R5-254553 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
|  | 38.533 | 19.6.5.3 | L1-SINR measurement with CSI-RS based CMR and dedicated IMR for ATG | [5 empty] | 0
151 | Y | 38.533 | 19.6.5.3.1 | NR SA FR1 L1-SINR absolute measurement accuracy with CSI-RS based CMR and dedicated IMR for ATG | The purpose of this test is to verify that the L1-SINR absolute measurement accuracy is within the specified limits. This test will partly verify the requirements in Clauses 9.8D.4.3 and clause 10.1.27.3 of TS 38.133 for L1-SINR measurements based on CSI-RS as CMR and CSI-IM as IMR with the testing configurations for NR cells in Table A.19.6.5.3.1-1. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-250703,R5-255341(38.522),R5-255328(38.903),R5-254553 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
152 | Y | 38.533 | 19.6.5.3.2 | NR SA FR1 L1-SINR relative measurement accuracy with CSI-RS based CMR and dedicated IMR for ATG | The purpose of this test is to verify that the L1-SINR relative measurement accuracy is within the specified limits. This test will partly verify the requirements in Clauses 9.8D.4.3 and clause 10.1.27.3 of TS 38.133 for L1-SINR measurements based on CSI-RS as CMR and CSI-IM as IMR with the testing configurations for NR cells in Table A.19.6.5.3.1-1. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-250704,R5-255341(38.522),R5-255328(38.903),R5-254553 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
|  | 38.533 | 19.6.6 | CSI-RSRP for ATG | [5 empty] | 0
153 |  | 38.533 | 19.6.6.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 10.1.2.3.1, Clause 10.1.2.3.2, Clause 10.1.4.3.1 and Clause 10.1.4.3.2 of TS 38.133 | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-253493 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
|  | 38.533 | 19.6.6.1 | Intra-frequency measurements for ATG | [5 empty] | 0
154 | Y | 38.533 | 19.6.6.1.1 | NR SA FR1 CSI-RSRP absolute measurement accuracy for ATG | The purpose of this test is to verify that the CSI-RSRP absolute measurement accuracy is within the specified limits. This test will verify the requirements in clauses 10.1.2.3.1 and 10.1.2.3.2 of TS 38.133 for CSI-RS intra-frequency measurements. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-253493,R5-254551,R5-256899,R5-256900(MU/TT),R5-256903(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> Editor’s Note: This test case is incomplete in following aspects. - Test requirements are missing - TT analysis is missing - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procrdures for providing network assistance on ATG cells reference locations are FFS. | 1 | 85% (+15%) | 85% (+15%) |  | 85%
155 | Y | 38.533 | 19.6.6.1.2 | NR SA FR1 CSI-RSRP relative measurement accuracy for ATG | The purpose of this test is to verify that the CSI-RSRP relative measurement accuracy is within the specified limits. This test will verify the requirements in clauses 10.1.4.3.1 and 10.1.4.3.2 of TS 38.133 for CSI-RS inter-frequency measurements with the testing configurations for NR cells in Table A.19.6.6.2.1-1. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-253493,R5-254550,R5-254551,R5-256899,R5-256900(MU/TT),R5-256903(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> Editor’s Note: This test case is incomplete in following aspects. - Test requirements are missing - TT analysis is missing - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procrdures for providing network assistance on ATG cells reference locations are FFS. | 1 | 85% (+15%) | 85% (+15%) |  | 85%
|  | 38.533 | 19.6.6.2 | Inter-frequency measurements for ATG | [5 empty] | 0
175 | Y | 38.533 | 19.6.6.2.1 | NR SA FR1-FR1 CSI-RSRP absolute measurement accuracy for ATG | The purpose of this test is to verify that the CSI-RSRQ measurement accuracy is within the specified limits. This test will verify the requirements in Clause 10.1.9.2.1 and 10.1.9.2.2 of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-255341(38.522),R5-255381,R5-254550 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> Editor’s Note: This test case is incomplete in following aspects. - Message content is missing - Test procedure is missing - Test requirements are missing - TT analysis is missing - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procrdures for providing network assistance on ATG cells reference locations are FFS. | 1 | 50% (+50%) | 50% (+50%) |  | 50%
176 | Y | 38.533 | 19.6.6.2.2 | SA Inter-frequency measurement accuracy with FR1 serving cell and FR1 target cell | The purpose of this test is to verify that the CSI-RSRQ measurement accuracy is within the specified limits. This test will verify the requirements in Clause 10.1.9.2.1 and 10.1.9.2.2 of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-255341(38.522),R5-255381,R5-254550 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> Editor’s Note: This test case is incomplete. The following still is missing: - Message content is missing - Test procedure is missing - Cell mapping is missing - Antenna connection diagram is missing - Applicability is missing - TT is missing | 1 | 50% (+50%) | 50% (+50%) |  | 50%
|  | 38.533 | 19.6.7 | CSI-RSRQ for ATG UE | [5 empty] | 0
156 |  | 38.533 | 19.6.7.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 10.1.7.2, Clause 10.1.9.2.1 and Clause 10.1.9.2.2 of TS 38.133 | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-253494 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
157 | Y | 38.533 | 19.6.7.1 | SA Intra-frequency measurement accuracy with FR1 serving cell and FR1 target cell | The purpose of this test is to verify that the CSI-RSRQ measurement accuracy is within the specified limits. This test will verify the requirements in Clause 10.1.7.2 of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-253494,R5-254551,R5-256138,R5-256900(MU/TT),R5-256904(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> Editor’s Note: This test case is incomplete in following aspects. - Test requirements are missing - TT analysis is missing - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procrdures for providing network assistance on ATG cells reference locations are FFS. | 1 | 85% (+15%) | 85% (+15%) |  | 85%
|  | 38.533 | 19.6.7.2 | Inter-frequency measurements for ATG | [5 empty] | 0
158 | Y | 38.533 | 19.6.7.2.1 | NR SA FR1-FR1 CSI-RSRQ absolute measurement accuracy for ATG | The purpose of this test is to verify that the CSI-RSRQ absolute measurement accuracy is within the specified limits. This test will verify the requirements in Clause 10.1.9.2.1 and 10.1.9.2.2 of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-255341(38.522),R5-255381,R5-254550 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> Editor’s Note: This test case is incomplete in following aspects. - Message content is missing - Test procedure is missing - Test requirements are missing - TT analysis is missing - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procrdures for providing network assistance on ATG cells reference locations are FFS. | 1 | 50% (+50%) | 50% (+50%) |  | 50%
177 | Y | 38.533 | 19.6.7.2.2 | NR SA FR1-FR1 CSI-RSRQ relative measurement accuracy for ATG | The purpose of this test is to verify that the CSI-RSRQ relative measurement accuracy is within the specified limits. This test will verify the requirements in Clause 10.1.9.2.1 and 10.1.9.2.2 of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-255341(38.522),R5-255381,R5-254550 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> Editor’s Note: This test case is incomplete in following aspects. - Message content is missing - Test procedure is missing - Test requirements are missing - TT analysis is missing - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procrdures for providing network assistance on ATG cells reference locations are FFS. | 1 | 50% (+50%) | 50% (+50%) |  | 50%
|  | 38.533 | 19.6.8 | CSI-SINR for ATG UE | [5 empty] | 0
159 |  | 38.533 | 19.6.8.0 | Minimum conformance requirements | To add the minimum conformance requirements from Clause 10.1.12.2.1, Clause 10.1.14.2.1 and Clause 10.1.14.2.2 of TS 38.133 | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-253495 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 100% | 100% |  | 100%
160 | Y | 38.533 | 19.6.8.1 | SA intra-frequency measurement accuracy with FR1 serving cell and FR1 target cell | The purpose of this test is to verify that the CSI-SINR measurement accuracy is within the specified limits. This test will verify the requirements in clause 10.1.12.2.1 of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-253495,R5-254551,R5-256139,R5-256900(MU/TT),R5-256905(38.903) | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> Editor’s Note: This test case is incomplete in following aspects. - Test requirements are missing - TT analysis is missing - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procrdures for providing network assistance on ATG cells reference locations are FFS. | 1 | 85% (+15%) | 85% (+15%) |  | 85%
|  | 38.533 | 19.6.8.2 | Inter-frequency measurements for ATG | [5 empty] | 0
178 | Y | 38.533 | 19.6.8.2.1 | NR SA FR1-FR1 CSI-SINR absolute measurement accuracy for ATG | The purpose of this test is to verify that the CSI-SINR absolute measurement accuracy is within the specified limits. This test will verify the requirements in clauses 10.1.14.2.1 and 10.1.14.2.2 of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-255381,R5-254550 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> Editor’s Note: This test case is incomplete in following aspects. - Message content is missing - Test procedure is missing - Test requirements are missing - TT analysis is missing - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procrdures for providing network assistance on ATG cells reference locations are FFS. | 1 | 50% (+50%) | 50% (+50%) |  | 50%
161 | Y | 38.533 | 19.6.8.2.2 | NR SA FR1-FR1 CSI-SINR relative measurement accuracy for ATG | The purpose of this test is to verify that the CSI-SINR relative measurement accuracy is within the specified limits. This test will verify the requirements in clauses 10.1.14.2.1 and 10.1.14.2.2 of TS 38.133. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-255381,R5-254550 | Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> Editor’s Note: This test case is incomplete in following aspects. - Message content is missing - Test procedure is missing - Test requirements are missing - TT analysis is missing - AT commands for UE positioning and UE speed setting are FFS. - UE specific positioning and the specific gNB reference location emulated by test system are FFS. - Test procrdures for providing network assistance on ATG cells reference locations are FFS. | 1 | 50% (+50%) | 50% (+50%) |  | 50%
162 |  | 38.533 | Annexs | Cell configuration mapping, Measurement uncertainties and test tolerances | To add Cell configuration mapping and Measurement uncertainties and test tolerances for ATG test cases in 38.533 Annex E and Annex F, respectively. | Huawei, Hisilicon | RAN5#109 (Nov-25) | R5-251586,R5-252697,R5-251868,R5-255630,R5-256898,R5-256446 | Needs to fix "19.6.1.1.2" into "19.6.6.1.2" in Table E.17 Huawei, Hisilicon Wangxuesong (Cedar, Beijing Branch of Hisilicon Research Dept)<cedar.wang@HISILICON.COM> | 1 | 50% | 50% |  | 50%
TR 38.903: Test Tolerances analysis RRM and RF Rx test cases
|  | 38.903 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
TBD |  | 38.903 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.903 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TS 38.523-1: Protocol test cases
|  | 38.523-1 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
163 |  | 38.523-1 | 3.2 | Abbreviations | Add "ATG" into "Abbreviations" | CMCC | RAN5#109 (Nov-25) |  | CMCC Luyang Zhao <zhaoluyang@chinamobile.com> | 0.5 | 0% | 0% |  | 0%
|  | 38.523-1 | 6.8 | Air To Ground | [5 empty] | 0
|  | 38.523-1 | 6.8.1 | ATG idle mode operations | [5 empty] | 0
164 | Y | 38.523-1 | 6.8.1.1 | ATG idle mode operations / Cell selection / GNSS position | The purpose is to verify that UE performs cell selection with valid GNSS position. This test will verify the requirements in clause 5.2.2.4.1, 5.2.2.4.2 and 5.2.2.5 of TS 38.331. | ZTE | RAN5#109 (Nov-25) | R5-253135,R5-252197(38.523-2) | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> | 1 | 100% | 100% |  | 100%
165 | Y | 38.523-1 | 6.8.1.2 | ATG idle mode operations / Cell selection / Serving cell selection (cellBarredATG) | The purpose is to verify that UE performs cell selection and re-selection with different configuration for cellBarredATG. This test will verify the requirements in clause 5.2.2.4.1, 5.2.2.4.2 and 5.2.2.5 of TS 38.331. | ZTE | RAN5#109 (Nov-25) | R5-253136,R5-252197(38.523-2) | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> | 1 | 100% | 100% |  | 100%
166 | Y | 38.523-1 | 6.8.1.3 | ATG idle mode operations / Cell selection / MultiTAC | The purpose is to verify that UE forwards the trackingAreaList to upper layers when there are more than one TAC per PLMN. This test will verify the requirements in clause 5.2.2.4.1, 5.2.2.4.2 and 5.2.2.5 of TS 38.331. | ZTE | RAN5#109 (Nov-25) |  | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> | 0 | 0% | 0% |  | 0%
167 | Y | 38.523-1 | 7.1.1.10.5 | ATG / TA report / Koffsetta-ReportATG / offsetThresholdTA | The purpose is to verify that UE performs TA report and applies Koffset received. This test will verify the requirements in clause 16.19.2.1 of TS 38.300, clause 5.3.3.3 of TS 38.331, clause 5.4.8 and 5.18.24 of TS 38.321 | ZTE | RAN5#109 (Nov-25) | R5-253137,R5-253140(38.523-2),R5-255626 | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> | 1 | 100% | 100% |  | 100%
168 | Y | 38.523-1 | 8.1.4.4.8 | ATG / Conditional handover / Success / CondEventD1 | The purpose is to verify that UE performs CHO CondEventD1 successfully. This test will verify the requirements in clause 16.19.3.2.2 of TS 38.300, clause 5.3.5.1, 5.3.5.13.1, 5.5.4.15 and 5.3.5.13.4 of TS 38.331 | ZTE | RAN5#109 (Nov-25) | R5-253138, R5-253139(35.523-2) | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> | 1 | 100% | 100% |  | 100%
169 | Y | 38.523-1 | 8.1.4.4.10 | ATG / Conditional handover / Success / CondEventA4 | The purpose is to verify that UE performs CHO CondEventA4 successfully. This test will verify the requirements in clause 16.19.3.2.2 of TS 38.300, clause 5.3.5.13.1, 5.5.4.5 and 5.3.5.13.4 of TS 38.331 | ZTE | RAN5#109 (Nov-25) | R5-254028,R5-254029 | ZTE xu.jiali@zte.com.cn<xu.jiali@zte.com.cn> | 1 | 100% | 100% |  | 100%
TBD |  | 38.523-1 | <Clause> | <Title of new sub-clause header> | New sub-clause header |  | TBD |  |  | 0
TBD |  | 38.523-1 | <Clause> | <Title of task> | <Describe task> |  | TBD |  |  | 1 | 0% | 0% |  | 0%
TR 38.905: Test Point analysis receiver and transmitter test cases
|  | 38.905 |  | Placeholder for estimation of not yet identified tasks within the area (to be removed when no further tasks expected). | [5 empty] | TBD
49 |  | 38.905 | 4.1.1.8 | FR1 ATG test cases | Add TP analysis for ATG test cases | CAICT | RAN5#109 (Nov-25) | R5-241765,R5-247717, R5-250115, R5-251515,R5-256810 | CAICT Yufeng Zhang zhangyufeng@caict.ac.cn | 1 | 70% | 70% |  | 70%
End of workplan items. Note! Do not remove this row. Introduce new work plan rows/items above this row.
Note on A6: Unique ID for WP items (unique within the sub-area work plan) Note! As WP item numbers may be referenced from outside of this WP that means: - Do not change number for WP items that have been published. - Do not re-use WP item numbers if a WP item is deleted
Note on B6: Set to Y if the WP item represents a new test case that will be specified in RAN5 test specifications as an executable test case else leave blank.
Note on K6: The WP item's weight number is used to set the reletive weights between WP items used in the overall calculation of completeness. Setting it to 0 for a WP item means that it will not be included at all in the calculation.