## Slide 1
Puneet Jain
TSG SA Chair
SA Rel-20 5G-Advanced Content Definition Process and Next Steps

## Slide 2
Rel-20 (5G-Advanced)
  For 5G-Advanced: 18-month. Assuming no delay of Rel-19
    Stage-1 freeze : Jun 2025
    Stage-2 freeze : Jun 2026 (>=80%); Sep 2026 (100%)
    Stage-3 freeze : Mar 2027
    ASN.1/OpenAPI freeze: June 2027
Release 20: 5G-Advanced Timeline
2024
#103
Mar.
#111
Mar.
#107
Mar.
#104
Jun.
#108
Jun.
#112
Jun.
#105
Sep.
#109
Sep.
#102
Dec.
#106
Dec.
#110
Dec.
TSGs
SA1 5GA SID definition
100%
SA1 5GA Studies + Norm 80%
100%
St. 2 (SA2, SA6, …) 5GA St.+Norm 80%
Stage 3 5GA St + Norm
#113
Sep.
#114
Dec.
#115
Mar.
Jun
RAN1
RAN Completion (RAN2/3/4core)
#116
RAN4 C.def.
RAN4 Perf
RP Content def.
Rel-20 - 5GA part
2025
2026
2027
5GA ASN.1 & Open APIs
St.2 SID def. TBD
St.3 SID def. TBD
Workshop 5GA SA

## Slide 3: Rel-20 5G-Advaced Content Definition Process (Endorsed in SP-241738)
TSG #107
TSG #108
TSG #109
TSG #110
TSG #111
TSG #112
TSG #113
TSG #114
TSG #115
TSG #116
TSG #117
TSG #118
TSG #105
2026
2027
Mar.
Sep.
Sep.
Sep.
Dec.
Dec.
Dec.
Mar.
Mar.
Jun.
Jun.
Jun.
Jun.
Stage-3 (CT & SA)
Stage-2 Study/Work Phase
Rel-20 5GA Content Approval
Rel-20 5GA
Workshop
TSG #106
Dec.
2025
Now
100%
SA1 Stage-1 80%
ASN.1 / Open API
Stage-1 Freeze
Selected Rel-20 SID/WID Approval
Rel-20 Final Package Approval
Stage-2 Freeze
Stage-3 Freeze
Rel-20 5GA complete
MED
Moderated Email Discussions
MED
WG starts working on Rel-20 SID/WID approved at SA#107
Rel-20 Scope Discussion / Guidance to WG
2024
ASN.1 / Open API
Stage-2 80% Complete
(Source SP-250xxx)

## Slide 4: SA Rel-20 5GA Content Definition steps (Endorsed in SP-241738)
Discussion and Guidance for Rel-20 5GA Scope: The content proposals for Rel-20 5GA will be discussed during the SA Rel-20 5GA Workshop, and overall guidance will be provided to the SA WGs on Rel-20 5GA topics.
  This guidance will include a list of core and miscellaneous topics for Rel-20 5GA. The core topics have garnered significant interest based on numerous presentations, while the miscellaneous topics have been presented in a limited number of instances. The level of detail is yet to be determined.
  The WG's capacity including Max# of SID/WID and TU budget estimates will be taken into account.
Moderated Email Discussions: The Working Group may organize Moderated Email Discussions to develop SID/WID details corresponding to the Rel-20 5GA topics identified in the Core/Miscellaneous list. The focus will be on defining technical objectives, work tasks, and estimated budgets for each task. These discussions can occur in either Q1 or Q2 or both.
Approval of Selected Rel-20 5GA SID/WID: This marks the first step in the approval process for Rel-20 5GA content. The WG may submit the SID/WID to SA#107 for approval. Ideally, the Rel-20 5GA SID/WID for approval at this step should have no dependencies on RAN. SID/WID for approval should follow the guidance on Rapporteurship (see SP-230746). Part of WG capacity will be assigned during the first step approval process.
WG commences Rel-20 5GA SI/WI Work: After the approval of the SID/WID at SA#107, the Working Group can start working on the approved SID/WID during their Q2 meetings.
Final Approval of Rel-20 5GA Package: This represents the second and final step in the approval process for the Rel-20 5GA content definition. The WG can submit the Rel-20 5GA SID/WID to SA#108 for approval. SID/WID for approval should follow the guidance on Rapporteurship (see SP-230746). Further prioritization, if necessary, will be handled based on WG capacity.
Completed
SA#108 focus
Completed
Completed
Completed

## Slide 5
SA2 Rel-20 5G-A candidate topics
(Endorsed in SP-241738)
See SP-241972 for the consolidated list.
NOTE: A Topic may result in one or more SIDs.
S.No. | Rel-20 Core Topics | Rel-20 Miscellaneous Topics
1 | Integration of satellite components in the 5G architecture Phase 4 | XR and Media Services
2 | AI/ML Enhancements | Indirect Network Sharing Phase 2
3 | Ambient IoT | User Identities and Authentication Architecture - Phase 2
4 | Integrated Sensing and Communication | Enhancements for ePDG based access to 5GC
5 | Energy Efficiency Enhancements | Mission Critical Services, Multimedia Priority Services
6 |  | Industrial network enhancements
7 |  | SMS to emergency centre
8 |  | NG_RTC continuation

## Slide 6
Guidance to SA2 on Rel-20 5GA work planning
(Endorsed in SP-241738)
SA2 should target a maximum number of 7 Rel-20 5GA SIDs
  NOTE: This limit may be revisited at SA#107 after SA2 reaches an agreement on the 5GA and 6G TU split.
SA2 shall allocate the TU budget for TEI20 at a level no less than the TEI19 budget in Rel-19.
SA2 should prioritize following “core” topics for Q1 2025 and should aim to submit SIDs at SA#107 for approval (as per normal consensus). Remaining topics may also be discussed if time permits. If SA2 cannot come to an agreement on these items for SA#107 then they can come for approval at SA#108.
    Integration of satellite components in the 5G architecture Phase 4
    AI/ML enhancements
    Integrated Sensing and Communication
    Energy Efficiency Enhancements
    NOTE: A topic may result in one or more SIDs.
The “Brief Description and Key Objectives” in SP-241972 should serve as a starting point for the moderated discussion on the candidate topics (as shown in slide#2) and objectives of the candidate topics can be updated during the process.
Any miscellaneous topics that could not be handled in Q1 2025 will be a candidate for moderated discussion during Q2 2025.
Any new normative stage-1 requirements from SA1 approved by SA are not precluded from Rel-20 5GA scope. This needs to be discussed at TSG#107/TSG#108.
The final decision on the complete set of SIDs for Rel-20 5GA (and the work tasks and TU budget of each SID) will be taken in SA#108.
For topic SMS to emergency centre, no SA2 moderated discussion expected in Q1 2025.
For topic User Identities and Authentication, whether moderated discussion can take place in Q2 2025 will be determined in TSG#107.
Checkpoint in TSG#108 to check SA3 status on Rel-20 UIA and discussion on related SA2 aspects for Rel-20 UIA

## Slide 7: SA2 Rel-20 capacity summary (Source SP-250341)
SA2 capacity (March 2025 – September 2026) as per SP-250284:
  Max TUs for release planning purposes: 157
    For 5G Advanced SIDs and WIDs, and 6G SID
  Max number of SIs/WIs: 7- 9 (5G Advanced) – Note: this doesn’t have consensus
    Note: one feature made up of SI+WI is counted as one item
  Max TUs per Feature: 2 TUs per meeting (excluding the 6G study)
  Max TUs overall per feature: 14 TU (excluding the 6G study)
Additional TUs for 6G study after September 2026: 30 (if study is to complete by December 2026)
Assumptions
  Number of meetings: 9
  Expected total TUs per meeting (for all releases): 30
  Total TUs (for all releases): 270
  TUs for maintenance of past releases: 86
  TUs for additional buffer: 27

## Slide 8: Rel-20 5GA and 6G TU budgets (Source SP-250730)
Assuming that typically 6 sessions per meeting are required for the 6G study, and the 6G study is scheduled in parallel with 5GA
The per-meeting schedule and totals could look something like this
  NOTE: This per-meeting schedule is for illustration purposes only and for determining the overall TU budget for release planning purposes. The per-meeting allocation may change over time
Total TU Budget for Rel-20 5GA
  72 TUs for 5GA items; 12 TU already used in Q2; Total 5GA TUs remaining = 60 TUs
  In addition, 12 TUs are planned for 5GA TEI20 items
 |  |  | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026 | 2026 | 2026
 |  |  | Apr #168 | May #169 | Aug #170 | Oct #171 | Nov #172 | Feb #173 | Apr #174 | May #175 | Aug #176 | Oct #177 | Nov #178
 |  | Totals between Mar and Sep |  |  |  |  | Study deadline A | Study deadline B |  | Stage 2 80% | Stage 2 100% |  | 
Rel-20 |  |  |  |  |  |  |  |  |  |  |  |  | 
20.x | Planned TU's (not TEI20, Maint) | 148 | 4 | 8 | 15 | 18 | 19 | 21 | 21 | 21 | 21 |  | 
5GA |  | 72 | 4 | 8 | 7 | 8 | 9 | 9 | 9 | 9 | 9 |  | 
6G |  | 76 | 0 | 0 | 8 | 10 | 10 | 12 | 12 | 12 | 12 |  | 

## Slide 9: Candidate SA2 Rel-20 5GA SIDs/WIDs
SID/WID | Status | Study | Norm | Total | New Study | New Norm | New Total | Comments
FS_5GSAT_Ph4_ARC | SA Approved | 8.5 | 8.5 | 17 | 8.5 (3*) | 8.5 | 17 | Exceed max 14 TUs limit
FS_AIML_CN_Ph2 | SA Approved | 5 | 2 | 7 | 5 (3*) | 2 | 7 | No normative TUs for WT#1; dependent on RAN discussion
FS_Sensing_ARC | SA Approved | TBD | TBD | 0 | TBD (3*) | TBD | TBD | No TU estimate; dependent on RAN scope
FS_EnergySys_Ph2 | SA Approved | 6 | 6 | 12 | 6 (3*) | 6 | 12 | 
FS_AmbientIoT_ARC_Ph2 | SA2 Agreed | 6 | 6 | 12 | 6 | 6 | 12 | dependent on RAN scope
NetShare_ph2 | SA2 Agreed | 0 | 2 | 2 | 0 | 2 | 2 | 
FS_MPS_IOT | SA2 Agreed | 3 | 3 | 6 | 3 | 3 | 6 | 
ProSe_Ph4-ARC | SA2 Agreed | 0 | 1 | 1 | 0 | 1 | 1 | 
FS_NG_RTC_Ph3 | SA2 Agreed | 5 | 4 | 9 | 5 | 4 | 9 | 
FS_SMS2EC_Ph2_ARC | SA2 Agreed | 4 | 3.5 | 7.5 | 4 | 3.5 | 7.5 | 
FS_XRM_Ph3 | SA2 Noted | 3 | 3.5 | 6.5 |  |  |  | 
FS_ePDG5GC | SA2 Noted | 1.5 | 1.5 | 3 |  |  |  | 
Vertical_LAN_Loop_Ph2 | SA2 Noted | 0 | 1 | 1 |  |  |  | 
FS_ARCH_enIMS | NEW | TBD | TBD | 0 |  |  |  | 5GA/6G track?
Total |  | 42 | 42 | 84 | 37.5 (12*) | 36 | 73.5 (12*) | Total TU Budget: 72; TUs remaining: 60; Max SIDs/WIDs: 7-9
Total number of items | 14 |  |  |  |  |  |  | 
*: Donate the # of TUs already used in Q2

## Slide 10: Next Steps
Endorse the SA2 Rel-20 5GA TU budget (Total TUs: 72, Remaining TUs: 60), max number of SIDs/WIDs (7-9 SIDs/WIDs), max number of TUs per feature (14 TUs for SI started in Q2; 12 TUs for SI starting in Q3).
Ensure all candidate SA2 Rel-20 5GA SIDs/WIDs reach the same status—“SA Endorsed”, which indicates that SID/WID content and TU estimates are technically correct, with no objections. “SA Endorsed” status does not imply inclusion in the final SA2 Rel-20 5GA content. Action needed –
  Finalizing the scope and TU estimated (with input on scope from RAN) for FS_AIML_CN_Ph2, FS_Sensing_ARC, FS_AmbientIoT_ARC_Ph2.
  Applying max TU per feature limit of 14 TU to all SIDs/WIDs started in Q2 – FS_5GSAT_Ph4_ARC.
  Review and Agree on SA2 NOTED SIDs/WIDs – FS_XRM_Ph3, FS_ePDG5GC, Vertical_LAN_Loop_Ph2.
  Evaluate and Agree on NEW SIDs/WIDs – FS_ARCH_enIMS. Discuss relationship with FS_NG_RTC_Ph3.
  NOTE 1: If there are sustained objections regarding the content and/or TU estimates of any SID/WID, it will not be included in the SA2 Rel-20 5GA content definition process.
Agree on the final SA2 Rel-20 5GA content (fitting within the TU budget) through consensus. This may involve –
  Deprioritizing some SIDs/WIDs
  Removing the WTs within SIDs/WIDs
  Conversion of some WIDs to TEI20 WIDs
  Approve the SA2 Rel-20 5GA SIDs/WIDs, including assigning Rapporteur(s).

## Slide 11: Thank You !
Puneet Jain
Chair of 3GPP SA
puneet.jain@intel.com
www.3gpp.org