3GPP TSG-RAN WG3 Meeting #131	R3-260331

Goteborg, Sweden, 9 – 13 February 2026

Agenda item:	13.1

Source:	China Telecom, Xiaomi

Title:	Work plan for study on Integrated Sensing And Communication (ISAC) for NR

Document for:	Discussion

Introduction

At RAN#109, the updated SID on Integrated Sensing and Communication (ISAC) for NR was agreed [1].

This study item aims to study the following aspects for Integrated Sensing and Communication (ISAC): Evaluate the performance of gNB-based mono-static sensing (i.e., single TRP with co-located sensing transmitter and receiver) for UAV use case [RAN1] - Identify and study metrics, measurements, and relevant measurement quantization for UAV use case - As baseline, existing DL NR waveform and DL NR reference signals are to be used for evaluations. - For other waveform and reference signals, companies are to share relevant information - No UE impacts - Deployment scenario and assumptions for channel model calibration for UAV sensing targets in the Rel-19 ISAC channel model SI [FS_Sensing_NR] are used as starting point for evaluation assumptions. - FR1 frequency range is prioritized. Study the procedures, signaling between RAN and CN to support ISAC [RAN3] Study network architecture for gNB-based mono-static sensing for UAV sensing target use cases [RAN3] - Applicability to gNB bistatic sensing may be considered as part of this network architecture without additional architecture impacts. - No inter-gNB coordination will be studied. - Coordination with SA2 as necessary.

In this contribution, we propose a work plan for the study item.

Time budget

The time budget approved at RAN#108 meeting in [1] is shown as below.

Table 1: Time budget allocation

| Data | Aug 2025 | Oct 2025 | Nov 2025[Note 1] | Feb 2026 | April 2026 | May 2026 |
| --- | --- | --- | --- | --- | --- | --- |
| RAN1 meetings | R1#122 1 TU | R1#122bis 1 TU | R1#123 1 TU | R1#124 1 TU | - | - |
| RAN3 Meetings | - | R3#129bis 1 TU | R3#130 1 TU | R3#131 1 TU | R3#131bis 1 TU | R3#132 1 TU |

Note 1, the last meeting of SA2 in R20 SI.

Work Plan in RAN1

Based on the SID and the assigned time budget, i.e., 4 RAN1 meetings in 9 months, the following detailed work plan is proposed for the study in RAN1.

RAN1 #122 (August 2025)

- Discuss skeleton TR

- Discuss the performance metrics

- Discuss the evaluation assumptions based on the assumptions for channel model calibration for UAV sensing targets in Rel-19

- Discuss the possible measurements

- Capture the agreements into TR

RAN1 #122bis (October 2025)

- Conclude the evaluation assumptions

- Conclude a list of performance metrics, and if possible, the targeted KPI values

- Discuss the preliminary evaluation results with and without measurement quantization

- Continue discussion on the measurements

- Capture the agreements into TR

RAN1 #123 (November 2025)

- Continue discussion on the evaluation results with and without measurement quantization

- Finalize the KPI values if possible

- Finalize the list of measurements

- Capture the agreements into TR

RAN1 #124 (February 2026)

- Complete collection/observation on the evaluation results with and without measurement quantization

- Finalize the TR

Work plan in RAN3

In order to achieve the objectives specified in the SID [1] within the time budget, we propose the following work plan for discussion.

RAN3 #129bis (October 2025)

- Network architecture & general aspects (initial discussion):

  - Overall network architecture, e.g., direct or indirect connectivity.

  - CN-RAN interface and protocol.

- RAN-CN Procedures and Signalling (initial discussion):

  - Sensing procedures.

- TR Development

  - Endorse RAN3 TR skeleton.

  - Capture agreements, if any.

RAN3 #130 (November 2025)

- Network architecture & general aspects (consider SA2’s progress):

  - Continue discussion on the architecture and interface protocol option(s).

- RAN-CN Procedures and Signalling

  - Continue discussion on the details of sensing procedures and signalling, taking RAN1 progress into account.

- TR Development

  - Capture agreements, if any.

RAN3 #131 (February 2026)

- Network Architecture & general aspects (aligned with SA2 conclusion)

  - Continue discussion on the architecture and interface protocol option(s).

  - Evaluate the options, if needed.

  - Conclude on issues that are not controversial

- RAN-CN Procedures and Signalling

  - Continue discussion on the details of sensing procedures and signalling, taking RAN1 progress into account.

- TR Development

  - Capture agreements, if any.

RAN3 #131bis (April 2026)

- Network Architecture & general aspects

  - Conclude the RAN architecture and interface protocol.

- RAN-CN Procedures and Signalling

  - Conclude the sensing procedures and signalling. (Aligned with RAN1 conclusion)

- TR Development

  - Capture agreements.

RAN3 #132 (May 2026)

- Network Architecture & general aspects

  - Resolve leftover if any.

  - Conclude recommendations for TR.

- RAN-CN Procedures and Signalling

  - Resolve leftover if any.

  - Conclude recommendations for TR.

- TR Development

  - Capture agreements.

  - Formulate conclusions.

Conclusion

This contribution provides an initial work plan for the study on NR ISAC. It is proposed that RAN1/3 take the work plan as reference for the study in Rel-20.

- References

- RP-253246, Study on Integrated Sensing And Communication (ISAC) for NR (Revised), Xiaomi, CTC