## Slide 1: SA2 Work Planning
Andy Bennett
SA2 Chair
SA WG2 Meeting #172 Dallas
November 17 – November 21, 2025

## Slide 2: SA2 and SA meeting dates for 2025 and 2026
Q4 2025 | SA2#171 | Monday, October 13, 2025 | Friday, October 17, 2025 | Wuhan, China
 | SA2#172 | Monday, November 17, 2025 | Friday, November 21, 2025 | Dallas, USA
 | SA#110 | Tuesday, December 09, 2025 | Friday, December 12, 2025 | Baltimore, USA
Q1 2026 | SA2#173 | Monday, February 09 , 2026 | Friday, February 13, 2026 | Goa, India
 | SA#111 | Tuesday, March 10, 2026 | Friday, March 13, 2026 | Fukuoka, Japan
Q2 2026 | SA2#174 | Monday, April 13, 2026 | Friday, April 17, 2026 | Europe
 | SA2#175 | Monday, May 18, 2026 | Friday, May 22, 2026 | China
 | SA#112 | Tuesday, June 09, 2026 | Friday, June 12, 2026 | Singapore
Q3 2026 | SA2#176 | Monday, August 24, 2026 | Friday, August 28, 2026 | Prague, Czech Republic
 | SA#113 | Tuesday, September 15, 2026 | Friday, September 18, 2026 | Madrid, Spain
Q4 2026 | SA2#177 | Monday, October 12, 2026 | Friday, October 16, 2026 | Prague, Czech Republic
 | SA2#178 | Monday, November 16, 2026 | Friday, November 20, 2026 | Calgary, Canada
 | SA#114 | Tuesday, December 08, 2026 | Friday, December 11, 2026 | Boston, USA

## Slide 3: Rel-20 planning – 5G Advanced
Stage-2 freeze
  Jun 2026 (>=80%)
  Sep 2026 (100%)
Study Item deadlines
Study deadline A applies to FS_5GSAT_Ph4_ARC, FS_Sensing_ARC, FS_AIML_CN_Ph2 and FS_EnergySys_Ph2
Study deadline B applies to FS_AmbientIoT_Ph2_ARC, FS_NG_RTC_Ph3_ARC and FS_SMS2EC_ARC
No exceptions are expected to the Stage 2 100% freeze as Stage 3 group require sufficient time for their work
This means it is essential that normative work starts promptly after the respective study deadlines
 | 2025 | 2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
 | Apr #168 Goteborg | May #170 Fukuoka | Aug #170 Goteborg | Oct #171 China | Nov #172 Dallas | Feb #173 India | Apr #174 EU | May #175 China | Aug #176 EU
 |  |  |  |  | Study deadline A | Study deadline B |  | Stage 2 80% | Stage 2 100%

## Slide 4: Rel-20 planning – 5G Advanced
In this (November 2025) meeting
  The FS_5GSAT_Ph4_ARC, FS_Sensing_ARC, FS_AIML_CN_Ph2 and FS_EnergySys_Ph2 studies are due to complete
  Need to determine the status of these studies
  Discuss and approve WID’s based on the conclusions
  Discuss how to handle aspects that do not have conclusions
In the Goa (February 2025) meeting
  The FS_AmbientIoT_Ph2_ARC, FS_NG_RTC_Ph3_ARC and FS_SMS2EC_ARC studies are due to complete
  Need to determine the status of these studies
  Discuss and approve WID’s based on the conclusions
  Discuss how to handle aspects that do not have conclusions
  Any study work on the FS_5GSAT_Ph4_ARC, FS_Sensing_ARC, FS_AIML_CN_Ph2 and FS_EnergySys_Ph2 studies continued after November (see above) needs to be complete and the WID(s) updated based on these

## Slide 5: Rel-20 planning – 6G
Previously endorsed high level plan
  SA2#170 August 2025
    Input papers to provide justification and clarification of Work Task scope
    During the meeting assess for each WT whether Key Issue submission can start in the next meeting
      (Drafting of Key Issues during the meeting is not precluded)
    Document agreed Work Task scope updates in an annex of the TR
    Input papers on architectural assumptions and principles, with a focus on WT’s in August
  SA2#171 October 2025
    Start Key Issue discussions for Work Tasks identified in previous meeting
    For the Work Tasks not identified in previous meeting as ready for Key Issues, continue 1. 2. and 3. above
    Input papers on architectural assumptions and principles
  SA2#172 November 2025
    Continue as in SA2#171 for Work Tasks and Key Issues
    Completion of Key Issues, Arch assumptions and principles is in general targeted for the end of this meeting unless there are dependencies on other WG’s
    Update Study Item Description with updated Work Task descriptions from the TR annex
    Add TU estimates and completion date to the SID
    Input papers on architectural assumptions and principles

## Slide 6: Rel-20 planning – 6G
At some point it is expected that some 6G topics will need to be scheduled in parallel with other 6G topics
This need not happen for the February meeting (SA2#173 Goa)
At that meeting we will discuss whether, and what, topics can be scheduled in parallel in future meetings
There would still be at least two 6G sessions per meeting scheduled as a single stream
  For example, to handle topics that have significant dependencies on them and to allow for cross-topic issue resolution

## Slide 7: Rel-20 planning – TEI20
12 TU’s are proposed for handling TEI20 items
Items filling 7.5 TU’s have already been approved by SA Plenary
Items filling up to 4.5 TU’s will be discussed in February 2026
Items noted in August 2025 are not encouraged to be re-submitted in February 2026
Meeting by meeting plan:
2025 | 2025 | 2025 | 2025 | 2026 | 2026 | 2026 | 2026
May #170 Fukuoka | Aug #170 Goteborg | Oct #171 China | Nov #172 Dallas | Feb #173 Goa | Apr #174 EU | May #175 China | Aug #176 EU
 |  |  |  |  |  | Stage 2 80% | Stage 2 100%
Proposals for information | Proposals for SA2 approval |  | Proposals for information | Proposals for SA2 approval |  |  | 
 |  | Approved items on agenda | Approved items on agenda | Approved items on agenda | Approved items on agenda | Approved items on agenda | Approved items on agenda

## Slide 8: Making use of January 2026
No SA2 meeting has been scheduled for January 2026
Proposal (for discussion)
  Rapporteurs of Rel-20 study and work items to prepare agenda(s) for a conference call during the first 3 weeks, with email discussion also encouraged
    The 6G study can have more than one CC
  Rapporteurs of Rel-19 items (maintenance) to identify a few key topics for email discussion and for a conference call if needed
  Email discussions to take place on the DISCUSSIONS email
05 – 09 Jan | 12 – 16 Jan | 19 – 23 Jan | 26 – 30 Jan | 02 – 06 Feb | 09 – 13 Feb
 |  |  | Submission deadline 30 Jan |  | SA2#173
Conference calls (starting 07 Jan?) | Conference calls | Conference calls | Conference calls (except 30 Jan) | Post-deadline conference calls | 

## Slide 9: Upcoming meetings

## Slide 10
SA2#173 (Goa) Dates/Agenda
SA2#173 will be a F2F ordinary meeting
Preliminary Agenda (subjected to changes):
  AI 4.1: Incoming LSs on all agenda items
  Maintenance: 5.x, 6.x, 7.x, 8.x, 9.x
    Quota limited: 2 per company per AI
  AI 19.X: Rel-19 maintenance
    Quota limited: 4 per company per AI
  AI 20.X: Approved WIDs and SIDs (including TEI20 items already approved)
  TEI20 proposals for approval
Doc request deadline | Friday 30 January 2026 |  | 2359 UTC
Doc submission deadline | Friday 30 January 2026 |  | 2359 UTC
Registration | Monday 02 February 2026 |  | 0800 UTC
Start of meeting | Monday 09 February 2026 | 0900 Local time | 0430 UTC
Close of meeting | Friday 13 February 2026 | 1630 Local time (or earlier) | 1200 UTC
Upload approved documents | Friday 13 February 2026 | 1730 Local time | 1300 UTC
  Email Approval may be scheduled immediately after the meeting, only if it becomes really necessary. Further details on email approval such as TDoc list, date/timings will be decided during the meeting