Source:	Working Methods Convenor (Editor of Trial sections)

Title:	Structure and Workplan of Trial sections

Agenda item:	5.5

| Decision | X |
| --- | --- |
| Discussion |  |
| Information |  |

Document for:

# 1	Introduction

As discussed in the initial 3GPP OP MHSG call, here are a proposed template and a workplan for the discussions related to the Trial proposals. It is aimed as a placeholder for future contributions.

# 2	Proposed Workplan

Based on the master time plan endorsed at the initial OP MHSG call, the following workplan is proposed for Service Level related contributions:

| Meeting # | Date | Time (KST) | Actions specific for Trial related sections | Remarks |
| --- | --- | --- | --- | --- |
| 1 | 16 Oct. | 21:00 - 23:00 (12:00 - 14:00 UTC) | TR skeleton approved and the editor for each section endorsed | Completed |
| 2 | 30 Oct. | 14:00 - 16:00 (05:00 - 07:00 UTC) | Provide the goals of the trial in section 4.5 |  |
| 3 | 13 Nov. | 05:00 - 07:00 (20:00 - 22:00 UTC) |  |  |
| 4 | 27 Nov. | 21:00 - 23:00 | Introduce trial proposals into section 5.5 |  |
| 5 (F2F) | 8 Dec. | 15:00 - 17:00 |  | TSG #86 (Sitges) |
| 6 | 18 Dec. | 12:00 - 14:00 |  |  |
| 7 | 8 Jan. | 05:00 - 07:00 | Eva;uate tril proposals into section 6.5 |  |
| 8 | 22 Jan. | 21:00 - 23:00 |  |  |
| 9 | 5 Feb. | 12:00 - 14:00 |  |  |
| 10 | 19 Feb. | 05:00 - 07:00 | Conclusion and recommendations in Section 7.5 |  |
| 11 | 4 March | 21:00 - 23:00 |  |  |
| 12 (F2F) | 15 March | 15:00 - 17:00 |  | TSG #87 (Jeju) |
| 13 | 25 March | 12:00 - 14:00 | Correction and modification (If necessary) |  |
| - | 31 March |  | Submission to OP #43 |  |

# 3	Proposed Structure

Here are the proposed modifications of the document skeletons with revision marks:

* * * First Change * * * *

## 4.5	Requirements for Trial Proposals Improvements

## Editor’s Note: It is assumed that the trial (if done) will address issues that affect the meetings such as service level or the funding model.

## 4.5.1 	Goals for the Meeting Trial

Editor’s Note: This will describe what the trial is intended to accomplish (e.g., verify the feasibility of a proposal, work out the mechanics and details of a proposal, collect statistics on delegate behaviour under the proposal)

* * * Next Change * * * *

## 5.5	Proposals for a 3GPP Meeting Trial

### 5.5.0	Proposal for No Trial

Editor’s Note: This provides the possibility of not running a trial, but instead to just go ahead and implement the agreed proposals.

### 5.5.1	Proposed for Trial Tx

Editor’s Note: This provides a proposal for a trial at a specific meeting X.   It will describe either any aspects of the agreed proposals that are to be tested.

* * * Next Change * * * *

## 6.5	Evaluation of 3GPP Meeting Trial Proposals

### 6.5.0	Evaluation of Proposal for No Trial

Editor’s Note: Describe risks and advantages associated with not performing a trial

### 6.5.1	Evaluation of Proposal Tx

Editor’s Note: Describe what is to be accomplished under Trial Tx

* * * Next Change * * * *

## 7.5	Conclusions to 3GPP Meeting Trial Proposals

Editor’s Note: Proposed conclusions regarding the trial are described here.

* * * End of Change * * * *