## Sheet1
Rel-12 and before incomplete items
Keys:
Red: level of completion between 0 and 49%
Orange: level of completion between 50 and 79%
Yellow: level of completion between 80 and 99%
ID | Unique_ID | Name | Acronym | Outline_Level | Release | Resource_Names | Start_Date | Finish_Date | Percent_Complete | Hyperlink | WI_rapporteur_e_mail | Last_update | Notes
327 | 1012 | Release 12 Features | - | 1 | Rel-12 | SP;CP;RP;GP | 2013-10-14 08:00 | 2014-12-12 17:00 | 65% | - | - | 2014-09-17 08:00 | -
382 | 530042 | IMS-based Telepresence | IMS_TELEP | 1 | Rel-12 | S1;C1;C3;C4;IETF | 2010-03-22 13:00 | 2014-12-09 17:00 | 60% | SP-110588 | Orange | 2012-06-08 08:00 | This feature does not introduce any changes to the IMS architecture, and no stage 2 impacts are identified
384 | 580001 | CT part for IMS Telepresence (Stage 2/3) | IMS_TELEP | 2 | Rel-12 | C1;C3;C4;IETF | 2010-03-22 13:00 | 2014-12-09 17:00 | 59% | CP-140624 | Huawei | 2014-09-06 08:00 | CP#65 updated WID CP-140196=>CP-140624
387 | 641001 | (IETF) CT1 part of IMS Telepresence (mmusic-sctp-sdp) | IMS_TELEP | 3 | Rel-12 | C1-IETF | 2010-03-22 13:00 | 2014-12-09 17:00 | 50% | CP-140624 | christer.holmberg@ericsson.com | 2014-09-02 08:00 | work in progress
388 | 641002 | (IETF) CT1 part of IMS Telepresence (clue-framework ) | IMS_TELEP | 3 | Rel-12 | C1-IETF | 2010-03-22 13:00 | 2014-12-09 17:00 | 50% | CP-140624 | christer.holmberg@ericsson.com | 2014-09-02 08:00 | work in progress
389 | 641003 | (IETF) CT1 part of IMS Telepresence (clue-datachannel) | IMS_TELEP | 3 | Rel-12 | C1-IETF | 2010-03-22 13:00 | 2014-12-09 17:00 | 50% | CP-140624 | christer.holmberg@ericsson.com | 2014-09-02 08:00 | work in progress
390 | 641004 | (IETF) CT1 part of IMS Telepresence (clue-signaling) | IMS_TELEP | 3 | Rel-12 | C1-IETF | 2010-03-22 13:00 | 2014-12-09 17:00 | 50% | CP-140624 | christer.holmberg@ericsson.com | 2014-09-02 08:00 | work in progress
391 | 641005 | (IETF) CT1 part of IMS Telepresence (clue-data-model-schema) | IMS_TELEP | 3 | Rel-12 | C1-IETF | 2010-03-22 13:00 | 2014-12-09 17:00 | 50% | CP-140624 | christer.holmberg@ericsson.com | 2014-09-02 08:00 | work in progress
393 | 610011 | CT4 part of IMS Telepresence (Stage 2/3) | IMS_TELEP | 3 | Rel-12 | C4 | 2013-09-13 08:00 | 2014-12-09 17:00 | 0% | CP-140624 | Huawei | 2014-09-06 08:00 | CP#65 updated WID CP-140196=>CP-140624. Completion 09/14=>12/14. Exception in CP-140477
394 | 560020 | Group Communication System Enablers for LTE | GCSE_LTE | 1 | Rel-12 | S1;S2;S3;C3;C4;R3;C1 | 2012-06-18 08:00 | 2014-12-11 17:00 | 94% | SP-140433 | Nokia Networks | 2014-09-07 08:00 | Linked to Rel-12 FS_ProSe TR 22.803 Study on Proximity-based Services. External requirements: NIST, MESA, APCO Global Alliance, TCCA. Specify 3GPP system enablers to support group communication over LTE for Public Safety
404 | 640037 | Group Call eMBMS congestion management for LTE | GCSE_LTE-MBMS_CM | 2 | Rel-12 | R3 | 2014-06-16 08:00 | 2014-12-11 17:00 | 25% | RP-141035 | Alcatel-Lucent | 2014-09-09 08:00 | -
405 | 640137 | Core part: Group Call eMBMS congestion management for LTE | GCSE_LTE-MBMS_CM-Core | 3 | Rel-12 | R3 | 2014-06-16 08:00 | 2014-12-11 17:00 | 25% | RP-141035 | Alcatel-Lucent | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14. Exception in RP-141441
406 | 560022 | Machine-Type and other mobile data applications Communications enhancements | MTCe | 1 | Rel-12 | S2;S1;S3;C1;C3;C4;C6;R2;R3;G1 | 2009-12-10 08:00 | 2014-12-09 17:00 | 99% | SP-130327 | Intel | 2013-11-28 08:00 | -
418 | 560322 | BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP | 2 | Rel-12 | S2;C1;C4;C6;G1 | 2012-06-18 08:00 | 2014-12-09 17:00 | 98% | SP-120442 | Ericsson | 2013-11-28 08:00 | -
421 | 620007 | Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP-CT | 3 | Rel-12 | C1;C4;C6 | 2013-12-06 08:00 | 2014-12-09 17:00 | 96% | CP-130714 | Ericsson | 2013-11-18 08:00 | -
424 | 620307 | CT6 part of Stage 3 for BB3: UE Power Consumptions Optimizations (UEPCOP) | MTCe-UEPCOP-CT | 4 | Rel-12 | C6 | 2013-12-09 08:00 | 2014-12-09 17:00 | 90% | CP-130714 | Ericsson | 2014-09-16 08:00 | CP#65 completion 09/14=>12/14. Exception in CP-140697
429 | 560024 | Policy and Charging Control for supporting fixed broadband access networks | P4C | 1 | Rel-12 | S2;S1;S5;C3;C1;C4 | 2012-06-20 08:00 | 2014-12-12 17:00 | 99% | SP-120443 | Huawei | 2013-01-08 08:00 | Linked to BBF, IETF work. SP#58 stopped BB3 to BB6. Split BB1 and BB2 into TR and Stage 2 work
431 | 560124 | BB1: Policy and Charging Control for supporting traffic from fixed terminals and NSWO (Non Seamless WLAN Offload) traffic from 3GPP UEs in fixed broadband access networks (P4C-F) | P4C-F | 2 | Rel-12 | S2;S5;C3;C1;C4 | 2012-06-20 08:00 | 2014-12-12 17:00 | 99% | SP-120275 | Huawei | 2013-01-08 08:00 | -
447 | 560025 | IMS Business Trunking for IP-PBX in Static Mode of Operation | BusTI | 1 | Rel-12 | S2;S1;C1;C3 | 2011-09-28 16:12 | 2014-12-09 17:00 | 99% | SP-120862 | Deutsche Telekom | 2012-12-10 08:00 | Linked to Rel-11 IPXS Feature UID_470051 Advanced IP Interconnection of Services. This WI defines a generic framework for interconnecting with any type of IMS based network including IP-PBXs.
451 | 610007 | CT aspects of IMS Business Trunking for IP-PBX in Static Mode of Operation (Stage 3) | BusTI-CT | 2 | Rel-12 | C1;C3 | 2013-09-06 08:00 | 2014-12-09 17:00 | 99% | CP-140197 | Deutsche Telekom | 2014-03-03 08:00 | -
465 | 580059 | Proximity-based Services | ProSe | 1 | Rel-12 | S1;S2;S3;C1;C3;C4;C6;R1;R2;R4;S5;IETF | 2012-12-13 08:00 | 2015-06-12 17:00 | 84% | SP-140574 | Qualcomm | 2014-09-15 08:00 | SP#65 SA3 updated the SA-wide WID SP-140300=>SP-140574 (Moved the TR phase to Rel-13 as a stand-alone Study). Triggered by Rel-12 TR 22.803 Study on Proximity-based Services (FS_ProSe) UID_530044
469 | 590036 | Security for Proximity-based Services | ProSe | 2 | Rel-12 | S3 | 2013-03-13 08:00 | 2014-12-12 17:00 | 90% | SP-140574 | Qualcomm | 2014-09-15 08:00 | SP#65 re-opened. Completion 06/14=>12/14. Exception in SP-140584. Updated WID SP-140300=>SP-140574 (Moved the TR phase to Rel-13 as a stand-alone Study). SP#64 completed. TS 33.303 v100 for 1-step Approval
470 | 651104 | (IETF) Security for Proximity-based Services (ietf-avtcore-srtp-aes-gcm) | ProSe | 2 | Rel-12 | S3-IETF | 2014-09-12 08:00 | 2014-12-09 17:00 | 75% | SP-140574 | Atle Monrad | 2014-09-15 08:00 | Submitted to IESG for publication
471 | 640039 | Charging Aspects of Proximity-based Services | ProSe-CH | 2 | Rel-12 | S5 | 2014-06-19 08:00 | 2015-03-13 17:00 | 85% | SP-140401 | Qualcomm | 2014-09-10 08:00 | SP#65 exception in SP-140543
473 | 640239 | Specification of Charging Aspects of Proximity-based Services | ProSe-CH | 3 | Rel-12 | S5 | 2014-06-19 08:00 | 2015-03-13 17:00 | 75% | SP-140401 | Qualcomm | 2014-12-03 08:00 | SP#65 completion 09/14=>12/14. Exception in SP-140543. SP#65 TR 32.277v100 for Information. LM: CD: 09/14->03/15, 40->75%
474 | 630006 | CT aspects of Proximity-based Services (Stage 3) | ProSe-CT | 2 | Rel-12 | C1;C3;C4;C6 | 2014-03-05 08:00 | 2014-12-09 17:00 | 99% | CP-140290 | Qualcomm | 2014-03-03 08:00 | CP#64 updated WID CP-140194=>CP-140290
479 | 630030 | LTE Device to Device Proximity Services | LTE_D2D_Prox | 2 | Rel-12 | R1;R2;R4 | 2014-03-11 08:00 | 2015-06-12 17:00 | 21% | RP-140955 | Qualcomm | 2014-09-09 08:00 | follow-up of TR 36.843 FS_LTE_D2D_Prox
480 | 630130 | Core part: LTE Device to Device Proximity Services | LTE_D2D_Prox-Core | 3 | Rel-12 | R1;R2;R4 | 2014-07-11 10:40 | 2014-12-11 17:00 | 84% | RP-140955 | Qualcomm | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14. Exception in RP-141704
481 | 630230 | Perf. part: LTE Device to Device Proximity Services | LTE_D2D_Prox-Perf | 3 | Rel-12 | R4 | 2014-03-11 08:00 | 2015-06-12 17:00 | 0% | RP-140955 | Qualcomm | 2014-09-09 08:00 | RP#65 completion 12/14=>06/15
482 | 580062 | Web Real Time Communication access to IMS | IMS_WebRTC | 1 | Rel-12 | S1;S2;S3 | 2012-12-14 08:00 | 2014-12-12 17:00 | 78% | SP-130707 | China Mobile | 2013-09-09 08:00 | IETF RTCWEB and W3C WEBRTC groups are specifying a browser-based client to support communication services. Interoperability for WebRTC clients to access 3GPP IMS is needed.
486 | 631001 | (IETF) Web Real Time Communication access to IMS (rtcweb-overview) | IMS_WebRTC | 2 | Rel-12 | S2-IETF | 2013-06-19 08:00 | 2014-12-12 17:00 | 50% | SP-130707 | Uwe Rauschenbach | 2014-06-06 08:00 | In WGLC
489 | 630003 | CT aspects of Web Real Time Communication (WebRTC) Access to IMS | IMS_WebRTC-CT | 2 | Rel-12 | C1;C4;IETF | 2014-03-05 08:00 | 2014-12-09 17:00 | 70% | CP-140192 | China Mobile | 2014-09-06 08:00 | -
490 | 630103 | CT1 part of CT aspects of Web Real Time Communication (WebRTC) Access to IMS | IMS_WebRTC-CT | 3 | Rel-12 | C1 | 2014-03-05 08:00 | 2014-12-09 17:00 | 90% | CP-140192 | China Mobile | 2014-12-04 08:00 | CP#65 TS 24.371v100 for Information. Completion 09/14=>12/14. Exception in CP-140621. LM: 70->90%
491 | 641006 | (IETF) Web Real Time Communication access to IMS (rtcweb-data-channel) | IMS_WebRTC-CT | 3 | Rel-12 | C1-IETF | 2014-03-06 08:00 | 2014-12-09 17:00 | 90% | CP-140192 | christer.holmberg@ericsson.com | 2014-09-06 08:00 | Submitted to IESG for publication
492 | 641007 | (IETF) Web Real Time Communication access to IMS (rtcweb-stun-consent-freshness) | IMS_WebRTC-CT | 3 | Rel-12 | C1-IETF | 2014-03-06 08:00 | 2014-12-09 17:00 | 50% | CP-140192 | christer.holmberg@ericsson.com | 2014-09-06 08:00 | work in progress
493 | 651001 | (IETF) Web Real Time Communication access to IMS (draft-yusef-sipcore-sip-oauth) | IMS_WebRTC-CT | 3 | Rel-12 | C1-IETF | 2014-09-12 08:00 | 2014-12-09 17:00 | 25% | CP-140192 | christer.holmberg@ericsson.com | 2014-09-06 08:00 | work in progress
494 | 660031 | (IETF) Web Real Time Communication access to IMS (draft-holmberg-sipcore-auth-id) | IMS_WebRTC-CT | 3 | Rel-12 | C1-IETF | 2014-09-12 08:00 | 2014-12-09 17:00 | 25% |  | christer.holmberg@ericsson.com | 2014-12-04 08:00
495 | 630203 | CT4 part of CT aspects of Web Real Time Communication (WebRTC) Access to IMS | IMS_WebRTC-CT | 3 | Rel-12 | C4 | 2014-03-05 08:00 | 2014-12-09 17:00 | 80% | CP-140192 | China Mobile | 2014-12-04 08:00 | CP#65 completion 09/14=>12/14. Exception in CP-140732. LM: 30->80%
503 | 610038 | Enhanced S2a Mobility Over trusted WLAN access to EPC | eSaMOG | 1 | Rel-12 | S2;C1;C4 | 2013-09-09 08:00 | 2014-12-09 17:00 | 99% | SP-130391 | ZTE | 2013-09-09 08:00 | -
505 | 610009 | Stage 3 for Enhanced S2a Mobility Over trusted WLAN access to EPC | eSaMOG-St3 | 2 | Rel-12 | C1;C4 | 2013-09-09 08:00 | 2014-12-09 17:00 | 99% | CP-130715 | ZTE | 2013-11-28 08:00 | CP#62 updated WID CP-130580=>CP-130715
533 | 560030 | Extended IMS media plane security features | eMEDIASEC | 1 | Rel-12 | S3;C4;C1;C3;IETF | 2012-06-20 08:00 | 2014-12-09 17:00 | 99% | SP-120447 | Vodafone | 2013-02-19 08:00 | Triggered by Rel-11 TR 33.829 Study on Extended IMS media plane security features (FS_eMEDIASEC)
536 | 580005 | CT aspects of Extended IMS media plane security features (Stage 2/3) | eMEDIASEC-CT | 2 | Rel-12 | C4;C1;C3;IETF | 2012-12-13 08:00 | 2014-12-09 17:00 | 99% | CP-130597 | Alcatel-Lucent | 2013-11-19 08:00 | -
540 | 641009 | (IETF) CT4 part of Extended IMS media plane security features (draft-schwarz-mmusic-sdp-for-gw) | eMEDIASEC-CT | 3 | Rel-12 | C4-IETF | 2014-06-12 08:00 | 2014-12-09 17:00 | 75% | CP-130597 | christer.holmberg@ericsson.com | 2014-09-02 08:00 | Work in progress
544 | 570032 | Lawful Interception in the 3GPP Rel-12 | LI12 | 1 | Rel-12 | S3 | 2012-09-17 08:00 | 2014-12-12 17:00 | 75% | SP-130650 | PIDS, Alcatel-Lucent | 2014-06-09 08:00 | -
549 | 470030 | Codec for Enhanced Voice Services | EVS_codec | 1 | Rel-12 | S4;S1;C4;C1;C3 | 2010-03-25 08:00 | 2014-12-12 17:00 | 93% | SP-140151 | Huawei | 2014-02-27 08:00 | Triggered by UID_370045 Study on enhanced voice service requirements for EPS (TR 22.813)
551 | 470032 | Stage 2/3 for Codec for Enhanced Voice Services | EVS_codec | 2 | Rel-12 | S4 | 2010-03-25 08:00 | 2014-12-12 17:00 | 95% | SP-140151 | Huawei | 2014-12-03 08:00 | SP#65 completion 09/14=>12/14. Exception in SP-140467. TS 26.441v200 for Approval. TSs 26.442/44/45/46/47/48/49/50/51v100 for 1-step Approval. Ongoing TS 26.443 EVS Codec ANSI C code (floating point). LM: 90->95
552 | 470132 | TR on Performance characterization of Codec for Enhanced Voice Services | EVS_codec | 2 | Rel-12 | S4 | 2010-03-25 08:00 | 2014-12-12 17:00 | 90% | SP-140151 | Huawei | 2014-09-02 08:00 | SP#65 completion 09/14=>12/14. Ongoing TR 26.952 EVS Codec Performance Characterization. Exception in SP-140467
563 | 570033 | High Efficiency Video Coding | HEVC | 1 | Rel-12 | S4;IETF | 2012-09-12 08:00 | 2014-12-05 17:00 | 81% | SP-130569 | Qualcomm | 2014-04-16 08:00 | Specify the support of HEVC in 3GPP services (PSS, DASH, MTSI, MMS, MBMS, IMS Messaging and Presence)
566 | 631002 | (IETF) High Efficiency Video Coding | HEVC | 2 | Rel-12 | S4-IETF | 2012-09-17 08:00 | 2014-12-05 17:00 | 50% | SP-130569 | Thomas Stockhammer | 2014-02-19 08:00 | Submitted to IESG for publication
571 | 580067 | Acoustic Requirements and Test methods for IMS-based conversational speech services over LTE | ART_LTE | 1 | Rel-12 | S4 | 2012-12-12 08:00 | 2014-12-12 17:00 | 99% | SP-120769 | Qualcomm | 2013-04-19 08:00 | Triggered by Rel-12 Feature Codec for Enhanced Voice Services (EVS_codec) UID_470030. Need for super wideband acoustic requirements and test methods
583 | 560031 | Rel-12 Operations, Administration, Maintenance and Provisioning (OAM&P) | OAM12 | 1 | Rel-12 | S5 | 2011-09-21 08:00 | 2014-12-12 17:00 | 99% | - | - | 2012-04-18 08:00 | OAM12 is an umbrella Feature for changes that are not part of any other dedicated feature/WI
592 | 580053 | Rel-12 Network Infrastructure Management | OAM12-NIM | 2 | Rel-12 | S5 | 2013-12-11 08:00 | 2014-12-12 17:00 | 99% | - | - | 2012-11-19 08:00 | -
619 | 580013 | IMS Stage 3 IETF Protocol Alignment - phase 6 | IMSProtoc6 | 1 | Rel-12 | C1;C3;IETF | 2012-12-07 08:00 | 2014-12-09 17:00 | 67% | CP-120905 | Alcatel-Lucent | 2012-12-06 08:00 | -
621 | 601002 | (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (holmberg-sipcore-received-realm) | IMSProtoc6 | 2 | Rel-12 | C1-IETF | 2013-05-21 08:00 | 2014-12-09 17:00 | 50% | CP-120905 | christer.holmberg@ericsson.com | 2014-06-03 08:00 | Not completed internet-draft
622 | 651002 | (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (allen-sipcore-sip-tree-cap-indicators) | IMSProtoc6 | 2 | Rel-12 | C1-IETF | 2014-09-12 08:00 | 2014-12-09 17:00 | 25% | CP-120905 | christer.holmberg@ericsson.com | 2014-09-02 08:00 | Not completed internet-draft
623 | 660038 | (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-ietf-insipid-session-id) | IMSProtoc6 | 2 | Rel-12 | C1-IETF | 2014-09-12 08:00 | 2014-12-09 17:00 | 25% |  | christer.holmberg@ericsson.com | 2014-12-04 08:00 | work in progress
625 | 611001 | (IETF) CT3 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (holmberg-sipcore-received-realm) | IMSProtoc6 | 2 | Rel-12 | C3-IETF | 2013-09-06 08:00 | 2014-12-05 17:00 | 50% | CP-120905 | christer.holmberg@ericsson.com | 2014-06-03 08:00 | Not completed internet-draft
664 | 610008 | Updating IMS to conform to RFC 6665 (Stage 3) | UP6665 | 1 | Rel-12 | C1;C3 | 2013-09-09 08:00 | 2014-12-09 17:00 | 97% | CP-130717 | BlackBerry | 2013-09-09 08:00 | Stage 3. Review the references related to RFC 3265 in the 3GPP IMS specifications and determine the impact of the RFC 6665 changes
665 | 610108 | CT1 part of Updating IMS to conform to RFC 6665 | UP6665 | 2 | Rel-12 | C1 | 2013-09-09 08:00 | 2014-12-09 17:00 | 96% | CP-130717 | BlackBerry | 2014-09-06 08:00 | CP#65 completion 09/14=>12/14. Exception in CP-140620
670 | 620006 | Signalling Improvements for Network Efficiency (Stage 3) | SINE | 1 | Rel-12 | C1 | 2013-12-06 08:00 | 2014-12-09 17:00 | 85% | CP-130713 | Huawei | 2014-12-04 08:00 | CP#65 completion 09/14=>12/14. Exception in CP-140617.LM: 80->85%
674 | 630005 | Transfer of ETSI business trunking specifications | IMS_Corp2 | 1 | Rel-12 | C1;S1 | 2014-03-05 08:00 | 2014-12-09 17:00 | 99% | SP-140170 | Alcatel-Lucent | 2014-03-07 08:00 | Rel-12 enhancements to business trunking (BusTI). ETSI E2NA(14)000019 asked 3GPP to take responsibility of business communications over IMS: TS 181 019, TS 182 023, TS 182 024, TS 182 025, TR 183 060
677 | 630007 | IMS Signalling Activated Trace | ISAT | 1 | Rel-12 | C1;C3;C4;IETF | 2014-03-05 08:00 | 2014-12-09 17:00 | 29% | CP-140195 | Vodafone | 2014-03-03 08:00 | Linked to Rel-8 OAM8-Trace. Update interface protocols to include the procedures defined in SA5 TS 32.422 for trace activation, and for conveying a signalling activated tracing indicator.
678 | 630107 | CT1 part of IMS Signalling Activated Trace | ISAT | 2 | Rel-12 | C1 | 2014-03-10 08:00 | 2014-12-09 17:00 | 0% | CP-140195 | Vodafone | 2014-09-06 08:00 | CP#65 completion 09/14=>12/14. Exception in CP-140606
679 | 651003 | (IETF) IMS Signalling Activated Trace (draft-dawes-sipping-debug) | ISAT | 2 | Rel-12 | C1-IETF | 2014-09-12 08:00 | 2014-12-09 17:00 | 25% | CP-140195 | Vodafone | 2014-09-02 08:00 | Not completed internet-draft
680 | 651103 | (IETF) IMS Signalling Activated Trace (draft-dawes-sipping-debug) | ISAT | 2 | Rel-12 | C3-IETF | 2014-09-12 08:00 | 2014-12-09 17:00 | 25% | CP-140195 | Vodafone | 2014-09-02 08:00 | Not completed internet-draft
681 | 651203 | (IETF) IMS Signalling Activated Trace (draft-dawes-sipping-debug) | ISAT | 2 | Rel-12 | C4-IETF | 2014-09-12 08:00 | 2014-12-09 17:00 | 25% | CP-140195 | Vodafone | 2014-09-02 08:00 | Not completed internet-draft
682 | 630207 | CT3 part of IMS Signalling Activated Trace | ISAT | 2 | Rel-12 | C3 | 2014-03-10 08:00 | 2014-12-09 17:00 | 0% | CP-140195 | Vodafone | 2014-09-06 08:00 | CP#65 completion 09/14=>12/14. Exception in CP-140564
683 | 630307 | CT4 part of IMS Signalling Activated Trace | ISAT | 2 | Rel-12 | C4 | 2014-03-05 08:00 | 2014-12-09 17:00 | 90% | CP-140195 | Vodafone | 2014-09-06 08:00 | CP#65 completion 09/14=>12/14. Exception in CP-140480
688 | 640003 | Diameter Overload Control Mechanisms | DOCME | 1 | Rel-12 | C4;IETF | 2014-06-13 08:00 | 2014-12-09 17:00 | 75% | CP-140273 | Orange | 2014-06-16 08:00 | Triggered by TR 29.809 Study on Diameter overload control mechanism (FS_DOCME)
690 | 641010 | (IETF) Diameter Overload Control Mechanisms | DOCME | 2 | Rel-12 | C4-IETF | 2014-06-13 08:00 | 2014-12-09 17:00 | 50% | CP-140273 | christer.holmberg@ericsson.com | 2014-06-16 08:00 | work in progress
694 | 640007 | Indication of NNI Routeing scenarios in SIP requests | NNI_RS | 1 | Rel-12 | C1;C3;IETF | 2014-06-13 08:00 | 2014-12-09 17:00 | 84% | CP-140288 | Ericsson | 2014-04-07 08:00 | Triggered by TR 24.802 Study on Indication of Network to Network Interface (NNI) Routeing scenarios in SIP requests UID_580025
696 | 641008 | (IETF) CT1 part of Indication of NNI Routeing scenarios in SIP requests (holmberg-dispatch-iotl) | NNI_RS | 2 | Rel-12 | C1-IETF | 2014-06-13 08:00 | 2014-12-09 17:00 | 50% | CP-140288 | christer.holmberg@ericsson.com | 2014-06-06 08:00 | Publication requested
700 | 640011 | Overload Control for PCC based Diameter applications | DOCME-PCC | 1 | Rel-12 | C3;IETF | 2014-06-13 08:00 | 2014-12-09 17:00 | 67% | CP-140405 | Huawei | 2014-06-16 08:00 | Triggered by TR 29.809 Study on Diameter overload control mechanism (FS_DOCME)
702 | 641011 | (IETF) Overload Control for PCC based Diameter applications | DOCME-PCC | 2 | Rel-12 | C3-IETF | 2014-06-13 08:00 | 2014-12-09 17:00 | 50% | CP-140405 | christer.holmberg@ericsson.com | 2014-06-16 08:00 | work in progress
708 | 570002 | Downlink Multi Carrier GERAN | DMCG | 1 | Rel-12 | G2;G1;C1;G3new | 2012-09-10 08:00 | 2015-03-13 17:00 | 91% | GP-140190 | Ericsson | 2014-03-01 08:00 | Linked to Rel-7 Downlink Dual Carrier UID_50579 (Previous work on multiple carriers on the downlink was limited to two). Ref: TR 45.912 Feasibility study for evolved GERAN, TS 43.064 GPRS Stage 2
711 | 570302 | Test part: Downlink Multi Carrier GERAN | DMCG-MStest | 2 | Rel-12 | G3new | 2012-09-10 08:00 | 2015-03-13 17:00 | 80% | GP-120930 | ST-Ericsson | 2014-12-03 08:00 | GP#63 completion 08/14=>11/14. LM: 35->80%, CD:11/14->03/15
712 | 590033 | Mobile Station Receive Diversity (MSRD) for Voice Services over Adaptive Multi-user channels on One Slot (VAMOS) | MSRD_VAMOS | 1 | Rel-12 | G1;G2;C1;G3new | 2013-03-01 08:00 | 2014-11-21 17:00 | 99% | GP-130849 | Nokia Networks, Microsoft | 2014-08-29 08:00 | GP#63 completion 08/14=>11/14. Exception in GP-140579. Linked to Rel-7 Mobile Station Receive Diversity (DARP Phase II) UID_50569, Rel-9 Voice Services over Adaptive Multiuser channels on One Slot (VAMOS) UID_420002
716 | 620014 | New Training Sequence Codes (TSC) for GERAN | NewToN | 1 | Rel-12 | G1;G2;C1 | 2013-11-22 08:00 | 2014-12-09 17:00 | 76% | GP-131139 | Ericsson | 2014-05-27 08:00 | GP#63 completion 08/14=>11/14. Exception in GP-140542. GP#60 approved WID. Triggered by GP-131041, GP#40 GP-081949 (WID VAMOS). Linked to Rel-9 VAMOS (Previous work where new TSCs were defined for GMSK modulation) UID_420002
718 | 620214 | GERAN2 part of New Training Sequence Codes (TSC) for GERAN | NewToN | 2 | Rel-12 | G2 | 2013-11-22 08:00 | 2014-11-21 17:00 | 80% | GP-131139 | Ericsson | 2014-05-30 08:00 | GP#63 completion 08/14=>11/14. Exception in GP-140542.
719 | 620314 | CT1 part of New Training Sequence Codes (TSC) for GERAN (Stage 3) | NewToN | 2 | Rel-12 | C1 | 2013-11-22 08:00 | 2014-12-09 17:00 | 50% | GP-131139 | Ericsson | 2014-07-28 08:00 | CP#65 completion 09/14=>12/14. CP#65 exception in CP-140604.
724 | 580037 | LTE UE Total Radiated Power (TRP) and Total Radiated Sensitivity (TRS) and UTRA Hand Phantom related UE TRP and TRS Requirements | LTE_UTRA_TRP_TRS | 1 | Rel-12 | R4;R5 | 2013-03-15 08:00 | 2015-06-12 17:00 | 22% | RP-130703 | Nokia | 2014-09-15 08:00 | Triggered by Rel-11 TR 37.902 Study on Measurements of radio performances for LTE terminals - TRP and TRS test methodology (FS_LTE_OTA) UID_550022
725 | 580137 | Core part: LTE UE TRP and TRS and UTRA Hand Phantom related UE TRP and TRS Requirements | LTE_UTRA_TRP_TRS-Core | 2 | Rel-12 | R4 | 2013-03-15 08:00 | 2014-12-11 17:00 | 30% | RP-130703 | Nokia | 2014-09-15 08:00 | RP#65 completion 09/14=>12/14. Exception in RP-141161
726 | 630011 | Test part: LTE UE TRP and TRS and UTRA Hand Phantom | LTE_UTRA_TRP_TRS-UEConTest | 2 | Rel-12 | R5 | 2014-03-06 08:00 | 2015-06-12 17:00 | 10% | RP-140090 | ZTE | 2014-09-09 08:00 | -
727 | 590019 | Support for BeiDou Navigation Satellite System (BDS) for UTRA and LTE | LCS_BDS | 1 | Rel-12 | R2;R3;R4;R5 | 2013-03-04 08:00 | 2015-06-12 17:00 | 81% | RP-130416 | CATR | 2013-03-05 08:00 | BeiDou = Chinese Navigation Satellite System. Location Services (LCS) TS 22.071 Stage 1, TS 23.271 Stage 2
732 | 640013 | Test part: BeiDou Navigation Satellite System (BDS) Positioning Support for LTE and UMTS | LCS_BDS-UEConTest | 2 | Rel-12 | R5 | 2014-06-16 08:00 | 2015-06-12 17:00 | 5% | RP-140730 | CATT | 2014-09-09 08:00 | -
733 | 620011 | Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN | LCS_BDS_GERAN | 1 | Rel-12 | G2;G1;G3new | 2013-11-22 08:00 | 2015-03-13 17:00 | 93% | GP-140211 | ZTE | 2014-03-01 08:00 | GP#60 approved WID. Based on the same framework used in Rel-8 Support for Additional Navigation Satellite Systems (ANSS) for LCS UID_38001
736 | 630009 | Support for BeiDou Navigation Satellite System (BDS) for LCS in GERAN3new | LCS_BDS_GERAN-GERAN3new | 2 | Rel-12 | G3new | 2014-03-01 08:00 | 2015-03-13 17:00 | 80% | GP-140244 | CATR | 2014-08-29 08:00 | LM: 25->80%, CD: 11/14->03/15
738 | 590030 | Base Station (BS) RF requirements for Active Antenna System (AAS) | AAS_BS_LTE_UTRA | 1 | Rel-12 | R4 | 2013-03-04 08:00 | 2015-06-12 17:00 | 44% | RP-130373 | Huawei | 2014-09-15 08:00 | Triggered by Rel-12 TR 37.840 Study of RF and EMC Requirements for Active Antenna Array System BS (FS_AAS_BS_LTE_UTRA)
739 | 590130 | Core part: Base Station (BS) RF requirements for Active Antenna System (AAS) | AAS_BS_LTE_UTRA-Core | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-11 17:00 | 75% | RP-130373 | Huawei | 2014-09-15 08:00 | RP#65 completion 09/14=>12/14. Exception in RP-141713. TR 37.842v100 for Information
740 | 590230 | Perf. part: Base Station (BS) RF requirements for Active Antenna System (AAS) | AAS_BS_LTE_UTRA-Perf | 2 | Rel-12 | R4 | 2013-03-07 08:00 | 2015-06-12 17:00 | 20% | RP-130373 | Huawei | 2014-09-15 08:00 | RP#65 completion 12/14=>06/15
752 | 620042 | Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA | LTE_UTRA_IncMon | 1 | Rel-12 | R4;R2 | 2013-12-10 08:00 | 2015-06-18 17:00 | 28% | RP-132061 | Ericsson | 2014-09-09 08:00 | -
753 | 620142 | Core part: Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA | LTE_UTRA_IncMon-Core | 2 | Rel-12 | R4;R2 | 2013-12-10 08:00 | 2014-12-09 17:00 | 85% | RP-132061 | Ericsson | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14. Exception in RP-141601
754 | 620242 | Perf. part: Increasing the minimum number of carriers for UE monitoring in UTRA and E-UTRA | LTE_UTRA_IncMon-Perf | 2 | Rel-12 | R4 | 2013-12-12 08:00 | 2015-06-18 17:00 | 0% | RP-132061 | Ericsson | 2014-09-09 08:00 | RP#65 completion 12/14=>06/15
755 | 620048 | WLAN/3GPP Radio Interworking | UTRA_LTE_WLAN_interw | 1 | Rel-12 | R2;S2;C1;C4 | 2013-12-06 08:00 | 2014-12-09 17:00 | 97% | RP-140981 | Intel | 2013-12-09 08:00 | Triggered by Rel-12 TR 37.834 Study on WLAN/3GPP Radio Interworking (FS_UTRA_LTE_WLAN_interw)
758 | 640006 | CT aspects of WLAN/3GPP Radio Interworking (Stage 2/3) | UTRA_LTE_WLAN_interw-CT | 2 | Rel-12 | C1;C4 | 2014-09-09 08:00 | 2014-12-09 17:00 | 88% | CP-140623 | Alcatel-Lucent | 2014-09-09 08:00 | CP#65 revised WID CP-140287=>CP-140623 (added CT4 part)
759 | 640106 | CT1 part of CT aspects of WLAN/3GPP Radio Interworking (Stage 3) | UTRA_LTE_WLAN_interw-CT | 3 | Rel-12 | C1 | 2014-09-09 08:00 | 2014-12-09 17:00 | 78% | CP-140623 | Alcatel-Lucent | 2014-09-09 08:00 | CP#65 completion 09/14=>12/14. Exception in CP-140720
761 | 551000 | Rel-12 LTE Carrier Aggregation | LTE_CA_Rel-12 | 1 | Rel-12 | R4 | 2011-09-19 08:00 | 2015-03-12 17:00 | 88% | - | - | 2012-12-14 08:00 | LTE_CA_Rel-12
828 | 590029 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 | LTE_CA_2UL-A1 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-11 17:00 | 38% | RP-140475 | Huawei | 2014-09-09 08:00 | Inter-band CA 2UL
829 | 590129 | Core part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 | LTE_CA_2UL-A1-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-11 17:00 | 75% | RP-140475 | Huawei | 2014-09-09 08:00 | RP#65 excep RP-141242. Current CA (generic & band-specific) defined for inter-band CA with 1UL CC & 2 DL CCs. Work needed on band-specific basis for 2UL/2DL inter-band CA. 2UL inter-band CA WIs according to 5 CA classes A1 to A5 according to Operator need
830 | 590229 | Perf. part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A1 | LTE_CA_2UL-A1-Perf | 3 | Rel-12 | R4 | 2013-03-13 08:00 | 2014-12-11 17:00 | 0% | RP-140475 | Huawei | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14. Class A1: Low-high band combination without harmonic relation between bands or intermodulation problem
831 | 590028 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 | LTE_CA_2UL-A2 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-11 17:00 | 38% | RP-130327 | Qualcomm | 2014-09-09 08:00 | Inter-band CA 2UL
832 | 590128 | Core part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 | LTE_CA_2UL-A2-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-11 17:00 | 75% | RP-130327 | Qualcomm | 2014-09-09 08:00 | RP#65 excep RP-141430. Current CA (generic & band-specific) defined for inter-band CA with 1UL CC & 2 DL CCs. Work needed on band-specific basis for 2UL/2DL inter-band CA. 2UL inter-band CA WIs according to 5 CA classes A1 to A5 according to Operator need
833 | 590228 | Perf. part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A2 | LTE_CA_2UL-A2-Perf | 3 | Rel-12 | R4 | 2013-03-13 08:00 | 2014-12-11 17:00 | 0% | RP-130327 | Qualcomm | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14. Class A2: Low-high band combination with harmonic relation between bands
834 | 590023 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A3 | LTE_CA_2UL-A3 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-11 17:00 | 38% | RP-140853 | Ericsson | 2014-09-09 08:00 | Inter-band CA 2UL
835 | 590123 | Core part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A3 | LTE_CA_2UL-A3-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-11 17:00 | 75% | RP-140853 | Ericsson | 2014-09-09 08:00 | RP#65 exception in RP-141372. Current CA (generic&band-specific) for inter-band CA with 1UL CC&2 DL CCs. Work need on band-specific basis for 2UL/2DL inter-band CA. 2UL inter-band CA WIs according to 5 CA classes A1 to A5 according to Operator need
836 | 590223 | Perf. part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A3 | LTE_CA_2UL-A3-Perf | 3 | Rel-12 | R4 | 2013-03-13 08:00 | 2014-12-11 17:00 | 0% | RP-140853 | Ericsson | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14. Class A3: Low-low or high-high band combination without intermodulation problem (low order IM)
837 | 590031 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A4 | LTE_CA_2UL-A4 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-11 17:00 | 35% | RP-141160 | Nokia | 2014-09-09 08:00 | Inter-band CA 2UL. RP#65 updated WID RP-140476=>RP-141160.
838 | 590131 | Core part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A4 | LTE_CA_2UL-A4-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-11 17:00 | 70% | RP-141160 | Nokia | 2014-09-09 08:00 | RP#65 excep RP-141163. Current CA (generic & band-specific) defined for inter-band CA with 1UL CC & 2 DL CCs. Work needed on band-specific basis for 2UL/2DL inter-band CA. 2UL inter-band CA WIs according to 5 CA classes A1 to A5 according to Operator need
839 | 590231 | Perf. part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A4 | LTE_CA_2UL-A4-Perf | 3 | Rel-12 | R4 | 2013-03-13 08:00 | 2014-12-11 17:00 | 0% | RP-141160 | Nokia | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14. Class A4: Low-low, low-high or high-high band combination with intermodulation problem (low order IM)
840 | 590026 | LTE Advanced dual uplink inter-band Carrier Aggregation Class A5 | LTE_CA_2UL-A5 | 2 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-11 17:00 | 35% | RP-141195 | NTT DOCOMO | 2014-09-09 08:00 | Inter-band CA 2UL. RP#65 updated WID RP-131146=>RP-141195. Changed Rapp Renesas=>Broadcom=>NTT DOCOMO
841 | 590126 | Core part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A5 | LTE_CA_2UL-A5-Core | 3 | Rel-12 | R4 | 2013-03-04 08:00 | 2014-12-11 17:00 | 70% | RP-141195 | NTT DOCOMO | 2014-09-09 08:00 | RP#65 excep RP-141194. Current CA (generic & band-specific) defined for inter-band CA with 1UL CC & 2 DL CCs. Work needed on band-specific basis for 2UL/2DL inter-band CA. 2UL inter-band CA WIs according to 5 CA classes A1 to A5 according to Operator need
842 | 590226 | Perf. part: LTE Advanced dual uplink inter-band Carrier Aggregation Class A5 | LTE_CA_2UL-A5-Perf | 3 | Rel-12 | R4 | 2013-03-13 08:00 | 2014-12-11 17:00 | 0% | RP-141195 | NTT DOCOMO | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14. Class A5: Combinations not classified in A1-A4
846 | 600022 | LTE Advanced intra-band non-contiguous Carrier Aggregation: framework requirements for 2UL | LTE_CA_NC_2UL | 2 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-12-11 17:00 | 95% | RP-140267 | Nokia | 2014-09-09 08:00 | Intra-band non-contig. CA 2DL
847 | 600122 | Core part: LTE Advanced intra-band non-contiguous Carrier Aggregation: framework requirements for 2UL | LTE_CA_NC_2UL-Core | 3 | Rel-12 | R4 | 2013-06-18 08:00 | 2014-12-11 17:00 | 95% | RP-140267 | Nokia | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14. Exception in RP-141162
851 | 600024 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 for 2UL | LTE_CA_NC_B4_2UL | 2 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-12-11 17:00 | 45% | RP-131136 | T-Mobile USA | 2014-09-09 08:00 | Intra-band non-contig. CA 2DL
852 | 600124 | Core part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 for 2UL | LTE_CA_NC_B4_2UL-Core | 3 | Rel-12 | R4 | 2013-06-19 08:00 | 2014-12-11 17:00 | 90% | RP-131136 | T-Mobile USA | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14. Exception in RP-141285. Separated from UID_560016 LTE_CA_NC_B4 which remained 1UL-only
853 | 600224 | Perf. part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 4 for 2UL | LTE_CA_NC_B4_2UL-Perf | 3 | Rel-12 | R4 | 2013-06-25 08:00 | 2014-12-11 17:00 | 0% | RP-131136 | T-Mobile USA | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14
911 | 610022 | LTE Advanced intra-band contiguous Carrier Aggregation in Band 41 for 3DL | LTE_CA_C_B41_3DL | 2 | Rel-12 | R4 | 2013-09-09 08:00 | 2015-03-12 17:00 | 76% | RP-140100 | Alcatel-Lucent | 2014-09-08 08:00 | Intra-band contig. CA 3DL
913 | 610222 | Perf. part: LTE Advanced intra-band contiguous Carrier Aggregation in Band 41 for 3DL | LTE_CA_C_B41_3DL-Perf | 3 | Rel-12 | R4 | 2013-09-09 08:00 | 2015-03-12 17:00 | 60% | RP-140100 | Alcatel-Lucent | 2014-09-08 08:00 | RP#65 completion 09/14=>03/15
920 | 620019 | LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 28 | LTE_CA_B1_B28 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-11 17:00 | 35% | RP-132028 | KDDI | 2014-09-09 08:00 | Inter-band CA 2DL
921 | 620119 | Core part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 28 | LTE_CA_B1_B28-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-11 17:00 | 70% | RP-132028 | KDDI | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14. Exception in RP-141135
922 | 620219 | Perf. part: LTE Advanced inter-band Carrier Aggregation of Band 1 and Band 28 | LTE_CA_B1_B28-Perf | 3 | Rel-12 | R4 | 2013-12-12 08:00 | 2014-12-11 17:00 | 0% | RP-132028 | KDDI | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14
944 | 620027 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 12 | LTE_CA_B2_B4_B12 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-11 17:00 | 99% | RP-140189 | U.S. Cellular | 2014-09-09 08:00 | Inter-band CA 3DL
946 | 620227 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 2, Band 4 and Band 12 | LTE_CA_B2_B4_B12-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-11 17:00 | 98% | RP-140189 | U.S. Cellular | 2014-09-12 08:00 | RP#65 completion 09/14=>12/14
974 | 620038 | LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 3 DL | LTE_CA_NC_B41_3DL | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2015-03-12 17:00 | 75% | RP-140101 | Sprint, Alcatel-Lucent | 2014-09-08 08:00 | Intra-band non-contig. CA 3DL
976 | 620238 | Perf. part: LTE Advanced intra-band non-contiguous Carrier Aggregation in Band 41 for 3 DL | LTE_CA_NC_B41_3DL-Perf | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2015-03-12 17:00 | 60% | RP-140101 | Sprint, Alcatel-Lucent | 2014-09-08 08:00 | RP#65 completion 09/14=>03/15
989 | 620053 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 8 and Band 20 | LTE_CA_B7_B8_B20 | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-11 17:00 | 42% | RP-132080 | Vodafone | 2014-09-09 08:00 | Inter-band CA 3DL
990 | 620153 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 8 and Band 20 | LTE_CA_B7_B8_B20-Core | 3 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-11 17:00 | 85% | RP-132080 | Vodafone | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14. Exception in RP-141622
991 | 620253 | Perf. part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) for Band 7, Band 8 and Band 20 | LTE_CA_B7_B8_B20-Perf | 3 | Rel-12 | R4 | 2013-12-12 08:00 | 2014-12-11 17:00 | 0% | RP-132080 | Vodafone | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14
1029 | 640021 | Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5 | LTE_CA_B2_B5_BWset | 2 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-11 17:00 | 0% | RP-140642 | AT&T | 2014-09-09 08:00 | 2DL/1UL
1030 | 640121 | Core part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5 | LTE_CA_B2_B5_Bwset-Core | 3 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-11 17:00 | 0% | RP-140642 | AT&T | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14. Exception in RP-141210. There was a WI LTE_CA_B2_B5 completed in Rel-12. Add a bandwidth combination set 1 to the channel bandwidth combination table of B2+B5 CA for 1UL/2DL as well as 2UL/2DL
1031 | 640221 | Perf. Part: Additional bandwidth combination set for LTE Advanced inter-band Carrier Aggregation of Band 2 and Band 5 | LTE_CA_B2_B5_BWset-Perf | 3 | Rel-12 | R4 | 2014-06-18 08:00 | 2014-12-11 17:00 | 0% | RP-140642 | AT&T | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14
1032 | 640027 | E-UTRA UE demodulation/Channel State Information (CSI) performance requirements for multiple Carrier Aggregation configurations | LTE_CA_Mult | 2 | Rel-12 | R4 | 2014-06-16 08:00 | 2015-03-12 17:00 | 10% | RP-141304 | China Mobile | 2014-09-09 08:00 | LTE
1033 | 640127 | Perf. Part: E-UTRA UE demodulation/Channel State Information (CSI) performance requirements for multiple Carrier Aggregation configurations | LTE_CA_Mult-Perf | 3 | Rel-12 | R4 | 2014-06-16 08:00 | 2015-03-12 17:00 | 10% | RP-141304 | China Mobile | 2014-09-09 08:00 | RP#65 updated WID RP-140975=>RP-141304 (changed Title to better reflect the work scope)
1040 | 640030 | LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 42 and Band 42 | LTE_CA_B3_B42_B42 | 2 | Rel-12 | R4 | 2014-06-16 08:00 | 2014-12-11 17:00 | 50% | RP-141005 | NTT DOCOMO | 2014-09-09 08:00 | 3DL/1UL
1041 | 640130 | Core part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 42 and Band 42 | LTE_CA_B3_B42_B42-Core | 3 | Rel-12 | R4 | 2014-06-16 08:00 | 2014-12-11 17:00 | 50% | RP-141005 | NTT DOCOMO | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14. Exception in RP-141144
1042 | 640230 | Perf. Part: LTE Advanced 3 Band Carrier Aggregation (3DL/1UL) of Band 3, Band 42 and Band 42 | LTE_CA_B3_B42_B42-Perf | 3 | Rel-12 | R4 | 2014-06-16 08:00 | 2014-12-11 17:00 | 50% | RP-141005 | NTT DOCOMO | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14
1052 | 610013 | UE Conformance Test Aspects – Further Rel-12 configurations for LTE Advanced Carrier Aggregation | LTE_CA_Rel12-UEConTest | 1 | Rel-12 | R5 | 2013-09-09 08:00 | 2014-12-11 17:00 | 70% | RP-140621 | Microsoft | 2014-09-09 08:00 | RP#64 updated WID RP-140460=>RP-140621. Completion 09/14=>12/14
1053 | 650011 | UE Conformance Test Aspects – Further Rel-12 configurations for LTE Advanced Carrier Aggregation with 3DL | LTE_CA_Rel12_3DL-UEConTest | 1 | Rel-12 | R5 | 2014-09-16 08:00 | 2015-09-11 17:00 | 0% | RP-141445 | Microsoft | 2014-09-09 08:00 | Testing for generic core requirements in 3DL Carrier Aggregation
1056 | 570017 | LTE in the US Wireless Communications Service (WCS) Band 30 | LTE_WCS_band | 1 | Rel-12 | R4;R2;R5 | 2012-09-12 08:00 | 2014-12-11 17:00 | 85% | RP-130843 | AT&T | 2013-06-11 08:00 | RP#58 RP-121701 work can start based on FCC Order (FCC-12-130) http://hraunfoss.fcc.gov/edocs_public/attachmatch/FCC-12-130A1.pdf
1059 | 640002 | Test Part: LTE in the US Wireless Communications Service (WCS) Band 30 | LTE_WCS_band-UEConTest | 2 | Rel-12 | R5 | 2014-06-16 08:00 | 2014-12-11 17:00 | 40% | RP-140643 | Ericsson | 2014-09-09 08:00 | -
1064 | 570020 | Further Downlink MIMO Enhancement for LTE Advanced | LTE_eDL_MIMO_enh | 1 | Rel-12 | R1;R4 | 2012-09-11 08:00 | 2014-12-11 17:00 | 92% | RP-121416 | Alcatel-Lucent | 2012-12-06 08:00 | Stage 3
1066 | 570220 | Perf. part: Further Downlink MIMO Enhancement for LTE Advanced | LTE_eDL_MIMO_enh-Perf | 2 | Rel-12 | R4 | 2012-09-18 08:00 | 2014-12-11 17:00 | 85% | RP-121416 | Alcatel-Lucent | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14
1070 | 580027 | Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation | LTE_TDD_eIMTA | 1 | Rel-12 | R1;R2;R3;R4 | 2012-12-07 08:00 | 2014-12-11 17:00 | 24% | RP-121772 | CATT | 2012-12-10 08:00 | Stage 3. Triggered by Rel-11 TR 36.828 Study on Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation (FS_LTE_TDD_eIMTA) UID_510039
1072 | 580227 | Perf. part: Further Enhancements to LTE TDD for DL-UL Interference Management and Traffic Adaptation | LTE_TDD_eIMTA-Perf | 2 | Rel-12 | R4 | 2012-12-07 08:00 | 2014-12-11 17:00 | 20% | RP-121772 | CATT | 2014-09-09 08:00 | RP#64 completion 09/14=>12/14
1079 | 600012 | Low cost & enhanced coverage MTC UE for LTE | LC_MTC_LTE | 1 | Rel-12 | R1;R2;R4 | 2013-06-20 08:00 | 2015-03-13 17:00 | 65% | RP-130848 | Vodafone | 2014-09-09 08:00 | Triggered by Rel-11 TR 36.888 (FS_LC_MTC_UE)
1080 | 600112 | Core part: Low cost & enhanced coverage MTC UE for LTE | LC_MTC_LTE-Core | 2 | Rel-12 | R1;R2;R4 | 2013-10-15 16:28 | 2014-12-11 17:00 | 90% | RP-130848 | Vodafone | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14. Exception in RP-141220
1081 | 600212 | Perf. part: Low cost & enhanced coverage MTC UE for LTE | LC_MTC_LTE-Perf | 2 | Rel-12 | R4 | 2013-06-20 08:00 | 2015-03-13 17:00 | 55% | RP-130848 | Vodafone | 2014-09-09 08:00 | -
1082 | 600013 | LTE TDD-FDD joint operation including Carrier Aggregation | LTE_CA_TDD_FDD | 1 | Rel-12 | R1;R2;R4 | 2013-04-12 16:44 | 2014-12-11 17:00 | 43% | RP-140465 | Nokia | 2014-03-13 08:00 | -
1084 | 600213 | Perf. part: LTE TDD-FDD joint operation including Carrier Aggregation | LTE_CA_TDD_FDD-Perf | 2 | Rel-12 | R4 | 2013-06-20 08:00 | 2014-12-11 17:00 | 30% | RP-140465 | Nokia | 2014-09-09 08:00 | -
1085 | 600014 | LTE Coverage Enhancements | Cov_Enh_LTE | 1 | Rel-12 | R1;R2;R4;R5 | 2013-03-01 15:38 | 2015-09-11 17:00 | 49% | RP-130833 | China Telecom | 2013-06-17 08:00 | Triggered by Rel-11 TR 36.824 (FS_Cov_Enh_LTE)
1087 | 600214 | Perf. part: LTE Coverage Enhancements | Cov_Enh_LTE-Perf | 2 | Rel-12 | R4 | 2013-06-20 08:00 | 2014-12-11 17:00 | 70% | RP-130833 | China Telecom | 2014-09-15 08:00 | -
1088 | 650012 | Test part: LTE Coverage Enhancements | Cov_Enh_LTE-UEConTest | 2 | Rel-12 | R5 | 2014-09-16 08:00 | 2015-09-11 17:00 | 0% | RP-141150 | China Telecom | 2014-09-09 08:00 | -
1089 | 610024 | Further MBMS operations support for E-UTRAN | MBMS_LTE_OS | 1 | Rel-12 | R2;R1;R3;R4 | 2013-12-09 08:00 | 2014-12-11 17:00 | 83% | RP-140282 | Verizon | 2014-09-09 08:00 | Solutions for Minimization of Drive Tests (MDT), in order to reduce the need for manual drive testing for MBMS.
1090 | 610124 | Core part: Further MBMS operations support for E-UTRAN | MBMS_LTE_OS-Core | 2 | Rel-12 | R2;R1;R3;R4 | 2014-04-04 15:00 | 2014-12-11 17:00 | 95% | RP-140282 | Verizon | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14. Exception in RP-141432
1091 | 620073 | Perf. part: Further MBMS operations support for E-UTRAN | MBMS_LTE_OS-Perf | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-11 17:00 | 75% | RP-140282 | Verizon | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14
1092 | 620040 | Dual connectivity for LTE | LTE_SC_enh_dualC | 1 | Rel-12 | R2;R1;R3;R4;S2;C4 | 2013-12-10 08:00 | 2015-06-12 17:00 | 45% | RP-141266 | NTT DOCOMO | 2014-09-15 08:00 | Triggered by TR 36.842 Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Higher-layer aspects (UID_580044)
1093 | 620140 | Core part: Dual connectivity for LTE | LTE_SC_enh_dualC-Core | 2 | Rel-12 | R2;R1;R3;R4 | 2014-04-29 08:00 | 2014-12-11 17:00 | 65% | RP-141266 | NTT DOCOMO, NEC | 2014-09-15 08:00 | RP#65 completion 09/14=>12/14. Exception in RP-141265. Updated WID RP-132069=>RP-141266 (added new RAN3 TS 36.425)
1094 | 620240 | Perf. part: Dual Connectivity for LTE | LTE_SC_enh_dualC-Perf | 2 | Rel-12 | R4 | 2013-12-10 08:00 | 2015-06-12 17:00 | 10% | RP-141266 | NTT DOCOMO | 2014-09-15 08:00 | RP#65 completion 12/14=>06/15
1097 | 620041 | E-UTRA Small cell enhancements - Physical layer aspects | LTE_SC_enh_L1 | 1 | Rel-12 | R1;R2;R4 | 2013-07-19 10:00 | 2015-03-13 17:00 | 46% | RP-141459 | Huawei | 2014-09-15 08:00 | Triggered by TR 36.872 Study on Small Cell Enhancements for E-UTRA and E-UTRAN – Physical-layer aspects (UID_580041)
1098 | 620141 | Core part: E-UTRA Small cell enhancements - Physical layer aspects | LTE_SC_enh_L1-Core | 2 | Rel-12 | R1;R2;R4 | 2013-07-19 10:00 | 2014-12-11 17:00 | 78% | RP-141459 | Huawei | 2014-09-15 08:00 | RP#65 updated WID RP-132073=>RP-141459. Completion 06/14=>12/14. Exception in RP-141631
1099 | 620241 | Perf. part: E-UTRA Small cell enhancements - Physical layer aspects | LTE_SC_enh_L1-Perf | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2015-03-13 17:00 | 20% | RP-141459 | Huawei | 2014-09-15 08:00 | RP#65 updated WID RP-132073=>RP-141459. Completion 09/14=>03/15
1100 | 620047 | Inter-eNB Coordinated Multi-Point (CoMP) for LTE | COMP_LTE_IeNB | 1 | Rel-12 | R3;R1 | 2014-03-14 10:48 | 2014-12-11 17:00 | 85% | RP-140983 | Samsung | 2013-12-07 08:00 | Stage 3. Rel-11 did not address support of a network interface for CoMP involving multiple eNBs with non-ideal backhaul (affected operators might not take advantage of performance benefit from inter-eNB CoMP operation).
1101 | 620147 | Core part: Inter-eNB Coordinated Multi-Point (CoMP) for LTE | COMP_LTE_IeNB-Core | 2 | Rel-12 | R3;R1 | 2014-03-14 10:48 | 2014-12-11 17:00 | 85% | RP-140983 | Samsung | 2014-09-21 08:00 | RP#65 completion 09/14=>12/14. Exception in RP-141117. Triggered by TR 36.874 Study on Coordinated Multi-Point (CoMP) operation for LTE with Non-Ideal Backhaul (UID_600015)
1108 | 630046 | Network-Assisted Interference Cancellation and Suppression for LTE | LTE_NAICS | 1 | Rel-12 | R1;R2;R4;R3 | 2014-03-11 08:00 | 2015-06-12 17:00 | 23% | RP-141634 | MediaTek | 2014-09-09 08:00 | follow-up of TR 36.866 FS_LTE_NAICS
1109 | 630146 | Core part: Network-Assisted Interference Cancellation and Suppression for LTE | LTE_NAICS-Core | 2 | Rel-12 | R1;R2;R4;R3 | 2014-07-11 10:40 | 2014-12-08 14:02 | 95% | RP-141634 | MediaTek | 2014-09-09 08:00 | RP#65 updated WID RP-140519=>RP-141634. Completion 09/14=>12/14. Exception in RP-141440
1110 | 630246 | Perf. part: Network-Assisted Interference Cancellation and Suppression for LTE | LTE_NAICS-Perf | 2 | Rel-12 | R4 | 2014-03-11 08:00 | 2015-06-12 17:00 | 0% | RP-141634 | MediaTek | 2014-09-09 08:00 | -
1111 | 630047 | Performance requirements of interference cancellation and suppression receiver for SU-MIMO | LTE_SUMIMO_RX | 1 | Rel-12 | R4 | 2014-03-06 08:00 | 2015-03-13 17:00 | 50% | RP-140520 | Huawei | 2014-03-10 08:00 | no Core part
1112 | 630147 | Perf. part: Performance requirements of interference cancellation and suppression receiver for SU-MIMO | LTE_SUMIMO_RX-Perf | 2 | Rel-12 | R4 | 2014-03-06 08:00 | 2015-03-13 17:00 | 50% | RP-140520 | Huawei | 2014-09-29 08:00 | -
1118 | 610025 | Dedicated Channel (DCH) enhancements for UMTS | UTRA_DCHenh | 1 | Rel-12 | R1;R2;R3;R4 | 2013-09-10 08:00 | 2014-12-11 17:00 | 52% | RP-140771 | Qualcomm | 2014-09-09 08:00 | Triggered by Rel-12 TR 25.702 Study on Dedicated Channel (DCH) enhancements for UMTS (FS_UTRA_DCHenh) UID_580040. Stage 2/3
1120 | 610225 | Perf. part: Dedicated Channel (DCH) enhancements for UMTS | UTRA_DCHenh-Perf | 2 | Rel-12 | R4 | 2013-09-10 08:00 | 2014-12-11 17:00 | 35% | RP-140771 | Qualcomm | 2014-09-09 08:00 | RP#64 revised WID RP-131357=>RP-140771. Completion 09/14=>12/14
1124 | 620054 | UMTS Heterogeneous Networks enhancements | UTRA_HetNet_enh | 1 | Rel-12 | R1;R2;R3;R4 | 2013-12-06 08:00 | 2014-12-11 17:00 | 43% | RP-141701 | Huawei | 2014-09-15 08:00 | Triggered by the 2nd part of TR 25.800 (FS_UTRA_HetNet); the 1st part is addressed by UTRA_HetNet_mob UID_610026
1126 | 620254 | Perf. part: Heterogeneous Networks enhancements | UTRA_HetNet_enh-Perf | 2 | Rel-12 | R4 | 2013-12-12 08:00 | 2014-12-11 17:00 | 0% | RP-141701 | Huawei | 2014-09-15 08:00 | RP#65 updated WID RP-140463=>RP-141701
1127 | 620055 | Enhanced Broadcast of System Information | UTRA_SIBenh | 1 | Rel-12 | R2;R1;R3;R4 | 2013-12-06 08:00 | 2014-12-11 17:00 | 58% | RP-140131 | Ericsson | 2014-09-15 08:00 | Triggered by Rel-12 UTRA TR 25.704 Study on Enhanced Broadcast of System Information (FS_UTRA_SIBenh)
1129 | 620255 | Perf. part: Enhanced Broadcast of System Information | UTRA_SIBenh-Perf | 2 | Rel-12 | R4 | 2013-12-10 08:00 | 2014-12-11 17:00 | 30% | RP-140131 | Ericsson | 2014-09-15 08:00 | RP#63 updated WID RP-132077=>RP-140131
1130 | 620049 | Further Enhanced Uplink (EUL) enhancements | EDCH_enh | 1 | Rel-12 | R2 | 2013-12-09 08:00 | 2014-12-11 17:00 | 67% | RP-140127 | Ericsson | 2014-09-15 08:00 | Triggered by Rel-12 UTRA TR 25.700 Study on Further Enhanced Uplink (EUL) enhancements (FS_EDCH_enh)
1131 | 620149 | Core part: Further Enhanced Uplink (EUL) enhancements | EDCH_enh-Core | 2 | Rel-12 | R2;R1;R3;R4 | 2014-04-29 08:00 | 2014-12-11 17:00 | 95% | RP-140127 | Ericsson | 2014-09-15 08:00 | RP#65 completion 09/14=>12/14. Exception in RP-141685
1132 | 620249 | Perf. part: Further Enhanced Uplink (EUL) enhancements | EDCH_enh-Perf | 2 | Rel-12 | R4 | 2013-12-09 08:00 | 2014-12-11 17:00 | 50% | RP-140127 | Ericsson | 2014-09-15 08:00 | -
1134 | 660032 | (IETF) (Small) Technical Enhancements and Improvements for Rel-12 (draft-ietf-insipid-session-id) | TEI12_IETF | 1 | Rel-12 | C1-IETF | 2014-06-13 08:00 | 2014-12-09 17:00 | 50% |  | Alcatel-Lucent | 2014-12-04 08:00 | work in progress
1136 | 1112 | Release 12 Studies | - | 1 | Rel-12 | SP;CP;GP;RP | 2013-08-05 13:00 | 2014-09-17 17:00 | 80% | - | - | 2011-09-15 08:00 | -
1177 | 620001 | Study on Development of conformance requirements for the IP Multimedia Services Identity Module (ISIM) application support in ME | FS_ISIM_CR | 1 | Rel-12 | C6 | 2013-12-09 08:00 | 2014-12-09 17:00 | 30% | CP-130812 | Gemalto | 2014-09-16 08:00 | CP#65 completion 09/14=>12/14. Gathering of all ISIM-related conformance requirements and the assessment of CT6 coverage
1178 | 620002 | Study on Shared Data Update for Multiple Subscribers | FS_SHARED_SubData_UPD | 1 | Rel-12 | C4 | 2013-12-06 08:00 | 2014-12-09 17:00 | 85% | CP-130809 | Huawei | 2014-12-04 08:00 | CP#65 TR 29.854v200 for Approval. Completion 09/14=>12/14. LM: 80->85%
Release 11 and before
1361 | 530001 | Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC | 1 | Rel-11 | S2;C1;C3;C4;G2;R2;R3;R5 | 2011-09-12 08:00 | 2014-12-11 17:00 | 94% | SP-110475 | Orange | 2011-09-20 08:00 | Stage 1 in Rel-8 TS 22.278 clause 7.1.4.2. Triggered by Rel-11 TR 23.885 Study on Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA (FS_rSRVCC) UID_460030
1370 | 640012 | Test part: Single Radio Voice Call Continuity from UTRAN/GERAN to E-UTRAN/HSPA | rSRVCC-UEConTest | 2 | Rel-11 | R5 | 2014-06-16 08:00 | 2014-12-11 17:00 | 5% | RP-140960 | Ericsson | 2014-09-09 08:00 | Testing for core part: rSRVCC-CT and rSRVCC-RAN_UTRA-Core
1384 | 560027 | IMS Overload Control | IOC | 1 | Rel-11 | S2;C1;C3;IETF | 2012-06-18 08:00 | 2014-12-09 17:00 | 97% | SP-120273 | Orange, China Mobile | 2012-07-24 08:00 | SP#57 Stage 2 completed. Moved Rel-12=>Rel-11 as CT finished Stage 3. Linked to UID_410041 Study on IMS Evolution (TR 23.812). Solutions from IETF SOC WG and existing 3GPP procedures to be re-used if possible & backward compatibility ensured
1386 | 570007 | Stage 3 for IMS Overload Control | IOC | 2 | Rel-11 | C1;C3;IETF | 2012-09-05 08:00 | 2014-12-09 17:00 | 97% | CP-120561 | Alcatel-Lucent | 2012-11-20 08:00 | -
1390 | 571002 | (IETF) CT part of Stage 3 for IMS Overload Control (soc-overload-rate-control) | IOC | 3 | Rel-11 | C1-IETF;C3-IETF | 2013-07-29 08:00 | 2014-12-09 17:00 | 90% | CP-120561 | Keith Drage | 2014-12-04 08:00 | Submitted to IESG for publication. LM; 50->90%
1521 | 510021 | Further Enhanced Non CA-based ICIC for LTE | eICIC_enh_LTE | 1 | Rel-11 | R1;R2;R3;R4;R5 | 2011-03-22 08:00 | 2014-12-11 17:00 | 99% | RP-120860 | China Mobile | 2012-12-05 08:00 | -
1524 | 600001 | Test part: Further Enhanced Non CA-based ICIC for LTE | eICIC_enh_LTE-UEConTest | 2 | Rel-11 | R5 | 2013-06-18 08:00 | 2014-12-11 17:00 | 98% | RP-130649 | ZTE | 2014-09-15 08:00 | RP#65 completion 09/14=>12/14
1545 | 530032 | Coordinated Multi-Point Operation for LTE | COMP_LTE | 1 | Rel-11 | R1;R2;R3;R4;R5 | 2011-09-19 08:00 | 2014-12-11 17:00 | 97% | RP-111365 | Huawei, Samsung | 2011-09-15 08:00 | Stage 3. Triggered by Rel-11 TR 36.819 Study on Coordinated Multi-Point Operation for LTE (FS_CoMP_LTE)
1550 | 590004 | Test part: Coordinated Multi-Point Operation for LTE | COMP_LTE-UEConTest | 2 | Rel-11 | R5 | 2013-03-04 08:00 | 2014-12-11 17:00 | 85% | RP-130376 | Samsung | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14
1564 | 580158 | Rel-11 LTE Carrier Aggregation | LTE_CA_Rel-11 | 1 | Rel-11 | R1;R2;R3;R4;R5 | 2010-12-10 08:00 | 2014-12-11 17:00 | 99% | - | - | 2012-11-30 08:00 | LTE_CA_Rel-11
1565 | 510030 | LTE Carrier Aggregation Enhancements | LTE_CA_enh | 2 | Rel-11 | R1;R2;R3;R4;R5 | 2011-03-22 08:00 | 2014-12-11 17:00 | 92% | RP-121999 | Nokia | 2012-09-04 08:00 | Stage 3
1566 | 510130 | Core part: LTE Carrier Aggregation Enhancements | LTE_CA_enh-Core | 3 | Rel-11 | R1;R2;R4;R3 | 2011-03-22 08:00 | 2013-08-27 10:00 | 80% | RP-121999 | Nokia | 2013-02-27 08:00 | RP#59 completed. New TR 36.823 v100 for Information and Approval
1567 | 510230 | Perf. part: LTE Carrier Aggregation Enhancements | LTE_CA_enh-Perf | 3 | Rel-11 | R4 | 2011-03-29 08:00 | 2014-12-11 17:00 | 98% | RP-121999 | Nokia | 2014-06-11 08:00 | RP#64 completion 06/14=>12/14
1635 | 450016 | UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test | UEAnt_FSTest | 1 | Rel-11 | R4;R5 | 2009-09-18 08:00 | 2014-12-11 17:00 | 97% | RP-111381 | CATR | 2011-09-17 08:00 | -
1637 | 520011 | Test part: UE Over The Air (Antenna) conformance testing methodology - Laptop mounted equipment Free Space test | UEAnt_FSTest-UEConTest | 2 | Rel-11 | R5 | 2011-06-07 08:00 | 2014-12-11 17:00 | 95% | RP-110629 | ZTE | 2014-09-09 08:00 | RP#64 completion 06/14=>12/14
1656 | 510020 | Further Enhancements to CELL_FACH | Cell_FACH_enh | 1 | Rel-11 | R1;R2;R3;R4;R5 | 2011-03-18 08:00 | 2014-12-11 17:00 | 98% | RP-111321 | Qualcomm | 2011-09-16 08:00 | -
1659 | 600004 | Test part: Further Enhancements to CELL_FACH | Cell_FACH_enh-UEConTest | 2 | Rel-11 | R5 | 2013-06-18 08:00 | 2014-12-11 17:00 | 90% | RP-130644 | Ericsson | 2014-09-09 08:00 | RP#65 completion 09/14=>12/14
1660 | 530034 | HSDPA Multiflow Data Transmission | HSDPA_MFTX | 1 | Rel-11 | R2;R1;R3;R4;R5 | 2011-09-19 08:00 | 2014-12-11 17:00 | 89% | RP-111375 | Nokia Siemens Networks | 2011-09-15 08:00 | Stage 2,3
1663 | 620016 | Test part: HSDPA Multiflow Data Transmission | HSDPA_MFTX-UEConTest | 2 | Rel-11 | R5 | 2013-12-06 08:00 | 2014-12-11 17:00 | 55% | RP-131692 | Qualcomm | 2014-09-09 08:00 | -
2002 | 521004 | (IETF) (Small) Technical Enhancements and Improvements for Rel-10 (draft-atarius) | TEI10_IETF | 1 | Rel-10 | C1-IETF | 2009-06-04 08:00 | 2014-12-09 17:00 | 75% | - | Andrew Allen | 2013-12-06 08:00 | Not completed internet-draft, waiting for draft-montemurro to complete
2229 | 440070 | Operational description of the Inter-IMS Network to Network Interface (II-NNI) | II-NNI | 1 | Rel-9 | C3;IETF | 2009-05-29 08:00 | 2014-12-09 17:00 | 95% | CP-090331 | Orange | 2013-02-28 08:00 | -
2233 | 561006 | (IETF) Operational description of the Inter-IMS Network to Network Interface | II-NNI | 2 | Rel-9 | C3-IETF | 2012-04-20 08:00 | 2014-12-09 17:00 | 90% | CP-090331 | Roland Jesske | 2014-12-04 08:00 | In RFC Editors Queue. LM: 75->90
2234 | 561007 | (IETF) Operational description of the Inter-IMS Network to Network Interface | II-NNI | 2 | Rel-9 | C3-IETF | 2012-04-20 08:00 | 2014-12-09 17:00 | 90% | CP-090331 | Roland Jesske | 2013-11-27 08:00 | In RFC Editors Queue
2235 | 561008 | (IETF) Operational description of the Inter-IMS Network to Network Interface | II-NNI | 2 | Rel-9 | C3-IETF | 2012-04-20 08:00 | 2014-12-09 17:00 | 90% | CP-090331 | Keith Drage | 2014-12-04 08:00 | In RFC Editors Queue. LM: 75->90
2257 | 430013 | Rel-9 RAN improvements | - | 1 | Rel-9 | RP | 2000-01-03 08:00 | 2009-03-06 08:00 | 99% | - | - | 2010-09-08 08:00 | RP#47 completed
2412 | 370025 | IMS Centralized Service control | ICSRA | 1 | Rel-8 | S1;S2;C1;C3;C4;IETF | 2005-11-01 16:12 | 2014-12-09 17:00 | 98% | SP-070924 | AT&T | 2009-12-02 08:00 | CP#46 completed
2415 | 400205 | Stage 3 for ICSRA – Protocol, Addressing, Subscriber Data | ICSRA | 2 | Rel-8 | C1;C3;C4;IETF | 2005-11-01 16:12 | 2014-12-09 17:00 | 98% | CP-091046 | Ericsson | 2009-12-07 08:00 | CP#46 completed
2417 | 521014 | (IETF) CT1 aspects - Stage 3 for ICSRA (draft-ietf-salud-alert-info-urns) | ICSRA | 3 | Rel-8 | C1-IETF | 2008-05-30 08:00 | 2014-12-09 17:00 | 90% | CP-091046 | Roland Jesske | 2014-12-04 08:00 | In RFC Editors Queue. LM: 75->90
2425 | 370059 | IMS Multimedia Telephony and Supplementary Services | IMSTSS | 1 | Rel-8 | S1;S5;C1;C3;C4;IETF | 2007-05-02 08:00 | 2014-12-09 17:00 | 98% | - | - | 2007-11-19 08:00 | SP#43 completed
2441 | 380009 | Communication Wait on IMS | CW_IMS | 2 | Rel-8 | C1;C3;IETF | 2007-06-22 08:00 | 2014-12-09 17:00 | 93% | CP-080214 | Deutsche Telekom | 2008-04-15 08:00 | CP#43 completed
2443 | 521020 | (IETF) Stage 3 CW-IMS (salud-alert-info-urns) | CW_IMS | 3 | Rel-8 | C1-IETF | 2007-06-22 08:00 | 2014-12-09 17:00 | 90% | CP-080214 | Roland Jesske | 2014-12-04 08:00 | In RFC Editors Queue. LM: 75->90
2497 | 360029 | IMS Stage 3 IETF Protocol Alignment - phase 2 | IMSProtoc2 | 1 | Rel-8 | C1;IETF | 2007-06-22 08:00 | 2014-12-09 17:00 | 96% | CP-080794 | Alcatel-Lucent | 2009-02-20 08:00 | CP#43 completed
2501 | 521025 | (IETF) IMS Stage 3 IETF Protocol Alignment (draft-ietf-salud-alert-info-urns) | IMSProtoc2 | 2 | Rel-8 | C1-IETF | 2007-06-22 08:00 | 2014-12-09 17:00 | 90% | CP-080794 | Roland Jesske | 2014-12-04 08:00 | In RFC Editors Queue. LM: 75->90
2502 | 380014 | Interworking between User-to-User Signalling (UUS) and SIP | UUSIW | 1 | Rel-8 | C1;C3;IETF | 2007-11-30 08:00 | 2014-12-09 17:00 | 93% | CP-070782 | Huawei | 2009-03-11 08:00 | CP#43 completed
2504 | 521026 | (IETF) Stage 3 MGCF UUSIW (cuss-sip-uui) | UUSIW | 2 | Rel-8 | C1-IETF;C3-IETF | 2007-11-30 08:00 | 2014-12-09 17:00 | 90% | CP-070782 | Roland Jesske | 2014-06-06 08:00 | In RFC Editors Queue.
2505 | 551001 | (IETF) Stage 3 MGCF UUSIW (cuss-sip-uui-isdn) | UUSIW | 2 | Rel-8 | C1-IETF;C3-IETF | 2011-03-17 13:00 | 2014-12-09 17:00 | 90% | CP-070782 | Keith Drage | 2014-12-04 08:00 | In RFC Editors Queue. LM: 75->90
2616 | 380063 | Charging for multi-phases services | CHRGMPH | 1 | Rel-8 | S1 | 2007-12-06 08:00 | 2008-03-12 17:00 | 99% | SP-080053 | Telecom Italia | 2008-12-10 08:00 | SP#39 Stage 1 completed
3025 | 34035 | Optimizations for Multimedia Telephony over IMS | OMTIMS | 1 | Rel-7 | S4 | 2005-09-28 08:00 | 2005-09-28 08:00 | 99% | SP-060226 | Ericsson | 2007-03-29 08:00 | -
3582 | 50096 | Alignment between the test-regimes for GERAN capable MS | ALTERE | 1 | Rel-6 | G3new | 2003-08-29 08:00 | 2005-09-02 17:00 | 99% | GP-032236 | Ericsson | 2006-01-13 08:00 | -
4233 | 401800 | Rel-4 (U)SIM toolkit enhancements | USAT1, USAT1-LocLnk, USAT1APIJAVA, USAT1SM | 1 | Rel-4 | T3;S1 | 2000-06-05 08:00 | 2001-03-23 17:00 | 99% | - | Gemplus | 2003-01-13 08:00 | -