## Sheet1
New Items proposed at TSG#66
ID | Unique_ID | Name | Acronym | Outline_Level | Release | Resource_Names | Start_Date | Finish_Date | Percent_Complete | Hyperlink | Status_Report | WI_rapporteur_name | WI_rapporteur_e_mail | Notes | Impacted_TSs_and_TRs | TSG_approved | PCG_approved | TSG_stopped | PCG_stopped | Created | last_modif
15 | 640044 | Co-ordinated packet data network gateway (P-GW) change for SIPTO | CSIPTO | 1 | Rel-13 | S1 | 2014-06-18 08:00 | 2015-06-17 17:00 | 32% | SP-140509 | Intel | 2014-08-29 08:00 | SP#65 completed. Updated WID SP-140235=>SP-140509. Triggered by Rel-13 Study TR 22.828 (FS_CSIPTO)
16 | 660012 | Stage 1 for Co-ordinated packet data network gateway (P-GW) change for SIPTO | CSIPTO | 2 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-09-16 17:00 | 100% | SP-140509 | Intel | 2014-12-03 08:00 | SP#65 completed. Updated WID SP-140235=>SP-140509. Triggered by Rel-13 Study TR 22.828 (FS_CSIPTO). LM: former S1-only feature split
17 | 660007 | Feasibility Study on Co-ordinated P-GW Change for SIPTO - Stage 2 | FS_CSIPTO_St2 | 2 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-06-17 17:00 | 0% |  |  | 2014-12-03 08:00
18 | 640052 | Application specific Congestion control for Data Communication | ACDC | 1 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-12-04 17:00 | 99% | SP-140234 | NTT DOCOMO | 2014-08-29 08:00 | SP#65 completed. Triggered by Rel-13 Study TR 22.806
19 | 660013 | Stage 1 for Application specific Congestion control for Data Communication | ACDC | 2 | Rel-13 | S1 | 2014-06-18 08:00 | 2014-09-17 17:00 | 100% | SP-140234 | NTT DOCOMO | 2014-08-29 08:00 | Results from MCC Split of the SA1 feature into F+BB for stage 1
20 | 660033 | Stage 3 for Application specific Congestion control for Data Communication | ACDC-CT | 2 | Rel-13 | C1 | 2014-12-04 08:00 | 2014-12-04 17:00 | 0% |  |  | 2014-12-04 08:00 | Presented at CT#66
22 | 650019 | Flexible Mobile Service Steering | FMSS | 1 | Rel-13 | S1 | 2014-09-15 08:00 | 2015-06-17 17:00 | 9% | SP-140638 | China Mobile | 2014-08-28 08:00 | SP#65 WID approved & completed. Triggered by Rel-13 TR 22.808 (FS_FMSS)
24 | 660002 | Flexible Mobile Service Steering TR Phase | FMSS | 2 | Rel-13 | S2 | 2014-12-12 08:00 | 2015-06-17 17:00 | 15% |  | China Mobile | 2014-12-03 08:00 | proposed at SA#66
25 | 660003 | Flexible Mobile Service Steering - Stage 2 | FMSS | 2 | Rel-13 | S2 | 2014-12-12 08:00 | 2015-06-17 17:00 | 0% |  | China Mobile | 2014-12-03 08:00 | proposed at SA#66
92 | 640053 | Double Resource Reuse for Multiple Media Sessions | DRuMS | 1 | Rel-13 | S2 | 2014-03-14 08:00 | 2015-03-13 17:00 | 89% | SP-140393 | Ericsson | 2014-06-11 08:00 | -
94 | 660019 | CT aspects of Double Resource Reuse for Multiple Media Sessions | DRuMS-CT | 2 | Rel-13 | C3 | 2014-12-03 08:00 | 2015-03-13 17:00 | 65% |  | Ericsson | 2014-12-04 08:00 | Ptroposed at TSG#66
152 | 660001 | Usage Monitoring Control PCC Extension | eUMONC | 1 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-06-16 17:00 | 7% |  | CTBRI | 2014-12-03 08:00 | Ptroposed at TSG#66
153 | 660022 | Stage 2 of Usage Monitoring Control PCC Extension | eUMONC | 2 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-06-16 17:00 | 6% |  | CTBRI | 2014-12-03 08:00 | Ptroposed at TSG#66
154 | 660020 | CT3 Aspect of Usage Monitoring Control extension | eUMONC-CT3 | 2 | Rel-13 | C3 | 2014-12-03 08:00 | 2015-03-13 17:00 | 10% | C3-144174 | ZTE | 2014-12-04 08:00 | Ptroposed at TSG#66
155 | 660004 | Service Domain Centralization | SeDoC | 1 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-06-16 17:00 | 0% |  | T-Mobile | 2014-12-03 08:00 | Ptroposed at TSG#66
156 | 660005 | Service Domain Centralization TR Phase | SeDoC | 2 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-06-16 17:00 | 0% |  | T-Mobile | 2014-12-03 08:00 | Ptroposed at TSG#66
157 | 660006 | Service Domain Centralization - Stage 2 | SeDoC | 2 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-06-16 17:00 | 0% |  | T-Mobile | 2014-12-03 08:00 | Ptroposed at TSG#66
158 | 660009 | MBMS Enhancements | MBMS_enh | 1 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-09-14 17:00 | 0% |  | Rainer Liebhart | 2014-12-03 08:00 | Ptroposed at TSG#66
159 | 660010 | MBMS Enhancements TR Phase | MBMS_enh | 2 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-09-14 17:00 | 0% |  | Rainer Liebhart | 2014-12-03 08:00 | Ptroposed at TSG#66
160 | 660011 | MBMS Enhancements - Stage 2 | MBMS_enh | 2 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-09-14 17:00 | 0% |  | Rainer Liebhart | 2014-12-03 08:00 | Ptroposed at TSG#66
161 | 660030 | Enhanced P-CSCF discovery using signalling for access to EPC via WLAN | ePCSCF_WLA | 1 | Rel-13 | C1 | 2014-10-06 08:00 | 2015-09-14 17:00 | 20% |  |  | 2014-12-04 08:00 | Ptroposed at TSG#66
162 | 660014 | CT1 aspects of Enhanced P-CSCF discovery using signalling for access to EPC via WLAN | ePCSCF_WLA | 2 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-09-14 17:00 | 0% |  |  | 2014-12-04 08:00 | Ptroposed at TSG#66
163 | 660023 | CT4 aspects of Enhanced P-CSCF discovery using signalling for access to EPC via WLAN | ePCSCF_WLA | 2 | Rel-13 | C4 | 2014-10-06 08:00 | 2014-12-12 17:00 | 100% |  |  | 2014-12-04 08:00 | Ptroposed at TSG#66
164 | 660016 | SAES4, SAES4-CSFB, SAES4-non3GPP | SAES4, SAES4-CSFB, SAES4-non3GPP | 1 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-09-14 17:00 | 0% |  |  | 2014-12-04 08:00 | Ptroposed at TSG#66
165 | 660017 | IMS Stage-3 IETF Protocol Alignment | IMSProtoc7 | 1 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-12-11 17:00 | 0% |  | Alcatel-Lucent | 2014-12-04 08:00 | Ptroposed at TSG#66
166 | 660034 | Interworking solution for Called IN number and original called IN number ISUP parameters | INNB_IW | 1 | Rel-13 | C3 | 2014-12-03 08:00 | 2015-03-13 17:00 | 53% |  | Orange | 2014-12-04 08:00 | Ptroposed at TSG#66
167 | 660036 | (IETF) CT1 part of Interworking solution for Called IN number and original called IN number ISUP parameters | INNB_IW | 2 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-03-13 17:00 | 25% |  | Orange | 2014-12-04 08:00 | Ptroposed at TSG#66
168 | 660021 | CT3 aspects of Interworking solution for Called IN number and original called IN number ISUP parameters | INNB_IW | 2 | Rel-13 | C3 | 2014-12-03 08:00 | 2015-03-13 17:00 | 80% |  | Orange | 2014-12-04 08:00 | Ptroposed at TSG#66
169 | 660024 | Warning Status Report in EPS | WSR_EP | 1 | Rel-13 | C4 | 2014-12-03 08:00 | 2015-09-14 17:00 | 0% |  |  | 2014-12-04 08:00 | Ptroposed at TSG#66
170 | 660015 | CT1 aspects of Warning Status Report in EPS | WSR_EP | 2 | Rel-13 | C1 | 2014-12-03 08:00 | 2015-09-14 17:00 | 0% |  |  | 2014-12-04 08:00 | Ptroposed at TSG#66
171 | 660029 | CT4 aspects of Warning Status Report in EPS | WSR_EP | 2 | Rel-13 | C4 | 2014-12-03 08:00 | 2015-09-14 17:00 | 0% |  |  | 2014-12-04 08:00 | Ptroposed at TSG#66
172 | 660025 | Diameter Load Control Mechanisms | DLoCME | 1 | Rel-13 | C4 | 2014-12-03 08:00 | 2014-12-03 17:00 | 5% |  |  | 2014-12-04 08:00 | Ptroposed at TSG#66
173 | 660026 | Shared Data Update for Multiple Subscriber |  | 1 | Rel-13 | C4 | 2014-12-03 08:00 | 2014-12-03 17:00 | 0% |  |  | 2014-12-04 08:00 | Ptroposed at TSG#66
174 | 660027 | Study on EPC Signalling Improvement for Race Scenarios |  | 1 | Rel-13 | C4 | 2014-12-03 08:00 | 2014-12-03 17:00 | 0% |  |  | 2014-12-04 08:00 | Ptroposed at TSG#66
175 | 660028 | P-CSCF Restoration Enhancements with WLAN |  | 1 | Rel-13 | C4 | 2014-12-03 08:00 | 2014-12-03 17:00 | 5% |  |  | 2014-12-04 08:00 | Ptroposed at TSG#66
176 | 660035 | ULI and release causes for charging enhancement for VoLTE |  | 1 | Rel-13 | S5 | 2014-12-03 08:00 | 2015-09-11 17:00 | 0% | S5-146227 |  | 2014-12-04 08:00 | Ptroposed at TSG#66
177 | 660033 | Multi-Broadcast Single Frequency Network (MBSFN) Minimization of Drive Tests (MDT) enhancement |  | 1 | Rel-13 | S5 | 2014-12-03 08:00 | 2015-06-12 17:00 | 0% | S5-145398 |  | 2014-12-04 08:00 | Ptroposed at TSG#66
325 | 660008 | Feasibility study on Extended DRX cycle for Power Consumption Optimization | FS_eDRX | 1 | Rel-13 | S2 | 2014-12-03 08:00 | 2015-06-16 17:00 | 0% |  | Qualcomm | 2014-12-03 08:00 | Proposed TSG#66
326 | 660037 | Study on KQIs for Service Experience |  | 1 | Rel-13 | S5 | 2014-12-03 08:00 | 2015-09-11 17:00 | 0% | S5-146364 |  | 2014-12-04 08:00 | Proposed TSG#66
482 | 580062 | Web Real Time Communication access to IMS | IMS_WebRTC | 1 | Rel-12 | S1;S2;S3 | 2012-12-14 08:00 | 2014-12-12 17:00 | 78% | SP-130707 | China Mobile | 2013-09-09 08:00 | IETF RTCWEB and W3C WEBRTC groups are specifying a browser-based client to support communication services. Interoperability for WebRTC clients to access 3GPP IMS is needed.
489 | 630003 | CT aspects of Web Real Time Communication (WebRTC) Access to IMS | IMS_WebRTC-CT | 2 | Rel-12 | C1;C4;IETF | 2014-03-05 08:00 | 2014-12-09 17:00 | 70% | CP-140192 | China Mobile | 2014-09-06 08:00 | -
494 | 660031 | (IETF) Web Real Time Communication access to IMS (draft-holmberg-sipcore-auth-id) | IMS_WebRTC-CT | 3 | Rel-12 | C1-IETF | 2014-09-12 08:00 | 2014-12-09 17:00 | 25% |  | christer.holmberg@ericsson.com | 2014-12-04 08:00
619 | 580013 | IMS Stage 3 IETF Protocol Alignment - phase 6 | IMSProtoc6 | 1 | Rel-12 | C1;C3;IETF | 2012-12-07 08:00 | 2014-12-09 17:00 | 67% | CP-120905 | Alcatel-Lucent | 2012-12-06 08:00 | -
623 | 660038 | (IETF) CT1 part of IMS Stage 3 IETF Protocol Alignment - phase 6 (draft-ietf-insipid-session-id) | IMSProtoc6 | 2 | Rel-12 | C1-IETF | 2014-09-12 08:00 | 2014-12-09 17:00 | 25% |  | christer.holmberg@ericsson.com | 2014-12-04 08:00 | work in progress
1134 | 660032 | (IETF) (Small) Technical Enhancements and Improvements for Rel-12 (draft-ietf-insipid-session-id) | TEI12_IETF | 1 | Rel-12 | C1-IETF | 2014-06-13 08:00 | 2014-12-09 17:00 | 50% |  | Alcatel-Lucent | 2014-12-04 08:00 | work in progress