## IMT schedule for 3GPP
PCG# | TSG# | deadline date | event | remarks
|  | 2020-02-12 | OPs to send Form A to ITU-R secretariat | In fact it is proposed (by ATIS) to perform this action in December 2019.
| 87 | 2020-03-19 | GCS clause of ITU-R Rec [IMT-2020] available | Listing all required specs. No TRs, no test specs (??). Should include any late performance specs (from RAN4).
| 87 | 2020-03-20 | Rel-16 stage 3 freeze | Triggers production of any v16.0.0 versions for specs not yet promoted from Rel-15 by virtue of approved Rel-16 CRs.
44 |  | 2020-04-05 | MCC sends first draft Excel list of GCS to PCG | List will show all GCS specs (including any not yet under change control) with ex-TSGs#87 versions, ordered by clause number and Release. Cannot take into consideration post-TSGs#88 versions because CR records will not all be available in 3GU by this date.
44 |  | 2020-05-10 | PCG to convey any remarks on the draft list to MCC and empowers MCC to produce final "anticipated GCS" showing correct version numbers. | MCC updates 3GU database accordingly
|  | 2020-05-29 | MCC sends second draft Excel list of GCS to PCG | To contain corrections as necessary. This list will still not contain definitive version numbers (see below). This step only needed if PCG found errors in the first draft.
|  | 2020-06-10 | PCG to convey any remarks on the second draft list to MCC | This step only needed if PCG found errors in the first draft.
|  | 2020-06-12 | Deadline for upload of RAN WG meeting tdoc lists | Allowing for post-WG-meeting decision making and MCC processing. RAN ITU-R ad hoc group to present the overview section of the 3GPP 5G to RAN#88, ideally pre-approved by correspondence.
|  | 2020-06-12 | MCC to review list of Rel-15 & -16 CRs to GCS specs being offered for approval to TSGs#88 | And thus estimate the probable post #88 version numbers
|  | 2020-06-12 | MCC to update any GCS spec titles not already definitively fixed (3GU)
| 88 | 2020-06-16 | MCC to have prepared final draft GCS with putative post-TSGs88 version numbers | List will reflect decisions at CT and RAN meetings, though GCS believed to contain only RAN specs, no CT or SA specs)
| 88 | 2020-06-17 | MCC to have prepared final "anticipated GCS" with putative post-TSGs88 version numbers | List will reflect decisions at SA meeting - MUST BE DONE BY 12h CEST LATEST in order for MCC to manually update the GCS list. In fact, if no SA specs in GCS, can be done earlier, say evening of 2020-06-17
| 88 | 2020-06-17 | MCC to dispatch final "anticipated GCS" to ITU-R secretariat. Also titles and synopsis elements, and the overview clause of Rec M.[IMT-2020]. | To arrive by 16h latest. 3GPP ITU-R ad hoc will need to have prepared these elements in advance and TSG RAN#85 to have approved them.
|  | 2020-06-17 | OPs to send Cert B to ITU-R Secretariat | To arrive by 16h latest
| 88 | 2020-06-19 | End of TSG meetings, all CRs finalized. Rel-16 protocols frozen. | Enables definitive production of revised specs. Not possible to correct "anticipated GCS" at this stage.
|  | 2020-06-26 | MCC to have uploaded 90% of post CT & SA#88 specs | Normal schedule. All necessary specs for first post-TSG#88 WG meetings to be available. OPs can begin transposition exercise from the moment that specs start to become available, possibly as early as 2020-06-19. Specs for transposition can be found at https://www.3gpp.org/ftp/3guInternal/3GPP_ultimate_versions_to_be_transposed/sentToDpc/
|  | 2020-07-03 | MCC to have uploaded 90% of post RAN#88 specs and 100% of CT and SA specs | Normal schedule
|  | 2020-07-06 | MCC to have made available all post-#88 GCS specs | In practice, since OPs cannot transpose all specs at once, this deadline implies that, say, 50% of the GCS specs be available. Remainder to be available by 2020-07-10.
|  | 2020-07-06 | First post TSGs#88 WG meetings start (SA3-LI, SA6, followed by other SA and CT WGs) | Specs needed for these meetings ~ 10 days in advance, so CR implementation for these needs to be done in parallel with the GCS specs.
|  | 2020-07-10 | MCC to have uploaded 100% of post RAN#88 specs | Normal schedule (ncluding any remaining GCS specs from #88)
| 89 | 2020-09-18 | End of RAN#89 meeting, all remaining specs (performance) finalized.
|  | 2020-10-02 | MCC to have uploaded 90% of post RAN#89 specs | Prioritize the few "late" performance specs not stable at RAN#88. (Normal schedule)
|  | 2020-10-08 | OPs to complete their transpositions and to provide individual lists of their transposed publications' URLs to ITU-R secretariat. | Includes the "late" specs ex RAN#89
|  | 2020-10-08 | OPs to send Cert C to ITU-R secretariat
|  | 2020-10-09 | MCC to have uploaded 100% of post RAN#89 specs | Normal schedule