## Slide 1: CT view on Rel-18 Planning
Mr Lionel Morand
CT Chair, Orange

## Slide 2: Release 18 Planning
Current freeze dates
  Stage 2: March '23 (TSG#99)
  Stage 3: December '23 (TSG#102)
  ASN.1/OpenAPI: March '24 (TSG#103)
Discussion on Release 18 stage 2 extension at SA#98
  Possible outcomes:
    No shift of the Stage 2 freeze date, WI exception for remaining work
    Shift the stage 2 freeze date by X Months

## Slide 3: CT view on possible Rel-18 Stage 2 extension
Hardline:
  Ensure 9 months between stage 2 freeze and the stage 3 freeze
    To grant enough time for TSG cross-coordination.
    For CT, Stage 2 requirements coming from SA2 but also from SA3, SA4, SA5, SA6
  Ensure 3 months between stage 3 freeze and ASN.1/OpenAPI freeze
    To avoid protocol backward incompatible change and provide some buffer protocol consolidation
  Common CT stage 3/RAN functional freeze date and ASN.1/OpenAPI freeze date
If Stage 2 freeze date is maintained
  The number of Stage 2 WI exceptions should remain "under control"
    Having too many stage 2 WI exceptions would mean a stage 3 done in only 6 months
If Stage 2 freeze date shifted by X months
  Stage 3 AND ASN.1/OpenAPI freeze dates MUST be shifted by X months
  No (or few) stage 2 WI exceptions should be allowed after the stage 2 freeze

## Slide 4: Thank You!
Lionel Morand
3GPP TSG CT Chair
ETSI
lionel.morand@orange.com