## Tdoc cover sheet
3GPP TSG CT WG1 Meeting #124e |  | C1-203718
Source: | Nokia, Nokia Shanghai Bell
Title: | Work plan for the CT1 part of eMONASTERY2
Agenda item: | 17.
Document for: | Discussion

## Contributions plan
|  | Topic | Responsible company in stage-3 | is done? | Impacted Specs | CT1 meeting #; tdoc(s) # | Open issues | Related stage2 tdoc(s) # | Comments
1 | Extensions to other services | Solution 1 on restricting incoming private communications |  | 0 | 24.484 configuration management 24.379 call control MCPTT 24.281 call control MCVideo 24.282 call control MCData 24.483 | CT1#119; C1-194820,C1-194821,C1-1950610, C1-195062 | MCVideo Missing | S6-190698 (CR 0119r1, Cat B, Rel-16, 23.281)
2 |  | Solution 2 on implicit activation and deactivation of functional alias(es) |  | 0 | 24.379 | CT1#121; C1-198801 | MCVideo Missing | S6-190815 (CR 0122r2, Cat B, Rel-16, 23.281)
3 |  | Solution 3 on client performs automatic group affiliation/de-affiliation |  | 0 | 24.483, 24.379, 24.484 | CT1#122: C1-200409; C1-200410; C1-200886 | MCVideo Missing | S6-190859 (CR 0123r3, Cat B, Rel-16, 23.281)
|  | Extension of Solution 4 on support of functional aliases in private calls and private emergency calls (config data for allowed) | Nokia | 0 |  |  |  | S6-191556 (CR0226r2, Cat B, Rel-17, 23.379)
4 |  | Solution 14 on MC service server limits the number of simultaneous successful service authorisations |  | 0 | 24.379, 24.484, 24.281, 24.282 | CT1#122: C1-201056 | MCVideo Missing | S6-190934 (CR 0131, Cat B, Rel-16, 23.281)
5 |  | Solution 31 on client activation and deactivation functional aliases based on location |  | 0 | 24.281 24.484,24.483 | CT1#120; C1-196814,C1-196815,C1-196816 | MCVideo Missing | S6-190939 (CR 0132, Cat B, Rel-16, 23.281)
6 |  | Solution 33 on communication priority for functional aliases | Nokia | 0 | 24.281, 24.282, 24.484 configuration management 24.379 call control MCPTT | CT1#121; C1-198659 | MCData,MCVideo Missing | S6-191444 (CR0134r1, Cat B, Rel-17, 23.281) S6-191445 (CR0166r1, Cat B, Rel-17, 23.282)
7 | MCVideo | Solution 18 on support of functional aliases for video emergency group calls together with solution 23 on support functional alias controlling for MCVideo services |  | 0 |  |  |  | S6-190721 (CR 0124r1, Cat B, Rel-16, 23.281), S6-190878 (CR 0127r4, Cat B, Rel-16, 23.281)
8 |  | Solution 20 on support of functional aliases for video group calls together with solution 23 on support functional alias controlling for MCVideo services |  | 0 |  |  |  | S6-190878 (CR 0127r4, Cat B, Rel-16, 23.281)
9 |  | Solution 21 on support of functional aliases for private and emergency video calls together with solution 23 on support functional alias controlling for MCVideo services |  | 0 |  |  |  | S6-190865 (CR 0125r3, Cat B, Rel-16, 23.281), S6-190866 (CR 0126r3, Cat B, Rel-16, 23.281)
10 | Partially covered in Rel-16 in stage 2 | Solution 10 on location information for a specific functional alias |  | 0 |  |  |  | S6-191182 (CR 0203r3, Cat B, Rel-16, 23.280)
11 |  | Solution 26 on user requests application layer priorities |  | 0 |  |  | MCPTT stage 2 part not concluded within Rel-16 | S6-190710 (CR 0196r1, Cat B, Rel-16, 23.379), S6-190711 (CR 0121r1, Cat B, Rel-16, 23.281), S6-190712 (CR 0141r1, Cat B, Rel-16, 23.282)
12 |  | Solution 29 on call forwarding/transfer for private calls +media security for private call forwarding |  | 0 |  |  | MCPTT stage 2 part not concluded within Rel-16 | S6-191185 (CR 0210r2, Cat B, Rel-16, 23.379) S6-191230 (CR 0211r3, Cat B, Rel-16, 23.379) S6-191990 (CR 0229r7, Cat B, Rel-17, 23.379) S6-200332 (CR 0246r5, Cat B, Rel-17, 23.379) S6-200573 (CR 0253r1, Cat F, Rel-16, 23.379) S6-200574 (CR 0254r1, Cat A, Rel-17, 23.379) S6-200821 (CR 0253r3, Cat F, Rel-16, 23.379) S6-200822 (CR 0254r3, Cat A, Rel-17, 23.379) S6-201208 (CR 0262r1, Cat B, Rel-17, 23.379) S6-201209 (CR 0263r1, Cat B, Rel-17, 23.379)
13 |  | IP connectivity extensions:P2P using FA to address the target MC service user, P2P remote establishment, withdrawal a connection by an authorized user, control of QoS based on per packet priority, MCData Group communication |  | 0 | 24.282 | CT1#122:C1-201022; CT1#123: C1-20288, 3C1-202884C1-202885 |  | S6-190864 (CR 0148r3, Cat B, Rel-16, 23.282), S6-190727 (CR 0149r1, Cat B, Rel-16, 23.282), S6-191231 (CR 0159r3, Cat B, Rel-16, 23.282) (to be completed in Rel-17) S6-191508 (CR0162r2, Cat B, Rel-17, 23.282) S6-191615 (CR0164r4, Cat B, Rel-17, 23.282) S6-191616 (CR0165r4, Cat B, Rel-17, 23.282) S6-191850 (CR 0189r3, Cat B, Rel-17, 23.282) S6-191849 (CR 0182r2, Cat B, Rel-17, 23.282)
14 |  | Alias vs Group | Nokia |  |  |  |  | S6-191606 (CR0207r3, Cat B, Rel-17, 23.280) Resolve editor's note: How the functional alias to group binding impacts existing group call requests is FFS. S6-192085 (CR 0224, Cat C, Rel-17, 23.280) S6-192206 (CR 0238r1, Cat B, Rel-17, 23.379)
15 |  | Solution 11 on MC service server prevents de-affiliation when using a specific functional alias(es) (subclause 7.11) | [5 empty] | S6-191450 (CR 0209r1, Cat B, Rel-17, 23.280)
16 |  | Solution 12 on list of functional aliases used by affiliated group members (subclause 7.12) | [5 empty] | S6-191555 (CR 0208r2, Cat B, Rel-17, 23.280)
17 | FA as target | Use of functional alias as target address used for establishing MCData, especially SDS, FD | [5 empty] | S6-191557 (CR 0163r2, Cat B, Rel-17, 23.282) S6-191991 (CR 0181r3, Cat B, Rel-17, 23.282)
18 |  | MCVideo communications using functional alias to address target user | [5 empty] | S6-200936 (CR 0257r1, Cat B, Rel-17, 23.280 S6-200897 (CR 0142r6, Cat B, Rel-17, 23.281) S6-201191 (CR 0145r1, Cat F, Rel-17, 23.281)
19 |  | MCPTT communications using functional alias to address target user – security aspects. Impacts also on call forwarding und call transfer procedures. | [5 empty] | S6-200553 (CR 0251r3, Cat F, Rel-16, 23.379) S6-200554 (CR 0252r3, Cat A, Rel-17, 23.379)
20 |  | MCData communications using functional alias to address target user – security aspects | [5 empty] | S6-200898 (CR 0256r3, Cat F, Rel-17, 23.379) S6-201190 (CR 0261r1, Cat F, Rel-17, 23.379) S6-201225 (CR 0269r1, Cat B, Rel-17, 23.379)
21 |  | Use of functional alias as target address used for establishing an MCPTT emergency private call | [5 empty] | S6-201188 (CR 0230r1, Cat F, Rel-17, 23.282) S6-201187 (CR 0229r1, Cat F, Rel-17, 23.282) S6-201186 (CR 0228r1, Cat F, Rel-17, 23.282) S6-201189 (CR 0231r1, Cat F, Rel-17, 23.282)
22 |  | Functional alias to be used by a called MC service user for private communications | [5 empty] | S6-191846 (CR 0225r3, Cat B, Rel-17, 23.379)
23 | Missing requirements | Requirements TS 22.179 [R-5.6.3-015] and [R-6.7.4-016] are only partially fulfilled. | [5 empty] | S6-191446 (CR 0228r1, Cat F, Rel-16, 23.379)
24 |  | Call deflection from requirements TS 22.179 [R-5.6.3-015] and [R-6.7.4-016] | [5 empty] | S6-200333 (CR 0247r5, Cat B, Rel-17, 23.379)
25 |  | Requirements [R-6.8.7.2-007], [R-6.8.7.2-008], [R-6.8.7.2-009], [R-6.8.7.2-010] are only partly fulfilled by CRs S6-190710, S6-190711 and S6-190712. The network behaviour (e.g. authorisation, downgrading) and required configuration data needs to be completed. | [5 empty] | S6-190710, S6-190711 and S6-190712 S6-192345 (CR 0221r4, Cat F, Rel-17, 23.280) S6-192225 (CR 0190r2, Cat F, Rel-17, 23.282) S6-192212 (CR 0191r1, Cat B, Rel-17, 23.282) S6-192346 (CR 0193r2, Cat B, Rel-17, 23.282) S6-192347 (CR 0240r2, Cat B, Rel-17, 23.379) S6-192348 (CR 0137r2, Cat B, Rel-17, 23.281)
26 |  | Solution 32 on functional alias and alternative addressing scheme for interworking with GSM-R |  | 0 |  |  | MCPTT stage 2 part not concluded within Rel-16, Rel-17 considered also incomplete | S6-191187 (CR 0035r2, Cat B, Rel-16, 23.283), (only management aspects covered) S6-191457 (CR0036r2, Cat B, Rel-17, 23.283) S6-191561 (CR0048r2, Cat B, Rel-17, 23.283) S6-192208 (CR 0049r3, Cat B, Rel-17, 23.283) S6-191458 (CR0037r2, Cat B, Rel-17, 23.283) S6-191460 (CR 0050r1, Cat B, Rel-17, 23.283)
27 |  | Interconnection-MCPTT (private, group) | [5 empty] | S6-192207 (CR 0239r1, Cat B, Rel-17, 23.379)
|  | Interconnection - MCVideo (private, group) | [5 empty] | S6-200182 (CR 0143r1, Cat F, Rel-17, 23.281) S6-200183 (CR 0144r1, Cat F, Rel-17, 23.281)
red=posponed to Rel-18 (for now)
0

## Incoming LSs
Incoming liaision statements (LS)
Tdoc # | Topic | Reply LS | Related tdocs: CT1 meeting #; tdoc(s) # | Open issues | Comments