3GPP TSG RAN meeting #102									           RP-232858

Edinburgh, GB, Dec 11-15, 2023

## Status Report to TSG

Title:			Status report for WI NR NTN (Non-Terrestrial Networks) enhancements; rapporteur: Thales

Agenda item:			9.3.2.7

| WI / SI Name | Rel-18 NR NTN (Non-Terrestrial Networks) enhancements |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| included in this status report | Study Item: No | Core part: Yes | Performance part: Yes |  | Testing part: No |
| Acronym | NR-NTN-enh |  |  |  |  |
| Unique ID | 941006 |  |  |  |  |
| TSG Tdoc of latest approved WI/SI description (if any) | RP-232669 |  |  |  |  |
| Target Completion Date (indicate if changed) | Study Item: | Core part: 12/2023 -> 03/2024 | Performance part: 06/2024 | Testing part: |  |
| Overall Completion level | Study Item: | Core part: Overall: 95% RAN1: 100% RAN2: 100% RAN3: 100% RAN4: 90% | Performance Part: Overall: 10% RAN4: 10% | Testing part: |  |

Note: Overall completion level percentage numbers should use one of the colors below:

- xx%: Normal progress, no RAN plenary action needed

- xx%: Progress behind schedule, may need RAN plenary intervention. If so, SR should clearly define requested action

- xx%: Progress critically behind, RAN plenary shall intervene. SR should define requested action

Source:

| Leading WG |  | RAN2 |
| --- | --- | --- |
| Rapporteur | Name | Nicolas Chuberre |
|  | Company | Thales |
|  | Email | Nicolas.chuberre@thalesaleniaspace.com |

## 1	Work plan related evaluation

| Do you want to modify the time budget for this WI/SI compared to what was endorsed at the last RAN meeting? | Yes |
| --- | --- |

If you answered No:	Then please remove the Excel file from the zip file of this status report.

If you answered Yes:	Then please fill out the attached Excel template to request a modification of the time 		budgets for your WI /SI. The Excel table has to be filled out for all affected RAN WGs and 		up to the target date of the WI/SI. The basis are the endorsed time budgets of the last 		RAN meeting. Please highlight all changes of the values.
		One time unit (TU) corresponds to ~ 2 hours in the meeting.
		If this status report covers a WI with Core and Performance part, then please have one 		line for each in the attached Excel table.
		Note: If no Excel table is attached, then this means no time budget change.

Extension request by one quarter for RAN4 as per the exception sheet in RP-232859

## 2.	Detailed progress in RAN WGs since last TSG meeting (for all involved WGs)

NOTE: Agreements and Open issues impacted cross-TSG aspects shall be explicitly highlighted

## 2.1	RAN1

#### 2.1.1	Agreements

- RAN1#114bis meeting, Xiamen, China, October 9 – 13, 2023:

FR2-NTN:

Agreement

Endorse the attachment in R1-2310650 with the following updates:

- Row 3 column P: the following FFS text should be marked in black:

  - FFS signaling details, e.g. whether RSRP threshold for PUCCH repetition for Msg4 HARQ-ACK is signaled as a relative or absolute value

- Row 3 column P: add the RAN plenary agreement as in row 2

- Row 5 column P: add square brackets as shown below

  - value range: [-265…+265 (-26,5 µs/s… +26,5 µs/s)]

Working assumption

For PRACH configuration for operation in FR2-NTN, Table 6.3.3.2-4 of TS 38.211 is used as baseline.

FFS: Whether further modifications would be needed

Conclusion

For operation in FR2-NTN, the value range in ms for K_offset and K-MAC shall be the same as for Rel-17 NR over NTN.

Working assumption

For operation in FR2-NTN, use a reference SCS of 15 kHz for the indication of K_offset and K_MAC.

Working assumption:

For operation in FR2-NTN, for cell search procedure, at least Case D in TS 38.213 is used to allow FDD operation in bands defined by FR2-NTN without any update to SSB pattern.

FFS: whether Case E can also be used

Conclusion

For operation in FR2-NTN and for Rel-18, no additional MAC CE TCI application delay is introduced to facilitate mechanical beam steering with VSAT.

Working assumption

From RAN1 perspective, for operation in FR2-NTN, the granularity used for TA reporting is the same as corresponding to the reference subcarrier spacing applied for K_offset.

RACH-less handover:

Observation

There is potential RAN1 discussion for the following aspects to support the RAN2 work on RACH-less handover.

- The pre-allocated grant is provided with association to SSBs

- The mapping between type-1 CG and SSBs in CG-SDT can be the baseline of how to configure pre-allocated grant mapped to SSBs

Coverage enhancement for NR NTN:

Agreement

For RSRP threshold to determine whether capability of PUCCH repetition on common PUCCH resources is reported or not,

- Option 1: the RSRP threshold is signaled as an absolute value, i.e. not as a relative value to RSRP threshold for R17 Msg3 repetition

Agreement

With respect to dynamic indication of PUCCH repetition factor by using DAI field in DCI format 1_0 with CRC scrambled by TC-RNTI for UE that has indicated capability of the PUCCH repetition, when multiple repetition factors are configured:

- the 1st/2nd/3rd/4th configured repetition factors are mapped to ‘00’, ’01’, ‘10’, ‘11’ of 2 bits DAI field, respectively. When the 3rd and/or the 4th repetition factors is/are not configured, the corresponding codepoint(s) (i.e., ‘10’ and/or ‘11’) is(are) not used.

Agreement

The TP below is endorsed for TS38.212 clause 7.3.1.2.1.

- Reason for change

A: How to map the configured repetition factors to DAI bits in DCI format 1_0 with CRC scrambled by TC-RNTI to indicate the PUCCH repetition factor is unclear in the current specification.

B: The use of DAI bits in DCI format 1_0 with CRC scrambled by TC-RNTI to indicate the PUCCH repetition factor should be conditioned on that the UE has indicated capability of PUCCH repetition on common PUCCH resources.

- Summary of change

A: Regardless of the number of configured repetition factors, two bits are used for indication of repetition factor. If two or three repetition factors, the third and/or the fourth codepoint(s) is/are not used.

B: It is clarified that the use of DAI bits in DCI format 1_0 with CRC scrambled by TC-RNTI to indicate the PUCCH repetition factor is conditioned on that the UE has indicated capability of PUCCH repetition on common PUCCH resources.

- Consequences if not approved

A: gNB and UE may have misunderstanding of an indicated repetition factor.

B: The DAI field in DCI format 1_0 with CRC scrambled by TC-RNTI is incorrectly defined to carry repetition information to UEs that have not indicated support for repetition.

##### 7.3.1.2.1 Format 1_0 <Unchanged parts omitted> The following information is transmitted by means of the DCI format 1_0 with CRC scrambled by TC-RNTI: <Unchanged parts omitted> - Downlink assignment index – 2 bits - 2 bits indicating the number of repetitions for PUCCH as defined in clause 9.2.6 of [5, TS38.213] according to Table 7.3.1.2.1-4, if the higher layer parameter numberOfPUCCHforMsg4HARQACK-RepetitionsList is configured with at least two values and the UE has indicated capability of PUCCH repetition on common PUCCH resource [8, TS38.321]; - otherwise, reserved. <Unchanged parts omitted> Table 7.3.1.2.1-4: Number of repetitions NPUCCHrepeat as a function of 2 bits of Downlink assignment index field Bit field; NPUCCHrepeat. 00; First value of numberOfPUCCHforMsg4HARQACK-RepetitionsList. 01; Second value of numberOfPUCCHforMsg4HARQACK-RepetitionsList. 10; Third value of numberOfPUCCHforMsg4HARQACK-RepetitionsList (if provided). 11; Fourth value of numberOfPUCCHforMsg4HARQACK-RepetitionsList (if provided). <Unchanged parts omitted>

Agreement

Update higher layer parameters for R18 NR NTN PUCCH repetitions as follows, and include the RAN plenary agreement in the comment column.

| Parameter name in the spec | Description | Value range | Default value aspect | Per (UE, cell, TRP, …) |
| --- | --- | --- | --- | --- |
| numberOfPUCCHforMsg4HARQACK-RepetitionsList | Indicates the number of repetitions for PUCCH transmission for Msg4 HARQ-ACK. If multiple values are configured, a single value from the configured values is indicated in DCI. | One or more of {1,2,4,8} except for {1} | NA | Per cell |
| rsrp-ThresholdPUCCHforMsg4HARQACK | If this parameter is configured, and numberOfPUCCHforMsg4HARQACK-RepetitionsList is provided, UE capable of PUCCH repetition for Msg4 HARQ-ACK reports the capability of PUCCH repetition for Msg4 HARQ-ACK only if measured RSRP is lower than the configured RSRP threshold indicated by this parameter. If this parameter is not configured, and numberOfPUCCHforMsg4HARQACK-RepetitionsList is provided, UE capable of PUCCH repetition for Msg4 HARQ-ACK reports the capability of PUCCH repetition for Msg4 HARQ-ACK [This RSRP threshold is an absolute value / a relative value of the RSRP threshold for R17 Msg3 repetition] | TBD RSRP-range | NA | Per cell |

Network verified UE location for NR NTN:

Agreement

The actual index difference between subframe j and subframe i defined in RAN1#114 agreement on UE Rx-Tx time difference is reported in 10 bits with a value range up to 542 subframes.

Working assumption

The DL timing drift due to Doppler over the service link associated with the UE RX-TX time difference measurement period is reported with the following range, granularity and bits allocation:

| Value range | Granularity | Bits allocation |
| --- | --- | --- |
| [-265...+265 (i.e: -26.5 μs/s..+26.5 μs/s -26.5 μs/s..+26.5 μs/s)] | 0.1 µs/s | 10 bits |

Note: value range is given in unit of corresponding granularity

Agreement

For network verified UE location in NTN common TA, parameters (ta-Common, ta-CommonDrift, ta-CommonDriftVariant, Epoch time) can be reported from gNB to LMF.

Agreement

Endorse the following TP for TS 38.215

--- unchanged text omitted ---

5.2.3	gNB Rx – Tx time difference

| Definition | The gNB Rx – Tx time difference is defined as TgNB-RX – TgNB-TX Where: TgNB-RX is the Transmission and Reception Point (TRP) [18] received timing of uplink subframe #i containing SRS associated with UE, defined by the first detected path in time. TgNB-TX is the TRP transmit timing of downlink subframe #j that is closest in time to the subframe #i received from the UE. Multiple SRS resources can be used to determine the start of one subframe containing SRS. The reference point for TgNB-RX shall be: - for type 1-C base station TS 38.104 [9]: the Rx antenna connector, - for type 1-O or 2-O base station TS 38.104 [9]: the Rx antenna (i.e. the centre location of the radiating region of the Rx antenna), - for type 1-H base station TS 38.104 [9]: the Rx Transceiver Array Boundary connector. The reference point for TgNB-TX shall be: - for type 1-C base station TS 38.104 [9]: the Tx antenna connector, - for type 1-O or 2-O base station TS 38.104 [9]: the Tx antenna (i.e. the centre location of the radiating region of the Tx antenna), - for type 1-H base station TS 38.104 [9]: the Tx Transceiver Array Boundary connector. In NTN, the gNB Rx – Tx time difference at the uplink time synchronization reference point [5] is reported. |
| --- | --- |

--- End of text proposal ---

Agreement

Endorse the following TP for TS38.215 clause 5.1.46.

| Reason for change: | Modify the definition of UE Rx – Tx time difference subframe offset to align with the RAN1#114 agreement. |
| --- | --- |
| Summary of change: | Modify the definition of UE Rx – Tx time difference subframe offset - modify measurement naming - add more clarification to the defintion |
| Consequences if not approved: | The definition of this new UE measurement is ambiguous. It does not reflect the RAN1#114 agreement. And the wording used (i.e. “actual”) is not consistent with specification language |

--- unchanged text omitted ---

5.1.46	UE Rx – Tx time difference subframe offset

| Definition | UE Rx – Tx time difference offset is the actual index difference between subframe #j and subframe #i of the subframes used for the UE Rx – Tx time difference measurement as defined in Clause 5.1.30, where uplink subframe #j is the closest in time to the DL subframe #i received from a transmission point (TP) [18]. UE Rx – Tx time difference subframe offset is the index difference which represents the number of subframes between the uplink subframe #j and the uplink subframe #i, where uplink subframe #j is the closest in time to the DL subframe #i received from a transmission point (TP) [18] as defined in Clause 5.1.30 and i is the index of the DL subframe used for the UE Rx – Tx time difference measurement as defined in Clause 5.1.30. For frequency range 1, the reference point for UE Rx – Tx time difference subframe offset measurement shall be the same antenna connectors as defined in Clause 5.1.30 for the UE Rx – Tx time difference measurement. For frequency range 2, the reference point UE Rx – Tx time difference subframe offset measurement shall be the same antenna as defined in Section 5.1.30 for of the UE Rx – Tx time difference measurement. |
| --- | --- |
| Applicable for | RRC_CONNECTED |

--- End of change ---

Agreement

Endorse the following TP for TS 38.215:

| Reason for change: | Modify the definition of DL timing drift in clause 5.1.47 to align with the RAN1#114 agreement. |
| --- | --- |
| Summary of change: | Add more clarification to the defintion of DL timing drift |
| Consequences if not approved: | The definition of this new UE measurement is ambiguous |

--- unchanged text omitted ---

5.1.47	DL timing drift

| Definition | DL timing drift measurement is defined as the variation rate of the downlink delay in ppm due to the as estimated service link Doppler as the DL timing to be shifted due to Doppler over the service link associated with over the UE Rx-Tx time difference measurement period. For frequency range 1, the reference point for the DL timing drift measurement shall be the Rx antenna connector of the UE. For frequency range 2, the reference point for the DL timing drift measurement shall be the Rx antenna of the UE. |
| --- | --- |
| Applicable for | RRC_CONNECTED |

--- End of change ---

Agreement

Adopt the following TP for TS 38.214:

Reason for change:; Existing spec TS 38.214 is still pending with bracket on “actual” which is not used so far in the specifications. Summary of change:; The detailed definition of UE Rx – Tx time difference subframe offset as well as the DL timing drift has already been defined in section 5.1.46 and 5.1.47 of TS 38.215. Then, to avoid the duplicated description and potential mismatch, in TS 38.214, it is sufficient to update the spec with simply citation on the offset and timing drift defined in TS 38.215. Consequences if not approved:; Duplicated description and potential mismatch between specs. ----------------------------------------TP: Start of TP for TS 38.214 V18.0.0--------------------------- #### 5.1.6.5 PRS reception procedure <Unchanged parts are omitted> The UE may be configured to measure and report, via higher layer parameter [undetermined NTN related parameter] subject to UE capability, UE Rx-Tx time difference measurements on a PRS resource associated with a dl-PRS-ID. T, and report the UE shall report the [actual] index difference between the uplink subframe j and closest in time DL subframe i, UE Rx – Tx time difference subframe offset and the DL timing drift due to Doppler over the radio link associated with the UE RX-TX time difference measurement period as described in [7, TS 38.215]. <Unchanged parts are omitted> --------------------End of TP for TS 38.214 V18.0.0 ---------------------------------

- RAN1#115 meeting, Chicago, US, November 13 – 17, 2023:

Agreement

The higher layer parameters in R1-2312424 is endorsed.

TP for TS 38.300

Agreement

The TP below for TS38.300 is endorsed from RAN1 perspective.

- Note: further text may be provided later for NTN-specific PUSCH DMRS bundling.

---------------------- TEXT PROPOSAL BEGIN ----------------------

16.14.X	 Support for NR NTN coverage enhancements

To improve NR uplink coverage in NTN, the following enhancements are supported:

- PUCCH repetition for Msg4 HARQ-ACK:

- Supported number of transmissions are 1, 2, 4, 8.

  - If a single value from {2, 4, 8} is configured via SIB, the configured repetition factor is applied.

  - If multiple values from {1, 2, 4, 8} are configured via SIB, one of the multiple values is indicated in DAI field of DCI format 1_0 with CRC scrambled by TC-RNTI.

- The existing mechanism on repetition slot counting (as in section 9.2.6 of TS 38.213) is applied.

- Frequency hopping mechanism in R15/16/17 defined for PUCCH transmission for Msg4 HARQ-ACK, in every slot is applied.

- A RSRP threshold can be configured via SIB when the number of repetitions is configured by SIB. If the RSRP threshold is configured, UE capable of PUCCH repetition for Msg4 HARQ-ACK reports the capability of PUCCH repetition for Msg4 HARQ-ACK via Msg3 PUSCH only if measured RSRP is lower than the configured RSRP threshold. If the RSRP threshold is not configured, UE capable of PUCCH repetition for Msg4 HARQ-ACK reports the capability of PUCCH repetition for Msg4 HARQ-ACK via Msg3 PUSCH.

- The repetition factor applied to Msg4 HARQ-ACK is used also for any PUCCH transmission before dedicated PUCCH resource is provided.

- NTN-specific PUSCH DMRS bundling

16.14.x	Verification of UE location

For UE location verification based on multi-RTT with single satellite in NTN, at least the following UE and gNB measurements specified in [38.215] are reported: gNB receive-transmit time difference at the uplink time synchronization reference point, UE receive-transmit time difference, UE receive-transmit time difference subframe offset and DL timing drift.

The assistance information reported to the CN may include ephemeris information including accurate satellite position and velocity at the time of multi-RTT measurement, and common TA parameters (ta-Common, ta-CommonDrift, ta-CommonDriftVariant, Epoch time).

*** Unchanged text is omitted ***

---------- TEXT PROPOSAL END ---------

Text Proposal for TS38.300:

<UNCHANGED TEXT IS OMITTED>

---------------------- TEXT PROPOSAL BEGIN ----------------------

16.14.X	 Support for NR NTN coverage enhancements

- NTN-specific PUSCH DMRS bundling enhancement that enables DMRS bundling in presence of timing drift, whereby UE maintains phase continuity considering effects of transmission delay variation between UE and uplink time synchronization reference point to enable improved channel estimation.

---------- TEXT PROPOSAL END ---------

Agreement

The LS in R1-2312670 is endorsed and will be revised and is agreed in R1-2312681 to change the source to RAN1, with the attachment in R1-2312669.

FR2-NTN

Agreement

Confirm working assumption from RAN1#114-bis on reference SCS for K_offset and K_MAC.

Agreement

Confirm working assumption from RAN1#114-bis on the TA reporting granularity.

Agreement

The working assumption for cell search procedure is replaced with the following, and confirmed:

- For operation in FR2-NTN, for cell search procedure, Case D and Case E in TS 38.213 are used to allow FDD operation in bands defined by FR2-NTN without any update to SSB pattern.

Agreement

Confirm the working assumption from RAN1#114-bis on the PRACH configuration.

Working assumption

For PRACH configuration for operation in FR2-NTN, Table 6.3.3.2-4 of TS 38.211 is used as baseline.

FFS: Whether further modifications to the PRACH configuration Table would be needed

Agreement

Create an LS response for RAN4 with the following text, and copy the relevant RAN1 agreements and conclusions made for FR2-NTN in the LS:

Overall description

RAN1 would like to thank RAN4 for their LS R4-2305926 (R1-2304309) on the operation of NR over NTN in frequency bands above 10 GHz.

RAN1 have had discussion on the topic over the past meetings and have reached a number of agreements, but some topics are still under consideration. The topics still under consideration are mainly related to the timing requirements associated to operation in bands defined by FR2-NTN. To help RAN1 progressing on the topic, it would be appreciated if RAN4 could provide the timing requirements for supporting NR over NTN in bands defined by FR2-NTN.

Actions:

RAN1 respectfully asks RAN4 to provide a response to the above question in order to aid the RAN1 discussions related to timing accuracy requirements.

Final LS is agreed in R1-2312553.

RACH-less handover in NR NTN

Agreement

The text proposal for TS 38.213 in section 3.3 in R1-2312377 is endorsed in principle. Draft CR to be reviewed and endorsed in RAN1#116.

- Note: further discuss the TP for search space, repetition, power control, collision with valid PRACH occasion, TDD aspect, etc.

- Note to the TS 38.213 editor: it is not expected to capture this TP for RAN#102

Conclusion

Which CORESET to use for RACH-less handover can be further discussed at a future meeting.

### Coverage enhancement for NR NTN

Conclusion

For frequency hopping of PUCCH repetition on common PUCCH resources for NR NTN, no specification change in Rel-18.

Conclusion

For PUCCH repetition on common PUCCH resources for NR NTN, for the case of SI modification and no DCI format 1_0 with CRC scrambled by a TC-RNTI, no further discussion for this issue in Rel-18.

Conclusion

There is no consensus on the following for PUCCH repetition on common PUCCH resources in Rel-18 NR NTN.

- Whether to introduce dynamic indication when a single repetition factor is configured

- Whether to enhance capacity of common PUCCH resources

- Whether to extend previous agreements for common PUCCH resources to dedicated PUCCH resources

Conclusion

No further discussion is necessary for the following for PUCCH repetition on common PUCCH resources in Rel-18 NR NTN.

- UE behavior when no repetition factor is configured

- UE behavior if configured repetition factor(s) does not include ‘1’, the RSRP threshold is configured, and the measured RSRP < the RSRP threshold

Conclusion

There is no consensus on antenna switching-related enhancements for PUSCH DMRS bundling in Rel-18 NR NTN.

Agreement

The TP below is endorsed for TS38.213

- Reason for change: It was agreed that this WI can support PUCCH repetition not only for Msg4 HARQ-ACK but also for subsequent PUCCH e.g., to report HARQ-ACK corresponding to a PDSCH conveying RRC configuration parameters.

- Summary of change: It is clarified that the indicated repetition factor is applied to any PUCCH transmission by using common PUCCH resource.

- Consequences if not approved: It is unclear which repetition factor is applied to PUCCH transmissions after Msg4 HARQ-ACK transmission when dedicated PUCCH resource configuration is not provided.

9.2.6 PUCCH repetition procedure A UE that does not have dedicated PUCCH resource configuration and indicates a capability to transmit with repetitions a PUCCH with HARQ-ACK information [11, TS 38.321], determines a number of slots for repetitions of a PUCCH transmission with HARQ-ACK information based on an indication by numberOfPUCCHforMsg4HARQACK-RepetitionsList. If numberOfPUCCHforMsg4HARQACK-RepetitionsList provides more than one values, the DAI field in a DCI format 1_0 with CRC scrambled by a TC-RNTI scheduling a PDSCH reception that includes a UE contention resolution identity indicates from the more than one values. The number of repetitions is applied to any PUCCH transmission before dedicated PUCCH resource configuration is provided. The UE transmits each repetition of the PUCCH using frequency hopping as described in Clause 9.2.1. In the remaining of this clause, a UE without dedicated PUCCH resource configuration determines a value of a parameter, if applicable, according to Table 9.2.1-1 and/or as specified above in this clause for a PUCCH transmission with repetitions from the UE. *** Unchanged parts are omitted ***

Conclusion

For PUCCH repetition on common PUCCH resources, with respect to the number of symbols and the first symbol for PUCCH transmission, no specification change in Rel-18.

### Network verified UE location for NR NTN

Agreement

Confirm the following working assumption with the following modification: replacing µs/s with ppm and removing the brackets.

Working assumption

The DL timing drift due to Doppler over the service link associated with the UE RX-TX time difference measurement period is reported with the following range, granularity and bits allocation

| Value range | Granularity | Bits allocation |
| --- | --- | --- |
| i.e: |  | 10 bits |

Note: value range is given in unit of corresponding granularity

Working assumption

For UE RX-TX measurements in NTN, the time of the beginning of a subframe is determined by assuming the time durations of the OFDM symbols at the receiver are the same as defined in 38.211.

#### 2.1.2	Remaining Open issues

Further corrections may be discussed/implemented at next meeting. However none of these would require category B CR (addition of feature)

FR2-NTN:

- PRACH configuration for operation in FR2-NTN

- Other topics related to the timing requirements associated to operation in bands defined by FR2-NTN

- Waiting for RAN4 LS reply on timing requirements for FR2-NTN

Network verified UE location: -

- Determination of the time of the beginning of a subframe for UE RX-TX measurements in NTN

## 2.2	RAN2

#### 2.2.1	Agreements

- RAN2#123-bis meeting, Xiamen, China, October 9 – 13, 2023:

Coverage enhancements

RAN2 continues to focus on a solution to address PUCCH repetition for Msg4 HARQ-ACK in Msg3 only for random access procedure triggered by RRC connection establishment, RRC connection re-establishment or RRC connection resume, i.e. to CCCH/CCCH1 (in the future we can consider random access during RRC connected, depending on RAN1)

No explicit NW indication to enable/disable PUCCH repetition for Msg4 HARQ-ACK besides the needed signalling for number of repetition, RSRP configuration in SIB (meaning that if these parameters are signalled, PUCCH repetition for Msg4 HARQ-ACK is enabled)

Network verified UE location

Add in NR-Multi-RTT-SignalMeasurementInformation the measurements relevant to RAN1 agreed offset (e.g., the actual index difference between subframe j and subframe i and the DL timing drift due to Doppler over the service link associated with the UE RX-TX time difference measurement period) with detailed definition referred to RAN1 agreements.

Ephemeris and corresponding time information (e.g., epochTime) is not provided by the UE. How this is provided to the LMF is up to RAN3 (can come back to see whether the problem that the UE could use a different ephemeris – and then should report it back to the gNB – is a valid case to consider)

RAN2 assumes that FG 44-3 should be an LPP capability to be reported to the LMF (no need for other capabilities)

RAN2 understands that to solve the mirror point issue, the measurements reported by RAN should include the information of the cells on the opposite side

Send LS to RAN3 clarifying the scenarios of satellite switch cases and ask them how to handle it. Ask question whether existing cause value can be used to handle the satellite switch specially in case of RAN node has not changed.

Include in the LS the RAN2 assumption that we expect no LPP impact (in HO/satellite switch). It is up to RAN3 to decide if any NRPPa signaling update is needed.

NTN-TN and NTN-NTN mobility and service continuity enhancements

The maximum number of TN coverage area information is 32 (5 bits)

RAN2 will not specify restrictions on TN coverage description (i.e., description of TN coverage is left to NW implementation). The signalled TN coverage can describe areas not currently covered by the satellite cell footprint (FFS how to reflect this in the specification)

TN coverage information can be broadcast by both (quasi)earth-fixed and earth-moving cells

The working assumption “We do not introduce new triggers making the UE reacquire the TN coverage information from SI” in Rel-18 is confirmed

The new SIB including the TN coverage information is not an essential SIB for NTN. An NTN-capable UE does not need to consider the cell barred if it is unable to acquire the SIB when scheduled.

Legacy SI update procedure will be used when the network updates the TN coverage information (can further check for moving cell case)

For location-based CHO for earth-moving cells, re-use the procedure from cell reselection as baseline to derive the candidate cell’s reference location as the cell moves (FFS on how to signal the needed parameters, e.g. ephemeris and Epoch time)

Upon T304 expiry, the UE does not fallback to RACH-based HO.

Preallocated UL grant must be configured with an associated RSRP threshold.

UE relies on T304 and RRC Re-establishment procedure to address RACH-less HO failure in Rel-18 NTN (as in LTE). No new NTN-specific enhancements are introduced. If TAT expires, the UE follows the legacy procedures, regardless of the RACH-less HO configuration. RAN2 understands that the NW can ensure a proper configuration for TAT and T304 values (up to NW implementation, no need to capture this in the specs).

As for RACH-less LTM, for RACH-less NTN, the UE determines successful reception of its first UL data based on receiving a PDCCH addressing the UE’s C-RNTI in the target cell scheduling a new transmission as first UL transmission. Can be either DL assignment or UL grant addressed to same HARQ process for the “new transmission”. RAN understands this does not exclude the possibility to use a Contention Resolution MAC CE but this will not be used as a determination of the RACH less HO completion

We follow the LTE baseline for when UE starts the PTAG timeAlignmentTimer in NTN RACH-less HO (option 1 in R2-2311318)

Combination of RACH-less HO with time-based CHO is supported in Rel-18 NTN for both Configured and Dynamic Grant. For the Dynamic Grant case this should be configured by the NW only when the is no risk of confusion about which beam to use (up to NW implementation).

RAN2 confirms satellite switching with unchanged PCI is only applicable on quasi-earth fixed system

Only 1 target satellite information (i.e. NTN-config) of serving cell is provided in SIB19. FFS on exact signalling

SMTC configuration of target satellite needs further discussion: FFS on whether and how to provide the SMTC configuration of target satellite; FFS on how to handle the SMTC adjustment.

We support soft satellite switching in Rel-18

There will be an indication (FFS if explicit or implicit) whether hard switch or soft switch is used.

At least soft satellite switching, network provides SSB information of target satellite to UE. FFS on the details: options include e.g. indicating a time offset/information or indicating a different SSB index for the target satellite (FFS for Hard satellite switch)

In soft satellite switching, UE can start synchronizing with target satellite before T-service of source satellite.

We introduce a T-start which indicates the earliest occasion when the UE can start synchronizing with target satellite (actual signalling is FFS). In soft switch scenario, T-start of target satellite is earlier than T-service of source satellite (FFS if T-start is also used for hard satellite switch)

For soft satellite switching, the exact time when the UE starts synchronizing with target satellite (between T-start and T-service) is up to UE implementation

UE is not required to connect to source satellite when the UE switches to target satellite.

Common signalling (e.g. using servingCellConfigCommon) for the purpose of (C)HO in NTN is not supported in Rel-18

Email discussions

- [Post123bis][306][NR-NTN Enh] 38.300 running CR (Thales)

- [Post123bis][307][NR-NTN Enh] 38.331 running CR (Ericsson)

- [Post123bis][308][NR-NTN Enh] 38.321 running CR (Interdigital)

- [Post123bis][309][NR-NTN Enh] 38.304 running CR (ZTE)

- [Post123bis][310][NR-NTN Enh] EU caps running CR (Intel)

- [Post123bis][311][NR-NTN Enh] 37.355 running CR (CATT)

- [Post123bis][312][NR-NTN Enh] Unchanged PCI (CMCC/Apple)

- RAN2#124 Chicago/USA, November 13th - 17th, 2023:

Coverage enhancements

Use the LCID codepoint within the Rel-18 extension space to indicate the request/capability of PUCCH repetition for Msg4 HARQ-ACK.

Feature combination of NTN, RedCap and eRedCap should be supported for Msg3-based early indication via LCID: 6 LCID codepoints will be specified for this in Rel-18

Network verified UE location

Legacy procedure can be reused to indicate the LMF about the happening of CHO.

NTN-TN and NTN-NTN mobility and service continuity enhancements

To define a new UE capability, e.g., locationBasedCondHandoverNTN-r18, to indicate whether the UE supports location-based conditional handover for moving cell in NTN bands (which involves the calculation of the present reference location from ephemeris and one reference location at epoch time, as specified in TS 38.331).

This locationBasedCondHandoverNTN-r18 capability is defined per Band, optional with signaling capability, and N/A for FDD/TDD DIFF and FR1/FR2 Diff. This is defined as part of §4.2.7.2 BandNR parameters in TS 38.306.

An editor’s note is added to locationBasedCondHandoverNTN-r18 to capture “FFS whether any change or update is needed considering how locationBasedCondHandover-r17 is defined”, or whether location-based conditional handover for moving cell refers to source cell, target cell or both.

For UE capabilities that indicate the support of satellite switch with re-sync (i.e., unchanged PCI) with hard and soft switch, two UE capabilities are introduced with some dependencies: hardSatelliteSwitch-Resync-NTN-r18 can be supported by itself; but if UE supports softSatelliteSwitch-Resync-NTN-r18, UE is required to also indicate the support of hardSatelliteSwitch-Resync-NTN-r18.

A UE only supporting hardSatelliteSwitch-Resync-NTN-r18 will be able to perform hard satellite switch with re-sync (after T-service) in a NW supporting soft satellite switch with re-sync (and then broadcasting “T-start” and "SSB time offset"). To be reflected in the description of hardSatelliteSwitch-Resync-NTN-r18

SIB19 can be broadcast in TN cells to provide satellite assistance information for NTN neighbour cells (e.g., ntn-NeighCellConfigList-r17).

SIB19 is not an essential SIB when provided in a TN serving cell, i.e. UE does not consider the TN serving cell as barred if it fails to acquire SIB19 (no spec impact)

UE in RRC_IDLE/INACTIVE is not required to ensure having a valid version of SIB19 in a TN serving cell (no spec impact)

The exact time of reacquiring SIB19 for UE in RRC_IDLE/INACTIVE in TN serving cell is up to UE implementation (no spec impact)

UE in RRC_CONNECTED does not start T430 when SIB19 is provided in a TN cell (consider clarifying “Upon receiving SIB19 in a NTN cell …” in 5.2.2.4.21)

The SFN and subframe numbers of epoch time indicated in SIB19 in TN serving cell are based on the timing of the serving cell (no spec impact)

If the epoch time indicated in SIB19 in TN serving cell is absent, UE considers the epoch time as the end of SI window where this SIB19 is scheduled in the TN serving cell (no spec impact).

If the validity duration indicated in SIB19 in TN serving cell is absent, the UE follows R17 behaviour (left to UE implementation) (no spec impact)

Legacy SI update procedure will be used for earth moving cell when the network updates the TN coverage information (no spec change)

The new SIB containing TN coverage area information belongs to Other SI, either periodically broadcast, broadcast on-demand, or sent in a dedicated manner.

When SIB19 is broadcast in a TN cell, SIB19 belongs to Other SI in TN, and is provided by either periodically broadcast, broadcast on-demand, or a dedicated manner.

Separate capability description for location-based measurement initiation for quasi-earth-fixed system and earth moving system is used in 38.304 to align with the capability definition in 38.306.

Adopt the terminology “Skipping TN measurement” in both 38.304 and 38.306

For dynamic grant case, beam information is mandatorily included in the RACH-less HO command.

In NTN RACH-less HO, for dynamic grant case, the beam information included in RACH-less HO command is an SSB index (not tci-stateid).

Similar to LTE, UE shall not trigger RACH for SR when rach-lessHO is configured. LTE text is used as a baseline

UE releases preallocated grant after successful RACH-less HO completion without additional signaling from the network. Nothing is needed to address this issue in MAC.

When CG for initial UL transmission is configured, CG occasions mapping to SSB (i.e. ssb position in burst), is optional. If it is not provided, the RACH-less HO configuration is applicable in all SSBs. Adopt similar wording to CG-SDT in the RRC field description.

If CG for initial UL transmission is configured, UE starts to monitor PDCCH according to existing DRX behaviour on the selected SSB from RACH-less HO configuration after initial UL transmission.

If CG is configured in RACH-less HO, UE uses the earliest available CG occasion associated to the selected SSB for the initial UL transmission. Spec impact is FFS and can use CG-SDT as baseline (if applicable)

It is up to NW to configure HARQ mode A or B. RAN2 understands that HARQ mode A should be used the HARQ process of the initial UL transmission using CG

We don’t introduce a threshold-based mechanism for Dynamic Grant

Check during the final [Post124] review of the joint NTN/mIAB MAC CR for RACH-less HO if the CG-LTM-retransmission timer for the initial UL transmission using CG introduced in LTM can be used for NTN as well (possibly with updates to the value range)

Target cell provides the DG so that the UE can complete the RACH-less CHO within the (t1, t2) time window (no spec impact, up to NW implementation)

For time-based only CHO (no RSRP-based criterion) the UE shall start monitoring for DG from t1

For CHO in EMC a new event (e.g. condEventD2) is introduced.

New event comprises a reference location and distance threshold for source and target cell.

Ephemeris and epochTime information for candidate CHO cell is also provided in RRC Reconfiguration (configuring the CHO) within the configuration prepared by the source cell (outside of the new event).

If ephemeris and epochTime information for candidate CHO cell is not provided in RRC Reconfiguration, the UE may use the corresponding neighbour information from SIB19.

Introduce one new target satellite configuration, e.g. ntn-TargetSatConfig, (but we can keep the current terminology in the running CR) and provide the NTN-config of the target satellite in it for the specific signaling format about the target satellite information in SIB19. The presence of this information indicates that satellite switch without PCI change is supported

At least for soft switch, there needs to be an “SSB time offset” between the source and the target satellite. “SSB time offset” is specified as a new IE, with the same format as “offset” in SSB-MTC4

Target satellite SSB tracking is handled autonomously by the UE based on the provided SSB time offset

The “SSB time offset” between the source and the target satellite should be provided in SIB19

Support implicit indication to inform UE it is hard switch or soft switch case

For soft satellite switch, as a baseline, it is sufficient to provide the “SSB time offset” of the target satellite in SIB19. (Can come back in the next meeting to check whether a different SSB index for the target satellite can optionally be provided)

T-start is explicitly signalled (same format as T-service). If T-start is not signalled, T-start is assumed to be equal to T-service, i.e. hard switch.

For R18 we clarify that signalling a T-start higher than T-service is an unforeseen case and the UE will assume T-start = T-service

During satellite switching procedure, UE should reset the L3 filter for serving cell RRM measurement and RLM, and it’s up to UE implementation (i.e. no RAN2 spec impact).

If UE receive the HO command before UE initiates the satellite switching procedure (i.e. before the time point of satellite switching), UE will initiate the HO procedure immediately.

Both CHO and satellite switching procedure can be configured simultaneously.

When both CHO (for a different cell) and satellite switching procedure are configured, the UE initiates the procedure that triggers earlier; it's up to UE implementation if both procedures are triggered at the same time.

This feature will be called “satellite switch with re-sync”

RACH-less satellite switch procedure as shown in Figure-1 in R2-2313877 is endorsed as the baseline to be further checked in the CR review

Check in the RRC CR review whether the UE may need to acquire SIB19 immediately when UE acquires DL sync of target satellite

A UE supporting TA reporting may trigger TAR and TAR-SR based on network configuration (as in legacy)

It is up to NW implementation to signal T-start, e.g. if it does not want to receive UL TX before T-service (if there is no T-start, UL TX cannot happen before T-service)

We don’t introduce specific changes (e.g. no new indication in SIB19) to a support RACH-based procedure but this does not exclude the possibility for the NW to trigger PDCCH order

Email discussions

- [Post124][301][NR-NTN Enh] 38.300 CR (Thales)

- [Post124][302][NR-NTN Enh] 38.331 CR (Ericsson)

- [Post124][303][NR-NTN Enh] 38.321 CR (Interdigital)

- [Post124][304][NR-NTN Enh] 38.304 CR (ZTE)

- [Post124][305][NR-NTN Enh] 37.355 CR (CATT)

- [Post124][306][NR-NTN Enh] 38.305 CR (Qualcomm)

- [Post124][312][NR-NTN Enh/mIAB] MAC CR on RACH-less HO (Interdigital)

- [Post124][313][NR-NTN Enh] UE Caps CRs (Intel)

#### 2.2.2	Remaining Open issues

Further corrections may be discussed/implemented at next meeting. However none of these would require category B CR (addition of feature)

## 2.3	RAN3

#### 2.3.1	Agreements

- RAN3#121-bis meeting, Xiamen, China, October 9 – 13, 2023:

Endorsed CR

- R3-235057	(BL CR to 38.300) Stage 2 BL CR for NR NTN (Ericsson, CATT, Thales, Huawei, Samsung, ZTE, Nokia, Nokia Shanghai Bell, Qualcomm Incorporated)	draftCR

- R3-235839	(BLCR to 38.413) BL CR for NR NTN (Nokia, Nokia Shanghai Bell, Ericsson, Thales, ZTE, Omnispace, TTP, CATT, Hughes Network Systems, Huawei, Lockheed Martin, Intelsat, ESA, Samsung, Qualcomm Incorporated)	CR1008r3, TS 38.413 v17.6.0, Rel-18, Cat. B

- R3-235840	(BLCR to 38.423) BL CR for NR NTN (Huawei, Ericsson, Thales, ZTE, Omnispace, TTP, Nokia, Nokia Shanghai Bell, CATT, Hughes, EchoStar, CMCC)	CR0933r8, TS 38.423 v17.6.0, Rel-18, Cat. B

Endorsed TP

- R3-235945	(TP for TS38.413 BL CR and TS38.423 BL CR) miscellaneous Correction on the BL CRs (Nokia, Nokia Shanghai Bell)

- RAN3#122 meeting, Chicago, USA, November 13 – 17, 2023:

Endorsed CR

- R3-237058 (BL CR to 38.300) Stage 2 BL CR for NR NTN (Ericsson, CATT, Thales, Huawei, Samsung, ZTE, Nokia, Nokia Shanghai Bell, Qualcomm Incorporated)	draftCR

- R3-237060 (BLCR to 38.423) BL CR for NR NTN (Huawei, Ericsson, Thales, ZTE, Omnispace, TTP, Nokia, Nokia Shanghai Bell, CATT, Hughes, EchoStar, CMCC)	draftCR

- R3-237697 (BLCR to 38.413) BL CR for NR NTN (Nokia, Nokia Shanghai Bell, Ericsson, Thales, ZTE, Omnispace, TTP, CATT, Hughes Network Systems, Huawei, Lockheed Martin, Intelsat, ESA, Samsung, Qualcomm Incorporated) draftCR

Network verified UE location

For NTN UE location verification, we should assume a TRP is associated to a satellite.

Ephemeris info of the satellites should be configured to the LMF via OAM.

Association between the satellite and TRP ID should also be configured to LMF via OAM.

No consensus to have any enhancements to address Mirror positions ambiguity in R18.

It is proposed to introduce the Common TA Information and capture it in TP for BLCR on 38.455.

Reply to RAN2 that all the proposed scenarios from RAN2 in the LS are supported by current NRPPa.

#### 2.3.2	Remaining Open issues

Further corrections may be discussed/implemented at next meeting. However none of these would require category B CR (addition of feature)

## 2.4	RAN4

The applicable work plan in RAN4 can be found under R4-2300973

#### 2.4.1	Agreements

- RAN4#108-bis meeting, Xiamen, China, October 9 – 13, 2023:

UE RF

Agreement:

- Define the UE RF requirements based on the envelope of mathematical antenna model to cover both UE with mechanical steering antenna and UE with electronic steering antenna.

- FFS whether and how to capture the information in the TS.

Agreement:

- RAN4 to consider the following UE Types:

1/ Terminal Type 1 (Electronic steering antenna) with the following NFs:

- 2.5 dB NF (Class 1) - for both LEO and GEO;

- 6 dB NF (Class 2) - for LEO only.

2/ Terminal Type 2 (Mechanical steering antenna) with the following NFs:

- 2.5 dB NF (Class 1) – for both LEO and GEO.

Agreement:

- Reuse the existing RF requirement with Modulation limited up to 16QAM and optional to support 64QAM

Agreement/WF:

Take following information as working assumption for beam switching time:

Ø  For mechanical steering: the typical values can be 22 degree/second, 6~8 seconds (if 120 degrees steering is assumed) for inter-satellite beam switching.

Ø  For electronic steering: A typical value is FFS for beam steering.

BS RF/Demod

EISREFSENS_50M declaration

- Agreement:

The SAN reference sensitivity to be specified based on manufacturer declared value  EISREFSENS_50M  within a specified range

EISREFSENS_50M definition – GEO class SAN

- Agreement:

The interval for the declaration of EISREFSENS_50M for GEO class SAN shall be [-140] to [-149] as a starting point for decision in the next meeting

EISREFSENS_50M definition – LEO class SAN

- Agreement:

  - The interval for the declaration of EISREFSENS_50M for LEO class SAN shall be [-120] to [-129] as a starting point for decision in the next meeting

Agreement:

- Circular aperture antenna model for SAN and NTN UE is used in the co-existence study for Rel-18 NTN. Use of phased array antenna model needs further discussion.

- Remove the angle range limitation of ± 90° for NTN UE antenna.

- Equivalent satellite antenna aperture values for co-existence study:

| GEO | LEO-1200 | LEO-600 |
| --- | --- | --- |
| 5.9/3.66m (DL/UL) | 0.6/0.36 m (DL/UL) | 0.6/0.36 m (DL/UL) |

- Simulation of VSAT with 1.5m height can be covered by ESIM cases taking into account the agreement of Issue 1-1.

- Assume 1 dB of atmospheric losses and the scintillation losses in the co-existence study.

- To use FRF=2 with ideal polarization isolation for the coexistence study.

- Stick with TN 20% active ratio rather than changing the TN cell diameter and the Scaling Factors of TN to NTN

- Stick with previous agreements to continue study on cases with 90 and 25 degree elevation angles.

- Do not discuss on the change of TN ACLR & ACS values @ 17GHz at this stage and as the normal approach, ACIR values will be achieved first and ACLR and ACS values of NTN will be derived based on those ACIR when TN values @17GHz may be discussed and referred to.

- Use the flat ACIR model for both NTN & TN. 10 NTN UEs in UL and 1 TN UE in UL.

- Not to consider the NTN UL TxP increase as a potential way forward to improve LEO orbits in scenario 4 at this stage but noting in some scenarios those parameters may not satisfy the desired performance.

- Update simulation assumption document with latest agreements.

Agreement:

- While running the NTN-TN coexistence simulations, RAN4 should continue investigating why the TN UL results are so diverging (especially for 27GHz)

- Assume shadowing correlation between beams of the same satellite as 1.

- Companies are encouraged to share exact uplink Tx power control value used for calibration and as well to share UL TxP statistics and UL CLx-tile actual values between companies to align UL SINR.

-	Single beam UL SINR (no interference) should be 15 dB for all users in LEO! Moreover, some GEO users may be power limited.

Agreement:

- Update and use the table in Attachment 2 of R4-2316265 to collect results of the co-existence study of NTN in above 10GHz bands.

- Further discuss considerations on Scenario 5 taking into account related Issues in Topic 1.

Issue 1-1: Workplan

- Agreement

  - Workplan is agreed at RAN4#108-bis meeting.

| RAN4#108-bis Oct 2023 |  |
| --- | --- |
|  | Discussion and agreement on work plan. Initial round of discussion on performance requirements scope. Initial round of discussion on simulation assumptions. |
| RAN4#109 Nov 2023 |  |
|  | Second round of discussion on performance requirements scope. Second round of discussions on simulation assumptions. Initial round of simulation results collection and alignment. |
| RAN4#110 Feb 2024 |  |
|  | Finalize discussions on performance requirements scope. Discussions on CR split. Second round of simulation results collection and alignment. |
| RAN4#110-bis Apr 2024 |  |
|  | Finalize discussions on simulation assumptions. Third round of simulation results collection and alignment. Endorse draft CRs. |
| RAN4#111 May 2024 |  |
|  | Final round of simulation results collection and alignment. Agree formal CRs. |

Issue 2-1-1: Scenario

- Agreement

  - At least NGSO scenario to be considered for requirement definition, companies can check whether GSO can also be considered for NTN demod.

  - Focus on the mobility scenario assumed by RRM. (Mobility VSAT with LEO is not considered)

Issue 2-1-2: Channel model

- Agreement

  - For FR2-NTN, consider NTN-TDLA and/or NTN-TDL-C with down selection if necessary.

  - FFS delay and Doppler

  - For delay selection, consider the worst case based on typical angle selection, e.g. [30 degree].

  - How to derive the Doppler:

    - Option 1: Based on residual frequency error.

    - Option 2: Based on UE speed

      - FFS UE speed: [120km/h, 1000km/h], other Options are not precluded.

    - Interested companies are encourage to propose values for doppler and delay spread.

  - Other options are not precluded

Issue 3-1-1: Whether to define UE PDSCH demodulation performance requirements for above 10 GHz bands

- Agreement

  - Agree to define UE PDSCH demodulation performance requirements for above 10 GHz bands.

Issue 3-1-2: HARQ processes for above 10 GHz bands

- Agreement

  - FFS 16 HARQ process, 32 HARQ process, HARQ process disabled.

  - Interested Companies can provide further analysis for 16 HARQ process, 32 HARQ process, HARQ process disabled.

Issue 3-1-5: Whether to define UE CSI reporting requirements for above 10 GHz bands?

- Agreement

  - Do not consider PMI reporting and RI reporting.

  - Companies can provide feasibility analysis on CQI reporting under AWGN or fading channels.

Issue 3-2-1: Frequency/timing drift

- Agreement

  - Assumption: UE is assumed to do compensation for frequency and timing drift , and is not part of baseband processing for demod.

  - No frequency and timing drift are modelled in Rel-18 NTN UE requirements.

Issue 3-2-5: Receiver assumption

- Agreement

  - MMSE-IRC

Issue 3-2-6: Duplex

- Agreement

  - FDD

Issue 3-2-7: Payload

- Agreement

  - Transparent payload for both GSO and NGSO scenarios.

Issue 4-1-1: Which feature can be considered for SAN PUSCH demodulation performance requirements for above 10 GHz bands?

- Agreement

  - Define PUSCH with DFT-S-OFDM and CP-OFDM demodulation performance requirements for above 10 GHz bands.

  - FFS PUSCH repetition Type A, companies can do some analysis on the link budget.

  - Do not consider UL timing adjustment

Issue 4-1-2: Which format can be considered for SAN PUCCH demodulation performance requirements for above 10 GHz bands?

- Agreement

  - Define PUCCH format 0/1/2/3/4 demodulation performance requirements for above 10 GHz bands.

Issue 4-1-3: Which format can be considered for SAN PRACH demodulation performance requirements for above 10 GHz bands?

- Agreement

  - Define PRACH burst format B4/C2 demodulation performance requirements for above 10 GHz bands.

  - Do not consider PRACH burst format A2.

Issue 4-1-4: Whether to define SAN PUSCH demodulation performance requirements for DMRS bundling?

- Agreement

  - Define SAN PUSCH demodulation performance requirements for DMRS bundling for FR1 only if RF confirm that phase continuous is feasible.

Issue 4-1-5: Whether to define SAN PUCCH demodulation performance requirements for Msg4 HARQ-ACK?

- Agreement

  - Do not define PUCCH requirements Msg4 HARQ-ACK for NLOS channel.

Issue 4-1-6: Whether to define SAN demodulation performance requirements for network verified UE location?

- Agreement

  - Do not define SAN demodulation performance requirements for network verified UE location.

Issue 4-1-7: Whether to define SAN demodulation performance requirements for NTN-TN and NTN-NTN mobility and service continuity enhancement?

- Agreement

  - Do not define SAN demodulation performance for NTN-TN and NTN-NTN mobility and service continuity enhancement.

Issue 4-1-8: WID update

- Agreement

  - Update the impacted specification TS 38.108 for the performance part in the WID.

  - Update the objective of performance part WI to include coverage enhancement if necessary.

Issue 4-2-1: Frequency and timing drift

- Agreement

  - Assumption: UE will do pre-compensation for frequency and timing drift.

  - No frequency and timing drift are modelled in Rel-18 NTN SAN requirements.

Issue 4-2-2: SCS and channel bandwidth

- Agreement

  - Start demod work with 120 kHz SCS for initial alignment.  If RRM concludes that 120 kHz SCS is not feasible, then further discussion is needed at that time on how to proceed

  - FFS channel bandwidth

Issue 4-2-3: Antenna configuration

- Agreement

  - For the SAN Rx, we need both 1Rx and 2Rx.  For UE Tx, more discussion is needed to cover 1 Tx only or also 2Tx.

Issue 4-2-4: MCS & rank

- Agreement

  - Postpone to discuss this issue after channel model is selected.

  - Companies can do some link budget analysis until the next meeting.

Issue 4-2-5: SAN type

- Agreement

  - Prioritize to define SAN demodulation requirement for Type 2-O. FFS to define BS demodulation requirement for Type 2-H, pending on conclusion of RF core requirement.

Issue 4-2-6: Duplex

- Agreement

  - FDD

Issue 4-3-1: Test setup for SAN PUSCH demodulation performance requirements

- Agreement

  - Option 1 as the starting point, other options are not precluded.

    - Option 1:

| Parameter |  | Value |
| --- | --- | --- |
| Transform precoding |  | Disabled, Enabled |
| HARQ | Maximum number of HARQ transmissions | 4 |
|  | RV sequence | 0, 2, 3, 1 |
| DM-RS | DM-RS configuration type | 1 |
|  | DM-RS duration | single-symbol DM-RS |
|  | Additional DM-RS symbols | [Pos2] |
|  | Number of DM-RS CDM group(s) without data | 2 |
|  | Ratio of PUSCH EPRE to DM-RS EPRE | -3 dB |
|  | DM-RS port(s) | {0} [, {0, 1}] |
|  | DM-RS sequence generation | NID=0, nSCID =0 |
| Time domain | PUSCH mapping type | B |
| resource | Start symbol index | 0 |
|  | Allocation length | 10 |
| Frequency domain | RB assignment | Full applicable test bandwidth |
| resource | Frequency hopping | Disabled |
| TPMI index for 2Tx two-layer spatial multiplexing transmission |  | 0 |
| Code block group based PUSCH transmission |  | Disabled |
| PT-RS | Frequency density (KPT-RS) | 2, |
| configuration | Time density (LPT-RS) | 1, |

Issue 4-3-2: Test setup for SAN PUCCH demodulation performance requirements

- Agreement

  - Option 1 as the starting point, other options are not precluded.

    - Option 1:

Table 3:  Test parameters of PUCCH format 0

| Parameter | Test |
| --- | --- |
| Number of UCI information bits | 1 |
| Number of PRBs | 1 |
| First PRB prior to frequency hopping | 0 |
| Intra-slot frequency hopping | N/A for 1 symbol Enabled for 2 symbols |
| First PRB after frequency hopping | The largest PRB index – (Number of PRBs - 1) |
| Group and sequence hopping | neither |
| Hopping ID | 0 |
| Initial cyclic shift | 0 |
| First symbol | 13 for 1 symbol 12 for 2 symbols |
| Test metric | DTX to ACK probability ACK missed detection probability |
| Channel Model | [NTN-TDLA10-3000] |

Table 4:  Test parameters of PUCCH format 1

| Parameter | Test |
| --- | --- |
| Number of information bits | 2 |
| Number of PRBs | 1 |
| Number of symbols | 14 |
| First PRB prior to frequency hopping | 0 |
| Intra-slot frequency hopping | enabled |
| First PRB after frequency hopping | The largest PRB index – (nrofPRBs – 1) |
| Group and sequence hopping | neither |
| Hopping ID | 0 |
| Initial cyclic shift | 0 |
| First symbol | 0 |
| Index of orthogonal cover code (timeDomainOCC) | 0 |
| Test metric | NACK to ACK probability ACK missed detection probability |

Table 5   Test parameters of PUCCH format 2

| Parameter | Value |
| --- | --- |
| Modulation order | QSPK |
| Starting RB location | 0 |
| Intra-slot frequency hopping | N/A |
| Number of PRBs | 4 |
| Number of symbols | 1 |
| The number of UCI information bits | 4 |
| First symbol | 13 |
| DM-RS sequence generation | NID0=0 |
| Test metric | DTX to ACK probability ACK missed detection probability |

Table 6:  Test parameters of PUCCH format 2

| Parameter | Value |
| --- | --- |
| Modulation order | QSPK |
| First PRB prior to frequency hopping | 0 |
| Intra-slot frequency hopping | enabled |
| Frist PRB after frequency hopping | The largest PRB index – (Number of PRBs – 1) |
| Number of PRBs | 9 |
| Number of symbols | 2 |
| The number of UCI information bits | 22 |
| First symbol | 12 |
| DM-RS sequence generation | NID0=0 |
| Test metric | BLER |

Table 7:  Test parameters of PUCCH format 3

| Parameter | Test 1 | Test 2 |
| --- | --- | --- |
| Modulation order | QPSK |  |
| First PRB prior to frequency hopping | 0 |  |
| Intra-slot frequency hopping | enabled |  |
| First PRB after frequency hopping | The largest PRB index – (Number of PRBs – 1) |  |
| Group and sequence hopping | neither |  |
| Hopping ID | 0 |  |
| Number of PRBs | 1 | 3 |
| Number of symbols | 14 | 4 |
| The number of UCI information bits | 16 | 16 |
| First symbol | 0 | 0 |
| Test metric | BLER |  |

Table 8:  Test parameters of PUCCH format 4

| Parameter | Value |
| --- | --- |
| Modulation order | QPSK |
| First PRB prior to frequency hopping | 0 |
| Number of PRBs | 1 |
| Intra-slot frequency hopping | enabled |
| First PRB after frequency hopping | The largest PRB index – (Number of PRBs – 1) |
| Group and sequence hopping | neither |
| Hopping ID | 0 |
| Number of symbols | 14 |
| The number of UCI information bits | 22 |
| First symbol | 0 |
| Length of the orthogonal cover code | n2 |
| Index of the orthogonal cover code | n0 |
| Test metric | BLER |

Issue 4-3-3: Test setup for SAN PRACH demodulation performance requirements

- Agreement

  - Option 1 as the starting point, other options are not precluded.

    - Option 1:

      - PRACH format: C2 and B4

      - Test preamble configuration

| Burst format | SCS (kHz) | Ncs | Logical sequence index | v |
| --- | --- | --- | --- | --- |
|  | 60 | 69 | 0 | 0 |
| B4, C2 | 120 | 69 | 0 | 0 |

      - Frequency offset

        - [AWGN: 0Hz]

        - [Fading: 3000Hz]

      - Time error tolerance

        - 0.522μ+Tdelay where Tdelay is the largest delay of the propagation channel

      - Channel Model: [NTN-TDLA10-3000]

Test setup for UL coverage enhancement

- Agreement

  - Postpone this topic discuss to the next meeting.

RRM

### Issue 1-1: Common vs. Different UE uplink timing requirements for different UE types

Agreement:

- A common set of UE uplink timing requirements is defined for both UE types.

### Issue 1-2: Common vs. Different UE uplink timing accuracy requirements for different cases (Case-1/2/3)

Agreement:

- Further discuss achievable UE performance under different cases, FFS whether separate requirements needed or not.

### Issue 1-3: Further relaxation of Te_NTN for PRACH

Agreement:

- Define Te_NTN requirements for uplink signals/channels except for PRACH first, and come back to the issue to decide whether to introduce a different set of requirements for PRACH.

### Issue 1-5: Te_NTN for 120kHz

Agreement:

- FFS whether different set of Te_NTN requirements needed for UL SCS 120kHz.

### Issue 1-6: Te_NTN for 60kHz and 120kHz

Agreement:

Companies should provide ‘the exact value of Te_NTN and values assumed for X and Y’ and ‘the analysis result based on the following criterion.’ Otherwise, the values/proposals won’t be captured in the list of options.

Tg =  0.5*Tcp – (Td + Tp + Tr + Ta + Tf + Tm): an effective guard period in CP

  - Tcp: a length of CP for the given SCS of UL channel/signal

  - Td: UE downlink synchronization error for the given SCS of SSB (BW of PBCH DMRS, i.e. 20 PRBs)

  - Tp = Tp,ue + Tp,sat: a round trip propagation delay estimation error due to UE position and satellite position estimation errors

    - Tp,ue: a round trip propagation delay estimation error due to [X]m of UE position error

    - Tp,sat: a round trip propagation delay estimation error due to [Y]m of satellite position estimation error

  - Tr: TAC resolution error (from TS38.213)

  - Ta: TA adjustment accuracy error (from Table 7.3.2.2-1 of TS38.133)

  - Tf: an accumulated timing drift over 160ms due to a frequency offset of 0.1ppm

  - Tm: a margin needed at gNB receiver to accommodate any additional impairments if needed.

    - If a non-zero value is assumed in the proposal for Tm, the source of the impairments shall be provided too.

Technical analysis is required if any number will be provided for each of the components in the next meeting.

Whether the same or different values for different channels is contribution driven.

### Issue 2-1: RRC Idle and Inactive mobility

Agreement:

- For Type 1 UE, UE requirements on RRC Idle and Inactive mobility in intra-satellite scenario reuse FR1 NTN requirements with Ksatellite = 1 without inter-satellite measurement configuration.

- For Type 2 UE, UE requirements on RRC Idle and Inactive mobility in intra-satellite scenario reuse FR1 NTN requirements with Ksatellite = 1 without inter-satellite measurement configuration. Note: RRC Idle and Inactive mobility in inter-satellite scenario is out of scope according to the endorsed RP-232694.

### Issue 2-2: L1 measurements

Agreement:

- For Type 1 and Type 2 UE, L1-RSRP measurements are the same as the existing FR1 NTN requirements (9.5C).

### Issue 2-3: RLM

Agreement:

- For Type 1 UE, RLM requirements specified based the assumption that the measurement delay without beam sweeping scaling factor.

  - RLM requirements are the same as the existing FR1 NTN requirements (8.1C).

- For Type 2 UE, RLM requirements are the same as the existing FR1 NTN requirements (8.1C).

### Issue 2-5: L3 measurements

Agreement:

- For Type 1 UE and Type 2 UE, intra-satellite L3 measurements are the same as the existing FR1 NTN requirements defined in 9.2C and 9.3C without inter-satellite measurement configuration.

  - Existing UE capabilities need further clarification if these capabilities are expanded to NTN UE in Ka band, e.g.,

    - maxNumber-NGSO-SatellitesWithinOneSMTC-r17 and

    - parallelMeasurementWithoutRestriction-r17

  - Note: no inter-satellite L3 measurements based on the endorsed RP-232694.

### Issue 2-7: Measurement gap

Agreement:

- FR2 MG patterns are used for NTN in bands above 10 GHz.

### Issue 2-8: Scheduling and Measurement Restrictions

Agreement:

- Introduce scheduling and measurement restrictions only for mixed numerologies, as defined in FR 1 NTN, for the relevant FR2 NTN requirements, e.g.

  - radio link monitoring

  - L1-RSRP measurement

    - For Type 1 UE only

  - intra-frequency measurements

  - [inter-frequency measurements]

### Issue 2-9: Intra-satellite Handover

Agreement:

- For Type 1 UE, intra-satellite HO/CHO requirements are the same as the existing FR1 NTN HO/CHO requirements.

- For Type 2 UE, intra-satellite HO/CHO requirements are the same as the existing FR1 NTN HO/CHO requirements.

### Issue 2-10: Inter-satellite Handover

Agreement:

- For Type 1 UE, inter-satellite HO requirements are the existing FR1 NTN HO requirements with unknown cell condition plus an additional interruption component for UE beam refinement to address a concern about beam mis-alignment at the handover period due to the target satellite position error and/or UE beam steering error. TBD on the additional interruption length.

- For Type 2 UE, inter-satellite HO requirements are the existing FR1 NTN HO requirements with unknow cell condition plus an additional interruption component for the retuning of the mechanical beam direction. TBD on the additional interruption length.

- Postpone the discussion on inter-satellite CHO requirements on above 10GHz bands in future releases.

### Issue 2-11: Mechanical beam steering for Type 2 UE

Agreement:

- For Type 2 UE, in RAN4#109, discuss and decide whether/how to resolve issues due to non-zero beam switching delay from one satellite to another.

  - The beam switching delay can be an implicit or explicit UE capability.

  - The capability can be static or semi-static one. RAN4 to aim to decide the details (including any procedure modification, which may be needed in RAN1/2/, to accommodate Type 2 UE beam switching latency).

### Issue 3-1: RRC state

Conclusion:

- No discussion. Do not have to repeat discussions and make agreement on the issue already agreed by other working groups.

### Issue 3-2: Measurement period and accuracy requirements on RTD

Agreement:

- Measurement period requirements for UE Rx-Tx measurement is defined to reuse the existing TN requirements with MG as baseline.

  - Option 1: a higher Es/Iot than the existing one is needed, targeting the same accuracy as the existing one.

  - Other options are not precluded.

### Issue 3-3: Measurement period and accuracy requirements on DL timing drift

Agreement:

Discuss further on the interpretation on ‘UE Rx-Tx time difference measurement period’ as specified in RAN1 following conclusion.

RAN1 agreement in RAN1#114 meeting

- DL timing drift measurement is defined as the DL timing estimated to be shifted due to Doppler over the service link associated with the UE Rx-Tx time difference measurement period.

### Issue 3-4: Measurement accuracy requirements on UL timing drift

Agreement:

Discuss and decide the following in RAN4#109.

- Whether the requirements apply when the total autonomous variation applied by the UE in the timing advance during a measurement period exceeds a threshold (e.g. 5*Tp)

### Issue 4-1: TN to NTN cell reselection

Agreement:

- FFS: whether/how to define TN to NTN cell reselection.

### Issue 4-2: NTN to TN cell reselection

Agreement:

- UE is allowed to skip TN neighbour cells measurement in an area where there is no coverage of the frequency based on the provided TN cell coverage information and UE GNSS position information. FFS whether and how to implement it RAN4 CR.

- FFS on how to enhance NTN-to-TN cell reselection in case of mismatch between practical TN cell coverage and TN cell coverage information provided by serving cell.

### Issue 4-3: NTN to NTN time-based measurement initiation for cell reselection in earth-moving cell

Agreement:

Further discuss the requirements on time-based measurement initiation for cell reselection in earth-moving cell based on following Options:

- Option 1: For NTN to NTN time-based measurement initiation for cell reselection in earth-moving cell, the existing RRC idle/inactive mode requirements referring to ‘t-service’ are reused.

- Option 2: Enhance the requirements on time-based measurement initiation for cell reselection in earth-moving cell

  - Introduce coverage information of serving cell for helping UE to assess the available time left for cell reselection measurement before UE leaves the coverage area of serving cell

- Option 3: For earth-moving cell, time-based measurement initiation may only apply to hard satellite switch in RAN2 design. (Nokia)

### Issue 4-4: NTN to NTN location-based measurement initiation for cell reselection in earth-moving cell

Agreement:

- For NTN to NTN location-based measurement initiation for cell reselection in earth-moving cell, RAN4 to define the requirements based on the existing requirements on ‘4.2C Cell Re-selection for NR UE for Satellite Access,’ and introduce a new definition of reference location and an extra location margin.

### Issue 4-5: NTN to NTN higher priority frequency layer in earth-moving cell

Conclusion:

- No discussion in RAN4#108bis

### Issue 4-6: Autonomous SMTC adjustment in RRC Idle/Inactive mode

Agreement:

- For autonomous SMTC adjustment in RRC Idle/Inactive mode, no specific UE requirement is defined.

### Issue 5-1: NTN to NTN RACH-less (C)HO

Agreement:

- RACH-less handover delay requirement consists of ‘RRC procedure delay + Interruption time,’ i.e. = TRRC + TInterrupt, where  TInterrupt = Tprocessing + Tsearch + T∆ + Tmargin + TIU.

  - Tsearch: the definition and values are the same as that in 6.1C.1.2.2 in NTN HO.

  - Tprocessing: the definition and values are the same as that in 6.1C.1.2.2 in NTN HO.

  - T∆: the definition and values are the same as that in 6.1C.1.2.2 in NTN HO.

  - Tmargin: the definition and values are the same as that in 6.1C.1.2.2 in NTN HO.

  - TIU is the interruption uncertainty in acquiring the first UL transmission resource, which can be a configured grant based PUSCH, dynamic grant based PUSCH, SR on PUCCH, according to NW configuration and scheduling, or PRACH if no SSB mapping to pre-allocated grant has RSRP above the threshold while T304 is running.

- The RACH-less handover delay requirement applies to

  - both known and unknown cases

  - both intra-satellite and inter-satellite handover cases

  - both intra-frequency and inter-frequency target cell cases

- The RACH-less handover delay requirement is applicable only when the UE is provided with all essential information of the target satellite as the existing NTN handover requirement, i.e.

  - (from 6.1C.1.2 of TS38.133) The requirements apply provided that UE has the valid and applicable parameters of ephemeris information, common TA, DL and UL Polarization information, K offset , and K mac  for target NR SAN cell during D handover, otherwise interruption time may be longer than the requirements in clause 6.1C.1.2.2.

### Issue 5-2: NTN to NTN Satellite switching without PCI change

Agreement:

- For satellite switching without PCI change,

  - define requirements for both hard and soft switch scenarios.

    - TBD on how to define hard/soft satellite switch without PCI change (which will be determined mostly based on further clarification expected to be made by RAN2)

  - define requirements for PRACH-based and for without RACH performed solution.

  - The above does not necessarily mean that a common requirement formula cannot be defined. e.g. requirements for each case can be represented by a common formula with different definitions of respective components.

    - Starting point of the interruption time for the switch is t-Service, FFS other starting point needs to be considered for other cases depending on RAN2 progress

    - Ending point of the interruption time for the switch is PRACH transmission for PRACH-based case and [first UL transmission excepting PRACH for without RACH performed solution]

- Interruption time for the hard switch is defined as Tinterrupt = Tsearch + TIU + Tprocessing + T∆ + Tmargin

  - Tsearch = [Trs] ms

  - Tprocessing = [5] ms

  - T∆, Tmargin and TIU are same as existing requirements

- FFS Interruption time for soft switch

- FFS on

  - whether/how to define requirements resulting from separate link switch time instances for UL and DL.

    - Note: the starting and ending may be revisited depending outcome of discussions

  - whether/how to define UE behavior (e.g. skipping/relaxation of L1/L3 measurement and evaluation) during the switch.

### Issue 5-3: NTN to NTN time and location-based trigger CHO enhancements

Agreement:

- Define time and location-based NTN to NTN CHO requirements without L3 measurement criteria by modifying the current NTN to NTN CHO requirements.

- RAN4#109 meeting, Chicago, USA, November 13 – 17, 2023:

UE RF

Issue 1-1 NTN UE power class/types definition

Agreement:

- Define the requirements based on the following UE types

| UE class | UE type | Type description |
| --- | --- | --- |
| Fixed VSAT | 1 | Fixed VSAT supporting GSO and LEO with mechanical steering antenna. |
|  | 2 | Fixed VSAT supporting GSO and LEO with electronical steering antenna. |
|  | 3 | Fixed VSAT supporting LEO only with electronical steering antenna. |
| Mobile VSAT | 4 | Mobile VSAT supporting GSO with mechanical steering antenna. |
|  | 5 | Mobile VSAT supporting GSO with electronical steering antenna. |
| Note: Assuming that UE has single beam towards one single satellite at a given time. |  |  |

- UE capabilities for Rel-18 NTN UE

  - The following new UE capabilities will be specified

    - Capability signalling to distinguish electronic or mechanical steering antenna

    - Capability signalling to distinguish fixed or mobile VSAT

  - Reuse the capability of NTN_ScenearioSuppot_R17 to distinguish LEO, GSO or both

Issue 1-2: Mapping between NF and NTN UE power class/types

Agreement:

Fixed VSAT:

Electronic steering

Class 1: 2.5 dB NF  (LEO and GSO)

Class 2: 6 dB NF  (LEO only)

Mechanical steering

Class 1: 2.5 dB NF  (LEO and GSO)

Mobile VSAT:

electronic steering

Class 1: 2.5 dB NF  (GSO)

mechanical steering

Class 1: 2.5 dB NF  (GSO)

Issue 1-3: the necessity of introduction of NTN UE capable of both electronic steering and mechanical steering and how reflect in the above UE types.

Agreement:

- For the hybrid beam steering capable NTN UE, one clarification note is suggested to be added in 38.133 and 38.101-5 that the requirement could follow either electronic or mechanical beam steering requirements depending on the declared UE types.

Issue 1-4: network signalling for barring certain VAST access

Agreement: Specify a network IE to signal that network supports either a mobile VSAT UE, a fixed VSAT UE or both in Ka band.

Issue 2-1: How to define the on-axis EIRP limit

Agreement:

- maximum EIRP limit is 76.2dBm.

- The maximum TRP limit for NTN UE follows the regulatory requirements, including both ECC and FCC requirements.

Issue 2-2: Transmit power assumption for each UE types

Agreement:

- for each UE type, single value for minimum EIRP limit for certain elevation angle and FFS for the exact value;

- If UE is capable of communicating with both GSO and LEO, to follow the minimum EIRP for worse case.

Issue 2-3: MPR and A-MPR requirement for VSAT

Agreement:

- Not to introduce MPR and A-MPR requirement for NTN VSAT

- To use NS value approach to indicate the regional requirement if necessary

Issue 2-4: freq error requirement for NTN VSAT

Agreement: Reuse the existing FR1 NTN UE freq error requirement [+/-0.1ppm with 1ms]

Issue 2-5: EVM requirement for NTN VSAT

Agreement: postpone the support of Pi/2 BPSK for NTN VSAT in Rel-18 into future release

Issue 2-6:  Other transmitter signal quality requirement for NTN VSAT

Agreement:

- Do not define the following requirements

  - carrier leakage requirement for NTN VSAT

  - legacy TN UE in-band emission for NTN VSAT

  - EVM equalizer spectrum flatness requirement for NTN VSAT

Issue 2-7:  Transmitter dynamic range requirement for NTN VSAT

Agreement: The following requirements need be specified.

- The minimum output power

- The OFF output power

- The transition period requirement

- Power control requirement,

Issue 2-8 OBW

Agreement: follow the existing requirement of TS 38.101-2

Issue 2-9 SEM requirement

Agreement:

Option 1:

- Proposal 1:

- for the out-of-band emission requirement, propose to use the ITU-R SM.1541-6, Annex 5 OoB domain emission limits for space services (earth and space stations) as starting point and further discuss any modification if necessary (e.g. to keep consistency with other regional out-of-band emission requirement). [ZTE,R4-2320332]

Option 2:

Table 9.5.2.2-1: General NR spectrum emission mask for FR2-NTN.

|  | Spectrum emission limit (dBm) / Channel bandwidth |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| ΔfOOB (MHz) | 50 MHz | 100 MHz | 200 MHz | 400 MHz | Measurement bandwidth |
| 0-5 | -5 | -5 | -5 | -5 | 1 MHz |
| 5-10 | -13 | -5 | -5 | -5 | 1 MHz |
| 10-20 | -13 | -13 | -5 | -5 | 1 MHz |
| 20-40 | -13 | -13 | -13 | -5 | 1 MHz |
| 40-80 | -13 | -13 | -13 | -13 | 1 MHz |
| 80-100 | -13 | -13 | -13 | -13 | 1 MHz |
| 100-160 |  | -13 | -13 | -13 | 1 MHz |
| 160-200 |  | -13 | -13 | -13 | 1 MHz |
| 200-400 |  |  | -13 | -13 | 1 MHz |
| 400-800 |  |  |  | -13 | 1 MHz |
| ± 800-1600 |  |  |  |  | 1 MHz |
| ± 1600-3200 |  |  |  |  | 1 MHz |
| ± 3200-4000 |  |  |  |  | 1 MHz |
| NOTE 1: Void |  |  |  |  |  |

Option 3:  other options are not precluded.

Issue 2-10 transmitter spurious emission requirement

Agreement:

Option 1:

- The following regulatory requirement should be taken into account.

- for the general transmitter spurious emission requirement, propose to follow the ITU-R SM.39 recommendation.[ZTE,R4-2320332]

TABLE  2 [ITU-R SM.329]

| Space services (mobile earth stations)(3), (4) | 43  10 log P, or 60 dBc, whichever is less stringent |
| --- | --- |
| Space services (fixed earth stations)(3), (4) | 43  10 log P, or 60 dBc, whichever is less stringent |

- CEPT ERC 74.01

- FCC 25.202(f)(4)

Issue 2-11 Phase continuity requirement for DMRS bundling.

Agreement:

- NOT applicable for FR2-NTN VSAT

Issue 3-1  REFSENS requirements

Agreement for polarization assumption:

- For polarization assumption for VSAT receiver requirement, the default assumption is single polarization

- If VSAT is capable of both polarization reception at the same time, the delta_R [TBD] for diversity gain could be added;

Agreement for REFSENS:

For UE type 3 supporting with LEO only:

- Link budget is based on the LEO600KM at [90] degree elevation angle and NF as 6dB;

For UE types supporting with both GEO and LEO:

- Link budget is based on GEO assumption with [25] degree elevation angle  and NF as 2.5dB;

Issue 3-2 FRC and FDD pattern in Annex.

Agreement:

- Reuse the existing DL FRC defined in TS38.101-2 with update TDD pattern configuration for FDD.  FFS for UL FRC/ PRB configuration.

Issue 3-3: Maximum input power for NTN VSAT

Agreement :

For UE type 3 supporting with LEO only:

- Link budget is based on the LEO400KM at [90] degree elevation;

For UE types supporting with both GEO and LEO:

- Link budget is based on LEO600KM at [90] degree elevation;

Issue 3-4: In-band blocking requirement for

Agreement :

for in-band blocking requirement for VSAT, propose to specify the power level of IBB to the same as power level of interfering signal of ACS requirement and reuse the freq offset of FR2 TN UE in-band blocking requirement

Issue 3-5: Receiver spurious emission requirement for NTN VSAT.

Agreement :

- Option 1: not needed since this is FDD band and OTA conformance testing.

Issue 4-2: applicability of DMRS bundling for GSO and NGSO

Agreement:

For GSO:

- To reuse maxDurationDMRS-Bundling-r17 for Rel-18 NTN UE DMRS bundling

- reuse the same requirement from Rel-17 TN coverage enhancement requirement (DMRS bundling )for Rel-18 NTN UE DMRS bundling requirement;

- . The requirement is verified under [0.17ppm] Doppler and constant delay test conditions. The delay condition is a constant and derived from the ephemeris information (SIB-19) and UE location associated with the Doppler value under test.

For NGSO:

- To define new capability for Rel-18 NTN UE DMRS bundling for Rel-18 NTN UE DMRS bundling;

- RAN4 will not introduce the requirement in Rel-18;

- There are no conformance testing with emulated varying channel model under NGSO up to Rel-18, whether to enable the DMRS bundling feature in NGSO, it’s up to the network decision;

- RAN4 recommend to specify side condition for NGSO under the varying Doppler and time delay in the future release.

BS RF/Demod

Agreement:

Separate GEO and LEO in 2 different classes

Agreement:

Specify ΔFR2_REFSENS

Agreement:

As FRF=1 was not considered in Rel-18 coexistence study for this WI, there is no need to specify dynamic range.

Issue 1-1: NTN UE antenna model

- Proposals

  - Option 1: Change NTN UE antenna model parameter as below

1 for θ=0 4J1kasinθπ180kasinθπ1802 for 0<θ≤90° For UE, 4J1kasinπ2kasinπ22 for θ>90° where: - J1(x) is the Bessel function of the first kind and first order with argument ‘x’; - a is the radius of the antenna's circular aperture; - k = 2f/c is the wave number; - f is the frequency of operation; - c is the speed of light in a vacuum and  is the angle measured from the bore sight of the antenna's main beam. Note that ka equals to the number of wavelengths on the circumference of the aperture and is independent of the operating frequency. And the sin () function is in radian.

- Agreement: Option 1 agreed

Issue 2-2: Treatment of NaN value

- Proposals

  - Option 1: In case that cell edge throughput is NaN due to the out of coverage, RAN4 can conclude based on average throughput loss.

- Agreement: option 1 agreed

Issue 2-3: Conclusion on ACIR

Agreement:

Based on collected results till RAN#109, RAN4 conclude below tentative ACIR from co-existence perspective:

- For case 6 &7 (SAN ACLR), required ACIR below 5 dB from RAN4 co-existence perspective

- For case 1 (VSAT UE ACLR), ACIR as [10.5] for GEO; ACIR for LEO: [13.15]

- For case 4 (SAN ACS), ACIR as [14.3] for GEO; ACIR for LEO:[16.2]

- For case 5 (VSAT UE ACS), ACIR as [39.2] for GEO; ACIR for LEO: [42.9]

Note: It’s not precluded to further discuss and make refinement if needed on above ACIR conclusion with associated ACLR/ACS requirements in future RAN4 meetings.

Issue 2-5: ACLR & ACS

Agreement:

For SAN ACLR: [12] dBc for both GEO and LEO

For VSAT UE ACLR: [14] dBc for both fixed VSAT and mobile VSAT

For SAN ACS: For GEO: [18] dBc, and LEO: [24] dBc.

For VSAT ACS:

- Considering below candidate values as starting point for VSAT ACS

  - Option 1: 23 dBc

  - Option 2: 30 dBc

  - Option 3: 35 dBc

- FFS for the additional means to address the co-existence issue, candidate options for further discussion

  - Option 1: Limit the elevation angles on DL side for VSAT UE

  - Option 2: Configure additional guard-band

  - Option 3: Consider different channel model (e.g. UMa instead of free space loss) between VSAT UE and TN BS.

  - Other options not precluded

Issue 1-1-1: Scenario

- Agreement:

  - For UE side

    - Define requirements for NGSO and GSO. FFS whether one or two sets of requirements are specified for NGSO and GSO.

  - For SAN side

    - Define one set of requirements for both NGSO and GSO.

Issue 1-1-2: Channel model

- Agreement:

  - Only NTN-TDLC will be considered.

Issue 1-1-3: Doppler

- Agreement: Consider the following Doppler value for initial evaluation

- UE: [600Hz, 1200HZ, 2000Hz]

- SAN: [600Hz, 3000Hz]

- Leave some margin with respect to 0.1ppm requirement if all of them found to be feasible. Margin to be discussed.

Issue 1-1-4: Delay spread

- Agreement:

  - 5ns for NTN-TDLC

Issue 2-1-1: HARQ processes for above 10 GHz bands

- Agreement

  - Consider both 16 and 32 HARQ processes; need further consideration on how to apply these to GSO and NGSO. Disabled HARQ requires further discussion.

Issue 2-1-3: Whether to define UE PBCH demodulation requirements for above 10 GHz bands?

- Agreement:

- Don’t define PBCH requirement for NR NTN enhancements.

Issue 2-1-4: Whether to define UE CQI reporting requirements for above 10 GHz bands?

- Agreement:

  - Do not define UE CQI reporting requirements for above 10 GHz bands

Issue 2-2-1: SCS (except PBCH testing)

- Agreement:

  - Confirm 120 kHz SCS for initial alignment as confirmed in RRM session.

Issue 2-3-2: Rank for PDSCH

- Agreement

  - Consider Rank 1 only.

Issue 2-3-3: PDSCH mapping type

- Agreement

  - PDSCH mapping type A

Issue 2-3-5: Configuration for PBCH test (If agreed to be introduced)

- Agreement

  - Not applicable (PBCH requirement will not be introduced)

Issue 2-3-6: Configuration for CQI reporting test (If agreed to be introduced)

- Agreement

  - Not applicable (CQI requirement will not be introduced)

Issue 3-1-1: Whether to define PUSCH repetition Type A for SAN PUSCH demodulation requirements for above 10 GHz bands?

- Agreement:

- Define PUSCH repetition Type A for SAN PUSCH demodulation requirements for above 10 GHz bands.

Issue 3-1-2: Whether to define SAN PUSCH demodulation performance requirements for DMRS bundling?

- Agreement:

- Define SAN PUSCH demodulation performance requirements for DMRS bundling

- FFS on whether actual model to be used for timing drift.

Issue 3-1-3: Whether to define SAN multi-slot PUCCH format 1 demodulation requirements under LOS channel?

- Agreement:

- Don’t define SAN PUCCH for msg4 HARQ-ACK demodulation requirements under LOS channel

Issue 3-2-1: Channel bandwidth

- Agreement:

- Consider 50MHz as the channel bandwidth.

Issue 3-2-2: Antenna configuration

- Agreement:

  - Keep the previous agreement to consider both 1Tx1Rx and 1Tx2Rx

  - FFS 2Tx2Rx pending on conclusion of the 2Tx UE RF requirement.

Issue 3-2-3: Rank

- Agreement

  - Rank 1 for 1Tx

Issue 3-2-5: SAN type

- Agreement

  - Do not define SAN demodulation requirement for SAN Type 2-H

RRM

### Issue 1-6: Te_NTN for 60kHz and 120kHz

Agreement:

- UL 60kHz SCS:

  - 13 Ts for all cases with 120kHz/240kHz SSB

- UL 120kHz SCS:

  - Case 1 and case 2: 7.5 Ts

    - FFS for the applicable side condition on case 2

  - Case 3: Higher than 7.5 Ts, FFS for the exact value

### Issue 1-7: NTA-offset

Agreement:

- RAN4 to define the exact value of NTA,offset for NR NTN band above 10 GHz.

  - Option 1: the value of NTA-offset defined in Table 7.1.2-2 for FR2

  - Other options are not precluded.

### Issue 1-8: UE Timing Advance adjustment accuracy

Agreement:

- RAN4 to define the timing advance adjustment accuracy requirement for NR NTN band above 10 GHz. The values for 60kHz and 120kHz UL SCSs are the same as those defined in Table 7.3A.2.2-1.

### Issue 1-9: UL timer accuracy requirements

Agreement:

- RAN4 to define the UL timer accuracy requirements for NR NTN band above 10 GHz. The values are the same as those defined in Table 7.2C.2-1.

### Issue 1-10: Gradual timing adjustment requirements

Agreement:

- RAN4 to define the gradual timing adjustment requirements for NR NTN band above 10 GHz. The values are the same as those defined in Table 7.1.2.1-1.

### Issue 2-1: RRC Idle and Inactive mobility

Agreement:

- RAN4 not to define RRC Idle and Inactive mobility requirements for inter-sat scenario for Type 1 UE.

### Issue 2-3: RLM

Agreement:

- Lmax = 64 and NRLM = 8; for both Type 1 and Type 2 UEs

### Issue 2-4: RRC Re-establishment

Agreement:

- For type 1 UE

  - Inter-satellite RRC re-establishment: No RRC re-establishment requirements

- For type 1 UE:

  - Intra-satellite RRC re-establishment: Define RRC re-establishment requirement, and the requirement is the same as the existing FR1 NTN requirements (6.2C.1). And the requirement applies when the UE is not configured with inter-satellite measurement.

  - FFS whether exception case need to be considered

- For type 2 UE

  - Intra-satellite RRC re-establishment

    - Define RRC re-establishment requirement, and the requirement is the same as the existing FR1 NTN requirements (6.2C.1). And the requirement applies when the UE is not configured with inter-satellite measurement.

    - FFS whether exception case need to be considered

  - Inter-satellite RRC re-establishment

    - No RRC re-establishment requirements

### Issue 2-5: L3 measurements

Agreement:

- For intra-frequency intra-satellite measurements, a UE shall be capable of performing SS-RSRP, SS-RSRQ, SS-SINR measurements for at least:

  - 8 identified cells, and 1 SSB per identified Cell

- For inter-frequency intra-satellite measurements, a UE shall be capable of performing SS-RSRP, SS-RSRQ, SS-SINR measurements for at least:

  - 4 identified cells, and 1 SSB per identified Cell

### Issue 2-7: Measurement gap

Agreement:

- Companies are encouraged to discuss the per FR and per gap pattern capability aspects.

### Issue 2-10: Inter-satellite Handover

Agreement:

- For type 1 UE, the additional interruption length X: 3*Trs

- For type 2 UE: Introduce requirements based on the assumption as 22 degree/s for beam steering speed without UE capability

  - using formula as Angle offset / UE beam steering speed

  - UE beam steering speed as 22 degree/s

Agreement:

- Send an LS to RAN2 to notify that for type 2 UEs, the steering of the antenna beam is close to the maximum configurable value for T304.

### Issue 3-2: Measurement period and accuracy requirements on RTD

Agreement:

- For UE Rx-Tx measurement period requirement, as baseline, the scope does not include measurements across different frequency layers.

- For the core part CR, Nsample = [1].

### Issue 4-1: TN to NTN cell reselection

Agreement:

- Define requirements on TN to NTN cell reselection.

  - Define core requirements for GNSS ON and GNSS switch OFF to ON, no test case.

  - No specific value for the GNSS time to first fix to be define for the case of GNSS switch OFF to ON.

### Issue 4-2: NTN to TN cell reselection

Agreement:

- Define requirements on NTN to TN cell reselection.

#### 2.4.2	Remaining Open issues

Specify remaining core requirements for NR-NTN deployment in above 10 GHz

- Rx/Tx for the selected VSAT UE class/types for the Ka band (i.e. Off axis, spurious, EIS, EIRP, ACS)

- Rx/Tx for SAN node for the Ka band (i.e. ICS)

- RRM for electronically-steered beam UEs (Type 1) and mechanically-steered beam UEs (Type 2) (e.g. additional interruption time during inter satellite HO, non zero beam switching delay)

Specify performance requirements for NR-NTN deployment in above 10 GHz

- Specify RRM performance requirements and test cases especially for Idle/Inactive mode  and connected mode mobility enhancement and network verified UE location

- Specify UE demodulation and CSI reporting requirements

- Specify satellite access node demodulation requirements

- Specify satellite access node conformance tests

## 3.	Detailed progress in SA/CT WGs since last TSG meeting (for all involved WGs)

NOTE: This section only needs to be filled in for WI/SIs where there is a corresponding relevant WI/SI in SA/CT.

## 3.1	SA2

#### 3.1.1	Agreements with cross-TSG impacts

#### 3.1.2	Remaining Open issues with cross-TSG impacts

NOTE: This section should also flag any critical dependencies that need TSG attention.

-

## 4.	References

## 4.1	RAN1

RAN1#114bis Xiamen/China, October 9th - 13th, 2023:

- R1-2310221	R18 WI NR-NTN-enh work plan at RAN1, 2 and 3	THALES

- R1-2308863	Considerations on the system parameters for FR2-NTN	THALES

- R1-2310650	Rel-18 Higher Layer Parameters for NR NTN	Moderator (Thales)

- R1-2309988	Discussion on RAN4 LS on the system parameters for NTN above 10 GHz	MediaTek Inc.

- R1-2309149	Discussion on the RAN1 related aspects for NTN above 10 GHz	ZTE

- R1-2309333	Discussion on RAN4 LS on FR2-NTN PRACH aspects	LG Electronics

- R1-2309492	Discussion on FR2 issues for NR NTN	CATT

- R1-2309543	Discussion on the RAN1 impact for NTN above 10GHz	Beijing Xiaomi Mobile Software

- R1-2309849	Discussion on NTN above 10 GHz	Apple

- R1-2310049	Discussion on FR2-NTN for NR NTN	NTT DOCOMO, INC.

- R1-2310108	Discussions on RAN4 LS on FR2-NTN aspects	Sharp

- R1-2309041	Discusion of the LS on the system parameters for NTN above 10 GHz	vivo

- R1-2309342	Discussion on RAN4 LS on system parameters for NTN above 10 GHz	Samsung

- R1-2309735	Open issues related to NTN operation in frequency bands above 10 GHz	Nokia, Nokia Shanghai Bell

- R1-2310239	Discussion on RAN4 LS on the system parameters for NTN above 10 GHz	Ericsson

- R1-2310262	Discussion on RAN1 impact to support RAN4 work on NTN above 10GHz	Huawei, HiSilicon

- Discussion to be handled in agenda item 8.13. Determine whether/how RAN1 specifications need to be changed.

- R1-2310158	Power control for RACH-less handover in NR NTN	Qualcomm Incorporated

- R1-2308910	Further discussion on LS for RACH-less handover	Huawei, HiSilicon

- R1-2309040	Discussions on RAN2 LS on RACH-less Handover	vivo

- R1-2309341	Discussion on RAN2 LS on RACH-less handover	Samsung

- R1-2309610	Discussion on remaining issue for RACH less handover for NR NTN	OPPO

- R1-2309808	Draft Reply LS on RACH-less Handover	Apple

- R1-2310219	Discussion on RAN2 LS on RACH-less handover	Ericsson

- Discussion to be handled in agenda item 8.13.

- R1-2308908	Maintenance of coverage enhancement for NR NTN	Huawei, HiSilicon

- R1-2309091	Discussions on remaining issues of coverage enhancements in NR NTN	vivo

- R1-2309150	Remaining issue on coverage enhancement	ZTE

- R1-2309230	Remaining issues on coverage enhancement for NR NTN	Spreadtrum Communications

- R1-2309250	Maintenance of coverage enhancement for NR NTN	Baicells

- R1-2309313	On coverage enhancements for NR NTN	Ericsson

- R1-2309334	Remaining issues on coverage enhancement for NR NTN	LG Electronics

- R1-2309392	Remaining issues on coverage enhancement for NR NTN	Samsung

- R1-2309434	Discussion on remaining issues on coverage enhancement for NR-NTN	xiaomi

- R1-2309504	Discussion on remaining issues of UL coverage enhancement for NR NTN	CATT

- R1-2309598	Discussion on remaining issue for coverage enhancement for NR NTN	OPPO

- R1-2309687	Remaining issues on coverage enhancement for NR NTN	CMCC

- R1-2309710	Maintenance of coverage enhancements for NR NTN	ETRI

- R1-2309712	Remaining issues on coverage enhancement for NR-NTN	Panasonic

- R1-2309736	Open issues related to coverage enhancements for NR over NTN	Nokia, Nokia Shanghai Bell

- R1-2309793	Discussion on remaining issues of coverage enhancement for NR NTN	Lenovo

- R1-2309850	On Remaining Issues of Coverage Enhancement for NR NTN	Apple

- R1-2309986	Coverage enhancement for NR NTN	MediaTek Inc.

- R1-2310050	Maintenance of coverage enhancement for NR NTN	NTT DOCOMO, INC.

- R1-2310109	Remaining issues on coverage enhancement for NR NTN	Sharp

- R1-2310159	Maintenance on coverage enhancements for NR NTN	Qualcomm Incorporated

- R1-2308862	Maintenance on network verified UE location in NR NTN	THALES

- R1-2308909	Maintenance of network-verified UE location for NR NTN	Huawei, HiSilicon

- R1-2309092	Discussions on remaining issues of UE location verification in NR NTN	vivo

- R1-2309151	Remaining issue on network verified UE location	ZTE

- R1-2309393	Remaining issues on network verified UE location for NR NTN	Samsung

- R1-2309505	Discussion on remaining issues on Network verified UE location for NR NTN	CATT

- R1-2309599	Discussion on remaining issue for network verified UE location for NR NTN	OPPO

- R1-2309737	Open issues related to network verified UE location for NR over NTN	Nokia, Nokia

- R1-2309851	On Remaining Issues of Network Verified UE Location	Apple

- R1-2309987	Network verified UE location for NR NTN	MediaTek Inc.

- R1-2310051	Remaining issue on Network verified UE location for NR NTN	NTT DOCOMO, INC.

- R1-2310160	Maintenance on network verified UE location for NR NTN	Qualcomm Incorporated

- R1-2310236	On maintenance of network verified UE location for NR NTN	Ericsson Limited

- R1-2308864	Feature Lead Summary #1 on Network verified UE location for NR NTN	THALES

- R1-2308865	Feature Lead Summary #2 on Network verified UE location for NR NTN	THALES

- R1-2308911	Maintenance of disabling of HARQ feedback for IoT NTN	Huawei, HiSilicon

- R1-2309000	Remaining issues on disabling of HARQ feedback for IoT NTN	Spreadtrum Communications

- R1-2309172	Remaining issue on disabling of HARQ feedback	ZTE

- R1-2309280	Disabling of HARQ-ACK feedback for IoT NTN	NEC

RAN1#115 Chicago/USA, November 13th - 17th, 2023:

- R1-2312496	LS out	LS on NR-NTN TP for TS 38.300	RAN1, THALES

- R1-2312518	discussion	FLS#1 on NR-NTN TP for TS 38.300	Moderator (THALES)

- R1-2312510	other	Session notes for 8.13 (Maintenance on NTN (Non-Terrestrial Networks) enhancements)	Ad-Hoc Chair (Huawei)

- R1-2312625	discussion	FLS#2 on NR-NTN TP for TS 38.300	Moderator (THALES)

- R1-2312553	LS out	Response on LS on the system parameters for NTN above 10 GHz	RAN1, Nokia

- R1-2312655	discussion	RAN1 agreements for Rel-18 WI on IoT NTN enhancements up to RAN1#115	Moderator (MediaTek Inc.)

- R1-2312495	draftCR	TP for TS 38.300	Moderator (THALES)

- R1-2312681	LS out	LS on NR-NTN TP for TS 38.300	RAN1, THALES

- R1-2312669	draftCR	TP for TS 38.300	Moderator (THALES)

- R1-2312670	LS out	LS on NR-NTN TP for TS 38.300	RAN1, THALES

- R1-2312301	discussion	Rel-18 Higher Layer Parameters for IoT NTN	Moderator (MediaTek)

- R1-2312377	discussion	Summary of discussion on remaining issues for RACH-less handover	Moderator (Samsung)

- R1-2312424	discussion	Rel-18 Higher Layer Parameters for NR NTN	Moderator (THALES)

- R1-2312246	discussion	TP for TS 38.300	THALES

- R1-2312247	discussion	On RAN1 related aspects for NTN above 10 GHz	Mitsubishi Electric RCE

- R1-2312136	discussion	Further discussion of open issues related to NTN operation in frequency bands above 10 GHz	Nokia, Nokia Shanghai Bell

- R1-2312141	discussion	Summary #1 for FR2-NTN	Moderator (Nokia)

- R1-2312142	discussion	Summary #2 for FR2-NTN	Moderator (Nokia)

- R1-2311312	discussion	Remaining issue on NTN above 10 GHz	CATT

- R1-2310936	discussion	Considerations on the system parameters for FR2-NTN	THALES

- R1-2310877	discussion	Discussion on RAN1 impact to support the RAN4 work on NTN above 10GHz	Huawei, HiSilicon

- R1-2310917	discussion	On RAN1 impact of NTN above 10 GHz	Ericsson

- R1-2311429	discussion	Power control for RACH-less handover in NR NTN	NEC

- R1-2311199	discussion	Discussion on the RAN1 related aspects for NTN above 10 GHz	ZTE

- R1-2311700	discussion	Discussion on NTN above 10 GHz	Apple

- R1-2311636	discussion	Discussion on FR2-NTN for NR NTN	NTT DOCOMO, INC.

- R1-2311585	discussion	Discussion on the RAN1 impact for NTN above 10GHz	Beijing Xiaomi Mobile Software

- R1-2311772	discussion	Discussions on RAN4 LS on FR2-NTN aspects	Sharp

- R1-2312051	discussion	On RACH-less handover in NR NTN	Qualcomm Incorporated

- R1-2311996	discussion	Discussion on RAN4 LS on the system parameters for NTN above 10 GHz	MediaTek Inc.

- R1-2312004	discussion	Remaining issues on coverage enhancements for NR NTN	Hyundai Motor Company

- R1-2311994	discussion	Coverage enhancement for NR NTN	MediaTek Inc.

- R1-2312052	discussion	Maintenance on coverage enhancements for NR NTN	Qualcomm Incorporated

- R1-2311918	discussion	Remaining issues of coverage enhancement for NR NTN	LG Electronics

- R1-2311861	discussion	Remaining issues on coverage enhancement for NR NTN	Samsung

- R1-2311773	discussion	Maintenance on coverage enhancement for NR NTN	Sharp

- R1-2311637	discussion	Maintenance on coverage enhancement for NR NTN	NTT DOCOMO, INC.

- R1-2311200	discussion	Remaining issue on coverage enhancement	ZTE

- R1-2311245	discussion	Discussion on remaining issue for coverage enhancement for NR NTN	OPPO

- R1-2311389	discussion	Discussion on remaining issues on coverage enhancement for NR-NTN	xiaomi

- R1-2311498	discussion	Remaining issues on coverage enhancement for NR NTN	CMCC

- R1-2311179	discussion	Remaining issues on coverage enhancements for NTN	Spreadtrum Communications

- R1-2311513	discussion	Remaining issues on NR NTN Coverage Enhancement	NEC

- R1-2311112	discussion	Discussions on remaining issues of coverage enhancements in NR NTN	vivo

- R1-2310916	discussion	On maintenance of coverage enhancements for NR NTN	Ericsson

- R1-2310874	discussion	Maintenance of coverage enhancement for NR NTN	Huawei, HiSilicon

- R1-2312137	discussion	Open issues related to coverage enhancements for NR over NTN	Nokia, Nokia Shanghai Bell

- R1-2312091	discussion	Maintenance of coverage enhancement for NR NTN	Baicells

- R1-2312319	discussion	Summary #1 on 8.13.1 Coverage enhancement for NR NTN	Moderator (NTT DOCOMO, INC.)

- R1-2312320	discussion	Summary #2 on 8.13.1 Coverage enhancement for NR NTN	Moderator (NTT DOCOMO, INC.)

- R1-2312321	discussion	Summary #3 on 8.13.1 Coverage enhancement for NR NTN	Moderator (NTT DOCOMO, INC.)

- R1-2312672	discussion	Summary #EOM on 8.13.1 Coverage enhancement for NR NTN	Moderator (NTT DOCOMO, INC.)

- R1-2312258	discussion	Network verified UE location for NR NTN	MediaTek Inc.

- R1-2312138	discussion	Remaining open issues related to network verified UE location for NR over NTN	Nokia, Nokia Shanghai Bell

- R1-2310875	discussion	Maintenance of network-verified UE location for NR NTN	Huawei, HiSilicon

- R1-2310935	discussion	Maintenance on network verified UE location in NR NTN	THALES

- R1-2310937	discussion	Feature Lead Summary #1 on Network verified UE location for NR NTN	Moderator (THALES)

- R1-2310938	discussion	Feature Lead Summary #2 on Network verified UE location for NR NTN	Moderator (THALES)

- R1-2310939	discussion	Feature Lead Summary #3 on Network verified UE location for NR NTN	Moderator (THALES)

- R1-2311325	discussion	Remaining issue on network verified UE location	CATT

- R1-2311113	discussion	Discussions on remaining issues of UE location verification in NR NTN	vivo

- R1-2311521	discussion	Maintenance on Network-verified UE location for NR-NTN	PANASONIC

- R1-2311246	discussion	Discussion on remaining issue for network verified UE location for NR NTN	OPPO

- R1-2311201	discussion	Remaining issue on network verified UE location	ZTE

- R1-2311638	discussion	Remaining issue on Network verified UE location for NR NTN	NTT DOCOMO, INC.

- R1-2311701	discussion	On Remaining Issues of Network Verified UE Location	Apple

- R1-2311759	discussion	Remaining Issues on Network Verified UE Location for NR NTN	ETRI

- R1-2311862	discussion	Remaining issues on network verified UE location for NR NTN	Samsung

- R1-2311942	discussion	On maintenance of network verified UE location for NR NTN	Ericsson Inc.

- R1-2312053	discussion	Maintenance on network verified UE location for NR NTN	Qualcomm Incorporated

- R1-2311995	discussion	Network verified UE location for NR NTN	MediaTek Inc.

## 4.2	RAN2

RAN2#123bis Xiamen/China, October 9th - 13th, 2023:

- R2-2310084	discussion	Remaining Issues on NR Non-Terrestrial Networks (NTN)	THALES

- R2-2310085	Work Plan	R18 WI NR-NTN-enh work plan at RAN1, 2 and 3	THALES

- R2-2310157	draftCR	UE Capabilities for Rel-18 NR NTN Enh. WI	Intel Corporation

- R2-2310158	draftCR	UE Capabilities for Rel-18 NR NTN Enh. WI	Intel Corporation

- R2-2310552	draftCR	Stage 3 running 38.304 CR for NTN	ZTE Corporation, Sanechips

- R2-2310840	draftCR	Stage 3 NTN running CR for 38.321 - RAN2#123	InterDigital

- R2-2310841	discussion	MAC open issues in NTN	InterDigital

- R2-2311230	CR	Stage 3 Running RRC CR for NR NTN Rel-18	Ericsson

- R2-2311231	discussion	Rapporteur s input to 38.331 regarding TN area information	Ericsson

- R2-2311255	draftCR	Stage-2 running CR for TS 38.300 for Rel-18 NTN enhancements	THALES (Rapporteur)

- R2-2309407	LS in	LS on the service requirement of restricting satellite access RAT type (C1-236567; contact: Google)	CT1

- R2-2309421	LS in	Reply LS to RAN2 on unchanged PCI (R1-2308566; contact: CATT)	RAN1

- R2-2309422	LS in	Reply LS on RACH-less Handover (R1-2308568; contact: Samsung)	RAN1

- R2-2309438	LS in	Reply LS on Common Signaling in (C)HO (R3-234664; contact: Qualcomm)	RAN3

- R2-2309476	LS in	Reply LS on time-based trigger condition in NG HO for NR NTN (S2-2310013; contact: Samsung)	SA2

- R2-2310000	discussion	Higher layer signalling for PUCCH repetition for Msg4 HARQ-ACK	Huawei, HiSilicon

- R2-2310559	discussion	Consideration on coverage enhancements	ZTE Corporation, Sanechips

- R2-2309529	discussion	Discussion on PUCCH enhancement for Msg4 HARQ-ACK in NR NTN	OPPO

- R2-2310037	discussion	Discussion on network verified UE location in NR NTN	THALES

- R2-2310133	discussion	Discussion on network verified UE location	Ericsson

- R2-2310147	discussion	Open issues on Network verified location	Nokia, Nokia Shanghai Bell

- R2-2310176	discussion	Single satellite Multi-RTT based positioning	Qualcomm Incorporated

- R2-2310245	discussion	Discussion on the remaining issues for network verified UE location	CMCC

- R2-2310418	discussion	Discussion on network verified UE location	Xiaomi

- R2-2310560	discussion	Consideration on NW verified UE location	ZTE Corporation, Sanechips

- R2-2310985	discussion	UE location verification by Network	NEC Telecom MODUS Ltd.

- R2-2311009	discussion	Network Verified UE Location in NTN	Samsung Electronics Iberia SA

- R2-2309503	discussion	Remaining issues on NW verification of UE location in R18 NR NTN	CATT

- R2-2309700	discussion	Handling of UE location verification during handover	Huawei, Turkcell, HiSilicon

- R2-2309989	discussion	Views on some remaining issues for network verified UE location	Lenovo Information Technology

- R2-2309990	discussion	Discussion on Network Verified UE Location	TCL

- R2-2309995	discussion	Multiple-RTT positioning in NTN	Quectel

- R2-2311323	LS out	Draft LS on NW verified UE location failure during cell change	Qualcomm Incorporated

- R2-2311316	discussion	Report of [304][NR-NTN Enh] NW verified UE location failure during cell change	Qualcomm Incorporated

- R2-2311324	LS out	LS on NW verified UE location failure during cell change	RAN2

- R2-2310046	discussion	Discussion on mobility enhancements for VSAT	THALES

- R2-2310246	discussion	Discussion on left issues for cell reselection	CMCC

- R2-2310065	discussion	Open issues of cell reselection enhancement	Samsung Research America

- R2-2310177	discussion	TN cell coverage info and measurement relaxation	Qualcomm Incorporated

- R2-2310306	discussion	NTN-TN cell reselection enhancement	Apple

- R2-2310419	discussion	Cell reselection enhancements for NTN-TN mobility	Xiaomi

- R2-2310626	discussion	Discussion on TN Measurement Relaxation Issues	FGI

- R2-2310842	discussion	NTN-TN mobility and service continuity	InterDigital

- R2-2310986	discussion	On the use of TN coverage signalling to indicate non-TN areas	NEC Telecom MODUS Ltd.

- R2-2311229	discussion	NTN neighbour cell information in TN cells	Ericsson, Thales

- R2-2309653	discussion	Remaining Issues on Cell Reselection for Power Saving	vivo

- R2-2309862	discussion	Remaining issues on NTN-TN cell reselection enhancement	LG Electronics France

- R2-2309909	discussion	Discussion on TN Coverage Area Information Update Issues	FGI

- R2-2309960	discussion	Views on some remaining issues for NTN-TN mobility	Lenovo

- R2-2311317	discussion	Report of [AT123bis][305][NR-NTN Enh] Support of NTN neighbor cell info	Ericsson

- R2-2310413	discussion	Discussion on location-based measurement initiation in moving cells	Huawei, HiSilicon, Turkcell

- R2-2310843	discussion	Cell reselection enhancements for Earth moving cell	InterDigital

- R2-2311228	discussion	Cell reselection enhancements	Ericsson

- R2-2310022	discussion	Discussion on remaining issues of PCI unchanged handover	Transsion Holdings

- R2-2310034	discussion	Discussion on satellite switch with longer gap in conjunction with unchanged PCI	PANASONIC R&D Center Germany

- R2-2310066	discussion	CHO Enhancements for NTN	Samsung Research America

- R2-2310067	discussion	Open issues on NTN RACH-less HO and PCI unchanged switch	Samsung Research America

- R2-2310178	discussion	RACH-less handover for NTN	Qualcomm Incorporated

- R2-2310179	discussion	Details on satellite switch with PCI unchange	Qualcomm Incorporated

- R2-2310225	discussion	Aquisition of target satellite information with PCI unchanged	China Telecom

- R2-2310247	discussion	Further discussion on PCI unchanged	CMCC

- R2-2310307	discussion	Satellite switching with unchanged PCI	Apple

- R2-2310308	discussion	NR NTN specific HO enhancement	Apple

- R2-2310412	discussion	Discussion on handover enhancements	Huawei, HiSilicon, Turkcell

- R2-2310420	discussion	Discussion on handover enhancements for NTN-NTN mobility	Xiaomi

- R2-2310435	discussion	Remaining issue on RACH-less HO for NTN	ITL

- R2-2310561	discussion	Consideration on remaining issues on NTN HO enhancements	ZTE Corporation, Sanechips

- R2-2310636	discussion	On Common HO Signalling for Rel-18 NTN	Nokia, Nokia Shanghai Bell

- R2-2310637	discussion	Final View on RACH-less HO in Rel-18 NTN	Nokia, Nokia Shanghai Bell

- R2-2310638	discussion	On How To Resolve Remaining Issues for Unchanged PCI (Satellite Switching without L3 Mobility)	Nokia, Nokia Shanghai Bell

- R2-2310662	discussion	Remaining Issues of RACH-less (C)HO	NEC

- R2-2310663	discussion	Remaining Details of Unchanged PCI Switch	NEC

- R2-2310696	discussion	Remaining issues on the unchanged PCI satellite switch	Google Inc.

- R2-2310697	discussion	Discussion on the unchanged PCI scenario with optional random access	ETRI

- R2-2310768	discussion	Common handover signalling for NTN	Sony

- R2-2310769	discussion	Signaling overhead reduction during NTN-NTN HOs	Sony

- R2-2310844	discussion	NTN mobility enhancements for RRC_CONNECTED	InterDigital

- R2-2310845	discussion	Satellite switching without PCI change	InterDigital

- R2-2311019	discussion	Remaining issues on RACH-less HO for NR NTN	ETRI

- R2-2311144	discussion	Discussion on NTN HO enhancements	Sharp

- R2-2311212	discussion	Common signalling of HO common information	Sequans Communications

- R2-2311223	discussion	“Unchanged PCI” solution vs “PCI change only” solution	Sequans Communications

- R2-2311227	discussion	Handover enhancements	Ericsson

- R2-2309500	discussion	Discussion on common (C)HO configuration	CATT

- R2-2309501	discussion	Discussion on RACH-less HO in NR NTN	CATT

- R2-2309502	discussion	Discussion on unchanged PCI mechanism	CATT

- R2-2309537	discussion	Discussion on handover enhancement for NR NTN	OPPO

- R2-2309654	discussion	Further Discussion on CHO Enhancements for NR NTN	vivo

- R2-2309655	discussion	Remaining Issue on RACH-less for R18 NR NTN	vivo

- R2-2309656	discussion	Further Discussion on Service Link Switching with Unchanged PCI	vivo

- R2-2309784	discussion	Handover Enhancement in LEO NTN: Unchanged PCI	MediaTek Inc.

- R2-2309863	discussion	Remaining issues on handover enhancements	LG Electronics France

- R2-2309864	discussion	Discussion on unchanged PCI	TCL

- R2-2309865	discussion	Discussion on RACH-less HO	TCL

- R2-2309883	discussion	Discussion on moving cell reference location for CHO	ASUSTeK

- R2-2309884	discussion	Discussion on remaining issue for unchanged PCI switch	ASUSTeK

- R2-2309961	discussion	Views on some remaining issues for PCI-unchanged scenario	Lenovo

- R2-2309962	discussion	Views on some remaining issues for RACH-less HO in NTN	Lenovo

- R2-2311318	discussion	[AT123bis][306][NR-NTN Enh] RACH-less HO	InterDigital

- R2-2311319	discussion	[AT123bis][307][NR-NTN Enh] Unchanged PCI (Apple)	Apple

RAN2#124 Chicago/USA, November 13th - 17th, 2023:

- R2-2312857	discussion	Remaining Issues on NR Non-Terrestrial Networks (NTN)	THALES

- R2-2312858	CR	Introduction of NTN enhancements	THALES

- R2-2312162	discussion	Open topics on UE capabilities for Rel-18 NR NTN Enh. WI including summary report of email discussion [Post123bis][310]	Intel Corporation

- R2-2312163	draftCR	UE capabilities for Rel-18 NR NTN Enh. WI	Intel Corporation

- R2-2312164	draftCR	UE capabilities for Rel-18 NR NTN Enh. WI	Intel Corporation

- R2-2312276	draftCR	Multi-RTT positioning in NTN	Qualcomm Incorporated

- R2-2312210	CR	Introduction of NR NTN enhancements in 38.304	ZTE Corporation, Sanechips

- R2-2313014	CR	Introduction of RACH-less handover to TS 38.321	InterDigital, Samsung

- R2-2313531	CR	Introduction of Rel-18 NR NTN enhancements	Ericsson

- R2-2313533	discussion	TS 38.331 Open Issue List for NR NTN Rel-18	Ericsson

- R2-2313002	discussion	MAC open issues in NTN	InterDigital

- R2-2313225	CR	Introduction of network verification of UE location in TS 37.355	CATT

- R2-2313226	Work Plan	LPP stage-3 issue and open issue status for Rel-18 NR NTN	CATT (Rapporteur)

- R2-2313003	discussion	Coverage enhancement in Non-Terrestrial Networks	InterDigital

- R2-2313294	discussion	Indication for Msg3 based request for PUCCH repetition	LG Electronics Inc.

- R2-2312280	discussion	UE capability indication for Msg4 ACK repetition	Qualcomm Incorporated

- R2-2312052	discussion	Discussion on remaining issue for NR NTN coverage enhancement	CATT

- R2-2311960	discussion	Discussion on PUCCH enhancement for Msg4 HARQ-ACK in NR NTN	OPPO

- R2-2312908	discussion	Further consideration on PUCCH repetition for Msg4 HARQ-ACK	Huawei, HiSilicon

- R2-2312702	discussion	Msg3 indication for PUCCH repetition for Msg4 HARQ-ACK	Nokia, Nokia Shanghai Bell

- R2-2312789	discussion	Consideration on remaining coverage enhancements issues	ZTE Corporation, Sanechips

- R2-2312649	discussion	Considerations on the coverage enhancements	CMCC

- R2-2312650	discussion	Discussion on network verified UE location	CMCC

- R2-2312461	discussion	Views on cell change during UE location verification	Lenovo

- R2-2312517	discussion	Discussion on network verified UE location	Ericsson

- R2-2312713	discussion	Remaining issues on UE location verification	Huawei, Turkcell, HiSilicon

- R2-2312121	discussion	Remaining Issues in Network verified UE Location	MediaTek Inc.

- R2-2312948	discussion	UE location verification by Network	NEC Telecom MODUS Ltd.

- R2-2313007	discussion	Network Verified UE Location in NTN	Samsung Electronics Iberia SA

- R2-2313050	discussion	Remaining Aspects on Network Verified UE Location	Nokia, Nokia Shanghai Bell

- R2-2313346	discussion	Discussion on network verified UE location in NR NTN	IPLOOK

- R2-2313530	discussion	NTN neighbour cell information in TN cells	Ericsson, Thales, Apple, Samsung, Deutsche Telekom, Qualcomm

- R2-2313532	discussion	Cell reselection enhancements for hard switch	Ericsson

- R2-2312950	discussion	On the use of TN coverage signalling to indicate non-TN areas	NEC Telecom MODUS Ltd.

- R2-2313401	discussion	Remaining issues on NTN-TN cell reselection enhancement	LG Electronics France

- R2-2313506	discussion	Discussion on mobility enhancements for VSAT	THALES

- R2-2313552	discussion	Remaining issues on NTN-TN cell reselection enhancement	LG Electronics France, Google Inc., Thales

- R2-2313411	discussion	Discussion on NTN-TN cell reselection enhancements	ETRI

- R2-2313481	discussion	Support of NTN neighbor cell info in TN cell	Sequans Communications

- R2-2313079	discussion	Discussion on TN broadcasting NTN assistance information	Huawei, HiSilicon, Turkcell

- R2-2312949	discussion	TN-NTN Mobility	NEC Telecom MODUS Ltd.

- R2-2312291	discussion	NTN-TN cell reselection enhancement	Apple

- R2-2312104	discussion	Remaining issues of cell reselection enhancement	Samsung

- R2-2312277	discussion	Cell coverage info and measurements	Qualcomm Incorporated

- R2-2311967	discussion	Discussion on the change of TN coverage information	OPPO

- R2-2311968	discussion	Discussion on support of NTN neighbor cell info in TN cell	OPPO

- R2-2311888	discussion	Cell (re)selection – discussion on broadcasting SIB19 in terrestrial networks	PANASONIC

- R2-2311834	discussion	Remaining Issues on Cell Reselection for NR NTN	vivo

- R2-2312547	discussion	Discussions on providing NTN neighbor cell information in TN cell	ITRI

- R2-2312841	discussion	Support of NTN neighbour cell info in TN cells	Sony

- R2-2312462	discussion	Views on providing NTN information in TN cell	Lenovo

- R2-2312651	discussion	Discussion on NTN-TN cell reselection	CMCC

- R2-2312644	discussion	Remaining issues on cell reselection enhancements	ZTE Corporation, Sanechips

- R2-2312609	discussion	FFS issues of unchanged PCI solution	NEC

- R2-2313080	discussion	Discussion on HO enhancements	Huawei, HiSilicon, Turkcell

- R2-2313051	discussion	Remaining issues for IDLE and CONNECTED mode mobility in Rel-18 NTN	Nokia, Nokia Shanghai Bell

- R2-2313052	discussion	Remaining Issues for Satellite Switching without L3 Mobility	Nokia, Nokia Shanghai Bell

- R2-2313529	discussion	Remaining issues with connected mode enhancements	Ericsson

- R2-2313399	discussion	Remaining issues on handover enhancements	LG Electronics France

- R2-2313297	discussion	Remaining open issues on RACH-less HO for NTN	ETRI

- R2-2313004	discussion	Remaining open issues: RACH-less handover	InterDigital

- R2-2313005	discussion	Remaining open issues: CHO for Earth-moving cells	InterDigital

- R2-2313190	discussion	Discussion on CHO configuration for moving cell location	ASUSTeK

- R2-2312463	discussion	Some remaining issues for CHO and RACH-less HO in NTN	Lenovo

- R2-2312356	discussion	Open issues on RACH-less in NR NTN	Apple

- R2-2312500	discussion	Remaining issue for RACH-less	Sharp

- R2-2312840	discussion	Signaling overhead reduction during NTN-NTN HOs	Sony

- R2-2312790	discussion	Consideration on RACH-less HO remaining issues	ZTE Corporation, Sanechips

- R2-2312763	discussion	Discussion on the remaining issues for the handover enhancements	Xiaomi

- R2-2311835	discussion	Remaining Issues on CHO Enhancements for NR NTN	vivo

- R2-2311836	discussion	Remaining Issues on RACH-less for R18 NR NTN	vivo

- R2-2311859	Work Plan	Remaining Issues on RACH-less for R18 NR NTN	Quectel

- R2-2311966	discussion	Discussion on handover enhancement for NR NTN	OPPO

- R2-2312278	discussion	Open issues for handover enhancements	Qualcomm Incorporated

- R2-2312105	discussion	Remaining issues on Handover enhancements	Samsung

- R2-2312292	discussion	CHO enhancement to earth moving target cell	Apple

- R2-2312053	discussion	Configuration for location-based CHO for earth-moving cell	CATT

- R2-2312057	discussion	Discussion on RACH-less HO in NR NTN	CATT

- R2-2312058	discussion	Discussion on unchanged PCI mechanism	CATT

- R2-2312047	discussion	Leftover issues on the unchanged PCI satellite switch	Google Inc.

- R2-2312120	discussion	On Outstanding Issues in Unchanged PCI in LEO NTN	MediaTek Inc.

- R2-2312293	discussion	Satellite switching with unchanged PCI	Apple

- R2-2312106	discussion	Remaining issues on PCI unchanged satellite switch	Samsung

- R2-2312279	discussion	Major issues for satellite switch with PCI unchanged	Qualcomm Incorporated

- R2-2311989	discussion	Signalling design of satellite switching with PCI unchanged	China Telecom

- R2-2311837	discussion	Remaining Issues on Service Link Switching with Unchanged PCI	vivo

- R2-2311849	discussion	Discussion on unchanged PCI mechanism	Quectel

- R2-2312546	discussion	Discussions on SMTC configuration for satellite switch without PCI change	ITRI

- R2-2312632	discussion	Discussion on remaining issues of soft and hard satellite switch with PCI unchanged	Transsion Holdings

- R2-2312464	discussion	On some remaining issues for PCI-unchanged scenario	Lenovo

- R2-2312645	discussion	Usage and signaling of t-start	ZTE Corporation, Sanechips

- R2-2312646	discussion	Discussion on remaining issues of soft and hard satellite switch with PCI unchanged	Transsion Holdings

- R2-2313191	discussion	Discussion on remaining issue for unchanged PCI switch	ASUSTeK

- R2-2313206	discussion	Report of [Post123bis][312][NR-NTN Enh] Unchanged PCI	CMCC, Apple

- R2-2313006	discussion	Remaining open issues: Satellite switching without PCI change	InterDigital

- R2-2313279	discussion	Remaining issues on Unchanged PCI	ITL

- R2-2313400	discussion	Remaining issues on unchanged PCI	LG Electronics France

- R2-2313475	discussion	Unchanged PCI satellite switch considerations	Sequans Communications

## 4.3	RAN3

RAN3#121bis Xiamen/China, October 9th - 13th, 2023:

- R3-235981	CR	(BLCR to 38.413) BL CR for NR NTN	Nokia, Nokia Shanghai Bell, Ericsson, Thales, ZTE, Omnispace, TTP, CATT, Hughes Network Systems, Huawei, Lockheed Martin, Intelsat, ESA, Samsung, Qualcomm Incorporated

- R3-235982	CR	(BLCR to 38.423) BL CR for NR NTN	Huawei, Ericsson, Thales, ZTE, Omnispace, TTP, Nokia, Nokia Shanghai Bell, CATT, Hughes, EchoStar, CMCC

- R3-235057	draftCR	(BL CR to 38.300) Stage 2 BL CR for NR NTN	Ericsson, CATT, Thales, Huawei, Samsung, ZTE, Nokia, Nokia Shanghai Bell, Qualcomm Incorporated

- R3-235063	CR	(BL CR to 38.413) BL CR for NR NTN	Nokia, Nokia Shanghai Bell, Ericsson, Thales, ZTE, Omnispace, TTP, CATT, Hughes Network Systems, Huawei, Lockheed Martin, Intelsat, ESA, Samsung, Qualcomm Incorporated

- R3-235839	CR	(BL CR to 38.413) BL CR for NR NTN	Nokia, Nokia Shanghai Bell, Ericsson, Thales, ZTE, Omnispace, TTP, CATT, Hughes Network Systems, Huawei, Lockheed Martin, Intelsat, ESA, Samsung, Qualcomm Incorporated

- R3-235072	CR	(BL CR to 38.423) BL CR for NR NTN	Huawei, Ericsson, Thales, ZTE, Omnispace, TTP, Nokia, Nokia Shanghai Bell, CATT, Hughes, EchoStar, CMCC

- R3-235840	CR	(BLCR to 38.423) BL CR for NR NTN	Huawei, Ericsson, Thales, ZTE, Omnispace, TTP, Nokia, Nokia Shanghai Bell, CATT, Hughes, EchoStar, CMCC

- R3-235221	Work Plan	R18 WI NR-NTN-enh work plan at RAN1, 2 and 3	THALES

- R3-235023	LS in	Reply LS on time-based trigger condition in NG HO for NR NTN	SA2(Samsung)

- R3-235516	other	(TP for TS38.413 BL CR and TS38.423 BL CR) miscellaneous Correction on the BL CRs	Nokia, Nokia Shanghai Bell

- R3-235944	other	(TP to BL CR for TS 38.413) miscellaneous Correction on the BL CRs	Nokia, Nokia Shanghai Bell

- R3-235945	other	(TP to BL CR for TS 38.423) miscellaneous Correction on the BL CRs	Nokia, Nokia Shanghai Bell

- R3-235498	other	(TP to BL CR for TS 38.423) Time Margin for CHO in NR NTN - XnAP Impact	Ericsson, ESA, Thales

- R3-235499	other	(TP to BL CR for TS 38.423) Location-Triggered CHO for NR NTN	Ericsson, ESA, ZTE, Thales, Inmarsat

- R3-235696	other	(TP to BL CR for TS 38.423) Location-Triggered CHO for NR NTN	Ericsson, ESA, ZTE, Thales, Inmarsat, Hughes

- R3-235497	discussion	Time Margin for CHO in NR NTN	Ericsson, Thales, ESA

- R3-235215	discussion	Consideration on OAM requirements for UE location verification	CATT,Ericsson, Huawei

- R3-235216	other	(TP to BL CR for TS 38.455, 38.300, 38.305)Positioning support for NR NTN UE location verification	CATT

- R3-235146	discussion	Discussion on E-CID method for NTN	THALES, Huawei, Ericsson

- R3-235254	discussion	On NTN NW verified UE location	Lenovo

- R3-235325	other	(draftCR to 38.305, TP to BL CR for TS 38.300) Discussion on OAM configuration for network verified UE location	ZTE

- R3-235326	discussion	Discussion on mirror positions ambiguity for network verified UE location	ZTE

- R3-235392	discussion	Discussion on UE location verification for NTN	China Telecommunication

- R3-235460	other	(TP to BL CR for TS 38.455, 38.473) Discussion on TRP Information for NR NTN	Qualcomm Incorporated

- R3-235463	other	(TP to BL CR for TS 38.455) Discussion on Mirror Point Resolution and ECID Measurement	Qualcomm Incorporated

- R3-235474	discussion	Leftover issue on UE location verification	Samsung

- R3-235505	discussion	Discussion on Altitude for the NTN TRP	Huawei, Thales, Ericsson

- R3-235517	discussion	Discussion on UE location verification	Nokia, Nokia Shanghai Bell

- R3-235496	draftCR	OAM Requirements for UE Location Verification	Ericsson, CATT, Huawei

- R3-235504	other	(TP BL 38.300) OAM Requirements for UE Location Verification	Huawei, Ericsson, CATT

- R3-235506	other	(TP BL 38.455) NTN Access Point Position	Huawei, Thales, Ericsson

- R3-235507	LS out	Draft LS on Altitude for the Access Point (to: SA2; cc: CT1, CT4, SA5, RAN2, RAN1; contact: Huawei)	Huawei, Thales, Ericsson

- R3-235508	CR	Mapped Cell Id Introduction for E-CID and NR NTN	Huawei, Thales, Ericsson

RAN3#122 Chicago/USA, November 13th - 17th, 2023:

- R3-237058	draftCR	(BL CR to 38.300) Stage 2 BL CR for NR NTN	Ericsson, CATT, Thales, Huawei, Samsung, ZTE, Nokia, Nokia Shanghai Bell, Qualcomm Incorporated

- R3-237059	CR	(BLCR to 38.413) BL CR for NR NTN	Nokia, Nokia Shanghai Bell, Ericsson, Thales, ZTE, Omnispace, TTP, CATT, Hughes Network Systems, Huawei, Lockheed Martin, Intelsat, ESA, Samsung, Qualcomm Incorporated

- R3-237060	CR	(BLCR to 38.423) BL CR for NR NTN	Huawei, Ericsson, Thales, ZTE, Omnispace, TTP, Nokia, Nokia Shanghai Bell, CATT, Hughes, EchoStar, CMCC

- R3-237697	CR	(BLCR to 38.413) BL CR for NR NTN	Nokia, Nokia Shanghai Bell, Ericsson, Thales, ZTE, Omnispace, TTP, CATT, Hughes Network Systems, Huawei, Lockheed Martin, Intelsat, ESA, Samsung, Qualcomm Incorporated

- R3-237428	draftCR	OAM Requirements for UE Location Verification	Ericsson, CATT, Huawei

- R3-237454	discussion	Discussion on E-CID method for NTN	THALES, Huawei, Ericsson

- R3-237244	discussion	The discussion on location verification of NTN	NEC

- R3-237260	discussion	Discussion on remaining issues in Network Verified UE Location	Qualcomm Incorporated

- R3-237138	LS in	LS on NW verified UE location failure during cell change	RAN2(Qualcomm)

- R3-237436	other	(TP for TS 38.455) Support UE location verification in NR NTN	Nokia, Nokia Shanghai Bell

- R3-237443	discussion	Remaining Issues on UE Location Verification	Ericsson, Thales, Huawei

- R3-237445	discussion	UE Location Verification Failure During Cell Change	Ericsson, Huawei

- R3-237420	discussion	On NTN NW verified UE location	Lenovo

- R3-237636	discussion	Leftovers for UE location verification	Samsung

- R3-237375	discussion	Discussion on NW verified UE location failure during cell change and reply LS	Huawei, Ericsson, Thales

- R3-237368	other	(TP BL 38.300) OAM Requirements for UE Location Verification	Huawei, Ericsson, CATT

- R3-237369	other	(TP to 38.305) Mapped cell Id usage for UE disambiguation in multi-RTT	Huawei, Thales, Ericsson

- R3-237370	CR	Mapped Cell Id Introduction for E-CID and NR NTN	Huawei, Thales, Ericsson

- R3-237371	discussion	Discussion on Altitude for the NTN TRP	Huawei, Thales, Ericsson

- R3-237372	other	(TP BL 38.455) NTN Access Point Position	Huawei, Thales, Ericsson

- R3-237373	LS out	LS on Altitude for the Access Point	Huawei, Thales, Ericsson

- R3-237300	discussion	Further discussion on OAM requirements for UE location verification	CATT, Huawei, Ericsson, Nokia, Nokia Shanghai Bell, Samsung

- R3-237301	other	(TP to BL CR for TS 38.455) Positioning support for NR NTN UE location	CATT

- R3-237338	other	Discussion on remaining issues for network verified UE location	ZTE

- R3-237571	discussion	On NTN network verified UE location	China Telecommunication

## 4.4	RAN4

RAN4#108bis Xiamen/China, October 9th - 13th, 2023:

- R4-2316495	other	Discussions on NTN regulatory information	Samsung

- R4-2315767	draftCR	NTN enhancement: draft CR to TR 38.863 NTN Ka-band Regulatory aspects	Ericsson

- R4-2316904	draftCR	NTN enhancement: draft CR to TR 38.863 NTN Ka-band Regulatory aspects	Ericsson

- R4-2316215	other	Discussion on DMRS bundling	Huawei, HiSilicon

- R4-2316216	draftCR	Draft CR for 38.101-5 to update the clause of Transmit modulation quality	Huawei, HiSilicon

- R4-2315246	discussion	Discussion on RRM requirements impact for LS on PUSCH DMRS bundling	MediaTek inc.

- R4-2317653	draftCR	draft CR to TS 38.101-5: spec skeleton for NTN UE in Ka-band	ZTE Corporation, Samsung

- R4-2316870	discussion	Calibration updates for above 10 GHz and related information	THALES, Magister Solutions Ltd

- R4-2316868	discussion	Initial coexistence simulation results for above 10 GHz and related requirements	THALES, Magister Solutions Ltd

- R4-2316514	other	Coexistence simulation results between TN and NTN above 10GHz bands	Qualcomm Incorporated

- R4-2316535	other	Initial simulation results for Ka-band NTN coexistence study	ZTE Corporation

- R4-2315119	other	Further discussion on co-existence study for above 10GHz bands	CATT

- R4-2315120	other	Co-existence study result for above 10GHz bands	CATT

- R4-2316213	discussion	Some simulation results for Rel-18 NTN coexistence study	Huawei, HiSilicon

- R4-2316265	discussion	Discussion on simulation assumptions and results of NTN co-existence study in above 10GHz	Samsung Electronics Iberia SA

- R4-2316250	other	Assumption and results of calibration for NTN co-existence in above 10GHz bands	Samsung Electronics Iberia SA

- R4-2315764	other	NTN enhancement: coexistence simulations assumptions	Ericsson

- R4-2315765	other	NTN enhancement: calibration outcomes and coexistence simulations results	Ericsson

- R4-2315769	draftCR	draft CR to TS 38.108 - NTN enhancement SAN RF requirements	Ericsson

- R4-2315121	other	Further discussion on SAN RF requirements for above 10GHz bands	CATT

- R4-2315122	draftCR	Draft CR for TS 38.108, On introduction of above 10GHz bands to clause 10.1-10.4	CATT

- R4-2315124	other	Simulation results for Ka-band NTN SAN dynamic range	CATT

- R4-2316536	other	Further discussion on SAN RF requirements for NTN in Ka-band	ZTE Corporation

- R4-2316891	draftCR	Draft CR on TS 38.108 for Clause 9.6 - OTA transmitted signal quality	THALES

- R4-2316888	draftCR	Draft CR on TS 38.108 for Clause 5 - Operating bands and channel arrangement	THALES

- R4-2316889	draftCR	Draft CR on TS 38.108 for Clause 9.2 - Radiated transmit power and Clause 9.3 - OTA Satellite Access Node output power	THALES

- R4-2316848	draftCR	Draft CR to TS 38.108: FRC annex for FR2-NTN, Rel-18	Huawei, HiSilicon

- R4-2316853	draftCR	Draft CR to TS 38.108: EVM measurement annex for FR2-NTN, Rel-18	Huawei, HiSilicon

- R4-2315123	other	Discussion on SAN RF conformance testing requirements for above 10GHz bands	CATT

- R4-2315766	other	NTN enhancement: UE RF requirements	Ericsson

- R4-2316214	other	Discussion on Ka band NTN UE	Huawei, HiSilicon

- R4-2316790	discussion	On DMRS bundling with Doppler pre-compensation for NTN	Apple

- R4-2316871	discussion	Mapping NTN UE terminal requirements on NTN types	THALES

- R4-2316537	other	Further discussion on UE RF requirements for NTN in Ka-band	ZTE Corporation

- R4-2316496	other	Discussions on NTN UE RF	Samsung

- R4-2316282	other	On PUSCH DMRS bundling for NR NTN coverage enhancement	Ericsson

- R4-2315768	draftCR	NTN enhancement: draft CR to TS 38.307 release independant aspects for NTN UE	Ericsson

- R4-2316054	discussion	Discussion on general issues for NTN RRM requirements in Ka band	Huawei, HiSilicon

- R4-2316254	discussion	General Timing aspects for operation at 10 GHz in NTN	Nokia, Nokia Shanghai Bell

- R4-2315406	discussion	Discussion on RRM requirements for NTN deployment in above 10 GHz bands	Xiaomi

- R4-2315734	discussion	General discussion on NTN RRM requirements in above 10 GHz bands	vivo

- R4-2315756	other	Discussion on NR-NTN deployment in above 10GHz bands	ZTE Corporation

- R4-2316705	discussion	NTN UE types above 10 GHz beam steering time	Inmarsat, Viasat

- R4-2316872	discussion	Clarification on the NTN RRM testing procedure configuration	THALES

- R4-2316882	other	NTN support for frequency band above 10GHz	Qualcomm Incorporated

- R4-2316585	discussion	On RRM requirements for electronically-steered beam UEs (Type 1)	Apple

- R4-2315355	discussion	Discussion on RRM requirements for electronically-steered beam UEs in NTN above 10GHz bands	Samsung

- R4-2315514	discussion	Discussion on RRM requirements for Type 1 NR NTN UE in above 10GHz bands	LG Electronics Inc.

- R4-2315136	discussion	Discussion on RRM requirements for electronically-steered beam UEs (Type 1) in above 10 GHz bands	CATT

- R4-2315242	discussion	Discussion on RRM requirements for electronically-steered beam UEs (Type 1) for NTN above 10 GHz bands	MediaTek inc.

- R4-2316255	discussion	General requirements for Electronically steered beams in NTN	Nokia, Nokia Shanghai Bell

- R4-2316055	discussion	Discussion on mobility requirements for Type 1 NTN UE	Huawei, HiSilicon

- R4-2315740	discussion	Discussion on RRM requirements for electronically-steered beam UEs (Type 1)	vivo

- R4-2315876	discussion	RRM requirements for electronically-steered beam UEs (Type 1)	Ericsson

- R4-2315877	discussion	RRM requirements for mechanically-steered beam UEs (Type 2)	Ericsson

- R4-2315741	discussion	Discussion on RRM requirements for mechanically-steered beam UEs (Type 2)	vivo

- R4-2316056	discussion	Discussion on mobility requirements for Type 2 NTN UE	Huawei, HiSilicon

- R4-2316256	discussion	General requirements for Mechanically steered beams in NTN	Nokia, Nokia Shanghai Bell

- R4-2315243	discussion	Discussion on RRM requirements for mechanically-steered beam UEs (Type 2) for NTN above 10 GHz bands	MediaTek inc.

- R4-2315137	discussion	Discussion on RRM requirements for mechanically-steered beam UEs (Type 2) in above 10 GHz bands	CATT

- R4-2315515	discussion	Discussion on RRM requirements for Type 2 NR NTN UE in above 10GHz bands	LG Electronics Inc.

- R4-2315356	discussion	Discussion on RRM requirements for mechanically-steered beam UEs in NTN above 10GHz bands	Samsung

- R4-2316586	discussion	On RRM requirements for mechanically-steered beam UEs (Type 2)	Apple

- R4-2316875	discussion	RRM Requirements for Type 2 UE Terminal in above 10 GHz	THALES

- R4-2316883	other	Network verified UE location	Qualcomm Incorporated

- R4-2315735	discussion	Discussion on RRM impacts on Network verified UE location for NTN enhancement	vivo

- R4-2315244	discussion	Discussion on RRM requirements for Network verified UE location	MediaTek inc.

- R4-2316257	discussion	Discussion on updating the RX-TX measurements for NTN	Nokia, Nokia Shanghai Bell

- R4-2316057	discussion	Discussion on RRM requirements for NW verified location	Huawei, HiSilicon

- R4-2315874	discussion	Network verified UE location	Ericsson

- R4-2315875	discussion	NTN-TN and NTN-NTN mobility and service continuity enhancements	Ericsson

- R4-2316058	discussion	Discussion on mobility enhancements in NTN	Huawei, HiSilicon

- R4-2316258	discussion	Service continuity and mobility enhancements between TN and NTN	Nokia, Nokia Shanghai Bell

- R4-2315407	discussion	Discussion on RRM requirements for NTN-TN and NTN-NTN mobility and service continuity enhancements	Xiaomi

- R4-2315245	discussion	Discussion on RRM requirements for NR NTN mobility enhancement	MediaTek inc.

- R4-2315138	discussion	Discussion on RRM requirements for NTN-TN and NTN-NTN mobility and service continuity enhancements	CATT

- R4-2315173	discussion	Discussion on RRM core requirement for NR NTN mobility enhancements	CMCC

- R4-2315733	discussion	Discussion on RRM requirements for mobility on NTN enhancement	vivo

- R4-2315757	other	Discussion on RRM requirements for NTN enhancement	ZTE Corporation

- R4-2315357	discussion	Discussion on RRM requirements for NTN-NTN and NTN-TN mobility	Samsung

- R4-2315524	discussion	Discussion on NTN service continuity enhancement	LG Electronics Inc.

- R4-2316587	discussion	On mobility and service continuity for eNTN	Apple

- R4-2316259	discussion	Test cases scope and configuration for NTN enhancements	Nokia, Nokia Shanghai Bell

- R4-2316015	Work Plan	Workplan on demodulation requirements for NR NTN enhancements	Huawei,HiSilicon

- R4-2315999	discussion	Discussion on SAN demodulation requirements for NR NTN enhancements	Huawei,HiSilicon

- R4-2316153	discussion	View on BS demodulation requirements for NTN enhancement	Samsung

- R4-2315591	discussion	Discussion on NR NTN enhancement SAN demodulation	Ericsson

- R4-2315050	discussion	Discussion on NR NTN SAN Demodulation	Nokia, Nokia Shanghai Bell

- R4-2315051	discussion	NR NTN UE demodulation disussion	Nokia, Nokia Shanghai Bell

- R4-2315592	discussion	Discussion on NR NTN enhancement general issue and UE demodulation	Ericsson

- R4-2315348	discussion	Discussion on the UE demodulation and CSI requirements for NR NTN enhancements	Qualcomm Inc

- R4-2315483	discussion	On UE demod and CSI requirements for NR NTN enhancement	Apple

- R4-2315998	discussion	Discussion on UE demodulation requirements for NR NTN enhancements	Huawei,HiSilicon

- R4-2317275	other	Ad-hoc minutes for NR_NTN_enh	Samsung

- R4-2317261	other	Topic summary for [108-bis][138] NR_NTN_enh_UERF	Moderator (ZTE)

- R4-2316919	other	Offline meeting minutes on NR NTN UE and SAN demod	Huawei

- R4-2316921	other	WF on NR_NTN_enh_SAN_UE_demod	Huawei

- R4-2316905	other	WF on NR NTN SAN RF requirements	Ericsson

- R4-2316906	other	WF on NR NTN coexistence	Samsung

- R4-2316997	other	Ad-hoc meeting minutes for NR NTN coexistence	Samsung

- R4-2316998	other	Collection of NR NTN coexistence study results	Samsung

- R4-2316999	other	Simulation assumptions NR NTN coexistence in >10 GHz bands	Samsung

- R4-2317214	other	Topic summary for [108-bis][222] NR_NTN_enh	Moderator (Qualcomm)

- R4-2317648	other	WF on NR_NTN_enh_UERF	Main Session

- R4-2317649	other	WF on DMRS bundling for NTN	Thales

- R4-2317327	other	RRM WF and CR work split for NR_NTN_enh	Qualcomm

- R4-2317374	other	RRM WF and CR work split for NR_NTN_enh	Qualcomm

- R4-2317008	other	Simulation assumptions NR NTN coexistence in >10 GHz bands	Samsung

- R4-2317767	other	WF on DMRS bundling for NTN	Thales

- R4-2317939	other	Topic summary for [108bis][307] NR_NTN_enh_Part1	Moderator(Thales)

- R4-2317940	other	Topic summary for [108bis][308] NR_NTN_enh_Part2	Moderator(Ericsson)

- R4-2317941	other	Topic summary for [108bis][309] NR_NTN_enh_Part3	Moderator(Samsung)

- R4-2317953	other	Topic summary for [108bis][322] NR_NTN_enh_SAN_UE_demod	Moderator(Huawei)

RAN4#109 Chicago/USA, November 13th - 17th, 2023:

- R4-2320152	draftCR	Draft CR on TS 38.108: Corrections on channel raster and synchronization raster	NEC

- R4-2319569	other	NTN enhancement: system parameters update	Ericsson

- R4-2319571	CR	NTN enhancement: CR to TR 38.863 NTN Ka-band Regulatory aspects	Ericsson

- R4-2319182	other	Discussion on regulatory information on NTN UE	Samsung

- R4-2320952	pCR	Draft TP for TR 37.911 - Study on self-evaluation towards the IMT-2020 submission of the 3GPP Satellite Radio Interface Technology	THALES

- R4-2320949	CR	Draft CR proposal to add Doppler and Delay variation examples as a function of time for NGSO and GSO in a new Annex	THALES

- R4-2320970	discussion	NTN-TN co-existence simulation results in above 10 GHz bands	THALES, Magister Solutions Ltd

- R4-2318298	other	Co-existence study result for above 10GHz bands	CATT

- R4-2318493	other	Discussion on Co-existence study result for above 10GHz bands	CATT

- R4-2319566	other	NTN enhancement: coexistence simulations results	Ericsson

- R4-2319567	other	NTN enhancement: initial conclusion from simulations results	Ericsson

- R4-2319260	discussion	Joint proposals on NTN co-existence study	Samsung R&D Institute UK

- R4-2319777	discussion	Results of NTN coexistence study in above 10GHz	Samsung Electronics Nordic AB

- R4-2319890	other	Some simulation results for Rel-18 NTN coexistence study	Huawei, HiSilicon

- R4-2320330	other	Coexistence simulation results for NTN in Ka-band	ZTE Corporation

- R4-2320392	other	Coexistence simulation results between TN and NTN above 10GHz bands for VSAT and L-ESIM	Qualcomm Incorporated

- R4-2320331	other	Further discussion on SAN RF requirements for NTN in Ka-band	ZTE Corporation

- R4-2320334	draftCR	Draft CR to TS 38.108 Clause 10.5 OTA in-band selectivity and blocking	ZTE Corporation

- R4-2320335	draftCR	Draft CR to TS 38.108 Clause 10.6 OTA out-of-band blocking	ZTE Corporation

- R4-2320336	draftCR	Draft CR to TS 38.108 Clause 10.7 OTA in-channel selectivity	ZTE Corporation

- R4-2320153	draftCR	Draft CR on TS 38.108: Radiated transmit power requirements in extreme conditions	NEC

- R4-2320154	draftCR	Draft CR on TS 38.108: OTA modulation quality	NEC

- R4-2320155	draftCR	Draft CR on TS 38.108: EVM annex for FR2-NTN	NEC

- R4-2319711	draftCR	Draft CR to TS 38.108: correction on EVM measurement annex for FR2-NTN, Rel-18	Keysight Technologies UK Ltd

- R4-2319570	draftCR	NTN enhancement: draft CR to TS 38.108 NTN Ka-band - system parameters udpate	Ericsson

- R4-2319577	draftCR	NTN enhancement: draft CR to TS 38.108 NTN Ka-band - clause 4.3	Ericsson

- R4-2319578	draftCR	NTN enhancement: draft CR to TS 38.108 NTN Ka-band - clause 4.6	Ericsson

- R4-2319579	draftCR	NTN enhancement: draft CR to TS 38.108 NTN Ka-band - clause 9.4	Ericsson

- R4-2319580	CR	NTN enhancement: Running CR to TS 38.108 NTN Ka-band	Ericsson, Huawei, Thales

- R4-2318299	other	Further discussion on SAN RF requirements for above 10GHz bands	CATT

- R4-2318300	draftCR	Draft CR for TS 38.108, On introduction of above 10GHz bands to clause 10.1-10.4	CATT

- R4-2318302	other	Simulation results for Ka-band NTN SAN dynamic range	CATT

- R4-2320972	discussion	Remaining issues for SAN RF requirements in above 10 GHz	THALES

- R4-2320917	CR	Draft CR on TS 38.108 for Clause 9.7 - OTA unwanted emissions	THALES

- R4-2318301	other	Discussion on SAN RF conformance testing requirements for above 10GHz bands	CATT

- R4-2320551	other	LS on UE capability of PUSCH DMRS bundling for NR NTN	Ericsson

- R4-2320900	discussion	Details on NTN UE terminal requirements based on different NTN UE types	THALES

- R4-2320903	CR	Draft CR to TS 38.101-5: NTN UE in Ka-band	THALES

- R4-2320552	draftCR	CR on DMRS bundling	Ericsson

- R4-2320337	draftCR	Draft CR to TS 38.101-5 Clause 9.3 Output power dynamics	ZTE Corporation

- R4-2320338	draftCR	Draft CR to TS 38.101-5 Clause 10.4 Maximum input power requirement	ZTE Corporation

- R4-2320339	draftCR	Draft CR to TS 38.101-5 Clause 10.6 Blocking requirement	ZTE Corporation

- R4-2320340	draftCR	Draft CR to TS 38.101-5 Annex: NTN VSAT related FRC	ZTE Corporation

- R4-2320332	other	Further discussion on UE RF requirements for NTN in Ka-band	ZTE Corporation

- R4-2320333	other	Joint contribution for NTN VSAT RF requirements in Ka-band	ZTE Corporation , Thales, Samsung, Ericsson, Huawei

- R4-2319572	draftCR	NTN enhancement: draft CR to TS 38.101-5 NTN Ka-band - clause 5	Ericsson

- R4-2319573	draftCR	NTN enhancement: draft CR to TS 38.101-5 NTN Ka-band - clauses 9.1	Ericsson

- R4-2319574	draftCR	NTN enhancement: draft CR to TS 38.101-5 NTN Ka-band - clauses 9.2.2	Ericsson, Verizon

- R4-2319575	draftCR	NTN enhancement: draft CR to TS 38.101-5 NTN Ka-band - clauses 9.2.3	Ericsson

- R4-2319576	draftCR	NTN enhancement: draft CR to TS 38.101-5 NTN Ka-band - clauses 10.7	Ericsson

- R4-2319568	other	NTN enhancement: UE RF requirements	Ericsson

- R4-2319891	draftCR	Draft CR for 38.101-5 to introduce clause 10.1~10.3	Huawei, HiSilicon

- R4-2319892	other	Discussion on Ka band NTN UE	Huawei, HiSilicon

- R4-2319893	other	Discussion on DMRS bundling	Huawei, HiSilicon

- R4-2319894	CR	CR for 38.101-5 to introduce Phase continuity requirements for NTN UE DMRS bundling	Huawei, HiSilicon

- R4-2318425	CR	CR to 38.101-5 on the introduction of NTN DMRS bundling feature	Apple

- R4-2318426	discussion	On DMRS bundling with Doppler pre-compensation for NTN	Apple

- R4-2319179	other	Discussions on NTN UE RF	Samsung

- R4-2319180	draftCR	Draft CR to TS 38.101-5: sub-clause 9.2.1	Samsung

- R4-2319181	draftCR	Draft CR to TS 38.101-5: regulatory related RF requirements	Samsung

- R4-2320574	draftCR	Draft CR: Cell Re-selection for NR UE satellite access in RRC_IDLE state	ZTE Corporation

- R4-2320575	draftCR	Draft CR: Cell Re-selection for NR UE satellite access in RRC_INACTIVE state	ZTE Corporation

- R4-2320003	discussion	Discussion on RRM impacts of DMRS bundling	Huawei, HiSilicon

- R4-2320004	discussion	Discussion on RRM requirements for NTN in Ka band	Huawei, HiSilicon

- R4-2320005	draftCR	draftCR on HO requirements for NTN in Ka band	Huawei, HiSilicon

- R4-2320557	other	Discussion on NR-NTN deployment in above 10GHz bands	ZTE Corporation

- R4-2319212	discussion	Discussion on RRM requirements for NR-NTN UEs in above 10GHz bands	Samsung

- R4-2319214	draftCR	Draft CR on VSAT UE timing requirements for NTN in above 10GHz	Samsung

- R4-2319062	discussion	General discussion on NTN RRM requirements in above 10 GHz bands	vivo

- R4-2318845	discussion	Discussion on RRM requirements for NTN bands above 10GHz	Xiaomi

- R4-2318846	draftCR	DraftCR on measurement delay requirements for NTN bands above 10GHz	Xiaomi

- R4-2318819	draftCR	draft CR on handover for VSAT UE	Ericsson

- R4-2318821	discussion	RRM requirements in above 10 GHz bands	Ericsson

- R4-2318841	discussion	Discussion on RRM requirements for NR NTN UE in above 10GHz bands	LG Electronics Inc.

- R4-2318460	discussion	Discussion on RRM requirements for NTN above 10 GHz bands and other enhancement	MediaTek inc.

- R4-2318340	discussion	Discussion on NTN RRM requirements in above 10 GHz bands	CATT

- R4-2318341	draftCR	Draft CR on RRC_IDLE and RRC_INACTIVE state mobility for NTN in above 10 GHz bands	CATT

- R4-2318654	discussion	On NR-NTN RRM requirements in above 10 GHz bands	Apple

- R4-2320736	discussion	On solutions for NTN requirements for operations above 10 GHz	Nokia, Nokia Shanghai Bell

- R4-2320965	draftCR	draft Cat-B CR RLM in NTN band above 10GHz	Qualcomm Incorporated

- R4-2320966	other	NTN support for frequency band above 10GHz	Qualcomm Incorporated

- R4-2320971	discussion	On the NTN UL Timing Accuracy for above 10 GHz	THALES

- R4-2320967	other	Network verified UE location	Qualcomm Incorporated

- R4-2320737	discussion	Impact of NTN specificities on RX-TX Difference measurements	Nokia, Nokia Shanghai Bell

- R4-2320738	draftCR	DraftCR on requirements for UE verified Location	Nokia, Nokia Shanghai Bell

- R4-2319063	discussion	Discussion on RRM impacts on Network verified UE location for NTN enhancement	vivo

- R4-2320006	discussion	Discussion on RRM requirements for NW verified location	Huawei, HiSilicon

- R4-2320007	discussion	Discussion on mobility enhancements in NTN	Huawei, HiSilicon

- R4-2320558	other	Discussion on RRM requirements for NTN enhancement	ZTE Corporation

- R4-2319064	draftCR	draft CR on RRC_CONNECTED state mobility for NTN	vivo

- R4-2319061	discussion	Discussion on RRM requirements for mobility on NTN enhancement	vivo

- R4-2319213	discussion	Discussion on RRM requirements for NTN-NTN and NTN-TN mobility	Samsung

- R4-2318897	discussion	Discussion on NTN service continuity enhancement	LG Electronics Inc.

- R4-2318908	discussion	Discussion on RRM core requirement for NR NTN mobility enhancements	CMCC

- R4-2318820	discussion	NTN-TN and NTN-NTN mobility and service continuity enhancements	Ericsson

- R4-2318655	discussion	On mobility and service continuity for eNTN	Apple

- R4-2318342	discussion	Discussion on RRM requirements for NTN-TN and NTN-NTN mobility and service continuity enhancements	CATT

- R4-2318461	discussion	Discussion on RRM requirements for NR NTN mobility enhancement	MediaTek inc.

- R4-2320739	discussion	Service continuity and mobility enhancements between TN and NTN	Nokia, Nokia Shanghai Bell

- R4-2320740	discussion	Test cases scope and configuration for NTN enhancements	Nokia, Nokia Shanghai Bell

- R4-2318822	discussion	RRM performance requirement for NTN	Ericsson

- R4-2320008	discussion	Discussion on performance requirements for Rel-18 NTN	Huawei, HiSilicon

- R4-2320238	discussion	Discussion on general issues for demodulation requirements for NR NTN enhancements	Huawei,HiSilicon

- R4-2320239	discussion	Discussion on SAN demodulation requirements for NR NTN enhancements	Huawei,HiSilicon

- R4-2319846	discussion	View on BS demodulation requirements for NTN enhancement	Samsung

- R4-2318058	discussion	Discussion on NR NTN SAN Demodulation	Nokia, Nokia Shanghai Bell

- R4-2318059	discussion	NR NTN UE demodulation disussion	Nokia, Nokia Shanghai Bell

- R4-2318582	discussion	On UE demod and CSI requirements for NR NTN enhancement	Apple

- R4-2318735	discussion	Discussion on the UE demodulation and CSI requirements for NR NTN enhancements	Qualcomm India Pvt Ltd

- R4-2318736	discussion	Simulation results summary for NR NTN enhancements	Qualcomm India Pvt Ltd

- R4-2319223	discussion	On general issues and UE demodulation requirements for NR NTN enh.	Ericsson

- R4-2319224	other	Simulation results for NR NTN enhancement UE demodulation	Ericsson

- R4-2319313	discussion	Discussion on NR NTN enhancement SAN demodulation requirements	Ericsson

- R4-2319314	other	Simulation results for NR NTN enhancement SAN demodulation requirements	Ericsson

- R4-2320240	discussion	Discussion on UE demodulation requirements for NR NTN enhancements	Huawei,HiSilicon

- R4-2318182	other	Topic summary for [109][226] NR_NTN_enh	Moderator (Qualcomm)

- R4-2318145	other	Topic summary for [109][139] NR_NTN_enh_UERF	Moderator (ZTE)

- R4-2318200	other	Topic summary for [109][308] NR_NTN_enh_Part1	Moderator (Thales)

- R4-2318201	other	Topic summary for [109][309] NR_NTN_enh_Part2	Moderator (Ericsson)

- R4-2318202	other	Topic summary for [109][310] NR_NTN_enh_Part3	Moderator (Samsung)

- R4-2318216	other	Topic summary for [109][324] NR_NTN_enh_SAN_UE_demod	Moderator (Huawei)

END