## Slide 1: Views on 6G Timeline
CMCC
2024.3
3GPP TSG RAN Meeting #103 RP-240151
Maastricht, Netherlands, March 18-21, 2024
Agenda Item: 15
Source: CMCC
Document for: Discussion

## Slide 2
Considerations on 6G Timeline
Reasonable time window for further development of 5G and its evolution
  The global development of 5G is behind the market expectation, and the standardization of 6G should not be started too early to impact the commercialization of 5G and evolution.
  For R20, how to juggle the potentially timely deployment of 5G-A features and expectation of sufficient study of 6G technologies
    Now, different time spans of R20 are proposed, e.g., 18, 21, 24 and 27 months, how/whether to match the expectation of both 5G-A and 6G SI to the time span
    Whether the duration of 5G-A and 6G SI in R20 shall be fully overlapped
  Learning from 5G standardization: To avoid the “Rush push”
  SA/NSA, early drop / main drop / late drop → Single option
  Sufficient study and clear understanding on scenarios and requirements is a “MUST”
  Focusing on one WI before 2030
  Sufficient study of new emerging technologies out/in 3GPP for a new generation network.
  Solve the issues identified in 5G commercial networks, e.g. cost, power consumption and complexity of O&M
  To identify the feasible technical objective
  Extensive new capabilities beyond communication, e.g. AI, Computing, Sensing, Data as a service

## Slide 3
6G Vision
6G FTT
Tech Performance Req.
EMD
submission templates
workshop
Tech. Proposals for IMT-2030
Evaluation
IMT-2030
Spec.
WRC-23
WRC-27
2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
RAN1 R17
RAN1 R16
RAN1 R18
RAN1 R19
RAN1 R20(8 Quarters)
RAN1 R21
(24 Months)
RAN1 R22 ...
6G SI on.Req.
2025.3
3GPP RAN
6G workshop
6G RAN1 SI
（8 Quarters）
6G RAN1 WI
（24 Months）
3GPP 6G
first version
6G SA2 SI （R20）
6G SA2 WI （R21）
6G SA1 SI+WI
on Req.（R21）
6G SA1 SI
on Req.（R20）
* Views on 6G timeline from CMCC (3GPP still hasn’t started to discuss it)
ready for commercialization
Enough time for a consolidated and stable release.
Focusing on one WI before 2030.
At least 1 year is needed for the large scale field trial.
Need to ensure the performance of 6G in 3GPP doesn’t worse than the requirements from ITU.
Interaction between ITU and 3GPP.
Tentative consideration on 6G Timeline – Option 1
Proposal 2: Focusing on one WI before 2030.

## Slide 4
6G Vision
6G FTT
Tech Performance Req.
EMD
submission templates
workshop
Tech. Proposals for IMT-2030
Evaluation
IMT-2030
Spec.
WRC-23
WRC-27
2018 | 2019 | 2020 | 2021 | 2022 | 2023 | 2024 | 2025 | 2026 | 2027 | 2028 | 2029 | 2030
RAN1 R17
RAN1 R16
RAN1 R18
RAN1 R19
RAN1 R20(27 Months)
RAN1 R21
(24 Months)
RAN1 R22 ...
6G SI on.Req.
2025.3
3GPP RAN
6G workshop
6G RAN1 SI
（24 Months）
6G RAN1 WI
（24 Months）
3GPP 6G
first version
6G SA2 SI （R20）
6G SA2 WI （R21）
6G SA1 SI+WI
on Req.（R21）
6G SA1 SI
on Req.（R20）
* Views on 6G timeline from CMCC (3GPP still hasn’t started to discuss it)
ready for commercialization
Enough time for a consolidated and stable release.
Focusing on one WI before 2030.
At least 1 year is needed for the large scale field trial.
Need to ensure the performance of 6G in 3GPP doesn’t worse than the requirements from ITU.
Interaction between ITU and 3GPP.
Tentative consideration on 6G Timeline – Option 2
Proposal 2: Focusing on one WI before 2030.

## Slide 5
Proposal 3: Focusing on one WI before 2030.
  Proposal 1: Sufficient study of deployment path and new capabilities beyond communication are needed in the first 6G spec.
  Proposal 2: Time span of R20 should consider potential deployment of 5G-A features and comprehensive study of 6G technologies jointly.

## Slide 6
THANK YOU