3GPP TSG-RAN #77	RP-172026

Sapporo, Japan, 11th – 14th September 2017

Agenda item:		A.I

Source:	NTT DOCOMO, Ericsson, Nokia, Nokia Shanghai Bell, Qualcomm

Title:	Updated work plan of RAN 1 and 4 NR

Document for:		Discussion and Decision

1	Introduction

According to the NR WID [1], RAN WGs 1 and 4 are working on NR specification towards Dec. 2017 for NR non-standalone (NSA) operation and June 2018 for NR standalone (SA) operation. For the successful completion of NR NSA/SA specifications on schedule, an update of the work plan is necessary to focus only on the functionalities that are essential for NSA and SA specifications. In this contribution, we provide the updated work plan of RAN WGs 1 and 4.

2.		Discussion

The list of functionalities that are considered to be essential to support the NSA and SAoperations are provided in this section for RAN WGs 1 and 4. Items not on the list below that are deemed essential by RAN1 for Dec. 2017 release should be completed by Dec. 2017.

2.1	RAN1

- Duplexing air-interface support

  - By December 2017

    - Dynamic TDD scheduling/HARQ framework

    - Semi-static TDD

    - FDD full duplexing

  - [By June 2018 or not by Dec. 2017]

    - [FDD half duplexing]

    - Interference measurement related to dynamic TDD

- Initial access and mobility

  - By December 2017

    - SS/PBCH block based cell/beam detection

    - Random access channel design

    - Contention based RACH procedure based on single Msg.1

    - Contention free RACH procedure based on single Msg.1

    - RRM/RLM measurement

    - Remaining minimum system information (RMSI) delivery

    - Broadcast other system information (OSI) delivery

  - By June 2018

    - Paging design

  - [By June 2018 or not by Dec. 2017]

- MIMO

  - By December 2017

    - RE mapping

    - CW mapping

    - Codebook based transmission for UL

    - PRB bundling

    - Rate matching

    - Framework for CSI acquisition including DL reciprocity and

      - CSI measurement

      - CSI reporting

      - CQI/MCS table

    - Framework for beam management

      - Beam measurement

      - Beam recovery

      - Beam reporting

      - Beam indication

      - CQI/MCS table

    - CSI-RS for both CSI acquisition and beam management

    - DM-RS incl. high-speed scenarios and limited support of mini-slot (7, 4, and 2 OFDM symbols)

    - PT-RS

    - SRS

    - TRS (single-port) incl. high-speed scenarios

    - QCL

  - By June 2018

    - RS design for mini-slot beyond what is covered in Dec.

    - Non-codebook based transmission for UL

  - [By June 2018 or not by Dec. 2017]

    - RS design for mini-slot beyond what is covered in Dec. ’17

    - Multiple TRP/panel/beam transmission/reception at gNB for PDSCH/PUSCH

    - RLF connected to beam management

- Channel coding and Modulation

  - By December 2017

    - Channel coding accroding to RAN1 decisions

    - Modulation accroding to RAN1 decisions

- Power control

  - By December 2017

    - NR power control framework

    - LTE-NR power sharing according to existing RAN1 agreements at RAN1#90

    - Power control for NR-NR CA

    - Power control for SUL

  - [By June 2018]

    - Power control for NR-NR DC

- Scheduling/HARQ aspects

  - By December 2017

    - Basic DL/UL control channels

      - PDCCH

      - Long/Short PUCCH

        - Contiguous PRB allocation for PUCCH with and without hopping

      - HARQ

      - SR

      - Aperiodic/periodic CSI feedback reporting

      - UCI on PUSCH

    - Slot-based scheduling for FDD/TDD/dynamic TDD

    - Slot-based HARQ for FDD/TDD/dynamic TDD

    - CBG-based re-transmission

    - UL grant-free for slot-based and mini-slot based

    - Semi-static and dynamic resource reservation

    - Control/data within CC/BWP with same numerology

    - Numerology is the same between DL and UL at least without SUL

    - BWP according to RAN1 agreement

    - NR-NR CA with the same and different numerologies

      - Same numerology within the same PUCCH group, including both DL and UL

    - Strive for support of preemption indication at least for downlink

    - Mini-slot (7, 4, and 2 OFDM symbols) based scheduling and HARQ

  - [By June 2018 or not byDec. 2017]

    - Mini-slot based scheduling beyond what is covered in Dec. ’17

    - Multi-beam/panel/TRP PDCCH

    - Transmit diversity for PUCCH (Rel-16)

    - Simultaneous transmission of PUSCH and PUCCH (not in Rel-15)

- NR-LTE Coexistence

  - By December 2017

    - DL NR-LTE coexistence based on 15kHz numerology for control/data

    - UL NR-LTE coexistence, i.e., UL sharing from network perspective

    - By June 2018Single UL Tx accoding to RAN1 decisions

    - Solution to harmonic issue

    - Supplementary UL

  - [By June 2018 or not by Dec. 2017]

    - Single UL Tx with further optimization, etc. To be updated

- NR CA/DC

  - By December 2017

    - Basic NR-NR CA support

    - [

  - By June 2018 or not by

  - Dec. 2017]

    - NR-NR DC

  - By December 2017

2.4	RAN4

Note: Importance for RAN4 to focus on basic functionality of likely commercial choices. Specific examples for RF and RRM core parts follow:

- Duplexing air-interface support

  - By Dce 2017

    - Focus on only FDD and synchronized TDD (no requirements for unsynchoniezed cases)

  - [By June 2018 or not by Dec 2017]

    - [Interference measurement related to dynamic TDD]

- LTE-NR DC

  - By December 2017

    - Focus on LTE-NR DC for 2UL without NR-LTE coxistence and supplementary UL

      - LTE - NR (sub6) DC

        - Note that analysis for 2UL can cover that for single UL Tx for RF part (FFS: RRM and demodulation parts)

      - LTE - NR (above 24) DC

  - By June 2018

    - UL sharing from UE perspective

- NR CA/DC

  - By December 2017

    - NR-NR CA for 1UL support (intra-band contiguous, non-contiguous and inter band band)

    - LTE-NR DC with NR-NR CA for 1UL

  - By June 2018

    - NR-NR CA support related with UL sharing and supplementary UL if any

- Suplemntary UL

  - By December 2017

    - Supplemntal UL

    - UL NR-LTE coexistence from network perspective

- UL resource allocations

  - By December 2017

    - For PUSCH, contiguous resource allocation for DFT-s-OFDM

      - ”almost” contiguous resource allocation for CP-OFDM unless issues of spectral fragmentation/inefficient resource utilization of the carrier is identified.

      - For CP-OFDM, ”almost” contiguous resource allocation to avoid spectral fragmentation due to PUCCH from other UEs shall be specified in Rel.15.

      - In case of revisit, non-contiguous resource allocation for PUSCH shall be specified by Dec.

  - By June 2018

    - Relaxed resource allocations including non-contigous allcoation for PUSCH

- RRM/RLM

  - By December 2017

    - SS Block based RRM/RLM

    - Gap pattern design should be forwared compabible to CSI-RS based measurement

  - By June 2018

    - CSI-RS based RRM/RLM

3	Conclusion

In this contribution, we provided the updated work plan of RAN WGs 1 and 4. We suggest RAN WGs 1 and 4 focus on the list of functionalities provided in Section 2 to achieve successful complition of NSA and SA specifiations.

References

- RP-171485, “New WID on New Radio Access Technology”, NTT DOCOMO