## Slide 1: Discussion on Rel-17 Timeline schedule
vivo
3GPP TSG RAN Meeting #89e RP-201648
Electronic Meeting, September 14 - 18, 2020
Agenda Item: 9
Document for: Discussion & Decision

## Slide 2: Background
According to the endorsed 3GPP Release timeline [see Annex]
  Rel-17 RAN1 freeze in June 2021
  Rel-17 stage three freeze in September 2021
  Rel-17 ASN.1 freeze in December 2021
At least from RAN1, RAN2 perspective, significant progress made in 2 weeks emeeting (recent) although it was tough for delegates
Efficiency of emeeting is still far from F2F meeting

## Slide 3: Views on Rel-17 timeline
With current situation of COVID-19 pandemic, F2F meeting in Q1 2021 is not foreseen hence Ad-Hoc meeting in Q1 2021 is not needed
Meeting schedules for Q1 and Q2 in 2021 should be reconsidered, probably also emeetings.
  1 emeeting per quarter is reasonable
  2 weeks per emeeting (counting preparation week and post email discussion it is 4 weeks),
Considering emeeting in Q1 and Q2 2021,
  RAN1 led Rel-17 items
    There are only 2 emeetings in WI phase for the SIs converting to WIs in December 2020, i.e. RedCap, Cov_enh, Pos_enh, B52.6Ghz
    There are 3 emeetings for other ongoing WIs
Keep the agreed package and scope for RAN1 and RAN2 WIs and SIs
Further postpone Rel-17 completion time by at least 1 quarter, i.e. Rel-17 RAN1 freeze in September 2021, Stage three freeze in December 2021, ASN.1 freeze in March 2022

## Slide 4: Annex Rel-17 overall timeline was shifted by one quarter (RP-200493)