## TU_overview_after_RAN_86
|  |  |  | 1 TU = ~2h; RD: RRM/demodulation | [5 empty] | RAN | R1 | R2 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | R6 | RAN | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R1 | R2 | R3 | R4RF | R4RD | RAN | R1 | R2 | R3 | R4RF | R4RD | R1 | R2 | R3 | R4RF | R4RD | RAN | Final column of TU total. Insert new quarters before this column. Do not remove this column
leading WG | RAT | WI code | WI or SI | Title | latest WID/SID | rapporteur | target | sum TUs | comment | 91 Mar.21 | 104bis | 113bis | 98bis | 98bis | 105 | 114 | 112 | 99 | 99 | 20 | 92 Jun.21 | 106 | 115 | 113 | 100 | 100 | 93 Sep.21 | 106bis | 107 | 116 | 114 | 101 | 101 | 94 Dec.21 | 107bis | 116bis | 114bis | 101bis | 101bis | 108 | 117 | 115 | 102 | 102 | 95 Mar.22
R1 | NR | NR_feMIMO-Core | WI | Core part: Further enhancements on MIMO for NR | RP-202024 | Samsung | Mar 22 | 28.5 | REL-17 |  | 6 |  |  |  | 2 | 0.5 |  | 0.25 | 0.25 |  |  | 4 | 0.5 |  | 0.25 | 1 |  | 4 | 4 | 0.5 |  | 0.25 | 1 |  |  | 0.5 |  | 0.25 | 1 |  | 1 |  | 0.25 | 1
R4 | NR | NR_feMIMO-Perf | WI | Perf. part: Further enhancements on MIMO for NR | RP-202024 | Samsung | Sept 22 | 0 | REL-17
R1 | NR | NR_ext_to_71GHz-Core | WI | Core part: Extending current NR operation to 71GHz | RP-193229 | Qualcomm | Jun 21 | 28.25 | REL-17 |  | 3 |  | 2 |  | 1 |  |  | 2 | 0.25 |  |  | 2 | 0.5 |  | 2 | 1 |  | 2 | 2 | 0.5 |  | 2 | 1 |  |  | 0.5 |  | 2 | 1 |  | 0.5 |  | 2 | 1
R4 | NR | NR_ext_to_71GHz-Perf | WI | Perf. part: Extending current NR operation to 71GHz | RP-193229 | Qualcomm | Sep.21 | 0 | REL-17
R1 | NR | NR_pos_enh-Core | WI | Core Part: NR positioning enhancements | RP-210903 | CATT | Mar 22 | 25.75 | REL-17 |  | 1 | 1.5 |  |  | 3 | 2 |  |  | 0.25 |  |  | 2 | 2 |  |  | 1 |  | 2 | 2 | 2 |  |  | 1 |  |  | 2 |  |  | 1 |  | 2 |  |  | 1
R1 | NR | NR_pos_enh-Perf | WI | Perf Part: NR positioning enhancements | RP-210903 | CATT | Sept 22 | 4.5 | REL-17 | [7 empty] | 1 | [6 empty] | 1 | [6 empty] | 0.5 | [5 empty] | 1 |  |  |  |  | 1
R1 | NR | NR_redcap-Core | WI | Core Part: support of reduced capability NR devices | RP-210918 | Ericsson | Mar 22 | 24 | REL-17 |  | 1 | 0.5 |  |  | 3 | 1 |  | 0.25 | 0.25 |  |  | 2 | 1 | 0.5 | 0.5 | 1 |  | 2 | 2 | 1 | 0.5 | 0.5 | 1 |  |  | 1 | 0.5 | 0.5 | 1 |  | 1 | 0.5 | 0.5 | 1
R1 | NR | NR_redcap-Perf | WI | Perf Part: support of reduced capability NR devices | RP-210918 | Ericsson | Sept 22 | 0.75 | REL-17 | [29 empty] | 0.25 |  |  |  |  | 0.5
R1 | NR | NR_cov_enh-Core | WI | Core Part: NR coverage enhancements | RP-210855 | China Telecom | Mar 22 | 12.5 | REL-17 |  | 1 |  | 0.25 |  | 3 |  |  | 0.25 |  |  |  | 2 |  |  | 0.5 |  |  | 2 | 2 |  |  | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_cov_enh-Perf | WI | NR coverage enhancements | RP-210855 | China Telecom | Sept 22 | 0.75 | REL-17 | [29 empty] | 0.25 |  |  |  |  | 0.5
R1 | LTE | NB_IOTenh4_LTE_eMTC6-Core | WI | Core part: Additional enhancements for NB-IoT and LTE-MTC | RP-201306 | Huawei, Ericsson | Mar 22 | 19.75 | REL-17 |  | 0.5 | 1 | 0.5 |  | 1.5 | 1 | 0.5 | 0.5 | 0.25 |  |  | 1 | 1 | 0.5 | 0.5 | 0.5 |  | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 |  |  | 1 | 1 | 0.5 | 0.5 |  | 1 | 1 | 0.5 | 0.5
R4 | LTE | NB_IOTenh4_LTE_eMTC6-Perf | WI | Perf part: Additional enhancements for NB-IoT and LTE-MTC | RP-201306 | Huawei, Ericsson | Sept 22 | 0.75 | REL-17 | [29 empty] | 0.25 |  |  |  |  | 0.5
R1 | NR | NR_SL_enh-Core | WI | Core part: NR Sidelink enhancement | RP-202846 | LG Electronics | Mar 22 | 28.75 | REL-17 |  | 3 | 1 | 1 |  | 1 | 1 |  | 1 | 0.25 |  |  | 2 | 1.5 |  | 1 | 1 |  | 2 | 2 | 1.5 |  | 1 | 1 |  |  | 1.5 |  | 1 | 1 |  | 2 |  | 1 | 1
R4 | NR | NR_SL_enh-Perf | WI | Perf. part: NR Sidelink enhancement | RP-202846 | LG Electronics | Sept 22 | 0.25 | REL-17 | [34 empty] | 0.25
R1 | NR | FS_NR_XR_eval | SI | Study on XR (Extended Reality) evaluations for NR | RP-201145 | Qualcomm | Dec 21 | 5 | REL-17 |  | 1 |  |  |  | 1 | [6 empty] | 1 | [5 empty] | 1 | 1
R1 | LTE | FS_LTE_NBIOT_eMTC_NTN | SI | Study on NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) | RP-202689 | MediaTek | Dec 21 | 8.5 | REL-17 |  | 1 | 0.5 |  |  | 1 | 0.5 | [5 empty] | 1 | 1 |  |  |  |  | 1 | 1 | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R1 | NR | NR_DSS-Core | WI | Core part: NR Dynamic spectrum sharing (DSS) | RP-193260 | Ericsson | Mar 22 | 5 | REL-17 |  | 0.5 |  |  |  | 1.5 | [6 empty] | 1 | [5 empty] | 1 | 1
R4 | NR | NR_DSS-Perf | WI | Perf part: NR Dynamic spectrum sharing (DSS) | RP-193260 | Ericsson | Sept 22 | 0 | REL-17
R4 | NR | NR_unlic-Perf | WI | Perf part: NR-based Access to Unlicensed Spectrum | RP-191575 | Qualcomm | Jun 21 | 4 | REL-16 |  |  |  | 0.5 | 1.5 |  |  |  | 0.5 | 1.5
R4 | NR | 5G_V2X_NRSL-Perf | WI | Perf part: 5G V2X with NR sidelink | RP-200129 | LG Electronics | Jun 21 | 2 | REL-16 |  |  |  |  | 1 |  |  |  |  | 1
R4 | NR | NR_POS-Perf | WI | Perf part：NR Positioning Support | RP-200218 | Intel | Jun 21 | 2 | REL-16 |  |  |  |  | 1 |  |  |  |  | 1
R1 | NR | Misc |  | Misc impacts coming from RAN2/3/4 SI/WI |  |  | Dec 19 | 9 | REL-17 |  | 1 |  |  |  | 2 | [6 empty] | 2 | [5 empty] | 2 | 2
R2 | NR | NR_IIOT_URLLC_enh-Core | WI | Core part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-210854 | Nokia | Mar 22 | 20 | REL-17 |  | 3 |  |  |  | 1 | 1 | 0.5 |  | 0.5 |  |  | 2 | 1 | 0.5 |  | 0.5 |  | 2 | 2 | 1 | 0.5 |  | 0.5 |  |  | 1 | 0.5 |  | 0.5 |  | 1 | 0.5 |  | 0.5
R4 | NR | NR_IIOT_URLLC_enh-Perf | WI | Core part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-193233 | Nokia | Sept 22 | 0.75 | REL-17 | [23 empty] | 0.25 | [5 empty] | 0.25 |  |  |  |  | 0.25
R2 | NR | NR_NTN_solutions-Core | WI | Core part: Solutions for NR to support non-terrestrial networks (NTN) | RP-210908 | Thales | Mar 22 | 32.5 | REL-17 |  | 0.5 | 1.5 | 2 | 0.5 | 1.5 | 1.5 | 1 | 2 | 0.5 |  |  | 1 | 1.5 | 1 | 2 | 0.5 |  | 1 | 1 | 1.5 | 1 | 2 | 0.5 |  |  | 1.5 |  | 2 | 0.5 |  | 2 |  | 2 | 0.5
R4 | NR | NR_NTN_solutions-Perf | WI | Perf. part: Solutions for NR to support non-terrestrial networks (NTN) | RP-210908 | Thales | Sept 22 | 0.75 | REL-17 | [29 empty] | 0.25 |  |  |  |  | 0.5
R2 | NR | NR_UE_pow_sav_enh-Core | WI | Core part: UE power saving enhancements for NR | RP-210938 | MediaTek | Mar 22 | 11.5 | REL-17 |  | 0.5 | 1 |  | 0.25 | 1.5 | 0 |  |  | 0.25 |  |  | 1 | 1 |  |  | 0.25 |  | 1 | 1 | 1 |  |  | 0.25 |  |  | 1 |  |  | 0.25 |  | 1 |  |  | 0.25
R4 | NR | NR_UE_pow_sav_enh-Perf | WI | Perf. part: UE power saving enhancements for NR | RP-210938 | MediaTek | Sept 22 | 0.25 | REL-17 | [34 empty] | 0.25
R2 | NR | NR_IAB_enh-Core | WI | Core part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-210758 | Qualcomm | Mar.22 | 25 | REL-17 |  | 0.5 | 1 | 0.25 |  | 1.5 | 1 | 1 | 0.5 | 0.25 |  |  | 1 | 1 | 1 | 1 | 0.5 |  | 1 | 1 | 1 | 2 | 1 | 0.5 |  |  | 1 | 1 | 1 | 0.5 |  | 1 | 2 | 1 | 0.5
R4 | NR | NR_IAB_enh-Perf | WI | Perf. part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-210758 | Qualcomm | Sept 22 | 0.25 | REL-17 | [34 empty] | 0.25
R2 | NR | NR_MBS-Core | WI | Core part: NR multicast and broadcast services | RP-201038 | Huawei | Mar.22 | 20.5 | REL-17 |  | 0.5 | 1.5 |  |  | 1.5 | 1.5 | 1 |  |  |  |  | 1 | 2 | 1 |  |  |  | 1 | 1 | 2 | 1 |  |  |  |  | 1.5 | 1 |  |  |  | 2 | 1
R4 | NR | NR_MBS_Perf | WI | Perf. part: NR multicast and broadcast services | RP-201038 | Huawei | Sept 22 | 0 | REL-17
R2 | NR | NR_SL_relay | WI | NR Sidelink Relay | RP-210904 | OPPO | Mar.22 | 14 | REL-17 |  |  | 1.5 |  |  |  | 1 | [6 empty] | 2 |  |  | 0.5 |  |  |  | 2 | 0.5 |  | 0.5 |  |  | 2 | 0.5 |  | 0.5 |  | 2 | 0.5 |  | 0.5
R2 | NR | FS_NR_SL_relay | SI | Study on NR Sidelink relay | RP-193253 | OPPO | Sep.20 | 0 | REL-17
R2 | NR | NR_Slice | WI | Enhancement of RAN Slicing for NR WID | RP-210912 | CMCC | Mar.22 | 4 | REL-17 |  |  | 0.5 |  |  |  | 0.5 | [6 empty] | 0.5 | [6 empty] | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  |  | 0.5
R2 | NR | FS_NR_slice | SI | Study on enhancement of RAN slicing for NR | RP-201612 | CMCC | Jun.21 | 0.5 | REL-17 | [7 empty] | 0.5
R2 | LTE, NR | LTE_NR_DC_enh2-Core | WI | Core part: Further Multi-RAT Dual-Connectivity enhancements | RP-201040 | Huawei | Mar.22 | 9 | REL-17 |  |  | 0.5 |  | 0.5 |  | 0.5 | 1 |  | 0.5 |  |  |  | 1 | 0.5 | [5 empty] | 1 | 0.5 |  |  |  |  | 1 | 0.5 |  |  |  | 1 | 0.5
R4 | LTE, NR | LTE_NR_DC_enh2-Perf | WI | Perf. part: Further Multi-RAT Dual-Connectivity enhancements | RP-193249 | Huawei | Dec.21 | 1 | REL-17 | [16 empty] | 0.5 | [6 empty] | 0.5
R2 | NR | NR_SmallData_INACTIVE-Core | WI | Core part: NR small data transmissions in INACTIVE state | RP-201305 | ZTE | Mar.22 | 11.5 | REL-17 |  |  | 1 |  |  |  | 0.5 | [6 empty] | 1.5 | [6 empty] | 1.5 | 1 |  | 0.5 |  |  | 1.5 | 1 |  | 0.5 |  | 1 | 1 |  | 0.5
R4 | NR | NR_SmallData_INACTIVE-Perf | WI | Perf. part: NR small data transmissions in INACTIVE state | RP-193252 | ZTE | Dec.21 | 0 | REL-17
R2 | NR, LTE | LTE_NR_MUSIM | WI | Support for Multi-SIM devices in Rel-17 | RP-193263 | vivo | Jun 21 | 4.5 | REL-17 |  |  | 1 |  |  |  | 0.5 | [6 empty] | 1 | [6 empty] | 1 | [5 empty] | 1
R4 | NR | NR_IAB-Perf | WI | Perf part: Integrated Access and Backhaul for NR | RP-192188 | Qualcomm | Jun 21 | 4 | REL-16 |  |  |  | 1 | 1 |  |  |  | 1 | 1
R4 | NR | LTE_NR_DC_CA_enh-Perf | WI | Multi-RAT Dual-Connectivity and Carrier Aggregation enhancements (LTE, NR) | RP-192336 | Ericsson | Jun 21 | 1 | REL-16 |  |  |  |  | 0.5 |  |  |  |  | 0.5
R2 | NR |  |  | Misc R1 items (Cov Enh, DSS sched enh etc) |  |  |  | 4.5 | REL-17 | [6 empty] | 0.5 | [6 empty] | 1 | [6 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1
R2 | NR, LTE |  |  | R17 Other (R4 items, 5G Bcast etc, including reserve) |  |  |  | 7.5 | REL-17 |  |  | 1 |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1.5 | [5 empty] | 1.5 |  |  |  |  | 1.5
RAN | NR, LTE | FS_5G_eval | SI | Study on Self Evaluation towards IMT-2020 Submission | RP-181318 | Huawei | Jun 18 | 0
R3 | NR | NR_SON_MDT | WI | SON/MDT Support for NR | RP-191776 | CMCC | Mar 20 | 0
R3 | NR | 5WWC-NG_interface | WI | NG Interface Usage for WWC (Wireless Wireline Convergence) | RP-190999 | Huawei | Mar 20 | 0
R3 | NR | NG_RAN_PRN | WI | Private Network Support for NG-RAN | RP-191563 | China Telecom | Mar 20 | 0
R3 | LTE, NR | NR_ENDC_SON_MDT_enh-Core | WI | Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | RP-201281 | CMCC | Mar 22 | 13 | REL-17 |  |  | 1 |  |  |  | 0.5 | 1.5 | [5 empty] | 1 | 2 | [5 empty] | 1 | 2 |  |  |  |  | 1 | 1 |  |  |  | 1 | 1
R3 | LTE, NR | LTE_NR_arch_evo_enh-Core | WI | Core part: Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN | RP-193181 | China Unicom | Sep 21 | 2 | REL-17 | [7 empty] | 1 | [6 empty] | 1
R3 | NR | FS_NR_ENDC_data_collect | SI | Further Enhancments to Data Collection SI | RP-201620 | CMCC | Mar 22 | 3.5 | REL-17 | [7 empty] | 1 | [6 empty] | 0.5 | [12 empty] | 1 |  |  |  |  | 1
R3 | NR | NR_QoE | WI | NR QoE WI | RP-210913 | China Unicom | Mar 22 | 8 | REL-17 |  |  | 0.5 |  |  |  | 0.5 | 1 | [5 empty] | 0.5 | 1 | [5 empty] | 0.5 | 1 |  |  |  |  | 0.5 | 1 |  |  |  | 0.5 | 1
R3 | NR | NG_RAN_PRN_enh | WI | NR Private Networks Enhancement WI | RP-202363 | China Telecom | Mar 22 | 5.5 | REL-17 |  |  | 0.5 |  |  |  | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 | [5 empty] | 0.5 | 0.5 |  |  |  |  | 0.5 | 0.5 |  |  |  |  | 1
R3 | NR | FS_NR_QoE | SI | Study on NR QoE (Quality of Experience) management and optimizations for diverse services | RP-193256 | China Unicom | Mar 21 | 0 | REL-17
R4 | NR | NR_CSIRS_L3meas | WI | Perf. part: CSI-RS based L3 measurement requirements for NR | RP-210590 | CATT | Jun 21 | 1 | REL-16 |  |  |  |  | 0.5 |  |  |  |  | 0.5
R4 | NR | FS_FR2_enhTestMethods | SI | Study on enhanced test methods for FR2 in NR | RP-210633 | Apple，CAICT |  |  | REL-17 |  |  |  | 0.5 |  |  |  |  | 0.5
R4 | LTE | FS_HPUE_B12_B5_FWVM | SI | High power UE operation in Band 12 and Band 5 for fixed-wireless and vehicle-mounted use cases | RP-201261 | Nokia |  |  | REL-17 |  |  |  | 0.25 |  |  |  |  | 0.25
R4 | NR | FS_NR_eff_BW_util | SI | Study on efficient utilization of licensed spectrum that is not aligned with existing NR channel bandwidths | RP-210706 | Ericsson |  |  | REL-17 |  |  |  | 0.5 |  |  |  |  | 0.5
R4 | NR | FS_NR_PC2_UE_FDD | SI | Study on high power UE (power class 2) for one NR FDD band | RP-202870 | China Unicom |  |  | REL-17 |  |  |  | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5
R4 | NR |  | SI | Study on extended 600MHz NR band | RP-202924 | Spark NZ Ltd | Sep 21 |  | REL-17 |  |  |  | 1 |  |  |  |  | 1 | [6 empty] | 1
R4 | NR | NR_MIMO_OTA-Core | WI | MIMO OTA requirements for NR UEs | RP-201800 | CAICT |  |  | REL-17 |  |  |  | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [6 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_MIMO_OTA-Perf | WI | MIMO OTA requirements for NR UEs | RP-201800 | CAICT |  |  | REL-17 |  |  |  | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [6 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_demod_enh2-Perf | WI | Further enhancement on NR demodulation performance | RP-210920 | China Telecom |  |  | REL-17 |  |  |  |  | 1.5 |  |  |  |  | 1.5 | [6 empty] | 1.5 | [6 empty] | 1.5 | [5 empty] | 1.5 |  |  |  |  | 1
R4 | NR | NR_DL1024QAM_FR1-Core | WI | Introduction of DL 1024QAM for NR FR1 | RP-202886 | Ericsson |  |  | REL-17 |  |  |  | 0.25 |  |  |  |  | 0.25 | [6 empty] | 0.25
R4 | NR | NR_DL1024QAM_FR1-Perf | WI | Introduction of DL 1024QAM for NR FR1 | RP-202044 | Ericsson |  |  | REL-17 | [22 empty] | 0.25 | 0.25 |  |  |  |  | 0.25 | 0.25 |  |  |  | 0.25 | 0.25
R4 | NR | NR_RRM_enh2-Core | WI | Further RRM enhancement for NR and MR-DC | RP-202874 | Apple |  |  | REL-17 |  |  |  |  | 1.5 |  |  |  |  | 1.5 | [6 empty] | 1.5 | [6 empty] | 1.5 | [5 empty] | 1.5 |  |  |  |  | 1
R4 | NR | NR_RRM_enh2-Perf | WI | Further RRM enhancement for NR and MR-DC | RP-202874 | Apple |  |  | REL-17
R4 | NR | NR_HST_FR1_enh-Core | WI | Enhanced NR support for high speed train scenario for frequency range 1 (FR1) | RP-210833 | CMCC |  |  | REL-17 |  |  |  |  | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [6 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_HST_FR1_enh-Perf | WI | Enhanced NR support for high speed train scenario for frequency range 1 (FR1) | RP-210833 | CMCC |  |  | REL-17 |  |  |  |  | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [6 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_RF_FR2_req_enh2-Core | WI | Further enhancements of NR RF requirements for frequency range 2 (FR2) | RP-210914 | Nokia |  |  | REL-17 |  |  |  | 2 | 1 |  |  |  | 2 | 1 | [5 empty] | 2 | 1 | [5 empty] | 2 | 1 |  |  |  |  | 2 | 1 |  |  |  | 2 | 1
R4 | NR | NR_RF_FR2_req_enh2-Perf | WI | Further enhancements of NR RF requirements for frequency range 2 (FR2) | RP-210914 | Nokia |  |  | REL-17
R4 | NR | NR_HST_FR2-Core | WI | NR support for high speed train scenario in FR2 | RP-210800 | Samsung |  |  | REL-17 |  |  |  | 0.25 | 1 |  |  |  | 0.25 | 1 | [5 empty] | 0.25 | 1 | [5 empty] | 0.25 | 1 |  |  |  |  | 0.25 | 1 |  |  |  | 0.25 | 0.75
R4 | NR | NR_HST_FR2-Perf | WI | NR support for high speed train scenario in FR2 | RP-210800 | Samsung |  |  | REL-17 |  |  |  |  | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [6 empty] | 1 | [5 empty] | 1 |  |  |  |  | 0.75
R4 | NR | NR_MG_enh-Core | WI | NR and MR-DC measurement gap enhancements | RP-210679 | MediaTek |  |  | REL-17 |  |  |  |  | 1 |  |  |  |  | 1 | [6 empty] | 1 |  |  |  | 0.5 |  |  | 1 |  |  | 0.5 |  |  | 1 |  | 0.5 |  |  | 1
R4 | NR | NR_MG_enh-Perf | WI | NR and MR-DC measurement gap enhancements | RP-210679 | MediaTek |  |  | REL-17
R4 | NR | NR_RF_FR1_enh-Core | WI | RF requirements enhancement for NR frequency range 1 (FR1) | RP-210899 | Huawei |  |  | REL-17 |  |  |  | 1.5 |  |  |  |  | 1.5 | 0.5 | [5 empty] | 1.5 | 0.5 | [5 empty] | 1.5 | 1 |  |  |  |  | 1.5 | 1 |  |  |  | 1.5 | 1
R4 | NR | NR_RF_FR1_enh-Perf | WI | RF requirements enhancement for NR frequency range 1 (FR1) | RP-210899 | Huawei |  |  | REL-17
RAN4 | NR | NR_repeaters-Core | WI | NR Repeaters | RP-210818 | Qualcomm, Commscope | March 22 |  | REL-17 |  |  |  | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1
R4 | NR | NR_BCS4-Core | WI | Core part: Introduction of bandwidth combination set 4 (BCS4) for NR | RP-202832 | Ericsson | Mar. 2022 |  | REL-17 |  |  |  | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1
R4 | NR | NR_FR1_TRP_TRS-Core | WI | Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | RP-210807 | vivo, OPPO, CMCC |  |  | REL-17 | [8 empty] | 0.25 | [6 empty] | 0.5 | [6 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | NR_FR1_TRP_TRS-Perf | WI | Introduction of UE TRP (Total Radiated Power) and TRS (Total Radiated Sensitivity) requirements and test methodologies for FR1 (NR SA and EN-DC) | RP-210807 | vivo, OPPO, CMCC |  |  | REL-17 | [22 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | FS_NR_Opt_pi2BPSK | SI | New study on optimizations of pi/2 BPSK uplink power in NR | RP-210910 | Qualcomm |  |  | REL-17 | [8 empty] | 0.5 | [6 empty] | 0.5 | [6 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | LTE_terr_bcast_bands-Core | WI | Core part: WID on new bands and bandwidth allocation for LTE based 5G terrestrial broadcast | RP-210907 | EBU | Dec 21 | 1.5 | REL-17 | [12 empty] | 0.5 | [5 empty] | 0.5 | 0.5
R4 | NR | R17 NR Basket Wis |  | RP-202187 Rel-17 NR intra band CA for xCC DL/yCC UL including contiguous and non-contiguous spectrum (x>=y) Ericsson RP-210495 Rel-17 NR Inter-band CA/DC for 2 bands DL with x bands UL (x=1,2) ZTE RP-202720 Rel-17 NR inter-band CA for 3 bands DL with 1 band UL CATT RP-210497 Rel-17 NR inter-band CA/DC for 3 bands DL with 2 bands UL ZTE RP-202189 Rel-17 NR inter-band CA for 4 bands DL with 1 band UL Ericsson RP-210802 Rel-17 NR inter-band CA/DC for DL 4 bands and 2UL bands Samsung RP-210560 Rel-17 NR inter-band CA for 5 bands DL with x bands UL (x=1, 2) Huawei RP-210204 Rel-17 DC of 1 LTE band (1DL/1UL) and 1 NR band (1DL/1UL) CHTTL RP-210559 Rel-17 DC of 2 bands LTE inter-band CA (2DL/1UL) and 1 NR band (1DL/1UL) Huawei RP-202188 Rel-17 DC of 3 bands LTE inter-band CA (3DL/1UL) and 1 NR band (1DL/1UL) Ericsson RP-210766 Rel-17 DC of 4 bands LTE inter-band CA (4DL/1UL) and 1 NR band (1DL/1UL) Nokia RP-210300 Dual connectivity (DC) of 5 bands LTE inter-band CA (5DL/1L) and 1 NR band (1DL/1UL) Samsung RP-202542 Dual Connectivity (DC) of x bands (x=2,3,4) LTE inter-band CA (xDL/1UL) and 1 NR FR1 band (1DL/1UL) and 1 NR FR2 band (1DL/1UL) Samsung RP-202292 Rel-17 DC of x bands (x=1,2,3,4) LTE inter-band CA (xDL/1UL) and 2 bands NR inter-band CA (2DL/1UL)inter-band CA (2DL/1UL) LG RP-210344 Rel-17 DC of x bands (x=1,2) LTE inter-band CA (xDL/xUL) and y bands (y=3-x) NR inter-band CA (yDL/yUL) ZTE RP-202194 Rel-17 DC of x bands (x=1,2,3) LTE inter-band CA (xDL/1UL) and 3 bands NR inter-band CA (3DL/1UL) ZTE RP-210563 Band combinations for SA NR supplementary uplink (SUL), NSA NR SUL, NSA NR SUL with UL sharing from the UE perspective (ULSUP) Huawei RP-210773 Study on band combination handling in RAN4 ZTE RP-202607 Introduction of channel bandwidths 35MHz and 45MHz for NR Huawei RP-210917 Rel-17 Adding CH BW support to existing NR bands Ericsson RP-210891 Support of full bandwidths Huawei RP-210890 Simultaneous Rx/Tx band combinations Huawei RP-210588 Band combinations on co-current operation between Uu frequency bands and V2X bands CATT RP-210557 Additional NR bands for UL-MIMO power class 3 (PC3) in Rel-17 Huawei RP-210478 Downlink interruption for band combinations to conduct dynamic Tx Switching China Telecom, CATT RP-201584 SAR schemes for UE PC2 for NR inter-band CA and SUL configs with 2 bands, China Telecom RP-210476 High power UE (power class 2) for NR inter-band Carrier Aggregation with 2 bands downlink and 2 bands uplink China Telecom RP-210327 Rel-17 High power UE (PC2) for EN-DC with 1 LTE band + 1 NR TDD band China Unicom RP-210543 Power Class 2 UE for NR inter-band CA and SUL configurations with x (x>2) bands DL and y (y=1, 2) bands UL Huawei, China Unicom RP-210816 PC2 for EN-DC with multiple DL bands Ericsson RP-210555 High power UE for NR TDD intra-band Carrier Aggregation in frequency range FR1 Huawei | RP-202187 RP-210495 RP-202720 RP-210497 RP-202189 RP-210802 RP-210560 RP-210204 RP-210559 RP-202188 RP-210766 RP-210300 RP-202542 RP-202292 RP-210344 RP-202194 RP-210563 RP-210773 RP-202607 RP-210917 RP-210891 RP-210890 RP-210588 RP-210557 RP-210478 RP-201584 RP-210476 RP-210327 RP-210543 RP-210816 RP-210555 |  |  |  | REL-17 |  |  |  | 3 |  |  |  |  | 3 | [6 empty] | 3 | [6 empty] | 3 | [5 empty] | 3 |  |  |  |  | 3
R4 | NR | R17 NR spectrum related WI/SI |  | RP-202844 Introduction of 6GHz NR licensed bands Huawei, Ericsson, Nokia, ZTE RP-210762 Introduction of lower 6GHz NR unlicensed operation for Europe Nokia RP-210878 Introduction of 900 MHz spectrum to 5G NR applicable for Rail Mobile Radio (RMR) Union Inter. Chemins de Fer RP-210879 Introduction of 1900 MHz spectrum to 5G NR applicable for Rail Mobile Radio (RMR) Union Inter. Chemins de Fer RP-210827 introduction of NR 47 GHz band Nokia RP-202829 Introduction of n67 Ericsson RP-210707 Introduction of NR band n85 Ericsson RP-202912 High-power UE (PC1.5) operation in NR bands n77 and n78 Qualcomm RP-210843 High power UE (power class 1.5) for NR band n79 CMCC RP-210844 High power UE (power class 2) for NR band n34 CMCC RP-210845 High power UE (power class 2) for NR band n39 CMCC RP-210875 Introduction of FR2 FWA UE with maximum TRP of 23dBm for band n259 Qualcomm | RP-202844 RP-210762 RP-210878 RP-210879 RP-210827 RP-202829 RP-210707 RP-202912 RP-210843 RP-210844 RP-210845 RP-210875 |  |  |  | REL-17 |  |  |  | 2 |  |  |  |  | 2 | [6 empty] | 2 | [6 empty] | 2 | [5 empty] | 2 |  |  |  |  | 2
R4 | LTE | R17 LTE basket WIs |  | RP-210227 Rel-17 LTE inter-band CA for 2 bands DL with 1 band UL Qualcomm RP-210540 Rel-17 LTE inter-band CA for 3 bands DL with 1 band UL Huawei RP-210542 Rel-17 LTE inter-band CA for 2 bands DL with 2 band UL Huawei RP-202212 Rel-17 LTE inter-band CA for x bands DL (x=4, 5) with 1 band UL Nokia RP-202289 Rel-17 LTE inter-band CA for x bands DL (x= 3, 4, 5) with 2 bands UL LG | RP-210227 RP-210540 RP-210542 RP-202212 RP-202289 |  |  |  | REL-17 |  |  |  | 1 |  |  |  |  | 1 | [6 empty] | 1 | [6 empty] | 1 | [5 empty] | 1 |  |  |  |  | 1
R4 | LTE | R17 LTE spectrum related WI/SI |  | RP-201646 Additional LTE bands for UE cat. M1/M2/NB1/NB2 in Rel-17 Ericsson RP-201356 Modification of LTE Band 24 specifications to comply with updated regulatory emission limits Ligado Networks | RP-201646 RP-201356 |  |  |  | REL-17 |  |  |  | 0.5 |  |  |  |  | 0.5 | [6 empty] | 0.5 | [6 empty] | 0.5 | [5 empty] | 0.5 |  |  |  |  | 0.5
R4 | NR | R17 LS activities | [6 empty] | REL-17 |  |  |  | 1 | 1 |  |  |  | 0.25 | 0.25
R4 | NR | R16 NR Maintenance and TEI | [6 empty] | REL-16 |  |  |  | 2 | 1.5 |  |  |  | 2 | 1.5 | [5 empty] | 1.5 | 1 | [5 empty] | 1.5 | 1 |  |  |  |  | 1.5 | 1 |  |  |  | 1.5 | 1
R4 | LTE | LTE Maintenance | [10 empty] | 0.5 | 0.25 |  |  |  | 0.5 | 0.25 | [5 empty] | 0.5 | 0.25 | [5 empty] | 0.5 | 0.25 |  |  |  |  | 0.5 | 0.25 |  |  |  | 0.5 | 0.25
0
| NR |  |  | allocated above | [6 empty] | 24 | 17 | 27.25 | 17 | 27 | 17 | 11.5 | 28 | 19 | 0 | 0 | 26.5 | 24 | 11 | 25.75 | 17.5 | 0 | 26.5 | 26.5 | 24.5 | 12 | 24.75 | 19.5 | 0 | 0 | 24 | 11 | 24.75 | 20 | 0 | 23.5 | 12.5 | 24.75 | 20.25 | 0
| NR |  |  | Legacy | [6 empty] | 6 | 11 |  |  | 3 | 11 | [5 empty] | 4 | 14.5 |  |  |  |  | 4 | 4 | 13 | [5 empty] | 0 |  |  |  |  | 13
| NR |  |  | TEI and other not planned issues | [6 empty] | 1 | 0 |  |  | 1 | 0 | 1 |  |  |  |  | 1 | 1 | 1 |  |  |  | 1 | 1 | 1 | [5 empty] | 2 | 1 |  |  |  | 2
| NR |  |  | Reserve | [18 empty] | 0.5 | [6 empty] | 1.5 | [5 empty] | 2 |  |  |  |  | 1.5
| NR |  |  | total used capacity | [6 empty] | 31 | 28 | 27.25 | 17 | 31 | 28 | 12.5 | 28 | 19 | 0 | 0 | 31.5 | 40 | 12 | 25.75 | 17.5 | 0 | 31.5 | 31.5 | 40 | 12 | 24.75 | 19.5 | 0 | 0 | 28 | 12 | 24.75 | 20 | 0 | 40 | 12.5 | 24.75 | 20.25 | 0
| NR |  |  | available capacity | [6 empty] | 31 | 28 | 24 | 15 | 31 | 28 | 12 | 24 | 15 |  |  | 31 | 40 | 12 | 24 | 15 |  | 31 | 31 | 40 | 12 | 24 | 15 |  |  | 28 | 12 | 24 | 15 |  | 40 | 12 | 24 | 15
| NR |  |  | remaining/exceeded capacity | [6 empty] | 0 | 0 | -3.25 | -2 | 0 | 0 | -0.5 | -4 | -4 |  |  | -0.5 | 0 | 0 | -1.75 | -2.5 |  | -0.5 | -0.5 | 0 | 0 | -0.75 | -4.5 |  | 0 | 0 | 0 | -0.75 | -5 | 0 | 0 | -0.5 | -0.75 | -5.25
| LTE |  |  | allocated above
| LTE |  |  | Legacy
| LTE |  |  | TEI and other not planned issues
| LTE |  |  | Reserve
| LTE |  |  | total used capcaity
| LTE |  |  | available capacity
| LTE |  |  | remaining/exceeded capacity
| UTRA |  |  | allocated above
| UTRAN |  |  | Legacy
| UTRAN |  |  | TEI and other not planned issues
| UTRAN |  |  | Reserve
| UTRAN |  |  | total used capacity
| UTRAN |  |  | available capacity
| UTRAN |  |  | remaining/exceeded capacity
| GERAN |  |  | allocated above
| GERAN |  |  | Legacy
| GERAN |  |  | TEI and other not planned issues
| GERAN |  |  | Reserve
| GERAN |  |  | total used capacity
| GERAN |  |  | available capacity
| GERAN |  |  | remaining/exceeded capacity
R3 |  |  |  | RAN3 overall Status | [12 empty] | -0.5 | [6 empty] | 0 | [6 empty] | 0 | [5 empty] | 0 |  |  |  |  | -0.5

## Sheet1
R5 | LTE | LTE_PC2_B31_B72-UEConTest | WI | UE Conformance Test Aspects – Addition of Power Class 2 UE for LTE bands 31 and 72 | RP-192506 | Airbus | 2019-03-20
R5 | LTE | NB_IOTenh2-UEConTest | WI | UE Conformance Test Aspects - Further NB-IoT enhancements | RP-192850 | CATT | Dec.20
R5 | LTE | LTE_eMTC4-UEConTest | WI | UE Conformance Test Aspects - Even further enhanced MTC for LTE | RP-192894 | Ericsson | Dec.20
R1 | LTE | FS_LTE_NBIOT_eMTC_NTN | SI | Study on NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) | RP-193235 | MediaTek | 2019-06-21
R1 | NR | FS_NR_pos_enh | SI | Study on NR positioning enhancements | RP-193237 | CATT | Sep.20
R1 | NR | FS_NR_redcap | SI | Study on support of reduced capability NR devices | RP-193238 | Ericsson | 2019-06-20
R1 | NR | FS_NR_cov_enh | SI | Study on on NR coverage enhancements | RP-193240 | China Telecom | 2019-06-20
R1 | NR | FS_NR_52_to_71GHz | SI | Study on supporting NR from 52.6 GHz to 71 GHz | RP-193259 | Intel | 2019-06-20
R2 | NR | FS_NR_SL_relay | SI | Study on NR Sidelink relay | RP-193253 | OPPO | Sep.20
R2 | NR | FS_NR_slice | SI | Study on enhancement of RAN slicing for NR | RP-193254 | CMCC | Dec.20
R1 | NR | NR_feMIMO-Core | WI | Core part: Further enhancements on MIMO for NR | RP-193133 | Samsung | 2019-06-21
R1 | NR | NR_feMIMO-Perf | WI | Perf. part: Further enhancements on MIMO for NR | RP-193133 | Samsung | Dec.21
R1 | NR | NR_ext_to_71GHz-Core | WI | Core part: Extending current NR operation to 71GHz | RP-193229 | Qualcomm | 2019-06-21
R4 | NR | NR_ext_to_71GHz-Perf | WI | Perf. part: Extending current NR operation to 71GHz | RP-193229 | Qualcomm | Sep.21
R1 | NR | NR_SL_enh-Core | WI | Core part: NR Sidelink enhancement | RP-193257 | LG Electronics | 2019-06-21
R4 | NR | NR_SL_enh-Perf | WI | Perf. part: NR Sidelink enhancement | RP-193257 | LG Electronics | Dec.21
R1 | NR | NR_DSS-Core | WI | Core part: NR Dynamic spectrum sharing (DSS) | RP-193260 | Ericsson | 2019-03-21
R1 | LTE | NB_IOTenh4_LTE_eMTC6-Core | WI | Core part: Additional enhancements for NB-IoT and LTE-MTC | RP-193264 | Huawei | 2019-06-21
R4 | LTE | NB_IOTenh4_LTE_eMTC6-Perf | WI | Perf. part: Additional enhancements for NB-IoT and LTE-MTC | RP-193264 | Huawei | Dec.21
R2 | NR | NR_IIOT_URLLC_enh-Core | WI | Core part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-193233 | Nokia | 2019-06-21
R2 | NR | NR_NTN_solutions-Core | WI | Core part: Solutions for NR to support non-terrestrial networks (NTN) | RP-193234 | Thales | 2019-06-21
R4 | NR | NR_NTN_solutions-Perf | WI | Perf. part: Solutions for NR to support non-terrestrial networks (NTN) | RP-193234 | Thales | Dec.21
R2 | NR | NR_UE_pow_sav_enh-Core | WI | Core part: UE power saving enhancements for NR | RP-193239 | MediaTek | 2019-06-21
R4 | NR | NR_UE_pow_sav_enh-Perf | WI | Perf. part: UE power saving enhancements for NR | RP-193239 | MediaTek | Dec.21
R2 | NR | NR_MBS-Core | WI | Core part: NR multicast and broadcast services | RP-193248 | Huawei | 2019-06-21
R2 | LTE, NR | LTE_NR_DC_enh2-Core | WI | Core part: Further Multi-RAT Dual-Connectivity enhancements | RP-193249 | Huawei | 2019-06-21
R4 | LTE, NR | LTE_NR_DC_enh2-Perf | WI | Perf. part: Further Multi-RAT Dual-Connectivity enhancements | RP-193249 | Huawei | Dec.21
R2 | NR | NR_IAB_enh-Core | WI | Core part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-193251 | Qualcomm | 2019-06-21
R4 | NR | NR_IAB_enh-Perf | WI | Perf. part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-193251 | Qualcomm | Dec.21
R2 | NR | NR_SmallData_INACTIVE-Core | WI | Core part: NR small data transmissions in INACTIVE state | RP-193252 | ZTE | 2019-06-21
R4 | NR | NR_SmallData_INACTIVE-Perf | WI | Perf. part: NR small data transmissions in INACTIVE state | RP-193252 | ZTE | Dec.21
R3 | LTE, NR | LTE_NR_arch_evo_enh-Core | WI | Core part: Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN | RP-193181 | China Unicom | Dec.20
R3 | LTE, NR | NR_ENDC_SON_MDT_enh-Core | WI | Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | RP-193255 | CMCC | 2019-06-21
R4 | UTRA, LTE, NR | OTA_BS_testing-Perf | WI | Perf. part: Over the air (OTA) base station (BS) testing TR | RP-193225 | Huawei | 2019-06-20
R4 | LTE, NR | ENDC_UE_PC2_FDD_TDD-Core | WI | High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) | RP-193244 | China Unicom | 2019-03-20
R4 | NR | NR_n53-Core | WI | Core part: Introduction of band n53 | RP-192409 | Globalstar | 2019-06-20
R4 | NR | NR_n53-Perf | WI | Perf. part: Introduction of band n53 | RP-192409 | Globalstar | 2019-06-20
R4 | LTE, NR | DC_R16_xBLTE_2BNR_yDL3UL-Core | WI | Core part: Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band | RP-192784 | NTT DOCOMO | 2019-03-20
R4 | LTE, NR | DC_R16_xBLTE_2BNR_yDL3UL-Perf | WI | Perf. part: Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band | RP-192784 | NTT DOCOMO | 2019-03-20
R4 | NR | NR_n3_BW-Core | WI | Core part: Addition of wider channel bandwidth in NR band n3 | RP-193056 | Ericsson | 2019-03-20
R4 | NR | NR_n3_BW-Perf | WI | Perf. part: Addition of wider channel bandwidth in NR band n3 | RP-193056 | Ericsson | 2019-03-20
R4 | NR | NR_n65_BW-Core | WI | Core part: Addition of wider channel bandwidth in NR band n65 | RP-193057 | Ericsson | 2019-03-20
R4 | NR | NR_n65_BW-Perf | WI | Perf. part: Addition of wider channel bandwidth in NR band n65 | RP-193057 | Ericsson | 2019-03-20
R4 | LTE, NR | NR_n48_LTE_48_coex-Core | WI | Core part: LTE/NR spectrum sharing in band 48/n48 frequency range | RP-193213 | Apple | 2019-03-20

## Sheet2
R5 | LTE | LTE_PC2_B31_B72-UEConTest | WI | UE Conformance Test Aspects – Addition of Power Class 2 UE for LTE bands 31 and 72 | RP-192506 | Airbus | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new | - | BB | s | tested: REL-16 WI LTE_PC2_B31_B72-Core | 13.1 | 860030 | T
R5 | LTE | NB_IOTenh2-UEConTest | WI | UE Conformance Test Aspects - Further NB-IoT enhancements | RP-192850 | CATT | Dec.20 | REL-15 | - | Dec.19 | 0 | new | - | BB |  | tested: REL-15 WI NB_IOTenh2-Core | 13.1 | 860031 | T
R5 | LTE | LTE_eMTC4-UEConTest | WI | UE Conformance Test Aspects - Even further enhanced MTC for LTE | RP-192894 | Ericsson | Dec.20 | REL-15 | - | Dec.19 | 0 | new | - | BB |  | tested: REL-15 WI LTE_eMTC4-Core | 13.1 | 860032 | T
R1 | LTE | FS_LTE_NBIOT_eMTC_NTN | SI | Study on NB-IoT/eMTC support for Non-Terrestrial Networks (NTN) | RP-193235 | MediaTek | 2019-06-21 | REL-17 | R2 | Dec.19 | 0 | new | - | SI |  | connecting LTE NB-IoT and LTE eMTC to NTN of NR; TR 36.7xx | 09.01.02 | 860033 | -
R1 | NR | FS_NR_pos_enh | SI | Study on NR positioning enhancements | RP-193237 | CATT | Sep.20 | REL-17 | R2 | Dec.19 | 0 | new | - | SI |  | compare REL-16 NR_pos WI; TR 38.8xx | 09.01.01 | 860034 | -
R1 | NR | FS_NR_redcap | SI | Study on support of reduced capability NR devices | RP-193238 | Ericsson | 2019-06-20 | REL-17 | R2 | Dec.19 | 0 | new | - | SI |  | TR 38.xxx | 09.01.01 | 860035 | -
R1 | NR | FS_NR_cov_enh | SI | Study on on NR coverage enhancements | RP-193240 | China Telecom | 2019-06-20 | REL-17 | - | Dec.19 | 0 | new | - | SI |  | TR 38.8xx | 09.01.01 | 860036 | -
R1 | NR | FS_NR_52_to_71GHz | SI | Study on supporting NR from 52.6 GHz to 71 GHz | RP-193259 | Intel | 2019-06-20 | REL-17 | R4 | Dec.19 | 0 | new | - | SI |  | TR 38.8xx | 09.01.01 | 860037 | -
R2 | NR | FS_NR_SL_relay | SI | Study on NR Sidelink relay | RP-193253 | OPPO | Sep.20 | REL-17 | - | Dec.19 | 0 | new | - | SI |  | TR 38.8xx | 09.01.02 | 860038 | -
R2 | NR | FS_NR_slice | SI | Study on enhancement of RAN slicing for NR | RP-193254 | CMCC | Dec.20 | REL-17 | R3 | Dec.19 | 0 | new | - | SI |  | TR 38.8xx | 09.01.02 | 860039 | -
R1 | NR | NR_feMIMO-Core | WI | Core part: Further enhancements on MIMO for NR | RP-193133 | Samsung | 2019-06-21 | REL-17 | R2, R4 | Dec.19 | 0 | new | - | BB |  | compare REL-16 WI NR_eMIMO | 09.01.01 | 860140 | C
R1 | NR | NR_feMIMO-Perf | WI | Perf. part: Further enhancements on MIMO for NR | RP-193133 | Samsung | Dec.21 | REL-17 | - | Dec.19 | 0 | new | - | BB |  |  | 09.01.01 | 860240 | P
R1 | NR | NR_ext_to_71GHz-Core | WI | Core part: Extending current NR operation to 71GHz | RP-193229 | Qualcomm | 2019-06-21 | REL-17 | - | Dec.19 | 0 | new |  | BB |  |  | 09.01.01 | 860141 | C
R4 | NR | NR_ext_to_71GHz-Perf | WI | Perf. part: Extending current NR operation to 71GHz | RP-193229 | Qualcomm | Sep.21 | REL-17 | - | Dec.19 | 0 | new |  | BB |  |  | 09.01.01 | 860241 | P
R1 | NR | NR_SL_enh-Core | WI | Core part: NR Sidelink enhancement | RP-193257 | LG Electronics | 2019-06-21 | REL-17 | R2, R4 | Dec.19 | 0 | new | - | BB |  | compare REL-16 WI 5G_V2X_NRSL | 09.01.01 | 860142 | C
R4 | NR | NR_SL_enh-Perf | WI | Perf. part: NR Sidelink enhancement | RP-193257 | LG Electronics | Dec.21 | REL-17 | - | Dec.19 | 0 | new | - | BB |  |  | 09.01.01 | 860242 | P
R1 | NR | NR_DSS-Core | WI | Core part: NR Dynamic spectrum sharing (DSS) | RP-193260 | Ericsson | 2019-03-21 | REL-17 | R2 | Dec.19 | 0 | new | - | BB |  | no Perf. part | 09.01.01 | 860143 | C
R1 | LTE | NB_IOTenh4_LTE_eMTC6-Core | WI | Core part: Additional enhancements for NB-IoT and LTE-MTC | RP-193264 | Huawei | 2019-06-21 | REL-17 | R2, R3, R4 | Dec.19 | 0 | new | - | BB |  |  | 10.1.1 | 860144 | C
R4 | LTE | NB_IOTenh4_LTE_eMTC6-Perf | WI | Perf. part: Additional enhancements for NB-IoT and LTE-MTC | RP-193264 | Huawei | Dec.21 | REL-17 | - | Dec.19 | 0 | new | - | BB |  |  | 10.1.1 | 860244 | P
R2 | NR | NR_IIOT_URLLC_enh-Core | WI | Core part: Enhanced Industrial Internet of Things (IoT) and ultra-reliable and low latency communication (URLLC) support for NR | RP-193233 | Nokia | 2019-06-21 | REL-17 | R1 | Dec.19 | 0 | new | - | BB |  | no Perf. part; compare REL-16 WI NR_IIOT and NR_L1enh_URLLC | 09.01.02 | 860145 | C
R2 | NR | NR_NTN_solutions-Core | WI | Core part: Solutions for NR to support non-terrestrial networks (NTN) | RP-193234 | Thales | 2019-06-21 | REL-17 | R1, R3, R4 | Dec.19 | 0 | new | - | BB |  | follow-up WI of REL-16 SI FS_NR_NTN_solutions | 09.01.02 | 860146 | C
R4 | NR | NR_NTN_solutions-Perf | WI | Perf. part: Solutions for NR to support non-terrestrial networks (NTN) | RP-193234 | Thales | Dec.21 | REL-17 | - | Dec.19 | 0 | new | - | BB |  |  | 09.01.02 | 860246 | P
R2 | NR | NR_UE_pow_sav_enh-Core | WI | Core part: UE power saving enhancements for NR | RP-193239 | MediaTek | 2019-06-21 | REL-17 | R1, R4 | Dec.19 | 0 | new | - | BB |  | compare REL-16 WI NR_UE_pow_sav | 09.01.02 | 860147 | C
R4 | NR | NR_UE_pow_sav_enh-Perf | WI | Perf. part: UE power saving enhancements for NR | RP-193239 | MediaTek | Dec.21 | REL-17 | - | Dec.19 | 0 | new | - | BB |  |  | 09.01.02 | 860247 | P
R2 | NR | NR_MBS-Core | WI | Core part: NR multicast and broadcast services | RP-193248 | Huawei | 2019-06-21 | REL-17 | R1, R3 | Dec.19 | 0 | new | - | BB |  | no Perf. part | 09.01.02 | 860148 | C
R2 | LTE, NR | LTE_NR_DC_enh2-Core | WI | Core part: Further Multi-RAT Dual-Connectivity enhancements | RP-193249 | Huawei | 2019-06-21 | REL-17 | R1, R3, R4 | Dec.19 | 0 | new | - | BB |  | compare REL-16 WI LTE_NR_DC_CA_enh | 09.01.02 | 860149 | C
R4 | LTE, NR | LTE_NR_DC_enh2-Perf | WI | Perf. part: Further Multi-RAT Dual-Connectivity enhancements | RP-193249 | Huawei | Dec.21 | REL-17 | - | Dec.19 | 0 | new | - | BB |  |  | 09.01.02 | 860249 | P
R2 | NR | NR_IAB_enh-Core | WI | Core part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-193251 | Qualcomm | 2019-06-21 | REL-17 | R1, R3, R4 | Dec.19 | 0 | new | - | BB |  | compare REL-16 WI NR_IAB | 09.01.02 | 860150 | C
R4 | NR | NR_IAB_enh-Perf | WI | Perf. part: Enhancements to Integrated Access and Backhaul (IAB) for NR | RP-193251 | Qualcomm | Dec.21 | REL-17 | - | Dec.19 | 0 | new | - | BB |  |  | 09.01.02 | 860250 | P
R2 | NR | NR_SmallData_INACTIVE-Core | WI | Core part: NR small data transmissions in INACTIVE state | RP-193252 | ZTE | 2019-06-21 | REL-17 | R1, R3 | Dec.19 | 0 | new | - | BB |  |  | 09.01.02 | 860151 | C
R4 | NR | NR_SmallData_INACTIVE-Perf | WI | Perf. part: NR small data transmissions in INACTIVE state | RP-193252 | ZTE | Dec.21 | REL-17 | - | Dec.19 | 0 | new | - | BB |  |  | 09.01.02 | 860251 | P
R3 | LTE, NR | LTE_NR_arch_evo_enh-Core | WI | Core part: Enhanced eNB(s) architecture evolution for E-UTRAN and NG-RAN | RP-193181 | China Unicom | Dec.20 | REL-17 |  | Dec.19 | 0 | new | - | BB |  | no Perf. part; compare REL-16 WI LTE_NR_arch_evo | 09.01.03 | 860152 | C
R3 | LTE, NR | NR_ENDC_SON_MDT_enh-Core | WI | Core part: Enhancement of data collection for SON (Self-Organising Networks)/MDT (Minimization of Drive Tests) in NR and EN-DC | RP-193255 | CMCC | 2019-06-21 | REL-17 | R2, R4 | Dec.19 | 0 | new | - | BB |  | no Perf. part; compare REL-16 SI FS_LTE_NR_data_collect and REL-16 WI NR_SON_MDT-Core; includes EN-DC and MR-DC changes and therefore LTE changes | 09.01.03 | 860153 | C
R4 | UTRA, LTE, NR | OTA_BS_testing-Perf | WI | Perf. part: Over the air (OTA) base station (BS) testing TR | RP-193225 | Huawei | 2019-06-20 | REL-16 | - | Dec.19 | 0 | new |  | BB |  | no Core part; note: WI will introduce TR 37.9xx for REL-15 and REL-16 | 09.01.04 | 860254 | P
R4 | LTE, NR | ENDC_UE_PC2_FDD_TDD-Core | WI | High power UE (power class 2) for EN-DC (1 LTE FDD band + 1 NR TDD band) | RP-193244 | China Unicom | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new |  | BB | s | no Perf. part | 09.01.05 | 860155 | C
R4 | NR | NR_n53-Core | WI | Core part: Introduction of band n53 | RP-192409 | Globalstar | 2019-06-20 | REL-17 | - | Dec.19 | 0 | new |  | BB | s |  | 09.01.05 | 860156 | C
R4 | NR | NR_n53-Perf | WI | Perf. part: Introduction of band n53 | RP-192409 | Globalstar | 2019-06-20 | REL-17 | - | Dec.19 | 0 | new |  | BB | s |  | 09.01.05 | 860256 | P
R4 | LTE, NR | DC_R16_xBLTE_2BNR_yDL3UL-Core | WI | Core part: Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band | RP-192784 | NTT DOCOMO | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new |  | BB | s (xLTE/2NR_FR1_FR2) | basket WI; suggested TR 37.716-41-22 | 09.01.05 | 860157 | C
R4 | LTE, NR | DC_R16_xBLTE_2BNR_yDL3UL-Perf | WI | Perf. part: Dual Connectivity (EN-DC) of LTE inter-band CA xDL/1UL bands (x=2,3,4) and NR FR1 1DL/1UL band and NR FR2 1DL/1UL band | RP-192784 | NTT DOCOMO | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new |  | BB | s (xLTE/2NR_FR1_FR2) |  | 09.01.05 | 860257 | P
R4 | NR | NR_n3_BW-Core | WI | Core part: Addition of wider channel bandwidth in NR band n3 | RP-193056 | Ericsson | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new |  | BB | s |  | 09.01.05 | 860158 | C
R4 | NR | NR_n3_BW-Perf | WI | Perf. part: Addition of wider channel bandwidth in NR band n3 | RP-193056 | Ericsson | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new |  | BB | s |  | 09.01.05 | 860258 | P
R4 | NR | NR_n65_BW-Core | WI | Core part: Addition of wider channel bandwidth in NR band n65 | RP-193057 | Ericsson | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new |  | BB | s |  | 09.01.05 | 860159 | C
R4 | NR | NR_n65_BW-Perf | WI | Perf. part: Addition of wider channel bandwidth in NR band n65 | RP-193057 | Ericsson | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new |  | BB | s |  | 09.01.05 | 860259 | P
R4 | LTE, NR | NR_n48_LTE_48_coex-Core | WI | Core part: LTE/NR spectrum sharing in band 48/n48 frequency range | RP-193213 | Apple | 2019-03-20 | REL-16 | - | Dec.19 | 0 | new |  | BB | s | no Perf. part | 09.01.05 | 860160 | C