3GPP TSG-RAN Meeting #93-e									RP-212624

Electronic Meeting, September 2021

## Status Report to TSG

Agenda item:			9.4.1.3

| WI / SI Name | WID on introduction of lower 6GHz NR unlicensed operation for Europe |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| included in this status report | Study Item: No | Core part: Yes | Performance part: Yes |  | Testing part: No |
| Acronym | NR_6GHz_unlic_EU |  |  |  |  |
| Unique ID | 890051 |  |  |  |  |
| TSG Tdoc of latest approved WI/SI description (if any) | RP-210762 |  |  |  |  |
| Target Completion Date (indicate if changed) | Study Item: mm/yyyy | Core part: 03/2022 | Performance part: 03/2022 | Testing part: mm/yyyy |  |
| Overall Completion level | Study Item: xx % | Core part: 30% | Performance Part: 15% | Testing part: xx% |  |

Note: Overall completion level percentage numbers should use one of the colors below:

- xx%: Normal progress, no RAN plenary action needed

- xx%: Progress behind schedule, may need RAN plenary intervention. If so, SR should clearly define requested action

- xx%: Progress critically behind, RAN plenary shall intervene. SR should define requested action

Source:

| Leading WG |  | RAN WG4 |
| --- | --- | --- |
| Rapporteur | Name | Johannes Hejselbaek |
|  | Company | Nokia |
|  | Email | johannes.hejselbaek@nokia.com |

## 1	Work plan related evaluation

| Do you want to modify the time budget for this WI/SI compared to what was endorsed at the last RAN meeting? | YES |
| --- | --- |

If you answered No:	Then please remove the Excel file from the zip file of this status report.

If you answered Yes:	Then please fill out the attached Excel template to request a modification of the time 		budgets for your WI /SI. The Excel table has to be filled out for all affected RAN WGs and 		up to the target date of the WI/SI. The basis are the endorsed time budgets of the last 		RAN meeting. Please highlight all changes of the values.
		One time unit (TU) corresponds to ~ 2 hours in the meeting.
		If this status report covers a WI with Core and Performance part, then please have one 		line for each in the attached Excel table.
		Note: If no Excel table is attached, then this means no time budget change.

Additional explanations/motivations for the time budget changes in the attached Excel table:

Since the Core have not been finalized as planned at RAN4#99 nor RAN4#100, TUs is needed also at RAN4#101 and RAN4#102. The WI have been targeted completion 09/2021(RAN#93) which clearly cannot be meet. Hence, an extension of the WI were agreed at RAN#93 until 03/2022(RAN#95).

The main open issue delaying progress on all other aspects is whether a new band shall be defined or already defined n96 (5925 MHz to 7125 MHz) can be reused for unlicensed operation in the frequency range 5945 MHz to 6425 MHz in Europe.

The discussed options, with no conclusion during the last RAN4 meetings, are:

- Option 1: Re-using already defined band n96, for the frequency range 5945 MHz to 6425 MHz

  - FFS if additional notes and/or clarifications are needed. Regional specific requirements to be included in relevant specifications.

- Option 2: Defining a new band n[xx], for the frequency range 5945 MHz to 6425 MHz

  - On top of specific requirements provided by ECC, the new band shall reuse requirements already defined for n96, where possible.

Both options will for the UE require specific NS(s) to be defined to contain the regulatory requirements. The BS shall follow regional regulations per general statement when operating in shared spectrum. The regulations for unlicensed operation in the frequency range 5945 MHz to 6425 MHz in Europe is defined by ECC Decision (20)01 which initiated this WI. It has during the RAN4 meetings been questioned if these regulations are sufficient to introduce unlicensed operation in the lower 6 GHz range (5945 MHz to 6425 MHz) and if further considerations should be given to the upper 6 GHz range (6425 MHz to 7125 MHz). Note that no regulations have yet been defined in Europe for the upper 6 GHz range.

The above elaboration leaves the question if the WI shall wait for regulations in Europe for the upper 6 GHz range and which of the two options for introducing unlicensed operation in the frequency range 5945 MHz to 6425 MHz in Europe shall be followed.

REQUESTED ACTION: RAN plenary shall decide if unlicensed operation in the frequency range 5945 MHz to 6425 MHz in Europe shall be based on available ECC Decision (20)01 or RAN4 shall consider other aspects as well. Further, RAN plenary is requested to decide which of the two listed options RAN4 shall follow to introduce unlicensed operation in the frequency range 5945 MHz to 6425 MHz in Europe.

## 2	Detailed progress in RAN WGs since last TSG meeting (for all involved WGs)

NOTE: Agreements and Open issues impacted cross-TSG aspects shall be explicitly highlighted

At the November 2020 meeting the ECC with ECC Decision (20)01 “on the harmonised use of the frequency bands 5945 to 6425 MHz for the implementation of Wireless Access Systems including Radio Local Area Networks (WAS/RLANs)” approved unlicensed operation in the range 5945 to 6425 MHz. As a result, the work regarding defining the range 5945 to 6425 MHz for NR operation was commence within 3GPP.

Below is the workplan as agreed in R4-2101929:

- 3GPP RAN4#98-e (Jan. 2021)

  - Agree or endorse on the work plan, TR 38.849 skeleton and revised WID if any updates;

  - Agree if the frequency range for unlicensed operation in Europe are best introduced to the specification by relevant updates (if any) of band n96 or whether a new band is needed.

  - Agree WF or TP to TR 38.849 detailing the remaining work needed to complete the objectives of the WID

  - Agree work split, if needed, for the WI

- 3GPP RAN4#98bis-e (Apr. 2021)

  - Agree or endorse TR 38.849 and revised WID if any updates;

  - Discussions on core requirements for UE and BS;

- 3GPP RAN4#99-e (May. 2021)

  - Agree or endorse TR 38.849 and revised WID if any updates;

  - Conclude discussions related to core requirements for UE and BS

  - Endorse BIG CRs for impacted core TSs;

  - Discussions on conformance requirements for BS testing

- 3GPP RAN#92-e (Jun. 2021)

  - Present TR 38.849 for information;

- 3GPP RAN4#100-e (Aug. 2021)

  - Agree or endorse TR 38.849 and revised WID if any updates;

  - Conclude discussions related to conformance requirements for BS testing

  - Endorse BIG CRs for impacted performance TSs;

- 3GPP RAN#93-e (Sep. 2021)

  - Approve TR 38.849;

  - Approve CRs to introduce operation in the frequency range for unlicensed operation in Europe to TSs;

## 2.1	RAN1

#### 2.1.1	Agreements

#### 2.1.2	Remaining Open issues

## 2.2	RAN2

#### 2.2.1	Agreements

#### 2.2.2	Remaining Open issues

## 2.3	RAN3

#### 2.3.1	Agreements

#### 2.3.2	Remaining Open issues

## 2.4	RAN4

#### 2.4.1	Agreements

RAN4#98-e

- TR 38.849 Skeleton was agreed in R4-2101927

- WF R4-2103229 was agreed including:

- LPI devices to be supported by 3GPP Specifications

- NR-ARFCN and GSCN already defined for n96 should be re-used in the frequency range applicable to 6GHz NR unlicensed operation in Europe. This is independent if n96 is reused or a new band is defined

- 0 dBi antenna gain is assumed for the purpose of deriving 3GPP specifications on MOP, PSD, and ASE for LPI deployments and, if introduced, also VLP deployments.

- A-MPR evaluation shall be performed with the following assumptions:

  - A-MPR for PC5 is assessed using band n96 PC5 definitions for VLP and LPI device A-MPR.

  - No filter rejection is assumed <5935 MHz and >6425MHz for spurious emissions

  - Same PA model and calibration setpoint from Band n96 is to be used.

  - A-MPR for other power classes are to be added at a later stage.

  - A-MPR studies for PC5 are to be compared and, if possible, decided at next RAN4 meeting.

- NS shall be defined corresponding to LPI deployments and if introduced also VLP deployments.

- The currently, by ECC, defined OOB limit at -45 dBm/MHz for VLP shall be used. If/when a new limit is introduced by ECC the NS(s) will be revised accordingly.

RAN4#98bis-e

- Draft TR 38.849 was agreed in R4-2107196

- WF R4-2105383 was agreed including:

- Two options for introducing unlicensed operation in the frequency range 5945 MHz to 6425 MHz in Europe.

- VLP deployment is subject to further checking of regulations.

- The note for n96 restricting it for use in US only shall be modified.

- Reusing existing PC5 with additional NS limitations to TX power is sufficient to limit MOP for VLP.

- Proposals for A-MPR for PC5 LPI

- There is no further need for clarifications for BS maximum output power, as compared to those given for n96 in 38.104.

- There is no further need for additional REFSENS, as compared to those given for n96 in 38.104.

- TP to TR 38.849 on NR-ARFCN and GSCN in R4-2105384

RAN4#99-e

- Draft TR 38.849 was agreed in R4-2110691

- WF R4-2108020 was agreed including:

- Two options for introducing unlicensed operation in the frequency range 5945 MHz to 6425 MHz in Europe.

- That selecting any of the options above shall not in any way interfere with regulatory activities and timelines for the 6 GHz range.

- VLP deployment can be included in specification given the available regulations.

  - Further discussion is needed in future meeting about the possible regulation issues.

- Values for A-MPR for PC5 LPI

- TP to TR 38.849 on MPR values for LPI deployments in R4-2107789

RAN4#100-e

- Draft TR 38.849 was agreed in R4-2113692

- GTW Agreements captured by RAN4 chair:

  - The same hardware of UE as for n96 may be reused on the frequency range 5945MHz to 6425MHz no matter whether to define a new band or define new NS for the existing n96.

  - For outdoor UEs connecting to the indoor LPI base stations, no solution is needed to meet the regulatory requirements in Rel-17.

- TP to TR 38.849 on A-MPR values for PC5 VLP deployments in R4-2114883

#### 2.4.2	Remaining Open issues

- How to introduce the frequency range 5945 to 6425 MHz for unlicensed operation in Europe to the specification by RAN4. As agreed in WF R4-2103229 unlicensed operation in the range 5945-6425 MHz can be introduced by:

  - Option 1: Re-using already defined band n96

    - FFS if additional notes and/or clarifications are needed. Regional specific requirements to be included in relevant specifications.

  - Option 2: Defining a new band n[xx]

    - On top of specific requirements provided by ECC, the new band shall reuse requirements already defined for n96, where possible.

- If if ΔfOBUE/ ΔfOOBB  should follow n46 or n96

- How to define the NSs needed to cover existing regional regulations

## 2.5	RAN5

#### 2.5.1	Agreements

#### 2.5.2	Remaining Open issues

#### 2.5.3	Remaining Open issues with cross-WG dependencies

## 2.6	RAN6

#### 2.6.1	Agreements

#### 2.6.2	Remaining Open issues

## 3.	Detailed progress in SA/CT WGs since last TSG meeting (for all involved WGs)

NOTE: This section only needs to be filled in for WI/SIs where there is a corresponding relevant WI/SI in SA/CT.

## 3.1	SAx/CTs

#### 3.1.1	Agreements with cross-TSG impacts

#### 3.1.2	Remaining Open issues with cross-TSG impacts

NOTE: This section should also flag any critical dependencies that need TSG attention.

## 4.	References

RAN4#100:

R4-2115008	Email discussion summary for [100-e][108] NR_6GHz_unlic_EU, Nokia

R4-2114883	TP to TR 38.849 on A-MPR values for PC5 VLP deployments, Qualcomm

R4-2113692	draft TR 38.849 v0.4.0, Nokia, Nokia Shanghai Bell

R4-2113693	On system parameters for the lower 6GHz NR unlicensed operation, Nokia, Nokia Shanghai Bell

R4-2112342	Band plan for lower 6GHz NR unlicensed operation in EU/CEPT, Apple, Facebook, Hewlett Packard Enterprise, Skyworks Solutions Inc., Microsoft

R4-2113934	Comparison of reusing n96 and defining a new band, ZTE Corporation

R4-2114219	NR-U 6 GHz band for Europe from a UE perspective, Qualcomm Incorporated

R4-2114231	6GHz unliscenced band numbering, Huawei

R4-2114476	Band plan for unlicensed operation in 6GHz in Europe, Ericsson

R4-2114220	A-MPR for NR-U VLP in 6 GHz for Europe, Qualcomm Incorporated

RAN#92:

RP-211320	SR for introduction of lower 6GHz NR unlicensed operation for Europe, RAN4

RP-211321	Draft TR 38.849 - Introduction of lower 6GHz NR unlicensed operation for Europe. Nokia

RAN4#99:

RP-2107921	Email discussion summary for [99-e][111] NR_6GHz_unlic_EU, Nokia

R4-2108020	WF on introduction of lower 6GHz NR unlicensed operation for Europe, Nokia

R4-2107789	TP to TR 38.849 on MPR values for LPI deployments, Nokia

R4-2109429	Band plan for lower 6GHz NR unlicensed operation in EU/CEPT, Apple, Facebook, Hewlett Packard Enterprise, Skyworks Solutions Inc.

R4-2110691	draft TR 38.849 v0.3.0, Nokia, Nokia Shanghai Bell

R4-2110692	On system parameters for the lower 6GHz NR unlicensed operation, Nokia, Nokia Shanghai Bell

R4-2111165	On NR unlicensed operation for lower 6GHz in Europe, Ericsson

R4-2109430	A-MPR for 6GHz NR unlicensed band in EU/CEPT, Apple

R4-2110693	On UE RF aspects for the lower 6GHz NR unlicensed operation, Nokia, Nokia Shanghai Bell

R4-2110983	NR-U VLP for EU 6 GHz, Qualcomm Incorporated

R4-2110617	Discussion on BS RF requirements for Europe unlicensed 6GHz, ZTE Corporation

R4-2110618	draft CR for introduction of Europe unlicensed 6GHz, ZTE Corporation

R4-2110694	On BS RF aspects for the lower 6GHz NR unlicensed operation, Nokia, Nokia Shanghai Bell

R4-2109431	On LPI and VLP modes for mixed indoor/outdoor scenarios, Apple

R4-2111408	Discussion on EU band allocation, Huawei

RAN4#98bis:

RP-2105461	Email discussion summary for [98-bis-e][124] NR_6GHz_unlic_EU, Nokia

R4-2105383	WF on introduction of lower 6GHz NR unlicensed operation for Europe, Nokia

R4-2105384	TP to TR 38.849 on NR-ARFCN and GSCN points, Nokia

R4-2104882	Band plan for lower 6GHz NR unlicensed operation for Europe, Apple

R4-2106273	RF front-end supporting NRU in 6GHz EU spectrum with band n96, Skyworks Solutions Inc.

R4-2107196	draft TR 38.849 v0.2.0, Nokia, Nokia Shanghai Bell

R4-2107197	On system parameters for the lower 6GHz NR unlicensed operation, Nokia, Nokia Shanghai Bell

R4-2106274	A-MPR due to in-band PSD limit for 6GHz EU unlicensed spectrum, Skyworks Solutions Inc.

R4-2107198	On UE RF aspects for the lower 6GHz NR unlicensed operation, Nokia, Nokia Shanghai Bell

R4-2107351	A-MPR for European NR-U 6 GHz band, Qualcomm Incorporated

R4-2106604	Discussion on BS RF requirements for Europe unlicensed 6GHz, ZTE Corporation

R4-2106659	draft CR for introduction of Europe unlicensed 6GHz, ZTE Corporation

R4-2107199	On BS RF aspects for the lower 6GHz NR unlicensed operation, Nokia, Nokia Shanghai Bell

R4-2104883	On simultaneous low power and very low power operation, Apple

RAN#91:

RP-210762	WID on introduction of lower 6GHz NR unlicensed operation for Europe, Nokia

RP-210486	SR for Introduction of lower 6GHz NR unlicensed operation for Europe, Nokia

RAN4#98:

RP-2103320 	Email discussion summary for [98e][133] NR_6GHz_unlic_EU, Nokia

R4-2103229 	WF on introduction of lower 6GHz NR unlicensed operation for Europe, Nokia, Qualcomm, Charter Communications Inc

R4-2100514	Band plan for lower 6GHz NR unlicensed operation for Europe, Apple Inc.

R4-2100546	NRU in 6GHz EU spectrum: Band Definition and Related Emission Requirements, Skyworks Solutions Inc.

R4-2101927	Skeleton TR 38.849 v0.0.0, Nokia, Nokia Shanghai Bell

R4-2101928	draft TR 38.849 v0.1.0, Nokia, Nokia Shanghai Bell

R4-2101929	Work plan for Introduction of lower 6GHz NR unlicensed operation for Europe, Nokia, Nokia Shanghai Bell

R4-2101965	Discussion on Europe unlicensed 6GHz for NR-U, ZTE Corporation

R4-2101930	On UE RF aspects for the lower 6GHz NR unlicensed operation, Nokia, Nokia Shanghai Bell

R4-2102416	UE requirements for EU NR-U 6 GHz band, Qualcomm Incorporated

R4-2101931	On BS RF aspects for the lower 6GHz NR unlicensed operation, Nokia, Nokia Shanghai Bell

R4-2101966	Discussion on BS RF requirements for Europe unlicensed 6GHz, ZTE Corporation

RAN#90:

RP-202592 	WID on introduction of lower 6GHz NR unlicensed operation for Europe, Nokia

RP-202591 	SR for Introduction of lower 6GHz NR unlicensed operation for Europe, Nokia

RAN#89:

RP-202116 	New WID on introduction of lower 6GHz NR unlicensed operation for Europe, Nokia